## Sheet1
| UPC | DESCRIPTION | ROUTE | ROAD_SYSTEM | SCOPE_OF_WORK | ADMINISTERED_BY | CITY_COUNTY | RESIDENCY | DISTRICT | MPO | PROGRAM_MANAGER | DASHBOARD_CONTACT | DASHBOARD_CONTACT_EMAIL | DASHBOARD_CONTACT_PHONE | VDOT_PROJECT_MANAGER | VDOT_PROJECT_MANAGER_EMAIL | VDOT_PROJECT_MANAGER_PHONE | NON_VDOT_PROJECT_MANAGER | NON_VDOT_PROJECT_MANAGER_EMAIL | NON_VDOT_PROJECT_MANAGER_PHONE | SMART_SCALE_INDICATOR | SMARTSCALE_COHORT | STATE_OF_GOOD_REPAIR_INDICATOR | FISCAL_YEAR | BUDGET | ESTIMATE | PROJECT_STATUS | ON_TIME_STATUS | ON_TIME_STATUS_REASON | ON_BUDGET_STATUS | ON_BUDGET_STATUS_REASON | LOCAL_AGMT_10_PLND_START_DT | LOCAL_AGMT_10_ACT_START_DT | LOCAL_AGMT_10_PLND_END_DT | LOCAL_AGMT_10_ACT_END_DT | LOCAL_AGREEMENT_10_STATUS | START_DEV_12_PLND_START_DT | START_DEV_12_ACT_START_DT | START_DEV_12_PLND_END_DT | START_DEV_12_ACT_END_DT | START_DEVELOPMENT_12_STATUS | DET_REQ_22_PLND_START_DT | DET_REQ_22_ACT_START_DT | DET_REQ_22_PLND_END_DT | DET_REQ_22_ACT_END_DT | DET_REQ_22_STATUS | ENG_PUB_47_PLND_START_DT | ENG_PUB_47_ACT_START_DT | ENG_PUB_47_PLND_END_DT | ENG_PUB_47_ACT_END_DT | ENGAGE_PUBLIC_47_STATUS | ENG_PUB_49_PLND_START_DT | ENG_PUB_49_ACT_START_DT | ENG_PUB_49_PLND_END_DT | ENG_PUB_49_ACT_END_DT | ENGAGE_PUBLIC_49_STATUS | STRT_PUR_ROW_52_PLND_START_DT | STRT_PUR_ROW_52_ACT_START_DT | STRT_PUR_ROW_52_PLND_END_DT | STRT_PUR_ROW_52_ACT_END_DT | STRT_PUR_ROW_52_STATUS | REL_UTL_67U_PLND_START_DT | REL_UTL_67U_ACT_START_DT | REL_UTL_67U_PLND_END_DT | REL_UTL_67U_ACT_END_DT | RELOCATE_UTILITIES_67U_STATUS | CMP_PUR_ROW_69_PLND_START_DT | CMP_PUR_ROW_69_ACT_START_DT | CMP_PUR_ROW_69_PLND_END_DT | CMP_PUR_ROW_69_ACT_END_DT | CMP_PUR_ROW_69_STATUS | OBTAIN_PMT_70_PLND_START_DT | OBTAIN_PMT_70_ACT_START_DT | OBTAIN_PMT_70_PLND_END_DT | OBTAIN_PMT_70_ACT_END_DT | OBTAIN_PERMITS_70_STATUS | CN_PMT_70R_PLND_START_DT | CN_PMT_70R_ACT_START_DT | CN_PMT_70R_PLND_END_DT | CN_PMT_70R_ACT_END_DT | CN_PMT_70R_STATUS | SOLICIT_BIDS_80_PLND_START_DT | SOLICIT_BIDS_80_ACT_START_DT | SOLICIT_BIDS_80_PLND_END_DT | SOLICIT_BIDS_80_ACT_END_DT | SOLICIT_BIDS_80_STATUS | START_DLVR_84_PLND_START_DT | START_DLVR_84_ACT_START_DT | START_DLVR_84_PLND_END_DT | START_DLVR_84_ACT_END_DT | START_DELIVERY_84_STATUS | DASHBOARD_COMMENT | GENERATED_DATE | REFRESHED_DATE | ACCOMPLISHMENT | COMPLETED_DEV | Prediction | Probability of Red
0 | 98956 | RTE 761 ??? Replace Bridge 05453 & Appr over Opequon Creek | 0761 | Secondary | Bridge Replacement w/ Added Capacity | VDOT | Clarke County | EDINBURG | Staunton | NonMPO:NonMPO | Infrastructure Investment Division | Edwin Z Carter | Edwin.Carter@vdot.virginia.gov | (540) 534-3204 | Keith N Harrop | Keith.Harrop@VDOT.Virginia.gov | (540) 332-9190 |  |  |  | 0 |  | 0 | FY2024 | 4355591 | 4355591 | ACTIVITY DATES SET | R | Determine Requirements milestone finished 960 days late | G | Project is on budget | [5 empty] | 2011-07-01 | 2011-07-01 | 2011-07-18 | 2011-07-18 | G | 2011-08-01 | 2011-08-01 | 2018-03-01 | 2020-10-16 | R | [5 empty] | 2021-06-21 |  | 2021-12-13 |  | G | 2022-07-13 |  | 2022-07-25 |  | G | 2022-08-10 |  | 2023-08-10 |  | G | 2022-08-10 |  | 2023-08-10 |  | G | 2022-04-29 |  | 2023-05-01 |  | G | [5 empty] | 2023-11-17 |  | 2023-12-14 |  | G | 2024-04-01 |  | 2024-04-30 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.065044
1 | 103262 | Tyson East Sidewalk South Side of Route 123 - CMAQ | 0123 | Primary | Facilities for Pedestrians and Bicycles | Locally | Fairfax County | FAIRFAX | Northern Virginia | Northern Virginia:Fairfax County | Infrastructure Investment Division | Amir Salahshoor | A.Salahshoor@VDOT.Virginia.gov | (703) 259-1957 | Rita Hockman | Rita.Hockman@vdot.virginia.gov | (804) 824-7421 | Francesco Lauretti | francesco.lauretti@fairfaxcounty.gov | (703) 877-5600 | 0 |  | 0 | FY2020 | 3120000 | 2646633 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 434 days early | G | Project is on budget | 2011-12-13 | 2011-12-13 | 2013-08-10 | 2013-08-09 | G | 2013-08-15 | 2011-12-13 | 2013-08-15 | 2013-08-14 | G | 2013-07-31 | 2013-07-31 | 2013-11-30 | 2017-08-11 | R | [10 empty] | 2016-02-01 | 2016-02-01 | 2016-04-12 | 2016-04-12 | G | [5 empty] | 2016-04-15 | 2016-04-15 | 2017-08-07 | 2017-08-07 | G | [10 empty] | 2019-04-25 | 2018-10-31 | 2019-09-16 | 2019-01-14 | G | 2019-09-17 | 2019-01-15 | 2020-06-22 | 2019-04-15 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.081497
2 | 106490 | POTOMAC HERITAGE TRAIL AT FEATHERSTONE WILDLIFE REFUGE | 0006 | Miscellaneous | Facilities for Pedestrians and Bicycles | Locally | Prince William County | MANASSAS | Northern Virginia | Northern Virginia:Prince William County | Infrastructure Investment Division | Amir Salahshoor | A.Salahshoor@VDOT.Virginia.gov | (703) 259-1957 | Jeffrey S Daily | Jeff.Daily@VDOT.Virginia.gov | (703) 259-2993 | Matthew M. White (PWC Park & Rec) | mwhite3@pwcgov.org | (703) 792-4234 | 0 |  | 0 | FY2019 | 750000 | 750000 | ACTIVITY DATES SET | R | Solicit Bids milestone is 838 days past the expected completion date | Y | Estimate not current | 2015-10-20 | 2015-10-27 | 2015-10-27 | 2015-10-27 | G | 2015-11-10 | 2015-10-28 | 2015-11-10 | 2015-11-06 | G | 2015-11-10 | 2015-11-10 | 2016-01-08 | 2017-06-08 | R | [35 empty] | 2018-06-15 | 2018-06-15 | 2018-11-06 |  | R | 2018-11-07 |  | 2019-04-30 |  | R | Project advertisement is still underway | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.21477
3 | 108690 | ELDEN STREET AND MONROE STREET INTERSECTION IMPROVEMENT | 9999 | Urban | Reconstruction w/o Added Capacity | Locally | Herndon | FAIRFAX | Northern Virginia | Northern Virginia:Herndon | Local Assistance Division | Amir Salahshoor | A.Salahshoor@VDOT.Virginia.gov | (703) 259-1957 | Christer P Carshult | Christer.Carshult@vdot.virginia.gov | (703) 259-1765 | John Irish | john.irish@herndon-va.gov | (703) 435-6800 | 0 |  | 0 | FY2021 | 2000000 | 2000000 | ACTIVITY DATES SET | R | Solicit Bids milestone is 32 days past the expected completion date | Y | Estimate not current | 2016-07-01 | 2016-07-01 | 2016-09-26 | 2017-05-12 | R | 2016-09-27 | 2017-05-15 | 2016-09-29 | 2017-05-15 | R | 2016-09-30 | 2017-05-15 | 2017-04-12 | 2018-05-02 | R | [10 empty] | 2019-10-10 | 2019-10-10 | 2019-11-12 | 2019-11-12 | G | [5 empty] | 2019-11-14 | 2019-11-14 | 2020-10-29 | 2020-10-29 | G | [10 empty] | 2020-12-18 | 2020-12-18 | 2021-01-20 |  | R | 2021-01-21 |  | 2021-03-03 |  | Y |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.20575
5 | 109609 | SUP from 5th St Sta. dev to ex. facilities on 5th St. Extend |  | Secondary | Facilities for Pedestrians and Bicycles | Locally | Albemarle County | CHARLOTTESVILLE | Culpeper | Charlottesville:Albemarle County | Local Assistance Division | Tracy Elliott |  |  | Michael D Barnes | MichaelD.Barnes@vdot.virginia.gov | (434) 422-9861 | Billie Campbell, TJPDC | cboyles@tjpdc.org | (434) 979-7310 | 0 |  | 0 | FY2021 | 612880 | 599800 | ACTIVITY DATES SET | R | Solicit Bids milestone is 314 days past the expected completion date | G | Project is on budget | 2016-10-03 | 2016-11-16 | 2016-12-30 | 2016-11-16 | G | 2017-01-03 | 2016-12-16 | 2017-01-05 | 2016-12-16 | G | 2017-01-06 | 2016-12-16 | 2017-07-13 | 2018-02-12 | R | [35 empty] | 2020-03-03 |  | 2020-04-13 |  | R | 2020-04-14 |  | 2020-07-15 |  | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.30832
6 | 110875 | Lee Highway Shared Use Path - Phase 1 | 0011 | Urban | Safety | Locally | Bristol | ABINGDON | Bristol | Bristol:Bristol | Infrastructure Investment Division | Tabitha H Crowder | Tabitha.Crowder@vdot.virginia.gov | (276) 696-3482 | Kenneth R Plummer | KR.Plummer@VDOT.Virginia.gov | (276) 696-3261 | Wallace McCulloch | wallace.mcculloch@bristolva.org | (276) 642-2315 | 0 |  | 0 | FY2024 | 198600 | 289057 | ACTIVITY DATES SET | G | Determine Requirements milestone finished on-time | R | Project estimate is less than $5M and is 20% or more over budget | 2017-12-15 | 2017-12-15 | 2018-02-22 | 2018-02-22 | G | 2018-02-23 | 2018-02-23 | 2018-07-30 | 2018-06-25 | G | 2018-07-31 | 2018-06-26 | 2020-01-08 | 2020-01-08 | G | [10 empty] | 2022-02-28 |  | 2022-04-01 |  | G | [5 empty] | 2022-04-05 |  | 2023-08-25 |  | G | [10 empty] | 2023-10-11 |  | 2023-12-11 |  | G | 2023-12-12 |  | 2024-01-25 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.098654
7 | 111485 | #SMART18 - POTOMAC COMMUTER GARAGE | 9999 | Secondary | Other | Locally | Prince William County | MANASSAS | Northern Virginia | Northern Virginia:Prince William County | Infrastructure Investment Division | Claudia H Llana | Claudia.Llana@VDOT.Virginia.gov | (703) 259-1768 | Rhoderick M Undan | Rhoderick.Undan@vdot.virginia.gov | (703) 259-3347 | Dagmawie Shikurye | DShikurye@pwcgov.org | (703) 792-5537 | 1 | 2018 | 0 | FY2022 | 37670000 | 53328850 | ACTIVITY DATES SET | R | Determine Requirements milestone finished 701 days late | R | Project estimate is greater than $10M and is over budget by (a) 10% or more or (b) $5M or more | 2019-07-01 | 2019-04-01 | 2019-09-24 | 2019-05-07 | G | 2018-02-01 | 2019-05-08 | 2018-02-05 | 2019-05-24 | R | 2018-02-06 | 2019-05-28 | 2019-02-06 | 2021-01-07 | R | [10 empty] | 2021-04-27 |  | 2021-05-24 |  | G | [20 empty] | 2021-03-03 |  | 2021-05-28 |  | G | 2021-12-15 |  | 2021-12-30 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.361
8 | 112615 | RTE 50 INTERSECTION AT INDEPENDENCE DR (NFCU) | 0050 | Primary | Reconstruction w/ Added Capacity | VDOT | Frederick County | EDINBURG | Staunton | Winchester:Frederick County | Infrastructure Investment Division | Clifton Balderson | clifton.balderson@dbiservices.com | (540) 460-1313 | Michael L Branscome | Michael.Branscome@VDOT.Virginia.gov | (540) 332-2377 |  |  |  | 0 |  | 0 | FY2019 | 1615548 | 1624721 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 23 days early | Y | Project estimate is less than $5M and is up to 20% over budget | [10 empty] | 2017-12-15 | 2018-03-01 | 2017-12-21 | 2018-10-31 | R | [35 empty] | 2018-04-10 | 2019-01-22 | 2019-02-12 | 2019-01-22 | G | 2019-03-28 | 2019-03-11 | 2019-04-03 | 2019-03-11 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.07072
9 | 112865 | #SGR19VB - RT 653 BRIDGE & APPR OVER NS RAILWAY Fed 12538 | 0653 | Secondary | Bridge Replacement w/o Added Capacity | VDOT | Nelson County | DILLWYN | Lynchburg | NonMPO:NonMPO | Infrastructure Investment/Asset Management Division | Anthony W Revelle | Anthony.Revelle@vdot.virginia.gov | (434) 856-8258 | Anthony W Revelle | Anthony.Revelle@vdot.virginia.gov | (434) 856-8258 |  |  |  | 0 |  | 1 | FY2024 | 5349361 | 5349361 | ACTIVITY DATES SET | G | Determine Requirements milestone finished on-time | G | Project is on budget | [5 empty] | 2020-01-27 | 2019-12-04 | 2020-02-07 | 2019-12-04 | G | 2020-02-10 | 2019-12-05 | 2021-01-05 | 2021-01-05 | G | [5 empty] | 2021-10-04 |  | 2021-10-15 |  | G | 2023-02-22 |  | 2023-03-07 |  | G | 2023-09-25 |  | 2024-04-04 |  | G | 2023-03-22 |  | 2023-09-22 |  | G | 2023-02-14 |  | 2023-10-13 |  | G | [5 empty] | 2024-04-09 |  | 2024-04-09 |  | G | 2024-06-28 |  | 2024-06-28 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.063653
10 | 87954 | #SGR21VB - RT 635 Bridge Replacement -Orange County | 0635 | Secondary | Bridge Replacement w/o Added Capacity | VDOT | Orange County | LOUISA | Culpeper | NonMPO:NonMPO | Infrastructure Investment Division | Dewitt D Sprinkel | Brent.Sprinkel@VDOT.Virginia.gov | (540) 829-7552 | Brian A Arnold | Brian.Arnold@VDOT.Virginia.gov | (540) 829-7557 |  |  |  | 0 |  | 0 | FY2020 | 4451232 | 5606014 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 14 days early | R | Project estimate is less than $5M and is 20% or more over budget | [5 empty] | 2016-01-31 | 2013-05-23 | 2016-01-31 | 2013-05-29 | G | 2017-10-17 | 2017-09-22 | 2018-05-30 | 2018-03-07 | G | [5 empty] | 2018-03-01 | 2018-03-01 | 2018-03-07 | 2018-03-07 | G | 2018-11-15 | 2018-10-05 | 2018-11-15 | 2018-10-05 | G | 2019-09-03 | 2019-09-26 | 2020-01-14 | 2020-02-27 | R | 2018-12-04 | 2018-11-19 | 2019-08-30 | 2019-08-19 | G | [10 empty] | 2020-03-10 | 2019-12-10 | 2020-03-10 | 2019-12-10 | G | 2020-03-12 | 2020-02-27 | 2020-03-12 | 2020-02-27 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.062721
11 | 103021 | Turner Drive Intersection Improvements at Benns Church Blvd | 0644 | Secondary | Traffic Management/Engineering | Locally | Isle of Wight County | FRANKLIN | Hampton Roads | Hampton Roads:Isle of Wight County | Infrastructure Investment Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Keisha Wilkins | Keisha.Wilkins@vdot.virginia.gov | (757) 956-3110 | Jamie Oliver | joliver@isleofwightus.net | (757) 365-1653 | 0 |  | 0 | FY2019 | 511428 | 697979 | WAITING FINANCIAL CLOSURE | R | Start Delivery milestone finished 405 days late | R | Project estimate is less than $5M and is 20% or more over budget | [5 empty] | 2017-07-01 | 2017-06-29 | 2017-07-01 | 2017-07-01 | G | 2018-01-30 | 2018-01-30 | 2018-05-30 | 2018-05-30 | G | [10 empty] | 2018-06-01 | 2018-08-14 | 2018-06-29 | 2018-08-15 | R | [20 empty] | 2018-06-29 | 2018-10-02 | 2018-06-29 | 2019-04-09 | R | 2018-07-02 | 2019-04-10 | 2018-08-15 | 2019-09-24 | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.36608
12 | 106027 | #TAP15 BUFFALO CREEK BIKE/PED BRIDGE & TRAIL CONNECTIONS |  | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Farmville | DILLWYN | Lynchburg | NonMPO:NonMPO | Local Assistance Division | Sharon S White | Sharon.White@VDOT.Virginia.gov | (434) 856-8220 | Sharon S White | Sharon.White@VDOT.Virginia.gov | (434) 856-8220 | Gerald Spates | gspates@farmvilleva.com | (434) 392-5686 | 0 |  | 0 | FY2019 | 987995 | 1287443 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 17 days early | R | Project estimate is less than $5M and is 20% or more over budget | [5 empty] | 2014-10-01 | 2014-11-10 | 2014-10-01 | 2014-11-10 | R | 2017-04-30 | 2017-03-30 | 2017-04-30 | 2017-04-28 | G | [35 empty] | 2018-05-31 | 2018-05-29 | 2018-06-15 | 2018-06-10 | G | 2018-08-02 | 2018-07-26 | 2018-10-01 | 2018-09-14 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.34579
13 | 107038 | REPLACE TRAFFIC SIGNALS - DISTRICTWIDE | 9999 | Miscellaneous | Safety | VDOT | Richmond District-wide |  | Richmond | Richmond:Richmond District-wide | Infrastructure Investment Division | Adam S Brooks | Adam.Brooks@VDOT.Virginia.gov | (804) 609-5274 | Adam S Brooks | Adam.Brooks@VDOT.Virginia.gov | (804) 609-5274 |  |  |  | 0 |  | 0 | FY2025 | 4000000 | 4000000 | ACTIVITY DATES SET | G | Engage Public milestone finished on-time | G | Project is on budget | [5 empty] | 2018-10-19 | 2018-07-11 | 2018-11-01 | 2018-07-20 | G | 2018-11-02 | 2018-07-23 | 2019-12-02 | 2019-12-02 | G | [5 empty] | 2020-10-06 | 2020-10-06 | 2020-10-20 | 2020-10-20 | G | 2022-06-07 |  | 2022-06-20 |  | G | 2023-12-08 |  | 2024-05-31 |  | G | 2022-07-07 |  | 2023-07-07 |  | G | [10 empty] | 2024-10-08 |  | 2024-10-08 |  | G | 2024-11-22 |  | 2025-01-02 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.07001
14 | 108796 | Norfolk Pedestrian Signal Upgrade - Citywide | 0000 | Urban | Facilities for Pedestrians and Bicycles | Locally | Norfolk | NORFOLK | Hampton Roads | Hampton Roads:Norfolk | Infrastructure Investment Division | Stephen Rowan | Steve.Rowan@vdot.virginia.gov | (757) 790-9925 | Joshua D Negovan | Joshua.Negovan@vdot.virginia.gov | (757) 956-3347 | Deborah Mangiaracina, P.E. | Deborah.Mangiaracina@norfolk.gov | (757) 664-7459 | 0 |  | 0 | FY2019 | 1870000 | 1709000 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 87 days early | G | Project is on budget | 2016-10-18 | 2016-10-18 | 2017-02-17 | 2017-02-17 | G | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | G | 2016-11-10 | 2016-11-10 | 2018-07-20 | 2018-07-20 | G | [35 empty] | 2018-08-24 | 2018-08-24 | 2018-10-05 | 2018-10-19 | R | 2018-10-08 | 2018-10-22 | 2019-04-04 | 2019-01-07 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.2378
15 | 109607 | VAN DORN STREET PEDESTRIAN AND BICYCLE ACCESS IMPROVEMENTS | 0613 | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Fairfax County | FAIRFAX | Northern Virginia | Northern Virginia:Fairfax County | Local Assistance Division | Bud Siegel |  |  | Susie X Lue | Susie.Lue@vdot.virginia.gov | (703) 259-2918 | Latesa Turner | Latesa.Turner@fairfaxcounty.gov | 70387758 | 0 |  | 0 | FY2025 | 1500000 | 3200000 | ACTIVITY DATES SET | G | Determine Requirements milestone finished on-time | R | Project estimate is less than $5M and is 20% or more over budget | 2017-04-17 | 2017-04-17 | 2017-04-17 | 2017-04-17 | G | 2017-04-26 | 2017-04-26 | 2017-04-26 | 2017-04-26 | G | 2018-02-20 | 2018-02-20 | 2019-09-23 | 2019-09-23 | G | 2020-09-29 | 2021-02-01 | 2021-07-30 |  | G | [5 empty] | 2021-08-02 |  | 2022-04-26 |  | G | [5 empty] | 2022-04-28 |  | 2023-07-31 |  | G | [10 empty] | 2023-12-06 |  | 2024-04-30 |  | G | 2024-05-01 |  | 2024-09-30 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.26255
16 | 110802 | Dam Neck Road/Holland Road Intersection Improvements |  | Urban | Reconstruction w/ Added Capacity | Locally | Virginia Beach | NORFOLK | Hampton Roads | Hampton Roads:Virginia Beach | Infrastructure Investment Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Marci Thompson | Marci.Thompson@vdot.virginia.gov | (757) 956-3093 | Katie Shannon, PE | kshannon@vbgov.com | (757) 385-1514 | 0 |  | 0 | FY2026 | 2190000 | 2190000 | NO DATES SET YET | G | Agreement with Locality milestone is 677 days ahead of the expected completion date | G | Project is on budget | 2022-10-03 |  | 2022-12-30 |  | G | 2023-01-03 |  | 2023-01-18 |  | G | 2023-01-19 |  | 2024-01-19 |  | G | [10 empty] | 2024-07-17 |  | 2024-08-05 |  | G | [5 empty] | 2024-08-07 |  | 2025-05-20 |  | G | [10 empty] | 2025-06-06 |  | 2025-07-18 |  | G | 2025-07-21 |  | 2026-01-13 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.19494
17 | 111378 | #SGR18VB - RT 708 RED HILL RD STRUCT 792 OVER N.F. HARDWARE | 0708 | Secondary | Bridge Replacement w/o Added Capacity | VDOT | Albemarle County | CHARLOTTESVILLE | Culpeper | Charlottesville:Albemarle County | Infrastructure Investment/Asset Management Division | Jennifer L Ahlin | Jennifer.Ahlin@vdot.virginia.gov | (804) 786-6581 | Brian A Arnold | Brian.Arnold@VDOT.Virginia.gov | (540) 829-7557 |  |  |  | 0 |  | 1 | FY2026 | 5100000 | 5100000 | NO DATES SET YET-PE OPEN | G | Start Development milestone finished 1274 days early | G | Project is on budget | [5 empty] | 2021-07-01 | 2018-01-09 | 2021-07-15 | 2018-01-18 | G | 2021-07-16 |  | 2022-06-14 |  | G | [5 empty] | 2023-05-18 |  | 2023-06-01 |  | G | 2024-08-01 |  | 2024-08-14 |  | G | 2025-01-13 |  | 2025-07-18 |  | G | 2024-08-29 |  | 2025-03-12 |  | G | 2024-07-25 | 2020-09-29 | 2025-04-02 |  | G | [5 empty] | 2025-08-12 |  | 2025-08-12 |  | G | 2025-10-02 |  | 2025-10-23 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.16897
18 | 112477 | MANASSAS SIGNAL REPLACEMENTS, GODWIN & LH, DUMFRIES & MILIC | 9999 | Urban | Reconstruction w/o Added Capacity | Locally | Manassas | MANASSAS | Northern Virginia | Northern Virginia:Manassas | Infrastructure Investment Division | Amir Salahshoor | A.Salahshoor@VDOT.Virginia.gov | (703) 259-1957 | Marlene Pinedo Fortich | Sofia.Pinedo@vdot.virginia.gov | (703) 259-1724 | Steve Burke |  | (703) 257-8476 | 0 |  | 0 | FY2026 | 750000 | 750000 | NO DATES SET YET | G | Agreement with Locality milestone is 768 days ahead of the expected completion date | Y | Estimate not current | 2022-09-01 |  | 2023-03-31 |  | G | 2023-04-03 |  | 2023-04-28 |  | G | 2023-05-01 |  | 2024-01-31 |  | G | [35 empty] | 2025-04-01 |  | 2025-09-30 |  | G | 2025-10-01 |  | 2026-03-30 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.15912
19 | 112815 | PRINCE WILLIAM PARKWAY INTERCHANGE @ REALIGNED BALLS FORD RD | 0234 | Primary | New Construction Roadway | Locally | Prince William County | MANASSAS | Northern Virginia | Northern Virginia:Prince William County | Infrastructure Investment Division | Amir Salahshoor | A.Salahshoor@VDOT.Virginia.gov | (703) 259-1957 | Veljibhai M Desai | Veljibhai.Desai@vdot.virginia.gov | (703) 259-2927 | Khattab Shammout | Kshammout@pwcgov.org | (703) 792-8164 | 0 |  | 0 | FY2021 | 145000000 | 145000000 | AWARDED | G | Start Delivery milestone finished 206 days early | G | Project is on budget | 2018-04-02 | 2018-04-02 | 2018-05-09 | 2018-05-09 | G | 2018-05-10 | 2018-05-10 | 2018-05-23 | 2018-05-23 | G | 2018-05-24 | 2018-05-24 | 2021-08-31 | 2019-08-23 | G | [5 empty] | 2019-04-16 | 2019-04-16 | 2019-10-29 | 2019-10-29 | G | 2019-09-03 | 2019-09-03 | 2019-09-24 | 2019-09-24 | G | [20 empty] | 2019-09-03 | 2019-09-03 | 2019-09-25 | 2019-09-25 | G | 2019-09-26 | 2019-09-26 | 2020-08-24 | 2020-01-31 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.13303
20 | 113789 | RTE F188- RURAL RUSTIC RD (SURFACE TREAT NON-HARDSURFACE RD) | 0188 | Primary | Reconstruction w/ Added Capacity | VDOT | Louisa County | LOUISA | Culpeper | NonMPO:NonMPO | Infrastructure Investment Division | Ken Connors |  |  | Bethel Kefyalew | Bethel.Kefyalew@vdot.virginia.gov | (540) 603-6015 |  |  |  | 0 |  | 0 | FY2026 | 55000 | 55000 | NO DATES SET YET | G | Start Development milestone is 964 days ahead of the expected completion date | Y | Estimate not current | [5 empty] | 2023-10-02 |  | 2023-10-13 |  | G | 2023-10-17 |  | 2024-06-11 |  | G | [5 empty] | 2025-02-20 |  | 2025-04-02 |  | G | [5 empty] | 2025-07-17 |  | 2025-11-07 |  | G | [5 empty] | 2025-07-01 |  | 2025-10-01 |  | G | [5 empty] | 2025-11-10 |  | 2025-11-10 |  | G | 2026-02-06 |  | 2026-02-06 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.084279
21 | 115382 | BUS 58 WBL - (ID 5487) RESURFACING (SOUTH BOSTON ROAD) | 0058 | Urban | Resurfacing | Locally | Danville | HALIFAX | Lynchburg | Danville:Danville | Local Assistance Division | Sharon S White | Sharon.White@VDOT.Virginia.gov | (434) 856-8220 | Sharon S White | Sharon.White@VDOT.Virginia.gov | (434) 856-8220 | Brian Dunevant | dunevbl@danvilleva.gov | (434) 799-5019 | 0 |  | 0 | FY2020 | 333000 | 333000 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 114 days early | G | Project is on budget | 2020-01-31 | 2019-07-01 | 2020-04-24 | 2019-09-20 | G | [5 empty] | 2020-01-31 | 2019-09-23 | 2020-02-13 | 2020-02-03 | G | [25 empty] | 2020-02-04 | 2020-02-06 | 2020-02-18 | 2020-02-06 | G | [5 empty] | 2020-02-19 | 2020-02-07 | 2020-03-17 | 2020-02-07 | G | 2020-06-04 | 2020-02-11 | 2020-06-04 | 2020-02-11 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.050288
22 | 116159 | #I81CIP NB MM 38.9 EXTEND DECEL LANE (ID #5) | 0081 | Interstate | Reconstruction w/o Added Capacity | VDOT | Smyth County | ABINGDON | Bristol | NonMPO:NonMPO | Infrastructure Investment Division | Donald A Necessary | Donald.Necessary@VDOT.Virginia.gov | (276) 696-3285 | Marvin E Holley | Gene.Holley@VDOT.Virginia.gov | (276) 696-3255 |  |  |  | 0 |  | 0 | FY2022 | 1476000 | 1476000 | ACTIVITY DATES SET | Y | Engage Public milestone is 16 days ahead of the expected completion date and there is a risk of missing this milestone date | G | Project is on budget | [5 empty] | 2020-07-01 | 2020-01-14 | 2020-07-15 | 2020-01-14 | G | 2020-07-16 | 2020-01-15 | 2021-03-12 | 2020-09-14 | G | [5 empty] | 2021-03-09 |  | 2021-03-09 |  | Y | [5 empty] | 2021-03-15 |  | 2021-03-15 |  | Y | [5 empty] | 2021-05-07 |  | 2021-07-12 |  | G | [5 empty] | 2021-08-10 |  | 2021-08-13 |  | G | 2021-11-04 |  | 2021-11-04 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.080213
23 | 116741 | Toll Integration - Systems Integrator | 9999 | Interstate | Other | VDOT | Hampton Roads District-wide |  | Hampton Roads | Hampton Roads:Hampton | Infrastructure Investment Division | Dwayne K Cook | Dwayne.Cook@VDOT.Virginia.gov | (757) 956-3014 | Michael J Miller | Michael.Miller@VDOT.Virginia.gov | (757) 605-8741 |  |  |  | 0 |  | 0 | FY2022 | 12786320 | 12786320 | ADVERTISED | G | Solicit Bids milestone finished 309 days early | G | Project is on budget | [5 empty] | 2020-04-02 | 2020-06-08 | 2020-04-15 | 2020-06-08 | R | 2020-04-16 | 2020-06-09 | 2021-05-04 | 2020-08-11 | G | [5 empty] | 2020-09-24 | 2020-10-06 | 2020-10-07 | 2020-10-06 | G | [25 empty] | 2021-08-11 | 2020-10-06 | 2021-08-11 | 2020-10-06 | G | 2021-12-03 |  | 2021-12-03 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | ADMINISTRATIVE SERVICES | 0 | 0 | 0.18062
24 | 116907 | MULTI-MODAL IMPROVEMENTS (CITYWIDE) REV SHARE FY21 | 9999 | Urban | Facilities for Pedestrians and Bicycles | Locally | Charlottesville | CHARLOTTESVILLE | Culpeper | Charlottesville:Charlottesville | Local Assistance Division | Gregory J Cooley | Gregory.Cooley@vdot.virginia.gov | (434) 906-7979 | Michael D Barnes | MichaelD.Barnes@vdot.virginia.gov | (434) 422-9861 | Jeanette Janiczek | janiczek@charlottesville.org | (434) 970-3309 | 0 |  | 0 | FY2024 | 1000000 | 1000000 | NO DATES SET YET | R | Agreement with Locality milestone is 6 days past the expected completion date | G | Project is on budget | 2020-10-01 |  | 2021-02-15 |  | R | 2021-02-16 |  | 2021-03-09 |  | Y | 2021-09-13 |  | 2022-01-10 |  | G | [10 empty] | 2023-05-02 |  | 2023-06-06 |  | G | [5 empty] | 2023-06-07 |  | 2023-11-03 |  | G | 2023-10-02 |  | 2024-03-07 |  | G | [5 empty] | 2024-02-14 |  | 2024-03-13 |  | G | 2024-05-31 |  | 2024-05-31 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.14084
25 | 117101 | #REVSH21 BUS 58 (RIVERSIDE DRIVE) - RECONSTRUCTION | 0058 | Urban | Reconstruction w/o Added Capacity | Locally | Danville | HALIFAX | Lynchburg | Danville:Danville | Local Assistance Division | Gregg Allen | Gregg.Allen@vdot.virginia.gov | (434) 426-5575 | Gregg Allen | Gregg.Allen@vdot.virginia.gov | (434) 426-5575 | BRIAN DUNEVANT | dunevbl@danvilleva.gov | (434) 799-5019 | 0 |  | 0 | FY2025 | 1560000 | 1560000 | NO DATES SET YET | G | Agreement with Locality milestone is 106 days ahead of the expected completion date | G | Project is on budget | 2021-01-29 |  | 2021-06-07 |  | G | 2021-06-08 |  | 2021-06-28 |  | G | 2022-01-07 |  | 2022-05-03 |  | G | [10 empty] | 2023-08-22 |  | 2023-09-26 |  | G | [5 empty] | 2023-09-27 |  | 2024-03-04 |  | G | 2024-01-30 |  | 2024-06-26 |  | G | [5 empty] | 2024-06-05 |  | 2024-07-02 |  | G | 2024-09-20 |  | 2024-09-20 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.071671
26 | 117134 | Citywide Sidewalk and Handicap Ramp | 0000 | Urban | Facilities for Pedestrians and Bicycles | Locally | Newport News | WILLIAMSBURG | Hampton Roads | Hampton Roads:Newport News | Local Assistance Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Chessica Villaflores | Chessica.Villaflores@vdot.virginia.gov | (757) 956-3094 | Bridjette Parker | parkerbj1@nnva.gov | (757) 926-8314 | 0 |  | 0 | FY2024 | 250000 | 250000 | NO DATES SET YET | Y | Agreement with Locality milestone is 11 days ahead of the expected completion date and there is a risk of missing this milestone date | G | Project is on budget | 2020-10-20 |  | 2021-03-04 |  | Y | 2021-03-05 |  | 2021-03-25 |  | G | 2021-09-29 |  | 2022-01-28 |  | G | [10 empty] | 2023-05-18 |  | 2023-06-22 |  | G | [5 empty] | 2023-06-23 |  | 2023-11-22 |  | G | 2023-10-19 |  | 2024-03-25 |  | G | [5 empty] | 2024-03-04 |  | 2024-03-29 |  | G | 2024-06-18 |  | 2024-06-18 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.20382
27 | 90188 | Rte 39 Over Maury River, VA Str. 1046 | 0039 | Primary | Bridge Replacement w/o Added Capacity | VDOT | Rockbridge County | LEXINGTON | Staunton | NonMPO:NonMPO | Infrastructure Investment Division | Kendal R Walus | Kendal.Walus@VDOT.Virginia.gov | (804) 786-4575 | Ashraf A Antonius | Ashraf.Antonius@vdot.virginia.gov | (540) 332-9107 |  |  |  | 0 |  | 0 | FY2025 | 7733061 | 929630 | ACTIVITY DATES SET | G | Start Purchasing Right-of-Way milestone finished on-time | G | Project is on budget | [5 empty] | 2010-07-01 | 2010-07-19 | 2010-07-01 | 2010-07-19 | R | 2010-10-04 | 2011-12-06 | 2012-05-31 | 2014-01-27 | R | [5 empty] | 2014-01-14 | 2014-01-14 | 2014-01-24 | 2014-01-24 | G | 2016-07-14 | 2016-07-14 | 2016-07-19 | 2016-07-19 | G | [10 empty] | 2022-12-12 |  | 2023-12-08 |  | G | [5 empty] | 2023-11-15 |  | 2024-12-10 |  | G | 2025-04-09 |  | 2025-04-16 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.054877
28 | 102974 | REEDY CREEK - STORMWATER UTILITY - PHASE 1 |  | Urban | Utilities | Locally | Richmond | ASHLAND | Richmond | Richmond:Richmond | Local Assistance Division | Brian J Lokker | Brian.Lokker@VDOT.Virginia.gov | (804) 524-6010 | Brian J Lokker | Brian.Lokker@VDOT.Virginia.gov | (804) 524-6010 | LAMONT BENJAMIN | lamont.benjamin@richmondgov.co | (804) 646-6339 | 0 |  | 0 | FY2019 | 800000 | 800000 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 73 days early | G | Project is on budget | [5 empty] | 2012-10-01 | 2012-12-20 | 2012-12-31 | 2012-12-20 | G | 2014-02-03 | 2013-12-13 | 2014-06-30 | 2013-12-27 | G | [35 empty] | 2017-10-27 | 2017-10-27 | 2017-10-27 | 2017-10-27 | G | 2017-12-21 | 2018-04-20 | 2018-07-02 | 2018-04-20 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.16104
29 | 104263 | North Massanutten St./Old Valley Pk. Pedestrian Improvements | 0011 | Primary | Other | Locally | Strasburg | EDINBURG | Staunton | NonMPO:NonMPO | Local Assistance Division | Kimberly Cameron | Kim.Cameron@vdot.virginia.gov | (540) 332-7886 | Kimberly Cameron | Kim.Cameron@vdot.virginia.gov | (540) 332-7886 | Wyatt Pearson | wpearson@strasburgva.com | (540) 465-9197 | 0 |  | 0 | FY2019 | 1271062 | 1112562 | AWARDED | R | Start Delivery milestone finished 146 days late | G | Project is on budget | [5 empty] | 2014-07-01 | 2015-02-09 | 2014-07-01 | 2015-02-09 | R | 2015-03-02 | 2015-02-10 | 2018-05-31 | 2018-03-02 | G | [35 empty] | 2018-09-28 | 2019-03-04 | 2018-09-28 | 2019-03-04 | R | 2018-11-01 | 2019-04-04 | 2019-01-31 | 2019-06-26 | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.32895
30 | 113694 | #SGR19LB??- Elbow Road over Spillway at Norfolk Reservoir | 0013 | Urban | Bridge Replacement w/o Added Capacity | Locally | Chesapeake | NORFOLK | Hampton Roads | Hampton Roads:Chesapeake | Infrastructure Investment Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Johndel A Alcaide | John.Alcaide@vdot.virginia.gov | (757) 956-3098 | Sam Sawan | sawan@cityofchesapeake.net | (757) 382-8263 | 0 |  | 1 | FY2022 | 7527886 | 7527886 | NO DATES SET YET-PE OPEN | R | Determine Requirements milestone is 289 days past the expected completion date | G | Project is on budget | 2019-07-31 | 2019-05-01 | 2019-10-24 | 2019-05-24 | G | 2019-10-25 | 2019-05-28 | 2019-10-29 | 2019-06-06 | G | 2019-10-30 |  | 2020-05-08 |  | R | [10 empty] | 2021-03-08 |  | 2021-03-26 |  | G | [5 empty] | 2021-03-30 |  | 2022-01-07 |  | G | 2020-06-16 |  | 2021-02-23 |  | Y | [5 empty] | 2022-01-27 |  | 2022-02-24 |  | G | 2022-05-13 |  | 2022-05-13 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.1595
31 | 114879 | RIVERSIDE PARKWAY INTERSECTION IMPROVEMENTS | 2401 | Secondary | Safety | VDOT | Loudoun County | LEESBURG | Northern Virginia | Northern Virginia:Loudoun County | Infrastructure Investment Division | Waqar A Siddiqui | Sid.Siddiqui@VDOT.Virginia.gov | (703) 259-3225 | Jessica Paris | Jessica.Paris@vdot.virginia.gov | (703) 259-2409 | Eloisa Thring | Eloisa.Thring@loudoun.gov | (571) 258-3526 | 0 |  | 0 | FY2020 | 480000 | 480000 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 21 days early | G | Project is on budget | [5 empty] | 2019-09-16 | 2019-09-11 | 2019-09-16 | 2019-09-11 | G | 2019-09-17 | 2019-09-12 | 2019-12-30 | 2019-11-25 | G | [5 empty] | 2019-12-11 | 2019-12-11 | 2019-12-12 | 2019-12-12 | G | [25 empty] | 2020-01-31 | 2020-01-27 | 2020-02-06 | 2020-01-30 | G | 2020-02-07 | 2020-01-31 | 2020-02-21 | 2020-01-31 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | WORK/TASK ORDER | 1 | 0 | 0.1431
32 | 115802 | #I81CIP NB EXIT 269 EXTEND DECELERATION LANE (ID #45) | 0081 | Interstate | Reconstruction w/o Added Capacity | VDOT | Shenandoah County | EDINBURG | Staunton | NonMPO:NonMPO | Infrastructure Investment Division | John-Allen L Ennis | JohnAllen.Ennis@VDOT.Virginia.gov | (540) 332-9118 | Alexander Alvarado | Alexander.Alvarado@vdot.virginia.gov | (540) 332-7372 |  |  |  | 0 |  | 0 | FY2020 | 1000000 | 425000 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished on-time | G | Project is on budget | [5 empty] | 2019-09-06 | 2019-08-26 | 2019-09-19 | 2019-08-26 | G | 2019-09-20 | 2019-08-27 | 2020-08-18 | 2019-09-09 | G | [5 empty] | 2020-07-02 | 2019-09-10 | 2020-07-30 | 2019-09-10 | G | 2020-09-21 | 2019-10-11 | 2020-09-21 | 2019-10-11 | G | 2020-07-27 | 2019-10-10 | 2020-07-27 | 2019-10-10 | G | 2020-09-21 | 2019-10-17 | 2020-09-21 | 2019-10-17 | G | [10 empty] | 2020-01-07 | 2020-01-07 | 2020-01-07 | 2020-01-07 | G | 2020-03-30 | 2020-03-30 | 2020-03-30 | 2020-03-30 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | SAAP CONTRACT | 1 | 0 | 0.06308
33 | 116278 | #I81CIP SB MM 234 TO 236, WEYERS CAVE TCL (ID #55) | 0081 | Interstate | Bridge Replacement w/ Added Capacity | VDOT | Augusta County | HARRISONBURG | Staunton | NonMPO:NonMPO | Infrastructure Investment Division | John-Allen L Ennis | JohnAllen.Ennis@VDOT.Virginia.gov | (540) 332-9118 | Jennifer Hoover | Jennifer.Hoover@vdot.virginia.gov | (540) 332-2264 |  |  |  | 0 |  | 0 | FY2025 | 29581960 | 29581960 | NO DATES SET YET-PE OPEN | G | Start Development milestone finished 159 days early | G | Project is on budget | [5 empty] | 2020-07-01 | 2020-01-27 | 2020-07-15 | 2020-02-07 | G | 2020-07-16 |  | 2021-08-24 |  | G | [5 empty] | 2022-08-23 |  | 2022-09-06 |  | G | 2023-11-29 |  | 2023-12-12 |  | G | 2024-05-09 |  | 2024-11-13 |  | G | 2023-12-29 |  | 2024-07-05 |  | G | 2023-05-22 |  | 2024-01-29 |  | G | [5 empty] | 2024-12-10 |  | 2024-12-10 |  | G | 2025-04-03 |  | 2025-04-03 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.079374
34 | 116884 | JEFFERSON STREET - MILLING, PAVEMENT & RECONSTRUCTION | 9999 | Urban | Resurfacing | Locally | Orange | LOUISA | Culpeper | NonMPO:NonMPO | Local Assistance Division | Gregory J Cooley | Gregory.Cooley@vdot.virginia.gov | (434) 906-7979 | John P Price | John.Price@VDOT.Virginia.gov | (540) 347-6371 | John Cooley | townplanner@townoforangeva.org | (540) 672-6917 | 0 |  | 0 | FY2023 | 117478 | 117478 | NO DATES SET YET | G | Agreement with Locality milestone is 326 days ahead of the expected completion date | G | Project is on budget | 2021-09-01 |  | 2022-01-13 |  | G | [5 empty] | 2022-01-18 |  | 2022-01-31 |  | G | [25 empty] | 2021-09-30 |  | 2022-03-08 |  | G | [5 empty] | 2022-05-04 |  | 2022-06-01 |  | G | 2022-08-19 |  | 2022-08-19 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.047965
35 | 117079 | Hampton Roads HAR ATMS Integrations and Repairs | 9999 | Interstate | Traffic Management/Engineering | VDOT | Hampton Roads District-wide |  | Hampton Roads | Hampton Roads:Hampton Roads District-wide | Infrastructure Investment Division | Dwayne K Cook | Dwayne.Cook@VDOT.Virginia.gov | (757) 956-3014 | Michael E Elliott | Mike.Elliott@vdot.virginia.gov | (757) 513-4372 |  |  |  | 0 |  | 0 | FY2020 | 250000 | 250000 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 12 days early | G | Project is on budget | [10 empty] | 2020-05-08 | 2020-04-13 | 2020-09-15 | 2020-04-13 | G | [35 empty] | 2020-04-29 | 2020-04-23 | 2020-05-05 | 2020-04-29 | G | 2020-05-06 | 2020-04-30 | 2020-05-12 | 2020-04-30 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | WORK/TASK ORDER | 1 | 0 | 0.19172
36 | 117125 | West Queens Drive Sidewalk | 0716 | Enhancement | Facilities for Pedestrians and Bicycles | Locally | York County | WILLIAMSBURG | Hampton Roads | Hampton Roads:York County | Local Assistance Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Keisha Wilkins | Keisha.Wilkins@vdot.virginia.gov | (757) 956-3110 | Elizabeth Mertz-Guinn | elizabeth.mertz-guinn@yorkcounty.gov | (757) 890-3785 | 0 |  | 0 | FY2024 | 130575 | 130575 | NO DATES SET YET | Y | Agreement with Locality milestone is 5 days ahead of the expected completion date and there is a risk of missing this milestone date | G | Project is on budget | 2020-10-13 |  | 2021-02-26 |  | Y | 2021-03-01 |  | 2021-03-19 |  | Y | 2021-09-23 |  | 2022-01-24 |  | G | [10 empty] | 2023-05-12 |  | 2023-06-16 |  | G | [5 empty] | 2023-06-19 |  | 2023-11-16 |  | G | 2023-10-12 |  | 2024-03-19 |  | G | [5 empty] | 2024-02-27 |  | 2024-03-25 |  | G | 2024-06-12 |  | 2024-06-12 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.31256
37 | 117212 | FY 21 Pedestrian Crossing Improvements | 9999 | Primary | Safety | VDOT | Salem District-wide |  | Salem | Roanoke:Salem District-wide | Infrastructure Investment/Asset Management Division | Bernard S Grinnell | Sean.Grinnell@VDOT.Virginia.gov | (540) 375-0148 | Jason W Knight | Jay.Knight@vdot.virginia.gov | (540) 375-0152 | N/a |  |  | 0 |  | 0 | FY2023 | 614824 | 614824 | ACTIVITY DATES SET | R | Determine Requirements milestone finished 62 days late | G | Project is on budget | [5 empty] | 2020-04-01 | 2020-05-11 | 2020-04-14 | 2020-05-12 | R | 2020-04-15 | 2020-05-12 | 2020-05-12 | 2020-07-13 | R | [35 empty] | 2022-04-12 |  | 2022-04-12 |  | G | 2022-07-01 |  | 2022-10-18 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.12181
38 | 100937 | #HB2.FY17 Route 58/ Holland Road Corridor Improvements | 0058 | Urban | Reconstruction w/ Added Capacity | Locally | Suffolk | NORFOLK | Hampton Roads | Hampton Roads:Suffolk | Infrastructure Investment Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Johndel A Alcaide | John.Alcaide@vdot.virginia.gov | (757) 956-3098 | Robert Lewis | relewis@suffolkva.us | (757) 514-7621 | 1 | 2017 | 0 | FY2021 | 77183424 | 83781184 | ADVERTISED | R | Start Delivery milestone is 235 days past the expected completion date | R | Project estimate is greater than $10M and is over budget by (a) 10% or more or (b) $5M or more | [5 empty] | 2012-01-03 | 2012-05-02 | 2012-02-01 | 2012-05-02 | R | 2012-08-01 | 2012-08-01 | 2013-01-17 | 2014-01-23 | R | [10 empty] | 2015-07-20 | 2015-07-20 | 2015-07-20 | 2015-07-20 | G | [20 empty] | 2020-05-02 | 2020-08-24 | 2020-05-02 | 2020-09-30 | R | 2020-06-01 |  | 2020-07-01 |  | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.17641
39 | 103606 | Town of St. Paul Downtown Streetscaping |  | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Saint Paul | WISE | Bristol | NonMPO:NonMPO | Local Assistance Division | Tabitha H Crowder | Tabitha.Crowder@vdot.virginia.gov | (276) 696-3482 | Kenneth R Plummer | KR.Plummer@VDOT.Virginia.gov | (276) 696-3261 | Debora Baca | dbaca@stpaulva.org | (276) 762-5297 | 0 |  | 0 | FY2019 | 492273 | 553355 | CONSTRUCTION COMPLETED | R | Start Delivery milestone finished 210 days late | Y | Project estimate is less than $5M and is up to 20% over budget | [5 empty] | 2012-10-01 | 2012-10-01 | 2012-10-05 | 2012-10-05 | G | 2012-10-01 | 2012-10-01 | 2018-07-30 | 2018-07-30 | G | [25 empty] | 2018-01-02 | 2019-02-07 | 2018-12-24 | 2019-02-07 | R | [5 empty] | 2019-01-08 | 2019-05-22 | 2019-04-04 | 2019-06-18 | R | 2019-01-09 | 2019-09-09 | 2019-02-11 | 2019-09-09 | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.34742
40 | 107023 | FLASHING YELLOW ARROW UPGRADES - STAUNTON DISTRICT | 9999 | Miscellaneous | Safety | VDOT | Staunton District-wide |  | Staunton | NonMPO:NonMPO | Infrastructure Investment Division | Matthew Bond | Matthew.Bond@vdot.virginia.gov | (540) 332-9275 | Michael L Surratt | Michael.Surratt@VDOT.Virginia.gov | (540) 332-9325 |  |  |  | 0 |  | 0 | FY2019 | 660000 | 660000 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 182 days early | G | Project is on budget | [5 empty] | 2016-09-30 | 2017-05-23 | 2016-10-14 | 2017-05-23 | R | 2016-10-17 | 2016-08-23 | 2016-11-14 | 2017-05-24 | R | [35 empty] | 2018-06-28 | 2018-02-25 | 2018-07-10 | 2018-02-25 | G | 2018-08-08 | 2018-02-26 | 2018-08-28 | 2018-02-27 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | WORK/TASK ORDER | 1 | 0 | 0.063384
41 | 108645 | Gay Ave. Construct Sidewalk | 9999 | Secondary | Facilities for Pedestrians and Bicycles | Locally | Henrico County | ASHLAND | Richmond | Richmond:Henrico County | Local Assistance Division | Douglas L Orcutt | Doug.Orcutt@vdot.virginia.gov | (804) 609-5428 | Douglas L Orcutt | Doug.Orcutt@vdot.virginia.gov | (804) 609-5428 | Todd Eure | eur@henrico.us | (804) 501-4617 | 0 |  | 0 | FY2020 | 2335470 | 3089032 | ACTIVITY DATES SET | R | Complete Purchasing Right-of-Way milestone is 464 days past the expected completion date | R | Project estimate is less than $5M and is 20% or more over budget | 2017-04-05 | 2016-07-01 | 2017-06-28 | 2016-10-10 | G | 2017-06-29 | 2016-07-01 | 2017-07-03 | 2016-12-13 | G | 2017-07-05 | 2017-08-02 | 2018-01-11 | 2017-09-07 | G | [10 empty] | 2019-01-15 | 2018-01-22 | 2019-02-06 | 2018-01-26 | G | [5 empty] | 2019-02-08 |  | 2019-11-15 |  | R | [10 empty] | 2019-12-05 |  | 2020-01-03 |  | R | 2020-01-06 |  | 2020-02-18 |  | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.35977
42 | 109062 | TRENCH WIDEN SHOULDERS AND INSTALL RUMBLE STRIPS RTE 259 | 0259 | Primary | Safety | VDOT | Rockingham County | HARRISONBURG | Staunton | NonMPO:NonMPO | Infrastructure Investment Division | Keith M Rider | Keith.Rider@VDOT.Virginia.gov | (434) 856-8145 | Kunal Kothawade | Kunal.Kothawade@vdot.virginia.gov | (540) 332-9259 |  |  |  | 0 |  | 0 | FY2023 | 2700000 | 2700000 | ACTIVITY DATES SET | G | Engage Public milestone finished 146 days early | G | Project is on budget | [5 empty] | 2019-12-02 | 2020-08-20 | 2019-12-13 | 2020-08-20 | R | 2019-12-16 | 2020-08-21 | 2020-08-06 | 2020-09-30 | R | [5 empty] | 2021-02-24 | 2020-10-01 | 2021-02-24 | 2020-10-01 | G | [5 empty] | 2021-03-29 |  | 2021-03-29 |  | G | [15 empty] | 2022-05-10 |  | 2022-06-02 |  | G | 2022-07-25 |  | 2022-08-12 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.06783
43 | 109311 | #HB2.FY17 LABURNUM AVE - IMPROVE INTERCHANGE AT RTE 195 | 0000 | Urban | Safety | VDOT | Richmond | ASHLAND | Richmond | Richmond:Richmond | Infrastructure Investment Division | Lawrence Ramsey | Brian.Ramsey@VDOT.Virginia.gov | (804) 585-3579 | Lawrence Ramsey | Brian.Ramsey@VDOT.Virginia.gov | (804) 585-3579 | Winston Phillips | Winston.Phillips@richmondgov.com | (804) 646-5994 | 1 | 2017 | 0 | FY2021 | 2435580 | 2435580 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 159 days early | G | Project is on budget | [5 empty] | 2017-06-20 | 2017-06-26 | 2017-07-03 | 2017-07-07 | R | 2017-07-05 | 2017-07-07 | 2018-06-01 | 2017-07-19 | G | [5 empty] | 2018-01-17 | 2018-03-02 | 2018-03-14 | 2018-03-09 | G | 2019-05-02 | 2019-04-10 | 2019-05-16 | 2019-04-10 | G | 2019-12-26 | 2019-04-10 | 2020-06-17 | 2019-04-10 | G | 2019-06-04 | 2019-04-10 | 2019-11-22 | 2019-04-10 | G | [10 empty] | 2020-08-11 | 2020-04-07 | 2020-08-11 | 2020-04-07 | G | 2020-09-17 | 2020-06-25 | 2020-12-01 | 2020-06-25 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.09619
44 | 109572 | Norfolk BusShelters and Pedestrian Improvements | 0000 | Urban | Transit | Locally | Norfolk | NORFOLK | Hampton Roads | Hampton Roads:Norfolk | Infrastructure Investment Division | Stephen Rowan | Steve.Rowan@vdot.virginia.gov | (757) 790-9925 | Derrick Williams | Derrick.Williams@vdot.virginia.gov | (757) 956-3097 | Deborah Mangiaracina, P. E. | deborah.mangiaracina@norfolk.gov | (757) 664-7459 | 0 |  | 0 | FY2025 | 1109356 | 1109356 | NO DATES SET YET | G | Agreement with Locality milestone is 410 days ahead of the expected completion date | G | Project is on budget | 2022-01-11 |  | 2022-04-07 |  | G | 2022-04-08 |  | 2022-04-21 |  | G | 2022-04-22 |  | 2023-04-24 |  | G | [35 empty] | 2024-03-06 |  | 2024-04-16 |  | G | 2024-04-17 |  | 2024-10-04 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.22631
45 | 110599 | #SGR18VB - RT 220 OVER REED CREEK (STR 10063) - BR REPLACE | 0220 | Primary | Bridge Replacement w/o Added Capacity | VDOT | Henry County | MARTINSVILLE | Salem | NonMPO:NonMPO | Infrastructure Investment/Asset Management Division | Anthony T Marshall | Todd.Marshall@VDOT.Virginia.gov | (540) 387-5460 | Bryan D Smith | BryanD.Smith@vdot.virginia.gov | (540) 375-3575 |  |  |  | 0 |  | 1 | FY2022 | 6350000 | 6350000 | NO DATES SET YET | G | Determine Requirements milestone is 199 days ahead of the expected completion date | G | Project is on budget | [10 empty] | 2021-09-01 |  | 2021-09-08 |  | G | [35 empty] | 2021-11-09 |  | 2021-11-09 |  | G | 2022-03-08 |  | 2022-04-11 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.062776
46 | 111085 | CITY-WIDE FLASHING YELLOW ARROW PROG |  | Urban | Safety | Locally | Harrisonburg | HARRISONBURG | Staunton | Harrisonburg:Harrisonburg | Infrastructure Investment Division | Keith M Rider | Keith.Rider@VDOT.Virginia.gov | (434) 856-8145 | Kunal Kothawade | Kunal.Kothawade@vdot.virginia.gov | (540) 332-9259 | Aaron Rhoney, City of Harrisonburg | Aaron.Rhoney@harrisonburgva.gov | (540) 434-5928 | 0 |  | 0 | FY2022 | 302000 | 295176 | AWARDED | G | Start Delivery milestone finished 529 days early | G | Project is on budget | 2017-07-13 | 2018-12-07 | 2019-05-03 | 2019-01-07 | G | 2019-05-06 | 2019-01-08 | 2019-09-25 | 2019-07-25 | G | 2019-09-26 | 2019-07-01 | 2020-08-27 | 2020-06-03 | G | [35 empty] | 2021-10-28 | 2020-09-14 | 2021-11-29 | 2020-09-14 | G | 2021-11-30 | 2020-09-15 | 2022-04-11 | 2020-10-29 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.078299
47 | 112066 | RTE 197 (W. LABURNUM AVE) EB - RESURFACE | 0197 | Urban | Resurfacing | Locally | Richmond | ASHLAND | Richmond | Richmond:Richmond | Local Assistance Division | Brian J Lokker | Brian.Lokker@VDOT.Virginia.gov | (804) 524-6010 | Brian J Lokker | Brian.Lokker@VDOT.Virginia.gov | (804) 524-6010 | Kenneth Horak | Kenny.Horak@Richmondgov.com | (804) 646-4781 | 0 |  | 0 | FY2019 | 611000 | 616000 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 43 days early | Y | Project estimate is less than $5M and is up to 20% over budget | 2017-06-01 | 2018-01-04 | 2017-08-24 | 2018-02-07 | R | 2017-08-25 | 2018-02-16 | 2017-08-29 | 2018-02-22 | R | 2017-08-30 | 2018-02-23 | 2018-03-13 | 2018-03-12 | G | [35 empty] | 2018-04-26 | 2018-04-02 | 2018-06-29 | 2018-05-25 | G | 2018-07-02 | 2018-07-02 | 2018-09-18 | 2018-08-06 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.082667
48 | 113127 | RS - Townwide Sidewalks - New Construction - Town of Bedford | 0000 | Urban | Facilities for Pedestrians and Bicycles | Locally | Bedford | BEDFORD | Salem | NonMPO:NonMPO | Local Assistance Division | Jessie Nester | Jessie.Nester@vdot.virginia.gov | (540) 613-4115 | Jessie Nester | Jessie.Nester@vdot.virginia.gov | (540) 613-4115 | Wayne Hale | whale@bedfordva.gov | (540) 587-6033 | 0 |  | 0 | FY2021 | 792333 | 532138 | ADVERTISED | R | Start Delivery milestone is 60 days past the expected completion date | G | Project is on budget | 2018-08-01 | 2018-08-01 | 2018-10-25 | 2018-10-17 | G | 2018-10-26 | 2018-10-17 | 2018-10-30 | 2018-10-17 | G | 2018-10-31 | 2019-01-09 | 2019-08-01 | 2019-08-01 | G | [35 empty] | 2020-05-19 | 2020-12-23 | 2020-06-15 | 2020-12-23 | R | 2020-11-06 |  | 2020-12-23 |  | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.20025
49 | 113250 | RTE 20 - PRIMARY EXTENSION PAVEMENT OVERLAY | 0020 | Urban | Resurfacing | Locally | Orange | LOUISA | Culpeper | NonMPO:NonMPO | Local Assistance Division | Ken Connors |  |  | John P Price | John.Price@VDOT.Virginia.gov | (540) 347-6371 | JOHN COOLEY | townplaner@townoforangeva.org | (540) 672-6917 | 0 |  | 1 | FY2019 | 221450 | 221450 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 140 days early | G | Project is on budget | 2018-08-17 | 2018-07-01 | 2018-11-13 | 2018-07-12 | G | [5 empty] | 2018-08-17 | 2018-07-02 | 2018-08-30 | 2018-08-08 | G | [25 empty] | 2018-08-09 | 2018-08-05 | 2018-11-02 | 2018-08-05 | G | [5 empty] | 2019-01-08 | 2018-08-01 | 2019-03-14 | 2018-08-17 | G | 2019-06-03 | 2018-11-01 | 2019-06-21 | 2019-02-01 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.048092
50 | 105581 | NURSERY AVENUE DRAINAGE IMPROVEMENTS | 9999 | Urban | Restoration and Rehabilitation | Locally | Purcellville | LEESBURG | Northern Virginia | Northern Virginia:Purcellville | Local Assistance Division | Christer P Carshult | Christer.Carshult@vdot.virginia.gov | (703) 259-1765 | Veljibhai M Desai | Veljibhai.Desai@vdot.virginia.gov | (703) 259-2927 | Jessica Mehl | jmehl@purcellvilleva.gov | (540) 751-2330 | 0 |  | 0 | FY2020 | 1823150 | 2390471 | CONSTRUCTION STARTED | R | Start Delivery milestone finished 319 days late | R | Project estimate is less than $5M and is 20% or more over budget | 2014-07-17 | 2014-07-17 | 2014-07-17 | 2014-07-17 | G | 2014-09-30 | 2014-07-01 | 2014-09-30 | 2014-07-01 | G | 2015-03-02 | 2015-02-27 | 2015-08-28 | 2015-08-27 | G | [10 empty] | 2018-02-05 | 2018-02-05 | 2018-04-05 | 2018-04-05 | G | [20 empty] | 2018-09-17 | 2019-09-04 | 2018-12-14 | 2020-05-08 | R | 2019-04-15 | 2020-06-20 | 2019-08-15 | 2020-06-29 | R | Delay due to changes in scope of work, project management, plan designs, or resolution of public comments | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.36497
51 | 107072 | US 460 Shoulder Initiative - Buchanan County | 0460 | Primary | Safety | VDOT | Buchanan County | LEBANON | Bristol | NonMPO:NonMPO | Infrastructure Investment Division | John W Bechtold | John.Bechtold@vdot.virginia.gov | (276) 696-3365 | Brandi Halloway | Brandi.Halloway@vdot.virginia.gov | (276) 696-3254 |  |  |  | 0 |  | 0 | FY2019 | 2889814 | 3028647 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 4 days early | Y | Project estimate is less than $5M and is up to 20% over budget | [5 empty] | 2017-07-03 | 2017-07-03 | 2017-07-17 | 2017-07-13 | G | 2017-07-18 | 2017-07-18 | 2017-08-14 | 2017-08-14 | G | [35 empty] | 2018-05-16 | 2018-05-22 | 2018-05-16 | 2018-05-22 | R | 2018-06-29 | 2018-07-16 | 2018-07-20 | 2018-07-16 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.060563
52 | 108810 | #HB2.FY17 Route 11 S. Valley Pike Roadway Improvements | 0011 | Primary | Reconstruction w/ Added Capacity | VDOT | Rockingham County | HARRISONBURG | Staunton | Harrisonburg:Rockingham County | Infrastructure Investment Division | John-Allen L Ennis | JohnAllen.Ennis@VDOT.Virginia.gov | (540) 332-9118 | Timothy Gregory | Tim.Gregory@vdot.virginia.gov | (540) 332-7891 |  |  |  | 1 | 2017 | 0 | FY2021 | 18296217 | 19345268 | ACTIVITY DATES SET | R | Start Purchasing Right-of-Way milestone is 482 days past the expected completion date | Y | Project estimate is greater than $10M and is over budget by (a) up to 10% or (b) up to $5M | [5 empty] | 2016-10-03 | 2016-10-03 | 2016-10-17 | 2016-10-17 | G | 2016-10-18 | 2016-10-18 | 2019-09-16 | 2018-02-12 | G | [5 empty] | 2018-11-29 | 2018-12-07 | 2018-12-27 | 2019-04-30 | R | 2019-10-14 |  | 2019-10-28 |  | R | 2020-03-30 |  | 2021-01-14 |  | R | 2019-11-14 |  | 2020-10-14 |  | R | 2019-05-01 |  | 2020-10-13 |  | R | [5 empty] | 2021-02-09 |  | 2021-02-09 |  | R | 2021-03-25 |  | 2021-06-10 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.10346
53 | 109194 | #SMART20 - N. PARHAM RD TRAFFIC SIGNAL AND SIDEWALK PROJECT | 9999 | Secondary | Safety | VDOT | Henrico County | ASHLAND | Richmond | Richmond:Henrico County | Infrastructure Investment Division | Evan Roberts | Evan.Roberts@vdot.virginia.gov | (804) 609-5427 | Evan Roberts | Evan.Roberts@vdot.virginia.gov | (804) 609-5427 | Steve Bandura | ban03@henrico.us | (804) 501-5985 | 1 | 2020 | 0 | FY2024 | 4460000 | 5556990 | NO DATES SET YET-PE OPEN | R | Determine Requirements milestone is 40 days past the expected completion date | Y | Project estimate is less than $5M and is up to 20% over budget | [5 empty] | 2020-02-03 | 2019-02-22 | 2020-02-14 | 2019-03-01 | G | 2020-02-18 |  | 2021-01-12 |  | R | [5 empty] | 2021-11-15 |  | 2021-11-30 |  | G | 2023-03-10 |  | 2023-03-23 |  | G | 2023-08-15 |  | 2024-02-26 |  | G | 2023-04-10 |  | 2023-10-11 |  | G | 2022-08-22 |  | 2023-03-03 |  | G | [5 empty] | 2024-03-12 |  | 2024-03-12 |  | G | 2024-05-31 |  | 2024-05-31 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.13383
54 | 109367 | Town Run Ln. Left Turn Lane at Stickley Dr.-Frederick County | 1012 | Secondary | Reconstruction w/o Added Capacity | VDOT | Frederick County | EDINBURG | Staunton | Winchester:Frederick County | Infrastructure Investment Division | Clifton Balderson | clifton.balderson@dbiservices.com | (540) 460-1313 | John-Allen L Ennis | JohnAllen.Ennis@VDOT.Virginia.gov | (540) 332-9118 |  |  |  | 0 |  | 0 | FY2020 | 150000 | 220000 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 85 days early | R | Project estimate is less than $5M and is 20% or more over budget | [5 empty] | 2017-10-02 | 2017-10-02 | 2017-10-13 | 2017-10-13 | G | 2017-10-17 | 2017-10-17 | 2018-02-27 | 2018-02-27 | G | [5 empty] | 2018-12-13 | 2018-05-18 | 2019-03-13 | 2018-08-13 | G | 2018-10-02 | 2018-10-02 | 2018-10-02 | 2018-10-02 | G | 2018-08-07 | 2018-08-07 | 2018-08-07 | 2018-08-07 | G | 2018-10-02 | 2018-10-02 | 2018-10-02 | 2018-10-02 | G | [10 empty] | 2019-06-11 | 2019-03-26 | 2019-06-11 | 2019-03-26 | G | 2019-08-01 | 2019-05-28 | 2019-08-21 | 2019-05-28 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | SAAP CONTRACT | 1 | 0 | 0.084535
55 | 109812 | INNOVATION TECH. PARK TRAILS/SIDEWALKS | 0840 | Secondary | Facilities for Pedestrians and Bicycles | Locally | Prince William County | MANASSAS | Northern Virginia | Northern Virginia:Prince William County | Infrastructure Investment Division | Amir Salahshoor | A.Salahshoor@VDOT.Virginia.gov | (703) 259-1957 | Veljibhai M Desai | Veljibhai.Desai@vdot.virginia.gov | (703) 259-2927 | Mary Ankers | mankers@pwcgov.org | (703) 792-4228 | 0 |  | 0 | FY2020 | 1858845 | 1931711 | CONSTRUCTION COMPLETED | R | Start Delivery milestone finished 166 days late | Y | Project estimate is less than $5M and is up to 20% over budget | 2016-11-30 | 2016-11-30 | 2017-02-28 | 2017-02-07 | G | 2017-03-01 | 2017-02-08 | 2017-03-03 | 2017-02-17 | G | 2017-03-06 | 2017-07-12 | 2017-09-06 | 2018-02-06 | R | [10 empty] | 2018-09-21 | 2018-09-21 | 2018-10-11 | 2018-11-05 | R | [5 empty] | 2018-10-16 | 2018-11-06 | 2019-09-23 | 2020-03-10 | R | [10 empty] | 2019-11-07 | 2020-04-24 | 2020-01-08 | 2020-06-09 | R | 2020-01-09 | 2020-06-10 | 2020-02-21 | 2020-08-05 | R | Project is behind on current milestone, but expected to complete on time | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.34686
56 | 110822 | #SGR18LB - Local RT 3 (BUS) RAPP RIVER, BR REPLAC, ID18073 | 0003 | Primary | Bridge Rehab w/o Added Capacity | VDOT | Fredericksburg | FREDERICKSBURG | Fredericksburg | Fredericksburg:Fredericksburg | Infrastructure Investment/Asset Management Division | Annette F Adams | Annette.Adams@VDOT.Virginia.gov | (540) 372-3583 | Robert Galen Ridgell | Robert.Ridgell@vdot.virginia.gov | (540) 372-3549 |  |  |  | 0 |  | 1 | FY2021 | 1707639 | 2515143 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 134 days early | R | Project estimate is less than $5M and is 20% or more over budget | [10 empty] | 2020-07-06 | 2018-05-15 | 2020-07-10 | 2019-07-30 | G | [35 empty] | 2020-01-07 | 2020-01-07 | 2020-01-07 | 2020-01-07 | G | 2020-06-30 | 2020-04-21 | 2020-09-02 | 2020-04-21 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.16016
57 | 111832 | ROADWAY DEPARTURE CRASH MITIGATION ROUND 2- NOVA | 0000 | Primary | Safety | VDOT | Northern Virginia District-wide |  | Northern Virginia | Northern Virginia:Northern Virginia District-wide | Infrastructure Investment Division | Waqar A Siddiqui | Sid.Siddiqui@VDOT.Virginia.gov | (703) 259-3225 | Anwar A Ansari | Anwar.Ansari@VDOT.Virginia.gov | (703) 334-0204 |  |  |  | 0 |  | 0 | FY2019 | 500000 | 500000 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 88 days early | G | Project is on budget | [5 empty] | 2017-07-25 | 2017-07-12 | 2017-08-07 | 2017-07-26 | G | 2017-08-08 | 2017-09-27 | 2018-04-04 | 2018-01-25 | G | [5 empty] | 2018-01-19 | 2017-12-13 | 2018-02-01 | 2017-12-27 | G | [5 empty] | 2018-02-07 | 2018-01-03 | 2018-02-07 | 2018-01-03 | G | [15 empty] | 2018-05-08 | 2018-05-08 | 2018-05-15 | 2018-05-08 | G | 2018-08-17 | 2018-07-16 | 2018-10-12 | 2018-07-16 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.068056
58 | 112940 | Memorial Drive Improvements | 0000 | Urban | Reconstruction w/o Added Capacity | Locally | Luray | HARRISONBURG | Staunton | NonMPO:NonMPO | Local Assistance Division | Michael S Fulcher | Michael.Fulcher@VDOT.Virginia.gov | (540) 332-2243 | Jamison Brown | Jamison.Brown@vdot.virginia.gov | (540) 332-7389 | Bryan Chrisman | bchrisman@townofluray.com |  | 0 |  | 0 | FY2022 | 3154170 | 3154170 | ACTIVITY DATES SET | R | Start Purchasing Right-of-Way milestone is 205 days past the expected completion date | G | Project is on budget | 2018-10-31 | 2018-10-31 | 2019-01-31 | 2019-01-07 | G | 2019-02-01 | 2019-02-01 | 2019-02-05 | 2019-02-05 | G | 2019-02-06 | 2019-02-06 | 2019-08-09 | 2019-08-09 | G | [10 empty] | 2020-07-01 |  | 2020-07-31 |  | R | [5 empty] | 2020-08-04 |  | 2021-09-16 |  | G | 2021-02-15 | 2021-02-10 | 2021-10-14 |  | G | [5 empty] | 2021-10-04 |  | 2021-12-15 |  | G | 2022-03-10 |  | 2022-03-10 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.089826
59 | 113181 | KING GEORGE MIDDLE SCHOOL TURN LANES | 0003 | Primary | Safety | Locally | King George County | FREDERICKSBURG | Fredericksburg | NonMPO:NonMPO | Local Assistance Division | Michael T Coffey | MichaelT.Coffey@vdot.virginia.gov | (540) 899-4225 | Michael T Coffey | MichaelT.Coffey@vdot.virginia.gov | (540) 899-4225 | Travis Quesenberry | tquesenberry@co.kinggeorge.state.va.us | (540) 775-8467 | 0 |  | 0 | FY2020 | 316000 | 316000 | CONSTRUCTION STARTED | R | Start Delivery milestone finished 209 days late | G | Project is on budget | 2018-06-18 | 2018-08-13 | 2018-09-11 | 2018-12-04 | R | [5 empty] | 2018-06-18 | 2018-12-04 | 2018-06-29 | 2019-03-26 | R | [25 empty] | 2018-07-02 | 2018-07-02 | 2018-09-25 | 2018-09-25 | G | [5 empty] | 2019-05-01 | 2019-04-19 | 2019-06-19 | 2019-04-21 | G | 2019-09-09 | 2019-04-21 | 2019-12-19 | 2020-07-15 | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.23332
60 | 113328 | ROUTE 293 - (MAIN STREET) - RECONSTRUCTION | 9999 | Urban | Reconstruction w/o Added Capacity | Locally | Danville | HALIFAX | Lynchburg | Danville:Danville | Local Assistance Division | Sharon S White | Sharon.White@VDOT.Virginia.gov | (434) 856-8220 | Sharon S White | Sharon.White@VDOT.Virginia.gov | (434) 856-8220 | Brian Dunevant, P.E. | dunevbl@danvilleva.gov | (434) 799-5019 | 0 |  | 0 | FY2020 | 700000 | 700000 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 321 days early | Y | Estimate not current | 2019-01-31 | 2018-11-05 | 2019-04-25 | 2018-11-05 | G | 2019-04-26 | 2018-11-06 | 2019-04-30 | 2018-11-08 | G | 2019-05-01 | 2018-11-09 | 2019-11-04 | 2018-12-17 | G | [10 empty] | 2019-03-06 | 2019-03-06 | 2019-03-26 | 2019-03-06 | G | [5 empty] | 2019-03-28 | 2019-03-08 | 2020-01-07 | 2019-03-08 | G | [10 empty] | 2020-01-27 | 2019-04-08 | 2020-02-24 | 2019-05-03 | G | 2020-05-12 | 2019-06-26 | 2020-05-12 | 2019-06-26 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.070176
61 | 113688 | MAPLE AVE. IMPROVEMENTS - PHASE 3 |  | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Covington | LEXINGTON | Staunton | NonMPO:NonMPO | Local Assistance Division | Susan E Hammond | Susan.Hammond@VDOT.Virginia.gov | (540) 462-6990 | Jamison Brown | Jamison.Brown@vdot.virginia.gov | (540) 332-7389 | City of Covington | rdouglas@covington.va.us | (540) 965-5300 | 0 |  | 0 | FY2022 | 872286 | 872286 | ACTIVITY DATES SET | G | Determine Requirements milestone finished 624 days early | Y | Estimate not current | 2021-02-01 | 2018-09-28 | 2021-04-26 | 2018-12-27 | G | 2021-04-27 | 2019-07-11 | 2021-04-29 | 2019-07-19 | G | 2021-04-30 | 2019-04-19 | 2021-11-03 | 2020-02-18 | G | [35 empty] | 2021-04-27 |  | 2021-05-24 |  | G | 2021-08-12 |  | 2021-08-12 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.39136
62 | 113698 | #SGR19LB??- Elwood Road over Kingsale Swamp | 0613 | Urban | Bridge Replacement w/ Added Capacity | Locally | Suffolk | NORFOLK | Hampton Roads | Hampton Roads:Suffolk | Infrastructure Investment Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Johndel A Alcaide | John.Alcaide@vdot.virginia.gov | (757) 956-3098 | L. Hansen | lhansen@suffolkva.us | (757) 514-7687 | 0 |  | 1 | FY2024 | 1199000 | 1199000 | NO DATES SET YET-PE OPEN | G | Start Development milestone finished 506 days early | Y | Estimate not current | 2021-09-15 | 2019-09-11 | 2021-12-13 | 2019-12-09 | G | 2021-12-14 | 2020-07-14 | 2021-12-16 | 2020-07-28 | G | 2021-12-17 |  | 2022-06-24 |  | G | [10 empty] | 2023-04-21 |  | 2023-05-11 |  | G | [5 empty] | 2023-05-15 |  | 2024-02-27 |  | G | 2022-08-02 |  | 2023-04-10 |  | G | [5 empty] | 2024-03-14 |  | 2024-04-10 |  | G | 2024-06-28 |  | 2024-06-28 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.14523
63 | 113747 | Mercury Blvd - Pedestrian Improvements | 0258 | Primary | Facilities for Pedestrians and Bicycles | Locally | Hampton | WILLIAMSBURG | Hampton Roads | Hampton Roads:Hampton | Infrastructure Investment Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Derrick Williams | Derrick.Williams@vdot.virginia.gov | (757) 956-3097 | Lynne M. Keenan | lyne.keenan@hampton.gov | (757) 727-6859 | 0 |  | 0 | FY2024 | 590000 | 590000 | NO DATES SET YET | G | Agreement with Locality milestone is 285 days ahead of the expected completion date | Y | Estimate not current | 2021-09-07 |  | 2021-12-03 |  | G | 2021-12-06 |  | 2021-12-08 |  | G | 2021-12-09 |  | 2022-06-16 |  | G | [25 empty] | 2022-07-25 |  | 2023-03-31 |  | G | [5 empty] | 2023-04-28 |  | 2023-05-25 |  | G | 2023-08-15 |  | 2023-08-15 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.19618
64 | 113863 | Resurface Statler Blvd (Rte. 261N) - Primary Extension | 0261 | Urban | Resurfacing | Locally | Staunton | HARRISONBURG | Staunton | SAW:Staunton | Local Assistance Division | Donald F Komara | Donald.Komara@VDOT.Virginia.gov | (540) 434-2587 | Michael S Fulcher | Michael.Fulcher@VDOT.Virginia.gov | (540) 332-2243 | Steve Yancey | yanceysc@ci.staunton.va.us | (540) 332-3892 | 0 |  | 1 | FY2020 | 104000 | 104000 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 412 days early | G | Project is on budget | 2018-12-31 | 2018-10-05 | 2019-03-28 | 2018-11-05 | G | 2019-03-29 | 2018-11-06 | 2019-04-02 | 2019-03-01 | G | 2019-04-03 | 2019-03-04 | 2019-10-04 | 2019-03-11 | G | [25 empty] | 2019-03-12 | 2019-03-10 | 2019-11-08 | 2019-03-12 | G | [5 empty] | 2020-01-21 | 2019-03-07 | 2020-02-18 | 2019-03-20 | G | 2020-05-06 | 2019-03-20 | 2020-05-06 | 2019-03-21 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.063078
65 | 114097 | DISTRICTWIDE - HIGH FRICTION SURFACE TREATMENT | 9999 | Primary | Safety | VDOT | Lynchburg District-wide |  | Lynchburg | NonMPO:NonMPO | Infrastructure Investment Division | Keith M Rider | Keith.Rider@VDOT.Virginia.gov | (434) 856-8145 | Keith M Rider | Keith.Rider@VDOT.Virginia.gov | (434) 856-8145 |  |  |  | 0 |  | 0 | FY2023 | 2148000 | 2148000 | NO DATES SET YET | G | Determine Requirements milestone is 515 days ahead of the expected completion date | G | Project is on budget | [10 empty] | 2022-07-15 |  | 2022-07-21 |  | G | [25 empty] | 2022-07-15 |  | 2023-01-25 |  | G | [5 empty] | 2023-02-14 |  | 2023-02-14 |  | G | 2023-05-05 |  | 2023-05-05 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.11925
66 | 115364 | City of Norfolk 894 N Military Hwy - Paving | 0013 | Urban | Restoration and Rehabilitation | Locally | Norfolk | NORFOLK | Hampton Roads | Hampton Roads:Norfolk | Local Assistance Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Derrick Williams | Derrick.Williams@vdot.virginia.gov | (757) 956-3097 | Eric Berger | eric.berger@norfolk.gov | (757) 823-4039 | 0 |  | 0 | FY2020 | 537451 | 537451 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 30 days early | G | Project is on budget | 2019-10-03 | 2019-10-03 | 2020-01-02 | 2019-12-30 | G | [5 empty] | 2019-10-03 | 2019-10-03 | 2019-10-16 | 2020-01-06 | R | [35 empty] | 2020-01-16 | 2020-01-15 | 2020-02-19 | 2020-01-15 | G | 2020-05-07 | 2020-04-07 | 2020-05-07 | 2020-04-07 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.10905
67 | 115795 | #I81CIP EXTEND ACCELERATION LANE EXIT 89 (ID #29) | 0081 | Interstate | Safety | VDOT | Pulaski County | CHRISTIANSBURG | Salem | NonMPO:NonMPO | Infrastructure Investment Division | Thomas W Digiulian | Thomas.DiGiulian@VDOT.Virginia.gov | (540) 387-5356 | Marvin D Mann | M.Mann@VDOT.Virginia.gov | (540) 378-5055 |  |  |  | 0 |  | 0 | FY2021 | 2870000 | 915510 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 279 days early | G | Project is on budget | [5 empty] | 2019-08-01 | 2019-07-25 | 2019-08-14 | 2019-08-06 | G | 2019-08-15 | 2019-08-07 | 2020-04-10 | 2020-01-15 | G | [5 empty] | 2020-07-10 | 2020-01-15 | 2020-07-10 | 2020-02-19 | G | [5 empty] | 2019-12-20 | 2019-12-20 | 2019-12-20 | 2019-12-20 | G | [5 empty] | 2020-07-13 | 2020-02-18 | 2020-09-09 | 2020-02-18 | G | [5 empty] | 2020-12-08 | 2020-03-10 | 2020-12-08 | 2020-03-10 | G | 2021-03-04 | 2020-05-29 | 2021-03-04 | 2020-05-29 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.085066
68 | 116976 | #SGR21VP Harrisonburg Res. Plant Mix Schedule (PM-8N-21) | 9999 | Interstate | Resurfacing | VDOT | Rockingham County | HARRISONBURG | Staunton | NonMPO:NonMPO | Infrastructure Investment/Asset Management Division | Joel D Denunzio | Joel.DeNunzio@VDOT.virginia.gov | (540) 332-9093 | Mark W Hisey | Mark.Hisey@VDOT.Virginia.gov | (540) 280-4820 |  |  |  | 0 |  | 1 | FY2021 | 2709043 | 2709043 | ADVERTISED | G | Solicit Bids milestone finished 91 days early | G | Project is on budget | [10 empty] | 2020-06-01 | 2020-09-29 | 2020-06-05 | 2020-09-30 | R | 2020-10-15 | 2020-10-15 | 2020-11-13 | 2020-10-19 | G | [30 empty] | 2020-12-08 | 2020-12-08 | 2021-03-09 | 2020-12-08 | G | 2021-05-27 |  | 2021-05-27 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.071023
69 | 116991 | #SGR21VP PM7D-967-F21,P401 Interstate Plant Mix | 9999 | Interstate | Resurfacing | VDOT | Culpeper District-wide |  | Culpeper | NonMPO:NonMPO | Infrastructure Investment/Asset Management Division | Donald R Schoch | Donald.Schoch@vdot.virginia.gov | (540) 829-7500 | Donald R Schoch | Donald.Schoch@vdot.virginia.gov | (540) 829-7500 |  |  |  | 0 |  | 1 | FY2021 | 1148871 | 1148871 | ADVERTISED | G | Solicit Bids milestone finished on-time | G | Project is on budget | [10 empty] | 2021-03-01 | 2020-11-24 | 2021-03-05 | 2021-01-22 | G | [35 empty] | 2021-02-09 | 2021-02-09 | 2021-02-09 | 2021-02-09 | G | 2021-04-30 |  | 2021-04-30 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.089228
70 | 113284 | PRINCE HENRY AVE & PELHAM ST - RECONSTRUCTION |  | Urban | Reconstruction w/o Added Capacity | Locally | Hopewell | PETERSBURG | Richmond | Tri-Cities:Hopewell | Local Assistance Division | James Shepherd | James.Shepherd@vdot.virginia.gov | (804) 609-5305 | Brian J Lokker | Brian.Lokker@VDOT.Virginia.gov | (804) 524-6010 | Austin Anderson | AANDERSON@HOPEWELLVA.GOV | (804) 541-2379 | 0 |  | 0 | FY2020 | 371140 | 371140 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished on-time | G | Project is on budget | 2018-07-02 | 2018-08-13 | 2018-09-25 | 2018-08-14 | G | 2018-09-26 | 2018-09-25 | 2018-11-07 | 2018-09-26 | G | 2018-11-08 | 2018-09-27 | 2019-02-08 | 2019-02-05 | G | [35 empty] | 2019-06-10 | 2019-06-10 | 2019-07-18 | 2019-07-18 | G | 2019-07-19 | 2019-07-19 | 2019-09-30 | 2019-09-30 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.071287
71 | 113576 | DASH TECHNOLOGY | 9999 | Public Transportation | Transit | Locally | Alexandria | FAIRFAX | Northern Virginia | Northern Virginia:Alexandria | Infrastructure Investment Division | Amir Salahshoor | A.Salahshoor@VDOT.Virginia.gov | (703) 259-1957 | Susie X Lue | Susie.Lue@vdot.virginia.gov | (703) 259-2918 | Martin Barna | Martin.Barna@Alexandriava.gov | (703) 746-5644 | 0 |  | 0 | FY2022 | 200000 | 200000 | ACTIVITY DATES SET | R | Determine Requirements milestone finished 455 days late | G | Project is on budget | 2018-06-15 | 2018-06-15 | 2019-01-31 | 2018-09-14 | G | 2019-02-01 | 2018-09-17 | 2019-02-28 | 2018-10-29 | G | 2019-03-01 | 2020-11-16 | 2019-09-03 | 2020-12-01 | R | [35 empty] | 2020-12-11 | 2020-12-11 | 2021-04-27 |  | G | 2021-04-28 |  | 2021-09-24 |  | G | Consultant contract is still in procurement | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.17698
72 | 113695 | #SGR19LB??- Old Mill Road over Deep Creek | 9999 | Urban | Bridge Replacement w/o Added Capacity | Locally | Chesapeake | NORFOLK | Hampton Roads | Hampton Roads:Chesapeake | Infrastructure Investment Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Johndel A Alcaide | John.Alcaide@vdot.virginia.gov | (757) 956-3098 | Sam Sawan | sawan@cityofchesapeake.net | (757) 382-8263 | 0 |  | 1 | FY2025 | 1153000 | 1153000 | NO DATES SET YET-PE OPEN | G | Start Development milestone finished 1009 days early | Y | Estimate not current | 2021-09-16 | 2018-10-12 | 2021-12-14 | 2019-01-11 | G | 2021-12-15 | 2019-01-14 | 2021-12-17 | 2019-03-14 | G | 2021-12-20 |  | 2022-06-27 |  | G | [10 empty] | 2023-04-24 |  | 2023-05-12 |  | G | [5 empty] | 2023-05-16 |  | 2024-02-28 |  | G | 2022-08-03 |  | 2023-04-11 |  | G | [5 empty] | 2024-03-15 |  | 2024-04-11 |  | G | 2024-07-01 |  | 2024-07-01 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.13647
73 | 113738 | RTE 635 - RURAL RUSTIC (SURFACE TREAT NON-HARDSURFACE ROAD) | 0635 | Secondary | Reconstruction w/o Added Capacity | VDOT | Orange County | LOUISA | Culpeper | NonMPO:NonMPO | Infrastructure Investment Division | Ken Connors |  |  | Bethel Kefyalew | Bethel.Kefyalew@vdot.virginia.gov | (540) 603-6015 |  |  |  | 0 |  | 0 | FY2026 | 320000 | 320000 | NO DATES SET YET | G | Start Development milestone is 964 days ahead of the expected completion date | G | Project is on budget | [5 empty] | 2023-10-02 |  | 2023-10-13 |  | G | 2023-10-17 |  | 2024-06-11 |  | G | [5 empty] | 2025-02-20 |  | 2025-04-02 |  | G | [5 empty] | 2025-07-17 |  | 2025-11-07 |  | G | [5 empty] | 2025-07-01 |  | 2025-10-01 |  | G | [5 empty] | 2025-11-10 |  | 2025-11-10 |  | G | 2026-02-06 |  | 2026-02-06 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | SAAP CONTRACT | 0 | 0 | 0.094343
74 | 113823 | Denbigh Boulevard Sidewalk | 0173 | Urban | Facilities for Pedestrians and Bicycles | Locally | Newport News | WILLIAMSBURG | Hampton Roads | Hampton Roads:Newport News | Infrastructure Investment Division | Susan Wilson | Susan.Wilson@vdot.virginia.gov | (757) 956-3099 | Chessica Villaflores | Chessica.Villaflores@vdot.virginia.gov | (757) 956-3094 | Bryan Stilley, P.E. | bstilley@nnva.gov | (757) 926-8699 | 0 |  | 0 | FY2025 | 515560 | 515560 | NO DATES SET YET | G | Agreement with Locality milestone is 222 days ahead of the expected completion date | G | Project is on budget | 2021-07-01 |  | 2021-10-01 |  | G | 2021-10-04 |  | 2021-10-15 |  | G | 2021-10-19 |  | 2022-04-28 |  | G | [10 empty] | 2023-05-02 |  | 2023-05-22 |  | G | [5 empty] | 2023-05-24 |  | 2024-03-07 |  | G | 2022-06-06 |  | 2023-02-10 |  | G | [5 empty] | 2024-03-25 |  | 2024-04-19 |  | G | 2024-07-10 |  | 2024-07-10 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.25124
75 | 114026 | RTE 29 - DYNAMIC FLASHERS AT RTE 6 (SOUTHERN INT.) | 6029 | Primary | Safety | VDOT | Nelson County | APPOMATTOX | Lynchburg | NonMPO:NonMPO | Infrastructure Investment Division | Anthony D Rago | anthony.rago@vdot.virginia.gov | (434) 856-8308 | Bernard S Grinnell | Sean.Grinnell@VDOT.Virginia.gov | (540) 375-0148 |  |  |  | 0 |  | 0 | FY2019 | 170848 | 170848 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished on-time | G | Project is on budget | [5 empty] | 2018-07-02 | 2018-07-11 | 2018-07-02 | 2018-08-03 | R | 2018-07-03 | 2018-08-06 | 2018-11-08 | 2018-11-08 | G | [5 empty] | 2018-11-05 | 2018-11-05 | 2018-11-09 | 2018-11-09 | G | [25 empty] | 2018-12-04 | 2018-12-04 | 2018-12-14 | 2018-12-14 | G | 2018-12-17 | 2018-12-17 | 2018-12-28 | 2018-12-28 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | WORK/TASK ORDER | 1 | 0 | 0.097884
76 | 114103 | ROUTE 7/ROUTE 9 INTERCHANGE MODIFICATIONS | 6007 | Primary | Traffic Management/Engineering | VDOT | Loudoun County | LEESBURG | Northern Virginia | Northern Virginia:Loudoun County | Infrastructure Investment Division | Kimberly Mccool | Kimberly.McCool@vdot.virginia.gov | (703) 259-3220 | William C Britt | Calvin.Britt@VDOT.Virginia.gov | (703) 259-2961 | Susan Glass, Loudoun County DTCI | susan.glass@loudoun.gov | (703) 777-0251 | 0 |  | 0 | FY2023 | 2002869 | 2002869 | NO DATES SET YET-PE OPEN | R | Determine Requirements milestone is 573 days past the expected completion date | G | Project is on budget | [5 empty] | 2018-08-15 | 2018-08-15 | 2018-08-28 | 2018-09-12 | R | 2018-08-29 | 2018-09-12 | 2019-07-29 |  | R | [5 empty] | 2020-06-03 |  | 2020-06-16 |  | R | 2021-09-21 |  | 2021-10-04 |  | G | 2022-03-07 |  | 2022-09-07 |  | G | 2021-10-21 |  | 2022-05-02 |  | G | 2021-03-12 | 2019-01-02 | 2021-09-14 | 2019-01-02 | G | [5 empty] | 2022-09-13 |  | 2022-09-13 |  | G | 2022-12-07 |  | 2022-12-07 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.1509
77 | 115532 | #SMART20 - WEST END TRANSITWAY CORRIDOR INVESTMENTS | 9999 | Urban | Safety | Locally | Alexandria | FAIRFAX | Northern Virginia | Northern Virginia:Alexandria | Infrastructure Investment Division | Nassre Y Obeed | Nassre.Obeed@VDOT.Virginia.gov | (703) 259-1723 | Marlene Pinedo Fortich | Sofia.Pinedo@vdot.virginia.gov | (703) 259-1724 | Steve Sindiong | steve.sindiong@alexandriava.gov | (703) 746-4047 | 1 | 2020 | 0 | FY2029 | 30104000 | 30104000 | NO DATES SET YET | G | Agreement with Locality milestone is 1103 days ahead of the expected completion date | G | Project is on budget | 2023-08-01 |  | 2024-02-29 |  | G | 2024-03-01 |  | 2024-03-29 |  | G | 2024-11-01 |  | 2025-11-26 |  | G | [10 empty] | 2027-01-04 |  | 2027-02-02 |  | G | [5 empty] | 2027-02-04 |  | 2027-11-30 |  | G | 2028-01-03 |  | 2028-02-29 |  | G | [5 empty] | 2028-04-03 |  | 2028-07-31 |  | G | 2028-10-19 |  | 2029-03-30 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.33295
78 | 116238 | 1831 Southampton Insurrection Tour - Wayfinding Signage |  | Enhancement | Scenic or Historic Highway Programs | Locally | Southampton County | FRANKLIN | Hampton Roads | NonMPO:NonMPO | Local Assistance Division | Darryll Lewis |  |  | Keisha Wilkins | Keisha.Wilkins@vdot.virginia.gov | (757) 956-3110 | Southampton County | mjohnson@southamptoncounty.org | (757) 653-3015 | 0 |  | 0 | FY2020 | 19500 | 29057 | ADVERTISED | R | Start Delivery milestone is 320 days past the expected completion date | R | Project estimate is less than $5M and is 20% or more over budget | 2019-09-03 | 2019-09-03 | 2019-11-27 | 2019-09-03 | G | [5 empty] | 2019-09-03 | 2019-09-03 | 2019-09-16 | 2019-09-12 | G | [35 empty] | 2019-12-17 | 2020-02-28 | 2020-01-15 | 2020-06-21 | R | 2020-04-07 | 2020-09-03 | 2020-04-07 |  | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.31642
79 | 116979 | #SGR21VP Harrisonburg Res. Plant Mix Schedule (PM-8Q-21) | 9999 | Interstate | Resurfacing | VDOT | Augusta County | HARRISONBURG | Staunton | NonMPO:NonMPO | Infrastructure Investment/Asset Management Division | Joel D Denunzio | Joel.DeNunzio@VDOT.virginia.gov | (540) 332-9093 | Mark W Hisey | Mark.Hisey@VDOT.Virginia.gov | (540) 280-4820 |  |  |  | 0 |  | 1 | FY2021 | 1871479 | 1746603 | ADVERTISED | G | Solicit Bids milestone finished 84 days early | G | Project is on budget | [10 empty] | 2020-06-01 | 2020-09-29 | 2020-06-05 | 2020-09-30 | R | 2020-10-15 | 2020-10-15 | 2020-11-13 | 2020-10-19 | G | [30 empty] | 2020-12-08 | 2020-12-15 | 2021-03-09 | 2020-12-15 | G | 2021-05-27 |  | 2021-05-27 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.070441
80 | 117061 | #SGR21VP CY21 GRAYSON WYTHE PRIMARY PM1J | 9999 | Primary | Resurfacing | VDOT | Bristol District-wide |  | Bristol | NonMPO:NonMPO | Infrastructure Investment Division | James B Parsons | James.Parsons@VDOT.Virginia.gov | (276) 696-3288 | David G Morrison | David.Morrison@VDOT.Virginia.gov | (276) 696-3328 |  |  |  | 0 |  | 1 | FY2021 | 5063245 | 5063245 | ADVERTISED | Y | Start Delivery milestone is 4 days ahead of the expected completion date and there is a risk of missing this milestone date | G | Project is on budget | [10 empty] | 2021-01-27 | 2021-01-28 | 2021-02-02 | 2021-01-28 | G | [35 empty] | 2020-12-01 | 2020-12-01 | 2020-12-01 | 2020-12-01 | G | 2021-02-25 |  | 2021-02-25 |  | Y |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.074091
81 | 117214 | FY 21 Centerline Rumble Strips | 9999 | Primary | Safety | VDOT | Salem District-wide |  | Salem | Roanoke:Salem District-wide | Infrastructure Investment/Asset Management Division | Bernard S Grinnell | Sean.Grinnell@VDOT.Virginia.gov | (540) 375-0148 | Jason W Knight | Jay.Knight@vdot.virginia.gov | (540) 375-0152 |  |  |  | 0 |  | 0 | FY2023 | 1013550 | 1013550 | ADVERTISED | G | Solicit Bids milestone finished 399 days early | G | Project is on budget | [5 empty] | 2020-06-01 | 2020-06-01 | 2020-06-12 | 2020-06-01 | G | 2020-06-15 | 2020-06-01 | 2020-07-13 | 2020-07-09 | G | [35 empty] | 2022-01-11 | 2020-12-08 | 2022-01-11 | 2020-12-08 | G | 2022-07-20 |  | 2022-07-20 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.12233
82 | 117972 | #81 CIP DETOUR IMPROVEMENTS - CITY OF SALEM & CITY OF RNKE | 9999 | Miscellaneous | Traffic Management/Engineering | VDOT | Salem | SALEM | Salem | Roanoke:Salem | Infrastructure Investment Division | Jennifer Robertson | Jennifer.Robertson@vdot.virginia.gov | (540) 375-0122 | Jennifer Robertson | Jennifer.Robertson@vdot.virginia.gov | (540) 375-0122 |  |  |  | 0 |  | 0 | FY2024 | 2800000 | 2800000 | NO DATES SET YET-PE OPEN | G | Obtained Permits milestone finished 817 days early | G | Project is on budget | [5 empty] | 2020-11-02 | 2020-11-02 | 2020-11-23 | 2020-11-23 | G | 2020-11-24 | 2020-11-24 | 2021-09-27 |  | G | [5 empty] | 2022-05-02 |  | 2022-05-27 |  | G | [5 empty] | 2023-01-25 |  | 2023-05-24 |  | G | [5 empty] | 2022-10-12 | 2020-12-23 | 2023-03-20 | 2020-12-23 | G | [5 empty] | 2023-06-13 |  | 2023-06-13 |  | G | 2023-08-31 |  | 2023-08-31 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 1 | 0.23349
83 | 118216 | GLADE SPRING PAVILION POINT SIDEWALK |  | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Glade Spring | ABINGDON | Bristol | NonMPO:NonMPO | Local Assistance Division | John W Bechtold | John.Bechtold@vdot.virginia.gov | (276) 696-3365 | Roger L Musser | Roger.Musser@VDOT.Virginia.gov | (276) 696-3260 | SCOTT MCCOY | smccoy@mrpdc.org | (276) 783-5103 | 0 |  | 0 | FY2025 | 281820 | 281820 | NO DATES SET YET | G | Agreement with Locality milestone is 464 days ahead of the expected completion date | G | Project is on budget | 2022-01-24 |  | 2022-05-31 |  | G | 2022-06-01 |  | 2022-06-21 |  | G | 2022-12-30 |  | 2023-04-26 |  | G | [25 empty] | 2024-04-22 |  | 2024-09-18 |  | G | [5 empty] | 2024-11-18 |  | 2024-12-17 |  | G | 2025-03-12 |  | 2025-03-12 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.24695
84 | 118460 | FOX MILL ROAD & PINECREST ROAD - INTERSECTION IMPROVEMENTS | 0665 | Secondary | Traffic Management/Engineering | VDOT | Fairfax County | FAIRFAX | Northern Virginia | Northern Virginia:Fairfax County | Infrastructure Investment Division | Andrew G Beacher | Andrew.Beacher@vdot.virginia.gov | (703) 259-2239 | Christopher Barksdale | Chris.Barksdale@vdot.virginia.gov | (703) 259-2768 |  |  |  | 0 |  | 0 | FY2024 | 5650000 | 5650000 | NO DATES SET YET | R | Start Development milestone is 89 days past the expected completion date | G | Project is on budget | 2020-12-14 |  | 2021-04-23 |  | G | 2020-11-03 |  | 2020-11-24 |  | R | 2020-11-25 |  | 2021-09-28 |  | G | [5 empty] | 2022-05-03 |  | 2022-05-31 |  | G | 2023-01-25 |  | 2023-03-01 |  | G | 2023-07-28 |  | 2023-11-30 |  | G | 2023-03-16 |  | 2023-08-11 |  | G | 2023-04-17 |  | 2023-09-13 |  | G | [5 empty] | 2023-12-12 |  | 2023-12-12 |  | G | 2024-03-06 |  | 2024-03-06 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.13036
85 | 104957 | #HB2.FY17 RTE 656 - SLIDING HILL ROAD CORRIDOR | 0656 | Secondary | Reconstruction w/ Added Capacity | Locally | Hanover County | ASHLAND | Richmond | Richmond:Hanover County | Infrastructure Investment Division | Brian J Lokker | Brian.Lokker@VDOT.Virginia.gov | (804) 524-6010 | Brian J Lokker | Brian.Lokker@VDOT.Virginia.gov | (804) 524-6010 | Randy Hardman | wrhardman@hanovercounty.gov | (804) 365-6181 | 1 | 2017 | 0 | FY2020 | 11410204 | 11373620 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 100 days early | G | Project is on budget | 2014-03-31 | 2014-03-14 | 2014-03-31 | 2014-03-14 | G | 2014-03-31 | 2014-04-16 | 2014-03-31 | 2014-04-16 | R | 2015-02-24 | 2017-01-11 | 2016-12-30 | 2017-01-11 | R | [5 empty] | 2017-04-13 | 2017-04-13 | 2017-04-13 | 2017-04-13 | G | 2017-06-05 | 2017-06-05 | 2017-06-13 | 2017-06-13 | G | [5 empty] | 2017-08-17 | 2017-08-17 | 2019-05-20 | 2018-10-11 | G | 2019-05-21 | 2015-11-23 | 2019-06-13 | 2018-03-12 | G | [5 empty] | 2019-07-05 | 2019-05-03 | 2019-07-05 | 2019-05-08 | G | 2019-08-15 | 2019-06-19 | 2019-11-14 | 2019-08-06 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.21131
86 | 105806 | IVY ROAD FY15RS (CONST. SIDEWALKS, BIKELANES, & PAVED SHLDRS | 0250 | Primary | Safety | Locally | Albemarle County | CHARLOTTESVILLE | Culpeper | Charlottesville:Albemarle County | Local Assistance Division | Gregory J Cooley | Gregory.Cooley@vdot.virginia.gov | (434) 906-7979 | Thomas Fitzpatrick | Thomas.Fitzpatrick@vdot.virginia.gov |  | Jack Kelsey | jkelsey@albemarle.org | (434) 872-4501 | 0 |  | 0 | FY2021 | 2478000 | 2478000 | ADVERTISED | R | Start Delivery milestone is 93 days past the expected completion date | G | Project is on budget | 2014-02-03 | 2014-02-01 | 2014-08-30 | 2014-07-28 | G | 2015-03-01 | 2014-07-28 | 2015-03-01 | 2014-07-28 | G | 2015-03-31 | 2016-12-08 | 2018-10-01 | 2018-08-15 | G | [10 empty] | 2018-08-16 | 2018-07-02 | 2019-05-16 | 2018-07-02 | G | [5 empty] | 2019-05-17 | 2018-07-03 | 2020-07-29 | 2020-10-23 | R | [10 empty] | 2020-07-31 | 2020-10-23 | 2020-10-05 | 2020-10-30 | R | 2020-10-07 |  | 2020-11-20 |  | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.35533
87 | 107405 | INSTALL SIGNAL @ BLACKBURN RD - RIPPON BLVD INTERSECTION | 0638 | Secondary | Traffic Management/Engineering | VDOT | Prince William County | MANASSAS | Northern Virginia | Northern Virginia:Prince William County | Infrastructure Investment Division | Angel Tao | Angel.Tao@vdot.virginia.gov | (703) 259-2377 | Jessica Paris | Jessica.Paris@vdot.virginia.gov | (703) 259-2409 |  |  |  | 0 |  | 0 | FY2020 | 1496000 | 1123872 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 8 days early | G | Project is on budget | [5 empty] | 2015-09-18 | 2015-09-24 | 2015-10-01 | 2015-09-24 | G | 2015-10-02 | 2015-09-25 | 2016-08-30 | 2018-11-01 | R | 2016-11-09 | 2016-11-09 | 2017-03-03 | 2017-03-03 | G | [5 empty] | 2018-12-07 | 2018-12-07 | 2019-01-07 | 2019-02-07 | R | [5 empty] | 2019-01-08 | 2019-02-20 | 2019-08-26 | 2019-05-31 | G | [10 empty] | 2019-12-10 | 2018-09-17 | 2019-12-10 | 2019-12-10 | G | 2020-01-28 | 2020-01-10 | 2020-02-18 | 2020-02-10 | G | Project is behind on current milestone, but expected to complete on time | 2021-02-21 11:00 | 2021-02-21 06:04 | WORK/TASK ORDER | 1 | 1 | 0.22656
88 | 108005 | RTE 95 - IMPROVE TRAFFIC OPERATIONS AND SOUND WALL DESIGN | 0095 | Interstate | Other | VDOT | Richmond District-wide |  | Richmond | Richmond:Richmond District-wide | Infrastructure Investment Division | Lawrence Ramsey | Brian.Ramsey@VDOT.Virginia.gov | (804) 585-3579 | Lawrence Ramsey | Brian.Ramsey@VDOT.Virginia.gov | (804) 585-3579 |  |  |  | 0 |  | 0 | FY2019 | 2163112 | 2163112 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 168 days early | G | Project is on budget | [5 empty] | 2016-01-05 | 2016-01-05 | 2016-03-18 | 2016-03-18 | G | 2016-01-05 | 2016-01-05 | 2018-03-30 | 2018-03-29 | G | [5 empty] | 2018-03-30 | 2018-03-30 | 2018-04-23 | 2018-04-18 | G | 2018-04-23 | 2018-04-18 | 2018-04-23 | 2018-04-18 | G | [10 empty] | 2016-04-18 | 2016-04-18 | 2016-08-22 | 2016-08-22 | G | [5 empty] | 2018-09-11 | 2018-10-09 | 2019-02-12 | 2018-10-09 | G | 2019-04-04 | 2018-12-27 | 2019-06-13 | 2018-12-27 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.079569
89 | 108857 | FY 17 RS - Research Center Drive Improvements - Phase II | 0000 | Urban | Reconstruction w/o Added Capacity | Locally | Blacksburg | CHRISTIANSBURG | Salem | New River Valley:Blacksburg | Local Assistance Division | Adam J Czesnowski | Adam.Czesnowski@vdot.virginia.gov | (540) 541-1216 | Adam J Czesnowski | Adam.Czesnowski@vdot.virginia.gov | (540) 541-1216 | Randy Formica |  |  | 0 |  | 0 | FY2020 | 1392248 | 1392248 | ADVERTISED | R | Start Delivery milestone is 286 days past the expected completion date | G | Project is on budget | 2016-07-01 | 2016-07-01 | 2016-08-24 | 2016-08-24 | G | 2016-09-29 | 2016-09-29 | 2016-10-07 | 2016-10-07 | G | 2016-11-07 | 2016-11-07 | 2018-02-15 | 2018-02-01 | G | [10 empty] | 2019-05-28 | 2019-06-17 | 2019-06-17 | 2019-06-17 | G | [5 empty] | 2019-06-19 | 2019-10-30 | 2019-10-30 | 2019-10-30 | G | [10 empty] | 2019-11-01 | 2020-04-07 | 2019-11-01 | 2020-04-10 | R | 2019-11-04 |  | 2020-05-11 |  | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.1633
90 | 117018 | #SGR21VB - RTE. 1460 OVER BR BVR DAM CR (STR. 24893) - REHAB | 1460 | Secondary | Bridge Rehab w/o Added Capacity | VDOT | Bedford County | BEDFORD | Salem | Roanoke:Bedford County | Infrastructure Investment Division | Anthony T Marshall | Todd.Marshall@VDOT.Virginia.gov | (540) 387-5460 | Dana E Pauley | Dana.Pauley@VDOT.Virginia.gov | (540) 387-5476 |  |  |  | 0 |  | 1 | FY2026 | 1389918 | 1389918 | NO DATES SET YET | G | Start Development milestone is 516 days ahead of the expected completion date | G | Project is on budget | [5 empty] | 2022-07-01 |  | 2022-07-22 |  | G | 2022-07-25 |  | 2023-05-26 |  | G | [5 empty] | 2023-12-28 |  | 2024-01-29 |  | G | 2024-09-16 |  | 2024-10-18 |  | G | 2025-03-27 |  | 2025-07-25 |  | G | 2024-11-05 |  | 2025-04-10 |  | G | 2024-12-16 |  | 2025-05-16 |  | G | [5 empty] | 2025-08-12 |  | 2025-08-12 |  | G | 2025-10-31 |  | 2025-10-31 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 1 | 0.41695
91 | 117183 | Capitol Landing Road (SR143) Outfall Stream Restoration |  | Urban | Restoration and Rehabilitation | Locally | Williamsburg | WILLIAMSBURG | Hampton Roads | Hampton Roads:Williamsburg | Local Assistance Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Chessica Villaflores | Chessica.Villaflores@vdot.virginia.gov | (757) 956-3094 | Aaron Small | asmall@williamsburgva.gov | (757) 220-6140 | 0 |  | 0 | FY2024 | 411750 | 411750 | NO DATES SET YET | R | Agreement with Locality milestone is 69 days past the expected completion date | G | Project is on budget | 2020-08-04 |  | 2020-12-14 |  | R | 2020-12-15 |  | 2021-01-06 |  | R | 2021-07-15 |  | 2021-11-05 |  | G | [25 empty] | 2022-11-02 |  | 2023-04-07 |  | G | [5 empty] | 2023-06-06 |  | 2023-07-03 |  | G | 2023-09-21 |  | 2023-09-21 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.11704
92 | 117661 | #HRRR - SIGNS & PAVEMENT MARKINGS (CN ONLY) | 9999 | Miscellaneous | Safety | VDOT | Fredericksburg District-wide |  | Fredericksburg | Fredericksburg:Fredericksburg District-wide | Infrastructure Investment Division | Peter A Hedrich | Peter.Hedrich@vdot.virginia.gov | (540) 899-4540 | Sylvester C Okpala | Sylvester.Okpala@VDOT.Virginia.gov | (540) 907-8174 |  |  |  | 0 |  | 0 | FY2021 | 574000 | 656059 | AWARDED | G | Start Delivery milestone finished 51 days early | Y | Project estimate is less than $5M and is up to 20% over budget | [10 empty] | 2020-06-29 | 2020-06-29 | 2020-07-13 | 2020-07-13 | G | [35 empty] | 2020-10-13 | 2020-09-22 | 2020-10-13 | 2020-09-22 | G | 2021-01-07 | 2020-11-17 | 2021-01-07 | 2020-11-17 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.070324
93 | 118183 | #SGR21VP - Roanoke FKEY 1366 Plantation Rd NE | 0000 | Urban | Resurfacing | VDOT | Roanoke | SALEM | Salem | Roanoke:Roanoke City | Infrastructure Investment/Asset Management Division | Ibrahim M Abuawad | Ibrahim.Abuawad@vdot.virginia.gov | (217) 418-8827 | Ibrahim M Abuawad | Ibrahim.Abuawad@vdot.virginia.gov | (217) 418-8827 | Mark Jamison | mark.jamison@roanokeva.gov | (540) 853-5471 | 0 |  | 1 | FY2021 | 806599 | 806599 | NO DATES SET YET | R | Determine Requirements milestone is 9 days past the expected completion date | G | Project is on budget | [10 empty] | 2021-02-01 |  | 2021-02-12 |  | R | [35 empty] | 2021-03-09 |  | 2021-03-09 |  | Y | 2021-05-27 |  | 2021-05-27 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.14992
94 | 118408 | #SGR21LP - City of Richmond 1254 Bells Rd E |  | Urban | Resurfacing | Locally | Richmond | ASHLAND | Richmond | Richmond:Richmond | Infrastructure Investment/Asset Management Division | Olena Fecek | Olena.Fecek@vdot.virginia.gov | (804) 524-6368 | Olena Fecek | Olena.Fecek@vdot.virginia.gov | (804) 524-6368 | Kenny Horak | Kenneth.horak@richmondgov.com | (804) 646-4781 | 0 |  | 1 | FY2024 | 143296 | 143296 | NO DATES SET YET | G | Agreement with Locality milestone is 292 days ahead of the expected completion date | G | Project is on budget | 2021-08-02 | 2021-01-11 | 2021-12-10 |  | G | 2021-12-13 |  | 2022-01-04 |  | G | 2022-02-04 |  | 2022-05-27 |  | G | [25 empty] | 2023-05-24 |  | 2023-10-23 |  | G | [5 empty] | 2023-12-22 |  | 2024-01-24 |  | G | 2024-04-12 |  | 2024-04-12 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.062547
96 | 105464 | #HB2.FY17 RTE. 606 WEST - RECONSTRUCTION MUDD TAVERN ROAD | 0606 | Secondary | Reconstruction w/ Added Capacity | VDOT | Spotsylvania County | FREDERICKSBURG | Fredericksburg | Fredericksburg:Spotsylvania County | Infrastructure Investment Division | Khalil Minhas | Khalil.Minhas@vdot.virginia.gov | (540) 374-3369 | Khalil Minhas | Khalil.Minhas@vdot.virginia.gov | (540) 374-3369 | Paul Agnello | pagnello@spotsylvania.va.us | (540) 507-7398 | 1 | 2017 | 0 | FY2021 | 21250000 | 21250000 | ACTIVITY DATES SET | R | Complete Purchasing Right-of-Way milestone is 270 days past the expected completion date | G | Project is on budget | [5 empty] | 2014-03-17 | 2014-12-12 | 2014-03-17 | 2014-12-12 | R | 2015-10-19 | 2015-09-08 | 2017-04-07 | 2017-04-05 | G | [5 empty] | 2017-11-30 | 2017-11-30 | 2018-03-23 | 2018-03-23 | G | 2018-10-23 | 2018-10-23 | 2018-11-05 | 2018-11-06 | R | 2019-08-01 |  | 2020-09-04 |  | R | 2018-11-26 | 2019-01-30 | 2020-05-27 |  | R | 2018-03-14 | 2018-03-14 | 2018-11-01 | 2018-10-17 | G | [5 empty] | 2020-09-08 |  | 2020-09-08 |  | R | 2020-10-30 |  | 2020-12-30 |  | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.11608
97 | 107074 | Route 23 Median Shoulders | 0023 | Primary | Safety | VDOT | Wise County | WISE | Bristol | NonMPO:NonMPO | Infrastructure Investment Division | Brian Holt | Brian.Holt@vdot.virginia.gov | (276) 696-3414 | Chase R Buchanan | Chase.Buchanan@VDOT.Virginia.gov | (276) 696-3251 |  |  |  | 0 |  | 0 | FY2021 | 2511000 | 2167819 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 69 days early | G | Project is on budget | [5 empty] | 2019-07-01 | 2019-07-01 | 2019-07-15 | 2019-07-10 | G | 2019-07-16 | 2019-07-16 | 2019-08-12 | 2019-08-08 | G | [35 empty] | 2020-05-11 | 2020-02-11 | 2020-05-11 | 2020-02-11 | G | 2020-06-24 | 2020-05-07 | 2020-07-15 | 2020-05-07 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.067809
98 | 107657 | Westminster Drive Sidewalk |  | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Front Royal | EDINBURG | Staunton | NonMPO:NonMPO | Local Assistance Division | Kimberly Cameron | Kim.Cameron@vdot.virginia.gov | (540) 332-7886 | Kimberly Cameron | Kim.Cameron@vdot.virginia.gov | (540) 332-7886 | Steve Scheulen | sscheulen@frontroyalva.com | (540) 635-7819 | 0 |  | 0 | FY2019 | 124025 | 124025 | WAITING FINANCIAL CLOSURE | R | Start Delivery milestone finished 45 days late | G | Project is on budget | 2015-10-01 | 2015-10-23 | 2015-12-30 | 2015-10-23 | G | 2015-12-31 | 2016-09-13 | 2016-01-14 | 2016-09-13 | R | 2016-01-19 | 2016-09-14 | 2016-09-08 | 2017-06-01 | R | [10 empty] | 2017-08-09 | 2017-08-09 | 2017-08-09 | 2017-08-09 | G | [20 empty] | 2017-08-31 | 2017-08-17 | 2017-12-28 | 2018-09-07 | R | 2018-05-10 | 2018-10-30 | 2018-10-30 | 2018-12-14 | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.42587
99 | 108665 | 22nd Street Bridge Replacement | 0166 | Urban | Bridge Replacement w/o Added Capacity | Locally | Chesapeake | NORFOLK | Hampton Roads | Hampton Roads:Chesapeake | Local Assistance Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Johndel A Alcaide | John.Alcaide@vdot.virginia.gov | (757) 956-3098 | Sam Sawan, PE | sawan@cityofchesapeake.net | (757) 382-8263 | 0 |  | 0 | FY2020 | 19922800 | 19922800 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 461 days early | G | Project is on budget | 2016-08-31 | 2016-08-31 | 2016-09-28 | 2016-09-28 | G | 2016-09-29 | 2016-09-29 | 2016-09-29 | 2016-09-29 | G | 2016-09-30 | 2016-09-30 | 2017-07-21 | 2017-07-20 | G | [10 empty] | 2017-04-06 | 2017-04-06 | 2017-04-06 | 2017-04-06 | G | [5 empty] | 2017-04-10 | 2017-04-10 | 2019-06-10 | 2018-02-15 | G | [10 empty] | 2019-06-26 | 2018-03-05 | 2019-07-24 | 2018-03-30 | G | 2019-07-25 | 2018-04-02 | 2019-09-04 | 2018-05-31 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.16634
100 | 111054 | #SMART18 - (St) I-81 EXIT 300 SOUTHBOUND ACCEL LANE EXT. | 0081 | Interstate | Reconstruction w/o Added Capacity | VDOT | Warren County | EDINBURG | Staunton | NonMPO:NonMPO | Infrastructure Investment Division | Matthew P Dana | Matt.Dana@VDOT.Virginia.gov | (540) 332-7786 | Ronald L Tabor | Ronald.Tabor@vdot.virginia.gov | (540) 332-7887 |  |  |  | 1 | 2018 | 0 | FY2021 | 3437422 | 8535200 | ACTIVITY DATES SET | R | Obtained Permits milestone is 255 days past the expected completion date | R | Project estimate is less than $5M and is 20% or more over budget | [5 empty] | 2017-08-03 | 2017-07-17 | 2017-08-16 | 2017-07-26 | G | 2017-08-17 | 2017-07-27 | 2018-12-07 | 2018-11-20 | G | [5 empty] | 2019-08-20 | 2019-06-10 | 2019-10-01 | 2019-06-25 | G | [5 empty] | 2020-04-16 |  | 2020-08-07 |  | R | [5 empty] | 2020-04-02 |  | 2020-06-11 |  | R | [5 empty] | 2020-10-13 |  | 2020-10-13 |  | R | 2020-12-02 |  | 2021-04-13 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.068207
101 | 111308 | Foxfire Pedestrian Trail - Ph 1 |  | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Virginia Beach | NORFOLK | Hampton Roads | Hampton Roads:Virginia Beach | Local Assistance Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Marci Thompson | Marci.Thompson@vdot.virginia.gov | (757) 956-3093 | Katie Shannon | kshannon@vbgov.com | (757) 385-1514 | 0 |  | 0 | FY2021 | 1123530 | 1123530 | NO DATES SET YET-PE OPEN | R | Determine Requirements milestone is 759 days past the expected completion date | G | Project is on budget | 2017-10-06 | 2017-10-06 | 2018-01-24 | 2018-01-24 | G | 2018-01-24 | 2018-01-24 | 2018-01-24 | 2018-01-24 | G | 2018-01-24 |  | 2019-01-24 |  | R | [10 empty] | 2020-05-20 |  | 2020-05-20 |  | R | [5 empty] | 2020-05-21 |  | 2020-05-21 |  | R | [10 empty] | 2020-06-09 |  | 2020-07-21 |  | R | 2020-07-22 |  | 2021-01-14 |  | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.27782
102 | 111701 | #SMART18 - Smart Cities: Centr. Transit SP / EV Preemption | 0000 | Urban | Safety | Locally | Richmond | ASHLAND | Richmond | Richmond:Richmond | Infrastructure Investment Division | Olena Fecek | Olena.Fecek@vdot.virginia.gov | (804) 524-6368 | Olena Fecek | Olena.Fecek@vdot.virginia.gov | (804) 524-6368 | Enrique Burgos | enrique.burgos@richmondgov.com | (804) 646-6337 | 1 | 2018 | 0 | FY2021 | 1911080 | 1911080 | NO DATES SET YET-PE OPEN | R | Determine Requirements milestone is 318 days past the expected completion date | G | Project is on budget | 2019-07-01 | 2019-02-25 | 2019-09-24 | 2019-08-07 | G | 2019-09-25 | 2019-09-26 | 2021-09-30 | 2019-10-15 | G | 2019-09-30 | 2019-10-16 | 2020-04-09 |  | R | [35 empty] | 2021-02-19 |  | 2021-03-19 |  | Y | 2021-03-22 |  | 2021-04-29 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.12832
103 | 111790 | #SMART18 - 301 South Median Crossover Project |  | Primary | Reconstruction w/o Added Capacity | VDOT | Greensville County | FRANKLIN | Hampton Roads | NonMPO:NonMPO | Infrastructure Investment Division | Joseph E Lomax | Joe.Lomax@VDOT.Virginia.gov | (757) 494-2447 | Kenneth D Mckinna | Kenneth.McKinna@VDOT.Virginia.gov | (757) 956-3271 | Linwood E Pope, Jr. | lpope@greensvillecountyva.gov | (434) 348-4232 | 1 | 2018 | 0 | FY2023 | 729480 | 927175 | CRITICAL DECISION NEEDED | G | Start Purchasing Right-of-Way milestone finished 102 days early | R | Project estimate is less than $5M and is 20% or more over budget | [5 empty] | 2018-09-04 | 2018-07-20 | 2018-09-17 | 2018-07-20 | G | 2018-09-18 | 2018-07-23 | 2019-02-14 | 2019-02-14 | G | [5 empty] | 2019-10-03 | 2019-07-09 | 2019-10-16 | 2019-07-25 | G | 2020-10-05 | 2020-06-18 | 2020-10-16 | 2020-07-06 | G | 2021-06-01 |  | 2021-12-07 |  | G | 2020-11-04 | 2020-07-07 | 2021-05-14 |  | G | [10 empty] | 2022-02-08 |  | 2022-02-08 |  | G | 2022-05-12 |  | 2022-07-08 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.14165
104 | 112982 | WOODBERRY FORREST ROAD - MILLING, PAVING & RECONSTRUCTION | 0634 | Urban | Resurfacing | Locally | Orange | LOUISA | Culpeper | NonMPO:NonMPO | Local Assistance Division | Ken Connors |  |  | Bobby J Jenkins | Bobby.JenkinsJr@VDOT.Virginia.gov | (540) 829-7694 | JOHN COOLEY | townplanner@townoforangeva.org | (540) 672-6917 | 0 |  | 0 | FY2019 | 47044 | 47044 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished on-time | G | Project is on budget | 2019-02-21 | 2018-07-01 | 2019-05-15 | 2018-07-09 | G | [5 empty] | 2019-02-21 | 2018-07-09 | 2019-03-06 | 2018-12-05 | G | [25 empty] | 2018-09-19 | 2018-09-19 | 2018-09-20 | 2018-09-19 | G | [5 empty] | 2018-12-15 | 2018-12-15 | 2019-01-05 | 2019-01-03 | G | 2019-01-05 | 2019-01-05 | 2019-02-01 | 2019-02-01 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.047879
105 | 113168 | INSTALL NEW SIDEWALK, NEEL ST., DEPOT ST., MT. LANE | 0000 | Urban | Facilities for Pedestrians and Bicycles | Locally | Bluefield | LEBANON | Bristol | NonMPO:NonMPO | Local Assistance Division | John R Watson | JR.Watson@VDOT.Virginia.gov | (276) 202-1240 | Roger L Musser | Roger.Musser@VDOT.Virginia.gov | (276) 696-3260 | Mike Watson | watson@bluefieldva.org | (276) 322-4626 | 0 |  | 0 | FY2021 | 80000 | 80000 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 16 days early | G | Project is on budget | 2019-03-01 | 2019-03-01 | 2019-05-23 | 2019-03-12 | G | [5 empty] | 2019-03-01 | 2019-03-01 | 2019-03-14 | 2019-03-14 | G | [25 empty] | 2019-03-15 | 2020-01-14 | 2020-03-02 | 2020-01-14 | G | [5 empty] | 2020-03-03 | 2020-03-03 | 2020-05-26 | 2020-04-17 | G | 2020-08-13 | 2020-07-08 | 2020-08-13 | 2020-07-28 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.083208
106 | 113311 | Primary Extension - Rte 116 (Lafayette Blvd) | 0000 | Urban | Resurfacing | Locally | Roanoke | SALEM | Salem | Roanoke:Roanoke City | Local Assistance Division | Cheryl B Becker | Cheryl.Becker@vdot.virginia.gov | (540) 492-2531 | Cheryl B Becker | Cheryl.Becker@vdot.virginia.gov | (540) 492-2531 | Mark Jamison | mark.jamison@roanokeva.gov | (540) 853-5471 | 0 |  | 0 | FY2019 | 475000 | 475000 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 147 days early | G | Project is on budget | 2018-10-01 | 2018-07-27 | 2018-12-28 | 2018-09-27 | G | 2018-12-31 | 2018-09-28 | 2019-01-03 | 2018-09-28 | G | 2019-01-04 | 2018-09-29 | 2019-03-22 | 2018-09-29 | G | [35 empty] | 2018-11-27 | 2018-11-07 | 2018-12-31 | 2018-11-21 | G | 2019-05-28 | 2018-11-21 | 2019-06-28 | 2019-02-01 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.12296
107 | 113443 | Route 36 Resurfacing, City of Petersburg | 0036 | Urban | Resurfacing | VDOT | Petersburg | PETERSBURG | Richmond | Tri-Cities:Petersburg | Local Assistance Division | James Shepherd | James.Shepherd@vdot.virginia.gov | (804) 609-5305 | James Shepherd | James.Shepherd@vdot.virginia.gov | (804) 609-5305 | Bill Riggleman | bill@petersburg-va.org | (804) 993-1927 | 0 |  | 1 | FY2019 | 186158 | 186158 | AWARDED | G | Start Delivery milestone finished 34 days early | G | Project is on budget | [10 empty] | 2019-01-02 | 2018-12-10 | 2019-01-08 | 2019-01-02 | G | [35 empty] | 2019-05-15 | 2019-03-12 | 2019-05-15 | 2019-03-12 | G | 2019-05-16 | 2019-03-13 | 2019-05-28 | 2019-04-24 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.067211
108 | 113713 | RTE 730 - RURAL RUSTIC (SURFACE TREAT NON-HARDSURFACE ROAD) | 0730 | Secondary | Reconstruction w/o Added Capacity | VDOT | Culpeper County | WARRENTON | Culpeper | NonMPO:NonMPO | Infrastructure Investment Division | Ken Connors |  |  | Benjamin Davison | Ben.Davison@vdot.virginia.gov | (540) 347-6446 |  |  |  | 0 |  | 0 | FY2023 | 385729 | 385729 | NO DATES SET YET-PE OPEN | G | Start Development milestone finished 41 days early | G | Project is on budget | [5 empty] | 2020-10-01 | 2020-08-21 | 2020-10-14 | 2020-09-03 | G | 2020-10-15 | 2020-09-04 | 2021-06-11 |  | G | [5 empty] | 2022-02-22 |  | 2022-04-04 |  | G | [5 empty] | 2022-07-19 |  | 2022-11-09 |  | G | [5 empty] | 2022-07-01 |  | 2022-10-03 |  | G | [5 empty] | 2022-12-13 |  | 2022-12-13 |  | G | 2023-03-09 |  | 2023-03-09 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | SAAP CONTRACT | 0 | 0 | 0.10367
109 | 113788 | RTE 617 - RURAL RUSTIC RD (SURFACE TREAT NON-HARDSURFACE RD) | 0617 | Secondary | Resurfacing | VDOT | Louisa County | LOUISA | Culpeper | NonMPO:NonMPO | Infrastructure Investment Division | Ken Connors |  |  | Bethel Kefyalew | Bethel.Kefyalew@vdot.virginia.gov | (540) 603-6015 |  |  |  | 0 |  | 0 | FY2025 | 252500 | 252500 | NO DATES SET YET | G | Start Development milestone is 600 days ahead of the expected completion date | Y | Estimate not current | [5 empty] | 2022-10-03 |  | 2022-10-14 |  | G | 2022-10-18 |  | 2023-06-13 |  | G | [5 empty] | 2024-02-22 |  | 2024-04-03 |  | G | [5 empty] | 2024-07-18 |  | 2024-11-08 |  | G | [5 empty] | 2024-07-02 |  | 2024-10-02 |  | G | [5 empty] | 2024-11-12 |  | 2024-11-12 |  | G | 2025-02-07 |  | 2025-02-07 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | SAAP CONTRACT | 0 | 0 | 0.066389
112 | 111371 | #SMART18 - Downtown Salem Int. & Streetscape Improvements | 0460 | Urban | Landscaping/Beautification | Locally | Salem | SALEM | Salem | Roanoke:Salem | Infrastructure Investment Division | Alex H Price | Alex.Price@VDOT.Virginia.gov | (540) 378-5053 | Cheryl B Becker | Cheryl.Becker@vdot.virginia.gov | (540) 492-2531 | Benjamin Tripp | btripp@salemva.gov | (540) 375-3032 | 1 | 2018 | 0 | FY2021 | 3629869 | 3629869 | NO DATES SET YET-PE OPEN | R | Determine Requirements milestone is 669 days past the expected completion date | G | Project is on budget | 2018-07-16 | 2018-07-16 | 2018-10-08 | 2019-04-02 | R | 2018-10-09 | 2019-04-29 | 2018-10-11 | 2019-05-06 | R | 2018-10-12 |  | 2019-04-24 |  | R | 2019-12-31 |  | 2020-02-13 |  | R | [30 empty] | 2020-06-16 |  | 2020-07-14 |  | R | 2020-07-15 |  | 2020-10-29 |  | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.37699
113 | 111779 | RTE. 702 - BRIDGE REPLACEMENT STR. 6401 | 0702 | Secondary | Bridge Replacement w/o Added Capacity | VDOT | Albemarle County | CHARLOTTESVILLE | Culpeper | Charlottesville:Albemarle County | Infrastructure Investment Division | Braden C Chapman | Braden.Chapman@VDOT.Virginia.gov | (540) 829-7421 | Brian A Arnold | Brian.Arnold@VDOT.Virginia.gov | (540) 829-7557 |  |  |  | 0 |  | 0 | FY2023 | 3500000 | 3500000 | ACTIVITY DATES SET | G | Start Purchasing Right-of-Way milestone finished 94 days early | G | Project is on budget | [5 empty] | 2017-09-20 | 2017-09-20 | 2017-09-20 | 2017-09-20 | G | 2017-09-21 | 2017-09-21 | 2018-09-07 | 2019-06-17 | R | [5 empty] | 2020-04-28 | 2019-09-17 | 2020-05-18 | 2019-10-29 | G | 2021-02-01 | 2020-10-15 | 2021-02-12 | 2020-11-10 | G | 2021-07-08 | 2021-01-27 | 2022-01-18 |  | G | 2021-03-02 |  | 2021-09-01 |  | G | 2018-10-26 | 2019-07-17 | 2019-10-28 | 2019-07-17 | G | [5 empty] | 2022-03-08 |  | 2022-03-08 |  | G | 2022-08-12 |  | 2022-09-01 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 1 | 0.25083
114 | 112959 | Youngs Drive, Phase II Rural Addition - Warren County | 0693 | Secondary | Reconstruction w/o Added Capacity | Locally | Warren County | EDINBURG | Staunton | NonMPO:NonMPO | Local Assistance Division | Kimberly Cameron | Kim.Cameron@vdot.virginia.gov | (540) 332-7886 | Kimberly Cameron | Kim.Cameron@vdot.virginia.gov | (540) 332-7886 | Mike Berry | mberry@warrencountyva.net | (540) 636-1543 | 0 |  | 0 | FY2022 | 473216 | 473216 | NO DATES SET YET-PE OPEN | R | Determine Requirements milestone is 45 days past the expected completion date | G | Project is on budget | 2020-04-01 | 2019-11-20 | 2020-06-24 | 2020-02-13 | G | 2020-06-25 | 2020-02-14 | 2020-06-29 | 2020-03-19 | G | 2020-06-30 |  | 2021-01-07 |  | R | [25 empty] | 2021-01-08 |  | 2021-09-10 |  | G | [5 empty] | 2021-11-16 |  | 2021-12-15 |  | G | 2022-03-10 |  | 2022-03-10 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.20572
115 | 113121 | UNIVERSITY DRIVE (SOUTH OF FAIRFAX BLVD) IMPROVEMENTS | 6627 | Urban | Facilities for Pedestrians and Bicycles | Locally | Fairfax | FAIRFAX | Northern Virginia | Northern Virginia:Fairfax | Local Assistance Division | Andrew G Beacher | Andrew.Beacher@vdot.virginia.gov | (703) 259-2239 | Rita Hockman | Rita.Hockman@vdot.virginia.gov | (804) 824-7421 | Patricia Sullivan | patricia.sullivan@fairfaxva.gov | (703) 385-3067 | 0 |  | 0 | FY2021 | 1150000 | 1150000 | CONSTRUCTION STARTED | G | Start Delivery milestone finished on-time | G | Project is on budget | 2018-07-01 | 2018-07-01 | 2018-08-13 | 2018-08-13 | G | 2019-02-05 | 2019-02-05 | 2019-02-19 | 2019-02-19 | G | 2019-11-01 | 2019-03-21 | 2020-03-31 | 2019-07-01 | G | [10 empty] | 2018-07-01 | 2019-02-20 | 2018-07-13 | 2019-03-04 | R | [5 empty] | 2020-05-28 | 2020-01-02 | 2021-04-26 | 2020-05-27 | G | 2020-05-28 | 2020-05-28 | 2021-03-03 | 2020-05-28 | G | [5 empty] | 2020-05-28 | 2020-05-28 | 2020-06-26 | 2020-06-26 | G | 2020-06-28 | 2020-06-28 | 2020-07-28 | 2020-07-28 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.18252
116 | 113188 | CROZET SQUARE / OAK STREET IMPROVEMENTS | 1217 | Secondary | New Construction Roadway | Locally | Albemarle County | CHARLOTTESVILLE | Culpeper | NonMPO:NonMPO | Local Assistance Division | Ken Connors |  |  | Thomas Fitzpatrick | Thomas.Fitzpatrick@vdot.virginia.gov |  | JACK KELSEY |  |  | 0 |  | 0 | FY2022 | 1510000 | 1510000 | NO DATES SET YET-PE OPEN | R | Determine Requirements milestone is 429 days past the expected completion date | G | Project is on budget | 2019-03-18 | 2018-08-01 | 2019-06-10 | 2018-08-21 | G | 2019-06-11 | 2019-03-01 | 2019-06-13 | 2019-03-08 | G | 2019-06-14 |  | 2019-12-20 |  | R | [10 empty] | 2020-12-23 |  | 2021-01-14 |  | R | [5 empty] | 2021-01-20 |  | 2021-10-26 |  | G | 2020-01-31 | 2019-03-05 | 2020-09-30 | 2019-03-05 | G | [5 empty] | 2021-11-12 |  | 2021-12-13 |  | G | 2022-03-08 |  | 2022-03-08 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.18044
117 | 113367 | DISTRICTWIDE TRENCH WIDENING - VARIOUS LOCATIONS | 9999 | Primary | Safety | VDOT | Stafford County | FREDERICKSBURG | Fredericksburg | Fredericksburg:Stafford County | Infrastructure Investment Division | Peter A Hedrich | Peter.Hedrich@vdot.virginia.gov | (540) 899-4540 | Sylvester C Okpala | Sylvester.Okpala@VDOT.Virginia.gov | (540) 907-8174 |  |  |  | 0 |  | 0 | FY2019 | 600000 | 648892 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 98 days early | Y | Project estimate is less than $5M and is up to 20% over budget | [10 empty] | 2018-08-01 | 2018-08-01 | 2018-08-07 | 2018-08-07 | G | [25 empty] | 2018-08-01 | 2018-08-01 | 2019-02-11 | 2018-08-01 | G | [5 empty] | 2019-03-12 | 2018-12-18 | 2019-03-12 | 2018-12-18 | G | 2019-05-31 | 2019-02-22 | 2019-05-31 | 2019-02-22 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.061052
118 | 113561 | RTE 709 - FLATFORD ROAD SIDEWALK | 0709 | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Stafford County | FREDERICKSBURG | Fredericksburg | Fredericksburg:Stafford County | Infrastructure Investment Division | Khalil Minhas | Khalil.Minhas@vdot.virginia.gov | (540) 374-3369 | Khalil Minhas | Khalil.Minhas@vdot.virginia.gov | (540) 374-3369 | Thomas O'Connor | toconnor@staffordcountyva.gov | (540) 658-4610 | 0 |  | 0 | FY2022 | 650000 | 966341 | ACTIVITY DATES SET | R | Start Purchasing Right-of-Way milestone finished 29 days late | R | Project estimate is less than $5M and is 20% or more over budget | 2018-09-04 | 2018-09-10 | 2018-11-30 | 2018-12-14 | R | 2018-12-03 | 2018-08-01 | 2018-12-05 | 2018-08-03 | G | 2018-12-06 | 2018-12-15 | 2019-06-13 | 2019-06-13 | G | [10 empty] | 2020-05-11 | 2020-06-22 | 2020-06-29 | 2020-07-28 | R | [5 empty] | 2020-07-01 |  | 2021-08-04 |  | G | 2020-01-07 | 2019-08-01 | 2020-10-05 | 2019-09-17 | G | [5 empty] | 2021-10-13 |  | 2021-11-10 |  | G | 2022-02-07 |  | 2022-03-07 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.20492
119 | 113765 | MANVILLE RD - REPLACE AND CONSTRUCT NEW SIDEWALK | 0665 | Secondary | Facilities for Pedestrians and Bicycles | Locally | Gate City | WISE | Bristol | Kingsport:Scott County | Infrastructure Investment Division | Allan D Sumpter | Allan.Sumpter@VDOT.virginia.gov | (276) 525-6461 | Kenneth R Plummer | KR.Plummer@VDOT.Virginia.gov | (276) 696-3261 | Greg Jones |  |  | 0 |  | 0 | FY2024 | 448103 | 448103 | NO DATES SET YET | G | Agreement with Locality milestone is 520 days ahead of the expected completion date | G | Project is on budget | 2022-05-02 |  | 2022-07-26 |  | G | 2022-07-27 |  | 2022-07-29 |  | G | 2022-08-01 |  | 2023-02-09 |  | G | [25 empty] | 2023-03-20 |  | 2023-11-17 |  | G | [5 empty] | 2024-02-29 |  | 2024-03-27 |  | G | 2024-06-14 |  | 2024-06-14 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.15016
120 | 113840 | EAST BROAD WAY STREETSCAPE IMPROVEMENTS | 0673 | Enhancement | Reconstruction w/o Added Capacity | Locally | Lovettsville | LEESBURG | Northern Virginia | Northern Virginia:Loudoun County | Local Assistance Division | Bud Siegel |  |  | Christer P Carshult | Christer.Carshult@vdot.virginia.gov | (703) 259-1765 | Robert Ritter (Town Manager) | townmanager@lovettsvilleva.gov | (540) 755-3000 | 0 |  | 0 | FY2023 | 1956000 | 1956000 | ACTIVITY DATES SET | G | Determine Requirements milestone finished 28 days early | G | Project is on budget | 2018-07-02 | 2018-07-02 | 2019-01-31 | 2019-01-09 | G | 2019-02-01 | 2019-01-10 | 2019-02-28 | 2019-01-31 | G | 2019-10-01 | 2019-09-04 | 2020-09-30 | 2020-09-02 | G | [10 empty] | 2021-08-02 |  | 2021-08-31 |  | G | [5 empty] | 2021-09-02 |  | 2022-06-30 |  | G | 2022-02-15 |  | 2022-10-31 |  | G | [5 empty] | 2022-08-01 |  | 2022-12-30 |  | G | 2023-01-03 |  | 2023-05-31 |  | G | Consultant contract is still in procurement | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.45269
121 | 114094 | RTE 29 - SHOULDER WIDENING AND RUMBLE STRIPS (CAMPBELL) | 0029 | Primary | Safety | VDOT | Campbell County | APPOMATTOX | Lynchburg | Lynchburg:Campbell County | Infrastructure Investment Division | Gerald L Harter | Gerry.Harter@vdot.virginia.gov | (434) 856-8211 | Lindsey S Hodges | Lindsey.Hodges@vdot.virginia.gov | (434) 856-8143 |  |  |  | 0 |  | 0 | FY2020 | 1462933 | 1338194 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 7 days early | G | Project is on budget | [10 empty] | 2019-07-15 | 2019-02-04 | 2019-07-19 | 2019-07-18 | G | [35 empty] | 2019-12-10 | 2019-12-10 | 2019-12-10 | 2019-12-10 | G | 2020-03-05 | 2020-02-27 | 2020-03-05 | 2020-02-27 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.096001
122 | 115454 | #SMART20 - Orange Ave (US 460) Improvements | 0460 | Urban | Safety | Locally | Roanoke | SALEM | Salem | Roanoke:Roanoke City | Local Assistance Division | Thomas W Digiulian | Thomas.DiGiulian@VDOT.Virginia.gov | (540) 387-5356 | Cheryl B Becker | Cheryl.Becker@vdot.virginia.gov | (540) 492-2531 | Mark Jamison | mark.jamison@roanokeva.gov | (540) 853-5471 | 1 | 2020 | 0 | FY2023 | 2818704 | 2818704 | NO DATES SET YET-PE OPEN | R | Start Development milestone finished 126 days late | G | Project is on budget | 2019-12-02 | 2020-06-23 | 2020-04-10 | 2020-08-21 | R | 2020-04-13 | 2020-08-24 | 2020-05-01 | 2020-09-04 | R | 2020-11-06 |  | 2021-03-09 |  | Y | [25 empty] | 2022-03-04 |  | 2022-08-01 |  | G | [5 empty] | 2022-09-28 |  | 2022-10-26 |  | G | 2023-01-23 |  | 2023-01-23 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.22772
123 | 115940 | HSIP HR Edge Line Rumbles Primaries | 9999 | Miscellaneous | Safety | VDOT | Hampton Roads District-wide |  | Hampton Roads | Hampton Roads:Hampton Roads District-wide | Infrastructure Investment/Asset Management Division | Todd M Halacy | Todd.Halacy@VDOT.Virginia.gov | (757) 956-3010 | Jesse Alan Williams | Alan.Williams@vdot.virginia.gov | (757) 925-1574 |  |  |  | 0 |  | 0 | FY2021 | 3065595 | 3065595 | NO DATES SET YET-PE OPEN | G | Start Development milestone finished on-time | G | Project is on budget | [5 empty] | 2020-01-14 | 2020-01-14 | 2020-02-20 | 2020-02-20 | G | 2020-02-21 | 2020-02-21 | 2021-03-29 |  | G | [5 empty] | 2021-03-30 |  | 2021-04-12 |  | G | [25 empty] | 2021-04-28 |  | 2021-05-04 |  | G | 2021-05-05 |  | 2021-05-11 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | WORK/TASK ORDER | 0 | 0 | 0.079571
124 | 116998 | #SGR21VP PM3D21 PRINCE EDWARD COUNTY PLANT MIX (P) | 9999 | Primary | Resurfacing | VDOT | Prince Edward County | DILLWYN | Lynchburg | NonMPO:NonMPO | Infrastructure Investment Division | Kevin S Chisnell | Kevin.Chisnell@VDOT.Virginia.gov | (434) 856-8113 | Kevin S Chisnell | Kevin.Chisnell@VDOT.Virginia.gov | (434) 856-8113 |  |  |  | 0 |  | 1 | FY2022 | 1523583 | 1523583 | ADVERTISED | G | Solicit Bids milestone finished 28 days early | G | Project is on budget | [10 empty] | 2020-11-24 | 2020-10-15 | 2020-12-02 | 2020-11-20 | G | [35 empty] | 2020-12-08 | 2021-01-12 | 2021-02-09 | 2021-01-12 | G | 2021-04-30 |  | 2021-07-15 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.081674
125 | 117052 | Church Road Sidewalk | 9999 | Secondary | Facilities for Pedestrians and Bicycles | Locally | Henrico County | ASHLAND | Richmond | Richmond:Henrico County | Local Assistance Division | Douglas L Orcutt | Doug.Orcutt@vdot.virginia.gov | (804) 609-5428 | Douglas L Orcutt | Doug.Orcutt@vdot.virginia.gov | (804) 609-5428 | TBD |  | TBD | 0 |  | 0 | FY2029 | 825696 | 825696 | NO DATES SET YET | G | Agreement with Locality milestone is 1543 days ahead of the expected completion date | G | Project is on budget | 2025-01-06 |  | 2025-05-14 |  | G | 2025-05-15 |  | 2025-06-05 |  | G | 2025-12-15 |  | 2026-04-10 |  | G | [10 empty] | 2027-07-30 |  | 2027-09-02 |  | G | [5 empty] | 2027-09-03 |  | 2028-02-09 |  | G | 2028-01-05 |  | 2028-06-05 |  | G | [5 empty] | 2028-05-12 |  | 2028-06-09 |  | G | 2028-08-29 |  | 2028-08-29 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.34928
126 | 118063 | Maymont Sidewalk- Phase II |  | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Richmond | ASHLAND | Richmond | Richmond:Richmond | Local Assistance Division | James Shepherd | James.Shepherd@vdot.virginia.gov | (804) 609-5305 | James Shepherd | James.Shepherd@vdot.virginia.gov | (804) 609-5305 | Adel Edward | adel.edward@richmondgov.com | (804) 646-6584 | 0 |  | 0 | FY2024 | 430000 | 430000 | NO DATES SET YET | G | Agreement with Locality milestone is 199 days ahead of the expected completion date | G | Project is on budget | 2021-05-03 |  | 2021-09-08 |  | G | 2021-09-09 |  | 2021-09-29 |  | G | 2022-04-13 |  | 2022-08-04 |  | G | [25 empty] | 2023-08-01 |  | 2024-01-03 |  | G | [5 empty] | 2024-03-05 |  | 2024-04-01 |  | G | 2024-06-19 |  | 2024-06-19 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.35241
127 | 118380 | Safety Improvements on Route 258 | 0258 | Primary | Safety | VDOT | Multi-jurisdictional: Hampton Roads MPO |  | Hampton Roads | Hampton Roads:Multi-jurisdictional: Hampton Roads MPO | Infrastructure Investment Division | Karen A Bourne | Karen.Bourne@VDOT.Virginia.gov | (757) 956-3084 | Kenneth D Mckinna | Kenneth.McKinna@VDOT.Virginia.gov | (757) 956-3271 | John Mihaly | jmihaly@hrtpo.org | (757) 420-8300 | 0 |  | 0 | FY2025 | 2100000 | 2100000 | NO DATES SET YET | G | Start Development milestone is 107 days ahead of the expected completion date | G | Project is on budget | [5 empty] | 2021-05-18 |  | 2021-06-08 |  | G | 2021-06-09 |  | 2022-04-13 |  | G | [5 empty] | 2022-11-09 |  | 2022-12-09 |  | G | 2023-08-02 |  | 2023-09-06 |  | G | 2024-02-12 |  | 2024-06-11 |  | G | 2023-09-21 |  | 2024-02-27 |  | G | 2023-11-08 |  | 2024-04-12 |  | G | [5 empty] | 2024-07-09 |  | 2024-07-09 |  | G | 2024-09-26 |  | 2024-09-26 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.13557
128 | 57034 | RTE 675 - VERTICAL CURVE IMPROVEMENT | 0675 | Secondary | Safety | VDOT | Botetourt County | SALEM | Salem | Roanoke:Botetourt County | Infrastructure Investment Division | Scott Woodrum |  |  | C E Cumbie | C.Cumbie@VDOT.Virginia.gov | (540) 387-5561 |  |  |  | 0 |  | 0 | FY2032 | 490400 | 1922328 | ACTIVITY DATES SET | G | Engage Public milestone finished on-time | R | Project estimate is less than $5M and is 20% or more over budget | [5 empty] | 2003-07-15 | 2003-07-07 | 2003-09-30 | 2003-07-08 | G | 2003-10-01 | 2004-03-11 | 2004-09-02 | 2004-08-30 | G | 2006-09-08 | 2006-09-08 | 2006-11-09 | 2006-11-09 | G | [5 empty] | 2030-11-04 |  | 2030-11-18 |  | G | 2031-04-11 |  | 2031-10-08 |  | G | 2030-12-06 |  | 2031-08-11 |  | G | 2030-04-23 |  | 2031-04-18 |  | G | [5 empty] | 2031-11-12 |  | 2031-12-15 |  | G | 2032-01-26 |  | 2032-02-13 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 1 | 0.26831
129 | 87002 | RTE. 220B - Henry County - Collinsville Streetscaping |  | Enhancement | Landscaping/Beautification | Locally | Henry County | MARTINSVILLE | Salem | NonMPO:NonMPO | Local Assistance Division | Anthony W Ford | Anthony.Ford@VDOT.Virginia.gov | (540) 378-5040 | Cheryl B Becker | Cheryl.Becker@vdot.virginia.gov | (540) 492-2531 | Mary Ann Mason | mmason@co.henry.va.us | (276) 634-4620 | 0 |  | 0 | FY2019 | 1495830 | 1139000 | CONSTRUCTION STARTED | R | Start Delivery milestone finished 173 days late | G | Project is on budget | [5 empty] | 2008-06-02 | 2008-08-28 | 2008-06-02 | 2008-08-28 | R | 2009-01-29 | 2009-01-29 | 2013-07-22 | 2015-11-30 | R | [35 empty] | 2016-04-18 | 2016-04-18 | 2018-03-25 | 2018-03-25 | G | 2018-03-30 | 2018-03-30 | 2018-09-28 | 2019-03-20 | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.352
130 | 113808 | #SGR19VP - PM6C-19 Asphalt Resurfacing - District Wide Pri | 9999 | Primary | Resurfacing | VDOT | Fredericksburg District-wide |  | Fredericksburg | NonMPO:NonMPO | Infrastructure Investment/Asset Management Division | Gina M Pelchat | Gina.Pelchat@vdot.virginia.gov | (504) 899-4010 | Sylvester C Okpala | Sylvester.Okpala@VDOT.Virginia.gov | (540) 907-8174 |  |  |  | 0 |  | 1 | FY2019 | 529650 | 529650 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished on-time | G | Project is on budget | [10 empty] | 2020-02-10 | 2018-08-31 | 2020-02-14 | 2018-09-27 | G | [35 empty] | 2018-12-04 | 2018-12-04 | 2018-12-04 | 2018-12-04 | G | 2019-01-30 | 2019-01-30 | 2019-01-30 | 2019-01-30 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.088634
131 | 113995 | SHOULDER RUMB LE STRIPS - DISTRICT WIDE | 9999 | Primary | Safety | VDOT | Fredericksburg District-wide |  | Fredericksburg | Fredericksburg:Fredericksburg District-wide | Infrastructure Investment Division | Jessica Graves | Jessica.Graves@vdot.virginia.gov | (540) 899-4267 | Jessica Graves | Jessica.Graves@vdot.virginia.gov | (540) 899-4267 |  |  |  | 0 |  | 0 | FY2024 | 206000 | 206000 | NO DATES SET YET | G | Start Development milestone is 960 days ahead of the expected completion date | G | Project is on budget | [5 empty] | 2023-09-19 |  | 2023-10-09 |  | G | 2023-10-10 |  | 2024-01-25 |  | G | [5 empty] | 2024-02-07 |  | 2024-02-21 |  | G | [25 empty] | 2024-03-08 |  | 2024-03-14 |  | G | 2024-03-15 |  | 2024-03-21 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | WORK/TASK ORDER | 0 | 0 | 0.067052
132 | 115208 | Harrowgate Road Sidewalk, Dogwood Ave to South St | 0144 | Primary | Facilities for Pedestrians and Bicycles | Locally | Chesterfield County | CHESTERFIELD | Richmond | Tri-Cities:Chesterfield County | Infrastructure Investment Division | Michael S Gray | Mike.Gray@vdot.virginia.gov | (804) 609-5347 | Michael S Gray | Mike.Gray@vdot.virginia.gov | (804) 609-5347 | Barb Smith | smithbk@chesterfield.gov | (804) 748-1037 | 0 |  | 0 | FY2022 | 877000 | 877000 | ACTIVITY DATES SET | G | Complete Purchasing Right-of-Way milestone finished on-time | G | Project is on budget | 2019-05-29 | 2019-05-29 | 2019-08-21 | 2019-08-07 | G | 2019-08-22 | 2019-08-08 | 2019-08-26 | 2019-08-14 | G | 2019-08-27 | 2019-08-15 | 2020-03-09 | 2020-01-22 | G | [5 empty] | 2020-05-01 | 2020-05-01 | 2020-05-29 | 2020-05-29 | G | 2020-06-08 | 2020-06-08 | 2020-06-29 | 2020-06-26 | G | 2021-02-01 |  | 2021-04-30 |  | G | 2020-07-31 | 2020-07-08 | 2021-01-29 | 2021-01-29 | G | 2020-12-28 |  | 2021-08-30 |  | G | [5 empty] | 2021-08-31 |  | 2021-08-31 |  | G | 2021-11-30 |  | 2021-11-30 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.173
133 | 115491 | #SMART20 RTE 642 - INTERSECTION REALIGNMENT AT RTE 29 | 0642 | Secondary | Safety | VDOT | Pittsylvania County | HALIFAX | Lynchburg | NonMPO:NonMPO | Infrastructure Investment Division | Robert F Guercia | Robert.Guercia@VDOT.Virginia.gov | (434) 841-6864 | Brian J Casto | Brian.Casto@VDOT.Virginia.gov | (434) 856-8276 |  |  |  | 1 | 2020 | 0 | FY2025 | 4768466 | 4768466 | NO DATES SET YET | G | Start Development milestone is 68 days ahead of the expected completion date | G | Project is on budget | [5 empty] | 2021-04-19 |  | 2021-04-30 |  | G | 2021-05-03 |  | 2021-12-21 |  | G | [5 empty] | 2022-10-25 |  | 2022-11-07 |  | G | 2024-01-04 |  | 2024-01-19 |  | G | 2024-08-08 |  | 2025-02-19 |  | G | 2024-02-06 |  | 2024-08-08 |  | G | [10 empty] | 2025-03-11 |  | 2025-03-11 |  | G | 2025-05-30 |  | 2025-05-30 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.087484
134 | 116934 | #SGR21LP North Main Street-Primary Extension Paving | 0011 | Urban | Resurfacing | VDOT | Marion | ABINGDON | Bristol | NonMPO:NonMPO | Infrastructure Investment/Asset Management Division | James B Parsons | James.Parsons@VDOT.Virginia.gov | (276) 696-3288 | David G Morrison | David.Morrison@VDOT.Virginia.gov | (276) 696-3328 |  |  |  | 0 |  | 1 | FY2021 | 375112 | 375112 | ADVERTISED | G | Solicit Bids milestone finished on-time | G | Project is on budget | [5 empty] | 2020-12-01 | 2020-12-01 | 2020-12-14 | 2020-12-14 | G | 2020-12-15 | 2020-12-15 | 2021-03-01 | 2021-02-09 | G | [35 empty] | 2021-02-09 | 2021-02-09 | 2021-02-09 | 2021-02-09 | G | 2021-04-30 |  | 2021-04-30 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.060373
135 | 117019 | #SGR21VB (07916) RTE. 705 OVER PIGG RIVER - BR REPLACE | 0705 | Secondary | Bridge Replacement w/o Added Capacity | VDOT | Franklin County | BEDFORD | Salem | NonMPO:NonMPO | Infrastructure Investment Division | Anthony T Marshall | Todd.Marshall@VDOT.Virginia.gov | (540) 387-5460 | Tejendrakumar D Patadia | Teju.Patadia@vdot.virginia.gov | (540) 378-5061 |  |  |  | 0 |  | 1 | FY2023 | 8482725 | 8482725 | NO DATES SET YET | G | Determine Requirements milestone is 509 days ahead of the expected completion date | G | Project is on budget | [10 empty] | 2022-07-01 |  | 2022-07-15 |  | G | [25 empty] | 2022-07-01 |  | 2022-12-02 |  | G | [5 empty] | 2022-10-11 |  | 2022-10-11 |  | G | 2023-01-05 |  | 2023-01-05 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.10898
136 | 117778 | SIGNAL MUTCD COMPLIANCE UPGRADES - DISTRICTWIDE | 9999 | Miscellaneous | Safety | VDOT | Richmond District-wide |  | Richmond | Richmond:Richmond District-wide | Infrastructure Investment/Asset Management Division | Adam S Brooks | Adam.Brooks@VDOT.Virginia.gov | (804) 609-5274 | Adam S Brooks | Adam.Brooks@VDOT.Virginia.gov | (804) 609-5274 | N\A |  |  | 0 |  | 0 | FY2023 | 1250000 | 1250000 | NO DATES SET YET | G | Determine Requirements milestone is 577 days ahead of the expected completion date | G | Project is on budget | [10 empty] | 2022-05-16 |  | 2022-09-21 |  | G | [35 empty] | 2022-09-23 |  | 2022-09-29 |  | G | 2022-09-30 |  | 2022-10-06 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | WORK/TASK ORDER | 0 | 0 | 0.060832
137 | 118235 | CITY OF FAIRFAX BIKE SHARE |  | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Fairfax | FAIRFAX | Northern Virginia | Northern Virginia:Fairfax | Local Assistance Division | Andrew G Beacher | Andrew.Beacher@vdot.virginia.gov | (703) 259-2239 | Saif-Ur Qargha | Saif.Qargha@vdot.virginia.gov | (703) 259-3223 | Wendy Sanford | wendy.sanford@fairfaxva.gov | (703) 385-7889 | 0 |  | 0 | FY2025 | 421000 | 421000 | NO DATES SET YET | G | Agreement with Locality milestone is 326 days ahead of the expected completion date | G | Project is on budget | 2021-09-01 | 2021-01-08 | 2022-01-13 |  | G | 2022-01-18 |  | 2022-02-07 |  | G | 2022-03-09 |  | 2022-06-29 |  | G | [10 empty] | 2023-10-19 |  | 2023-11-27 |  | G | [5 empty] | 2023-11-28 |  | 2024-04-29 |  | G | 2024-05-29 |  | 2024-10-25 |  | G | [5 empty] | 2024-08-01 |  | 2024-11-27 |  | G | 2025-02-24 |  | 2025-06-26 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.33284
138 | 51927 | #HB2.FY17 ROUTE 607 - INTERSECTION IMPROVEMENTS | 0607 | Secondary | Safety | VDOT | Greene County | CHARLOTTESVILLE | Culpeper | NonMPO:NonMPO | Infrastructure Investment Division | Dewitt D Sprinkel | Brent.Sprinkel@VDOT.Virginia.gov | (540) 829-7552 | Gabriel M Brown | Gabe.Brown@VDOT.Virginia.gov | (434) 422-9792 |  |  |  | 1 | 2017 | 0 | FY2017 | 4260000 |  | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 53 days early | R | Critical information missing | [5 empty] | 2007-11-01 | 2007-10-19 | 2007-11-01 | 2007-11-01 | G | 2009-11-10 | 2009-11-10 | 2011-01-30 | 2011-09-20 | R | [5 empty] | 2012-01-27 | 2012-01-27 | 2012-03-30 | 2012-03-13 | G | 2012-10-31 | 2013-04-15 | 2012-11-30 | 2013-05-08 | R | 2016-06-02 | 2016-06-01 | 2016-12-01 | 2016-09-27 | G | 2015-02-02 | 2015-03-26 | 2016-06-01 | 2016-05-18 | G | [10 empty] | 2016-09-13 | 2016-09-13 | 2016-09-13 | 2016-09-13 | G | 2016-12-21 | 2016-12-09 | 2017-01-31 | 2016-12-09 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.14895
139 | 81667 | RTE 615 (CREIGHTON RD) - ROUNDABOUT | 0615 | Secondary | Reconstruction w/o Added Capacity | Locally | Hanover County | ASHLAND | Richmond | Richmond:Hanover County | Infrastructure Investment Division | Brian J Lokker | Brian.Lokker@VDOT.Virginia.gov | (804) 524-6010 | Brian J Lokker | Brian.Lokker@VDOT.Virginia.gov | (804) 524-6010 | Randy Hardman | wrhardman@hanovercounty.gov | (804) 365-6181 | 0 |  | 0 | FY2020 | 4836000 | 7754437 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 197 days early | R | Project estimate is less than $5M and is 20% or more over budget | 2009-11-20 | 2009-11-20 | 2009-11-20 | 2009-11-20 | G | 2010-03-29 | 2010-03-29 | 2010-03-29 | 2010-03-29 | G | 2010-07-01 | 2010-07-01 | 2011-03-07 | 2011-03-07 | G | [5 empty] | 2017-06-14 | 2017-06-14 | 2017-06-14 | 2017-06-14 | G | 2013-02-06 | 2013-02-06 | 2013-02-08 | 2013-02-08 | G | [5 empty] | 2013-07-22 | 2013-07-22 | 2019-05-31 | 2018-09-24 | G | [10 empty] | 2019-10-31 | 2019-05-03 | 2019-10-31 | 2019-05-03 | G | 2020-02-28 | 2019-08-15 | 2020-02-28 | 2019-08-15 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.1799
140 | 107271 | Patrick Henry Drive Extension | 0000 | Urban | New Construction Roadway | Locally | Newport News | WILLIAMSBURG | Hampton Roads | Hampton Roads:Newport News | Local Assistance Division | Stephen Rowan | Steve.Rowan@vdot.virginia.gov | (757) 790-9925 | Chessica Villaflores | Chessica.Villaflores@vdot.virginia.gov | (757) 956-3094 | Bryan Stilley | bstilley@nnva.gov | (757) 926-8699 | 0 |  | 0 | FY2019 | 7240369 | 7240369 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 91 days early | G | Project is on budget | 2015-10-01 | 2013-07-03 | 2015-12-30 | 2013-07-03 | G | 2015-12-31 | 2013-07-03 | 2016-01-14 | 2013-07-03 | G | 2016-01-19 | 2018-03-01 | 2016-09-08 | 2018-03-01 | R | [10 empty] | 2018-03-02 | 2018-03-02 | 2018-03-02 | 2018-03-02 | G | [20 empty] | 2018-03-28 | 2018-03-28 | 2018-03-28 | 2018-03-28 | G | 2018-05-01 | 2018-04-25 | 2018-07-25 | 2018-04-25 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.2715
141 | 109249 | MAIN STREET STREETSCAPE - DUNGANNON |  | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Dungannon | WISE | Bristol | NonMPO:NonMPO | Local Assistance Division | Tabitha H Crowder | Tabitha.Crowder@vdot.virginia.gov | (276) 696-3482 | Roger L Musser | Roger.Musser@VDOT.Virginia.gov | (276) 696-3260 | Debra Horne | mayorhorne@townofdungannon.com | (276) 467-2522 | 0 |  | 0 | FY2020 | 176250 | 257590 | CONSTRUCTION STARTED | G | Start Delivery milestone finished on-time | R | Project estimate is less than $5M and is 20% or more over budget | 2018-12-17 | 2018-11-01 | 2019-03-15 | 2019-01-28 | G | 2019-03-18 | 2019-01-29 | 2019-03-20 | 2019-02-01 | G | 2019-03-21 | 2019-02-04 | 2019-09-23 | 2019-07-08 | G | [35 empty] | 2019-11-18 | 2019-11-18 | 2020-03-02 | 2020-03-02 | G | 2020-05-19 | 2020-05-19 | 2020-06-09 | 2020-06-09 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.34588
142 | 109534 | #HB2.FY17 RTE 29 - RIGHT TURN LANES AT RTE 655 | 0029 | Primary | Safety | VDOT | Nelson County | APPOMATTOX | Lynchburg | NonMPO:NonMPO | Infrastructure Investment Division | Daniel J Brown | Daniel.Brown@VDOT.Virginia.gov | (434) 856-8265 | Stanley E Murphy | Stanley.Murphy@VDOT.Virginia.gov | (434) 856-8285 |  |  |  | 1 | 2017 | 0 | FY2020 | 1133329 | 848585 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 78 days early | G | Project is on budget | [5 empty] | 2016-08-16 | 2016-08-16 | 2016-08-17 | 2016-08-17 | G | 2016-08-17 | 2016-08-17 | 2017-02-28 | 2017-03-01 | R | [5 empty] | 2017-07-28 | 2017-07-28 | 2017-08-10 | 2017-08-10 | G | 2018-05-16 | 2018-05-11 | 2018-05-30 | 2018-05-11 | G | 2018-12-10 | 2018-05-11 | 2019-04-05 | 2018-05-11 | G | 2018-06-15 | 2018-05-11 | 2018-12-07 | 2018-05-11 | G | [10 empty] | 2019-04-09 | 2019-02-12 | 2019-04-09 | 2019-02-12 | G | 2019-05-23 | 2019-04-29 | 2019-07-19 | 2019-05-02 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.098528
143 | 111017 | #SMART18 - Brambleton Ave/ Tidewater Dr. Intersection Imprv. | 0168 | Urban | Reconstruction w/ Added Capacity | Locally | Norfolk | NORFOLK | Hampton Roads | Hampton Roads:Norfolk | Infrastructure Investment Division | Todd M Halacy | Todd.Halacy@VDOT.Virginia.gov | (757) 956-3010 | Derrick Williams | Derrick.Williams@vdot.virginia.gov | (757) 956-3097 | Deborah A. Mangiaracina, PE | deborah.mangiaracina@norfolk.gov | (757) 664-7459 | 1 | 2018 | 0 | FY2023 | 645500 | 645500 | NO DATES SET YET | R | Agreement with Locality milestone is 194 days past the expected completion date | G | Project is on budget | 2020-05-18 |  | 2020-08-11 |  | R | 2020-08-12 |  | 2020-08-17 |  | R | 2020-08-18 |  | 2021-03-01 |  | Y | [35 empty] | 2022-07-19 |  | 2022-08-15 |  | G | 2022-08-16 |  | 2022-09-26 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.32264
144 | 111091 | #SMART18 - Jefferson Ave/Yorktown Rd Intersection Improvemnt | 0000 | Urban | Reconstruction w/ Added Capacity | Locally | Newport News | WILLIAMSBURG | Hampton Roads | Hampton Roads:Newport News | Infrastructure Investment Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Chessica Villaflores | Chessica.Villaflores@vdot.virginia.gov | (757) 956-3094 | Bryan Stilley | bstilley@nnva.gov | (757) 926-8699 | 1 | 2018 | 0 | FY2025 | 2460000 | 2460000 | NO DATES SET YET | G | Agreement with Locality milestone is 187 days ahead of the expected completion date | G | Project is on budget | 2021-06-04 |  | 2021-08-27 |  | G | 2021-08-30 |  | 2021-09-01 |  | G | 2021-09-02 |  | 2022-03-16 |  | G | [10 empty] | 2023-02-22 |  | 2023-03-13 |  | G | [5 empty] | 2023-04-04 |  | 2024-04-03 |  | G | [10 empty] | 2024-04-19 |  | 2024-06-14 |  | G | 2024-06-17 |  | 2024-12-09 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.3412
146 | 112706 | WESTLAKE MULTIUSE TRAIL |  | Miscellaneous | Facilities for Pedestrians and Bicycles | Locally | Franklin County | BEDFORD | Salem | NonMPO:NonMPO | Local Assistance Division | Jessie Nester | Jessie.Nester@vdot.virginia.gov | (540) 613-4115 | Jessie Nester | Jessie.Nester@vdot.virginia.gov | (540) 613-4115 | STEVE SANDY | STEVE.SANDY@FRANKLINCOUNTYVA.GOV | (540) 483-3030 | 0 |  | 0 | FY2024 | 2359636 | 2359636 | ACTIVITY DATES SET | R | Determine Requirements milestone finished 622 days late | G | Project is on budget | 2018-05-01 | 2018-04-12 | 2018-07-25 | 2018-05-07 | G | 2018-07-26 | 2018-07-31 | 2018-07-30 | 2018-07-31 | R | 2018-07-31 | 2019-01-23 | 2019-02-08 | 2020-10-22 | R | [10 empty] | 2021-10-11 |  | 2022-04-21 |  | G | [5 empty] | 2022-04-25 |  | 2023-04-25 |  | G | 2022-12-14 |  | 2023-04-25 |  | G | [5 empty] | 2023-08-18 |  | 2023-09-29 |  | G | 2023-12-22 |  | 2024-05-16 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.22834
147 | 113616 | MANASSAS CITY PRIMARY EXTENSION PAVING FY19 - SUDLEY ROAD | 0234 | Urban | Resurfacing | Locally | Manassas | MANASSAS | Northern Virginia | Northern Virginia:Manassas | Local Assistance Division | Amir Salahshoor | A.Salahshoor@VDOT.Virginia.gov | (703) 259-1957 | Rita Hockman | Rita.Hockman@vdot.virginia.gov | (804) 824-7421 | Steve Burke | sburke@ci.manassas.va.us | (703) 257-8476 | 0 |  | 0 | FY2019 | 256365 | 256365 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 108 days early | G | Project is on budget | 2018-07-02 | 2018-07-02 | 2018-09-25 | 2018-10-12 | R | [5 empty] | 2018-09-26 | 2018-10-16 | 2018-11-28 | 2018-10-16 | G | [35 empty] | 2018-11-02 | 2018-10-16 | 2018-12-04 | 2018-10-16 | G | 2018-12-05 | 2018-10-16 | 2019-02-01 | 2018-10-16 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.094521
148 | 113776 | RTE 720 - RURAL RUSTIC RD (SURFACE TREAT NON-HARDSURFACE RD) | 0720 | Secondary | Reconstruction w/o Added Capacity | VDOT | Albemarle County | CHARLOTTESVILLE | Culpeper | NonMPO:NonMPO | Infrastructure Investment Division | Ken Connors |  |  | Harold L Jones | Harold.Jones@VDOT.virginia.gov | (434) 422-9378 |  |  |  | 0 |  | 0 | FY2023 | 102500 | 102500 | NO DATES SET YET | R | Start Development milestone is 130 days past the expected completion date | Y | Estimate not current | [5 empty] | 2020-10-01 |  | 2020-10-14 |  | R | 2020-10-15 |  | 2021-06-11 |  | G | [5 empty] | 2022-03-22 |  | 2022-05-02 |  | G | [5 empty] | 2022-08-16 |  | 2022-12-12 |  | G | [5 empty] | 2022-08-01 |  | 2022-11-01 |  | G | [5 empty] | 2023-01-10 |  | 2023-01-10 |  | G | 2023-03-06 |  | 2023-03-24 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | SAAP CONTRACT | 0 | 0 | 0.15582
149 | 113849 | Jefferson Avenue Sidewalk | 0143 | Urban | Facilities for Pedestrians and Bicycles | Locally | Newport News | WILLIAMSBURG | Hampton Roads | Hampton Roads:Newport News | Infrastructure Investment Division | Susan Wilson | Susan.Wilson@vdot.virginia.gov | (757) 956-3099 | Chessica Villaflores | Chessica.Villaflores@vdot.virginia.gov | (757) 956-3094 | Bryan Stilley, P.E. | bstilley@nnva.gov | (757) 926-8699 | 0 |  | 0 | FY2025 | 1010000 | 1010000 | NO DATES SET YET | G | Agreement with Locality milestone is 222 days ahead of the expected completion date | G | Project is on budget | 2021-07-01 |  | 2021-10-01 |  | G | 2021-10-04 |  | 2021-10-15 |  | G | 2021-10-19 |  | 2022-04-28 |  | G | [10 empty] | 2023-05-02 |  | 2023-05-22 |  | G | [5 empty] | 2023-05-24 |  | 2024-03-07 |  | G | 2022-06-06 |  | 2023-02-10 |  | G | [5 empty] | 2024-03-25 |  | 2024-04-19 |  | G | 2024-07-10 |  | 2024-07-10 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.2547
150 | 104890 | RTE 360 E (Lonas Pkwy to Castle Rock Rd) - WIDENING | 0360 | Primary | Reconstruction w/ Added Capacity | Locally | Chesterfield County | CHESTERFIELD | Richmond | Richmond:Chesterfield County | Infrastructure Investment Division | Brian J Lokker | Brian.Lokker@VDOT.Virginia.gov | (804) 524-6010 | Brian J Lokker | Brian.Lokker@VDOT.Virginia.gov | (804) 524-6010 | Barb Smith | smithbk@chesterfield.gov | (804) 748-1037 | 0 |  | 0 | FY2021 | 7449000 | 7818000 | AWARDED | G | Start Delivery milestone finished 41 days early | Y | Project estimate is between $5M and $10M and is up to $1M over budget | 2017-01-31 | 2017-01-06 | 2017-01-31 | 2017-01-06 | G | 2016-12-31 | 2017-01-27 | 2016-12-31 | 2017-01-27 | R | 2018-12-03 | 2018-12-03 | 2019-02-01 | 2019-01-28 | G | [5 empty] | 2019-01-17 | 2019-01-17 | 2019-02-22 | 2019-02-19 | G | 2019-02-25 | 2019-03-07 | 2019-07-15 | 2019-03-14 | G | [5 empty] | 2019-07-25 | 2019-03-22 | 2020-07-24 | 2020-02-20 | G | [10 empty] | 2020-10-15 | 2020-10-15 | 2020-10-15 | 2020-10-15 | G | 2020-11-16 | 2020-11-16 | 2021-02-15 | 2021-01-05 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.13984
151 | 108907 | #HB2.FY17 US 460 S Curves | 0460 | Primary | Reconstruction w/o Added Capacity | VDOT | Bedford County | BEDFORD | Salem | NonMPO:NonMPO | Infrastructure Investment Division | Thomas W Digiulian | Thomas.DiGiulian@VDOT.Virginia.gov | (540) 387-5356 | Anthony L Handy | Tony.Handy@VDOT.Virginia.gov | (540) 352-9050 |  |  |  | 1 | 2017 | 0 | FY2020 | 18829369 | 15314217 | CONSTRUCTION STARTED | R | Start Delivery milestone finished 32 days late | G | Project is on budget | [5 empty] | 2016-06-21 | 2016-06-21 | 2016-07-05 | 2016-07-05 | G | 2016-07-06 | 2016-07-06 | 2016-12-28 | 2016-12-28 | G | [5 empty] | 2017-06-29 | 2017-04-19 | 2017-07-13 | 2017-07-10 | G | 2018-10-29 | 2018-10-16 | 2018-11-09 | 2018-11-09 | G | 2019-04-12 | 2019-04-02 | 2019-12-16 | 2020-05-22 | R | 2018-11-30 | 2018-11-16 | 2019-07-08 | 2019-06-03 | G | 2017-07-17 | 2017-07-17 | 2019-07-08 | 2019-03-28 | G | [5 empty] | 2020-01-14 | 2019-12-10 | 2020-01-14 | 2019-12-10 | G | 2020-03-02 | 2020-04-21 | 2020-03-20 | 2020-04-21 | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 1 | 0.28359
152 | 109528 | #HB2.FY17 RTE 151 - RIGHT TURN LANE AT RTE 664 | 0151 | Primary | Safety | VDOT | Nelson County | APPOMATTOX | Lynchburg | NonMPO:NonMPO | Infrastructure Investment Division | Raina A Rosado | Raina.Rosado@VDOT.Virginia.gov | (434) 856-8318 | Raina A Rosado | Raina.Rosado@VDOT.Virginia.gov | (434) 856-8318 |  |  |  | 1 | 2017 | 0 | FY2020 | 925177 | 925177 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 115 days early | G | Project is on budget | [5 empty] | 2016-08-16 | 2016-08-16 | 2016-08-17 | 2016-08-17 | G | 2016-08-19 | 2016-08-19 | 2017-02-23 | 2017-03-22 | R | [5 empty] | 2017-09-08 | 2017-08-21 | 2017-09-21 | 2017-08-25 | G | 2018-04-30 | 2018-02-05 | 2018-05-11 | 2018-02-22 | G | 2018-11-20 | 2018-08-27 | 2019-05-30 | 2019-01-02 | G | 2018-05-30 | 2018-03-07 | 2018-11-19 | 2018-08-13 | G | [10 empty] | 2019-06-11 | 2019-03-12 | 2019-06-11 | 2019-03-12 | G | 2019-07-26 | 2019-05-28 | 2019-09-20 | 2019-05-28 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.098504
153 | 110032 | #SGR17VB - MAJOR BRIDGE REHABILITATION AT RT 236 OVER I-395 | 0236 | Primary | Bridge Rehab w/o Added Capacity | VDOT | Alexandria | FAIRFAX | Northern Virginia | Northern Virginia:Alexandria | Infrastructure Investment/Asset Management Division | Gary Runco | Gary.Runco@vdot.virginia.gov | (703) 259-3341 | Sharif Ramsis | Sharif.Ramsis@vdot.virginia.gov | (703) 259-2607 |  |  |  | 0 |  | 1 | FY2022 | 15735787 | 16678401 | ADVERTISED | G | Solicit Bids milestone finished 9 days early | Y | Project estimate is greater than $10M and is over budget by (a) up to 10% or (b) up to $5M | [5 empty] | 2016-09-01 | 2016-09-15 | 2016-09-15 | 2016-09-15 | G | 2016-09-16 | 2016-09-16 | 2017-10-19 | 2017-03-08 | G | [25 empty] | 2017-01-19 | 2017-01-19 | 2017-01-20 | 2017-01-20 | G | [5 empty] | 2021-01-21 | 2021-01-12 | 2021-01-21 | 2021-01-12 | G | 2021-03-05 |  | 2021-08-31 |  | G | Final design is still underway | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.1528
154 | 111032 | #SGR18LB - Triple Decker Bridge - Lower Level |  | Urban | Bridge Rehab w/o Added Capacity | Locally | Chesapeake | NORFOLK | Hampton Roads | Hampton Roads:Chesapeake | Local Assistance Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Johndel A Alcaide | John.Alcaide@vdot.virginia.gov | (757) 956-3098 | Earl Sorey PE | easorey@cityofchesapeake.net | (757) 382-6101 | 0 |  | 1 | FY2022 | 2672200 | 2672200 | NO DATES SET YET-PE OPEN | Y | Determine Requirements milestone is 9 days ahead of the expected completion date and there is a risk of missing this milestone date | G | Project is on budget | 2020-05-11 | 2018-05-08 | 2020-08-04 | 2018-08-01 | G | 2020-08-05 | 2020-01-31 | 2020-08-18 | 2020-02-03 | G | 2020-08-19 |  | 2021-03-02 |  | Y | [25 empty] | 2021-03-03 | 2020-09-16 | 2021-11-01 | 2020-10-14 | G | [5 empty] | 2022-01-19 |  | 2022-02-15 |  | G | 2022-05-05 |  | 2022-05-05 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.19408
155 | 111405 | HILLSBORO GAPWAY SHARED-USE PATH |  | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Hillsboro | LEESBURG | Northern Virginia | Northern Virginia:Loudoun County | Local Assistance Division | Bud Siegel |  |  | Christer P Carshult | Christer.Carshult@vdot.virginia.gov | (703) 259-1765 | Town of Hillsboro |  |  | 0 |  | 0 | FY2021 | 640811 | 640811 | ACTIVITY DATES SET | R | Solicit Bids milestone is 114 days past the expected completion date | Y | Estimate not current | 2017-10-02 | 2017-10-02 | 2018-01-31 | 2018-01-30 | G | 2018-02-01 | 2018-01-25 | 2018-02-05 | 2018-02-20 | R | 2018-02-06 | 2018-02-06 | 2018-08-09 | 2018-08-23 | R | [35 empty] | 2020-04-21 |  | 2020-10-30 |  | R | 2020-11-02 |  | 2021-04-12 |  | G | Delay due to unforeseen issues with utilities, railroad coordination, or right-of-way acquisition | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.4874
156 | 111730 | #SMART18 - ROUTE 151/US 250 INTERSECTION IMPROVEMENTS | 0250 | Primary | Safety | VDOT | Albemarle County | CHARLOTTESVILLE | Culpeper | NonMPO:NonMPO | Infrastructure Investment Division | Gregory J Cooley | Gregory.Cooley@vdot.virginia.gov | (434) 906-7979 | William E Stowe | William.Stowe@vdot.virginia.gov | (540) 827-7287 |  |  |  | 1 | 2018 | 0 | FY2019 | 5800000 | 5878829 | CONSTRUCTION STARTED | R | Start Delivery milestone finished 34 days late | Y | Project estimate is between $5M and $10M and is up to $1M over budget | [5 empty] | 2017-08-01 | 2017-10-26 | 2017-08-14 | 2017-10-26 | R | 2017-08-15 | 2017-10-29 | 2018-07-13 | 2017-10-29 | G | [10 empty] | 2018-11-01 | 2018-11-01 | 2018-11-14 | 2018-11-14 | G | [20 empty] | 2018-10-30 | 2018-10-30 | 2018-11-27 | 2018-11-27 | G | 2019-05-28 | 2019-06-26 | 2019-06-19 | 2019-07-23 | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | DESIGN BUILD/PPTA | 1 | 0 | 0.15625
157 | 113296 | East Richmond Rd over Stony Run - Bridge Replacement | 7573 | Primary | Bridge Replacement w/o Added Capacity | Locally | Richmond | ASHLAND | Richmond | Richmond:Richmond | Local Assistance Division | Douglas L Orcutt | Doug.Orcutt@vdot.virginia.gov | (804) 609-5428 | Douglas L Orcutt | Doug.Orcutt@vdot.virginia.gov | (804) 609-5428 | Tom Westbrook | thomas.westbrook@richmondgov.com |  | 0 |  | 0 | FY2025 | 2247007 | 3050000 | ACTIVITY DATES SET | R | Determine Requirements milestone finished 73 days late | R | Project estimate is less than $5M and is 20% or more over budget | 2018-07-02 | 2018-07-02 | 2018-11-07 | 2018-07-10 | G | 2018-11-08 | 2018-12-14 | 2018-12-03 | 2018-12-17 | R | 2019-01-03 | 2018-12-20 | 2019-04-29 | 2019-07-11 | R | 2019-09-16 |  | 2022-02-17 |  | G | [5 empty] | 2019-07-02 |  | 2022-08-05 |  | G | 2023-04-24 |  | 2023-09-18 |  | G | 2022-08-08 |  | 2023-04-21 |  | G | 2023-05-23 |  | 2023-10-20 |  | G | [5 empty] | 2023-12-18 |  | 2023-12-18 |  | G | 2024-05-23 |  | 2024-07-05 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.14378
158 | 113742 | RTE 780-RURAL RUSTIC RD (SURFACE TREAT NON-HARD SURFACE RD) | 0780 | Secondary | Reconstruction w/o Added Capacity | VDOT | Fauquier County | WARRENTON | Culpeper | NonMPO:NonMPO | Infrastructure Investment Division | Ken Connors |  |  | Benjamin Davison | Ben.Davison@vdot.virginia.gov | (540) 347-6446 |  |  |  | 0 |  | 0 | FY2026 | 450000 | 450000 | NO DATES SET YET | G | Start Development milestone is 964 days ahead of the expected completion date | Y | Estimate not current | [5 empty] | 2023-10-02 |  | 2023-10-13 |  | G | 2023-10-17 |  | 2024-06-11 |  | G | [5 empty] | 2025-02-20 |  | 2025-04-02 |  | G | [5 empty] | 2025-07-17 |  | 2025-11-07 |  | G | [5 empty] | 2025-07-01 |  | 2025-10-01 |  | G | [5 empty] | 2025-11-10 |  | 2025-11-10 |  | G | 2026-02-06 |  | 2026-02-06 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | SAAP CONTRACT | 0 | 0 | 0.10378
159 | 113843 | Route 1 (Merriewood Rd to Elliham Ave) Sidewalk | 0001 | Primary | Facilities for Pedestrians and Bicycles | Locally | Chesterfield County | CHESTERFIELD | Richmond | Richmond:Chesterfield County | Infrastructure Investment Division | Michael S Gray | Mike.Gray@vdot.virginia.gov | (804) 609-5347 | Michael S Gray | Mike.Gray@vdot.virginia.gov | (804) 609-5347 | Barb Smith | smithbk@chesterfield.gov | 7481037 | 0 |  | 0 | FY2024 | 1686000 | 1686000 | NO DATES SET YET-PE OPEN | R | Engage Public milestone is 83 days past the expected completion date | G | Project is on budget | 2021-07-01 | 2019-02-19 | 2021-09-24 | 2019-03-27 | G | 2021-09-27 | 2019-05-06 | 2021-09-29 | 2019-06-04 | G | 2021-09-30 | 2019-06-05 | 2022-04-12 |  | G | [5 empty] | 2020-11-30 |  | 2020-11-30 |  | R | 2023-02-07 |  | 2023-02-28 |  | G | 2022-04-01 |  | 2023-03-31 |  | G | 2023-03-02 |  | 2023-12-08 |  | G | 2022-05-18 | 2020-02-13 | 2023-01-25 |  | G | [5 empty] | 2023-12-27 |  | 2024-01-26 |  | G | 2024-04-16 |  | 2024-04-16 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.13387
160 | 113982 | #SGR19VB - RT 58 VA Structure #1808 Federal #22453 | 0058 | Primary | Bridge Rehab w/o Added Capacity | VDOT | Norton | WISE | Bristol | NonMPO:NonMPO | Infrastructure Investment/Asset Management Division | Gary Lester |  |  | Darshan K Bansal | Darshan.Bansal@vdot.virginia.gov | (276) 696-3364 |  |  |  | 0 |  | 1 | FY2022 | 3022516 | 3022516 | NO DATES SET YET | G | Determine Requirements milestone is 268 days ahead of the expected completion date | G | Project is on budget | [10 empty] | 2021-11-02 |  | 2021-11-16 |  | G | [35 empty] | 2021-12-14 |  | 2021-12-14 |  | G | 2022-03-10 |  | 2022-03-10 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.16693
162 | 116007 | District-wide Pedestrian Crossings Installations | 9999 | Miscellaneous | Safety | VDOT | Culpeper District-wide |  | Culpeper | NonMPO:NonMPO | Infrastructure Investment/Asset Management Division | Gregory J Cooley | Gregory.Cooley@vdot.virginia.gov | (434) 906-7979 | Caroline Awua-Mensah | Caroline.Awua-Mensah@vdot.virginia.gov | (540) 829-7618 |  |  |  | 0 |  | 0 | FY2024 | 806956 | 806956 | NO DATES SET YET-PE OPEN | R | Determine Requirements milestone is 52 days past the expected completion date | G | Project is on budget | [5 empty] | 2020-06-04 | 2020-06-01 | 2020-06-23 | 2020-06-11 | G | 2020-06-24 | 2020-06-24 | 2020-12-31 |  | R | [35 empty] | 2021-11-09 |  | 2024-04-09 |  | G | 2024-06-28 |  | 2024-06-28 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.10443
163 | 116860 | FEDERAL STREET PATH, BLOCK 2 |  | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Harrisonburg | HARRISONBURG | Staunton | Harrisonburg:Harrisonburg | Local Assistance Division | Kimberly Cameron | Kim.Cameron@vdot.virginia.gov | (540) 332-7886 | Michael S Fulcher | Michael.Fulcher@VDOT.Virginia.gov | (540) 332-2243 | Erin Yancey | tom.hartman@harrisonburgva.gov | (540) 434-5928 | 0 |  | 0 | FY2024 | 539974 | 539974 | NO DATES SET YET | G | Agreement with Locality milestone is 57 days ahead of the expected completion date | G | Project is on budget | 2020-12-08 |  | 2021-04-19 |  | G | 2021-04-20 |  | 2021-05-10 |  | G | 2021-06-09 |  | 2021-09-30 |  | G | [10 empty] | 2023-01-27 |  | 2023-03-03 |  | G | [5 empty] | 2023-03-06 |  | 2023-08-01 |  | G | 2023-06-28 |  | 2023-11-29 |  | G | [5 empty] | 2023-11-03 |  | 2023-12-05 |  | G | 2024-02-28 |  | 2024-02-28 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.2128
164 | 117030 | RURAL ADDITION - PAVE UNPAVED EGRET COURT (GLEBE HARBOR SUB) | 9999 | Secondary | Resurfacing | VDOT | Westmoreland County | NORTHERN NECK | Fredericksburg | NonMPO:NonMPO | Local Assistance Division | David L Beale | David.Beale@vdot.virginia.gov | (804) 333-7941 | William C White | Carter.White@VDOT.Virginia.gov | (804) 333-7942 |  |  |  | 0 |  | 0 | FY2029 | 80000 | 80000 | NO DATES SET YET | G | Start Development milestone is 1704 days ahead of the expected completion date | G | Project is on budget | [5 empty] | 2025-10-01 |  | 2025-10-22 |  | G | 2025-10-23 |  | 2026-08-26 |  | G | [5 empty] | 2027-04-01 |  | 2027-04-28 |  | G | [5 empty] | 2027-12-21 |  | 2028-04-24 |  | G | [5 empty] | 2027-09-09 |  | 2028-02-14 |  | G | [5 empty] | 2028-05-09 |  | 2028-05-09 |  | G | 2028-07-28 |  | 2028-07-28 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | SAAP CONTRACT | 0 | 0 | 0.089502
165 | 118066 | Courthouse (Courts Complex - RT10) Trail |  | Primary | Facilities for Pedestrians and Bicycles | Locally | Chesterfield County | CHESTERFIELD | Richmond | Richmond:Chesterfield County | Local Assistance Division | Jorg Huckabee-Mayfield | Jorg.Huckabee-Mayfield@VDOT.Virginia.gov | (804) 609-5292 | Jorg Huckabee-Mayfield | Jorg.Huckabee-Mayfield@VDOT.Virginia.gov | (804) 609-5292 | Nate Mathis | mathisn@chesterfield.gov | (804) 748-1037 | 0 |  | 0 | FY2025 | 550000 | 550000 | NO DATES SET YET | G | Agreement with Locality milestone is 199 days ahead of the expected completion date | G | Project is on budget | 2021-05-03 |  | 2021-09-08 |  | G | 2021-09-09 |  | 2021-09-29 |  | G | 2021-10-29 |  | 2022-03-01 |  | G | [10 empty] | 2023-06-19 |  | 2023-07-24 |  | G | [5 empty] | 2023-07-25 |  | 2023-12-26 |  | G | 2023-11-20 |  | 2024-04-23 |  | G | [5 empty] | 2024-04-02 |  | 2024-04-29 |  | G | 2024-07-18 |  | 2024-07-18 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.20355
166 | 118156 | Brad McNeer Parkway Access Management and Roundabout | 9999 | Secondary | Safety | Locally | Chesterfield County | CHESTERFIELD | Richmond | Richmond:Chesterfield County | Infrastructure Investment Division | Michael S Gray | Mike.Gray@vdot.virginia.gov | (804) 609-5347 | Michael S Gray | Mike.Gray@vdot.virginia.gov | (804) 609-5347 | Chessa Faulkner | faulknerc@chesterfield.gov | (804) 748-1037 | 0 |  | 0 | FY2028 | 9336000 | 9336000 | NO DATES SET YET | G | Agreement with Locality milestone is 1179 days ahead of the expected completion date | G | Project is on budget | 2024-01-08 |  | 2024-05-15 |  | G | 2024-05-16 |  | 2024-06-06 |  | G | 2024-12-16 |  | 2025-04-11 |  | G | [10 empty] | 2026-07-31 |  | 2026-09-03 |  | G | [5 empty] | 2026-09-04 |  | 2027-02-10 |  | G | 2027-01-06 |  | 2027-06-07 |  | G | [5 empty] | 2027-05-14 |  | 2027-06-11 |  | G | 2027-08-31 |  | 2027-08-31 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 1 | 0.20989
167 | 80561 | DEVELOP ORANGE AVENUE TO URBAN 6 LANES |  | Urban | Reconstruction w/ Added Capacity | VDOT | Roanoke | SALEM | Salem | Roanoke:Roanoke City | Infrastructure Investment Division | Thomas W Digiulian | Thomas.DiGiulian@VDOT.Virginia.gov | (540) 387-5356 | Phillip V Hammack | Phillip.Hammack@VDOT.Virginia.gov | (540) 378-5041 |  |  |  | 0 |  | 0 | FY2031 | 1020847 | 1020847 | WAITING FINANCIAL CLOSURE | G | Start Development milestone finished 12 days early | Y | Estimate not current | [5 empty] | 2007-04-02 | 2007-02-23 | 2007-04-30 | 2007-04-18 | G | 2007-04-26 | 2007-04-26 | 2027-10-29 |  | G | [10 empty] | 2030-02-12 |  | 2030-02-26 |  | G | [20 empty] | 2031-01-08 |  | 2031-02-12 |  | G | 2031-04-25 |  | 2031-06-20 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 1 | 0.36412
168 | 97715 | Wythe Creek Road - Widen to 3 Lanes | 0172 | Urban | Reconstruction w/ Added Capacity | VDOT | Hampton | WILLIAMSBURG | Hampton Roads | Hampton Roads:Hampton | Infrastructure Investment Division | Samba Secka | Samba.Secka@vdot.virginia.gov | (757) 956-3058 | Samba Secka | Samba.Secka@vdot.virginia.gov | (757) 956-3058 | Sandon Rogers, P.E. | Sandon.rogers@hampton.gov | (757) 727-6786 | 0 |  | 0 | FY2020 | 29768934 | 41521750 | ACTIVITY DATES SET | R | Solicit Bids milestone is 530 days past the expected completion date | R | Project estimate is greater than $10M and is over budget by (a) 10% or more or (b) $5M or more | [5 empty] | 2011-10-01 | 2011-02-28 | 2011-10-01 | 2011-02-28 | G | 2014-06-04 | 2014-06-04 | 2015-08-04 | 2015-08-14 | R | [5 empty] | 2015-09-18 | 2015-09-18 | 2015-10-05 | 2015-10-05 | G | 2016-11-07 | 2016-11-07 | 2016-11-15 | 2016-11-15 | G | 2016-06-03 | 2016-06-03 | 2019-10-14 | 2020-01-17 | R | 2017-03-10 | 2017-03-10 | 2018-06-29 | 2018-06-08 | G | [10 empty] | 2019-09-10 |  | 2019-09-10 |  | R | 2019-10-24 |  | 2020-02-24 |  | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 1 | 0.31042
169 | 102990 | Nansemond Parkway Traffic Signal Upgrades | 0000 | Urban | Traffic Management/Engineering | Locally | Suffolk | NORFOLK | Hampton Roads | Hampton Roads:Suffolk | Infrastructure Investment Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Johndel A Alcaide | John.Alcaide@vdot.virginia.gov | (757) 956-3098 | Robert Lewis | relewis@suffolkva.us | (757) 514-7621 | 0 |  | 0 | FY2020 | 2748000 | 1696132 | ACTIVITY DATES SET | R | Solicit Bids milestone is 297 days past the expected completion date | G | Project is on budget | 2018-07-02 | 2018-09-19 | 2018-09-25 | 2018-12-05 | R | 2018-09-26 | 2018-12-06 | 2018-10-09 | 2018-12-20 | R | 2019-01-24 | 2019-04-02 | 2019-12-23 | 2019-11-12 | G | [35 empty] | 2020-03-20 |  | 2020-04-30 |  | R | 2020-06-03 |  | 2020-06-30 |  | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.2866
170 | 113850 | #SGR19VB - BRIDGE REPLACE RT 607 DRAGON RUN ID 06145 | 0607 | Secondary | Bridge Replacement w/ Added Capacity | VDOT | Essex County | SALUDA | Fredericksburg | NonMPO:NonMPO | Infrastructure Investment/Asset Management Division | Jessica Graves | Jessica.Graves@vdot.virginia.gov | (540) 899-4267 | Jessica Graves | Jessica.Graves@vdot.virginia.gov | (540) 899-4267 |  |  |  | 0 |  | 1 | FY2025 | 3000000 | 3000000 | NO DATES SET YET-PE OPEN | G | Start Development milestone finished 8 days early | G | Project is on budget | [5 empty] | 2020-08-03 | 2020-07-13 | 2020-08-14 | 2020-08-06 | G | 2020-08-17 | 2020-08-10 | 2021-07-15 |  | G | [5 empty] | 2022-06-20 |  | 2022-07-01 |  | G | 2023-09-01 |  | 2023-09-15 |  | G | 2024-02-15 |  | 2024-08-19 |  | G | 2023-10-02 |  | 2024-04-11 |  | G | 2023-08-25 |  | 2024-05-02 |  | G | [5 empty] | 2024-09-10 |  | 2024-09-10 |  | G | 2024-12-04 |  | 2024-12-04 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.071354
171 | 114536 | FAUQUIER COUNTY - WARRENTON BRANCH GREENWAY | 9999 | Secondary | Facilities for Pedestrians and Bicycles | Locally | Fauquier County | WARRENTON | Culpeper | NonMPO:NonMPO | Local Assistance Division | John P Price | John.Price@VDOT.Virginia.gov | (540) 347-6371 | John P Price | John.Price@VDOT.Virginia.gov | (540) 347-6371 | Gary Rzepecki | Gary.Rzepecki@fauquiercounty.gov | (540) 422-8550 | 0 |  | 0 | FY2021 | 997018 | 1339808 | AWARDED | G | Start Delivery milestone finished 181 days early | R | Project estimate is less than $5M and is 20% or more over budget | 2018-12-04 | 2018-11-18 | 2019-03-04 | 2019-02-19 | G | 2019-03-05 | 2019-02-20 | 2019-03-07 | 2019-03-20 | R | 2019-03-08 | 2019-01-31 | 2019-09-10 | 2019-08-30 | G | [25 empty] | 2020-03-30 | 2019-09-03 | 2020-12-01 | 2019-09-03 | G | [5 empty] | 2020-12-16 | 2020-05-13 | 2021-01-14 | 2020-06-30 | G | 2021-04-07 | 2020-08-21 | 2021-04-07 | 2020-10-08 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.16551
172 | 115371 | N. Great Neck/London Bridge & Virginia Beach Blvd Int Improv | 0058 | Urban | Traffic Management/Engineering | Locally | Virginia Beach | NORFOLK | Hampton Roads | Hampton Roads:Virginia Beach | Infrastructure Investment Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Marci Thompson | Marci.Thompson@vdot.virginia.gov | (757) 956-3093 | Katie Shannon | kshannon@vbgov.com | (757) 385-1514 | 0 |  | 0 | FY2027 | 2157100 | 2157100 | NO DATES SET YET | G | Agreement with Locality milestone is 1311 days ahead of the expected completion date | G | Project is on budget | 2024-07-01 |  | 2024-09-24 |  | G | 2024-09-25 |  | 2024-09-27 |  | G | 2024-09-30 |  | 2025-04-10 |  | G | [25 empty] | 2025-05-16 |  | 2026-01-23 |  | G | [5 empty] | 2026-04-29 |  | 2026-05-27 |  | G | 2026-08-14 |  | 2026-08-14 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.2517
173 | 116039 | #I81CIP DMS INSTALLATION | 0081 | Interstate | Traffic Management/Engineering | VDOT | Statewide |  | Statewide | Multiple MPOs:Statewide | Infrastructure Investment Division | Keith M Rider | Keith.Rider@VDOT.Virginia.gov | (434) 856-8145 | Kunal Kothawade | Kunal.Kothawade@vdot.virginia.gov | (540) 332-9259 |  |  |  | 0 |  | 0 | FY2020 | 12600000 | 12500000 | CONSTRUCTION STARTED | R | Relocate Utilities milestone is 556 days past the expected completion date | G | Project is on budget | [5 empty] | 2019-08-01 | 2019-08-22 | 2019-08-14 | 2019-08-22 | R | 2019-08-15 | 2019-08-15 | 2020-04-10 | 2019-08-15 | G | [5 empty] | 2019-10-03 |  | 2019-10-03 |  | R | [5 empty] | 2019-08-15 |  | 2019-08-15 |  | R | [15 empty] | 2020-01-14 | 2019-11-05 | 2020-01-14 | 2019-11-05 | G | 2020-04-07 | 2020-03-04 | 2020-04-07 | 2020-03-04 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 1 | 0.3848
174 | 116989 | #SGR21VP PM-9L-21 PRIMARY PLANT MIX | 9999 | Primary | Resurfacing | VDOT | Northern Virginia District-wide |  | Northern Virginia | Northern Virginia:Northern Virginia District-wide | Infrastructure Investment/Asset Management Division | Todd L Robson | Todd.Robson@VDOT.Virginia.gov | (703) 259-1992 | Harihar Shiwakoti | Harihar.Shiwakoti@vdot.virginia.gov | (703) 259-2292 |  |  |  | 0 |  | 1 | FY2022 | 2663436 | 3627520 | ADVERTISED | G | Solicit Bids milestone finished 91 days early | R | Project estimate is less than $5M and is 20% or more over budget | [10 empty] | 2020-04-10 | 2020-08-10 | 2020-04-16 | 2020-10-29 | R | [35 empty] | 2020-11-10 | 2021-01-12 | 2021-04-13 | 2021-01-12 | G | 2021-07-02 |  | 2021-07-02 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.079558
175 | 117773 | INSTALL GUARDRAIL - ROUTE 615 RUSSELL CO | 0615 | Secondary | Safety | VDOT | Russell County | LEBANON | Bristol | NonMPO:NonMPO | Infrastructure Investment Division | Brian Holt | Brian.Holt@vdot.virginia.gov | (276) 696-3414 | Jeremy J Mullins | Jeremy.Mullins@vdot.virginia.gov | (276) 696-3259 |  |  |  | 0 |  | 0 | FY2023 | 75775 | 75775 | NO DATES SET YET-PE OPEN | G | Start Development milestone finished on-time | G | Project is on budget | [5 empty] | 2020-07-07 | 2020-07-07 | 2020-07-27 | 2020-07-27 | G | 2020-07-28 | 2020-07-29 | 2021-06-01 |  | G | [5 empty] | 2022-01-03 |  | 2022-02-01 |  | G | [5 empty] | 2022-09-21 |  | 2023-01-27 |  | G | [5 empty] | 2022-06-15 |  | 2022-11-14 |  | G | [5 empty] | 2023-02-14 |  | 2023-02-14 |  | G | 2023-05-04 |  | 2023-05-04 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | REGIONAL ON-CALL CONTRACT | 0 | 0 | 0.068804
176 | 118067 | RT 1 (Gettings - Dwight) SW/Bike Project |  | Primary | Facilities for Pedestrians and Bicycles | Locally | Chesterfield County | CHESTERFIELD | Richmond | Richmond:Chesterfield County | Local Assistance Division | Jorg Huckabee-Mayfield | Jorg.Huckabee-Mayfield@VDOT.Virginia.gov | (804) 609-5292 | Jorg Huckabee-Mayfield | Jorg.Huckabee-Mayfield@VDOT.Virginia.gov | (804) 609-5292 | Barbara Smith | smithbk@chesterfield.gov | (804) 748-1037 | 0 |  | 0 | FY2025 | 575000 | 575000 | NO DATES SET YET | G | Agreement with Locality milestone is 199 days ahead of the expected completion date | G | Project is on budget | 2021-05-03 |  | 2021-09-08 |  | G | 2021-09-09 |  | 2021-09-29 |  | G | 2021-10-29 |  | 2022-03-01 |  | G | [10 empty] | 2023-06-19 |  | 2023-07-24 |  | G | [5 empty] | 2023-07-25 |  | 2023-12-26 |  | G | 2023-11-20 |  | 2024-04-23 |  | G | [5 empty] | 2024-04-02 |  | 2024-04-29 |  | G | 2024-07-18 |  | 2024-07-18 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.20364
177 | 118167 | FPS - Melrose Avenue Crossing - Drainage Improvements | 0000 | Urban | Mitigation of Water Pollution Due to Highway Runof | Locally | Roanoke | SALEM | Salem | Roanoke:Roanoke City | Local Assistance Division | Cheryl B Becker | Cheryl.Becker@vdot.virginia.gov | (540) 492-2531 | Cheryl B Becker | Cheryl.Becker@vdot.virginia.gov | (540) 492-2531 | Dwayne D'Ardenne | Dwayne.D'Ardenne@roanokeva.gov | (540) 853-5901 | 0 |  | 0 | FY2028 | 1600000 | 1600000 | NO DATES SET YET | G | Agreement with Locality milestone is 1422 days ahead of the expected completion date | G | Project is on budget | 2024-08-30 |  | 2025-01-13 |  | G | 2025-01-14 |  | 2025-02-05 |  | G | 2025-08-12 |  | 2025-12-08 |  | G | [25 empty] | 2026-12-03 |  | 2027-05-05 |  | G | [5 empty] | 2027-07-02 |  | 2027-07-30 |  | G | 2027-10-20 |  | 2027-10-20 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.20936
178 | 96721 | ROUTE 28 WIDENING - MANASSAS | 0028 | Urban | Reconstruction w/ Added Capacity | Locally | Manassas | MANASSAS | Northern Virginia | Northern Virginia:Manassas | Infrastructure Investment Division | Amir Salahshoor | A.Salahshoor@VDOT.Virginia.gov | (703) 259-1957 | Rhoderick M Undan | Rhoderick.Undan@vdot.virginia.gov | (703) 259-3347 | Sung Jin Chung | schung@ci.manassas.va.us | (703) 257-8339 | 0 |  | 0 | FY2020 | 6154500 | 22206577 | ADVERTISED | R | Start Delivery milestone is 478 days past the expected completion date | R | Project estimate is between $5M and $10M and is a $1M or more over budget | 2011-05-02 | 2011-05-02 | 2011-06-20 | 2011-06-20 | G | 2010-10-01 | 2012-01-10 | 2010-10-01 | 2012-04-24 | R | 2013-05-28 | 2013-05-28 | 2013-06-28 | 2013-06-28 | G | [10 empty] | 2017-05-26 | 2017-05-26 | 2017-09-10 | 2017-09-10 | G | [5 empty] | 2017-09-11 | 2017-09-11 | 2018-12-13 | 2019-12-13 | R | [10 empty] | 2018-12-31 | 2020-06-26 | 2019-05-30 | 2021-02-11 | R | 2019-06-03 |  | 2019-11-01 |  | R | Delay due to unforeseen issues with utilities, railroad coordination, or right-of-way acquisition | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.24818
179 | 101034 | #HB2.FY17 RTE 6 PATTERSON AVE AT PARHAM RD INTERSECTION | 0006 | Primary | Safety | VDOT | Henrico County | ASHLAND | Richmond | Richmond:Henrico County | Infrastructure Investment Division | Xuesong Zhang | Jason.Zhang@vdot.virginia.gov | (804) 609-5248 | Xuesong Zhang | Jason.Zhang@vdot.virginia.gov | (804) 609-5248 | Sharon Smidler | smi20@henrico.us | (804) 501-4621 | 1 | 2017 | 0 | FY2021 | 14000000 | 14000000 | AWARDED | G | Start Delivery milestone finished 20 days early | G | Project is on budget | [5 empty] | 2011-07-01 | 2011-09-08 | 2011-07-01 | 2011-09-08 | R | 2016-06-01 | 2016-05-24 | 2017-01-20 | 2016-12-20 | G | [5 empty] | 2017-06-09 | 2017-06-09 | 2017-07-13 | 2017-07-13 | G | 2018-03-08 | 2018-03-16 | 2018-04-24 | 2018-04-13 | G | 2019-11-25 | 2019-05-09 | 2020-11-24 | 2020-11-04 | G | 2018-05-10 | 2018-05-07 | 2019-10-17 | 2019-05-31 | G | 2019-04-29 | 2019-04-29 | 2020-04-29 | 2019-04-29 | G | [5 empty] | 2020-10-28 | 2020-11-04 | 2020-11-10 | 2020-11-04 | G | 2021-02-01 | 2021-01-19 | 2021-02-08 | 2021-01-19 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.083094
180 | 107235 | RECONSTRUCT ROADWAY, SIDEWALK, CURB/GUTTER, STORM DRAIN | 0000 | Urban | Reconstruction w/o Added Capacity | Locally | Saint Paul | WISE | Bristol | NonMPO:NonMPO | Local Assistance Division | Tabitha H Crowder | Tabitha.Crowder@vdot.virginia.gov | (276) 696-3482 | Kenneth R Plummer | KR.Plummer@VDOT.Virginia.gov | (276) 696-3261 | Michael W. Hatfield | countyadministrator@wisecounty.org | (276) 328-2321 | 0 |  | 0 | FY2019 |  |  | WAITING FINANCIAL CLOSURE | G | Determine Requirements milestone finished 7 days early | R | Critical information missing | 2015-08-03 | 2015-08-03 | 2015-08-03 | 2015-08-03 | G | 2016-04-26 | 2016-04-26 | 2016-04-26 | 2016-04-26 | G | 2016-04-29 | 2016-04-29 | 2018-11-01 | 2018-10-25 | G | [10 empty] | 2017-06-29 | 2017-06-29 | 2018-06-01 | 2018-06-01 | G | [20 empty] | 2018-05-01 | 2018-05-01 | 2018-07-24 | 2018-07-24 | G | 2018-07-17 | 2018-07-17 | 2018-10-01 | 2018-10-01 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.082924
181 | 109322 | #HB2.FY17 RTE 95 - IMPROVE INTERCHANGE AT RTE 10 | 0095 | Interstate | Safety | Locally | Chesterfield County | CHESTERFIELD | Richmond | Richmond:Chesterfield County | Infrastructure Investment Division | Brian J Lokker | Brian.Lokker@VDOT.Virginia.gov | (804) 524-6010 | Brian J Lokker | Brian.Lokker@VDOT.Virginia.gov | (804) 524-6010 | Stan Newcomb | newcombs@chesterfield.gov | (804) 748-1037 | 1 | 2017 | 0 | FY2021 | 10000000 | 11964089 | AWARDED | G | Start Delivery milestone finished 58 days early | R | Project estimate is between $5M and $10M and is a $1M or more over budget | 2016-10-03 | 2017-02-17 | 2016-12-30 | 2017-02-17 | R | 2017-01-03 | 2017-01-17 | 2017-01-05 | 2017-01-17 | R | 2017-01-06 | 2017-02-14 | 2017-12-26 | 2017-12-19 | G | [5 empty] | 2019-01-14 | 2018-08-31 | 2019-01-29 | 2019-01-28 | G | 2019-01-30 | 2019-04-18 | 2019-02-12 | 2019-05-08 | R | 2019-11-22 | 2019-11-28 | 2020-06-30 | 2020-11-02 | R | 2019-02-14 | 2019-05-17 | 2019-11-21 | 2019-11-27 | R | 2020-06-30 | 2018-03-26 | 2020-09-15 | 2019-11-22 | G | [5 empty] | 2020-09-30 | 2020-07-24 | 2020-09-30 | 2020-07-24 | G | 2020-10-01 | 2020-07-27 | 2020-12-30 | 2020-11-02 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.1302
182 | 109523 | #HB2.FY17 BRANDY STATION PARK & RIDE LOT EXPANSION AT 29/663 | 0029 | Primary | Other | VDOT | Culpeper County | WARRENTON | Culpeper | NonMPO:NonMPO | Infrastructure Investment Division | Gregory J Cooley | Gregory.Cooley@vdot.virginia.gov | (434) 906-7979 | Shelly Plaster | Shelly.Plaster@vdot.virginia.gov | (540) 727-7038 |  |  |  | 1 | 2017 | 0 | FY2021 | 900000 | 977100 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 414 days early | Y | Project estimate is less than $5M and is up to 20% over budget | [5 empty] | 2016-09-20 | 2016-09-20 | 2016-09-20 | 2016-09-20 | G | 2016-09-21 | 2016-09-21 | 2017-08-31 | 2017-08-28 | G | [5 empty] | 2018-07-26 | 2018-03-27 | 2018-08-08 | 2018-03-27 | G | 2019-08-19 | 2018-11-15 | 2019-08-29 | 2018-11-29 | G | 2019-10-14 | 2018-10-05 | 2020-04-23 | 2018-11-05 | G | 2019-09-17 | 2018-12-05 | 2019-12-13 | 2018-12-05 | G | [10 empty] | 2020-05-12 | 2019-04-09 | 2020-05-12 | 2019-04-09 | G | 2020-07-02 | 2019-06-26 | 2020-08-13 | 2019-06-26 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.089917
183 | 110488 | SPOTSYLVANIA COURTHOUSE VILLAGE STREETSCAPE - PHASE II & III |  | Enhancement | Landscaping/Beautification | Locally | Spotsylvania County | FREDERICKSBURG | Fredericksburg | Fredericksburg:Spotsylvania County | Local Assistance Division | Robert Galen Ridgell | Robert.Ridgell@vdot.virginia.gov | (540) 372-3549 | Michael T Coffey | MichaelT.Coffey@vdot.virginia.gov | (540) 899-4225 | Scott Powell | SPowell@spotsylvania.va.us | (540) 507-7330 | 0 |  | 0 | FY2020 | 1118753 | 810868 | CONSTRUCTION COMPLETED | R | Start Delivery milestone finished 57 days late | G | Project is on budget | 2017-01-17 | 2017-01-17 | 2017-04-11 | 2017-04-11 | G | 2017-04-12 | 2017-04-12 | 2017-04-14 | 2017-04-12 | G | 2017-04-17 | 2017-06-16 | 2017-10-19 | 2017-06-28 | G | [10 empty] | 2017-07-14 | 2017-07-25 | 2017-08-03 | 2017-08-14 | R | [5 empty] | 2017-08-07 | 2017-08-15 | 2019-06-07 | 2017-08-15 | G | [10 empty] | 2019-09-05 | 2019-08-26 | 2019-10-08 | 2019-09-11 | G | 2019-10-09 | 2020-01-16 | 2019-11-20 | 2020-01-16 | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.33198
184 | 110804 | #SMART18 - Indian River Road Phase 7B |  | Urban | Reconstruction w/ Added Capacity | Locally | Virginia Beach | NORFOLK | Hampton Roads | Hampton Roads:Virginia Beach | Infrastructure Investment Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Marci Thompson | Marci.Thompson@vdot.virginia.gov | (757) 956-3093 | Katie E. Shannon, P.E. | KShannon@vbgov.com | (757) 385-1514 | 1 | 2018 | 0 | FY2025 | 11430000 | 11430000 | NO DATES SET YET-PE OPEN | R | Determine Requirements milestone is 314 days past the expected completion date | G | Project is on budget | 2019-06-05 | 2019-09-05 | 2019-08-28 | 2019-11-04 | R | 2019-08-29 | 2020-02-20 | 2019-09-03 | 2020-02-24 | R | 2019-09-04 |  | 2020-04-13 |  | R | [10 empty] | 2023-09-20 |  | 2023-10-10 |  | G | [5 empty] | 2023-10-12 |  | 2024-07-25 |  | G | 2022-04-25 |  | 2022-12-28 |  | G | [5 empty] | 2024-08-12 |  | 2024-09-09 |  | G | 2024-12-02 |  | 2024-12-02 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.22493
185 | 111356 | Town of Pennington Gap - Downtown to Hospital Sidewalk |  | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Pennington Gap | WISE | Bristol | NonMPO:NonMPO | Local Assistance Division | Tabitha H Crowder | Tabitha.Crowder@vdot.virginia.gov | (276) 696-3482 | Roger L Musser | Roger.Musser@VDOT.Virginia.gov | (276) 696-3260 | Town of Pennington Gap |  |  | 0 |  | 0 | FY2021 | 556106 | 613070 | ACTIVITY DATES SET | Y | Complete Purchasing Right-of-Way milestone is 8 days ahead of the expected completion date and there is a risk of missing this milestone date | Y | Project estimate is less than $5M and is up to 20% over budget | 2017-10-02 | 2017-10-02 | 2017-11-06 | 2017-11-06 | G | 2017-11-07 | 2017-11-07 | 2017-12-06 | 2017-12-06 | G | 2018-04-23 | 2018-04-23 | 2019-02-11 | 2019-02-11 | G | [10 empty] | 2020-04-23 | 2020-04-23 | 2020-05-13 | 2020-05-13 | G | [5 empty] | 2020-05-15 | 2020-05-15 | 2021-03-01 |  | Y | [10 empty] | 2021-03-17 |  | 2021-04-13 |  | Y | 2021-04-14 |  | 2021-05-24 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.34773
186 | 111666 | #SMART18 - ROUTE 7/ROUTE 690 INTERCHANGE | 0007 | Primary | Reconstruction w/ Added Capacity | Locally | Loudoun County | LEESBURG | Northern Virginia | Northern Virginia:Loudoun County | Infrastructure Investment Division | Amir Salahshoor | A.Salahshoor@VDOT.Virginia.gov | (703) 259-1957 | Susie X Lue | Susie.Lue@vdot.virginia.gov | (703) 259-2918 | Gary Pozzouli | gary.pozzouli@loudoun.gov | (571) 258-3447 | 1 | 2018 | 0 | FY2025 | 36164900 | 36923925 | ACTIVITY DATES SET | R | Determine Requirements milestone finished 496 days late | Y | Project estimate is greater than $10M and is over budget by (a) up to 10% or (b) up to $5M | 2017-06-16 | 2017-05-22 | 2017-11-01 | 2018-05-08 | R | 2018-02-08 | 2019-01-14 | 2018-02-12 | 2019-01-18 | R | 2018-02-13 | 2018-05-31 | 2018-03-13 | 2019-07-22 | R | [5 empty] | 2020-09-29 | 2020-09-29 | 2021-05-28 |  | G | 2020-09-29 |  | 2021-03-25 |  | G | [5 empty] | 2021-03-31 |  | 2022-11-28 |  | G | 2023-02-28 |  | 2023-07-26 |  | G | [5 empty] | 2023-09-28 |  | 2024-03-26 |  | G | 2024-03-27 |  | 2024-08-27 |  | G | Design plans are being revised | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.29389
187 | 112304 | Fallowater Lane Extension | 9999 | Secondary | New Construction Roadway | Locally | Roanoke County | SALEM | Salem | Roanoke:Roanoke County | Infrastructure Investment Division | Thomas W Digiulian | Thomas.DiGiulian@VDOT.Virginia.gov | (540) 387-5356 | Cheryl B Becker | Cheryl.Becker@vdot.virginia.gov | (540) 492-2531 | David Henderson | dhenderson@roanokecountyva.gov | (540) 772-2083 | 0 |  | 0 | FY2022 | 4500000 | 4340114 | ACTIVITY DATES SET | G | Complete Purchasing Right-of-Way milestone finished 86 days early | G | Project is on budget | 2018-01-08 | 2017-02-14 | 2018-06-01 | 2018-05-18 | G | 2018-06-04 | 2018-05-02 | 2018-06-06 | 2018-05-18 | G | 2018-06-07 | 2018-05-19 | 2019-06-07 | 2019-09-17 | R | [5 empty] | 2019-09-18 | 2019-09-18 | 2019-12-16 | 2019-12-16 | G | 2019-03-08 | 2019-12-17 | 2020-06-30 | 2019-12-17 | G | [5 empty] | 2020-07-02 | 2020-03-24 | 2021-04-15 | 2021-01-19 | G | [10 empty] | 2021-05-03 |  | 2021-05-28 |  | G | 2021-06-01 |  | 2021-10-21 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.21635
188 | 113140 | Roanoke Citywide stormwater improvements - FY19-20RS | 0000 | Urban | Mitigation of Water Pollution Due to Highway Runof | Locally | Roanoke | SALEM | Salem | Roanoke:Roanoke City | Local Assistance Division | Cheryl B Becker | Cheryl.Becker@vdot.virginia.gov | (540) 492-2531 | Cheryl B Becker | Cheryl.Becker@vdot.virginia.gov | (540) 492-2531 | Dwayne R. D'Ardenne | Dwayne.D'Ardenne@roanokeva.gov | (540) 853-5901 | 0 |  | 0 | FY2021 | 6348564 | 2280 | ADVERTISED | G | Solicit Bids milestone finished 29 days early | G | Project is on budget | 2018-08-01 | 2018-08-01 | 2018-10-25 | 2018-11-27 | R | 2018-10-26 | 2018-11-28 | 2018-10-30 | 2018-11-28 | R | 2018-10-31 | 2018-11-29 | 2019-08-01 | 2019-07-31 | G | [35 empty] | 2020-10-02 | 2020-10-01 | 2020-10-30 | 2020-10-01 | G | 2021-04-01 |  | 2021-04-01 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.21386
189 | 113273 | Potomac Run Street Extension - | 1734 | Secondary | Reconstruction w/o Added Capacity | Locally | York County | WILLIAMSBURG | Hampton Roads | Hampton Roads:York County | Local Assistance Division | Christopher R Carroll | C.Carroll@VDOT.Virginia.gov | (757) 253-5140 | Joshua D Negovan | Joshua.Negovan@vdot.virginia.gov | (757) 956-3347 | Tim Cross | tcross@yorkcounty.gov | (757) 890-3496 | 0 |  | 0 | FY2022 | 204466 | 224875 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 511 days early | Y | Project estimate is less than $5M and is up to 20% over budget | 2018-10-01 | 2018-08-20 | 2018-12-28 | 2018-09-12 | G | 2018-12-31 | 2018-09-13 | 2019-01-03 | 2018-09-14 | G | 2019-01-04 | 2018-09-17 | 2019-07-11 | 2019-09-05 | R | [35 empty] | 2021-01-14 | 2020-01-22 | 2021-03-15 | 2020-01-28 | G | 2021-06-02 | 2020-01-29 | 2021-07-14 | 2020-02-19 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.17312
190 | 106958 | CAPITAL BIKESHARE | 9999 | Miscellaneous | Facilities for Pedestrians and Bicycles | Locally | Arlington County | FAIRFAX | Northern Virginia | Northern Virginia:Arlington County | Infrastructure Investment Division | Amir Salahshoor | A.Salahshoor@VDOT.Virginia.gov | (703) 259-1957 | Rhoderick M Undan | Rhoderick.Undan@vdot.virginia.gov | (703) 259-3347 | Paul DeMaio | paul@metrobike.net | (202) 684-8126 | 0 |  | 0 | FY2021 | 749255 | 749255 | NO DATES SET YET-PE OPEN | R | Determine Requirements milestone is 559 days past the expected completion date | G | Project is on budget | 2019-07-01 | 2019-07-01 | 2020-01-31 | 2020-01-13 | G | 2019-07-01 | 2020-01-14 | 2019-07-15 | 2020-01-24 | R | 2019-07-16 |  | 2019-08-12 |  | R | [35 empty] | 2020-05-13 |  | 2020-05-13 |  | R | 2020-06-26 |  | 2020-07-17 |  | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.15381
191 | 109053 | Independence Boulevard and Baxter Road Sidewalk |  | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Virginia Beach | NORFOLK | Hampton Roads | Hampton Roads:Virginia Beach | Local Assistance Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Marci Thompson | Marci.Thompson@vdot.virginia.gov | (757) 956-3093 | Katie Shannon | kshannon@vbgov.com | (757) 385-1514 | 0 |  | 0 | FY2021 | 1296007 | 1549868 | ADVERTISED | Y | Start Delivery milestone is 3 days ahead of the expected completion date and there is a risk of missing this milestone date | Y | Project estimate is less than $5M and is up to 20% over budget | 2017-02-17 | 2017-02-17 | 2017-05-01 | 2017-05-01 | G | 2017-05-02 | 2017-05-02 | 2017-05-24 | 2017-05-24 | G | 2017-05-25 | 2017-05-25 | 2018-08-31 | 2020-02-24 | R | [10 empty] | 2020-07-30 | 2020-07-30 | 2020-08-19 | 2020-07-30 | G | [5 empty] | 2020-08-21 | 2020-07-30 | 2020-09-01 | 2020-07-30 | G | [10 empty] | 2020-09-18 | 2020-08-19 | 2020-10-30 | 2020-10-11 | G | 2021-01-27 |  | 2021-02-24 |  | Y |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.27949
192 | 109368 | #HB2.FY17 I-81 Exit 222 NB Accel and SB Decel Lane Extension | 0081 | Interstate | Safety | VDOT | Augusta County | HARRISONBURG | Staunton | SAW:Augusta County | Infrastructure Investment Division | Ronald L Tabor | Ronald.Tabor@vdot.virginia.gov | (540) 332-7887 | Anthony E Pelina | Anthony.Pelina@vdot.virginia.gov | (540) 332-9575 |  |  |  | 1 | 2017 | 0 | FY2018 | 2045900 | 2045900 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 33 days early | Y | Estimate not current | [5 empty] | 2016-08-01 | 2016-08-01 | 2016-08-12 | 2016-08-12 | G | 2016-08-12 | 2016-08-12 | 2017-04-13 | 2017-04-13 | G | [5 empty] | 2017-07-19 | 2017-04-14 | 2017-07-19 | 2017-04-28 | G | [5 empty] | 2017-08-11 | 2017-09-28 | 2017-10-23 | 2017-09-28 | G | [5 empty] | 2017-07-27 | 2017-07-27 | 2017-10-27 | 2017-07-27 | G | [5 empty] | 2018-01-09 | 2018-01-09 | 2018-01-09 | 2018-01-09 | G | 2018-03-05 | 2018-04-27 | 2018-05-30 | 2018-04-27 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.080046
193 | 109949 | TOWN OF CLIFTON STREETSCAPE PROJECT - PHASE II | 0645 | Enhancement | Landscaping/Beautification | Locally | Fairfax County | FAIRFAX | Northern Virginia | Northern Virginia:Fairfax County | Local Assistance Division | Amir Salahshoor | A.Salahshoor@VDOT.Virginia.gov | (703) 259-1957 | Saif-Ur Qargha | Saif.Qargha@vdot.virginia.gov | (703) 259-3223 | Susan Yantis | syantis@aol.com | (703) 623-2198 | 0 |  | 0 | FY2019 | 1181009 | 1152306 | ACTIVITY DATES SET | R | Complete Purchasing Right-of-Way milestone is 752 days past the expected completion date | Y | Estimate not current | 2016-04-04 | 2016-06-27 | 2016-06-27 | 2016-09-20 | R | 2016-06-28 | 2016-06-28 | 2016-06-30 | 2016-09-23 | R | 2016-07-01 | 2017-07-13 | 2017-01-10 | 2018-02-21 | R | [10 empty] | 2018-08-10 | 2019-09-10 | 2018-08-30 | 2019-10-18 | R | [5 empty] | 2018-09-04 | 2019-11-27 | 2019-01-31 |  | R | [10 empty] | 2019-02-19 |  | 2019-03-18 |  | R | 2019-03-19 |  | 2019-04-26 |  | R | Delay due to unforeseen issues with utilities, railroad coordination, or right-of-way acquisition | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.35368
194 | 110634 | Nansemond Pkwy/Wilroy Rd Overpass over Commonwealth Railway | 0000 | Urban | New Construction Roadway | Locally | Suffolk | NORFOLK | Hampton Roads | Hampton Roads:Suffolk | Infrastructure Investment Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Johndel A Alcaide | John.Alcaide@vdot.virginia.gov | (757) 956-3098 | Robert Lewis | relewis@suffolkva.us | (757) 514-7621 | 0 |  | 0 | FY2023 | 27478741 | 27478741 | ACTIVITY DATES SET | R | Determine Requirements milestone finished 673 days late | G | Project is on budget | 2017-06-05 | 2017-06-05 | 2017-08-21 | 2017-08-21 | G | 2017-08-07 | 2017-08-07 | 2017-08-09 | 2017-08-09 | G | 2017-08-10 | 2017-08-10 | 2019-03-07 | 2021-01-08 | R | [10 empty] | 2021-03-19 |  | 2021-04-09 |  | G | [5 empty] | 2021-04-13 |  | 2022-10-13 |  | G | [10 empty] | 2022-12-28 |  | 2023-01-27 |  | G | 2023-04-18 |  | 2023-04-18 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.26886
195 | 111004 | Virginia Beach Boulevard Sidewalk |  | Urban | Safety | Locally | Virginia Beach | NORFOLK | Hampton Roads | Hampton Roads:Virginia Beach | Infrastructure Investment Division | Susan Wilson | Susan.Wilson@vdot.virginia.gov | (757) 956-3099 | Marci Thompson | Marci.Thompson@vdot.virginia.gov | (757) 956-3093 | Katie E Shannon, PE | kshannon@vbgov.com | (757) 385-4131 | 0 |  | 0 | FY2023 | 531604 | 531604 | NO DATES SET YET-PE OPEN | R | Determine Requirements milestone is 150 days past the expected completion date | G | Project is on budget | 2019-07-01 | 2019-09-09 | 2019-09-24 | 2019-10-25 | R | 2019-09-25 | 2019-10-28 | 2019-10-08 | 2019-11-05 | R | 2019-10-09 |  | 2020-09-24 |  | R | [10 empty] | 2021-07-22 |  | 2021-08-11 |  | G | [5 empty] | 2021-08-13 |  | 2022-05-26 |  | G | [10 empty] | 2022-06-14 |  | 2022-07-12 |  | G | 2022-07-13 |  | 2022-10-12 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.15221
196 | 111407 | #SMART18 - Rte 419 & Rte 221 Adaptive Traffic Control | 0419 | Primary | Traffic Management/Engineering | VDOT | Roanoke County | SALEM | Salem | Roanoke:Roanoke County | Infrastructure Investment Division | Bernard S Grinnell | Sean.Grinnell@VDOT.Virginia.gov | (540) 375-0148 | John L Bisnett | John.Bisnett@vdot.virginia.gov | (540) 529-5742 | David Holladay | dholladay@roanokecountyva.gov | (540) 772-2094 | 1 | 2018 | 0 | FY2019 | 663457 | 663457 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 22 days early | G | Project is on budget | [5 empty] | 2017-07-17 | 2017-07-07 | 2017-07-17 | 2017-07-07 | G | 2017-07-18 | 2017-07-17 | 2017-11-08 | 2017-10-19 | G | [5 empty] | 2018-11-01 | 2018-10-08 | 2018-11-01 | 2018-10-09 | G | [25 empty] | 2019-01-23 | 2018-12-27 | 2019-01-29 | 2019-01-03 | G | 2019-01-30 | 2019-01-04 | 2019-04-24 | 2019-04-02 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | WORK/TASK ORDER | 1 | 0 | 0.15137
197 | 112302 | INSTALL TRAFFIC SIGNAL ROUTE 50 AT FLEETWOOD ROAD | 0050 | Primary | Traffic Management/Engineering | VDOT | Loudoun County | LEESBURG | Northern Virginia | Northern Virginia:Loudoun County | Infrastructure Investment Division | Tara L Atkins | Tara.Atkins@VDOT.Virginia.gov | (703) 259-1931 | Jessica Paris | Jessica.Paris@vdot.virginia.gov | (703) 259-2409 | Susan Glass, Loudoun County DTCI | susan.glass@loudoun.gov | (703) 777-0251 | 0 |  | 0 | FY2019 | 498185 | 498185 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 14 days early | G | Project is on budget | [5 empty] | 2017-12-01 | 2018-02-28 | 2017-12-01 | 2018-03-06 | R | 2017-12-04 | 2017-10-18 | 2018-03-16 | 2018-03-16 | G | [5 empty] | 2018-05-25 | 2018-04-05 | 2018-06-08 | 2018-04-16 | G | [25 empty] | 2018-06-26 | 2018-06-12 | 2018-07-02 | 2018-06-25 | G | 2018-07-03 | 2018-06-21 | 2018-07-10 | 2018-06-26 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | WORK/TASK ORDER | 1 | 0 | 0.14786
198 | 113135 | Arbor Drive - Peppers Ferry Road Intersection | 0000 | Urban | Reconstruction w/ Added Capacity | Locally | Christiansburg | CHRISTIANSBURG | Salem | New River Valley:Christiansburg | Local Assistance Division | Adam J Czesnowski | Adam.Czesnowski@vdot.virginia.gov | (540) 541-1216 | Adam J Czesnowski | Adam.Czesnowski@vdot.virginia.gov | (540) 541-1216 | Wayne Nelson | wnelson@christiansburg.org | (540) 382-6120 | 0 |  | 0 | FY2022 | 1838374 | 1838374 | ACTIVITY DATES SET | G | Start Purchasing Right-of-Way milestone finished 43 days early | G | Project is on budget | 2018-08-01 | 2018-08-01 | 2018-10-25 | 2019-01-07 | R | 2018-10-26 | 2019-01-07 | 2018-10-30 | 2019-01-07 | R | 2018-10-31 | 2019-01-29 | 2019-08-01 | 2020-04-15 | R | [10 empty] | 2020-06-30 | 2020-05-27 | 2020-07-21 | 2020-06-08 | G | [5 empty] | 2020-07-23 |  | 2021-07-21 |  | G | [10 empty] | 2021-07-22 |  | 2021-08-18 |  | G | 2022-01-19 |  | 2022-01-19 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.1241
199 | 113174 | #SMART18 - SummitView Business Park Intersection Improvemnts | 0220 | Primary | Reconstruction w/ Added Capacity | Locally | Franklin County | BEDFORD | Salem | NonMPO:NonMPO | Local Assistance Division | Jessie Nester | Jessie.Nester@vdot.virginia.gov | (540) 613-4115 | Jessie Nester | Jessie.Nester@vdot.virginia.gov | (540) 613-4115 | Steve Sandy | steve.sandy@franklincountyva.gov | (540) 682-4537 | 0 |  | 0 | FY2023 | 13739564 | 12751444 | ACTIVITY DATES SET | G | Start Purchasing Right-of-Way milestone finished 8 days early | G | Project is on budget | 2018-08-01 | 2018-08-01 | 2018-10-16 | 2018-10-16 | G | 2018-10-16 | 2018-10-16 | 2018-10-16 | 2018-10-16 | G | 2018-10-31 | 2019-02-13 | 2019-08-01 | 2019-08-01 | G | [10 empty] | 2020-06-05 | 2020-12-17 | 2021-01-12 | 2021-01-04 | G | [5 empty] | 2021-01-14 |  | 2022-02-17 |  | G | [10 empty] | 2022-02-18 |  | 2022-07-07 |  | G | 2022-12-02 |  | 2023-02-09 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.39857
200 | 113634 | RCut US 13 @ Route 648 (Daugherty Road) Accomack Co | 0013 | Primary | Safety | VDOT | Accomack County | ACCOMAC | Hampton Roads | NonMPO:NonMPO | Infrastructure Investment Division | John G Harman | JohnG.Harman@vdot.virginia.gov | (757) 956-3269 | John G Harman | JohnG.Harman@vdot.virginia.gov | (757) 956-3269 |  |  |  | 0 |  | 0 | FY2027 | 764587 | 764587 | NO DATES SET YET | G | Start Development milestone is 617 days ahead of the expected completion date | G | Project is on budget | [5 empty] | 2022-10-18 |  | 2022-10-31 |  | G | 2022-11-01 |  | 2023-09-28 |  | G | [5 empty] | 2024-08-05 |  | 2024-08-16 |  | G | 2025-11-24 |  | 2025-12-09 |  | G | 2026-05-06 |  | 2026-11-09 |  | G | 2025-12-26 |  | 2026-07-02 |  | G | 2025-05-13 |  | 2025-11-17 |  | G | [5 empty] | 2026-11-10 |  | 2026-11-10 |  | G | 2027-02-08 |  | 2027-02-08 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.093079
201 | 115222 | Park-N-Ride Bus Purchase | 9999 | Urban | Other | Locally | Richmond | ASHLAND | Richmond | Richmond:Richmond | Infrastructure Investment Division | Olena Fecek | Olena.Fecek@vdot.virginia.gov | (804) 524-6368 | Olena Fecek | Olena.Fecek@vdot.virginia.gov | (804) 524-6368 | Dironna Clarke | Dironna.Clarke@richmondgov.com | (804) 646-3074 | 0 |  | 0 | FY2021 | 59320 | 59320 | NO DATES SET YET | R | Agreement with Locality milestone is 458 days past the expected completion date | G | Project is on budget | 2019-07-15 |  | 2019-11-21 |  | R | [5 empty] | 2020-02-25 |  | 2020-09-17 |  | R | [25 empty] | 2020-09-18 |  | 2021-01-19 |  | R | [5 empty] | 2021-02-26 |  | 2021-03-25 |  | Y | 2021-06-28 |  | 2021-06-28 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.13682
202 | 115365 | City of Hampton 340 Armistead Ave N - Paving | 0134 | Urban | Restoration and Rehabilitation | Locally | Hampton | WILLIAMSBURG | Hampton Roads | Hampton Roads:Hampton | Local Assistance Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Joshua D Negovan | Joshua.Negovan@vdot.virginia.gov | (757) 956-3347 | Angela Rico | Angela.Rico@Hampton.gov | (757) 209-1245 | 0 |  | 0 | FY2020 | 103000 | 103000 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 57 days early | G | Project is on budget | 2019-10-03 | 2019-10-03 | 2020-01-02 | 2019-11-06 | G | [5 empty] | 2019-10-03 | 2019-10-03 | 2019-10-16 | 2019-10-16 | G | [35 empty] | 2020-01-22 | 2019-10-10 | 2020-02-19 | 2019-11-07 | G | 2020-05-07 | 2020-02-04 | 2020-05-07 | 2020-03-11 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.10593
203 | 115373 | Opticom Emergency Vehicle Preemption (EVP) |  | Urban | Traffic Management/Engineering | Locally | Newport News | WILLIAMSBURG | Hampton Roads | Hampton Roads:Newport News | Infrastructure Investment Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Chessica Villaflores | Chessica.Villaflores@vdot.virginia.gov | (757) 956-3094 | Jacqueline Kassel | jkassel@nnva.gov | (757) 926-8666 | 0 |  | 0 | FY2028 | 775000 | 775000 | NO DATES SET YET | G | Agreement with Locality milestone is 1739 days ahead of the expected completion date | Y | Estimate not current | 2025-09-02 |  | 2025-11-26 |  | G | 2025-12-01 |  | 2025-12-03 |  | G | 2025-12-04 |  | 2026-06-11 |  | G | [25 empty] | 2026-07-20 |  | 2027-03-26 |  | G | [5 empty] | 2027-06-30 |  | 2027-07-28 |  | G | 2027-10-15 |  | 2027-10-15 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.35015
204 | 116722 | NOVA SYSTEMIC PEDESTRIAN CROSSINGS PH2 | 9999 | Miscellaneous | Safety | VDOT | Northern Virginia District-wide |  | Northern Virginia | Northern Virginia:Northern Virginia District-wide | Infrastructure Investment/Asset Management Division | Waqar A Siddiqui | Sid.Siddiqui@VDOT.Virginia.gov | (703) 259-3225 | Tienjung Ho | Tien-Jung.Ho@VDOT.Virginia.gov | (703) 259-2752 |  |  |  | 0 |  | 0 | FY2023 | 3300000 | 3300000 | NO DATES SET YET | G | Start Development milestone is 176 days ahead of the expected completion date | G | Project is on budget | [5 empty] | 2021-08-16 |  | 2021-08-16 |  | G | 2021-08-17 |  | 2022-05-23 |  | G | [5 empty] | 2022-05-24 |  | 2022-06-07 |  | G | [25 empty] | 2022-07-08 |  | 2022-07-14 |  | G | 2022-07-15 |  | 2022-07-21 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | WORK/TASK ORDER | 0 | 0 | 0.067189
205 | 117943 | Tredegar Street |  | Urban | Facilities for Pedestrians and Bicycles | Locally | Richmond | ASHLAND | Richmond | Richmond:Richmond | Local Assistance Division | James Shepherd | James.Shepherd@vdot.virginia.gov | (804) 609-5305 | James Shepherd | James.Shepherd@vdot.virginia.gov | (804) 609-5305 | Adel Edward | adel.edward@richmondgov.com | (804) 646-6584 | 0 |  | 0 | FY2025 | 380000 | 380000 | NO DATES SET YET | G | Agreement with Locality milestone is 199 days ahead of the expected completion date | G | Project is on budget | 2021-05-03 |  | 2021-09-08 |  | G | 2021-09-09 |  | 2021-09-29 |  | G | 2022-04-13 |  | 2022-08-04 |  | G | [10 empty] | 2023-11-28 |  | 2024-01-03 |  | G | [5 empty] | 2024-01-04 |  | 2024-06-04 |  | G | 2024-02-12 |  | 2024-07-10 |  | G | [5 empty] | 2024-09-06 |  | 2024-10-03 |  | G | 2024-12-27 |  | 2024-12-27 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.16651
206 | 118236 | SHREVEWOOD ES SRTS |  | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Fairfax County | FAIRFAX | Northern Virginia | Northern Virginia:Fairfax County | Local Assistance Division | Andrew G Beacher | Andrew.Beacher@vdot.virginia.gov | (703) 259-2239 | Saif-Ur Qargha | Saif.Qargha@vdot.virginia.gov | (703) 259-3223 | Lauren Delmare | lauren.delmare@fairfaxcounty.gov | (703) 877-5949 | 0 |  | 0 | FY2025 | 700000 | 700000 | NO DATES SET YET | G | Agreement with Locality milestone is 107 days ahead of the expected completion date | G | Project is on budget | 2021-02-01 |  | 2021-06-08 |  | G | 2021-06-09 |  | 2021-06-29 |  | G | 2021-07-29 |  | 2021-11-22 |  | G | [10 empty] | 2023-03-20 |  | 2023-04-21 |  | G | [5 empty] | 2023-04-24 |  | 2023-09-20 |  | G | 2023-11-14 |  | 2024-04-17 |  | G | [5 empty] | 2023-12-28 |  | 2024-05-21 |  | G | 2024-08-09 |  | 2025-01-06 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.25489
207 | 11908 | #HB2.FY17 10TH St - 2 Ln, Bike Ln, Curb & Gutter, & Sidewalk |  | Urban | Reconstruction w/o Added Capacity | VDOT | Roanoke | SALEM | Salem | Roanoke:Roanoke City | Infrastructure Investment Division | dan collins |  |  | Jeffrey A Echols | Jeff.Echols@VDOT.Virginia.gov | (540) 375-3595 |  |  |  | 1 | 2017 | 0 | FY2017 | 17451245 | 17843814 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished on-time | Y | Project estimate is greater than $10M and is over budget by (a) up to 10% or (b) up to $5M | [5 empty] | 1998-07-01 | 2001-12-12 | 1998-07-31 | 2001-12-13 | R | 1998-08-03 | 2001-12-04 | 1999-02-26 | 2002-02-05 | R | [5 empty] | 2011-08-18 | 2011-08-18 | 2011-08-31 | 2011-08-31 | G | 2011-09-30 | 2011-09-30 | 2011-10-31 | 2011-10-31 | G | 2016-04-12 | 2016-04-12 | 2016-09-06 | 2016-09-06 | G | 2011-11-01 | 2011-11-01 | 2013-10-04 | 2013-10-04 | G | [10 empty] | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | G | 2017-02-16 | 2017-02-16 | 2017-02-16 | 2017-02-16 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 1 | 0.29535
208 | 104050 | Cape Henry Lighthouse Restoration, C502 |  | Enhancement | Rehabilitation of Historic Bldgs/Facilities | Locally | Virginia Beach | NORFOLK | Hampton Roads | Hampton Roads:Virginia Beach | Local Assistance Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Marci Thompson | Marci.Thompson@vdot.virginia.gov | (757) 956-3093 | Mark A. Reed, Historic Resources Coordinator | mreed@vbgov.com | (757) 385-5104 | 0 |  | 0 | FY2019 | 390536 | 1022900 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 215 days early | R | Project estimate is less than $5M and is 20% or more over budget | [5 empty] | 2017-07-15 | 2017-09-15 | 2017-07-15 | 2017-09-15 | R | 2013-10-31 | 2014-05-10 | 2014-02-28 | 2014-06-01 | R | [35 empty] | 2017-11-29 | 2017-11-29 | 2018-01-26 | 2018-01-28 | R | 2018-12-03 | 2018-01-26 | 2019-01-15 | 2018-06-14 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.23392
209 | 106976 | EVERGREEN MILL ROAD WIDENING | 0621 | Secondary | Reconstruction w/ Added Capacity | Locally | Leesburg | LEESBURG | Northern Virginia | Northern Virginia:Leesburg | Local Assistance Division | Amir Salahshoor | A.Salahshoor@VDOT.Virginia.gov | (703) 259-1957 | Saif-Ur Qargha | Saif.Qargha@vdot.virginia.gov | (703) 259-3223 | Terry Yates | KFranklin@leesburgva.gov | (703) 771-6674 | 0 |  | 0 | FY2022 | 14302033 | 14302033 | NO DATES SET YET-PE OPEN | R | Determine Requirements milestone is 732 days past the expected completion date | G | Project is on budget | 2015-07-01 | 2015-07-01 | 2015-08-07 | 2015-08-07 | G | 2016-04-28 | 2016-04-28 | 2016-12-01 | 2016-12-01 | G | 2016-12-02 | 2016-12-02 | 2019-02-20 |  | R | [10 empty] | 2019-07-15 |  | 2019-08-23 |  | R | [20 empty] | 2020-11-02 |  | 2021-03-03 |  | Y | 2021-05-20 |  | 2021-10-11 |  | G | Delay due to changes in scope of work, project management, plan designs, or resolution of public comments | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.5
210 | 113621 | #SGR19LP - FAIRFAX PRIMARY EXT PAVING FY19 - FAIRFAX BLVD | 0029 | Urban | Resurfacing | Locally | Fairfax | FAIRFAX | Northern Virginia | Northern Virginia:Fairfax | Local Assistance Division | Gaby Y Hakim | Gaby.Hakim@VDOT.Virginia.gov | (703) 691-6742 | Rita Hockman | Rita.Hockman@vdot.virginia.gov | (804) 824-7421 | Peter Millard | peter.millard@fairfaxva.gov | (703) 246-6330 | 0 |  | 1 | FY2019 | 585114 | 585114 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 128 days early | G | Project is on budget | 2018-07-02 | 2018-07-02 | 2018-09-25 | 2018-09-13 | G | [5 empty] | 2018-09-26 | 2018-09-14 | 2018-11-28 | 2018-10-05 | G | [25 empty] | 2018-09-19 | 2018-09-19 | 2018-11-16 | 2018-10-09 | G | [5 empty] | 2018-11-19 | 2018-10-10 | 2018-12-18 | 2018-10-10 | G | 2018-12-19 | 2018-10-10 | 2019-02-15 | 2018-10-10 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.17691
211 | 115201 | Patterson Avenue Sidewalks | 0006 | Primary | Facilities for Pedestrians and Bicycles | Locally | Henrico County | ASHLAND | Richmond | Richmond:Henrico County | Infrastructure Investment Division | Melinda G Baicy | Melinda.Baicy@vdot.virginia.gov | (804) 609-5390 | Melinda G Baicy | Melinda.Baicy@vdot.virginia.gov | (804) 609-5390 | TBD | eur@henrico.us | TBD | 0 |  | 0 | FY2024 | 1366000 | 1366000 | NO DATES SET YET | G | Agreement with Locality milestone is 219 days ahead of the expected completion date | G | Project is on budget | 2021-07-06 |  | 2021-09-28 |  | G | 2021-09-29 |  | 2021-10-01 |  | G | 2021-10-04 |  | 2022-04-14 |  | G | [10 empty] | 2023-04-18 |  | 2023-05-08 |  | G | [5 empty] | 2023-05-10 |  | 2024-02-22 |  | G | 2022-05-20 |  | 2023-01-27 |  | G | [5 empty] | 2024-03-11 |  | 2024-04-05 |  | G | 2024-06-25 |  | 2024-06-25 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.15811
212 | 115312 | Crown Point Road Drainage Improvements | 0000 | Urban | Mitigation of Water Pollution Due to Highway Runof | Locally | Roanoke | SALEM | Salem | Roanoke:Roanoke City | Local Assistance Division | Cheryl B Becker | Cheryl.Becker@vdot.virginia.gov | (540) 492-2531 | Cheryl B Becker | Cheryl.Becker@vdot.virginia.gov | (540) 492-2531 | Joseph Arthur | Joseph.Arthur@roanokeva.gov | (540) 853-5901 | 0 |  | 0 | FY2022 | 450000 | 450000 | ACTIVITY DATES SET | R | Determine Requirements milestone finished 75 days late | G | Project is on budget | 2019-06-28 | 2019-06-28 | 2019-09-23 | 2020-06-18 | R | 2019-09-24 | 2020-06-18 | 2019-09-26 | 2020-06-18 | R | 2019-09-27 | 2020-06-18 | 2020-04-08 | 2020-06-22 | R | [25 empty] | 2021-02-05 |  | 2021-05-28 |  | G | [5 empty] | 2021-06-15 |  | 2021-07-13 |  | G | 2021-09-30 |  | 2021-09-30 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.20384
213 | 115368 | City of Newport News 691 J Clyde Morris Blvd | 0017 | Urban | Restoration and Rehabilitation | Locally | Newport News | WILLIAMSBURG | Hampton Roads | Hampton Roads:Newport News | Local Assistance Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Chessica Villaflores | Chessica.Villaflores@vdot.virginia.gov | (757) 956-3094 | Bridjette Parker | bjparker@nnva.gov | (757) 926-8314 | 0 |  | 0 | FY2020 | 433379 | 430279 | AWARDED | G | Start Delivery milestone finished 70 days early | G | Project is on budget | 2019-11-18 | 2019-11-18 | 2020-02-18 | 2019-11-19 | G | [5 empty] | 2019-11-18 | 2019-11-18 | 2019-12-03 | 2019-11-19 | G | [35 empty] | 2020-05-11 | 2020-02-20 | 2020-06-08 | 2020-04-14 | G | 2020-06-30 | 2020-04-14 | 2020-06-30 | 2020-04-21 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.15839
214 | 115455 | #SMART20 - Int Imprv on Rtes 220/619 (Pleasant Hill/Sontag) | 0220 | Primary | Safety | VDOT | Franklin County | BEDFORD | Salem | NonMPO:NonMPO | Infrastructure Investment Division | Thomas W Digiulian | Thomas.DiGiulian@VDOT.Virginia.gov | (540) 387-5356 | Brett A Elledge | Brett.Elledge@vdot.virginia.gov | (540) 375-3580 |  |  |  | 1 | 2020 | 0 | FY2028 | 5928000 | 5928000 | NO DATES SET YET-PE OPEN | G | Start Development milestone finished 1055 days early | G | Project is on budget | [5 empty] | 2023-08-01 | 2020-08-26 | 2023-08-14 | 2020-09-23 | G | 2023-08-15 |  | 2024-07-12 |  | G | [5 empty] | 2025-05-19 |  | 2025-06-02 |  | G | 2026-09-04 |  | 2026-09-18 |  | G | 2027-02-19 |  | 2027-08-23 |  | G | 2026-10-06 |  | 2027-04-16 |  | G | 2026-02-26 |  | 2026-08-28 |  | G | [5 empty] | 2027-09-14 |  | 2027-09-14 |  | G | 2027-12-08 |  | 2027-12-08 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 1 | 0.19327
215 | 117124 | Lakeside Drive Sidewalk | 0620 | Urban | Facilities for Pedestrians and Bicycles | Locally | York County | WILLIAMSBURG | Hampton Roads | Hampton Roads:York County | Local Assistance Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Keisha Wilkins | Keisha.Wilkins@vdot.virginia.gov | (757) 956-3110 | Timothy Cross | tcross@yorkcounty.gov | (757) 890-3496 | 0 |  | 0 | FY2025 | 462500 | 462500 | NO DATES SET YET | G | Agreement with Locality milestone is 232 days ahead of the expected completion date | G | Project is on budget | 2021-06-04 |  | 2021-10-11 |  | G | 2021-10-12 |  | 2021-11-02 |  | G | 2022-05-16 |  | 2022-09-07 |  | G | [10 empty] | 2024-01-02 |  | 2024-02-07 |  | G | [5 empty] | 2024-02-08 |  | 2024-07-08 |  | G | 2024-06-04 |  | 2024-10-31 |  | G | [5 empty] | 2024-10-09 |  | 2024-11-06 |  | G | 2025-02-03 |  | 2025-02-03 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.12329
216 | 118168 | 11th Street - Streetscape Improvements | 0000 | Urban | Reconstruction w/o Added Capacity | Locally | Roanoke | SALEM | Salem | Roanoke:Roanoke City | Local Assistance Division | Cheryl B Becker | Cheryl.Becker@vdot.virginia.gov | (540) 492-2531 | Cheryl B Becker | Cheryl.Becker@vdot.virginia.gov | (540) 492-2531 | Joseph Arthur | Joseph.Arthur@roanokeva.gov | (540) 853-5901 | 0 |  | 0 | FY2028 | 1500000 | 1500000 | NO DATES SET YET | G | Agreement with Locality milestone is 1422 days ahead of the expected completion date | G | Project is on budget | 2024-08-30 |  | 2025-01-13 |  | G | 2025-01-14 |  | 2025-02-05 |  | G | 2025-08-12 |  | 2025-12-08 |  | G | [10 empty] | 2027-04-01 |  | 2027-05-05 |  | G | [5 empty] | 2027-05-06 |  | 2027-10-04 |  | G | 2027-08-31 |  | 2028-02-04 |  | G | [5 empty] | 2028-01-12 |  | 2028-02-10 |  | G | 2028-05-01 |  | 2028-05-01 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.17801
217 | 4483 | #HB2.FY17 ATKINSON BLVD - 4 LANES |  | Urban | New Construction Roadway | Locally | Newport News | WILLIAMSBURG | Hampton Roads | Hampton Roads:Newport News | Infrastructure Investment Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Chessica Villaflores | Chessica.Villaflores@vdot.virginia.gov | (757) 956-3094 | Vincent Urbano | vurbano@nngov.com | (757) 926-8694 | 1 | 2017 | 0 | FY2018 | 68382794 | 68382794 | CONSTRUCTION STARTED | G | Start Delivery milestone finished on-time | G | Project is on budget | [5 empty] | 1987-10-01 | 1987-06-07 | 1987-10-30 | 1987-06-08 | G | 1989-09-01 | 1987-06-07 | 1990-09-28 | 1990-06-30 | G | [5 empty] | 2016-02-02 | 2016-02-02 | 2016-06-20 | 2016-06-20 | G | 2016-06-01 | 2016-06-01 | 2016-09-14 | 2016-09-14 | G | [5 empty] | 2016-09-22 | 2016-09-22 | 2017-04-01 | 2017-04-01 | G | 2003-02-28 | 2003-02-28 | 2012-06-18 | 2012-06-18 | G | [5 empty] | 2017-03-07 | 2017-03-07 | 2017-05-11 | 2017-05-11 | G | 2017-07-25 | 2017-07-25 | 2017-08-11 | 2017-08-11 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.27265
218 | 101004 | US 58 WB BRIDGE RPLCMNT OVER CROOKED CR: #SGR18VB | 0058 | Primary | Bridge Replacement w/o Added Capacity | VDOT | Carroll County | MARTINSVILLE | Salem | NonMPO:NonMPO | Infrastructure Investment/Asset Management Division | Anthony T Marshall | Todd.Marshall@VDOT.Virginia.gov | (540) 387-5460 | Ankur K Patel | Ankur.Patel@vdot.virginia.gov | (540) 387-5393 |  |  |  | 0 |  | 1 | FY2024 | 4583206 | 4051428 | ACTIVITY DATES SET | G | Determine Requirements milestone finished 1516 days early | G | Project is on budget | [10 empty] | 2023-10-30 | 2017-10-27 | 2023-11-03 | 2019-09-09 | G | [35 empty] | 2024-01-09 |  | 2024-01-09 |  | G | 2024-04-02 |  | 2024-04-02 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.06102
219 | 106470 | Dismal Swamp Canal Trail, Improved Amenities | 0017 | Miscellaneous | Facilities for Pedestrians and Bicycles | Locally | Chesapeake | NORFOLK | Hampton Roads | Hampton Roads:Chesapeake | Infrastructure Investment Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Johndel A Alcaide | John.Alcaide@vdot.virginia.gov | (757) 956-3098 | Troy Eisenberger, PE | teisenberger@cityofchesapeake.net | (757) 382-6176 | 0 |  | 0 | FY2019 | 401791 | 511174 | ACTIVITY DATES SET | R | Solicit Bids milestone is 968 days past the expected completion date | R | Project estimate is less than $5M and is 20% or more over budget | [5 empty] | 2014-10-01 | 2016-02-11 | 2015-11-30 | 2016-02-11 | R | 2017-03-01 | 2017-03-01 | 2017-09-01 | 2017-08-31 | G | [35 empty] | 2018-05-01 |  | 2018-06-29 |  | R | 2019-03-07 |  | 2019-04-19 |  | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.17307
220 | 108809 | #HB2.FY17 I-81 Exit 245 NB Off Ramp Realignment | 0081 | Interstate | Reconstruction w/o Added Capacity | Locally | Harrisonburg | HARRISONBURG | Staunton | Harrisonburg:Harrisonburg | Infrastructure Investment Division | John-Allen L Ennis | JohnAllen.Ennis@VDOT.Virginia.gov | (540) 332-9118 | Timothy Gregory | Tim.Gregory@vdot.virginia.gov | (540) 332-7891 | Tom Hartman | tom.hartman@harrisonburgva.gov | (540) 434-5928 | 1 | 2017 | 0 | FY2020 | 3923707 | 3645172 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 95 days early | G | Project is on budget | 2016-08-01 | 2016-08-01 | 2016-10-25 | 2016-10-25 | G | 2016-10-26 | 2016-10-26 | 2016-10-26 | 2016-10-26 | G | 2016-10-27 | 2016-10-27 | 2018-02-22 | 2017-11-20 | G | [10 empty] | 2019-02-22 | 2018-07-16 | 2019-03-14 | 2018-09-20 | G | [5 empty] | 2019-03-18 | 2018-09-21 | 2019-12-24 | 2018-12-21 | G | [10 empty] | 2020-01-13 | 2019-11-01 | 2020-02-11 | 2019-11-08 | G | 2020-02-12 | 2019-12-16 | 2020-03-24 | 2019-12-20 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.080011
224 | 113032 | #SGR19VB - RT707 over Pitts Creek (Fed 24320) Replacement | 0707 | Secondary | Bridge Replacement w/o Added Capacity | VDOT | Accomack County | ACCOMAC | Hampton Roads | NonMPO:NonMPO | Infrastructure Investment/Asset Management Division | Mark Wagner |  |  | John K Arms | John.Arms@vdot.virginia.gov | (757) 995-5156 |  |  |  | 0 |  | 1 | FY2021 | 3550000 | 2750000 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 279 days early | G | Project is on budget | [10 empty] | 2019-05-20 | 2019-03-04 | 2019-05-24 | 2019-03-08 | G | [10 empty] | 2019-12-03 | 2019-03-19 | 2019-12-16 | 2019-04-03 | G | 2020-05-13 | 2019-02-09 | 2020-11-17 | 2019-02-09 | G | 2020-01-03 | 2019-08-13 | 2020-07-09 | 2019-08-13 | G | 2019-05-28 | 2019-05-31 | 2019-12-03 | 2019-05-31 | G | [5 empty] | 2020-12-08 | 2020-03-10 | 2020-12-08 | 2020-03-10 | G | 2021-03-04 | 2020-05-29 | 2021-03-04 | 2020-05-29 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.10344
225 | 113315 | RTE 609 (Old Centralia, Rt 10-Thomas Dale HS) - SIDEWALK | 0609 | Secondary | Facilities for Pedestrians and Bicycles | Locally | Chesterfield County | CHESTERFIELD | Richmond | Richmond:Chesterfield County | Local Assistance Division | Brian J Lokker | Brian.Lokker@VDOT.Virginia.gov | (804) 524-6010 | Brian J Lokker | Brian.Lokker@VDOT.Virginia.gov | (804) 524-6010 | Barb Smith | SmithBK@chesterfield.gov | (804) 748-1037 | 0 |  | 0 | FY2020 | 557000 | 352465 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 138 days early | G | Project is on budget | 2018-07-02 | 2018-07-02 | 2018-09-25 | 2018-07-18 | G | 2019-07-01 | 2018-08-07 | 2019-07-03 | 2018-08-14 | G | 2019-07-05 | 2018-08-15 | 2020-07-06 | 2019-03-21 | G | [10 empty] | 2019-05-02 | 2019-05-13 | 2019-05-16 | 2019-05-14 | G | [5 empty] | 2019-05-20 | 2019-05-20 | 2019-12-20 | 2019-12-18 | G | [10 empty] | 2020-01-23 | 2020-01-22 | 2020-04-16 | 2020-01-22 | G | 2020-06-08 | 2020-01-22 | 2020-06-08 | 2020-01-22 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.27078
226 | 113778 | RTE 612 - RURAL RUSTIC RD (SURFACE TREAT NONHARDSURFACE RD) | 0612 | Secondary | Reconstruction w/o Added Capacity | VDOT | Albemarle County | CHARLOTTESVILLE | Culpeper | NonMPO:NonMPO | Infrastructure Investment Division | Ken Connors |  |  | Harold L Jones | Harold.Jones@VDOT.virginia.gov | (434) 422-9378 |  |  |  | 0 |  | 0 | FY2023 | 180000 | 180000 | NO DATES SET YET | R | Start Development milestone is 130 days past the expected completion date | G | Project is on budget | [5 empty] | 2020-10-01 |  | 2020-10-14 |  | R | 2020-10-15 |  | 2021-06-11 |  | G | [5 empty] | 2022-02-22 |  | 2022-04-04 |  | G | [5 empty] | 2022-07-19 |  | 2022-11-09 |  | G | [5 empty] | 2022-07-01 |  | 2022-10-03 |  | G | [5 empty] | 2022-12-13 |  | 2022-12-13 |  | G | 2023-03-09 |  | 2023-03-09 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | SAAP CONTRACT | 0 | 0 | 0.156
227 | 113887 | Improvements at Non-Median break Intersections | 9999 | Urban | Safety | Locally | Suffolk | NORFOLK | Hampton Roads | Hampton Roads:Suffolk | Infrastructure Investment Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Johndel A Alcaide | John.Alcaide@vdot.virginia.gov | (757) 956-3098 | Robert Lewis | relewis@suffolkva.us | (715) 514-7603 | 0 |  | 0 | FY2026 | 214000 | 214000 | NO DATES SET YET | G | Agreement with Locality milestone is 1012 days ahead of the expected completion date | Y | Estimate not current | 2023-09-01 |  | 2023-11-30 |  | G | 2023-12-01 |  | 2023-12-05 |  | G | 2023-12-06 |  | 2024-06-12 |  | G | [25 empty] | 2024-07-19 |  | 2025-03-27 |  | G | [5 empty] | 2025-04-24 |  | 2025-05-21 |  | G | 2025-08-11 |  | 2025-08-11 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.16256
228 | 113983 | NORTON ROAD - CONSTRUCT NEW SIDEWALK-PHASE 4 | 0000 | Urban | Facilities for Pedestrians and Bicycles | Locally | Wise | WISE | Bristol | NonMPO:NonMPO | Infrastructure Investment Division | Allan D Sumpter | Allan.Sumpter@VDOT.virginia.gov | (276) 525-6461 | Roger L Musser | Roger.Musser@VDOT.Virginia.gov | (276) 696-3260 | Laura Mullins | planner@townofwise.org | (276) 328-6013 | 0 |  | 0 | FY2022 | 355555 | 355555 | NO DATES SET YET-PE OPEN | R | Determine Requirements milestone is 11 days past the expected completion date | G | Project is on budget | 2020-05-01 | 2020-05-01 | 2020-07-27 | 2020-07-27 | G | 2020-07-28 | 2020-07-28 | 2020-07-30 | 2020-07-30 | G | 2020-07-31 |  | 2021-02-10 |  | R | [25 empty] | 2021-03-19 |  | 2021-11-18 |  | G | [5 empty] | 2022-03-02 |  | 2022-03-29 |  | G | 2022-06-16 |  | 2022-06-16 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.10428
230 | 108771 | WATKINS AVENUE - INSTALL STORM DRAIN,CURB,GUTTER, & PAVE | 9999 | Urban | Restoration and Rehabilitation | Locally | South Boston | HALIFAX | Lynchburg | NonMPO:NonMPO | Local Assistance Division | Gregg Allen | Gregg.Allen@vdot.virginia.gov | (434) 426-5575 | John E Neblett | John.Neblett@VDOT.Virginia.gov | (434) 856-8202 | C.W. Crowder, Jr. | ccrowder@southboston.va.us | (434) 575-4261 | 0 |  | 0 | FY2019 | 245516 | 245515 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 223 days early | G | Project is on budget | 2016-10-03 | 2016-07-01 | 2016-12-30 | 2016-07-08 | G | 2017-01-03 | 2016-08-16 | 2017-01-05 | 2016-08-16 | G | 2017-01-06 | 2017-10-03 | 2017-07-13 | 2017-10-03 | R | [35 empty] | 2017-08-10 | 2017-08-10 | 2017-08-31 | 2017-08-10 | G | 2017-10-17 | 2017-10-17 | 2019-04-08 | 2018-08-28 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.073672
231 | 108900 | #HB2.FY17 N Main Intersection Improvements at Rte 460 Bypass | 0460 | Primary | Safety | VDOT | Blacksburg | CHRISTIANSBURG | Salem | New River Valley:Blacksburg | Infrastructure Investment Division | Alex H Price | Alex.Price@VDOT.Virginia.gov | (540) 378-5053 | Marvin D Mann | M.Mann@VDOT.Virginia.gov | (540) 378-5055 | Randy Formica | rformica@blacksburg.gov | (540) 961-1121 | 1 | 2017 | 0 | FY2020 | 3316565 | 2389163 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 448 days early | G | Project is on budget | [5 empty] | 2017-06-20 | 2017-06-08 | 2017-07-03 | 2017-07-11 | R | 2017-07-05 | 2017-07-12 | 2018-06-01 | 2017-11-01 | G | [5 empty] | 2017-12-27 | 2017-10-10 | 2018-01-10 | 2017-11-08 | G | 2018-06-14 | 2017-11-07 | 2018-06-27 | 2017-11-13 | G | 2018-09-10 | 2017-09-21 | 2019-01-23 | 2018-05-01 | G | 2018-07-16 | 2017-11-27 | 2018-12-07 | 2018-01-16 | G | 2018-04-04 | 2018-01-10 | 2018-07-26 | 2018-01-10 | G | [5 empty] | 2019-03-12 | 2018-02-27 | 2019-03-12 | 2018-02-27 | G | 2019-04-25 | 2018-04-27 | 2019-07-19 | 2018-04-27 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.12245
232 | 110892 | #SGR18LB - BRIDGE MAINTNANCE - RT 250 OVER RT 29 BUS | 0250 | Urban | Bridge Rehab w/o Added Capacity | Locally | Charlottesville | CHARLOTTESVILLE | Culpeper | Charlottesville:Charlottesville | Infrastructure Investment Division | Ken Connors |  |  | Michael D Barnes | MichaelD.Barnes@vdot.virginia.gov | (434) 422-9861 | Kyle Kling | klingk@charlottesville.gov | (434) 970-3182 | 0 |  | 1 | FY2021 | 3847554 | 3638429 | CONSTRUCTION STARTED | G | Start Delivery milestone finished on-time | G | Project is on budget | 2018-01-02 | 2018-01-02 | 2018-03-29 | 2018-03-20 | G | 2018-03-30 | 2018-03-30 | 2018-04-03 | 2018-04-02 | G | 2018-04-04 | 2018-04-02 | 2018-10-05 | 2018-10-05 | G | [10 empty] | 2019-10-09 | 2019-10-09 | 2019-10-30 | 2019-10-17 | G | [5 empty] | 2019-11-01 | 2019-10-18 | 2020-08-13 | 2020-06-08 | G | [10 empty] | 2020-08-31 | 2020-08-24 | 2020-09-28 | 2020-09-11 | G | 2020-09-29 | 2020-09-14 | 2020-11-09 | 2020-11-09 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.21488
233 | 111161 | BELVIDERE STREET GATEWAY - PHASE IV |  | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Richmond | ASHLAND | Richmond | Richmond:Richmond | Local Assistance Division | Jorg Huckabee-Mayfield | Jorg.Huckabee-Mayfield@VDOT.Virginia.gov | (804) 609-5292 | Jorg Huckabee-Mayfield | Jorg.Huckabee-Mayfield@VDOT.Virginia.gov | (804) 609-5292 | Ishoc Salaam | ishoc.salaam@richmondgov.com | 804646631 | 0 |  | 0 | FY2022 | 717830 | 689087 | ACTIVITY DATES SET | G | Obtained Permits milestone finished 188 days early | G | Project is on budget | 2017-10-02 | 2017-10-02 | 2017-12-29 | 2018-11-29 | R | 2018-01-02 | 2018-07-16 | 2018-01-04 | 2018-07-25 | R | 2018-01-05 | 2018-11-29 | 2018-07-12 | 2020-04-16 | R | [25 empty] | 2020-08-04 | 2020-09-02 | 2021-03-09 | 2020-09-02 | G | [5 empty] | 2021-04-21 |  | 2021-06-22 |  | G | 2021-04-23 |  | 2021-10-20 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.35368
234 | 112897 | I-664 NB Auxiliary Lane | 0664 | Interstate | Safety | VDOT | Chesapeake | NORFOLK | Hampton Roads | Hampton Roads:Chesapeake | Infrastructure Investment Division | Blaine Tudor |  |  | John K Arms | John.Arms@vdot.virginia.gov | (757) 995-5156 |  |  |  | 0 |  | 0 | FY2019 | 3854841 | 3983636 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 121 days early | Y | Project estimate is less than $5M and is up to 20% over budget | [5 empty] | 2018-07-09 | 2018-05-11 | 2018-07-20 | 2018-05-11 | G | 2018-07-23 | 2018-05-11 | 2019-06-19 | 2018-08-24 | G | [5 empty] | 2018-07-09 | 2018-07-09 | 2018-07-09 | 2018-07-09 | G | 2018-07-31 | 2018-07-31 | 2018-07-31 | 2018-07-31 | G | 2018-07-31 | 2018-07-31 | 2018-07-31 | 2018-07-31 | G | 2018-07-31 | 2018-07-31 | 2018-07-31 | 2018-07-31 | G | [10 empty] | 2019-03-12 | 2018-11-20 | 2019-03-12 | 2018-11-20 | G | 2019-05-31 | 2019-01-23 | 2019-05-31 | 2019-01-30 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.14839
235 | 113143 | VA Rte 8 Pedestrian & Curb Improvements | 0008 | Primary | Reconstruction w/ Added Capacity | VDOT | Montgomery County | CHRISTIANSBURG | Salem | NonMPO:NonMPO | Local Assistance Division | Alex H Price | Alex.Price@VDOT.Virginia.gov | (540) 378-5053 | Ankur K Patel | Ankur.Patel@vdot.virginia.gov | (540) 387-5393 | Emily Gibson | Gibsonej@montgomerycountyva.gov | (540) 394-2148 | 0 |  | 0 | FY2027 | 1332871 | 1087452 | ACTIVITY DATES SET | G | Engage Public milestone finished 1497 days early | G | Project is on budget | [5 empty] | 2019-10-15 | 2019-10-15 | 2019-10-29 | 2019-10-22 | G | 2019-10-30 | 2019-10-23 | 2020-09-25 | 2020-09-25 | G | [5 empty] | 2024-12-04 | 2020-10-29 | 2024-12-16 | 2020-11-10 | G | 2025-12-05 |  | 2025-12-22 |  | G | 2026-07-15 |  | 2026-11-03 |  | G | 2026-01-09 |  | 2026-07-14 |  | G | [10 empty] | 2026-12-08 |  | 2026-12-08 |  | G | 2026-12-09 |  | 2027-05-07 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.16933
236 | 113463 | South Boulevard Sidewalk | 0000 | Urban | Facilities for Pedestrians and Bicycles | Locally | Virginia Beach | NORFOLK | Hampton Roads | Hampton Roads:Virginia Beach | Local Assistance Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Marci Thompson | Marci.Thompson@vdot.virginia.gov | (757) 956-3093 | Katie Shannon | kshannon@vbgov.com | (757) 385-1514 | 0 |  | 0 | FY2022 | 652935 | 652935 | NO DATES SET YET-PE OPEN | R | Determine Requirements milestone is 591 days past the expected completion date | G | Project is on budget | 2018-10-01 | 2018-10-01 | 2018-12-28 | 2019-04-04 | R | 2018-12-31 | 2019-04-10 | 2019-01-03 | 2019-04-25 | R | 2019-01-04 | 2019-04-26 | 2019-07-11 |  | R | [10 empty] | 2020-05-06 |  | 2020-05-27 |  | R | [5 empty] | 2020-05-29 |  | 2021-03-12 |  | Y | 2019-08-16 |  | 2020-04-23 |  | R | [5 empty] | 2021-03-30 |  | 2021-04-26 |  | G | 2021-07-15 |  | 2021-07-15 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.094947
237 | 113859 | RTE 600 - RURAL RUSTIC - SURFACE TREAT NON-HARDSURFACE ROAD | 0600 | Secondary | Reconstruction w/o Added Capacity | VDOT | Albemarle County | CHARLOTTESVILLE | Culpeper | NonMPO:NonMPO | Infrastructure Investment Division | Ken Connors |  |  | Harold L Jones | Harold.Jones@VDOT.virginia.gov | (434) 422-9378 |  |  |  | 0 |  | 0 | FY2026 | 437500 | 437500 | NO DATES SET YET | G | Start Development milestone is 964 days ahead of the expected completion date | Y | Estimate not current | [5 empty] | 2023-10-02 |  | 2023-10-13 |  | G | 2023-10-17 |  | 2024-06-11 |  | G | [5 empty] | 2025-02-20 |  | 2025-04-02 |  | G | [5 empty] | 2025-07-17 |  | 2025-11-07 |  | G | [5 empty] | 2025-07-01 |  | 2025-10-01 |  | G | [5 empty] | 2025-11-10 |  | 2025-11-10 |  | G | 2026-02-06 |  | 2026-02-06 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | SAAP CONTRACT | 0 | 0 | 0.15662
238 | 113895 | Abrams Creek Trail - Frederick County | 0657 | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Frederick County | EDINBURG | Staunton | Winchester:Frederick County | Infrastructure Investment Division | David C Morris | David.Morris2@VDOT.Virginia.gov | (540) 332-8607 | Kimberly Cameron | Kim.Cameron@vdot.virginia.gov | (540) 332-7886 | Jon Turkel - Fredrick County | jturkel@fcva.us | (540) 722-8300 | 0 |  | 0 | FY2025 | 1089900 | 1089900 | NO DATES SET YET | G | Agreement with Locality milestone is 344 days ahead of the expected completion date | G | Project is on budget | 2021-10-29 |  | 2022-01-31 |  | G | 2022-02-01 |  | 2022-02-03 |  | G | 2022-02-04 |  | 2022-08-09 |  | G | [10 empty] | 2023-06-06 |  | 2023-06-26 |  | G | [5 empty] | 2023-06-28 |  | 2024-04-10 |  | G | 2022-09-15 |  | 2023-05-23 |  | G | [5 empty] | 2024-04-26 |  | 2024-05-23 |  | G | 2024-08-13 |  | 2024-08-13 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.28109
239 | 114063 | NATIONWIDE DRIVE - PEDESTRIAN IMPROVEMENTS | 9999 | Urban | Safety | Locally | Lynchburg | APPOMATTOX | Lynchburg | Lynchburg:Lynchburg | Infrastructure Investment Division | Gregg Allen | Gregg.Allen@vdot.virginia.gov | (434) 426-5575 | Gregg Allen | Gregg.Allen@vdot.virginia.gov | (434) 426-5575 | Don DeBerry | donald.deberry@lynchburgva.gov | (434) 455-3935 | 0 |  | 0 | FY2024 | 685253 | 685253 | NO DATES SET YET | G | Agreement with Locality milestone is 64 days ahead of the expected completion date | G | Project is on budget | 2021-02-01 |  | 2021-04-26 |  | G | 2021-04-27 |  | 2021-04-29 |  | G | 2021-04-30 |  | 2021-11-03 |  | G | [10 empty] | 2022-11-07 |  | 2022-11-30 |  | G | [5 empty] | 2022-12-02 |  | 2023-09-12 |  | G | 2021-12-14 |  | 2022-08-17 |  | G | [5 empty] | 2023-09-28 |  | 2023-10-26 |  | G | 2024-01-23 |  | 2024-01-23 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.19199
240 | 115139 | #SMART20 University Blvd/Evelyn Byrd Ave Rd Diet & Sidewalk |  | Urban | Safety | Locally | Harrisonburg | HARRISONBURG | Staunton | Harrisonburg:Harrisonburg | Infrastructure Investment Division | Randolph S Kiser | Randy.Kiser@VDOT.Virginia.gov | (540) 332-9092 | Michael S Fulcher | Michael.Fulcher@VDOT.Virginia.gov | (540) 332-2243 | City of Harrisonburg | Tom.Hartman@harrisonburgva.gov | (540) 434-5928 | 1 | 2020 | 0 | FY2027 | 3515278 | 3515278 | NO DATES SET YET | G | Agreement with Locality milestone is 976 days ahead of the expected completion date | G | Project is on budget | 2023-08-01 |  | 2023-10-25 |  | G | 2023-10-26 |  | 2023-10-30 |  | G | 2023-10-31 |  | 2024-05-09 |  | G | [10 empty] | 2025-05-09 |  | 2025-05-30 |  | G | [5 empty] | 2025-06-03 |  | 2026-03-17 |  | G | 2024-06-17 |  | 2025-02-24 |  | G | [5 empty] | 2026-04-02 |  | 2026-04-29 |  | G | 2026-07-20 |  | 2026-07-20 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.083312
241 | 115354 | #SGR20LP - Franklin Bypass | 0058 | Urban | Resurfacing | Locally | Suffolk | NORFOLK | Hampton Roads | Hampton Roads:Suffolk | Infrastructure Investment/Asset Management Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Johndel A Alcaide | John.Alcaide@vdot.virginia.gov | (757) 956-3098 | Edward Heide | eheide@suffolkva.us | (757) 514-7615 | 0 |  | 1 | FY2020 | 382759 | 382759 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 188 days early | G | Project is on budget | 2019-10-01 | 2019-10-01 | 2019-12-30 | 2019-10-25 | G | [5 empty] | 2019-10-01 | 2019-10-01 | 2019-10-14 | 2019-10-14 | G | [35 empty] | 2020-01-16 | 2019-10-25 | 2020-02-14 | 2019-10-30 | G | 2020-03-10 | 2019-10-25 | 2020-05-05 | 2019-10-30 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.06811
242 | 115482 | #SMART20-College Avenue Traffic Signal Sync (APP ID#5039) | 0102 | Urban | Traffic Management/Engineering | VDOT | Bluefield | LEBANON | Bristol | NonMPO:NonMPO | Infrastructure Investment Division | Brian Holt | Brian.Holt@vdot.virginia.gov | (276) 696-3414 | Jeremy J Mullins | Jeremy.Mullins@vdot.virginia.gov | (276) 696-3259 |  |  |  | 1 | 2020 | 0 | FY2023 | 859000 | 859000 | ACTIVITY DATES SET | G | Determine Requirements milestone finished 1398 days early | G | Project is on budget | [5 empty] | 2023-09-01 | 2019-10-31 | 2023-09-15 | 2019-11-21 | G | 2023-09-18 | 2019-11-22 | 2024-05-13 | 2020-07-15 | G | [5 empty] | 2021-06-29 |  | 2021-08-10 |  | G | [5 empty] | 2022-01-12 |  | 2022-05-06 |  | G | [15 empty] | 2022-06-14 |  | 2022-06-16 |  | G | 2022-09-07 |  | 2022-09-07 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.11434
243 | 115892 | Rte. 748 / Lipscomb Rd. > 50 VPD | 0748 | Secondary | Resurfacing | VDOT | Bedford County | BEDFORD | Salem | NonMPO:NonMPO | Infrastructure Investment Division | John JP Morris | John.Morris@vdot.virginia.gov | (540) 682-7010 | John JP Morris | John.Morris@vdot.virginia.gov | (540) 682-7010 |  |  |  | 0 |  | 0 | FY2030 | 600000 | 600000 | NO DATES SET YET | G | Start Development milestone is 1635 days ahead of the expected completion date | Y | Estimate not current | [5 empty] | 2025-08-01 |  | 2025-08-14 |  | G | 2025-08-15 |  | 2026-07-15 |  | G | [5 empty] | 2027-05-20 |  | 2027-06-03 |  | G | 2028-09-07 |  | 2028-09-20 |  | G | 2029-02-21 |  | 2029-08-23 |  | G | 2028-10-06 |  | 2029-04-18 |  | G | 2028-02-29 |  | 2028-08-30 |  | G | [5 empty] | 2029-09-11 |  | 2029-09-11 |  | G | 2029-12-05 |  | 2029-12-05 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | SAAP CONTRACT | 0 | 0 | 0.12055
244 | 116327 | #I81CIP NWRO MAINTENANCE FOR NEW CMS & CAMERAS FY20-25 | 0081 | Interstate | Safety | VDOT | Staunton District-wide |  | Staunton | NonMPO:NonMPO | Infrastructure Investment Division | Ricky A Via | Ricky.Via@vdot.virginia.gov | (804) 371-2396 | Roy A Reid | Roy.Reid@VDOT.Virginia.gov | (540) 332-9148 |  |  |  | 0 |  | 0 | FY2020 | 1137923 | 1137923 | CONSTRUCTION STARTED | G | Start Delivery milestone finished on-time | G | Project is on budget | [10 empty] | 2019-09-25 | 2019-08-23 | 2020-02-07 | 2020-01-06 | G | [35 empty] | 2020-01-08 | 2020-01-08 | 2020-01-14 | 2020-01-14 | G | 2020-01-15 | 2020-01-15 | 2020-01-23 | 2020-01-23 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | WORK/TASK ORDER | 1 | 0 | 0.066139
245 | 118128 | CINDER BED ROAD BIKEWAY |  | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Fairfax County | FAIRFAX | Northern Virginia | Northern Virginia:Fairfax County | Local Assistance Division | Amir Salahshoor | A.Salahshoor@VDOT.Virginia.gov | (703) 259-1957 | Jeffrey S Daily | Jeff.Daily@VDOT.Virginia.gov | (703) 259-2993 | Jeffrey Fasceski | Jeffrey.Fasceski@fairfaxcounty.gov |  | 0 |  | 0 | FY2027 | 12750000 | 12750000 | NO DATES SET YET | R | Agreement with Locality milestone is 6 days past the expected completion date | G | Project is on budget | 2020-10-01 | 2020-10-01 | 2021-02-15 |  | R | 2021-02-16 |  | 2021-03-09 |  | Y | 2021-04-07 |  | 2021-12-09 |  | G | [10 empty] | 2024-03-14 |  | 2024-04-17 |  | G | [5 empty] | 2024-04-18 |  | 2025-04-29 |  | G | 2025-03-27 |  | 2025-11-26 |  | G | [5 empty] | 2025-08-01 |  | 2025-12-31 |  | G | 2026-03-25 |  | 2026-08-31 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.30171
246 | 71874 | #SGR18LB - Shawnee Ave. Bridge Repair/Replacement | 0023 | Urban | Bridge Replacement w/o Added Capacity | VDOT | Big Stone Gap | WISE | Bristol | NonMPO:NonMPO | Infrastructure Investment Division | Allan D Sumpter | Allan.Sumpter@VDOT.virginia.gov | (276) 525-6461 | Daniel B Cannon | Daniel.Cannon@VDOT.Virginia.gov | (276) 696-3376 |  |  |  | 0 |  | 1 | FY2021 | 1097000 | 2773222 | ACTIVITY DATES SET | R | Solicit Bids milestone is 195 days past the expected completion date | R | Project estimate is less than $5M and is 20% or more over budget | [5 empty] | 2005-01-17 | 2005-03-29 | 2005-01-31 | 2005-04-19 | R | 2005-05-25 | 2005-05-25 | 2005-08-19 | 2005-07-13 | G | [10 empty] | 2018-12-03 | 2018-12-03 | 2019-02-28 | 2019-02-28 | G | 2019-07-15 | 2019-05-30 | 2019-11-08 | 2020-04-06 | R | [5 empty] | 2018-09-17 | 2019-08-29 | 2019-08-30 | 2019-08-29 | G | [5 empty] | 2020-07-24 |  | 2020-08-10 |  | R | 2020-10-13 |  | 2020-11-25 |  | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.068399
247 | 97111 | #SGR17VB - Bridge Replacement RT 11 Over I-81 (Fed 15753) | 0011 | Primary | Bridge Replacement w/o Added Capacity | VDOT | Rockingham County | HARRISONBURG | Staunton | NonMPO:NonMPO | Infrastructure Investment/Asset Management Division | Rex L Pearce | Rex.Pearce@vdot.virginia.gov | (540) 332-9104 | Ronald L Tabor | Ronald.Tabor@vdot.virginia.gov | (540) 332-7887 |  |  |  | 0 |  | 1 | FY2020 | 12762219 | 16382997 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 7 days early | R | Project estimate is greater than $10M and is over budget by (a) 10% or more or (b) $5M or more | [5 empty] | 2010-09-01 | 2010-08-26 | 2010-09-01 | 2010-08-26 | G | 2010-10-01 | 2010-12-15 | 2012-01-16 | 2012-11-02 | R | [10 empty] | 2015-07-31 | 2015-07-31 | 2015-08-11 | 2015-08-11 | G | 2015-02-17 | 2018-10-11 | 2019-01-08 | 2019-05-10 | R | 2018-03-01 | 2018-08-20 | 2018-12-04 | 2018-12-10 | R | 2017-11-30 | 2017-11-30 | 2018-03-30 | 2018-03-30 | G | [5 empty] | 2019-01-08 | 2019-03-26 | 2019-01-08 | 2019-03-26 | R | 2019-04-08 | 2019-06-19 | 2019-07-08 | 2019-07-01 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.082453
248 | 100781 | #SGR17VB - RT. 33 Repl Bridges over NSRR (Fed 20446 & 20447) | 0033 | Primary | Bridge Replacement w/o Added Capacity | VDOT | Rockingham County | HARRISONBURG | Staunton | Harrisonburg:Rockingham County | Infrastructure Investment/Asset Management Division | Eulogio A Javier | Eulogio.Javier@VDOT.Virginia.gov | (540) 332-9105 | John-Allen L Ennis | JohnAllen.Ennis@VDOT.Virginia.gov | (540) 332-9118 |  |  |  | 0 |  | 1 | FY2023 | 19400144 | 19400143 | ACTIVITY DATES SET | R | Start Purchasing Right-of-Way milestone is 27 days past the expected completion date | G | Project is on budget | [5 empty] | 2016-07-02 | 2016-07-01 | 2016-07-02 | 2016-07-02 | G | 2015-11-02 | 2015-11-02 | 2018-11-30 | 2019-10-18 | R | [5 empty] | 2019-12-24 | 2019-12-24 | 2020-04-07 | 2020-03-26 | G | 2021-01-08 |  | 2021-01-25 |  | R | 2021-08-16 |  | 2022-10-11 |  | G | 2021-02-10 |  | 2021-10-11 |  | G | [10 empty] | 2022-10-07 |  | 2022-11-08 |  | G | 2022-12-13 |  | 2023-06-15 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.082759
249 | 104387 | #HB2.FY17 Intersection Improv - N. Franklin St/Cambria St | 0460 | Urban | Other | Locally | Christiansburg | CHRISTIANSBURG | Salem | New River Valley:Christiansburg | Infrastructure Investment Division | Anthony W Ford | Anthony.Ford@VDOT.Virginia.gov | (540) 378-5040 | Adam J Czesnowski | Adam.Czesnowski@vdot.virginia.gov | (540) 541-1216 | Wayne Nelson | wnelson@christiansburg.org | (540) 382-2349 | 1 | 2017 | 0 | FY2019 | 8489534 | 7483928 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 11 days early | G | Project is on budget | 2016-07-01 | 2016-07-01 | 2016-08-31 | 2016-09-07 | R | 2016-09-01 | 2016-07-22 | 2016-09-05 | 2016-08-25 | G | 2017-01-10 | 2017-02-28 | 2017-06-06 | 2017-06-12 | R | [5 empty] | 2017-11-17 | 2017-11-17 | 2017-12-12 | 2017-12-12 | G | 2018-05-21 | 2018-04-19 | 2018-06-04 | 2018-04-19 | G | [5 empty] | 2018-06-06 | 2018-04-20 | 2018-10-25 | 2018-10-12 | G | [10 empty] | 2019-01-03 | 2019-01-31 | 2019-02-04 | 2019-02-03 | G | 2019-02-05 | 2019-04-25 | 2019-05-21 | 2019-05-10 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.1671
250 | 115104 | #SGR20LP - SOUTH MAGNOLIA AVENUE Primary Extension Paving |  | Urban | Resurfacing | Locally | Buena Vista | LEXINGTON | Staunton | NonMPO:NonMPO | Local Assistance Division | Susan E Hammond | Susan.Hammond@VDOT.Virginia.gov | (540) 462-6990 | Michael L Branscome | Michael.Branscome@VDOT.Virginia.gov | (540) 332-2377 | City of Buena Vista | troberts@bvcity.org | (540) 261-8607 | 0 |  | 1 | FY2021 | 174761 | 174761 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 30 days early | G | Project is on budget | 2019-08-01 | 2019-08-01 | 2019-10-25 | 2019-09-16 | G | 2019-10-28 | 2019-09-17 | 2019-10-30 | 2019-10-29 | G | 2019-10-31 | 2019-10-30 | 2020-05-11 | 2020-02-28 | G | [35 empty] | 2020-06-19 | 2020-06-19 | 2020-07-31 | 2020-07-31 | G | 2020-10-21 | 2020-10-05 | 2020-12-04 | 2020-11-04 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.06207
251 | 115253 | Westover Hill Blvd (N) - Resurfacing | 0161 | Urban | Resurfacing | Locally | Richmond | ASHLAND | Richmond | Richmond:Richmond | Local Assistance Division | Brian J Lokker | Brian.Lokker@VDOT.Virginia.gov | (804) 524-6010 | Brian J Lokker | Brian.Lokker@VDOT.Virginia.gov | (804) 524-6010 | Kenny Horak | Kenneth.horak@richmondgov.com | (804) 646-4781 | 0 |  | 0 | FY2020 | 232048 | 232048 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 5 days early | G | Project is on budget | 2019-07-01 | 2019-04-06 | 2019-09-24 | 2020-01-30 | R | [5 empty] | 2019-09-25 | 2020-01-30 | 2019-11-27 | 2020-02-13 | R | [25 empty] | 2020-02-10 | 2020-03-04 | 2020-04-29 | 2020-03-04 | G | [5 empty] | 2020-05-01 | 2020-03-19 | 2020-05-01 | 2020-03-19 | G | 2020-06-30 | 2020-06-25 | 2020-06-30 | 2020-06-25 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 |  | 1 | 0 | 0.081929
252 | 115456 | #SMART20 - Int Imprv on Rtes 220/919 (Grassy Hill) | 0220 | Primary | Safety | VDOT | Franklin County | BEDFORD | Salem | NonMPO:NonMPO | Infrastructure Investment Division | Thomas W Digiulian | Thomas.DiGiulian@VDOT.Virginia.gov | (540) 387-5356 | Jesse N Weitzenfeld | Jesse.Weitzenfeld@VDOT.Virginia.gov | (540) 378-5050 |  |  |  | 1 | 2020 | 0 | FY2028 | 6958000 | 6958000 | NO DATES SET YET | G | Start Development milestone is 904 days ahead of the expected completion date | G | Project is on budget | [5 empty] | 2023-08-01 |  | 2023-08-14 |  | G | 2023-08-15 |  | 2024-07-12 |  | G | [5 empty] | 2025-05-19 |  | 2025-06-02 |  | G | 2026-09-04 |  | 2026-09-18 |  | G | 2027-02-19 |  | 2027-08-23 |  | G | 2026-10-06 |  | 2027-04-16 |  | G | 2026-02-26 |  | 2026-08-28 |  | G | [5 empty] | 2027-09-14 |  | 2027-09-14 |  | G | 2027-12-08 |  | 2027-12-08 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 1 | 0.19572
253 | 115788 | Primary Extension - Martinsville - S Memorial Blvd | 0220 | Urban | Reconstruction w/o Added Capacity | Locally | Martinsville | MARTINSVILLE | Salem | NonMPO:NonMPO | Local Assistance Division | Jessie Nester | Jessie.Nester@vdot.virginia.gov | (540) 613-4115 | Jessie Nester | Jessie.Nester@vdot.virginia.gov | (540) 613-4115 | Leon Towarnicki | LTOWARNICKI@ci.martinsville.va.us | (276) 403-5185 | 0 |  | 0 | FY2020 | 250000 | 250000 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 155 days early | G | Project is on budget | 2020-01-02 | 2019-07-02 | 2020-03-30 | 2019-09-19 | G | 2020-03-31 | 2019-09-19 | 2020-04-02 | 2019-09-19 | G | 2020-04-03 | 2019-09-26 | 2020-10-06 | 2019-10-02 | G | [35 empty] | 2019-12-31 | 2019-12-17 | 2019-12-31 | 2019-12-31 | G | 2020-01-27 | 2020-01-24 | 2020-06-30 | 2020-01-27 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.084596
254 | 115922 | HSIP HR Curve Delineation | 9999 | Miscellaneous | Safety | VDOT | Hampton Roads District-wide |  | Hampton Roads | Hampton Roads:Hampton Roads District-wide | Infrastructure Investment/Asset Management Division | Todd M Halacy | Todd.Halacy@VDOT.Virginia.gov | (757) 956-3010 | Jesse Alan Williams | Alan.Williams@vdot.virginia.gov | (757) 925-1574 |  |  |  | 0 |  | 0 | FY2023 | 1300996 | 1300996 | NO DATES SET YET-PE OPEN | G | Start Development milestone finished 17 days early | G | Project is on budget | [5 empty] | 2020-01-14 | 2020-01-14 | 2020-03-16 | 2020-02-28 | G | 2020-03-17 | 2020-03-02 | 2022-09-09 |  | G | [5 empty] | 2022-09-12 |  | 2022-09-23 |  | G | [25 empty] | 2022-10-11 |  | 2022-10-18 |  | G | 2022-10-19 |  | 2022-10-25 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | WORK/TASK ORDER | 0 | 0 | 0.077483
255 | 117154 | #SGR21LP City of Suffolk 1821 Kings Hwy | 0125 | Urban | Resurfacing | Locally | Suffolk | NORFOLK | Hampton Roads | Hampton Roads:Suffolk | Infrastructure Investment/Asset Management Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Johndel A Alcaide | John.Alcaide@vdot.virginia.gov | (757) 956-3098 | Edward Heide | eheide@suffolkva.us | (757) 514-7615 | 0 |  | 1 | FY2022 | 242572 | 242572 | NO DATES SET YET | G | Agreement with Locality milestone is 80 days ahead of the expected completion date | G | Project is on budget | 2021-01-04 |  | 2021-05-12 |  | G | 2021-05-13 |  | 2021-06-03 |  | G | 2021-07-02 |  | 2021-08-04 |  | G | [25 empty] | 2021-07-08 |  | 2021-08-04 |  | G | [5 empty] | 2021-10-01 |  | 2021-10-29 |  | G | 2022-01-26 |  | 2022-01-26 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.067885
256 | 118172 | #SGR21LP - Pulaski FKEY 1153 Lee Hwy | 0000 | Urban | Resurfacing | Locally | Pulaski | CHRISTIANSBURG | Salem | NonMPO:NonMPO | Infrastructure Investment/Asset Management Division | Adam J Czesnowski | Adam.Czesnowski@vdot.virginia.gov | (540) 541-1216 | Adam J Czesnowski | Adam.Czesnowski@vdot.virginia.gov | (540) 541-1216 | Rick Tawney | rtawney@pulaskitown.org | (540) 994-8618 | 0 |  | 1 | FY2024 | 213310 | 213310 | NO DATES SET YET | G | Agreement with Locality milestone is 50 days ahead of the expected completion date | G | Project is on budget | 2020-12-01 |  | 2021-04-12 |  | G | 2021-04-13 |  | 2021-05-03 |  | G | 2021-11-08 |  | 2022-03-09 |  | G | [25 empty] | 2023-03-06 |  | 2023-08-01 |  | G | [5 empty] | 2023-09-28 |  | 2023-10-26 |  | G | 2024-01-23 |  | 2024-01-23 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.066461
257 | 93087 | #SGR17VB - RT 195 - BR REPAIR OVER RT 76, CSX (Fed 21552) | 0195 | Interstate | Bridge Rehab w/o Added Capacity | VDOT | Richmond | ASHLAND | Richmond | Richmond:Richmond | Infrastructure Investment/Asset Management Division | Scott J Fisher | Scott.Fisher@VDOT.Virginia.gov | (804) 674-2452 | Jeremy B Cobb | Jeremy.Cobb@vdot.virginia.gov | (804) 586-2255 |  |  |  | 0 |  | 1 | FY2020 | 15700000 | 15700000 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 2 days early | G | Project is on budget | [5 empty] | 2012-11-01 | 2013-09-24 | 2013-07-26 | 2013-09-24 | R | 2017-01-19 | 2017-01-19 | 2018-03-30 | 2018-03-20 | G | [5 empty] | 2018-05-01 | 2018-05-01 | 2018-05-31 | 2018-05-31 | G | [25 empty] | 2019-03-12 | 2019-03-12 | 2019-03-12 | 2019-03-12 | G | 2019-05-23 | 2019-07-17 | 2019-07-19 | 2019-07-17 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.11427
258 | 97711 | RTE. 621 OVER IVY CREEK (STR. ID 02707) - BRIDGE REPLACEMENT | 0621 | Secondary | Bridge Replacement w/o Added Capacity | VDOT | Bedford County | BEDFORD | Salem | Lynchburg:Bedford County | Infrastructure Investment Division | Anthony T Marshall | Todd.Marshall@VDOT.Virginia.gov | (540) 387-5460 | Anthony L Handy | Tony.Handy@VDOT.Virginia.gov | (540) 352-9050 |  |  |  | 0 |  | 0 | FY2019 | 3542180 | 3805778 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 24 days early | Y | Project estimate is less than $5M and is up to 20% over budget | [5 empty] | 2010-09-01 | 2011-02-01 | 2010-10-01 | 2011-02-01 | R | 2016-04-01 | 2016-04-01 | 2017-04-24 | 2017-06-09 | R | [5 empty] | 2017-03-28 | 2017-03-28 | 2017-06-09 | 2017-06-09 | G | 2018-01-29 | 2018-01-29 | 2018-03-21 | 2018-03-21 | G | 2017-12-08 | 2017-12-08 | 2018-02-07 | 2018-12-17 | R | 2018-04-09 | 2018-04-09 | 2018-07-31 | 2018-07-25 | G | 2017-10-13 | 2017-10-13 | 2018-07-18 | 2018-07-02 | G | [5 empty] | 2018-06-07 | 2018-09-11 | 2018-07-10 | 2018-09-11 | R | 2018-08-16 | 2018-11-20 | 2018-12-14 | 2018-11-20 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.13192
259 | 102970 | CHERRY GARDENS - STORMWATER UTILITY - PHASE 2 |  | Urban | Utilities | Locally | Richmond | ASHLAND | Richmond | Richmond:Richmond | Local Assistance Division | Brian J Lokker | Brian.Lokker@VDOT.Virginia.gov | (804) 524-6010 | Brian J Lokker | Brian.Lokker@VDOT.Virginia.gov | (804) 524-6010 | CRAIG PITTMAN | craig.pittman@richmondgov.com | (804) 646-6454 | 0 |  | 0 | FY2019 | 400000 | 400000 | CONSTRUCTION COMPLETED | R | Start Delivery milestone finished 131 days late | G | Project is on budget | 2012-12-03 | 2012-12-02 | 2012-12-30 | 2012-12-02 | G | 2012-10-01 | 2012-12-20 | 2012-12-31 | 2012-12-20 | G | 2014-02-03 | 2013-12-13 | 2014-06-01 | 2013-12-27 | G | [35 empty] | 2015-05-29 | 2015-05-29 | 2015-05-29 | 2015-05-29 | G | 2017-12-01 | 2017-12-01 | 2018-08-31 | 2019-01-09 | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.15951
260 | 106053 | #HB2.FY17 Lifecore Drive Shared-Use Path |  | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Augusta County | HARRISONBURG | Staunton | SAW:Augusta County | Infrastructure Investment Division | Michael S Fulcher | Michael.Fulcher@VDOT.Virginia.gov | (540) 332-2243 | Michael S Fulcher | Michael.Fulcher@VDOT.Virginia.gov | (540) 332-2243 | Augusta County - Timmy Fitzgerald | tfitzgerald@co.augusta.va.us | (540) 248-5700 | 1 | 2017 | 0 | FY2017 | 1401503 | 1401503 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 48 days early | G | Project is on budget | [5 empty] | 2014-10-01 | 2014-09-15 | 2014-10-01 | 2014-10-01 | G | 2014-10-31 | 2014-10-31 | 2015-02-28 | 2015-02-28 | G | [10 empty] | 2016-03-31 | 2016-06-14 | 2016-03-31 | 2016-07-07 | R | [5 empty] | 2016-07-07 | 2016-07-07 | 2017-01-31 | 2017-01-31 | G | 2016-07-07 | 2015-08-28 | 2016-12-30 | 2016-05-10 | G | [5 empty] | 2017-02-14 | 2017-02-14 | 2017-02-28 | 2017-03-08 | R | 2017-05-15 | 2017-04-10 | 2017-06-15 | 2017-04-28 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.29481
261 | 108751 | RTE. 83 CURVE REALIGNMENT AND INTERSECTION IMPROVEMENT | 0083 | Primary | Reconstruction w/o Added Capacity | Locally | Buchanan County | LEBANON | Bristol | NonMPO:NonMPO | Local Assistance Division | Tabitha H Crowder | Tabitha.Crowder@vdot.virginia.gov | (276) 696-3482 | Roger L Musser | Roger.Musser@VDOT.Virginia.gov | (276) 696-3260 | Marcus Stiltner | marcus.stiltner@buchanancounty-va.gov | (276) 935-4013 | 0 |  | 0 | FY2021 | 6400000 | 6235604 | ACTIVITY DATES SET | R | Solicit Bids milestone is 38 days past the expected completion date | G | Project is on budget | 2016-06-03 | 2016-06-03 | 2017-01-12 | 2017-01-12 | G | 2017-01-17 | 2017-01-17 | 2017-01-19 | 2017-01-19 | G | 2017-01-20 | 2017-01-20 | 2019-09-10 | 2019-06-14 | G | [10 empty] | 2019-09-03 | 2019-09-03 | 2019-11-01 | 2019-11-01 | G | [5 empty] | 2019-11-06 | 2019-11-05 | 2020-04-01 | 2020-03-23 | G | [10 empty] | 2020-10-01 |  | 2021-01-14 |  | R | 2021-01-19 |  | 2021-04-30 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.13251
262 | 108888 | ROAD DIETS - IMPROVE BICYCLE ACCOMMODATIONS |  | Miscellaneous | Safety | Locally | Richmond | ASHLAND | Richmond | Richmond:Richmond | Local Assistance Division | Brian J Lokker | Brian.Lokker@VDOT.Virginia.gov | (804) 524-6010 | Brian J Lokker | Brian.Lokker@VDOT.Virginia.gov | (804) 524-6010 | Jian Xu | Jian.Xu@richmondgov.com | (804) 646-5402 | 0 |  | 0 | FY2020 | 1501500 | 1746816 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 59 days early | Y | Project estimate is less than $5M and is up to 20% over budget | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | G | 2016-11-10 | 2016-11-10 | 2016-11-10 | 2016-11-10 | G | 2016-11-14 | 2017-11-02 | 2018-08-01 | 2018-02-21 | G | [35 empty] | 2019-12-03 | 2019-07-19 | 2019-12-31 | 2019-07-23 | G | 2020-01-02 | 2019-11-07 | 2020-02-13 | 2019-12-16 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.12993
263 | 109310 | #HB2.FY17 SHOCKOE VALLEY ST IMPROVEMENT | 0360 | Urban | Safety | Locally | Richmond | ASHLAND | Richmond | Richmond:Richmond | Infrastructure Investment Division | Cynthia Crouch | Cynthia.Crouch@vdot.virginia.gov | (804) 609-5313 | Cynthia Crouch | Cynthia.Crouch@vdot.virginia.gov | (804) 609-5313 | Adel Edward | adel.edward@richmondgov.com | (804) 646-6584 | 1 | 2017 | 0 | FY2021 | 28042650 | 39250000 | ACTIVITY DATES SET | R | Start Purchasing Right-of-Way milestone is 464 days past the expected completion date | R | Project estimate is greater than $10M and is over budget by (a) 10% or more or (b) $5M or more | 2016-11-01 | 2016-08-25 | 2017-02-01 | 2017-01-18 | G | 2017-02-02 | 2017-01-18 | 2017-02-06 | 2017-01-18 | G | 2017-02-07 | 2017-01-16 | 2018-02-07 | 2018-01-05 | G | [5 empty] | 2019-11-08 |  | 2019-11-22 |  | R | 2019-10-25 |  | 2019-11-15 |  | R | [5 empty] | 2019-11-19 |  | 2020-10-13 |  | R | [10 empty] | 2020-10-30 |  | 2020-12-01 |  | R | 2020-12-02 |  | 2021-02-23 |  | Y |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.18622
264 | 111163 | MAYMONT AREA SIDEWALKS |  | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Richmond | ASHLAND | Richmond | Richmond:Richmond | Local Assistance Division | Jorg Huckabee-Mayfield | Jorg.Huckabee-Mayfield@VDOT.Virginia.gov | (804) 609-5292 | Jorg Huckabee-Mayfield | Jorg.Huckabee-Mayfield@VDOT.Virginia.gov | (804) 609-5292 | Ishoc Salaam | ishoc.salaam@richmondgov.com | (804) 646-6319 | 0 |  | 0 | FY2022 | 359334 | 359334 | ACTIVITY DATES SET | R | Determine Requirements milestone finished 692 days late | G | Project is on budget | 2017-10-02 | 2017-10-02 | 2017-12-29 | 2018-11-29 | R | 2018-01-02 | 2018-07-16 | 2018-01-04 | 2018-07-25 | R | 2018-01-05 | 2019-07-27 | 2018-07-12 | 2020-06-03 | R | [25 empty] | 2020-11-25 |  | 2021-07-12 |  | G | [5 empty] | 2021-07-27 |  | 2021-08-23 |  | G | 2021-08-24 |  | 2022-02-28 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.35208
265 | 111676 | Rte. 639 Drainage Improvements (SR) | 0639 | Secondary | Reconstruction w/o Added Capacity | VDOT | Augusta County | HARRISONBURG | Staunton | NonMPO:NonMPO | Infrastructure Investment Division | Donald F Komara | Donald.Komara@VDOT.Virginia.gov | (540) 434-2587 | Shelby T Hertzler | Shelby.Hertzler@vdot.virginia.gov | (540) 332-7799 |  |  |  | 0 |  | 0 | FY2026 | 1500000 | 1500000 | NO DATES SET YET-PE OPEN | G | Start Development milestone finished 1062 days early | G | Project is on budget | [5 empty] | 2021-10-29 | 2018-12-16 | 2021-11-12 | 2018-12-16 | G | 2021-11-15 |  | 2022-10-11 |  | G | [5 empty] | 2023-09-15 |  | 2023-09-28 |  | G | 2024-12-03 |  | 2024-12-16 |  | G | 2025-05-13 |  | 2025-11-17 |  | G | 2025-01-02 |  | 2025-07-09 |  | G | 2024-11-22 |  | 2025-07-30 |  | G | [5 empty] | 2025-12-09 |  | 2025-12-09 |  | G | 2026-02-03 |  | 2026-02-24 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | SAAP CONTRACT | 0 | 0 | 0.083304
266 | 113033 | #SGR19VB - Replace BR on RT 259 over Linville Cre(STR 15862) | 0259 | Primary | Bridge Replacement w/o Added Capacity | VDOT | Broadway | HARRISONBURG | Staunton | NonMPO:NonMPO | Infrastructure Investment/Asset Management Division | Eulogio A Javier | Eulogio.Javier@VDOT.Virginia.gov | (540) 332-9105 | Keith N Harrop | Keith.Harrop@VDOT.Virginia.gov | (540) 332-9190 |  |  |  | 0 |  | 1 | FY2025 | 6641121 | 6641121 | NO DATES SET YET-PE OPEN | Y | Determine Requirements milestone is 22 days ahead of the expected completion date and there is a risk of missing this milestone date | G | Project is on budget | [5 empty] | 2020-04-01 | 2020-04-01 | 2020-04-14 | 2020-04-14 | G | 2020-04-15 | 2020-04-15 | 2021-03-15 |  | Y | [5 empty] | 2022-02-16 |  | 2022-03-02 |  | G | 2023-05-02 |  | 2023-05-15 |  | G | 2023-10-06 |  | 2024-04-17 |  | G | 2023-05-31 |  | 2023-12-06 |  | G | 2023-04-25 |  | 2023-12-28 |  | G | [5 empty] | 2024-05-14 |  | 2024-05-14 |  | G | 2024-08-05 |  | 2024-08-05 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.07263
267 | 113198 | UNIVERSITY BLVD EXTENSION (EDMONSTON TO SUDLEY MANOR) | 0840 | Secondary | New Construction Roadway | Locally | Prince William County | MANASSAS | Northern Virginia | Northern Virginia:Prince William County | Local Assistance Division | Claudia H Llana | Claudia.Llana@VDOT.Virginia.gov | (703) 259-1768 | Jeffrey S Daily | Jeff.Daily@VDOT.Virginia.gov | (703) 259-2993 | Brittany Martin |  |  | 0 |  | 0 | FY2024 | 12847500 | 20000000 | ACTIVITY DATES SET | G | Start Purchasing Right-of-Way milestone finished on-time | R | Project estimate is greater than $10M and is over budget by (a) 10% or more or (b) $5M or more | 2018-11-05 | 2018-09-07 | 2019-04-30 | 2019-03-06 | G | 2019-02-08 | 2019-02-08 | 2019-02-22 | 2019-02-22 | G | 2019-05-01 | 2019-03-07 | 2019-11-27 | 2019-10-01 | G | [10 empty] | 2020-11-09 | 2020-11-09 | 2020-12-11 | 2020-12-11 | G | 2021-10-08 |  | 2022-10-07 |  | G | 2020-12-14 | 2020-12-14 | 2021-10-07 |  | G | [10 empty] | 2022-11-08 |  | 2023-04-11 |  | G | 2023-04-12 |  | 2023-09-08 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.37349
268 | 113613 | MILL STREET CROSSWALKS AND ADA COMPLIANT RAMPS |  | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Prince William County | MANASSAS | Northern Virginia | Northern Virginia:Prince William County | Local Assistance Division | Amir Salahshoor | A.Salahshoor@VDOT.Virginia.gov | (703) 259-1957 | Susie X Lue | Susie.Lue@vdot.virginia.gov | (703) 259-2918 | Javier Ibe |  |  | 0 |  | 0 | FY2022 | 321401 | 321401 | ACTIVITY DATES SET | G | Complete Purchasing Right-of-Way milestone finished on-time | G | Project is on budget | 2019-07-01 | 2018-08-16 | 2020-05-29 | 2018-12-27 | G | 2020-06-01 | 2019-01-09 | 2020-06-30 | 2019-05-09 | G | 2020-07-01 | 2019-05-10 | 2021-04-30 | 2020-12-14 | G | [10 empty] | 2020-12-16 | 2020-12-16 | 2020-12-16 | 2020-12-16 | G | [5 empty] | 2020-12-16 | 2020-12-16 | 2020-12-16 | 2020-12-16 | G | [10 empty] | 2021-08-02 |  | 2021-11-30 |  | G | 2021-12-01 |  | 2022-03-29 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.40858
269 | 113866 | Emergency Vehicle Preemption - Norfolk | 0000 | Urban | Traffic Management/Engineering | Locally | Norfolk | NORFOLK | Hampton Roads | Hampton Roads:Norfolk | Infrastructure Investment Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Derrick Williams | Derrick.Williams@vdot.virginia.gov | (757) 956-3097 | Christine Fuller, P. E. | christine.armstrong@norfolk.gov | (757) 664-7459 | 0 |  | 0 | FY2021 | 203988 | 203988 | ACTIVITY DATES SET | R | Solicit Bids milestone is 118 days past the expected completion date | Y | Estimate not current | 2018-10-16 | 2018-10-16 | 2019-01-14 | 2018-12-26 | G | 2019-01-15 | 2018-12-27 | 2019-01-17 | 2019-01-30 | R | 2019-01-22 | 2019-01-13 | 2019-07-25 | 2019-10-04 | R | 2019-11-18 | 2019-11-18 | 2020-01-02 | 2019-11-18 | G | [30 empty] | 2020-07-28 |  | 2020-10-26 |  | R | 2021-01-21 |  | 2021-01-27 |  | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.40484
270 | 105873 | RECONSTRUCT & PAVE NON-HARDSURFACE ROAD | 0662 | Secondary | Reconstruction w/o Added Capacity | VDOT | Tazewell County | LEBANON | Bristol | NonMPO:NonMPO | Infrastructure Investment Division | Conrad Hill | Conrad.Hill@vdot.virginia.gov | (804) 773-0170 | Chase R Buchanan | Chase.Buchanan@VDOT.Virginia.gov | (276) 696-3251 |  |  |  | 0 |  | 0 | FY2025 | 1759706 | 1753749 | ACTIVITY DATES SET | G | Determine Requirements milestone finished on-time | G | Project is on budget | [5 empty] | 2018-07-01 | 2018-06-29 | 2018-07-01 | 2018-06-29 | G | 2018-07-31 | 2018-07-31 | 2018-11-30 | 2018-11-30 | G | [35 empty] | 2025-01-21 |  | 2025-01-21 |  | G | 2025-02-04 |  | 2025-03-06 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | SAAP CONTRACT | 0 | 0 | 0.090051
271 | 106917 | #HB2.FY17 RTE 7 CORRIDOR IMPROVEMENTS - PHASE 2 | 0007 | Primary | Reconstruction w/ Added Capacity | VDOT | Fairfax County | FAIRFAX | Northern Virginia | Northern Virginia:Fairfax County | Infrastructure Investment Division | Terry Yates | Terry.Yates@vdot.virginia.gov | (703) 259-2118 | Md A Rahman | MD.Rahman@VDOT.Virginia.gov | (703) 259-1940 |  |  |  | 1 | 2017 | 0 | FY2018 | 98000000 | 98000000 | CONSTRUCTION STARTED | R | Engage Public milestone baseline missing | G | Project is on budget | 2016-11-01 | 2016-11-01 | 2017-02-28 | 2017-02-27 | G | 2016-09-23 | 2016-09-23 | 2016-09-23 | 2016-09-23 | G | 2016-09-26 | 2016-09-26 | 2017-07-13 | 2017-10-24 | R | [6 empty] | 2018-07-18 |  | 2018-11-15 | R | 2017-08-21 | 2017-11-21 | 2017-08-25 | 2017-11-21 | R | [20 empty] | 2017-08-28 | 2017-11-21 | 2017-09-06 | 2017-11-21 | R | 2018-03-21 | 2017-11-21 | 2018-04-17 | 2018-07-18 | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | DESIGN BUILD/PPTA | 1 | 1 | 0.37
272 | 108755 | CHARLOTTESVILLE / NEW ADA IMPROVEMENTS IN VARIOUS LOCATIONS | 0000 | Urban | Safety | Locally | Charlottesville | CHARLOTTESVILLE | Culpeper | Charlottesville:Charlottesville | Local Assistance Division | Ken Connors |  |  | Michael D Barnes | MichaelD.Barnes@vdot.virginia.gov | (434) 422-9861 | Tim Motsch | motscht@charlottesville.org | (434) 970-3309 | 0 |  | 0 | FY2019 | 190000 | 190000 | ACTIVITY DATES SET | R | Solicit Bids milestone is 783 days past the expected completion date | G | Project is on budget | 2017-02-15 | 2017-02-15 | 2017-05-10 | 2017-05-10 | G | 2017-08-01 | 2017-08-01 | 2017-08-03 | 2017-08-03 | G | 2017-08-04 | 2017-08-04 | 2018-07-02 | 2018-06-26 | G | [35 empty] | 2018-12-03 |  | 2018-12-31 |  | R | 2019-01-02 |  | 2019-02-13 |  | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.14388
273 | 109083 | #SMART18 - RTE 95 - ROADWAY LIGHTING | 0095 | Interstate | Safety | VDOT | Richmond | ASHLAND | Richmond | Richmond:Richmond | Infrastructure Investment Division | Lawrence Ramsey | Brian.Ramsey@VDOT.Virginia.gov | (804) 585-3579 | Lawrence Ramsey | Brian.Ramsey@VDOT.Virginia.gov | (804) 585-3579 |  |  |  | 1 | 2018 | 0 | FY2020 | 7199224 | 5262974 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 77 days early | G | Project is on budget | [5 empty] | 2017-07-03 | 2017-06-26 | 2017-07-17 | 2017-07-07 | G | 2017-07-18 | 2017-07-10 | 2018-02-12 | 2018-02-02 | G | [5 empty] | 2018-09-07 | 2018-03-08 | 2018-09-20 | 2018-03-21 | G | [15 empty] | 2017-08-09 | 2017-08-09 | 2017-09-20 | 2017-08-09 | G | [5 empty] | 2019-05-14 | 2019-05-07 | 2019-05-14 | 2019-05-07 | G | 2019-07-29 | 2019-07-29 | 2019-10-14 | 2019-07-29 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.073385
274 | 109587 | #SMART20 - ROUTE 29/662 RCUT AT SHELBY HSIP | 0029 | Primary | Safety | VDOT | Madison County | CHARLOTTESVILLE | Culpeper | NonMPO:NonMPO | Infrastructure Investment Division | Gregory J Cooley | Gregory.Cooley@vdot.virginia.gov | (434) 906-7979 | Justin Warfield | Justin.Warfield@vdot.virginia.gov | (540) 829-7599 |  |  |  | 1 | 2020 | 0 | FY2023 | 4750000 | 4750000 | NO DATES SET YET-PE OPEN | R | Determine Requirements milestone is 264 days past the expected completion date | G | Project is on budget | [5 empty] | 2016-11-01 | 2016-11-01 | 2016-11-01 | 2016-11-01 | G | 2016-11-28 | 2016-11-28 | 2020-06-02 |  | R | [5 empty] | 2021-01-04 |  | 2021-01-19 |  | R | 2021-11-18 |  | 2021-12-03 |  | G | 2022-05-02 |  | 2022-11-03 |  | G | 2021-12-21 |  | 2022-06-28 |  | G | 2021-07-13 |  | 2022-07-13 |  | G | [5 empty] | 2022-11-08 |  | 2022-11-08 |  | G | 2023-01-04 |  | 2023-03-10 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.15422
275 | 111278 | INSTALL SCOUR PROTECTION TO BRIDGES IN THE RICHMOND DISTRICT | 9999 | Miscellaneous | Bridge Rehab w/o Added Capacity | VDOT | Richmond District-wide |  | Richmond | NonMPO:NonMPO | Infrastructure Investment Division | Roy Soto | Roy.Soto@vdot.virginia.gov | (804) 609-5239 | Roy Soto | Roy.Soto@vdot.virginia.gov | (804) 609-5239 |  |  |  | 0 |  | 0 | FY2023 | 1900000 | 1759618 | ACTIVITY DATES SET | G | Obtained Permits milestone finished 420 days early | G | Project is on budget | [5 empty] | 2017-09-04 | 2017-09-04 | 2017-09-14 | 2017-09-14 | G | 2017-10-26 | 2017-10-26 | 2018-12-05 | 2019-11-26 | R | [5 empty] | 2020-08-28 | 2020-08-18 | 2020-09-11 | 2020-09-09 | G | 2021-08-04 | 2020-09-09 | 2021-08-17 | 2020-09-09 | G | 2022-04-12 | 2020-09-09 | 2022-04-12 | 2020-09-09 | G | 2021-09-01 | 2020-09-09 | 2022-03-15 | 2020-09-09 | G | 2021-05-10 | 2019-09-10 | 2022-01-13 | 2020-11-19 | G | [5 empty] | 2022-06-14 |  | 2022-06-14 |  | G | 2022-11-16 |  | 2022-11-16 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.15896
276 | 111746 | Route 23 and 671 Wise Co. - Dual Actuated Beacons | 0023 | Primary | Safety | VDOT | Wise County | WISE | Bristol | NonMPO:NonMPO | Infrastructure Investment Division | Robert T Ratliff | Robert.Ratliff@VDOT.Virginia.gov | (276) 696-3262 | Robert T Ratliff | Robert.Ratliff@VDOT.Virginia.gov | (276) 696-3262 |  |  |  | 0 |  | 0 | FY2019 | 186000 | 186000 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished on-time | G | Project is on budget | [10 empty] | 2018-06-15 | 2018-06-21 | 2018-06-21 | 2018-08-06 | R | [35 empty] | 2019-01-08 | 2019-01-08 | 2019-01-08 | 2019-01-08 | G | 2019-04-15 | 2019-04-15 | 2019-06-10 | 2019-06-10 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | WORK/TASK ORDER | 1 | 0 | 0.065787
277 | 113116 | #SMART20 RTE 221/501 - INTERSECTION IMPROVEMENT (SPLIT PAIR) | 0221 | Urban | Reconstruction w/ Added Capacity | Locally | Lynchburg | APPOMATTOX | Lynchburg | Lynchburg:Lynchburg | Local Assistance Division | Gregg Allen | Gregg.Allen@vdot.virginia.gov | (434) 426-5575 | Jay S Brown | Jay.Brown@VDOT.Virginia.gov | (434) 856-8246 | Lee Newland, P.E. | lee.newland@lynchburgva.gov | (434) 455-3947 | 1 | 2020 | 0 | FY2028 | 38538037 | 38538037 | NO DATES SET YET-PE OPEN | G | Start Development milestone finished 1488 days early | G | Project is on budget | 2024-01-31 | 2019-08-12 | 2024-04-24 | 2019-11-06 | G | 2024-04-25 | 2019-11-07 | 2024-04-29 | 2020-04-02 | G | 2024-04-30 | 2020-04-03 | 2025-04-30 |  | G | [10 empty] | 2026-05-13 |  | 2026-06-03 |  | G | [5 empty] | 2026-06-05 |  | 2027-03-19 |  | G | 2024-12-12 |  | 2025-08-15 |  | G | [5 empty] | 2027-04-06 |  | 2027-05-03 |  | G | 2027-07-22 |  | 2027-07-22 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.21797
278 | 113371 | REPLACE SUPERSTRUCTURE RTE 60 | 0060 | Primary | Bridge Rehab w/o Added Capacity | VDOT | New Kent County | ASHLAND | Richmond | Richmond:New Kent County | Infrastructure Investment Division | Thomas Kendrick | Thomas.Kendrick@vdot.virginia.gov | (804) 609-5281 | Thomas Kendrick | Thomas.Kendrick@vdot.virginia.gov | (804) 609-5281 |  |  |  | 0 |  | 0 | FY2025 | 2850000 | 2850000 | NO DATES SET YET-PE OPEN | G | Start Development milestone finished 587 days early | G | Project is on budget | [5 empty] | 2020-09-01 | 2019-01-29 | 2020-09-15 | 2019-02-06 | G | 2020-09-16 | 2019-02-07 | 2021-08-13 |  | G | [5 empty] | 2022-07-20 |  | 2022-08-02 |  | G | 2023-10-03 |  | 2023-10-17 |  | G | 2024-03-18 |  | 2024-09-18 |  | G | 2023-11-01 |  | 2024-05-10 |  | G | 2023-09-26 |  | 2024-06-03 |  | G | [5 empty] | 2024-10-08 |  | 2024-10-08 |  | G | 2025-01-03 |  | 2025-01-03 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.17856
279 | 113752 | Inst. Emer. Vehicle Preemption Software & Hardware - Hampton | 0064 | Urban | Traffic Management/Engineering | Locally | Hampton | WILLIAMSBURG | Hampton Roads | Hampton Roads:Hampton | Infrastructure Investment Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Derrick Williams | Derrick.Williams@vdot.virginia.gov | (757) 956-3097 | Sandon Rogers, P.E. | sandon.rogers@hampton.gov | (757) 727-6786 | 0 |  | 0 | FY2021 | 203988 | 189792 | ADVERTISED | R | Solicit Bids milestone finished 29 days late | G | Project is on budget | 2018-10-01 | 2018-10-01 | 2018-12-28 | 2019-06-28 | R | 2018-12-31 | 2019-07-01 | 2019-01-03 | 2019-07-11 | R | 2019-01-04 | 2019-07-12 | 2019-07-11 | 2020-07-09 | R | [35 empty] | 2020-11-30 | 2020-11-30 | 2020-12-28 | 2021-01-26 | R | 2021-03-22 |  | 2021-03-22 |  | Y |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.30013
281 | 115421 | Suffolk Transit Operations Facility | 0000 | Urban | Transit | Locally | Suffolk | NORFOLK | Hampton Roads | Hampton Roads:Suffolk | Infrastructure Investment Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Johndel A Alcaide | John.Alcaide@vdot.virginia.gov | (757) 956-3098 | LJ Hansen | lhansen@suffolkva.us | (757) 514-7687 | 0 |  | 0 | FY2025 | 1890066 | 1890066 | NO DATES SET YET | G | Determine Requirements milestone is 1328 days ahead of the expected completion date | Y | Estimate not current | 2024-09-30 |  | 2024-12-27 |  | G | [5 empty] | 2024-09-30 |  | 2024-10-11 |  | G | [25 empty] | 2024-10-14 |  | 2025-01-13 |  | G | [5 empty] | 2025-01-15 |  | 2025-02-13 |  | G | 2025-05-05 |  | 2025-05-05 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.14895
282 | 115669 | #SMART20 - SOUTH ELDEN STREET CORRIDOR IMPROVEMENTS | 9999 | Urban | Reconstruction w/o Added Capacity | VDOT | Herndon | FAIRFAX | Northern Virginia | Northern Virginia:Herndon | Infrastructure Investment Division | Andrew G Beacher | Andrew.Beacher@vdot.virginia.gov | (703) 259-2239 | Hamid R Misaghian | H.Misaghian@VDOT.Virginia.gov | (703) 259-1795 |  |  |  | 1 | 2020 | 0 | FY2029 | 16000000 | 16000399 | NO DATES SET YET | G | Agreement with Locality milestone is 1348 days ahead of the expected completion date | Y | Project estimate is greater than $10M and is over budget by (a) up to 10% or (b) up to $5M | 2024-07-01 |  | 2024-10-31 |  | G | 2024-11-01 |  | 2024-12-03 |  | G | 2024-12-04 |  | 2026-01-14 |  | G | [5 empty] | 2026-10-28 |  | 2026-11-10 |  | G | 2028-02-07 |  | 2028-02-18 |  | G | 2028-06-15 |  | 2028-12-21 |  | G | 2028-03-08 |  | 2028-09-08 |  | G | 2027-07-27 |  | 2028-04-03 |  | G | [5 empty] | 2029-01-09 |  | 2029-01-09 |  | G | 2029-05-01 |  | 2029-05-01 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.18671
283 | 116605 | NOVA SYSTEMIC HIGH VISIBILITY BACKPLATES PH1A | 9999 | Primary | Safety | VDOT | Northern Virginia District-wide |  | Northern Virginia | Northern Virginia:Northern Virginia District-wide | Infrastructure Investment/Asset Management Division | Waqar A Siddiqui | Sid.Siddiqui@VDOT.Virginia.gov | (703) 259-3225 | Tienjung Ho | Tien-Jung.Ho@VDOT.Virginia.gov | (703) 259-2752 |  |  |  | 0 |  | 0 | FY2020 | 600000 | 600000 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 63 days early | G | Project is on budget | [5 empty] | 2019-10-23 | 2019-10-23 | 2020-02-14 | 2020-02-14 | G | 2020-02-18 | 2020-02-18 | 2020-03-30 | 2020-02-26 | G | [5 empty] | 2020-02-25 | 2020-02-25 | 2020-02-26 | 2020-02-26 | G | [25 empty] | 2020-05-21 | 2020-04-07 | 2020-06-04 | 2020-04-07 | G | 2020-06-05 | 2020-04-08 | 2020-06-11 | 2020-04-09 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | WORK/TASK ORDER | 1 | 0 | 0.070199
284 | 117031 | RECONSTRUCTION - STAFFORD AVENUE | 3953 | Urban | Resurfacing | Locally | Fredericksburg | FREDERICKSBURG | Fredericksburg | Fredericksburg:Fredericksburg | Local Assistance Division | Catherine C Coffey | Catherine.Coffey@vdot.virginia.gov | (540) 899-4280 | Richard A Spurlock | Richard.Spurlock@VDOT.Virginia.gov | (540) 899-4302 | Erik Nelson | enelson@fredericksburgva.gov | (540) 937-0572 | 0 |  | 0 | FY2028 | 600000 | 600000 | NO DATES SET YET | G | Agreement with Locality milestone is 1461 days ahead of the expected completion date | G | Project is on budget | 2024-10-08 |  | 2025-02-21 |  | G | 2025-02-24 |  | 2025-03-14 |  | G | 2025-09-18 |  | 2026-01-15 |  | G | [25 empty] | 2027-01-12 |  | 2027-06-11 |  | G | [5 empty] | 2027-08-10 |  | 2027-09-07 |  | G | 2027-11-30 |  | 2027-11-30 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.10369
285 | 117349 | HSIP Hampton Roads Unsignalized Intersections | 9999 | Secondary | Safety | VDOT | Hampton Roads District-wide |  | Hampton Roads | Hampton Roads:Hampton Roads District-wide | Infrastructure Investment/Asset Management Division | Mark T Grass | Mark.Grass@VDOT.Virginia.gov | (757) 956-3165 | Jay Mohney | Jay.Mohney@vdot.virginia.gov | (757) 956-3168 |  |  |  | 0 |  | 0 | FY2021 | 250000 | 250000 | NO DATES SET YET-PE OPEN | G | Start Development milestone finished 55 days early | G | Project is on budget | [5 empty] | 2021-01-04 | 2020-11-18 | 2021-01-26 | 2020-12-02 | G | 2021-01-27 | 2020-12-03 | 2021-05-05 |  | G | [5 empty] | 2021-05-18 |  | 2021-06-01 |  | G | [25 empty] | 2021-06-17 |  | 2021-06-23 |  | G | 2021-06-24 |  | 2021-06-30 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | WORK/TASK ORDER | 0 | 0 | 0.098382
286 | 117954 | #81CIP DETOUR SIGNAL UPGRADES FOR VDOT MAINTAINED SIGNAL | 9999 | Miscellaneous | Traffic Management/Engineering | VDOT | Bristol District-wide |  | Bristol | Bristol:Bristol District-wide | Infrastructure Investment Division | Brian Holt | Brian.Holt@vdot.virginia.gov | (276) 696-3414 | Jeremy J Mullins | Jeremy.Mullins@vdot.virginia.gov | (276) 696-3259 |  |  |  | 0 |  | 0 | FY2024 | 982334 | 982334 | NO DATES SET YET-PE OPEN | G | Obtained Permits milestone finished 748 days early | G | Project is on budget | [5 empty] | 2020-10-01 | 2020-10-01 | 2020-10-22 | 2020-10-22 | G | 2020-10-23 | 2020-10-23 | 2021-08-26 |  | G | [5 empty] | 2022-04-01 |  | 2022-04-28 |  | G | [5 empty] | 2022-12-21 |  | 2023-04-25 |  | G | [5 empty] | 2022-09-08 | 2021-01-26 | 2023-02-13 | 2021-01-26 | G | [5 empty] | 2023-05-09 |  | 2023-05-09 |  | G | 2023-07-28 |  | 2023-07-28 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | REGIONAL ON-CALL CONTRACT | 0 | 0 | 0.11963
287 | 94726 | RTE. 221 OVER MARTINS CREEK (STR. 14945) - BRIDGE REPLACEMEN | 0221 | Primary | Bridge Replacement w/o Added Capacity | VDOT | Roanoke County | SALEM | Salem | Roanoke:Roanoke County | Infrastructure Investment Division | Anthony T Marshall | Todd.Marshall@VDOT.Virginia.gov | (540) 387-5460 | Jeffrey A Echols | Jeff.Echols@VDOT.Virginia.gov | (540) 375-3595 |  |  |  | 0 |  | 0 | FY2021 | 3647913 | 3635790 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 337 days early | G | Project is on budget | [5 empty] | 2010-03-22 | 2010-05-27 | 2010-04-30 | 2010-05-27 | R | 2015-11-02 | 2015-11-02 | 2017-09-15 | 2017-09-15 | G | [5 empty] | 2017-02-15 | 2017-02-15 | 2017-02-15 | 2017-02-15 | G | 2018-07-30 | 2018-05-24 | 2018-08-17 | 2018-05-29 | G | 2019-05-29 | 2019-03-20 | 2020-11-09 | 2020-07-08 | G | 2018-08-23 | 2018-06-25 | 2020-11-09 | 2019-03-20 | G | 2018-03-09 | 2019-10-09 | 2020-11-09 | 2020-01-06 | G | [5 empty] | 2020-10-16 | 2020-02-11 | 2020-11-10 | 2020-02-11 | G | 2020-12-01 | 2020-05-07 | 2021-04-09 | 2020-05-07 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.089196
288 | 104241 | Construction Sidewalk West Side of Giles Road |  | Urban | Other | Locally | Blacksburg | CHRISTIANSBURG | Salem | New River Valley:Blacksburg | Local Assistance Division | Anthony W Ford | Anthony.Ford@VDOT.Virginia.gov | (540) 378-5040 | Adam J Czesnowski | Adam.Czesnowski@vdot.virginia.gov | (540) 541-1216 | Randy Formica | rformica@blacksburg.gov | (540) 443-1300 | 0 |  | 0 | FY2019 | 823894 | 823894 | CONSTRUCTION STARTED | R | Start Delivery milestone finished 494 days late | G | Project is on budget | [5 empty] | 2013-08-01 | 2014-07-09 | 2013-08-01 | 2014-07-11 | R | 2013-09-03 | 2014-07-12 | 2013-12-31 | 2017-01-18 | R | [35 empty] | 2018-02-06 | 2020-01-06 | 2018-02-06 | 2020-02-04 | R | 2018-06-06 | 2020-02-05 | 2018-12-06 | 2020-04-13 | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.23126
289 | 106437 | RT. 616 FLEETWOOD RD. RECONSTR. AND PAVE GRAVEL RD. | 0616 | Secondary | Restoration and Rehabilitation | VDOT | Loudoun County | LEESBURG | Northern Virginia | Northern Virginia:Loudoun County | Infrastructure Investment Division | James Zeller |  |  | Michael D Gleasman | Michael.Gleasman@VDOT.Virginia.gov | (703) 259-1944 | Terrie Laycock, Loudoun County Dept. of Transportation & Capital Infrastructure | terrie.laycock@loudoun.gov | (703) 777-0553 | 0 |  | 0 | FY2028 | 1220000 | 1220000 | WAITING FINANCIAL CLOSURE | G | Solicit Bids milestone finished 336 days early | G | Project is on budget | [5 empty] | 2015-08-03 | 2015-04-28 | 2015-08-03 | 2015-04-28 | G | 2020-10-11 | 2013-09-25 | 2021-02-11 | 2013-11-13 | G | [35 empty] | 2016-08-10 | 2015-09-09 | 2016-08-10 | 2015-09-09 | G | 2027-09-24 | 2015-08-28 | 2027-10-24 | 2015-08-28 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | WORK/TASK ORDER | 1 | 0 | 0.18103
291 | 115358 | #SGR20LP - City of Chesapeake Cedar Rd, Segment 1 | 0165 | Urban | Restoration and Rehabilitation | Locally | Chesapeake | NORFOLK | Hampton Roads | Hampton Roads:Chesapeake | Infrastructure Investment/Asset Management Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Johndel A Alcaide | John.Alcaide@vdot.virginia.gov | (757) 956-3098 | Sam Sawan | ssawan@cityofchesapeake.net | (757) 382-8263 | 0 |  | 1 | FY2020 | 272280 | 272280 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 33 days early | G | Project is on budget | 2019-10-01 | 2019-07-01 | 2019-12-30 | 2019-09-24 | G | [5 empty] | 2019-10-01 | 2019-10-01 | 2019-10-14 | 2019-10-14 | G | [35 empty] | 2020-05-18 | 2020-04-21 | 2020-06-15 | 2020-05-15 | G | 2020-06-30 | 2020-05-28 | 2020-06-30 | 2020-05-28 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.094485
292 | 115495 | #SMART20 RTE 58 WBL - CONSTRUCT THIRD LANE | 0058 | Primary | Reconstruction w/ Added Capacity | Locally | Danville | HALIFAX | Lynchburg | Danville:Danville | Infrastructure Investment Division | Gregg Allen | Gregg.Allen@vdot.virginia.gov | (434) 426-5575 | Gregg Allen | Gregg.Allen@vdot.virginia.gov | (434) 426-5575 | Brian Dunevant | dunevbl@danvilleva.gov | (434) 799-5019 | 1 | 2020 | 0 | FY2027 | 3453896 | 3453896 | NO DATES SET YET | G | Agreement with Locality milestone is 1158 days ahead of the expected completion date | G | Project is on budget | 2024-01-31 |  | 2024-04-24 |  | G | 2024-04-25 |  | 2024-04-29 |  | G | 2024-04-30 |  | 2024-11-01 |  | G | [10 empty] | 2025-11-05 |  | 2025-11-26 |  | G | [5 empty] | 2025-12-02 |  | 2026-09-10 |  | G | 2024-12-12 |  | 2025-08-15 |  | G | [5 empty] | 2026-09-28 |  | 2026-10-26 |  | G | 2027-01-21 |  | 2027-01-21 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.099901
293 | 116589 | DISTRICT-WIDE SYSTEMIC RUMBLE STRIPS (FY20 THRU FY22) | 9999 | Primary | Safety | VDOT | Fredericksburg District-wide |  | Fredericksburg | Fredericksburg:Fredericksburg District-wide | Infrastructure Investment Division | Jessica Graves | Jessica.Graves@vdot.virginia.gov | (540) 899-4267 | Jessica Graves | Jessica.Graves@vdot.virginia.gov | (540) 899-4267 |  |  |  | 0 |  | 0 | FY2021 | 1666308 | 1652187 | ACTIVITY DATES SET | G | Engage Public milestone finished 221 days early | G | Project is on budget | [5 empty] | 2020-03-09 | 2020-01-27 | 2020-03-09 | 2020-03-02 | G | 2020-03-10 | 2020-03-03 | 2020-06-16 | 2020-06-12 | G | [5 empty] | 2021-04-06 | 2020-09-10 | 2021-04-19 | 2020-09-10 | G | [25 empty] | 2021-05-05 |  | 2021-05-11 |  | G | 2021-05-12 |  | 2021-05-18 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | REGIONAL ON-CALL CONTRACT | 0 | 0 | 0.068057
294 | 116966 | #SGR21LP ROUTE 340 PRIMARY EXTENSION PAVING |  | Primary | Resurfacing | VDOT | Luray | HARRISONBURG | Staunton | NonMPO:NonMPO | Infrastructure Investment Division | Joel D Denunzio | Joel.DeNunzio@VDOT.virginia.gov | (540) 332-9093 | Mark W Hisey | Mark.Hisey@VDOT.Virginia.gov | (540) 280-4820 |  |  |  | 0 |  | 1 | FY2021 | 90888 | 90888 | ACTIVITY DATES SET | Y | Solicit Bids milestone is 51 days ahead of the expected completion date and there is a risk of missing this milestone date | G | Project is on budget | [5 empty] | 2021-01-11 | 2020-11-03 | 2021-02-02 | 2020-11-24 | G | 2021-02-03 | 2020-11-25 | 2021-12-03 | 2021-01-11 | G | [5 empty] | 2021-01-12 | 2021-01-12 | 2021-01-12 | 2021-01-12 | G | [5 empty] | 2020-12-28 | 2021-01-14 | 2021-04-12 | 2021-01-19 | G | [15 empty] | 2021-04-13 |  | 2021-04-13 |  | Y | 2021-06-30 |  | 2021-06-30 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.060492
295 | 117147 | #SGR21LP 114-City of Hampton 376 Cunningham Drive | 0152 | Urban | Resurfacing | Locally | Hampton | WILLIAMSBURG | Hampton Roads | Hampton Roads:Hampton | Infrastructure Investment/Asset Management Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Derrick Williams | Derrick.Williams@vdot.virginia.gov | (757) 956-3097 | Sandon S. Rogers, P.E., LS | Sandon.rogers@hampton.gov | (757) 727-6786 | 0 |  | 1 | FY2022 | 166000 | 166000 | NO DATES SET YET | G | Agreement with Locality milestone is 81 days ahead of the expected completion date | G | Project is on budget | 2021-01-05 |  | 2021-05-13 |  | G | 2021-05-14 |  | 2021-06-04 |  | G | 2021-07-06 |  | 2021-08-02 |  | G | [25 empty] | 2021-07-06 |  | 2021-08-02 |  | G | [5 empty] | 2021-09-29 |  | 2021-10-27 |  | G | 2022-01-24 |  | 2022-01-24 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.096181
296 | 117832 | #SGR21VP PM-9A-21 INTERSTATE PLANT MIX | 9999 | Interstate | Resurfacing | VDOT | Fairfax County | FAIRFAX | Northern Virginia | Northern Virginia:Fairfax County | Infrastructure Investment/Asset Management Division | Todd L Robson | Todd.Robson@VDOT.Virginia.gov | (703) 259-1992 | Harihar Shiwakoti | Harihar.Shiwakoti@vdot.virginia.gov | (703) 259-2292 |  |  |  | 0 |  | 1 | FY2021 | 2045477 | 2045477 | ADVERTISED | G | Solicit Bids milestone finished 97 days early | G | Project is on budget | [10 empty] | 2020-07-28 | 2020-07-28 | 2020-08-03 | 2020-10-22 | R | [35 empty] | 2021-03-23 | 2020-12-15 | 2021-03-23 | 2020-12-16 | G | 2021-06-30 |  | 2021-06-30 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.070802
297 | 118292 | LEELAND ROAD WIDENING | 0626 | Secondary | Reconstruction w/ Added Capacity | VDOT | Stafford County | FREDERICKSBURG | Fredericksburg | Fredericksburg:Stafford County | Local Assistance Division | Curtis B Holloway | Curtis.Holloway@vdot.virginia.gov | (540) 374-3367 | Curtis B Holloway | Curtis.Holloway@vdot.virginia.gov | (540) 374-3367 |  |  |  | 0 |  | 0 | FY2028 | 7007000 | 7007000 | NO DATES SET YET | G | Start Development milestone is 1277 days ahead of the expected completion date | G | Project is on budget | [5 empty] | 2024-08-01 |  | 2024-08-21 |  | G | 2024-08-22 |  | 2025-06-26 |  | G | [5 empty] | 2026-01-30 |  | 2026-02-27 |  | G | 2026-10-15 |  | 2026-11-20 |  | G | 2027-04-27 |  | 2027-08-25 |  | G | 2026-12-09 |  | 2027-05-11 |  | G | 2027-01-21 |  | 2027-06-18 |  | G | [5 empty] | 2027-09-14 |  | 2027-09-14 |  | G | 2027-12-07 |  | 2027-12-07 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.13603
298 | 97709 | RTE. 636 OVER S FORK ROANOKE RIVER (STR 12246) - BRG. REPL. | 0636 | Secondary | Bridge Replacement w/o Added Capacity | VDOT | Montgomery County | CHRISTIANSBURG | Salem | NonMPO:NonMPO | Infrastructure Investment Division | Anthony T Marshall | Todd.Marshall@VDOT.Virginia.gov | (540) 387-5460 | Leslie T Repass | Todd.Repass@VDOT.Virginia.gov | (540) 381-7195 |  |  |  | 0 |  | 0 | FY2021 | 3489534 | 2849708 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 102 days early | G | Project is on budget | [5 empty] | 2012-10-01 | 2011-02-01 | 2012-11-01 | 2011-02-01 | G | 2014-12-01 | 2014-10-30 | 2018-03-30 | 2018-03-21 | G | [5 empty] | 2018-03-21 | 2018-03-21 | 2018-03-21 | 2018-03-21 | G | 2018-12-03 | 2018-06-12 | 2019-01-02 | 2018-06-12 | G | [5 empty] | 2019-02-01 | 2018-07-17 | 2019-07-31 | 2018-11-14 | G | 2018-11-28 | 2018-11-02 | 2020-03-09 | 2019-11-26 | G | [5 empty] | 2020-02-11 | 2020-01-07 | 2020-03-10 | 2020-01-28 | G | 2020-04-23 | 2020-03-30 | 2020-07-10 | 2020-03-30 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.062004
299 | 104886 | RTE 360 -(at Spring Run Rd) INTERSECTION IMPROVEMENTS | 0360 | Primary | Reconstruction w/o Added Capacity | Locally | Chesterfield County | CHESTERFIELD | Richmond | Richmond:Chesterfield County | Infrastructure Investment Division | Brian J Lokker | Brian.Lokker@VDOT.Virginia.gov | (804) 524-6010 | Brian J Lokker | Brian.Lokker@VDOT.Virginia.gov | (804) 524-6010 | Barb Smith | SmithBK@chesterfield.gov | (804) 748-1037 | 0 |  | 0 | FY2020 | 2191000 | 3143754 | AWARDED | G | Start Delivery milestone finished 3 days early | R | Project estimate is less than $5M and is 20% or more over budget | 2017-11-13 | 2017-11-13 | 2017-11-13 | 2017-11-13 | G | 2017-11-29 | 2017-11-29 | 2017-11-29 | 2017-11-29 | G | 2018-03-01 | 2018-03-01 | 2018-11-30 | 2018-12-19 | R | [5 empty] | 2019-01-31 | 2019-01-02 | 2019-01-31 | 2019-01-04 | G | 2019-04-01 | 2019-03-19 | 2019-04-01 | 2019-03-25 | G | [5 empty] | 2019-04-24 | 2019-04-04 | 2019-07-29 | 2019-11-19 | R | [10 empty] | 2019-12-31 | 2020-03-31 | 2019-12-31 | 2020-03-31 | R | 2020-04-13 | 2020-05-13 | 2020-06-01 | 2020-05-29 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.14667
300 | 107265 | Nansemond Pkwy/Bennetts Pasture Rd Intersection Improvements | 0337 | Urban | Reconstruction w/ Added Capacity | Locally | Suffolk | NORFOLK | Hampton Roads | Hampton Roads:Suffolk | Local Assistance Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Johndel A Alcaide | John.Alcaide@vdot.virginia.gov | (757) 956-3098 | Sandon Rogers | srogers@suffolkva.us | (757) 514-7683 | 0 |  | 0 | FY2022 | 11075000 | 11075000 | ACTIVITY DATES SET | R | Start Purchasing Right-of-Way milestone is 236 days past the expected completion date | G | Project is on budget | 2015-08-14 | 2015-08-14 | 2015-08-14 | 2015-08-14 | G | 2015-08-17 | 2015-08-17 | 2015-08-20 | 2015-08-20 | G | 2015-08-21 | 2015-08-21 | 2019-08-27 | 2019-12-09 | R | [10 empty] | 2020-06-17 |  | 2020-06-30 |  | R | [20 empty] | 2021-07-22 |  | 2021-11-15 |  | G | 2021-11-16 |  | 2022-02-04 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.17365
302 | 108628 | Mecklenburg Ave. Intersection Improvement | 0001 | Urban | Safety | Locally | South Hill | SOUTH HILL | Richmond | NonMPO:NonMPO | Local Assistance Division | James Shepherd | James.Shepherd@vdot.virginia.gov | (804) 609-5305 | Brian J Lokker | Brian.Lokker@VDOT.Virginia.gov | (804) 524-6010 | Allen Elliott | aelliott@southhillva.org | (434) 917-9463 | 0 |  | 0 | FY2019 | 2394140 | 2394140 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 13 days early | G | Project is on budget | 2017-06-08 | 2016-09-09 | 2017-08-31 | 2016-09-09 | G | 2017-09-01 | 2016-09-21 | 2017-09-06 | 2016-09-21 | G | 2017-09-07 | 2017-06-01 | 2018-03-20 | 2017-09-13 | G | [10 empty] | 2018-06-22 | 2018-06-22 | 2018-07-23 | 2018-07-23 | G | [5 empty] | 2018-07-25 | 2018-07-25 | 2018-09-14 | 2018-09-05 | G | [10 empty] | 2018-10-04 | 2018-10-04 | 2018-10-26 | 2018-10-17 | G | 2018-10-29 | 2018-10-18 | 2019-03-13 | 2019-02-28 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.11193
303 | 108852 | Huffman Lane Reconstruction - PE only | 0761 | Secondary | Reconstruction w/o Added Capacity | Locally | Roanoke County | SALEM | Salem | Roanoke:Roanoke County | Local Assistance Division | Cheryl B Becker | Cheryl.Becker@vdot.virginia.gov | (540) 492-2531 | Cheryl B Becker | Cheryl.Becker@vdot.virginia.gov | (540) 492-2531 | David Holladay |  |  | 0 |  | 0 | FY2019 | 40000 | 40000 | AWARDED | G | Start Delivery milestone finished 330 days early | G | Project is on budget | 2016-07-01 | 2016-08-12 | 2016-09-26 | 2016-09-09 | G | 2016-09-27 | 2017-02-13 | 2016-09-29 | 2017-02-15 | R | 2016-09-30 | 2016-12-02 | 2017-04-12 | 2017-04-12 | G | [35 empty] | 2018-02-23 | 2018-02-07 | 2018-03-22 | 2018-02-07 | G | 2018-08-09 | 2018-02-06 | 2019-01-04 | 2018-02-08 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.16378
304 | 109469 | #HB2.FY17 OLD CAMERON RUN TRAIL | 9999 | Urban | Facilities for Pedestrians and Bicycles | Locally | Alexandria | FAIRFAX | Northern Virginia | Northern Virginia:Alexandria | Infrastructure Investment Division | Amir Salahshoor | A.Salahshoor@VDOT.Virginia.gov | (703) 259-1957 | Robert J Strevell | Robert.Strevell@vdot.virginia.gov | (703) 259-1988 | Daphne Knott | Daphne.Kott@alexandriava.gov | (703) 746-4055 | 1 | 2017 | 0 | FY2020 | 7546209 | 7546209 | NO DATES SET YET-PE OPEN | R | Determine Requirements milestone is 1272 days past the expected completion date | G | Project is on budget | 2016-07-01 | 2016-07-14 | 2017-01-17 | 2016-11-18 | G | 2017-01-17 | 2016-07-14 | 2017-01-17 | 2016-09-09 | G | 2017-01-18 | 2016-11-21 | 2017-08-29 |  | R | [10 empty] | 2018-12-06 |  | 2018-12-27 |  | R | [5 empty] | 2018-12-31 |  | 2019-10-08 |  | R | [10 empty] | 2019-10-25 |  | 2019-11-22 |  | R | 2019-11-25 |  | 2020-01-08 |  | R | Delay due to changes in scope of work, project management, plan designs, or resolution of public comments | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.24108
305 | 109687 | Hampton Flashing Yellow Arrow Improvements | 0000 | Urban | Traffic Management/Engineering | Locally | Hampton | WILLIAMSBURG | Hampton Roads | Hampton Roads:Hampton | Infrastructure Investment Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Joshua D Negovan | Joshua.Negovan@vdot.virginia.gov | (757) 956-3347 | Sandon Rogers, P.E. | sandon.rogers@hampton.gov | (757) 727-6786 | 0 |  | 0 | FY2020 | 392000 | 357850 | CONSTRUCTION STARTED | R | Start Delivery milestone finished 125 days late | G | Project is on budget | 2016-07-01 | 2016-07-01 | 2016-12-02 | 2016-12-02 | G | 2016-09-14 | 2016-09-14 | 2016-09-14 | 2016-09-14 | G | 2016-09-15 | 2016-09-15 | 2017-12-07 | 2018-11-14 | R | [35 empty] | 2019-02-28 | 2019-02-28 | 2019-05-01 | 2019-08-14 | R | 2019-05-02 | 2019-09-06 | 2019-08-09 | 2019-12-12 | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.30149
306 | 110770 | HISTORIC HERNDON STREETSCAPE - PHASE III | 0606 | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Herndon | FAIRFAX | Northern Virginia | Northern Virginia:Herndon | Local Assistance Division | Christer P Carshult | Christer.Carshult@vdot.virginia.gov | (703) 259-1765 | Christer P Carshult | Christer.Carshult@vdot.virginia.gov | (703) 259-1765 | Town of Herndon |  |  | 0 |  | 0 | FY2021 | 550100 | 602244 | ACTIVITY DATES SET | R | Solicit Bids milestone is 242 days past the expected completion date | Y | Project estimate is less than $5M and is up to 20% over budget | 2017-02-21 | 2015-10-15 | 2017-05-15 | 2016-01-14 | G | 2017-05-16 | 2016-01-19 | 2017-05-18 | 2016-03-14 | G | 2017-05-19 | 2016-01-22 | 2017-11-27 | 2016-10-26 | G | [10 empty] | 2018-10-09 | 2018-10-09 | 2018-11-30 | 2019-04-29 | R | [5 empty] | 2018-12-04 | 2019-05-02 | 2019-09-30 | 2020-08-25 | R | [10 empty] | 2019-10-15 |  | 2020-06-24 |  | R | 2020-06-25 |  | 2020-11-30 |  | R | Delay due to unforeseen issues with utilities, railroad coordination, or right-of-way acquisition | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.33773
308 | 111015 | Route 620 - Safety Improvements | 0620 | Secondary | Reconstruction w/o Added Capacity | VDOT | Carroll County | MARTINSVILLE | Salem | NonMPO:NonMPO | Infrastructure Investment Division | Lisa P Hughes | Lisa.Hughes@VDOT.Virginia.gov | (276) 629-2582 | Jason L Patrick | Jason.Patrick@vdot.virginia.gov | (540) 381-7178 |  |  |  | 0 |  | 0 | FY2024 | 1057155 | 1057155 | ACTIVITY DATES SET | R | Engage Public milestone is 18 days past the expected completion date | G | Project is on budget | [5 empty] | 2019-04-01 | 2018-06-15 | 2019-04-12 | 2018-06-21 | G | 2019-04-15 | 2018-06-22 | 2020-03-12 | 2020-03-26 | R | [5 empty] | 2020-12-30 |  | 2021-02-03 |  | R | 2022-05-10 |  | 2022-05-23 |  | G | 2022-08-18 | 2020-06-08 | 2023-04-26 | 2020-11-17 | G | 2022-06-09 |  | 2022-12-15 |  | G | 2021-03-01 | 2020-03-17 | 2022-05-03 | 2020-03-17 | G | [5 empty] | 2023-05-09 |  | 2023-05-09 |  | G | 2023-06-29 |  | 2023-11-21 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.0925
309 | 112558 | INTERSECTION IMPROVEMENTS @ MAIN ST & MAPLE AVE - PHASE 2 | 9999 | Urban | Reconstruction w/o Added Capacity | Locally | Purcellville | LEESBURG | Northern Virginia | Northern Virginia:Purcellville | Infrastructure Investment Division | Kimberly Mccool | Kimberly.McCool@vdot.virginia.gov | (703) 259-3220 | Christer P Carshult | Christer.Carshult@vdot.virginia.gov | (703) 259-1765 | Dale Lehnig, Interim Public Works Director | dlehnig@purcellvilleva.gov | (540) 751-2327 | 0 |  | 0 | FY2025 | 1145000 | 1145000 | ACTIVITY DATES SET | R | Determine Requirements milestone finished 542 days late | G | Project is on budget | 2018-05-16 | 2018-05-16 | 2018-08-31 | 2018-06-18 | G | 2018-09-04 | 2018-06-19 | 2018-09-28 | 2018-08-15 | G | 2018-10-01 | 2018-08-16 | 2019-04-30 | 2020-10-23 | R | [10 empty] | 2021-12-14 |  | 2022-01-12 |  | G | [5 empty] | 2022-01-18 |  | 2023-01-30 |  | G | [10 empty] | 2023-02-15 |  | 2023-09-29 |  | G | 2023-12-22 |  | 2024-07-31 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.28972
310 | 107064 | Bus Stop Infrastructure and Accessibility Improvements |  | Urban | Facilities for Pedestrians and Bicycles | Locally | Virginia Beach | NORFOLK | Hampton Roads | Hampton Roads:Virginia Beach | Infrastructure Investment Division | Susan Wilson | Susan.Wilson@vdot.virginia.gov | (757) 956-3099 | Marci Thompson | Marci.Thompson@vdot.virginia.gov | (757) 956-3093 | Tonia Alger, P.E. | talger@vbgov.com | (757) 385-8746 | 0 |  | 0 | FY2024 | 398969 | 398969 | NO DATES SET YET | R | Agreement with Locality milestone is 6 days past the expected completion date | G | Project is on budget | 2020-10-01 |  | 2021-02-15 |  | R | 2021-02-16 |  | 2021-03-09 |  | Y | 2021-09-13 |  | 2022-01-10 |  | G | [25 empty] | 2023-01-05 |  | 2023-06-06 |  | G | [5 empty] | 2023-08-03 |  | 2023-08-30 |  | G | 2023-11-21 |  | 2023-11-21 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.14221
311 | 107350 | #SGR18LB - Centerville Turnpike Bridge Rehab |  | Urban | Bridge Rehab w/o Added Capacity | Locally | Chesapeake | NORFOLK | Hampton Roads | Hampton Roads:Chesapeake | Local Assistance Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Johndel A Alcaide | John.Alcaide@vdot.virginia.gov | (757) 956-3098 | Sam Sawan, P.E | sawan@cityofchesapeake.net | (757) 382-8513 | 0 |  | 1 | FY2019 | 3170000 | 8871745 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 9 days early | R | Project estimate is less than $5M and is 20% or more over budget | 2015-04-08 | 2015-08-25 | 2015-07-01 | 2015-09-29 | R | 2015-07-02 | 2015-09-29 | 2015-07-16 | 2015-09-29 | R | 2015-07-17 | 2016-04-19 | 2016-03-16 | 2016-04-20 | R | [10 empty] | 2017-02-03 | 2017-02-16 | 2017-02-16 | 2017-02-16 | G | [20 empty] | 2017-03-23 | 2018-08-06 | 2017-07-14 | 2018-12-06 | R | 2018-10-02 | 2018-12-07 | 2019-01-31 | 2019-01-22 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.21317
312 | 108459 | NEW TRAFFIC SIGNALS VI | 9999 | Urban | Traffic Management/Engineering | Locally | Falls Church | FAIRFAX | Northern Virginia | Northern Virginia:Falls Church | Local Assistance Division | Terry Yates | Terry.Yates@vdot.virginia.gov | (703) 259-2118 | Rhoderick M Undan | Rhoderick.Undan@vdot.virginia.gov | (703) 259-3347 | Scott Freda | sfreda@fallschurchva.gov | (703) 248-5308 | 0 |  | 0 | FY2019 | 825000 | 1245500 | ACTIVITY DATES SET | R | Complete Purchasing Right-of-Way milestone is 709 days past the expected completion date | R | Project estimate is less than $5M and is 20% or more over budget | 2016-10-03 | 2016-10-03 | 2016-12-30 | 2016-12-30 | G | 2017-01-03 | 2017-01-03 | 2017-01-05 | 2017-01-05 | G | 2017-01-06 | 2017-01-06 | 2017-07-13 | 2017-07-13 | G | [10 empty] | 2018-05-09 | 2018-05-09 | 2018-05-30 | 2018-05-30 | G | [5 empty] | 2018-06-01 | 2018-06-01 | 2019-03-15 |  | R | [10 empty] | 2019-04-02 |  | 2019-04-29 |  | R | 2019-04-30 |  | 2019-06-10 |  | R | Delay due to unforeseen issues with utilities, railroad coordination, or right-of-way acquisition | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.41803
313 | 108805 | OLDE TOWNE RD/LONGHILL RD TURN LANE IMPROVEMENTS | 0658 | Secondary | Reconstruction w/ Added Capacity | VDOT | James City County | WILLIAMSBURG | Hampton Roads | Hampton Roads:James City County | Local Assistance Division | Christopher R Carroll | C.Carroll@VDOT.Virginia.gov | (757) 253-5140 | Caleb Parsons | Caleb.Parsons@vdot.virginia.gov | (757) 359-1203 | Paul Holt | Paul.Holt@jamescitycountyva.gov | (757) 253-6674 | 0 |  | 0 | FY2021 | 661366 | 635452 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 618 days early | G | Project is on budget | [5 empty] | 2017-05-15 | 2017-03-22 | 2017-05-26 | 2017-03-27 | G | 2017-05-30 | 2017-03-28 | 2018-04-26 | 2018-04-26 | G | [5 empty] | 2019-02-04 | 2018-05-17 | 2019-02-15 | 2018-09-17 | G | 2020-01-16 | 2018-11-09 | 2020-01-31 | 2018-11-13 | G | 2020-10-23 | 2019-03-19 | 2021-08-23 | 2020-08-31 | G | 2020-02-19 | 2018-11-15 | 2020-03-10 | 2019-03-14 | G | [10 empty] | 2020-11-10 | 2019-04-09 | 2020-11-10 | 2019-04-09 | G | 2021-01-06 | 2019-09-18 | 2021-05-28 | 2019-09-18 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 1 | 0.25121
314 | 109467 | #HB2.FY17 - SAFETY IMPRV RTE 1 TELEGRAPH/WOODSTOCK | 0001 | Primary | Safety | Locally | Stafford County | FREDERICKSBURG | Fredericksburg | Fredericksburg:Stafford County | Infrastructure Investment Division | Khalil Minhas | Khalil.Minhas@vdot.virginia.gov | (540) 374-3369 | Khalil Minhas | Khalil.Minhas@vdot.virginia.gov | (540) 374-3369 | Alexander E. Owsiak | aowsiak@staffordcountyva.gov | (540) 658-4593 | 1 | 2017 | 0 | FY2022 | 8800000 | 9809405 | ACTIVITY DATES SET | R | Start Purchasing Right-of-Way milestone finished 266 days late | R | Project estimate is between $5M and $10M and is a $1M or more over budget | 2018-04-04 | 2017-05-09 | 2018-06-27 | 2017-06-15 | G | 2018-06-28 | 2017-06-16 | 2018-07-02 | 2017-06-16 | G | 2018-07-03 | 2017-07-10 | 2019-01-10 | 2019-01-10 | G | [10 empty] | 2019-12-12 | 2020-09-21 | 2020-01-03 | 2020-09-25 | R | [5 empty] | 2020-01-07 | 2020-11-18 | 2021-12-08 |  | G | [10 empty] | 2022-04-21 |  | 2022-04-21 |  | G | 2022-04-22 |  | 2022-06-02 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.10449
315 | 109480 | #HB2.FY17 EAST HIGH STREETSCAPE IMPROVEMENTS | 0000 | Urban | Reconstruction w/o Added Capacity | Locally | Charlottesville | CHARLOTTESVILLE | Culpeper | Charlottesville:Charlottesville | Infrastructure Investment Division | Ken Connors |  |  | Michael D Barnes | MichaelD.Barnes@vdot.virginia.gov | (434) 422-9861 | Tim Motsch | motscht@charlottesville.gov | (703) 314-9214 | 1 | 2017 | 0 | FY2022 | 5638000 | 7628000 | ACTIVITY DATES SET | R | Start Purchasing Right-of-Way milestone is 304 days past the expected completion date | R | Project estimate is between $5M and $10M and is a $1M or more over budget | 2016-07-01 | 2016-07-01 | 2016-09-22 | 2016-09-22 | G | 2016-09-23 | 2016-09-23 | 2016-09-23 | 2016-09-23 | G | 2016-09-24 | 2016-09-24 | 2017-04-12 | 2019-04-18 | R | 2019-12-17 | 2019-06-12 | 2019-12-17 | 2019-06-12 | G | [5 empty] | 2019-12-17 | 2019-04-20 | 2020-04-23 |  | R | [5 empty] | 2020-04-28 |  | 2021-05-17 |  | G | [10 empty] | 2021-06-03 |  | 2021-06-30 |  | G | 2021-07-01 |  | 2021-09-24 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.15877
316 | 109701 | CITYWIDE - INSTALL FLASHING ARROWS AND SIGNAL HEADS | 9999 | Urban | Safety | VDOT | Danville | HALIFAX | Lynchburg | Danville:Danville | Infrastructure Investment Division | Bhavesh Shah | Bhavesh.Shah@vdot.virginia.gov | (804) 524-6149 | Sharon S White | Sharon.White@VDOT.Virginia.gov | (434) 856-8220 | Brian Dunevant | dunevbl@danvilleva.gov | (434) 799-5019 | 0 |  | 0 | FY2019 | 45000 | 45000 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 35 days early | G | Project is on budget | 2016-10-03 | 2016-05-31 | 2016-12-30 | 2016-08-23 | G | 2017-01-03 | 2016-08-24 | 2017-01-05 | 2016-12-15 | G | 2017-01-06 | 2016-12-16 | 2017-07-13 | 2017-06-20 | G | [35 empty] | 2018-05-02 | 2018-05-01 | 2018-05-30 | 2018-05-22 | G | 2018-05-31 | 2018-05-23 | 2018-07-11 | 2018-06-06 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | WORK/TASK ORDER | 1 | 0 | 0.086
317 | 110901 | #SGR18VB - BRIDGE REPLACEMENT-RT 617 EXOL SWAMP ID 30879 | 0617 | Secondary | Bridge Replacement w/o Added Capacity | VDOT | King & Queen County | SALUDA | Fredericksburg | NonMPO:NonMPO | Infrastructure Investment/Asset Management Division | Wesley Foor | Wesley.Foor@vdot.virginia.gov | (540) 604-1370 | Wesley Foor | Wesley.Foor@vdot.virginia.gov | (540) 604-1370 |  |  |  | 0 |  | 1 | FY2020 | 2500000 | 2000000 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 161 days early | G | Project is on budget | [5 empty] | 2017-06-21 | 2017-03-17 | 2017-07-05 | 2017-03-17 | G | 2017-07-06 | 2017-03-20 | 2018-06-04 | 2018-01-23 | G | [5 empty] | 2018-02-23 | 2018-02-05 | 2018-03-08 | 2018-02-27 | G | 2018-07-25 | 2018-07-10 | 2018-08-07 | 2018-07-18 | G | 2018-10-04 | 2018-10-04 | 2018-11-16 | 2019-12-06 | R | 2018-08-22 | 2018-08-23 | 2019-10-04 | 2019-02-11 | G | 2017-08-01 | 2017-08-01 | 2020-01-14 | 2018-10-02 | G | [5 empty] | 2020-02-11 | 2019-08-13 | 2020-02-11 | 2019-08-13 | G | 2020-04-02 | 2019-11-13 | 2020-04-22 | 2019-11-13 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.060092
318 | 111006 | Cedar Road Flashing Yellow Arrows (FYA) |  | Urban | Safety | Locally | Chesapeake | NORFOLK | Hampton Roads | Hampton Roads:Chesapeake | Infrastructure Investment Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Johndel A Alcaide | John.Alcaide@vdot.virginia.gov | (757) 956-3098 | Sam Sawan, PE | sawan@cityofchesapeake.net | (757) 382-8263 | 0 |  | 0 | FY2023 | 313000 | 313000 | NO DATES SET YET-PE OPEN | G | Obtained Permits milestone finished 785 days early | G | Project is on budget | 2020-09-30 | 2020-07-15 | 2021-02-12 | 2020-08-26 | G | 2021-02-15 | 2020-08-28 | 2021-03-08 | 2020-09-14 | G | 2021-04-06 |  | 2021-07-28 |  | G | [25 empty] | 2022-07-25 | 2020-10-29 | 2022-12-23 | 2020-10-29 | G | [5 empty] | 2023-02-27 |  | 2023-03-24 |  | G | 2023-06-13 |  | 2023-06-13 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.20461
320 | 113202 | E Little Creek Rd & Admiral Taussig Blvd Intersection Improv | 0165 | Urban | Reconstruction w/o Added Capacity | Locally | Norfolk | NORFOLK | Hampton Roads | Hampton Roads:Norfolk | Local Assistance Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Derrick Williams | Derrick.Williams@vdot.virginia.gov | (757) 956-3097 | Olga Beltsar, P. E. | Olga.beltsar@norfolk.gov | (757) 664-7336 | 0 |  | 0 | FY2021 | 725776 | 837121 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 138 days early | Y | Project estimate is less than $5M and is up to 20% over budget | 2018-09-14 | 2018-09-14 | 2018-12-12 | 2018-10-02 | G | 2018-12-13 | 2018-09-19 | 2018-12-17 | 2018-10-02 | G | 2018-12-18 | 2018-10-03 | 2019-06-25 | 2019-07-24 | R | 2019-10-18 | 2019-10-18 | 2019-12-04 | 2019-11-08 | G | [20 empty] | 2019-04-10 | 2019-11-05 | 2019-05-21 | 2019-11-07 | R | [5 empty] | 2020-01-07 | 2020-01-07 | 2020-02-20 | 2020-02-28 | R | 2020-05-08 | 2020-05-18 | 2020-10-28 | 2020-06-12 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.12859
321 | 113271 | Reconstrruct Toano ADA Sidewalk and Bike and Ped. | 0060 | Primary | Reconstruction w/o Added Capacity | Locally | James City County | WILLIAMSBURG | Hampton Roads | Hampton Roads:James City County | Local Assistance Division | Christopher R Carroll | C.Carroll@VDOT.Virginia.gov | (757) 253-5140 | Keisha Wilkins | Keisha.Wilkins@vdot.virginia.gov | (757) 956-3110 | Tammy Rosario | Tammy.Rosario@jamescitycountyva.gov | (757) 253-6685 | 0 |  | 0 | FY2022 | 1665594 | 1699398 | ACTIVITY DATES SET | G | Determine Requirements milestone finished 39 days early | Y | Project estimate is less than $5M and is up to 20% over budget | 2019-10-01 | 2018-09-12 | 2019-12-30 | 2018-09-12 | G | 2019-12-31 | 2018-09-13 | 2020-01-03 | 2018-09-17 | G | 2020-01-06 | 2020-04-27 | 2020-07-10 | 2020-06-01 | G | [25 empty] | 2021-03-25 | 2020-01-30 | 2021-05-05 | 2020-01-30 | G | [5 empty] | 2021-05-06 |  | 2021-07-30 |  | G | 2021-10-20 |  | 2022-01-27 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.2201
322 | 113293 | Brookland Park Blvd Streetscape |  | Primary | Landscaping/Beautification | Locally | Richmond | ASHLAND | Richmond | Richmond:Richmond | Local Assistance Division | Mark White |  |  | Brian J Lokker | Brian.Lokker@VDOT.Virginia.gov | (804) 524-6010 | Adel Edward | adel.edward@richmondgov.com | (804) 646-6584 | 0 |  | 0 | FY2021 | 794000 | 794000 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 295 days early | G | Project is on budget | 2018-07-02 | 2018-07-10 | 2018-11-30 | 2018-07-10 | G | 2018-12-03 | 2018-12-14 | 2018-12-20 | 2018-12-17 | G | 2018-12-26 | 2018-12-20 | 2019-07-01 | 2019-07-01 | G | [25 empty] | 2019-03-19 | 2019-07-08 | 2020-01-02 | 2019-07-08 | G | [5 empty] | 2020-03-20 | 2019-07-15 | 2020-03-20 | 2019-09-16 | G | 2020-06-09 | 2019-09-17 | 2020-09-30 | 2019-12-10 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.31582
323 | 113837 | STAFFORD SIDEWALK -- MANNING ROAD AND LICHFIELD BOULEVARD | 9999 | Secondary | Facilities for Pedestrians and Bicycles | VDOT | Stafford County | FREDERICKSBURG | Fredericksburg | Fredericksburg:Stafford County | Infrastructure Investment Division | Peter A Hedrich | Peter.Hedrich@vdot.virginia.gov | (540) 899-4540 | Catherine C Coffey | Catherine.Coffey@vdot.virginia.gov | (540) 899-4280 |  |  |  | 0 |  | 0 | FY2028 | 587100 | 587100 | NO DATES SET YET | G | Start Development milestone is 950 days ahead of the expected completion date | Y | Estimate not current | [5 empty] | 2023-09-18 |  | 2023-09-29 |  | G | 2023-10-02 |  | 2024-08-28 |  | G | [5 empty] | 2025-07-07 |  | 2025-07-18 |  | G | 2026-10-23 |  | 2026-11-05 |  | G | 2027-04-07 |  | 2027-10-08 |  | G | 2026-11-24 |  | 2027-06-03 |  | G | 2026-04-14 |  | 2026-10-15 |  | G | [5 empty] | 2027-10-12 |  | 2027-10-12 |  | G | 2028-01-07 |  | 2028-01-07 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.07541
324 | 113896 | Gen-Oak Connector - Bridgewater | 0700 | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Bridgewater | HARRISONBURG | Staunton | NonMPO:NonMPO | Infrastructure Investment Division | David C Morris | David.Morris2@VDOT.Virginia.gov | (540) 332-8607 | Jeffery A Lineberry | Jeff.Lineberry@VDOT.Virginia.gov | (540) 332-2265 | Alex Wilmer | reuben.rhodes@vdot.virginia.gov | (540) 908-4212 | 0 |  | 0 | FY2022 | 277224 | 277224 | NO DATES SET YET-PE OPEN | R | Engage Public milestone baseline missing | G | Project is on budget | 2019-05-21 | 2019-01-22 | 2019-08-14 | 2019-04-16 | G | 2019-08-15 | 2019-07-10 | 2019-08-19 | 2019-07-29 | G | 2019-08-20 |  | 2020-03-02 |  | R | [9 empty] | R | 2020-12-22 |  | 2021-01-13 |  | R | [5 empty] | 2021-01-19 |  | 2021-10-25 |  | G | 2020-04-07 |  | 2020-12-09 |  | R | [5 empty] | 2021-11-10 |  | 2021-12-10 |  | G | 2022-03-07 |  | 2022-03-07 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.26909
325 | 115311 | Greenlee Road Drainage Improvements | 0000 | Urban | Mitigation of Water Pollution Due to Highway Runof | Locally | Roanoke | SALEM | Salem | Roanoke:Roanoke City | Local Assistance Division | Cheryl B Becker | Cheryl.Becker@vdot.virginia.gov | (540) 492-2531 | Cheryl B Becker | Cheryl.Becker@vdot.virginia.gov | (540) 492-2531 | Joseph Arthur | Joseph.Arthur@roanokeva.gov | (540) 853-5906 | 0 |  | 0 | FY2021 | 475000 | 475000 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 137 days early | G | Project is on budget | 2019-06-28 | 2019-06-28 | 2019-09-23 | 2020-06-18 | R | 2019-09-24 | 2020-06-18 | 2019-09-26 | 2020-06-18 | R | 2019-09-27 | 2020-06-18 | 2020-04-08 | 2020-06-18 | R | [35 empty] | 2020-07-08 | 2020-06-18 | 2020-07-08 | 2020-06-18 | G | 2020-09-25 | 2020-06-18 | 2020-11-02 | 2020-06-18 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.20396
326 | 115405 | #SMART20 - R-CUT at Lewiston Plank Rd at 460 | 0460 | Primary | Safety | VDOT | Nottoway County | PETERSBURG | Richmond | NonMPO:NonMPO | Infrastructure Investment Division | Roy Soto | Roy.Soto@vdot.virginia.gov | (804) 609-5239 | Roy Soto | Roy.Soto@vdot.virginia.gov | (804) 609-5239 |  |  |  | 1 | 2020 | 0 | FY2028 | 3364437 | 2828148 | NO DATES SET YET-PE OPEN | G | Start Development milestone finished 1431 days early | G | Project is on budget | [5 empty] | 2023-09-01 | 2019-09-18 | 2023-09-15 | 2019-10-15 | G | 2023-09-18 | 2019-10-16 | 2024-08-14 |  | G | [5 empty] | 2025-06-20 |  | 2025-07-03 |  | G | 2026-10-08 |  | 2026-10-22 |  | G | 2027-03-24 |  | 2027-09-24 |  | G | 2026-11-09 |  | 2027-05-19 |  | G | 2026-03-31 |  | 2026-10-01 |  | G | [5 empty] | 2027-10-12 |  | 2027-10-12 |  | G | 2028-01-07 |  | 2028-01-07 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.056009
327 | 115731 | #SGR20LP - 2006 Virginia Beach Blvd | 0058 | Urban | Restoration and Rehabilitation | Locally | Virginia Beach | NORFOLK | Hampton Roads | Hampton Roads:Virginia Beach | Infrastructure Investment/Asset Management Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Marci Thompson | Marci.Thompson@vdot.virginia.gov | (757) 956-3093 | Jimmy Evans | jrevans@vbgov.com | (757) 385-1505 | 0 |  | 1 | FY2020 | 565549 | 565549 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 206 days early | G | Project is on budget | 2019-08-05 | 2019-07-03 | 2019-10-29 | 2019-08-07 | G | [5 empty] | 2019-08-05 | 2019-07-18 | 2019-08-16 | 2019-08-08 | G | [35 empty] | 2019-12-03 | 2019-09-20 | 2019-12-31 | 2019-09-20 | G | 2020-03-24 | 2019-09-27 | 2020-04-20 | 2019-09-27 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.076991
328 | 116862 | NORTH SHENANDOAH AVENUE LIGHTING |  | Urban | Other | Locally | Front Royal | EDINBURG | Staunton | NonMPO:NonMPO | Local Assistance Division | Kimberly Cameron | Kim.Cameron@vdot.virginia.gov | (540) 332-7886 | Kimberly Cameron | Kim.Cameron@vdot.virginia.gov | (540) 332-7886 | Robert Brown | rbrown@frontroyalva.com | (540) 631-3595 | 0 |  | 0 | FY2025 | 265000 | 265000 | NO DATES SET YET | G | Agreement with Locality milestone is 107 days ahead of the expected completion date | G | Project is on budget | 2021-02-01 |  | 2021-06-08 |  | G | [5 empty] | 2021-06-09 |  | 2021-06-22 |  | G | [25 empty] | 2023-12-28 |  | 2024-05-29 |  | G | [5 empty] | 2024-07-12 |  | 2024-08-22 |  | G | 2024-11-13 |  | 2024-11-13 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.16422
329 | 117020 | #SGR21VB (VARIOUS) CULV REPL - SALEM DIST | 0000 | Secondary | Bridge Replacement w/o Added Capacity | VDOT | Salem District-wide |  | Salem | NonMPO:NonMPO | Infrastructure Investment Division | Anthony T Marshall | Todd.Marshall@VDOT.Virginia.gov | (540) 387-5460 | Jack D Bayne | Jack.Bayne@VDOT.Virginia.gov | (540) 387-5451 |  |  |  | 0 |  | 1 | FY2023 | 4697249 | 4697249 | NO DATES SET YET | G | Determine Requirements milestone is 509 days ahead of the expected completion date | G | Project is on budget | [10 empty] | 2022-07-01 |  | 2022-07-15 |  | G | [25 empty] | 2022-07-01 |  | 2022-12-02 |  | G | [5 empty] | 2022-10-11 |  | 2022-10-11 |  | G | 2023-01-05 |  | 2023-01-05 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.088188
330 | 113187 | MORVEN PARK RD NW IMPROVEMENTS | 9999 | Urban | Reconstruction w/o Added Capacity | Locally | Leesburg | LEESBURG | Northern Virginia | Northern Virginia:Leesburg | Local Assistance Division | Kimberly Mccool | Kimberly.McCool@vdot.virginia.gov | (703) 259-3220 | Susie X Lue | Susie.Lue@vdot.virginia.gov | (703) 259-2918 | Anna Geiger | AGeiger@LEESBURGVA.GOV | (703) 771-2742 | 0 |  | 0 | FY2025 | 4227536 | 4227536 | ACTIVITY DATES SET | G | Determine Requirements milestone finished 31 days early | G | Project is on budget | 2018-10-31 | 2018-07-10 | 2019-03-29 | 2018-08-13 | G | [5 empty] | 2019-11-01 | 2018-10-23 | 2020-10-30 | 2020-09-29 | G | [10 empty] | 2021-12-28 |  | 2022-05-20 |  | G | [5 empty] | 2022-05-23 |  | 2023-11-28 |  | G | [10 empty] | 2023-12-29 |  | 2024-05-30 |  | G | 2024-05-31 |  | 2024-10-29 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.35906
331 | 113254 | #SGR19LP - RT 29 BUS. SB - PRIMARY EXT PAVEMENT OVERLAY | 0029 | Urban | Resurfacing | Locally | Warrenton | WARRENTON | Culpeper | Northern Virginia:Warrenton | Local Assistance Division | John P Price | John.Price@VDOT.Virginia.gov | (540) 347-6371 | John P Price | John.Price@VDOT.Virginia.gov | (540) 347-6371 | Paul Bernard | pbernard@warrentonva.gov | (540) 347-1858 | 0 |  | 1 | FY2019 | 252126 | 252126 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 201 days early | G | Project is on budget | 2018-08-17 | 2018-07-12 | 2018-11-13 | 2018-07-12 | G | [5 empty] | 2018-08-17 | 2018-08-14 | 2018-08-30 | 2018-08-14 | G | [25 empty] | 2018-08-15 | 2018-08-15 | 2018-11-08 | 2018-08-15 | G | [5 empty] | 2018-11-09 | 2018-08-15 | 2018-12-11 | 2018-08-15 | G | 2019-03-06 | 2018-08-17 | 2019-03-06 | 2018-08-17 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.078713
332 | 113279 | Wormley Creek - Cook Road to Edgehill Outfall System Culvert | 0704 | Secondary | Reconstruction w/o Added Capacity | Locally | York County | WILLIAMSBURG | Hampton Roads | Hampton Roads:York County | Local Assistance Division | Christopher R Carroll | C.Carroll@VDOT.Virginia.gov | (757) 253-5140 | Keisha Wilkins | Keisha.Wilkins@vdot.virginia.gov | (757) 956-3110 | Anna Drake Stormwater Programs | drakea@yorkcounty.gov | (757) 890-3831 | 0 |  | 0 | FY2022 | 1331151 | 2140000 | ACTIVITY DATES SET | G | Obtained Permits milestone finished 97 days early | R | Project estimate is less than $5M and is 20% or more over budget | 2018-10-01 | 2018-09-12 | 2018-12-28 | 2018-09-12 | G | 2018-12-31 | 2018-09-13 | 2019-01-03 | 2018-09-14 | G | 2019-01-04 | 2018-09-17 | 2019-07-11 | 2019-09-05 | R | [25 empty] | 2019-08-28 | 2020-01-29 | 2020-05-05 | 2020-01-29 | G | [5 empty] | 2021-06-09 |  | 2021-07-21 |  | G | 2021-10-08 |  | 2021-10-08 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.18206
333 | 113464 | Mercury Blvd Rd Diet - Segment II | 0258 | Urban | Facilities for Pedestrians and Bicycles | Locally | Hampton | WILLIAMSBURG | Hampton Roads | Hampton Roads:Hampton | Local Assistance Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Derrick Williams | Derrick.Williams@vdot.virginia.gov | (757) 956-3097 | Sandon Rogers, P.E. | sandon.rogers@hampton.gov | (757) 727-6786 | 0 |  | 0 | FY2023 | 111000 | 111000 | ACTIVITY DATES SET | G | Obtained Permits milestone finished 559 days early | G | Project is on budget | 2018-09-04 | 2018-09-04 | 2018-11-30 | 2019-06-20 | R | 2018-12-03 | 2019-06-21 | 2018-12-05 | 2019-06-25 | R | 2018-12-06 | 2019-06-26 | 2019-06-13 | 2020-07-02 | R | 2020-07-06 | 2020-07-06 | 2020-08-14 | 2020-07-15 | G | [20 empty] | 2021-08-25 | 2020-07-21 | 2022-01-31 | 2020-07-21 | G | [5 empty] | 2022-03-07 |  | 2022-04-26 |  | G | 2022-07-15 |  | 2023-01-09 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.14678
334 | 113891 | Alt. 58 Median Rumble Strips - Wise County | 0058 | Primary | Safety | VDOT | Wise County | WISE | Bristol | NonMPO:NonMPO | Infrastructure Investment Division | Joseph Mullins | Joseph.Mullins@vdot.virginia.gov | (276) 321-6463 | Jonathan A Henegar | Jonathan.Henegar@vdot.virginia.gov | (276) 206-0360 |  |  |  | 0 |  | 0 | FY2021 | 68736 | 43982 | ACTIVITY DATES SET | R | Relocate Utilities milestone is 4 days past the expected completion date | G | Project is on budget | [5 empty] | 2018-12-31 | 2018-11-07 | 2019-01-14 | 2018-11-09 | G | 2019-01-15 | 2018-11-13 | 2019-09-05 | 2020-02-26 | R | [5 empty] | 2020-04-24 | 2020-04-24 | 2020-06-05 | 2020-06-05 | G | [5 empty] | 2020-10-20 |  | 2021-02-17 |  | R | [15 empty] | 2021-03-09 |  | 2021-03-09 |  | Y | 2021-05-27 |  | 2021-05-27 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.065667
335 | 115128 | #SMART20 John Marshall Hwy./Rte. 55 East Safety Improvements | 0055 | Primary | Safety | VDOT | Warren County | EDINBURG | Staunton | NonMPO:NonMPO | Infrastructure Investment Division | Keith M Rider | Keith.Rider@VDOT.Virginia.gov | (434) 856-8145 | Kunal Kothawade | Kunal.Kothawade@vdot.virginia.gov | (540) 332-9259 |  |  |  | 1 | 2020 | 0 | FY2026 | 1633637 | 1633637 | NO DATES SET YET | G | Start Development milestone is 904 days ahead of the expected completion date | G | Project is on budget | [5 empty] | 2023-08-01 |  | 2023-08-14 |  | G | 2023-08-15 |  | 2024-04-10 |  | G | [5 empty] | 2024-12-16 |  | 2025-01-30 |  | G | [5 empty] | 2025-05-15 |  | 2025-09-08 |  | G | [5 empty] | 2025-04-30 |  | 2025-07-31 |  | G | [5 empty] | 2025-09-09 |  | 2025-09-09 |  | G | 2025-12-03 |  | 2025-12-03 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.062222
336 | 115357 | #SGR20LP - RT 17 (Bridge Rd) | 0017 | Urban | Resurfacing | Locally | Suffolk | NORFOLK | Hampton Roads | Hampton Roads:Suffolk | Infrastructure Investment/Asset Management Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Johndel A Alcaide | John.Alcaide@vdot.virginia.gov | (757) 956-3098 | Edward Heide | eheide@suffolkva.us | (757) 514-7615 | 0 |  | 1 | FY2020 | 65987 | 65987 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 188 days early | G | Project is on budget | 2019-10-01 | 2019-10-01 | 2019-12-30 | 2019-10-25 | G | [5 empty] | 2019-10-01 | 2019-10-01 | 2019-10-14 | 2019-10-14 | G | [35 empty] | 2020-01-16 | 2019-10-25 | 2020-02-14 | 2019-10-30 | G | 2020-03-10 | 2019-10-25 | 2020-05-05 | 2019-10-30 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.067602
337 | 115485 | #SMART20-US Route 11 / SR 660 Roundabout North (App ID#3804) | 0011 | Primary | Reconstruction w/o Added Capacity | VDOT | Smyth County | ABINGDON | Bristol | NonMPO:NonMPO | Infrastructure Investment Division | Dennis R Harris | Dennis.Harris@VDOT.Virginia.gov | (276) 696-3289 | Ronald C Flanary | Ronald.Flanary@VDOT.Virginia.gov | (276) 696-3252 |  |  |  | 1 | 2020 | 0 | FY2024 | 3572022 | 3572022 | ACTIVITY DATES SET | G | Determine Requirements milestone finished 42 days early | G | Project is on budget | [5 empty] | 2020-02-07 | 2019-11-22 | 2020-02-21 | 2019-12-09 | G | 2020-02-24 | 2019-12-10 | 2020-11-05 | 2020-09-24 | G | [5 empty] | 2021-06-11 |  | 2021-06-24 |  | G | 2022-10-28 |  | 2022-11-10 |  | G | 2023-04-12 |  | 2023-10-13 |  | G | 2022-12-01 |  | 2023-09-25 |  | G | 2022-04-19 |  | 2023-06-29 |  | G | [5 empty] | 2023-12-12 |  | 2023-12-12 |  | G | 2024-03-07 |  | 2024-03-07 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.080812
338 | 116740 | I64 Toll Integration - Fiber Optic Communications | 0064 | Interstate | Other | VDOT | Multi-jurisdictional: Hampton Roads MPO |  | Hampton Roads | Hampton Roads:Multi-jurisdictional: Hampton Roads MPO | Infrastructure Investment Division | Michael J Miller | Michael.Miller@VDOT.Virginia.gov | (757) 605-8741 | Mark T Grass | Mark.Grass@VDOT.Virginia.gov | (757) 956-3165 |  |  |  | 0 |  | 0 | FY2021 | 14000 | 14000 | NO DATES SET YET | R | Determine Requirements milestone is 319 days past the expected completion date | G | Project is on budget | [10 empty] | 2020-04-02 | 2020-07-02 | 2020-04-08 |  | R | [25 empty] | 2020-04-02 | 2020-08-21 | 2020-10-05 | 2020-08-21 | G | [5 empty] | 2020-11-10 |  | 2020-11-10 |  | R | 2021-02-08 |  | 2021-02-08 |  | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | ADMINISTRATIVE SERVICES | 0 | 0 | 0.17275
339 | 116970 | #SGR21LP RIDGEWAY STREET WEST PRIMARY EXTENSION PAVING |  | Primary | Resurfacing | Locally | Clifton Forge | LEXINGTON | Staunton | NonMPO:NonMPO | Infrastructure Investment Division | Jamison Brown | Jamison.Brown@vdot.virginia.gov | (540) 332-7389 | Jamison Brown | Jamison.Brown@vdot.virginia.gov | (540) 332-7389 | Ricky Bourne | rbourne@cliftonforgeva.gov | (540) 863-2500 | 0 |  | 1 | FY2024 | 495626 | 495626 | NO DATES SET YET | G | Agreement with Locality milestone is 107 days ahead of the expected completion date | G | Project is on budget | 2021-02-01 |  | 2021-06-08 |  | G | 2021-06-09 |  | 2021-06-29 |  | G | 2021-07-29 |  | 2021-11-22 |  | G | [25 empty] | 2022-11-17 |  | 2023-04-21 |  | G | [5 empty] | 2023-06-20 |  | 2023-07-18 |  | G | 2023-10-05 |  | 2023-10-05 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.09154
340 | 117067 | Scott's Addition Green Space |  | Urban | Facilities for Pedestrians and Bicycles | Locally | Richmond | ASHLAND | Richmond | Richmond:Richmond | Local Assistance Division | Olena Fecek | Olena.Fecek@vdot.virginia.gov | (804) 524-6368 | Olena Fecek | Olena.Fecek@vdot.virginia.gov | (804) 524-6368 | TBD |  | TBD | 0 |  | 0 | FY2028 | 1106000 | 1106000 | NO DATES SET YET | G | Agreement with Locality milestone is 1543 days ahead of the expected completion date | G | Project is on budget | 2025-01-06 |  | 2025-05-14 |  | G | 2025-05-15 |  | 2025-06-05 |  | G | 2025-07-07 |  | 2025-10-28 |  | G | [10 empty] | 2027-02-24 |  | 2027-03-30 |  | G | [5 empty] | 2027-03-31 |  | 2027-08-26 |  | G | 2027-07-26 |  | 2027-12-27 |  | G | [5 empty] | 2027-12-03 |  | 2028-01-03 |  | G | 2028-03-24 |  | 2028-03-24 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.16914
341 | 117120 | Mallory St Reconstruction for Bike Lanes | 0169 | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Hampton | WILLIAMSBURG | Hampton Roads | Hampton Roads:Hampton | Local Assistance Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Derrick Williams | Derrick.Williams@vdot.virginia.gov | (757) 956-3097 | Sandon Rogers, P.E. | Sandon.Rogers@Hampton.gov | (757) 727-6786 | 0 |  | 0 | FY2024 | 960000 | 960000 | NO DATES SET YET | G | Agreement with Locality milestone is 80 days ahead of the expected completion date | G | Project is on budget | 2021-01-04 |  | 2021-05-12 |  | G | 2021-05-13 |  | 2021-06-03 |  | G | 2021-10-12 |  | 2022-02-10 |  | G | [10 empty] | 2023-03-03 |  | 2023-04-07 |  | G | [5 empty] | 2023-04-10 |  | 2023-09-06 |  | G | 2023-08-03 |  | 2024-01-05 |  | G | [5 empty] | 2023-11-29 |  | 2024-01-11 |  | G | 2024-04-03 |  | 2024-04-03 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.36684
342 | 117170 | #SGR21LP 137-City of Williamsburg 2197 S Henry St | 0132 | Urban | Resurfacing | Locally | Williamsburg | WILLIAMSBURG | Hampton Roads | Hampton Roads:Williamsburg | Local Assistance Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Chessica Villaflores | Chessica.Villaflores@vdot.virginia.gov | (757) 956-3094 | Aaron B. Smalll | asmall@williamsburgva.gov | (757) 220-6140 | 0 |  | 0 | FY2022 | 335100 | 335100 | NO DATES SET YET | G | Agreement with Locality milestone is 47 days ahead of the expected completion date | G | Project is on budget | 2021-03-01 |  | 2021-04-09 |  | G | 2021-04-12 |  | 2021-04-30 |  | G | 2021-06-01 |  | 2021-07-13 |  | G | [25 empty] | 2021-06-29 |  | 2021-08-10 |  | G | [5 empty] | 2021-10-07 |  | 2021-11-04 |  | G | 2022-02-01 |  | 2022-02-01 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.090897
343 | 117952 | #81CIP DETOUR SIGNAL UPGRADES FOR ABINGDON & MARION | 9999 | Primary | Traffic Management/Engineering | VDOT | Abingdon | ABINGDON | Bristol | NonMPO:NonMPO | Infrastructure Investment Division | Brian Holt | Brian.Holt@vdot.virginia.gov | (276) 696-3414 | Jeremy J Mullins | Jeremy.Mullins@vdot.virginia.gov | (276) 696-3259 |  |  |  | 0 |  | 0 | FY2024 | 4050619 | 4050619 | NO DATES SET YET-PE OPEN | G | Obtained Permits milestone finished 734 days early | G | Project is on budget | [5 empty] | 2020-10-01 | 2020-10-01 | 2020-10-22 | 2020-10-22 | G | 2020-10-23 | 2020-10-23 | 2021-08-26 |  | G | [5 empty] | 2022-04-01 |  | 2022-04-28 |  | G | [5 empty] | 2022-12-21 |  | 2023-04-25 |  | G | [5 empty] | 2022-09-08 | 2021-02-09 | 2023-02-13 | 2021-02-09 | G | [5 empty] | 2023-05-09 |  | 2023-05-09 |  | G | 2023-07-28 |  | 2023-07-28 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.096067
344 | 118154 | Old Bermuda Hundred Road at Ramblewood Drive Roundabout | 0618 | Secondary | Safety | Locally | Chesterfield County | CHESTERFIELD | Richmond | Richmond:Chesterfield County | Infrastructure Investment Division | Michael S Gray | Mike.Gray@vdot.virginia.gov | (804) 609-5347 | Michael S Gray | Mike.Gray@vdot.virginia.gov | (804) 609-5347 | Chessa Faulkner | faulknerc@chesterfield.gov | (804) 748-1037 | 0 |  | 0 | FY2028 | 5146000 | 5146000 | NO DATES SET YET | G | Agreement with Locality milestone is 1179 days ahead of the expected completion date | G | Project is on budget | 2024-01-08 |  | 2024-05-15 |  | G | 2024-05-16 |  | 2024-06-06 |  | G | 2024-12-16 |  | 2025-04-11 |  | G | [10 empty] | 2026-07-31 |  | 2026-09-03 |  | G | [5 empty] | 2026-09-04 |  | 2027-02-10 |  | G | 2027-01-06 |  | 2027-06-07 |  | G | [5 empty] | 2027-05-14 |  | 2027-06-11 |  | G | 2027-08-31 |  | 2027-08-31 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 1 | 0.19853
345 | 118409 | #SGR21LP - City of Richmond 1234 Belt Blvd N |  | Urban | Resurfacing | Locally | Richmond | ASHLAND | Richmond | Richmond:Richmond | Infrastructure Investment/Asset Management Division | Olena Fecek | Olena.Fecek@vdot.virginia.gov | (804) 524-6368 | Olena Fecek | Olena.Fecek@vdot.virginia.gov | (804) 524-6368 | Kenny Horak | Kenneth.horak@richmondgov.com | (804) 646-4781 | 0 |  | 1 | FY2024 | 299911 | 299911 | NO DATES SET YET | G | Agreement with Locality milestone is 292 days ahead of the expected completion date | G | Project is on budget | 2021-08-02 |  | 2021-12-10 |  | G | 2021-12-13 |  | 2022-01-04 |  | G | 2022-02-04 |  | 2022-05-27 |  | G | [25 empty] | 2023-05-24 |  | 2023-10-23 |  | G | [5 empty] | 2023-12-22 |  | 2024-01-24 |  | G | 2024-04-12 |  | 2024-04-12 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.06272
346 | 88830 | #SMART18 - BUS 15 - CONSTRUCT LTL @ UR3860 (MILNWOOD RD) | 0015 | Urban | Safety | Locally | Farmville | DILLWYN | Lynchburg | NonMPO:NonMPO | Infrastructure Investment Division | Sharon S White | Sharon.White@VDOT.Virginia.gov | (434) 856-8220 | Sharon S White | Sharon.White@VDOT.Virginia.gov | (434) 856-8220 | GERALS SPATES | GSPATES@FARMVILLEVA.COM | (434) 392-5686 | 1 | 2018 | 0 | FY2019 | 3719187 | 2534217 | CONSTRUCTION COMPLETED | R | Start Delivery milestone finished 9 days late | G | Project is on budget | 2012-04-20 | 2012-04-20 | 2012-04-20 | 2012-04-20 | G | 2013-11-29 | 2013-04-16 | 2013-11-29 | 2013-04-16 | G | 2016-08-01 | 2016-08-01 | 2016-09-01 | 2016-09-01 | G | [10 empty] | 2017-10-03 | 2017-10-03 | 2017-10-25 | 2017-10-25 | G | [5 empty] | 2018-01-03 | 2018-01-03 | 2019-03-01 | 2019-02-08 | G | [10 empty] | 2019-03-04 | 2019-03-01 | 2019-05-29 | 2019-04-26 | G | 2019-03-05 | 2019-05-22 | 2019-05-28 | 2019-06-06 | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.11891
347 | 102895 | SYCOLIN ROAD - WIDEN TO FOUR LANES (PH IV) | 0000 | Urban | Reconstruction w/ Added Capacity | Locally | Leesburg | LEESBURG | Northern Virginia | Northern Virginia:Leesburg | Infrastructure Investment Division | Kimberly Mccool | Kimberly.McCool@vdot.virginia.gov | (703) 259-3220 | Rita Hockman | Rita.Hockman@vdot.virginia.gov | (804) 824-7421 | Anne Geiger, PE | AGeiger@LEESBURGV.gov | (703) 771-2742 | 0 |  | 0 | FY2019 | 15437869 | 14457624 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 202 days early | G | Project is on budget | 2013-06-10 | 2013-06-09 | 2013-10-09 | 2013-09-03 | G | 2013-10-10 | 2013-10-10 | 2013-12-30 | 2014-04-09 | R | 2013-12-02 | 2014-12-01 | 2017-03-29 | 2016-08-09 | G | [5 empty] | 2017-01-17 | 2017-01-17 | 2017-02-17 | 2017-02-17 | G | 2016-08-19 | 2013-06-10 | 2016-12-02 | 2016-12-02 | G | 2016-12-03 | 2016-12-03 | 2018-05-30 | 2018-04-19 | G | 2016-12-03 | 2016-12-03 | 2018-05-30 | 2018-04-19 | G | 2015-10-10 | 2015-10-10 | 2018-02-02 | 2018-02-02 | G | [5 empty] | 2018-09-04 | 2018-06-26 | 2018-12-28 | 2018-08-09 | G | 2019-01-03 | 2018-08-14 | 2019-06-03 | 2018-11-13 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.41876
348 | 105573 | CITY OF FAIRFAX PEDESTRIAN IMPROVEMENTS | 9999 | Urban | Facilities for Pedestrians and Bicycles | Locally | Fairfax | FAIRFAX | Northern Virginia | Northern Virginia:Fairfax | Infrastructure Investment Division | Terry Yates | Terry.Yates@vdot.virginia.gov | (703) 259-2118 | Christer P Carshult | Christer.Carshult@vdot.virginia.gov | (703) 259-1765 | Wendy Block Sanford | Wendy.Sanford@fairfaxva.gov | (703) 385-7889 | 0 |  | 0 | FY2024 | 404956 | 404956 | NO DATES SET YET-PE OPEN | R | Determine Requirements milestone is 144 days past the expected completion date | Y | Estimate not current | 2019-02-14 | 2017-10-03 | 2019-10-31 | 2018-06-26 | G | 2019-11-01 | 2019-03-07 | 2019-12-31 | 2019-03-14 | G | 2019-12-04 | 2019-04-04 | 2020-09-30 |  | R | [10 empty] | 2021-02-18 |  | 2021-03-30 |  | G | [5 empty] | 2021-03-31 |  | 2021-11-30 |  | G | [10 empty] | 2023-02-03 |  | 2023-06-30 |  | G | 2023-09-28 |  | 2024-02-28 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.18858
349 | 106700 | FT EUSTIS INTERCHANGE | 0064 | Interstate | Reconstruction w/ Added Capacity | VDOT | Newport News | WILLIAMSBURG | Hampton Roads | Hampton Roads:Newport News | Infrastructure Investment Division | Janet M Hedrick | Janet.Hedrick@VDOT.Virginia.gov | (757) 956-3071 | Janet M Hedrick | Janet.Hedrick@VDOT.Virginia.gov | (757) 956-3071 |  |  |  | 0 |  | 0 | FY2030 | 180603787 | 180603787 | NO DATES SET YET | G | Start Development milestone is 1424 days ahead of the expected completion date | Y | Estimate not current | [5 empty] | 2025-01-02 |  | 2025-01-15 |  | G | 2025-01-16 |  | 2026-02-27 |  | G | [5 empty] | 2027-02-26 |  | 2027-03-11 |  | G | 2028-06-05 |  | 2028-06-16 |  | G | 2028-11-13 |  | 2029-05-22 |  | G | 2028-07-05 |  | 2029-01-11 |  | G | 2027-11-18 |  | 2028-07-25 |  | G | [5 empty] | 2029-06-12 |  | 2029-06-12 |  | G | 2029-10-01 |  | 2029-10-01 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.091686
350 | 117065 | Pavement Rehabilitation - Various Local Streets |  | Urban | Resurfacing | Locally | Hopewell | PETERSBURG | Richmond | Tri-Cities:Hopewell | Local Assistance Division | James Shepherd | James.Shepherd@vdot.virginia.gov | (804) 609-5305 | James Shepherd | James.Shepherd@vdot.virginia.gov | (804) 609-5305 | TBD |  | TBD | 0 |  | 0 | FY2028 | 1088192 | 1088192 | NO DATES SET YET | G | Agreement with Locality milestone is 1543 days ahead of the expected completion date | G | Project is on budget | 2025-01-06 |  | 2025-05-14 |  | G | 2025-05-15 |  | 2025-06-05 |  | G | 2025-07-07 |  | 2025-10-28 |  | G | [25 empty] | 2026-10-23 |  | 2027-03-30 |  | G | [5 empty] | 2027-05-26 |  | 2027-06-23 |  | G | 2027-09-13 |  | 2027-09-13 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.050623
351 | 117111 | #SGR21VB (FED ID 19706) Br Repl/Rte 643 over Cripple Creek | 0643 | Secondary | Bridge Replacement w/o Added Capacity | VDOT | Wythe County | WYTHEVILLE | Bristol | NonMPO:NonMPO | Infrastructure Investment/Asset Management Division | Gary Lester |  |  | Shane C Morrison | Shane.Morrison@vdot.virginia.gov | (276) 696-3380 |  |  |  | 0 |  | 1 | FY2023 | 2512168 | 2512168 | NO DATES SET YET | G | Start Development milestone is 235 days ahead of the expected completion date | G | Project is on budget | [5 empty] | 2021-10-01 |  | 2021-10-14 |  | G | 2021-10-15 |  | 2021-12-30 |  | G | [35 empty] | 2022-08-09 |  | 2022-08-09 |  | G | 2022-10-31 |  | 2022-10-31 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.066153
352 | 117126 | Route 17 Sidewalk | 0017 | Urban | Facilities for Pedestrians and Bicycles | Locally | York County | WILLIAMSBURG | Hampton Roads | Hampton Roads:York County | Local Assistance Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Keisha Wilkins | Keisha.Wilkins@vdot.virginia.gov | (757) 956-3110 | Timothy Cross | tcross@yorkcounty.gov | 757890349 | 0 |  | 0 | FY2024 | 352232 | 352232 | NO DATES SET YET | R | Agreement with Locality milestone is 72 days past the expected completion date | G | Project is on budget | 2020-08-03 |  | 2020-12-11 |  | R | 2020-12-14 |  | 2021-01-05 |  | R | 2021-07-14 |  | 2021-11-04 |  | G | [10 empty] | 2023-03-03 |  | 2023-04-06 |  | G | [5 empty] | 2023-04-07 |  | 2023-09-05 |  | G | 2023-08-02 |  | 2024-01-04 |  | G | [5 empty] | 2023-12-12 |  | 2024-01-10 |  | G | 2024-04-02 |  | 2024-04-02 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.12283
353 | 117746 | Traffic Calming - Old Wrexham Road | 4880 | Secondary | Traffic Management/Engineering | Locally | Chesterfield County | CHESTERFIELD | Richmond | Richmond:Chesterfield County | Infrastructure Investment Division | Michael S Gray | Mike.Gray@vdot.virginia.gov | (804) 609-5347 | Michael S Gray | Mike.Gray@vdot.virginia.gov | (804) 609-5347 | Nathan Mathis | mathisn@chesterfield.gov | (804) 748-1037 | 0 |  | 0 | FY2023 | 30000 | 30000 | NO DATES SET YET | G | Agreement with Locality milestone finished 465 days early | G | Project is on budget | 2021-12-27 | 2020-10-19 | 2022-05-05 | 2021-01-25 | G | [5 empty] | 2022-05-06 | 2021-01-26 | 2022-05-19 |  | G | [25 empty] | 2022-01-27 |  | 2022-06-24 |  | G | [5 empty] | 2022-08-23 |  | 2022-09-20 |  | G | 2022-12-13 |  | 2022-12-13 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.27052
354 | 118150 | Nuckols Road Pedestrian Improvements | 0157 | Secondary | Facilities for Pedestrians and Bicycles | Locally | Henrico County | ASHLAND | Richmond | Richmond:Henrico County | Infrastructure Investment Division | Douglas L Orcutt | Doug.Orcutt@vdot.virginia.gov | (804) 609-5428 | Douglas L Orcutt | Doug.Orcutt@vdot.virginia.gov | (804) 609-5428 | Conner Barnes | bar136@henrico.us | (804) 501-4244 | 0 |  | 0 | FY2028 | 2160000 | 2160000 | NO DATES SET YET | G | Agreement with Locality milestone is 1179 days ahead of the expected completion date | G | Project is on budget | 2024-01-08 |  | 2024-05-15 |  | G | 2024-05-16 |  | 2024-06-06 |  | G | 2024-12-16 |  | 2025-04-11 |  | G | [10 empty] | 2026-07-31 |  | 2026-09-03 |  | G | [5 empty] | 2026-09-04 |  | 2027-02-10 |  | G | 2027-01-06 |  | 2027-06-07 |  | G | [5 empty] | 2027-05-14 |  | 2027-06-11 |  | G | 2027-08-31 |  | 2027-08-31 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 1 | 0.26526
355 | 118310 | CROSON LANE WIDENING 2 TO 4 LANES | 0645 | Secondary | Reconstruction w/ Added Capacity | Locally | Loudoun County | LEESBURG | Northern Virginia | Northern Virginia:Loudoun County | Local Assistance Division | Kimberly Mccool | Kimberly.McCool@vdot.virginia.gov | (703) 259-3220 | Christer P Carshult | Christer.Carshult@vdot.virginia.gov | (703) 259-1765 | Bob Brown | bob.brown@loudoun.gov | (703) 777-0122 | 0 |  | 0 | FY2030 | 14540400 | 14540400 | NO DATES SET YET | G | Agreement with Locality milestone is 1433 days ahead of the expected completion date | G | Project is on budget | 2024-07-01 |  | 2025-01-24 |  | G | 2025-01-27 |  | 2025-02-14 |  | G | 2025-08-21 |  | 2026-04-29 |  | G | [10 empty] | 2028-07-28 |  | 2028-08-31 |  | G | [5 empty] | 2028-09-01 |  | 2029-03-29 |  | G | 2028-06-29 |  | 2029-03-08 |  | G | [5 empty] | 2029-07-02 |  | 2029-08-27 |  | G | 2029-11-16 |  | 2030-01-16 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.44328
356 | 56454 | CONSTRUCTION OF ROUND HILL-FRANKLIN PARK TRAIL | 0007 | Primary | Facilities for Pedestrians and Bicycles | Locally | Loudoun County | LEESBURG | Northern Virginia | Northern Virginia:Loudoun County | Local Assistance Division | Deepa Thandaveswara | Deepa.Thandaveswara@vdot.virginia.gov | (703) 259-3354 | Veljibhai M Desai | Veljibhai.Desai@vdot.virginia.gov | (703) 259-2927 | Edward del Rio | edward.delrio@loudoun.gov | (571) 258-3990 | 0 |  | 0 | FY2020 | 2001000 | 4220000 | CONSTRUCTION STARTED | R | Start Delivery milestone finished 340 days late | R | Project estimate is less than $5M and is 20% or more over budget | [5 empty] | 2001-01-03 | 2001-02-12 | 2001-01-31 | 2001-02-21 | R | 2013-02-25 | 2013-02-26 | 2013-06-24 | 2013-04-10 | G | [35 empty] | 2019-02-01 | 2019-09-05 | 2019-04-01 | 2019-09-05 | R | 2019-04-01 | 2019-11-05 | 2019-07-01 | 2020-06-05 | R | Delay due to scope of work change/Project Management change/plan or design change | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.35857
357 | 94847 | #HB2.FY17 Add thru lane from I81 to Rt37& lt turn lanes. | 0011 | Primary | Reconstruction w/ Added Capacity | VDOT | Frederick County | EDINBURG | Staunton | Winchester:Frederick County | Infrastructure Investment Division | Heather L Williams | Heather.Williams@VDOT.Virginia.gov | (804) 786-1872 | Robert S Good | Robert.Good@VDOT.Virginia.gov | (540) 743-1420 | Frederick County |  |  | 1 | 2017 | 0 | FY2017 | 2500755 | 2475755 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 32 days early | G | Project is on budget | [5 empty] | 2011-06-01 | 2011-06-30 | 2011-06-30 | 2011-06-30 | G | 2012-04-23 | 2012-04-03 | 2013-02-07 | 2013-08-07 | R | [35 empty] | 2016-10-14 | 2016-11-08 | 2016-11-08 | 2016-11-08 | G | 2017-01-16 | 2017-01-27 | 2017-02-28 | 2017-01-27 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.071517
358 | 102999 | Wythe Creek Road Traffic Signal Upgrade | 0000 | Urban | Traffic Management/Engineering | Locally | Poquoson | WILLIAMSBURG | Hampton Roads | Hampton Roads:Poquoson | Infrastructure Investment Division | Stephen Rowan | Steve.Rowan@vdot.virginia.gov | (757) 790-9925 | Chessica Villaflores | Chessica.Villaflores@vdot.virginia.gov | (757) 956-3094 | Ellen Roberts | Ellen.Roberts@poquoson-va.gov | (757) 868-3025 | 0 |  | 0 | FY2021 | 278000 | 217284 | AWARDED | G | Start Delivery milestone finished 104 days early | G | Project is on budget | 2018-01-03 | 2018-01-03 | 2018-04-20 | 2018-04-20 | G | 2018-04-02 | 2018-04-02 | 2018-04-02 | 2018-04-02 | G | 2018-06-13 | 2018-06-13 | 2019-04-22 | 2019-08-19 | R | [35 empty] | 2020-04-06 | 2020-07-20 | 2020-08-06 | 2020-08-30 | R | 2020-08-07 | 2020-10-09 | 2021-02-03 | 2020-10-22 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.27699
359 | 105990 | OLD COURTHOUSE ROAD SRTS SIDEWALK - FAIRFAX |  | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Fairfax County | FAIRFAX | Northern Virginia | Northern Virginia:Fairfax County | Local Assistance Division | Jeffrey S Daily | Jeff.Daily@VDOT.Virginia.gov | (703) 259-2993 | Rita Hockman | Rita.Hockman@vdot.virginia.gov | (804) 824-7421 | Fairfax County | wesley.minnix@fairfaxcounty.gov | (703) 877-5747 | 0 |  | 0 | FY2021 | 1850000 | 1346468 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 253 days early | G | Project is on budget | 2015-03-18 | 2015-03-18 | 2015-03-18 | 2015-03-18 | G | 2014-10-01 | 2015-04-17 | 2014-10-01 | 2015-04-17 | R | 2014-10-31 | 2014-10-31 | 2015-02-28 | 2015-02-28 | G | [10 empty] | 2018-11-28 | 2018-07-18 | 2018-12-28 | 2018-07-18 | G | [5 empty] | 2018-12-28 | 2018-07-19 | 2020-02-28 | 2019-07-29 | G | [10 empty] | 2020-02-28 | 2019-07-30 | 2020-04-30 | 2019-09-30 | G | 2020-04-30 | 2019-10-01 | 2020-08-28 | 2019-12-19 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.25843
360 | 107177 | ST. CLAIRE LN - ADD SIDEWALK | 9999 | Secondary | Facilities for Pedestrians and Bicycles | Locally | Henrico County | ASHLAND | Richmond | Richmond:Henrico County | Local Assistance Division | Douglas L Orcutt | Doug.Orcutt@vdot.virginia.gov | (804) 609-5428 | Douglas L Orcutt | Doug.Orcutt@vdot.virginia.gov | (804) 609-5428 | TODD EURE | eur@henrico.us | (804) 501-4617 | 0 |  | 0 | FY2021 | 1147000 | 1147000 | ACTIVITY DATES SET | R | Solicit Bids milestone is 870 days past the expected completion date | G | Project is on budget | 2015-07-01 | 2015-07-01 | 2015-09-24 | 2016-02-02 | R | 2015-09-25 | 2016-02-10 | 2015-10-08 | 2016-02-10 | R | 2015-10-09 | 2017-04-10 | 2016-06-08 | 2017-06-15 | R | [10 empty] | 2017-11-16 | 2017-11-23 | 2017-12-01 | 2017-11-28 | G | [20 empty] | 2018-08-13 |  | 2018-10-05 |  | R | 2018-07-02 |  | 2020-07-02 |  | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.35101
361 | 108360 | Huckleberry Trail - Phase 3 | 0000 | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Christiansburg | CHRISTIANSBURG | Salem | New River Valley:Christiansburg | Local Assistance Division | James M Guy | james.guy@vdot.virginia.gov | (540) 387-5247 | Adam J Czesnowski | Adam.Czesnowski@vdot.virginia.gov | (540) 541-1216 | Wayne Nelson | wnelson@christiansburg.org | (540) 382-6120 | 0 |  | 0 | FY2019 | 839505 | 1577500 | CONSTRUCTION COMPLETED | R | Start Delivery milestone finished 2 days late | R | Project estimate is less than $5M and is 20% or more over budget | 2016-03-01 | 2016-08-04 | 2016-05-23 | 2016-10-07 | R | 2016-05-24 | 2016-10-11 | 2016-05-26 | 2016-10-25 | R | 2016-05-27 | 2016-11-22 | 2016-12-05 | 2017-04-03 | R | [35 empty] | 2017-11-02 | 2019-01-14 | 2017-12-04 | 2019-01-17 | R | 2018-09-05 | 2019-01-18 | 2019-03-04 | 2019-03-06 | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.24931
362 | 109264 | TEMPLE AVE AND ROUTE 1 SIGNAL REPLACEMENT | 0001 | Primary | Safety | Locally | Colonial Heights | CHESTERFIELD | Richmond | Tri-Cities:Colonial Heights | Infrastructure Investment Division | Evan Austin | Evan.Austin@vdot.virginia.gov | (804) 609-5384 | Evan Austin | Evan.Austin@vdot.virginia.gov | (804) 609-5384 | Keith A Chisolm | chisolmk@colonialheightsva.gov | (804) 641-9106 | 0 |  | 0 | FY2024 | 1644944 | 1644944 | NO DATES SET YET-PE OPEN | G | Start Development milestone finished 109 days early | G | Project is on budget | 2020-10-01 | 2020-04-13 | 2020-12-30 | 2020-07-29 | G | 2020-12-31 | 2020-07-30 | 2021-01-04 | 2020-09-17 | G | 2021-01-05 |  | 2021-07-12 |  | G | [10 empty] | 2022-06-16 |  | 2022-07-07 |  | G | [5 empty] | 2022-07-11 |  | 2023-04-07 |  | G | [10 empty] | 2023-04-25 |  | 2023-05-22 |  | G | 2023-05-23 |  | 2023-07-03 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.11065
363 | 110880 | PEDESTRIAN SAFETY IMPROVEMENTS WITH HAWKS AND RRFBS |  | Miscellaneous | Safety | Locally | Richmond | ASHLAND | Richmond | Richmond:Richmond | Infrastructure Investment Division | Evan Austin | Evan.Austin@vdot.virginia.gov | (804) 609-5384 | Evan Austin | Evan.Austin@vdot.virginia.gov | (804) 609-5384 | Michael Sawyer | michael.sawyer@richmondgov.com | (804) 646-3435 | 0 |  | 0 | FY2022 | 754581 | 754581 | ACTIVITY DATES SET | G | Engage Public milestone finished 57 days early | G | Project is on budget | 2019-07-01 | 2019-02-19 | 2019-09-24 | 2019-07-09 | G | 2019-09-25 | 2019-07-17 | 2019-09-27 | 2019-07-23 | G | 2019-09-30 | 2019-07-24 | 2020-04-09 | 2020-04-09 | G | 2021-01-29 | 2020-12-03 | 2021-01-29 | 2020-12-03 | G | [20 empty] | 2020-07-20 | 2020-10-23 | 2021-04-30 | 2020-10-23 | G | [5 empty] | 2021-06-30 |  | 2021-06-30 |  | G | 2021-07-01 |  | 2021-12-30 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.0801
364 | 111307 | City of Va Beach - Salem Road Sidewalk |  | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Virginia Beach | NORFOLK | Hampton Roads | Hampton Roads:Virginia Beach | Local Assistance Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Marci Thompson | Marci.Thompson@vdot.virginia.gov | (757) 956-3093 | Katie Shannon, PE | kshannon@vbgov.com | (757) 385-1514 | 0 |  | 0 | FY2021 | 484821 | 484821 | ACTIVITY DATES SET | R | Complete Purchasing Right-of-Way milestone is 142 days past the expected completion date | G | Project is on budget | 2017-10-02 | 2017-10-02 | 2018-01-26 | 2018-01-26 | G | 2018-02-16 | 2018-02-16 | 2018-02-20 | 2018-02-16 | G | 2018-02-21 | 2018-02-20 | 2019-02-21 | 2019-03-12 | R | [10 empty] | 2019-09-10 | 2019-08-07 | 2019-09-30 | 2019-08-30 | G | [5 empty] | 2019-10-02 |  | 2020-10-02 |  | R | [10 empty] | 2020-10-21 |  | 2020-11-25 |  | R | 2021-02-19 |  | 2021-05-14 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.27454
365 | 112547 | Sidewalk and Crosswalk Improvements near Elkton Elementary | 0000 | Urban | Facilities for Pedestrians and Bicycles | VDOT | Elkton | HARRISONBURG | Staunton | NonMPO:NonMPO | Infrastructure Investment Division | Michael S Fulcher | Michael.Fulcher@VDOT.Virginia.gov | (540) 332-2243 | Ronald L Tabor | Ronald.Tabor@vdot.virginia.gov | (540) 332-7887 |  |  |  | 0 |  | 0 | FY2021 | 370525 | 370525 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 441 days early | G | Project is on budget | [5 empty] | 2018-03-15 | 2017-12-04 | 2018-03-28 | 2017-12-08 | G | 2018-03-29 | 2017-12-11 | 2019-02-26 | 2019-02-26 | G | [5 empty] | 2019-09-30 | 2019-04-16 | 2019-10-11 | 2019-04-16 | G | 2019-11-27 | 2019-05-30 | 2019-11-27 | 2019-05-30 | G | 2020-04-13 | 2019-10-08 | 2020-10-14 | 2019-10-08 | G | 2019-12-02 | 2019-06-03 | 2019-12-02 | 2019-06-03 | G | [10 empty] | 2020-11-10 | 2019-10-08 | 2020-11-10 | 2019-10-08 | G | 2020-12-30 | 2019-12-16 | 2021-03-01 | 2019-12-16 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.075434
366 | 113125 | East Atlantic Street Neighborhood Improvement Project | 0000 | Urban | Facilities for Pedestrians and Bicycles | Locally | Emporia | FRANKLIN | Hampton Roads | Hampton Roads:Emporia | Local Assistance Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Marci Thompson | Marci.Thompson@vdot.virginia.gov | (757) 956-3093 | Alton Mason | alton.mason@ci.emporia.va.us | (434) 634-4500 | 0 |  | 0 | FY2021 | 801630 | 801630 | NO DATES SET YET-PE OPEN | R | Determine Requirements milestone is 591 days past the expected completion date | G | Project is on budget | 2018-10-01 | 2018-06-06 | 2018-12-28 | 2018-10-19 | G | 2018-12-31 | 2018-10-22 | 2019-01-03 | 2018-10-30 | G | 2019-01-04 | 2018-10-31 | 2019-07-11 |  | R | [25 empty] | 2019-07-12 | 2019-07-01 | 2020-03-19 | 2019-07-02 | G | [5 empty] | 2020-05-21 |  | 2020-06-18 |  | R | 2020-06-19 |  | 2020-09-04 |  | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.15331
367 | 113248 | ROADWAY RECONSTRUCTION - CITYWIDE | 9999 | Urban | Restoration and Rehabilitation | Locally | Alexandria | FAIRFAX | Northern Virginia | Northern Virginia:Alexandria | Local Assistance Division | Amir Salahshoor | A.Salahshoor@VDOT.Virginia.gov | (703) 259-1957 | Rita Hockman | Rita.Hockman@vdot.virginia.gov | (804) 824-7421 | Mary Alice Winston | maryalice.winston@alexandriava.gov | (703) 746-4267 | 0 |  | 0 | FY2020 | 4017000 | 4017000 | CONSTRUCTION STARTED | G | Start Delivery milestone finished on-time | G | Project is on budget | 2018-10-31 | 2018-09-04 | 2019-03-29 | 2018-10-05 | G | 2019-04-01 | 2018-10-05 | 2019-04-30 | 2018-10-05 | G | 2019-11-04 | 2019-05-24 | 2020-10-30 | 2019-06-28 | G | [25 empty] | 2019-06-20 | 2019-06-20 | 2020-03-02 | 2019-06-20 | G | [5 empty] | 2020-03-03 | 2019-07-18 | 2020-03-16 | 2019-07-18 | G | 2019-07-19 | 2019-07-19 | 2019-07-19 | 2019-07-19 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.23856
368 | 113690 | #SGR19LP - Kempsville Road, Segment 2 | 0190 | Urban | Resurfacing | Locally | Chesapeake | NORFOLK | Hampton Roads | Hampton Roads:Chesapeake | Infrastructure Investment Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Johndel A Alcaide | John.Alcaide@vdot.virginia.gov | (757) 956-3098 | Sam Sawan | sawan@cityofchesapeake.net | (757) 382-8263 | 0 |  | 1 | FY2019 |  |  | WAITING FINANCIAL CLOSURE | G | Solicit Bids milestone finished 11 days early | R | Critical information missing | 2018-09-04 | 2018-07-31 | 2018-11-30 | 2018-09-04 | G | 2018-12-03 | 2018-10-25 | 2018-12-05 | 2018-11-19 | G | 2018-12-06 | 2018-11-20 | 2019-06-13 | 2019-05-30 | G | [35 empty] | 2019-06-10 | 2019-05-29 | 2019-06-10 | 2019-05-30 | G | 2019-06-28 | 2019-05-29 | 2019-06-28 | 2019-05-29 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.11758
369 | 114092 | RTE 460 - SHOULDER WIDENING AND RUMBLE STRIPS (APPOMATTOX) | 0460 | Primary | Safety | VDOT | Appomattox County | APPOMATTOX | Lynchburg | NonMPO:NonMPO | Infrastructure Investment Division | Gerald L Harter | Gerry.Harter@vdot.virginia.gov | (434) 856-8211 | Anthony W Revelle | Anthony.Revelle@vdot.virginia.gov | (434) 856-8258 |  |  |  | 0 |  | 0 | FY2021 | 3100860 | 3100860 | ADVERTISED | G | Solicit Bids milestone finished on-time | G | Project is on budget | [10 empty] | 2020-07-15 | 2020-02-05 | 2020-07-21 | 2020-06-17 | G | [35 empty] | 2020-12-08 | 2020-12-08 | 2020-12-08 | 2020-12-08 | G | 2021-03-04 |  | 2021-05-26 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.10037
370 | 107043 | I-64 WB Exit 296A Ramp Terminal Realignment | 0064 | Interstate | Safety | VDOT | Chesapeake | NORFOLK | Hampton Roads | Hampton Roads:Chesapeake | Infrastructure Investment Division | Emmanuel Eod Ofori-Darko | Emmanuel.Darko@VDOT.Virginia.gov | (757) 956-3261 | John K Arms | John.Arms@vdot.virginia.gov | (757) 995-5156 |  |  |  | 0 |  | 0 | FY2019 | 1180000 | 1132640 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 5 days early | G | Project is on budget | [5 empty] | 2017-08-01 | 2017-08-14 | 2017-08-14 | 2017-08-14 | G | 2017-08-15 | 2017-08-15 | 2018-04-11 | 2018-02-08 | G | [5 empty] | 2018-02-01 | 2018-02-01 | 2018-02-08 | 2018-02-01 | G | [5 empty] | 2018-03-16 | 2018-03-12 | 2018-03-16 | 2018-03-12 | G | [5 empty] | 2018-05-10 | 2018-04-13 | 2018-07-13 | 2018-04-13 | G | [5 empty] | 2018-12-11 | 2018-12-04 | 2018-12-11 | 2018-12-04 | G | 2019-01-30 | 2019-02-22 | 2019-03-27 | 2019-03-22 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.14376
371 | 107515 | CARNATION STREET - ADD SIDEWALK - TAP |  | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Richmond | ASHLAND | Richmond | Richmond:Richmond | Local Assistance Division | Brian J Lokker | Brian.Lokker@VDOT.Virginia.gov | (804) 524-6010 | Brian J Lokker | Brian.Lokker@VDOT.Virginia.gov | (804) 524-6010 | T. Loney, City of Richmond | Todd.Loney@richmondgov.com | (804) 646-0302 | 0 |  | 0 | FY2019 | 600000 | 655625 | CONSTRUCTION COMPLETED | R | Start Delivery milestone finished 189 days late | Y | Project estimate is less than $5M and is up to 20% over budget | 2015-10-01 | 2016-07-22 | 2015-12-30 | 2016-07-22 | R | 2015-10-01 | 2015-10-01 | 2015-10-01 | 2015-10-01 | G | 2016-01-19 | 2017-06-01 | 2016-09-08 | 2017-12-01 | R | [10 empty] | 2017-08-11 | 2017-08-11 | 2018-02-13 | 2017-08-11 | G | [20 empty] | 2017-10-20 | 2017-10-20 | 2018-03-30 | 2018-04-23 | R | 2018-05-16 | 2019-01-31 | 2018-09-14 | 2019-03-22 | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.35337
372 | 109068 | TRENCH WIDEN SHOULDERS AND INSTALL RUMBLE STRIPES - RTE 55 | 0055 | Primary | Safety | VDOT | Warren County | EDINBURG | Staunton | NonMPO:NonMPO | Infrastructure Investment Division | Keith M Rider | Keith.Rider@VDOT.Virginia.gov | (434) 856-8145 | Kunal Kothawade | Kunal.Kothawade@vdot.virginia.gov | (540) 332-9259 |  |  |  | 0 |  | 0 | FY2023 | 2275000 | 2275000 | ACTIVITY DATES SET | G | Engage Public milestone finished 259 days early | G | Project is on budget | [5 empty] | 2019-12-02 | 2020-08-20 | 2019-12-13 | 2020-08-20 | R | 2019-12-16 | 2020-08-21 | 2020-08-06 | 2020-09-30 | R | [5 empty] | 2021-06-17 | 2020-10-01 | 2021-06-17 | 2020-10-01 | G | [5 empty] | 2021-07-21 |  | 2021-07-21 |  | G | [15 empty] | 2022-07-12 |  | 2022-07-15 |  | G | 2022-09-06 |  | 2022-09-26 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.06279
373 | 109297 | #HB2.FY17 MAPLE AVE AND PARK ST SIGNAL RECONSTRUCTION | 0123 | Urban | Traffic Management/Engineering | Locally | Vienna | FAIRFAX | Northern Virginia | Northern Virginia:Vienna | Infrastructure Investment Division | Terry Yates | Terry.Yates@vdot.virginia.gov | (703) 259-2118 | Robert J Strevell | Robert.Strevell@vdot.virginia.gov | (703) 259-1988 | Michael Gallagher | mgallagher@viennava.gov | (703) 255-6386 | 1 | 2017 | 0 | FY2022 | 900000 | 900000 | ACTIVITY DATES SET | G | Complete Purchasing Right-of-Way milestone finished on-time | G | Project is on budget | 2016-06-22 | 2016-06-22 | 2016-12-23 | 2016-12-23 | G | 2016-12-23 | 2016-09-07 | 2017-05-04 | 2016-09-08 | G | 2017-05-05 | 2016-09-09 | 2017-12-08 | 2017-08-14 | G | [10 empty] | 2018-05-17 | 2018-05-17 | 2018-05-24 | 2018-05-24 | G | [5 empty] | 2018-06-25 | 2018-06-25 | 2020-04-17 | 2020-04-17 | G | [10 empty] | 2021-07-01 |  | 2021-10-29 |  | G | 2021-11-01 |  | 2022-03-31 |  | G | Delay due to unforeseen issues with utilities, railroad coordination, or right-of-way acquisition | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.26692
375 | 111739 | ROUTE 600/618 INTERSECTION IMPROVEMENTS | 0600 | Secondary | Safety | VDOT | Fluvanna County | LOUISA | Culpeper | NonMPO:NonMPO | Infrastructure Investment Division | Gregory J Cooley | Gregory.Cooley@vdot.virginia.gov | (434) 906-7979 | James D Cubbage | David.Cubbage@VDOT.Virginia.gov | (540) 727-7129 |  |  |  | 0 |  | 0 | FY2023 | 3900000 | 3900000 | NO DATES SET YET-PE OPEN | R | Determine Requirements milestone is 719 days past the expected completion date | G | Project is on budget | [5 empty] | 2017-11-16 | 2017-11-16 | 2017-11-16 | 2017-11-16 | G | 2018-01-31 | 2018-01-31 | 2019-03-05 |  | R | [5 empty] | 2019-10-29 |  | 2019-11-12 |  | R | 2021-02-19 |  | 2021-03-05 |  | Y | 2021-07-28 |  | 2022-02-07 |  | G | 2021-03-23 |  | 2021-09-23 |  | G | 2020-08-05 |  | 2021-02-15 |  | R | [5 empty] | 2022-02-08 |  | 2022-02-08 |  | G | 2022-05-12 |  | 2022-07-08 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.084676
377 | 113133 | Mountain Breeze Dr & Heartwood Xing Full Depth Reclamation | 0000 | Urban | Reconstruction w/o Added Capacity | Locally | Blacksburg | CHRISTIANSBURG | Salem | New River Valley:Blacksburg | Local Assistance Division | Adam J Czesnowski | Adam.Czesnowski@vdot.virginia.gov | (540) 541-1216 | Adam J Czesnowski | Adam.Czesnowski@vdot.virginia.gov | (540) 541-1216 | Randy Formica | rformica@blacksburg.gov | (540) 961-1121 | 0 |  | 0 | FY2020 | 400000 | 400000 | WAITING FINANCIAL CLOSURE | R | Start Delivery milestone finished 78 days late | G | Project is on budget | 2018-08-01 | 2018-08-01 | 2018-10-25 | 2018-08-21 | G | 2018-10-26 | 2018-08-30 | 2018-10-30 | 2018-08-30 | G | 2018-10-31 | 2018-09-27 | 2019-08-01 | 2018-11-14 | G | [35 empty] | 2019-07-05 | 2019-03-16 | 2019-08-01 | 2019-04-02 | G | 2019-12-30 | 2020-02-25 | 2019-12-30 | 2020-03-17 | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.15953
378 | 113618 | FAIRFAX CITY PRIMARY EXTENSION PAVING FY19 - MAIN STREET | 0236 | Urban | Resurfacing | Locally | Fairfax | FAIRFAX | Northern Virginia | Northern Virginia:Fairfax | Local Assistance Division | Amir Salahshoor | A.Salahshoor@VDOT.Virginia.gov | (703) 259-1957 | Rita Hockman | Rita.Hockman@vdot.virginia.gov | (804) 824-7421 | Peter Millard | peter.millard@fairfaxva.gov | (703) 246-6330 | 0 |  | 0 | FY2019 | 383897 | 383897 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 139 days early | G | Project is on budget | 2018-07-02 | 2018-07-02 | 2018-09-25 | 2018-09-14 | G | [5 empty] | 2018-09-26 | 2018-09-17 | 2018-11-28 | 2018-10-01 | G | [25 empty] | 2018-10-01 | 2018-10-01 | 2018-11-30 | 2018-10-03 | G | [5 empty] | 2018-11-29 | 2018-10-10 | 2018-12-27 | 2018-10-10 | G | 2018-12-28 | 2018-10-10 | 2019-02-26 | 2018-10-10 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.17616
379 | 113997 | ROUTE 1 UPGRADES BETWEEN WILLIAM AND CAROLINE STREETS | 0001 | Primary | Safety | Locally | Fredericksburg | FREDERICKSBURG | Fredericksburg | Fredericksburg:Fredericksburg | Infrastructure Investment Division | Peter A Hedrich | Peter.Hedrich@vdot.virginia.gov | (540) 899-4540 | Anastasia Kapitan | Anastasia.Kapitan@vdot.virginia.gov | (540) 899-4292 | Doug Fawcett |  |  | 0 |  | 0 | FY2023 | 1260000 | 1260000 | NO DATES SET YET-PE OPEN | R | Determine Requirements milestone is 26 days past the expected completion date | G | Project is on budget | 2019-10-07 | 2019-10-07 | 2020-01-07 | 2020-01-07 | G | 2020-07-01 | 2020-07-01 | 2020-07-15 | 2020-07-08 | G | 2020-07-16 |  | 2021-01-26 |  | R | [10 empty] | 2022-01-28 |  | 2022-02-17 |  | G | [5 empty] | 2022-02-22 |  | 2022-11-30 |  | G | 2021-03-04 |  | 2021-11-02 |  | G | [5 empty] | 2022-12-16 |  | 2023-01-18 |  | G | 2023-04-07 |  | 2023-04-07 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.14463
380 | 115271 | BUS 501 - (ID 5545) RESURFACING (RIVERMONT AVE/BOONSBORO RD) | 0501 | Urban | Resurfacing | Locally | Lynchburg | APPOMATTOX | Lynchburg | Lynchburg:Lynchburg | Local Assistance Division | Gregg Allen | Gregg.Allen@vdot.virginia.gov | (434) 426-5575 | Sharon S White | Sharon.White@VDOT.Virginia.gov | (434) 856-8220 | LEE NEWLAND | lee.newland@lynchburgva.gov | (434) 455-3947 | 0 |  | 0 | FY2021 | 480000 | 480000 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 38 days early | G | Project is on budget | 2020-01-31 | 2019-09-02 | 2020-04-24 | 2019-09-19 | G | [5 empty] | 2020-01-31 | 2020-01-31 | 2020-02-13 | 2020-02-13 | G | [35 empty] | 2020-05-12 | 2020-05-12 | 2020-06-09 | 2020-05-20 | G | 2020-08-27 | 2020-07-20 | 2020-08-27 | 2020-07-20 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.075776
381 | 115919 | HSIP HR High-Visibility Backplates | 9999 | Primary | Safety | VDOT | Hampton Roads District-wide |  | Hampton Roads | Hampton Roads:Hampton Roads District-wide | Infrastructure Investment/Asset Management Division | Todd M Halacy | Todd.Halacy@VDOT.Virginia.gov | (757) 956-3010 | Mark S Winslow | Mark.Winslow@VDOT.Virginia.gov | (757) 925-1528 |  |  |  | 0 |  | 0 | FY2020 | 323650 | 323650 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 34 days early | G | Project is on budget | [5 empty] | 2019-09-03 | 2019-09-03 | 2019-12-13 | 2019-12-13 | G | 2019-12-16 | 2019-12-16 | 2020-04-16 | 2020-03-30 | G | [5 empty] | 2020-03-30 | 2020-03-30 | 2020-03-30 | 2020-03-30 | G | [25 empty] | 2020-05-22 | 2020-04-27 | 2020-05-22 | 2020-04-27 | G | 2020-05-26 | 2020-04-28 | 2020-06-01 | 2020-04-28 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | WORK/TASK ORDER | 1 | 0 | 0.083573
382 | 117090 | #REVSH21 S MAIN ST - INTERSECTION IMPROVEMENTS AT RTE 86 | 0293 | Urban | Reconstruction w/o Added Capacity | Locally | Danville | HALIFAX | Lynchburg | Danville:Danville | Local Assistance Division | Gregg Allen | Gregg.Allen@vdot.virginia.gov | (434) 426-5575 | Gregg Allen | Gregg.Allen@vdot.virginia.gov | (434) 426-5575 | BRIAN DUNEVANT | dunevbl@danvilleva.gov | (434) 799-5019 | 0 |  | 0 | FY2025 | 724000 | 724000 | NO DATES SET YET | G | Agreement with Locality milestone is 106 days ahead of the expected completion date | G | Project is on budget | 2021-01-29 |  | 2021-06-07 |  | G | 2021-06-08 |  | 2021-06-28 |  | G | 2022-01-07 |  | 2022-05-03 |  | G | [10 empty] | 2023-08-22 |  | 2023-09-26 |  | G | [5 empty] | 2023-09-27 |  | 2024-03-04 |  | G | 2024-01-30 |  | 2024-06-26 |  | G | [5 empty] | 2024-06-05 |  | 2024-07-02 |  | G | 2024-09-20 |  | 2024-09-20 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.070217
383 | 118062 | Brown's Island Connector- Phase III |  | Urban | Facilities for Pedestrians and Bicycles | Locally | Richmond | ASHLAND | Richmond | Richmond:Richmond | Local Assistance Division | James Shepherd | James.Shepherd@vdot.virginia.gov | (804) 609-5305 | James Shepherd | James.Shepherd@vdot.virginia.gov | (804) 609-5305 | Adel Edward | adel.edward@richmondgov.com | (804) 646-6584 | 0 |  | 0 | FY2024 | 249924 | 249924 | NO DATES SET YET | G | Agreement with Locality milestone is 199 days ahead of the expected completion date | G | Project is on budget | 2021-05-03 |  | 2021-09-08 |  | G | 2021-09-09 |  | 2021-09-29 |  | G | 2022-04-13 |  | 2022-08-04 |  | G | [25 empty] | 2023-08-01 |  | 2024-01-03 |  | G | [5 empty] | 2024-03-05 |  | 2024-04-01 |  | G | 2024-06-19 |  | 2024-06-19 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.16605
384 | 118484 | #SGR21VB - 7th St over I-95 - Super Repl - FED ID 21289 | 9999 | Secondary | Bridge Rehab w/o Added Capacity | VDOT | Richmond | ASHLAND | Richmond | Richmond:Richmond | Infrastructure Investment/Asset Management Division | Anthony S Haverly | Anthony.Haverly@vdot.virginia.gov | (804) 609-5225 | Anthony S Haverly | Anthony.Haverly@vdot.virginia.gov | (804) 609-5225 | Brian Copple | Brian.Copple@richmondgov.com | (804) 646-3639 | 0 |  | 1 | FY2023 | 11117518 | 11117518 | NO DATES SET YET-PE OPEN | G | Start Development milestone finished 34 days early | G | Project is on budget | [5 empty] | 2021-01-04 | 2020-12-19 | 2021-01-26 | 2020-12-23 | G | 2021-01-04 | 2020-12-24 | 2021-06-09 |  | G | [10 empty] | 2021-11-29 |  | 2021-12-03 |  | G | [20 empty] | 2021-12-06 |  | 2021-12-14 |  | G | 2022-06-23 |  | 2022-07-21 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | DESIGN BUILD/PPTA | 0 | 0 | 0.16845
385 | 97735 | Jefferson Street (Rte 625) Pedestrian Improvements | 0055 | Primary | Safety | Locally | Haymarket | MANASSAS | Northern Virginia | Northern Virginia:Prince William County | Infrastructure Investment Division | Amir Salahshoor | A.Salahshoor@VDOT.Virginia.gov | (703) 259-1957 | Veljibhai M Desai | Veljibhai.Desai@vdot.virginia.gov | (703) 259-2927 | Emily Lockhart | elockhart@townofhaymarket.org | (703) 753-2600 | 0 |  | 0 | FY2020 | 499915 | 686854 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 43 days early | R | Project estimate is less than $5M and is 20% or more over budget | [5 empty] | 2011-02-28 | 2011-03-17 | 2011-02-28 | 2011-03-17 | R | 2011-01-12 | 2011-01-12 | 2011-05-12 | 2011-05-12 | G | [10 empty] | 2016-02-04 | 2016-02-04 | 2016-03-18 | 2016-03-18 | G | [20 empty] | 2019-04-30 | 2019-04-30 | 2019-08-30 | 2019-07-12 | G | 2019-09-03 | 2019-11-06 | 2019-12-31 | 2019-11-18 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.17533
386 | 105592 | Norfolk ATMS Phase 4C | 0000 | Urban | Traffic Management/Engineering | Locally | Norfolk | NORFOLK | Hampton Roads | Hampton Roads:Norfolk | Infrastructure Investment Division | Bryant H Porter | Bryant.Porter@VDOT.Virginia.gov | (757) 956-3092 | Joshua D Negovan | Joshua.Negovan@vdot.virginia.gov | (757) 956-3347 | Olga Beltsar, P. E., | Olga.beltsar@norfolk.gov | (757) 664-7304 | 0 |  | 0 | FY2019 | 1742000 | 2525000 | CONSTRUCTION STARTED | R | Start Delivery milestone finished 225 days late | R | Project estimate is less than $5M and is 20% or more over budget | [5 empty] | 2016-07-01 | 2016-07-19 | 2016-07-01 | 2016-08-04 | R | 2016-08-01 | 2016-07-31 | 2016-11-30 | 2016-10-21 | G | [35 empty] | 2018-03-01 | 2018-06-20 | 2018-05-01 | 2018-10-26 | R | 2018-10-04 | 2018-11-29 | 2018-11-05 | 2019-06-18 | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.42008
387 | 108573 | #HB2.FY17 COMMUTER LOT EXPANSION I-95 E OF EXIT 140 | 0095 | Interstate | Other | VDOT | Stafford County | FREDERICKSBURG | Fredericksburg | Fredericksburg:Stafford County | Infrastructure Investment Division | Michelle A Shropshire | Michelle.Shropshire@VDOT.Virginia.gov | (540) 899-4278 | Beau C Hoyt | Beau.Hoyt@vdot.virginia.gov | (804) 317-3326 |  |  |  | 1 | 2017 | 0 | FY2017 | 9719246 |  | CONSTRUCTION STARTED | G | Start Delivery milestone finished on-time | R | Critical information missing | [5 empty] | 2016-04-18 | 2016-04-18 | 2016-04-18 | 2016-04-18 | G | 2016-04-18 | 2016-04-18 | 2016-04-18 | 2016-04-18 | G | [10 empty] | 2016-12-12 | 2016-05-02 | 2016-12-20 | 2016-05-04 | G | [20 empty] | 2016-12-21 | 2016-05-04 | 2016-12-30 | 2016-05-06 | G | 2016-10-19 | 2016-10-19 | 2016-10-19 | 2016-10-19 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | DESIGN BUILD/PPTA | 1 | 0 | 0.066352
388 | 109582 | US 460 Safety Improvements: HSIP | 0460 | Primary | Safety | VDOT | Bedford County | BEDFORD | Salem | NonMPO:NonMPO | Infrastructure Investment Division | Alex H Price | Alex.Price@VDOT.Virginia.gov | (540) 378-5053 | Jeffrey A Echols | Jeff.Echols@VDOT.Virginia.gov | (540) 375-3595 |  |  |  | 0 |  | 0 | FY2021 | 4510000 | 4360000 | AWARDED | R | Start Delivery milestone finished 39 days late | G | Project is on budget | [5 empty] | 2016-07-01 | 2016-07-01 | 2016-07-13 | 2016-07-13 | G | 2016-07-14 | 2016-07-14 | 2018-08-28 | 2018-08-27 | G | [5 empty] | 2019-06-19 | 2019-03-21 | 2019-07-17 | 2019-03-21 | G | [5 empty] | 2019-04-24 | 2019-04-25 | 2020-03-26 | 2019-09-16 | G | [5 empty] | 2019-05-21 | 2019-04-12 | 2020-05-06 | 2019-04-12 | G | [5 empty] | 2020-06-09 | 2020-08-11 | 2020-06-09 | 2020-08-11 | R | 2020-07-30 | 2020-11-02 | 2020-09-24 | 2020-11-02 | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.18966
389 | 110843 | PEDESTRIAN IMPROVEMENTS AT MARY MUMFORD ELEMENTARY SCHOOL |  | Miscellaneous | Safety | Locally | Richmond | ASHLAND | Richmond | Richmond:Richmond | Infrastructure Investment Division | Evan Austin | Evan.Austin@vdot.virginia.gov | (804) 609-5384 | Evan Austin | Evan.Austin@vdot.virginia.gov | (804) 609-5384 | Maritza Feliz-Reyes | Maritza.Reyes@richmondgov.com | (804) 646-6334 | 0 |  | 0 | FY2022 | 175000 | 172116 | ACTIVITY DATES SET | G | Obtained Permits milestone finished 343 days early | G | Project is on budget | 2019-07-01 | 2019-02-19 | 2019-09-24 | 2019-07-09 | G | 2019-09-25 | 2019-07-17 | 2019-09-27 | 2019-07-23 | G | 2019-09-30 | 2019-07-24 | 2020-04-09 | 2020-02-26 | G | [25 empty] | 2020-12-24 | 2020-04-22 | 2021-03-31 | 2020-04-22 | G | [5 empty] | 2021-04-28 |  | 2021-05-25 |  | G | 2021-05-26 |  | 2021-11-18 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.079442
390 | 115105 | #SGR20LP - WEST 29th STREET - Primary Extension Paving |  | Urban | Resurfacing | Locally | Buena Vista | LEXINGTON | Staunton | NonMPO:NonMPO | Local Assistance Division | Susan E Hammond | Susan.Hammond@VDOT.Virginia.gov | (540) 462-6990 | Michael L Branscome | Michael.Branscome@VDOT.Virginia.gov | (540) 332-2377 | City of Buena Vista | troberts@bvcity.org | (540) 261-8607 | 0 |  | 1 | FY2021 | 723897 | 723897 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 6 days early | G | Project is on budget | 2019-08-01 | 2019-08-01 | 2019-10-25 | 2019-09-19 | G | 2019-10-28 | 2019-09-20 | 2019-10-30 | 2019-10-17 | G | 2019-10-31 | 2019-10-18 | 2020-05-11 | 2020-02-19 | G | [25 empty] | 2020-02-20 | 2020-02-20 | 2020-05-13 | 2020-02-20 | G | [5 empty] | 2020-05-29 | 2020-05-29 | 2020-07-10 | 2020-07-10 | G | 2020-09-29 | 2020-09-29 | 2020-11-10 | 2020-11-04 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.062941
391 | 115416 | #SMART20 Shockoe Bottom BRT Station Ped Safety/Streetscape | 9999 | Urban | Facilities for Pedestrians and Bicycles | Locally | Richmond | ASHLAND | Richmond | Richmond:Richmond | Infrastructure Investment Division | Melinda G Baicy | Melinda.Baicy@vdot.virginia.gov | (804) 609-5390 | Melinda G Baicy | Melinda.Baicy@vdot.virginia.gov | (804) 609-5390 | TBD |  |  | 1 | 2020 | 0 | FY2026 | 4900000 | 4900000 | NO DATES SET YET | G | Agreement with Locality milestone is 976 days ahead of the expected completion date | G | Project is on budget | 2023-08-01 |  | 2023-10-25 |  | G | 2023-10-26 |  | 2023-10-30 |  | G | 2023-10-31 |  | 2024-05-09 |  | G | [10 empty] | 2025-03-07 |  | 2025-03-27 |  | G | [5 empty] | 2025-03-31 |  | 2026-01-08 |  | G | 2024-06-17 |  | 2025-02-24 |  | G | [5 empty] | 2026-01-28 |  | 2026-02-25 |  | G | 2026-05-14 |  | 2026-05-14 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.14024
392 | 116846 | WESTERN LANE, PHASE II, RURAL ADDITION |  | Secondary | Reconstruction w/o Added Capacity | Locally | Warren County | EDINBURG | Staunton | NonMPO:NonMPO | Local Assistance Division | Kimberly Cameron | Kim.Cameron@vdot.virginia.gov | (540) 332-7886 | Kimberly Cameron | Kim.Cameron@vdot.virginia.gov | (540) 332-7886 | Bob Childress | rchildress@warrencountyva.net | (540) 636-4600 | 0 |  | 0 | FY2025 | 625000 | 625000 | NO DATES SET YET | G | Agreement with Locality milestone is 107 days ahead of the expected completion date | G | Project is on budget | 2021-02-01 |  | 2021-06-08 |  | G | 2021-06-09 |  | 2021-06-29 |  | G | 2021-07-29 |  | 2021-11-22 |  | G | [25 empty] | 2024-01-04 |  | 2024-06-04 |  | G | [5 empty] | 2024-08-01 |  | 2024-08-28 |  | G | 2024-11-19 |  | 2024-11-19 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.20648
393 | 117155 | #SGR21LP City of Virginia Beach 2003 N Landing Rd | 0165 | Urban | Resurfacing | Locally | Virginia Beach | NORFOLK | Hampton Roads | Hampton Roads:Virginia Beach | Infrastructure Investment/Asset Management Division | Susan Wilson | Susan.Wilson@vdot.virginia.gov | (757) 956-3099 | Marci Thompson | Marci.Thompson@vdot.virginia.gov | (757) 956-3093 | Jimmy Evans | jrevans@vbgov.com | (757) 385-1505 | 0 |  | 1 | FY2022 | 389894 | 389894 | NO DATES SET YET | G | Agreement with Locality milestone is 80 days ahead of the expected completion date | G | Project is on budget | 2021-01-04 |  | 2021-05-12 |  | G | 2021-05-13 |  | 2021-06-03 |  | G | 2021-07-02 |  | 2021-07-30 |  | G | [25 empty] | 2021-07-02 |  | 2021-07-30 |  | G | [5 empty] | 2021-09-28 |  | 2021-10-26 |  | G | 2022-01-21 |  | 2022-01-21 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.065351
394 | 118477 | #SGR21LP - City of Hopewell 509 Oaklawn Bvd | 0036 | Urban | Resurfacing | VDOT | Hopewell | PETERSBURG | Richmond | Tri-Cities:Hopewell | Infrastructure Investment/Asset Management Division | Raymond Chapman | Scott.Chapman@vdot.virginia.gov | (804) 609-5277 | Raymond Chapman | Scott.Chapman@vdot.virginia.gov | (804) 609-5277 |  |  |  | 0 |  | 1 | FY2023 | 332665 | 332665 | NO DATES SET YET | G | Start Development milestone is 190 days ahead of the expected completion date | G | Project is on budget | [5 empty] | 2021-08-17 |  | 2021-08-30 |  | G | 2021-08-31 |  | 2021-11-10 |  | G | [35 empty] | 2022-06-14 |  | 2022-06-14 |  | G | 2022-09-02 |  | 2022-09-02 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.048978
395 | 94723 | RTE. 122 OVER BIG OTTER RIVER (STR. 02602) - BRIDGE REPLAC. | 0122 | Primary | Bridge Replacement w/o Added Capacity | VDOT | Bedford County | BEDFORD | Salem | NonMPO:NonMPO | Infrastructure Investment Division | Anthony T Marshall | Todd.Marshall@VDOT.Virginia.gov | (540) 387-5460 | Anthony L Handy | Tony.Handy@VDOT.Virginia.gov | (540) 352-9050 |  |  |  | 0 |  | 0 | FY2020 | 6019401 | 6766550 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 60 days early | Y | Project estimate is between $5M and $10M and is up to $1M over budget | [5 empty] | 2010-08-02 | 2010-05-27 | 2010-08-31 | 2010-05-27 | G | 2016-06-15 | 2016-06-15 | 2018-03-16 | 2018-03-15 | G | [5 empty] | 2017-08-19 | 2017-08-19 | 2018-03-15 | 2018-03-15 | G | 2018-10-25 | 2019-01-07 | 2018-11-15 | 2019-01-08 | R | 2018-11-30 | 2019-07-10 | 2019-09-09 | 2020-04-13 | R | 2018-11-30 | 2019-03-27 | 2019-09-09 | 2019-08-13 | G | 2018-05-14 | 2019-04-22 | 2019-09-09 | 2019-07-30 | G | [5 empty] | 2019-08-09 | 2019-09-24 | 2019-09-10 | 2019-09-24 | R | 2019-10-17 | 2019-12-16 | 2020-02-14 | 2019-12-16 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.12319
396 | 101287 | DUPUY AVE - MINOR WIDENING | 9020 | Urban | Reconstruction w/o Added Capacity | Locally | Colonial Heights | CHESTERFIELD | Richmond | Tri-Cities:Colonial Heights | Infrastructure Investment Division | Brian J Lokker | Brian.Lokker@VDOT.Virginia.gov | (804) 524-6010 | Brian J Lokker | Brian.Lokker@VDOT.Virginia.gov | (804) 524-6010 | Kieth Chisolm | chisolmk@colonialheightsva.gov | (804) 520-9215 | 0 |  | 0 | FY2019 | 4083000 | 4016401 | CONSTRUCTION STARTED | R | Start Delivery milestone finished 45 days late | G | Project is on budget | 2011-07-20 | 2011-07-21 | 2011-07-21 | 2011-07-21 | G | 2011-09-06 | 2011-09-09 | 2011-09-09 | 2011-09-09 | G | 2012-04-02 | 2011-12-30 | 2013-03-29 | 2013-02-22 | G | [5 empty] | 2013-08-08 | 2013-08-08 | 2013-10-24 | 2013-10-24 | G | 2013-08-19 | 2013-08-19 | 2014-01-14 | 2014-01-14 | G | [20 empty] | 2018-10-02 | 2019-01-12 | 2018-11-02 | 2019-01-25 | R | 2018-11-05 | 2019-01-28 | 2019-02-01 | 2019-03-18 | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.20246
397 | 106496 | ARMY NAVY DR: COMPLETE STREET BIKE/PED IMPROVEMENTS | 6605 | Miscellaneous | Facilities for Pedestrians and Bicycles | Locally | Arlington County | FAIRFAX | Northern Virginia | Northern Virginia:Arlington County | Infrastructure Investment Division | Amir Salahshoor | A.Salahshoor@VDOT.Virginia.gov | (703) 259-1957 | Susie X Lue | Susie.Lue@vdot.virginia.gov | (703) 259-2918 | Jon Lawler | jlawler@arlingtonva.us | (703) 228-3724 | 0 |  | 0 | FY2023 | 14850000 | 14850000 | ACTIVITY DATES SET | R | Determine Requirements milestone finished 470 days late | G | Project is on budget | 2015-02-15 | 2015-02-15 | 2015-07-13 | 2015-07-13 | G | 2015-07-13 | 2015-07-13 | 2015-07-13 | 2015-07-13 | G | 2016-10-13 | 2016-10-13 | 2019-08-21 | 2020-12-03 | R | [5 empty] | 2020-12-04 | 2020-12-09 | 2021-04-29 |  | G | [25 empty] | 2021-08-23 |  | 2022-03-31 |  | G | 2022-04-01 |  | 2022-07-29 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.18564
398 | 109477 | BIKE AND PEDESTRIAN UPGRADES ON LEELAND ROAD | 0626 | Secondary | Facilities for Pedestrians and Bicycles | VDOT | Stafford County | FREDERICKSBURG | Fredericksburg | Fredericksburg:Stafford County | Infrastructure Investment Division | Curtis B Holloway | Curtis.Holloway@vdot.virginia.gov | (540) 374-3367 | Curtis B Holloway | Curtis.Holloway@vdot.virginia.gov | (540) 374-3367 |  |  |  | 0 |  | 0 | FY2023 | 3675756 | 2870378 | ACTIVITY DATES SET | Y | Start Purchasing Right-of-Way milestone is 17 days ahead of the expected completion date and there is a risk of missing this milestone date | G | Project is on budget | [5 empty] | 2017-06-23 | 2017-06-23 | 2017-06-23 | 2017-06-23 | G | 2017-07-12 | 2017-07-12 | 2018-11-20 | 2018-11-20 | G | [5 empty] | 2019-10-16 | 2019-10-04 | 2019-11-14 | 2019-10-31 | G | 2021-02-25 |  | 2021-03-10 |  | Y | 2022-01-28 |  | 2022-07-19 |  | G | 2021-03-26 |  | 2022-03-28 |  | G | 2020-08-07 | 2020-08-04 | 2021-08-09 |  | G | [5 empty] | 2022-08-09 |  | 2022-08-09 |  | G | 2022-10-13 |  | 2022-11-10 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.077739
399 | 110767 | #SMART18 - RTE 15 - CONSTRUCT ROUNDABOUT AT RTE 360 | 0015 | Primary | Safety | VDOT | Charlotte County | DILLWYN | Lynchburg | NonMPO:NonMPO | Infrastructure Investment Division | Brian J Casto | Brian.Casto@VDOT.Virginia.gov | (434) 856-8276 | Anthony W Revelle | Anthony.Revelle@vdot.virginia.gov | (434) 856-8258 |  |  |  | 1 | 2018 | 0 | FY2023 | 5217268 | 5217268 | ACTIVITY DATES SET | G | Engage Public milestone finished on-time | G | Project is on budget | [5 empty] | 2019-07-15 | 2019-06-25 | 2019-07-26 | 2019-07-03 | G | 2019-07-29 | 2019-07-05 | 2020-03-20 | 2020-02-27 | G | [5 empty] | 2020-12-22 | 2020-12-22 | 2021-01-06 | 2021-01-06 | G | 2021-11-29 |  | 2021-12-10 |  | G | 2022-05-10 |  | 2022-11-14 |  | G | 2021-12-29 |  | 2022-07-06 |  | G | [10 empty] | 2022-12-13 |  | 2022-12-13 |  | G | 2023-03-02 |  | 2023-05-24 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.098373
401 | 111542 | CITY OF FAIRFAX PRIMARY EXTENSION PAVING FY18 - RTE 123NB | 0123 | Urban | Resurfacing | Locally | Fairfax | FAIRFAX | Northern Virginia | Northern Virginia:Fairfax | Local Assistance Division | Amir Salahshoor | A.Salahshoor@VDOT.Virginia.gov | (703) 259-1957 | Rita Hockman | Rita.Hockman@vdot.virginia.gov | (804) 824-7421 | Wendy Sanford | wendy.sanford@fairfaxva.gov | (703) 385-7889 | 0 |  | 0 | FY2019 | 142962 | 142962 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 140 days early | G | Project is on budget | 2017-07-03 | 2017-07-03 | 2017-10-25 | 2017-07-03 | G | [5 empty] | 2017-07-03 | 2017-11-09 | 2017-07-17 | 2017-12-12 | R | [35 empty] | 2017-12-13 | 2017-12-13 | 2018-06-29 | 2018-03-23 | G | 2018-07-02 | 2018-03-23 | 2018-08-10 | 2018-03-23 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.17527
402 | 111938 | RTE 522 S Commerce Ave. Primary Extension Paving | 0522 | Urban | Reconstruction w/o Added Capacity | Locally | Front Royal | EDINBURG | Staunton | NonMPO:NonMPO | Local Assistance Division | Steven K Damron | Steven.Damron@VDOT.Virginia.gov | (804) 786-1172 | Steven K Damron | Steven.Damron@VDOT.Virginia.gov | (804) 786-1172 | Terry Lewis | tlewis@frontroyalva.com | (540) 635-7819 | 0 |  | 0 | FY2019 | 196880 | 196880 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 374 days early | G | Project is on budget | 2017-08-28 | 2017-08-10 | 2017-11-22 | 2017-08-30 | G | 2017-11-27 | 2017-08-31 | 2017-11-29 | 2017-08-31 | G | 2017-11-30 | 2017-09-01 | 2018-06-07 | 2017-09-08 | G | [35 empty] | 2018-07-23 | 2017-09-18 | 2018-08-17 | 2017-09-18 | G | 2018-08-20 | 2017-09-19 | 2018-09-28 | 2017-09-19 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.12066
403 | 112985 | BOXLEY LANE - MILLING, PAVING & RECONSTRUCTION | 9999 | Urban | Resurfacing | Locally | Orange | LOUISA | Culpeper | NonMPO:NonMPO | Local Assistance Division | Ken Connors |  |  | Bobby J Jenkins | Bobby.JenkinsJr@VDOT.Virginia.gov | (540) 829-7694 | JOHN COOLEY | townplanner@townoforange.org | (540) 672-6917 | 0 |  | 0 | FY2019 | 230472 | 230472 | WAITING FINANCIAL CLOSURE | G | Obtained Permits milestone finished 4 days early | G | Project is on budget | 2019-02-21 | 2018-07-01 | 2019-05-15 | 2018-07-09 | G | [5 empty] | 2019-02-21 | 2018-07-10 | 2019-03-06 | 2018-12-05 | G | [25 empty] | 2018-03-01 | 2019-03-01 | 2019-03-05 | 2019-03-01 | G | [5 empty] | 2018-12-15 | 2018-12-01 | 2019-01-04 | 2019-01-03 | G | 2019-01-05 | 2019-01-05 | 2019-02-01 | 2019-02-01 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.048103
404 | 113308 | Primary Extension - Lee Hwy FKEY 1201 | 0000 | Urban | Resurfacing | Locally | Radford | CHRISTIANSBURG | Salem | NonMPO:NonMPO | Local Assistance Division | Adam J Czesnowski | Adam.Czesnowski@vdot.virginia.gov | (540) 541-1216 | Adam J Czesnowski | Adam.Czesnowski@vdot.virginia.gov | (540) 541-1216 | Basil Edwards | basil.edwards@radfordva.gov | (540) 731-3603 | 0 |  | 0 | FY2019 | 32326 | 32326 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 246 days early | G | Project is on budget | 2018-10-01 | 2018-08-01 | 2018-12-28 | 2018-09-13 | G | 2018-12-31 | 2018-09-14 | 2019-01-03 | 2018-09-18 | G | 2019-01-04 | 2018-10-01 | 2019-03-22 | 2018-10-02 | G | [35 empty] | 2018-12-03 | 2018-10-09 | 2018-12-31 | 2018-10-09 | G | 2019-05-28 | 2018-10-10 | 2019-06-28 | 2018-10-25 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.06606
405 | 115063 | Route 60 (Ruthers Rd-Stonebridge Plaza Ave) Shared-Use Path | 0060 | Primary | Facilities for Pedestrians and Bicycles | Locally | Chesterfield County | CHESTERFIELD | Richmond | Richmond:Chesterfield County | Infrastructure Investment Division | Cynthia Crouch | Cynthia.Crouch@vdot.virginia.gov | (804) 609-5313 | Cynthia Crouch | Cynthia.Crouch@vdot.virginia.gov | (804) 609-5313 | Bill Arel | ArelB@chesterfield.gov | (804) 748-1998 | 0 |  | 0 | FY2023 | 5504000 | 5504000 | NO DATES SET YET-PE OPEN | R | Determine Requirements milestone is 290 days past the expected completion date | G | Project is on budget | 2019-07-01 | 2019-05-03 | 2019-09-24 | 2019-10-23 | R | 2019-10-07 | 2019-10-24 | 2019-10-28 | 2019-10-31 | R | 2019-10-29 | 2019-11-01 | 2020-05-07 |  | R | [5 empty] | 2021-07-14 |  | 2021-08-24 |  | G | 2021-05-11 |  | 2021-06-01 |  | G | 2023-05-18 |  | 2023-10-09 |  | G | 2021-06-03 |  | 2022-03-17 |  | G | 2020-06-26 |  | 2021-03-05 |  | Y | [5 empty] | 2022-04-11 |  | 2022-05-06 |  | G | 2022-08-05 |  | 2022-08-05 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.14158
406 | 115275 | BUS 29 - (ID 5416) RESURFACING (MEMORIAL DRIVE) | 0029 | Urban | Resurfacing | Locally | Danville | HALIFAX | Lynchburg | Danville:Danville | Local Assistance Division | Sharon S White | Sharon.White@VDOT.Virginia.gov | (434) 856-8220 | Sharon S White | Sharon.White@VDOT.Virginia.gov | (434) 856-8220 | Brian Dunevant | dunevbl@danvilleva.gov | (434) 799-5019 | 0 |  | 0 | FY2020 | 109000 | 109000 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 93 days early | G | Project is on budget | 2020-01-31 | 2019-07-01 | 2020-04-24 | 2019-09-20 | G | [5 empty] | 2020-01-31 | 2019-09-23 | 2020-02-13 | 2020-01-28 | G | [25 empty] | 2020-01-29 | 2020-01-30 | 2020-02-11 | 2020-01-30 | G | [5 empty] | 2020-01-29 | 2020-02-03 | 2020-02-26 | 2020-02-03 | G | 2020-05-14 | 2020-02-11 | 2020-05-14 | 2020-02-11 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.050026
407 | 115351 | #SMART20 Portsmouth Railroad Crossing Message Signs |  | Urban | Rail/Highway Crossing | Locally | Portsmouth | NORFOLK | Hampton Roads | Hampton Roads:Portsmouth | Infrastructure Investment Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Marci Thompson | Marci.Thompson@vdot.virginia.gov | (757) 956-3093 | James Wright | wrightj@portsmouthva.gov | (757) 383-8592 | 1 | 2020 | 0 | FY2024 | 773699 | 773699 | NO DATES SET YET | G | Agreement with Locality milestone is 215 days ahead of the expected completion date | G | Project is on budget | 2021-07-01 |  | 2021-09-24 |  | G | 2021-09-27 |  | 2021-10-08 |  | G | 2021-10-11 |  | 2022-09-27 |  | G | [25 empty] | 2022-05-27 |  | 2023-02-03 |  | G | [5 empty] | 2023-10-17 |  | 2023-11-14 |  | G | 2024-02-08 |  | 2024-02-08 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.18166
408 | 116155 | #I81CIP NB MM 19.2 DECEL LANE (ID #2) | 0081 | Interstate | Reconstruction w/o Added Capacity | VDOT | Abingdon | ABINGDON | Bristol | Bristol:Abingdon | Infrastructure Investment Division | Donald A Necessary | Donald.Necessary@VDOT.Virginia.gov | (276) 696-3285 | Marvin E Holley | Gene.Holley@VDOT.Virginia.gov | (276) 696-3255 |  |  |  | 0 |  | 0 | FY2022 | 1600000 | 1600000 | ACTIVITY DATES SET | G | Complete Purchasing Right-of-Way milestone finished 9 days early | G | Project is on budget | [5 empty] | 2020-07-01 | 2020-01-31 | 2020-07-15 | 2020-02-03 | G | 2020-07-16 | 2020-02-04 | 2021-06-14 | 2020-06-24 | G | [5 empty] | 2020-07-06 | 2020-06-25 | 2020-07-17 | 2020-07-09 | G | 2020-11-05 | 2020-10-27 | 2020-11-05 | 2020-10-27 | G | 2020-09-10 | 2020-09-01 | 2020-09-10 | 2020-09-01 | G | 2020-11-06 | 2020-10-28 | 2020-11-06 | 2020-10-28 | G | [10 empty] | 2021-05-11 |  | 2021-05-17 |  | G | 2021-08-06 |  | 2021-08-06 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.090022
409 | 116803 | ITTF HIGH SPEED COMMUNICATIONS ARTERIALS - NORTHWEST | 9999 | Miscellaneous | Traffic Management/Engineering | VDOT | Statewide |  | Statewide | NonMPO:NonMPO | Infrastructure Investment Division | Catherine C Mcghee | Cathy.McGhee@VDOT.Virginia.gov | (434) 293-1973 | Steven K Damron | Steven.Damron@VDOT.Virginia.gov | (804) 786-1172 |  |  |  | 0 |  | 0 | FY2021 | 490000 | 490000 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 14 days early | G | Project is on budget | [10 empty] | 2020-04-13 | 2020-04-13 | 2020-08-18 | 2020-08-18 | G | [35 empty] | 2020-09-04 | 2020-09-04 | 2020-10-09 | 2020-10-29 | R | 2020-10-12 | 2020-10-30 | 2020-11-24 | 2020-11-10 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | WORK/TASK ORDER | 1 | 1 | 0.25875
410 | 110863 | INSTALL RETRO-REFLECTIVE BACK PLATES -- DISTRICTWIDE | 9999 | Primary | Safety | VDOT | Fredericksburg District-wide |  | Fredericksburg | Fredericksburg:Fredericksburg District-wide | Infrastructure Investment Division | Jessica Graves | Jessica.Graves@vdot.virginia.gov | (540) 899-4267 | Jessica Graves | Jessica.Graves@vdot.virginia.gov | (540) 899-4267 |  |  |  | 0 |  | 0 | FY2022 | 1625000 | 1625000 | NO DATES SET YET | G | Start Development milestone is 222 days ahead of the expected completion date | G | Project is on budget | [5 empty] | 2021-10-01 |  | 2021-10-01 |  | G | 2021-10-04 |  | 2022-02-16 |  | G | [5 empty] | 2022-01-18 |  | 2022-01-31 |  | G | [25 empty] | 2022-02-16 |  | 2022-02-23 |  | G | 2022-02-24 |  | 2022-03-02 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | WORK/TASK ORDER | 0 | 0 | 0.068034
411 | 111304 | #SMART18 - RTE 29 - DYNAMIC FLASHERS AT RTE 151 | 6029 | Primary | Safety | VDOT | Amherst County | APPOMATTOX | Lynchburg | NonMPO:NonMPO | Infrastructure Investment Division | Craig Manges |  |  | Spencer Hall | Spencer.Hall@vdot.virginia.gov | (434) 471-1157 |  |  |  | 1 | 2018 | 0 | FY2018 | 195489 | 195489 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 24 days early | G | Project is on budget | [5 empty] | 2017-07-17 | 2017-07-07 | 2017-07-17 | 2017-07-07 | G | 2017-07-18 | 2017-07-10 | 2017-11-27 | 2017-10-06 | G | [5 empty] | 2017-10-27 | 2017-10-11 | 2017-10-30 | 2017-10-11 | G | [25 empty] | 2017-11-27 | 2017-11-01 | 2017-12-01 | 2017-11-02 | G | 2017-12-04 | 2017-11-03 | 2017-12-08 | 2017-11-14 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | WORK/TASK ORDER | 1 | 0 | 0.097904
412 | 111651 | #SGR18LB - REPAIR SUPERSTRUCTURE BEAVER CREEK(19974 FED.ID.) | 0000 | Urban | Bridge Rehab w/o Added Capacity | Locally | Bristol | ABINGDON | Bristol | Bristol:Bristol | Infrastructure Investment Division | Tabitha H Crowder | Tabitha.Crowder@vdot.virginia.gov | (276) 696-3482 | Kenneth R Plummer | KR.Plummer@VDOT.Virginia.gov | (276) 696-3261 | Wallace McCulloch |  |  | 0 |  | 1 | FY2021 | 279609 | 279609 | ACTIVITY DATES SET | R | Solicit Bids milestone is 25 days past the expected completion date | G | Project is on budget | 2017-10-31 | 2017-10-31 | 2018-01-31 | 2018-01-31 | G | 2018-05-08 | 2018-05-08 | 2018-05-08 | 2018-05-08 | G | 2018-05-09 | 2018-05-09 | 2019-07-22 | 2021-02-08 | R | [35 empty] | 2020-11-18 |  | 2021-01-27 |  | R | 2021-01-28 |  | 2021-03-10 |  | Y |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.16118
413 | 112890 | Route 29 and Woodbrook Intersection Modification | 0029 | Primary | Safety | VDOT | Albemarle County | CHARLOTTESVILLE | Culpeper | Charlottesville:Albemarle County | Infrastructure Investment Division | Ken Connors |  |  | Rowes Hanna | Rowes.Hanna@vdot.virginia.gov | (540) 727-7054 |  |  |  | 0 |  | 0 | FY2019 | 3852 | 3852 | CONSTRUCTION STARTED | R | Start Delivery milestone finished 37 days late | G | Project is on budget | [5 empty] | 2018-09-04 | 2018-05-24 | 2018-09-04 | 2018-05-31 | G | 2018-09-05 | 2018-09-10 | 2018-12-17 | 2018-12-17 | G | [5 empty] | 2018-12-18 | 2018-12-18 | 2019-01-02 | 2019-01-02 | G | [25 empty] | 2019-01-22 | 2019-03-08 | 2019-01-28 | 2019-03-12 | R | 2019-01-29 | 2019-03-13 | 2019-02-04 | 2019-03-13 | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | WORK/TASK ORDER | 1 | 1 | 0.35172
414 | 113113 | Resurfacing N. Lee Highway (Rt. 11) - Primary Extension | 0011 | Urban | Resurfacing | Locally | Lexington | LEXINGTON | Staunton | NonMPO:NonMPO | Local Assistance Division | Susan E Hammond | Susan.Hammond@VDOT.Virginia.gov | (540) 462-6990 | Michael L Branscome | Michael.Branscome@VDOT.Virginia.gov | (540) 332-2377 | Jeffrey A. Martone | jmartone@lexingtonva.gov | (540) 463-3154 | 0 |  | 1 | FY2019 | 445831 | 445831 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished on-time | G | Project is on budget | 2019-04-02 | 2018-11-01 | 2019-06-25 | 2019-01-30 | G | 2019-06-26 | 2019-02-04 | 2019-06-28 | 2019-02-06 | G | 2019-07-01 | 2019-02-07 | 2020-01-08 | 2019-03-20 | G | [35 empty] | 2019-03-26 | 2019-03-26 | 2019-03-27 | 2019-03-27 | G | 2019-03-28 | 2019-03-28 | 2019-03-28 | 2019-03-28 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.062497
415 | 113784 | RTE 633 - RURAL RUSTIC RD (SURFACE TREAT NON-HARDSURFACE RD) | 0633 | Secondary | Reconstruction w/o Added Capacity | VDOT | Albemarle County | CHARLOTTESVILLE | Culpeper | NonMPO:NonMPO | Infrastructure Investment Division | Ken Connors |  |  | Harold L Jones | Harold.Jones@VDOT.virginia.gov | (434) 422-9378 |  |  |  | 0 |  | 0 | FY2025 | 300000 | 300000 | NO DATES SET YET | G | Start Development milestone is 600 days ahead of the expected completion date | G | Project is on budget | [5 empty] | 2022-10-03 |  | 2022-10-14 |  | G | 2022-10-18 |  | 2023-06-13 |  | G | [5 empty] | 2024-02-22 |  | 2024-04-03 |  | G | [5 empty] | 2024-07-18 |  | 2024-11-08 |  | G | [5 empty] | 2024-07-02 |  | 2024-10-02 |  | G | [5 empty] | 2024-11-12 |  | 2024-11-12 |  | G | 2025-02-07 |  | 2025-02-07 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | SAAP CONTRACT | 0 | 0 | 0.15629
416 | 115136 | #SMART20 13th Street and Rosser Avenue Roundabout |  | Urban | Reconstruction w/o Added Capacity | Locally | Waynesboro | HARRISONBURG | Staunton | SAW:Waynesboro | Infrastructure Investment Division | Randolph S Kiser | Randy.Kiser@VDOT.Virginia.gov | (540) 332-9092 | Michael S Fulcher | Michael.Fulcher@VDOT.Virginia.gov | (540) 332-2243 | Waynesboro City | woodtd@ci.waynesboro.va.us | (540) 942-6694 | 1 | 2020 | 0 | FY2027 | 578937 | 578937 | NO DATES SET YET | G | Agreement with Locality milestone is 976 days ahead of the expected completion date | G | Project is on budget | 2023-08-01 |  | 2023-10-25 |  | G | 2023-10-26 |  | 2023-10-30 |  | G | 2023-10-31 |  | 2024-05-09 |  | G | [10 empty] | 2025-05-09 |  | 2025-05-30 |  | G | [5 empty] | 2025-06-03 |  | 2026-03-17 |  | G | 2024-06-17 |  | 2025-02-24 |  | G | [5 empty] | 2026-04-02 |  | 2026-04-29 |  | G | 2026-07-20 |  | 2026-07-20 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.093922
417 | 115276 | RTE 129 - (ID 5483) RESURFACING (NORTH MAIN STREET) | 0129 | Urban | Resurfacing | Locally | South Boston | HALIFAX | Lynchburg | NonMPO:NonMPO | Local Assistance Division | Gregg Allen | Gregg.Allen@vdot.virginia.gov | (434) 426-5575 | Sharon S White | Sharon.White@VDOT.Virginia.gov | (434) 856-8220 | C. W. CROWDER | ccrowder@southbostonva.us | (434) 575-4261 | 0 |  | 0 | FY2021 | 500001 | 500001 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 99 days early | Y | Estimate not current | 2020-01-31 | 2019-09-02 | 2020-04-24 | 2019-09-19 | G | [5 empty] | 2020-01-31 | 2020-01-31 | 2020-02-13 | 2020-02-13 | G | [35 empty] | 2020-05-12 | 2020-05-12 | 2020-06-09 | 2020-05-15 | G | 2020-08-27 | 2020-05-18 | 2020-08-27 | 2020-05-20 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.052395
418 | 115415 | #SMART20 - Rt 1 (Falling Ck. Wayside - Food Lion) Bike/Ped | 0001 | Primary | Facilities for Pedestrians and Bicycles | Locally | Chesterfield County | CHESTERFIELD | Richmond | Richmond:Chesterfield County | Infrastructure Investment Division | Michael S Gray | Mike.Gray@vdot.virginia.gov | (804) 609-5347 | Michael S Gray | Mike.Gray@vdot.virginia.gov | (804) 609-5347 | Barb Smith | smithbk@chesterfield.gov | (804) 748-1037 | 1 | 2020 | 0 | FY2027 | 3331242 | 3331242 | NO DATES SET YET-PE OPEN | G | Start Development milestone finished 1277 days early | G | Project is on budget | 2023-10-30 | 2020-03-30 | 2024-01-30 | 2020-07-22 | G | 2024-01-31 | 2020-07-23 | 2024-02-02 | 2020-08-04 | G | 2024-02-05 | 2020-08-05 | 2024-08-07 |  | G | [10 empty] | 2025-06-04 |  | 2025-06-24 |  | G | 2022-11-21 |  | 2023-02-27 |  | G | 2025-06-26 |  | 2026-04-09 |  | G | 2024-09-13 |  | 2025-05-21 |  | G | [5 empty] | 2026-04-27 |  | 2026-05-22 |  | G | 2026-08-12 |  | 2026-08-12 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.13716
419 | 116165 | #I81CIP SB MM 84.3 EXTEND DECEL LANE (ID #12) | 0081 | Interstate | Reconstruction w/o Added Capacity | VDOT | Wythe County | WYTHEVILLE | Bristol | NonMPO:NonMPO | Infrastructure Investment Division | Donald A Necessary | Donald.Necessary@VDOT.Virginia.gov | (276) 696-3285 | Marvin E Holley | Gene.Holley@VDOT.Virginia.gov | (276) 696-3255 |  |  |  | 0 |  | 0 | FY2022 | 2300000 | 1800000 | ACTIVITY DATES SET | G | Obtained Permits milestone finished 291 days early | G | Project is on budget | [5 empty] | 2020-07-01 | 2020-01-02 | 2020-07-15 | 2020-01-09 | G | 2020-07-16 | 2020-01-10 | 2021-03-12 | 2020-07-22 | G | [5 empty] | 2021-03-01 | 2020-07-28 | 2021-03-01 | 2020-07-28 | G | [5 empty] | 2021-04-23 | 2020-08-31 | 2021-04-23 | 2020-08-31 | G | [5 empty] | 2021-06-18 | 2020-10-21 | 2021-09-20 | 2020-12-03 | G | [5 empty] | 2021-12-14 |  | 2021-12-14 |  | G | 2022-03-10 |  | 2022-03-10 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.085741
420 | 117161 | #SGR21LP 131-City of Chesapeake 1621 Kempsville Rd EB | 0190 | Urban | Resurfacing | Locally | Chesapeake | NORFOLK | Hampton Roads | Hampton Roads:Chesapeake | Infrastructure Investment/Asset Management Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Johndel A Alcaide | John.Alcaide@vdot.virginia.gov | (757) 956-3098 | Sam Sawan | ssawan@cityofchesapeake.net | (757) 382-8263 | 0 |  | 1 | FY2022 | 403220 | 403220 | NO DATES SET YET | G | Agreement with Locality milestone is 80 days ahead of the expected completion date | G | Project is on budget | 2021-01-04 |  | 2021-05-12 |  | G | 2021-05-13 |  | 2021-06-03 |  | G | 2021-07-02 |  | 2021-08-04 |  | G | [25 empty] | 2021-07-08 |  | 2021-08-04 |  | G | [5 empty] | 2021-10-01 |  | 2021-10-29 |  | G | 2022-01-26 |  | 2022-01-26 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.081188
421 | 17817 | WIDEN BUSINESS ROUTE 23 TO FOUR LANES | 0023 | Urban | Reconstruction w/ Added Capacity | VDOT | Wise | WISE | Bristol | NonMPO:NonMPO | Infrastructure Investment Division | Steven B Buston | Steven.Buston@VDOT.Virginia.gov | (276) 696-3269 | James M Bullins | James.Bullins@VDOT.Virginia.gov | (276) 696-3349 |  |  |  | 0 |  | 0 | FY2022 | 10444001 | 10444000 | ACTIVITY DATES SET | Y | Relocate Utilities milestone is 16 days ahead of the expected completion date and there is a risk of missing this milestone date | G | Project is on budget | [5 empty] | 1997-08-01 | 1997-07-29 | 1997-08-29 | 1997-08-29 | G | 1998-09-01 | 1997-07-30 | 2017-12-20 | 2017-12-11 | G | [5 empty] | 2018-12-19 | 2018-12-19 | 2019-01-03 | 2019-01-03 | G | 2020-03-26 | 2020-03-26 | 2020-04-08 | 2020-04-08 | G | 2020-09-01 |  | 2021-03-09 |  | Y | 2020-04-24 |  | 2021-07-27 |  | G | 2019-10-04 | 2019-01-07 | 2021-06-01 |  | G | [5 empty] | 2021-06-10 |  | 2021-11-09 |  | G | 2021-12-22 |  | 2022-01-11 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.11804
422 | 81548 | 606-010-6016_Bridge Superstructure Replacment_Fed Id 03062 | 0606 | Secondary | Bridge Rehab w/o Added Capacity | VDOT | Bland County | WYTHEVILLE | Bristol | NonMPO:NonMPO | Infrastructure Investment Division | Matthew B Cox | Matthew.Cox@VDOT.Virginia.gov | (276) 696-3281 | John E Sproles | John.Sproles@VDOT.Virginia.gov | (276) 696-3391 |  |  |  | 0 |  | 0 | FY2020 | 724590 | 751870 | CONSTRUCTION COMPLETED | R | Start Delivery milestone finished 53 days late | Y | Project estimate is less than $5M and is up to 20% over budget | [5 empty] | 2010-04-26 | 2008-06-05 | 2015-07-01 | 2008-06-05 | G | 2013-11-12 | 2013-11-12 | 2017-08-01 | 2017-08-01 | G | [35 empty] | 2019-02-28 | 2019-06-11 | 2019-04-09 | 2019-06-11 | R | 2019-04-09 | 2019-08-23 | 2019-07-01 | 2019-08-23 | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 1 | 0.23272
423 | 97555 | I-81 BRIDGE PROJECT ROUTE 11 PE ONLY #17478 PE CN #17480 | 0081 | Interstate | Bridge Replacement w/o Added Capacity | VDOT | Smyth County | ABINGDON | Bristol | NonMPO:NonMPO | Infrastructure Investment Division | Conrad Hill | Conrad.Hill@vdot.virginia.gov | (804) 773-0170 | Jason A Graham | Jason.Graham@vdot.virginia.gov | (276) 696-3383 |  |  |  | 0 |  | 0 | FY2019 | 13819725 | 15075514 | CONSTRUCTION STARTED | R | Start Delivery milestone finished 30 days late | Y | Project estimate is greater than $10M and is over budget by (a) up to 10% or (b) up to $5M | [5 empty] | 2013-07-03 | 2013-07-03 | 2013-08-07 | 2013-08-07 | G | 2015-01-29 | 2015-01-29 | 2016-02-01 | 2016-02-01 | G | [35 empty] | 2018-08-22 | 2018-08-22 | 2018-08-27 | 2018-08-27 | G | 2019-02-20 | 2019-03-22 | 2019-02-20 | 2019-03-22 | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | DESIGN BUILD/PPTA | 1 | 0 | 0.068087
424 | 105099 | #HB2.FY17 Clifton Forge Business Park Access Road |  | Urban | New Construction Roadway | Locally | Clifton Forge | LEXINGTON | Staunton | NonMPO:NonMPO | Infrastructure Investment Division | Michael S Fulcher | Michael.Fulcher@VDOT.Virginia.gov | (540) 332-2243 | Michael S Fulcher | Michael.Fulcher@VDOT.Virginia.gov | (540) 332-2243 | Darlene Burcham | dlburcham@cliftonforgeva.gov | (540) 863-2500 | 1 | 2017 | 0 | FY2017 | 2078914 | 2078910 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 18 days early | G | Project is on budget | [5 empty] | 2013-07-31 | 2013-07-01 | 2013-07-31 | 2013-07-31 | G | 2014-10-31 | 2014-10-31 | 2014-12-16 | 2014-12-16 | G | [35 empty] | 2016-11-15 | 2016-11-15 | 2016-12-30 | 2017-01-07 | R | 2017-01-31 | 2017-01-31 | 2017-03-31 | 2017-03-13 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.10584
425 | 105898 | #SGR17VB - BR REHAB AT FEATHERBED LANE OVER CATOCTIN CREEK | 0673 | Secondary | Bridge Rehab w/ Added Capacity | VDOT | Loudoun County | LEESBURG | Northern Virginia | Northern Virginia:Loudoun County | Infrastructure Investment/Asset Management Division | Gary Runco | Gary.Runco@vdot.virginia.gov | (703) 259-3341 | Yusaf M Masud | Yusaf.Masud@vdot.virginia.gov | (703) 259-2973 |  |  |  | 0 |  | 1 | FY2021 | 4500000 | 4500000 | AWARDED | G | Start Delivery milestone finished 155 days early | G | Project is on budget | [10 empty] | 2017-02-28 | 2017-02-28 | 2018-01-25 | 2018-01-25 | G | [25 empty] | 2017-02-28 | 2017-02-28 | 2017-03-01 | 2017-03-01 | G | [5 empty] | 2021-02-09 | 2020-09-08 | 2021-02-09 | 2020-09-08 | G | 2021-04-01 | 2020-11-17 | 2021-04-21 | 2020-11-17 | G | Final design is still underway | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.12703
426 | 107797 | #HB2.FY17 RTE 95 - EXTEND NB ACCEL LANE AT BELVIDERE ST | 0095 | Interstate | Reconstruction w/o Added Capacity | VDOT | Richmond | ASHLAND | Richmond | Richmond:Richmond | Infrastructure Investment Division | Lawrence Ramsey | Brian.Ramsey@VDOT.Virginia.gov | (804) 585-3579 | Lawrence Ramsey | Brian.Ramsey@VDOT.Virginia.gov | (804) 585-3579 |  |  |  | 1 | 2017 | 0 | FY2021 | 5783000 | 3506576 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 34 days early | G | Project is on budget | [5 empty] | 2015-09-01 | 2015-08-18 | 2015-09-01 | 2015-08-18 | G | 2015-08-18 | 2015-08-18 | 2017-01-20 | 2017-01-17 | G | [5 empty] | 2017-05-08 | 2017-05-08 | 2017-05-16 | 2017-05-16 | G | 2018-04-06 | 2018-04-16 | 2018-04-20 | 2018-04-20 | G | 2019-05-21 | 2019-06-12 | 2020-05-06 | 2019-07-10 | G | 2018-05-07 | 2018-05-01 | 2019-04-23 | 2019-03-22 | G | [10 empty] | 2020-06-14 | 2020-05-05 | 2020-06-14 | 2020-05-05 | G | 2020-08-04 | 2020-07-21 | 2020-08-24 | 2020-07-21 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.083022
427 | 108643 | N. Parham Road construct sidewalk | 9999 | Secondary | Facilities for Pedestrians and Bicycles | Locally | Henrico County | ASHLAND | Richmond | Richmond:Henrico County | Local Assistance Division | Douglas L Orcutt | Doug.Orcutt@vdot.virginia.gov | (804) 609-5428 | Douglas L Orcutt | Doug.Orcutt@vdot.virginia.gov | (804) 609-5428 | Todd Eure | eur@henrico.us | (804) 501-4617 | 0 |  | 0 | FY2020 | 720000 | 720000 | ACTIVITY DATES SET | R | Solicit Bids milestone is 415 days past the expected completion date | G | Project is on budget | 2017-04-05 | 2016-07-01 | 2017-06-28 | 2016-10-18 | G | 2017-06-29 | 2016-10-28 | 2017-07-03 | 2016-12-14 | G | 2017-07-05 | 2017-08-02 | 2018-01-11 | 2017-09-07 | G | [10 empty] | 2019-01-15 | 2018-02-05 | 2019-02-06 | 2018-02-09 | G | [5 empty] | 2019-02-08 | 2018-03-05 | 2019-11-15 | 2020-09-14 | R | [10 empty] | 2019-12-05 |  | 2020-01-03 |  | R | 2020-01-06 |  | 2020-02-18 |  | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.34871
428 | 109304 | #HB2.FY17 Little Back River Road Reconstruction |  | Urban | Reconstruction w/o Added Capacity | Locally | Hampton | WILLIAMSBURG | Hampton Roads | Hampton Roads:Hampton | Local Assistance Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Derrick Williams | Derrick.Williams@vdot.virginia.gov | (757) 956-3097 | Sandon Rogers, P.E. | Sandon.rogers@hampton.gov | (757) 727-6786 | 1 | 2017 | 0 | FY2024 | 9270000 | 9270000 | ACTIVITY DATES SET | G | Determine Requirements milestone finished 35 days early | G | Project is on budget | 2019-05-01 | 2019-05-01 | 2019-07-25 | 2019-05-29 | G | 2019-07-26 | 2019-05-30 | 2019-07-30 | 2019-06-25 | G | 2019-07-31 | 2019-06-26 | 2020-07-30 | 2020-06-25 | G | [10 empty] | 2021-07-09 |  | 2021-07-29 |  | G | [5 empty] | 2021-08-04 |  | 2022-05-17 |  | G | [10 empty] | 2023-05-19 |  | 2023-06-30 |  | G | 2023-07-03 |  | 2023-11-08 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.20221
429 | 109438 | #HB2.FY17 - US58/23 Access Management With Park & Ride | 0058 | Primary | Reconstruction w/o Added Capacity | VDOT | Scott County | WISE | Bristol | Kingsport:Scott County | Infrastructure Investment Division | Allan D Sumpter | Allan.Sumpter@VDOT.virginia.gov | (276) 525-6461 | James R Jones | jamesr.jones@vdot.virginia.gov | (276) 696-3257 |  |  |  | 1 | 2017 | 0 | FY2021 | 7105471 | 5181458 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 51 days early | G | Project is on budget | [5 empty] | 2016-08-01 | 2016-08-01 | 2016-08-25 | 2016-08-25 | G | 2016-08-15 | 2016-08-15 | 2017-05-19 | 2017-05-18 | G | [5 empty] | 2018-02-20 | 2018-02-20 | 2018-03-05 | 2018-02-27 | G | 2019-04-23 | 2019-03-21 | 2019-05-06 | 2019-04-03 | G | 2019-09-27 | 2019-09-20 | 2020-04-22 | 2020-04-13 | G | 2019-05-22 | 2019-04-15 | 2020-04-09 | 2020-04-03 | G | 2018-10-04 | 2018-10-02 | 2019-10-04 | 2019-11-18 | R | [5 empty] | 2020-07-14 | 2020-06-09 | 2020-07-14 | 2020-06-09 | G | 2020-08-27 | 2020-09-02 | 2020-10-23 | 2020-09-02 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.089474
430 | 116944 | PEDESTRIAN CONNECTOR - PHASE II |  | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Chilhowie | ABINGDON | Bristol | NonMPO:NonMPO | Local Assistance Division | John W Bechtold | John.Bechtold@vdot.virginia.gov | (276) 696-3365 | Kenneth R Plummer | KR.Plummer@VDOT.Virginia.gov | (276) 696-3261 | John Clark | chilhowie.townmgr@chilhowie.org | (276) 646-3232 | 0 |  | 0 | FY2025 | 487334 | 487334 | NO DATES SET YET | G | Agreement with Locality milestone finished 91 days early | G | Project is on budget | 2020-12-01 | 2020-12-01 | 2021-04-12 | 2021-01-11 | G | 2021-04-13 |  | 2021-05-03 |  | G | 2021-11-08 |  | 2022-03-09 |  | G | [10 empty] | 2023-06-27 |  | 2023-08-01 |  | G | [5 empty] | 2023-08-02 |  | 2024-01-04 |  | G | 2023-11-30 |  | 2024-05-01 |  | G | [5 empty] | 2024-04-10 |  | 2024-05-07 |  | G | 2024-07-26 |  | 2024-07-26 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.24782
431 | 118373 | #SGR21LB Rt 166 over NS Railway-Bridge Repl-FED ID 21881 | 0166 | Urban | Bridge Replacement w/o Added Capacity | Locally | Chesapeake | NORFOLK | Hampton Roads | Hampton Roads:Chesapeake | Infrastructure Investment/Asset Management Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Johndel A Alcaide | John.Alcaide@vdot.virginia.gov | (757) 956-3098 | Sam Sawan | ssawan@cityofchesapeake.net | (757) 382-8263 | 0 |  | 1 | FY2027 | 20573000 | 20573000 | NO DATES SET YET | G | Agreement with Locality milestone is 260 days ahead of the expected completion date | G | Project is on budget | 2021-07-01 |  | 2021-11-08 |  | G | 2021-11-09 |  | 2021-12-02 |  | G | 2022-06-13 |  | 2023-02-17 |  | G | [10 empty] | 2025-05-19 |  | 2025-06-23 |  | G | [5 empty] | 2025-06-24 |  | 2026-01-15 |  | G | 2025-03-24 |  | 2025-11-21 |  | G | [5 empty] | 2026-04-22 |  | 2026-05-19 |  | G | 2026-08-07 |  | 2026-08-07 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.14136
432 | 59175 | AIR TERMINAL INTERCHANGE - INTERMODAL CONNECTOR | 0564 | Urban | New Construction Roadway | VDOT | Norfolk | NORFOLK | Hampton Roads | Hampton Roads:Norfolk | Infrastructure Investment Division | Frank F Fabian | Frank.Fabian@VDOT.Virginia.gov | (757) 272-9203 | Frank F Fabian | Frank.Fabian@VDOT.Virginia.gov | (757) 272-9203 |  |  |  | 0 |  | 0 | FY2023 | 169543968 | 169543968 | NO DATES SET YET-PE OPEN | R | Determine Requirements milestone is 662 days past the expected completion date | G | Project is on budget | [5 empty] | 2014-08-22 | 2014-08-22 | 2014-09-08 | 2014-09-08 | G | 2018-12-04 | 2018-12-04 | 2019-05-01 |  | R | [10 empty] | 2019-12-02 |  | 2020-01-31 |  | R | [10 empty] | 2019-12-03 |  | 2020-12-01 |  | R | [5 empty] | 2022-07-29 |  | 2022-09-13 |  | G | 2022-11-10 |  | 2022-11-10 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.1056
433 | 82849 | #HB2.FY17 RTE 460 AND RTE 629/630 INTERSECTION PROJECT | 0630 | Secondary | Safety | VDOT | Prince George County | PETERSBURG | Richmond | Tri-Cities:Prince George County | Infrastructure Investment Division | Susan Warr | Susan.Warr@VDOT.Virginia.gov | (804) 720-5478 | Susan Warr | Susan.Warr@VDOT.Virginia.gov | (804) 720-5478 |  |  |  | 1 | 2017 | 0 | FY2020 | 3119085 | 2746967 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 102 days early | G | Project is on budget | [5 empty] | 2007-02-23 | 2007-05-04 | 2007-02-23 | 2007-05-04 | R | 2016-09-02 | 2016-08-29 | 2017-03-16 | 2017-03-27 | R | [5 empty] | 2017-08-02 | 2017-08-02 | 2017-08-07 | 2017-08-07 | G | 2018-07-09 | 2018-07-09 | 2018-07-16 | 2018-07-16 | G | 2019-04-18 | 2019-03-20 | 2019-12-20 | 2019-04-29 | G | 2018-09-25 | 2018-11-06 | 2019-04-01 | 2019-02-21 | G | 2019-04-09 | 2019-04-18 | 2019-09-19 | 2019-04-18 | G | [5 empty] | 2020-01-14 | 2019-11-05 | 2020-01-14 | 2019-11-05 | G | 2020-03-10 | 2020-01-20 | 2020-05-01 | 2020-01-20 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.094185
434 | 102985 | Westhaven Bicycle Improvements | 0000 | Urban | Facilities for Pedestrians and Bicycles | Locally | Portsmouth | NORFOLK | Hampton Roads | Hampton Roads:Portsmouth | Infrastructure Investment Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Marci Thompson | Marci.Thompson@vdot.virginia.gov | (757) 956-3093 | James E. Wright, Jr. | wrightj@portsmouthva.gov | (757) 393-8592 | 0 |  | 0 | FY2022 | 500000 | 500000 | ACTIVITY DATES SET | G | Obtained Permits milestone finished 148 days early | G | Project is on budget | [5 empty] | 2018-07-02 | 2019-01-08 | 2018-09-25 | 2019-01-22 | R | 2019-04-24 | 2019-02-01 | 2020-04-23 | 2020-07-15 | R | 2020-11-17 | 2020-11-17 | 2020-12-31 | 2020-12-22 | G | [20 empty] | 2021-01-07 | 2021-01-11 | 2021-06-08 | 2021-01-11 | G | [5 empty] | 2021-07-22 |  | 2021-09-01 |  | G | 2021-09-21 |  | 2022-03-18 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.1833
435 | 105624 | #SGR18LB - Ft Eustis Boulevard BR Replacemt over NN Resevoir | 0105 | Urban | Bridge Replacement w/o Added Capacity | Locally | Newport News | WILLIAMSBURG | Hampton Roads | Hampton Roads:Newport News | Local Assistance Division | Stephen Rowan | Steve.Rowan@vdot.virginia.gov | (757) 790-9925 | Chessica Villaflores | Chessica.Villaflores@vdot.virginia.gov | (757) 956-3094 | Carolyn Bowman | bowmancd@nnva.gov | (757) 926-3667 | 0 |  | 1 | FY2020 | 24000000 | 24000000 | CONSTRUCTION STARTED | R | Start Delivery milestone finished 93 days late | G | Project is on budget | [5 empty] | 2014-10-01 | 2015-03-24 | 2014-10-01 | 2015-03-30 | R | 2014-10-31 | 2017-09-21 | 2015-02-28 | 2017-09-21 | R | [35 empty] | 2018-01-02 | 2020-02-05 | 2019-08-01 | 2020-03-10 | R | 2019-08-02 | 2020-05-01 | 2020-01-29 | 2020-05-01 | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.37447
436 | 107659 | Hamilton Pedestrian Improvements |  | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Loudoun County | LEESBURG | Northern Virginia | Northern Virginia:Loudoun County | Local Assistance Division | Amir Salahshoor | A.Salahshoor@VDOT.Virginia.gov | (703) 259-1957 | Veljibhai M Desai | Veljibhai.Desai@vdot.virginia.gov | (703) 259-2927 | Mayor Dave Simpson | drs755@gmail.com | (540) 338-2811 | 0 |  | 0 | FY2019 | 422472 | 768342 | CONSTRUCTION COMPLETED | R | Start Delivery milestone finished 358 days late | R | Project estimate is less than $5M and is 20% or more over budget | 2015-10-01 | 2015-10-01 | 2015-12-30 | 2015-11-02 | G | 2015-12-31 | 2016-05-06 | 2016-01-14 | 2016-05-06 | R | 2016-01-19 | 2015-11-19 | 2016-09-08 | 2017-01-30 | R | [10 empty] | 2018-04-18 | 2018-05-01 | 2018-05-01 | 2018-05-01 | G | [20 empty] | 2018-06-05 | 2019-06-13 | 2018-09-26 | 2019-07-18 | R | 2018-09-27 | 2019-07-19 | 2018-09-27 | 2019-09-20 | R | Delay due to changes in scope of work, project management, plan designs, or resolution of public comments | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.48733
437 | 108447 | ROADWAY DEPARTURE CRASH MITIGATION - NOVA | 0000 | Primary | Safety | VDOT | Northern Virginia District-wide |  | Northern Virginia | Northern Virginia:Northern Virginia District-wide | Infrastructure Investment Division | Ivan M Horodyskyj | Ivan.Horodyskyj@VDOT.Virginia.gov | (703) 259-2330 | Mehrdad Naderi | Mehrdad.Naderi@vdot.virginia.gov | (703) 259-2217 |  |  |  | 0 |  | 0 | FY2019 | 625000 | 641000 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 407 days early | Y | Project estimate is less than $5M and is up to 20% over budget | [5 empty] | 2016-02-19 | 2016-02-19 | 2016-05-24 | 2016-05-24 | G | 2017-01-25 | 2017-01-25 | 2017-01-26 | 2017-01-26 | G | [5 empty] | 2017-01-24 | 2017-01-24 | 2017-01-24 | 2017-01-24 | G | [5 empty] | 2017-01-24 | 2017-01-24 | 2017-01-24 | 2017-01-24 | G | [15 empty] | 2017-05-09 | 2017-05-09 | 2018-06-12 | 2017-05-09 | G | 2018-08-02 | 2017-07-11 | 2018-08-22 | 2017-07-11 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.068166
438 | 108647 | RTE 1703 (McRae Rd, Rockaway Rd-Forest Hill Ave) - SIDEWALK | 1703 | Secondary | Facilities for Pedestrians and Bicycles | Locally | Chesterfield County | CHESTERFIELD | Richmond | Richmond:Chesterfield County | Local Assistance Division | Michael S Gray | Mike.Gray@vdot.virginia.gov | (804) 609-5347 | Michael S Gray | Mike.Gray@vdot.virginia.gov | (804) 609-5347 | Chessa Faulkner | faulknerc@chesterfield.gov | (804) 748-1037 | 0 |  | 0 | FY2021 | 2500000 | 3375000 | ACTIVITY DATES SET | R | Complete Purchasing Right-of-Way milestone is 487 days past the expected completion date | R | Project estimate is less than $5M and is 20% or more over budget | 2017-01-31 | 2016-10-07 | 2017-04-25 | 2016-10-07 | G | 2017-04-26 | 2016-10-12 | 2017-04-28 | 2016-10-12 | G | 2017-05-01 | 2016-11-09 | 2017-11-02 | 2018-01-30 | R | [10 empty] | 2018-12-20 | 2019-10-28 | 2019-01-11 | 2019-12-03 | R | 2020-09-01 |  | 2021-02-26 |  | Y | 2019-01-15 | 2019-12-13 | 2019-10-23 |  | R | [10 empty] | 2019-11-08 |  | 2020-11-30 |  | R | 2020-12-01 |  | 2021-02-26 |  | Y |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.28363
439 | 109317 | #HB2.FY17 RTE 6 - INSTALL SIGNAL | 0006 | Primary | Safety | VDOT | Goochland County | ASHLAND | Richmond | Richmond:Goochland County | Infrastructure Investment Division | Robert W Alexander | Robert.Alexander@VDOT.Virginia.gov | (804) 609-5332 | Ronnie Hobson | Ron.Hobson@vdot.virginia.gov | (804) 840-5501 |  |  |  | 1 | 2017 | 0 | FY2020 | 869815 | 869815 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 376 days early | G | Project is on budget | [5 empty] | 2016-10-14 | 2016-10-14 | 2016-10-17 | 2016-10-17 | G | 2016-10-17 | 2016-10-17 | 2017-09-14 | 2017-07-12 | G | [5 empty] | 2017-10-30 | 2017-11-01 | 2017-11-08 | 2017-11-06 | G | 2017-12-01 | 2017-12-01 | 2018-01-11 | 2018-01-11 | G | 2018-07-10 | 2018-03-02 | 2018-07-10 | 2018-03-02 | G | 2018-09-06 | 2018-05-10 | 2019-02-04 | 2018-05-10 | G | [10 empty] | 2019-05-14 | 2018-07-10 | 2019-05-14 | 2018-07-11 | G | 2019-07-03 | 2018-07-11 | 2019-07-22 | 2018-07-11 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | WORK/TASK ORDER | 1 | 0 | 0.064735
440 | 109829 | #HB2.FY17 RTE 58- LEFT & RIGHT TURN LANES AT RTE 311 | 0058 | Primary | Safety | VDOT | Danville | HALIFAX | Lynchburg | Danville:Danville | Infrastructure Investment Division | Brian J Casto | Brian.Casto@VDOT.Virginia.gov | (434) 856-8276 | Lindsey S Hodges | Lindsey.Hodges@vdot.virginia.gov | (434) 856-8143 |  |  |  | 1 | 2017 | 0 | FY2021 | 3393452 | 2875105 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 306 days early | G | Project is on budget | [5 empty] | 2017-07-03 | 2017-07-07 | 2017-07-17 | 2017-07-07 | G | 2017-07-18 | 2017-07-10 | 2018-06-14 | 2017-08-04 | G | [5 empty] | 2018-06-28 | 2018-04-04 | 2018-07-12 | 2018-04-17 | G | 2019-08-05 | 2018-11-15 | 2019-08-23 | 2018-11-21 | G | 2020-03-24 | 2019-04-08 | 2020-09-24 | 2019-12-11 | G | 2019-09-11 | 2018-12-06 | 2020-03-23 | 2019-04-23 | G | 2019-01-29 | 2018-07-09 | 2020-01-29 | 2019-05-23 | G | [5 empty] | 2020-10-13 | 2019-12-10 | 2020-10-13 | 2019-12-10 | G | 2020-12-08 | 2020-02-27 | 2020-12-29 | 2020-02-27 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.076448
441 | 111002 | #SGR18LB - Triple Decker Bridge - Upper Level |  | Urban | Bridge Rehab w/o Added Capacity | Locally | Chesapeake | NORFOLK | Hampton Roads | Hampton Roads:Chesapeake | Infrastructure Investment Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Johndel A Alcaide | John.Alcaide@vdot.virginia.gov | (757) 956-3098 | Earl Sorey, PE |  | (757) 382-6101 | 0 |  | 1 | FY2022 | 5110040 | 5110040 | NO DATES SET YET-PE OPEN | Y | Determine Requirements milestone is 8 days ahead of the expected completion date and there is a risk of missing this milestone date | G | Project is on budget | 2020-05-08 | 2018-01-29 | 2020-08-03 | 2018-04-23 | G | 2020-08-04 | 2020-01-31 | 2020-08-17 | 2020-02-03 | G | 2020-08-18 |  | 2021-03-01 |  | Y | [25 empty] | 2021-03-02 | 2020-09-16 | 2021-10-29 | 2020-10-14 | G | [5 empty] | 2022-01-07 |  | 2022-02-07 |  | G | 2022-04-27 |  | 2022-04-27 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.30879
442 | 111702 | #SMART18 - US60 / Downtown Expy Gateway Ped Improvements | 0060 | Urban | Safety | Locally | Richmond | ASHLAND | Richmond | Richmond:Richmond | Infrastructure Investment Division | Olena Fecek | Olena.Fecek@vdot.virginia.gov | (804) 524-6368 | Olena Fecek | Olena.Fecek@vdot.virginia.gov | (804) 524-6368 | Yongping Wang | yongping.wang@richmondgov.com | (804) 646-2467 | 1 | 2018 | 0 | FY2021 | 3308614 | 3308613 | NO DATES SET YET-PE OPEN | R | Determine Requirements milestone is 318 days past the expected completion date | G | Project is on budget | 2019-07-01 | 2019-02-21 | 2019-09-24 | 2019-08-07 | G | 2019-09-25 | 2019-09-26 | 2019-09-27 | 2019-10-15 | R | 2019-09-30 | 2019-10-16 | 2020-04-09 |  | R | [25 empty] | 2021-06-04 |  | 2022-02-10 |  | G | [5 empty] | 2021-02-19 |  | 2021-03-19 |  | Y | 2021-03-22 |  | 2021-04-29 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.13133
443 | 113617 | MANASSAS CITY PRIMARY EXTENSION PAVING FY19 - DUMFRIES ROAD | 0234 | Urban | Resurfacing | Locally | Manassas | MANASSAS | Northern Virginia | Northern Virginia:Manassas | Local Assistance Division | Amir Salahshoor | A.Salahshoor@VDOT.Virginia.gov | (703) 259-1957 | Rita Hockman | Rita.Hockman@vdot.virginia.gov | (804) 824-7421 | Steve Burke | sburke@ci.manassas.va.us | (703) 257-8476 | 0 |  | 0 | FY2019 | 160846 | 160846 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 128 days early | G | Project is on budget | 2018-07-02 | 2018-07-02 | 2018-09-25 | 2018-10-12 | R | [5 empty] | 2018-09-26 | 2018-10-16 | 2018-11-28 | 2018-10-16 | G | [35 empty] | 2018-11-26 | 2018-10-15 | 2018-12-21 | 2018-10-16 | G | 2018-12-24 | 2018-10-16 | 2019-02-21 | 2018-10-16 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.094307
444 | 113893 | Appalachian Trail Crossing | 9999 | Secondary | Safety | VDOT | Smyth County | ABINGDON | Bristol | NonMPO:NonMPO | Infrastructure Investment Division | Conrad Hill | Conrad.Hill@vdot.virginia.gov | (804) 773-0170 | Jeremy J Mullins | Jeremy.Mullins@vdot.virginia.gov | (276) 696-3259 |  |  |  | 0 |  | 0 | FY2025 | 140000 | 140000 | NO DATES SET YET | G | Start Development milestone is 600 days ahead of the expected completion date | Y | Estimate not current | [5 empty] | 2022-10-03 |  | 2022-10-14 |  | G | 2022-10-18 |  | 2023-06-13 |  | G | [5 empty] | 2024-02-22 |  | 2024-04-03 |  | G | [5 empty] | 2024-07-18 |  | 2024-11-08 |  | G | [5 empty] | 2024-07-02 |  | 2024-10-02 |  | G | [5 empty] | 2024-11-12 |  | 2024-11-12 |  | G | 2025-02-07 |  | 2025-02-07 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.076802
446 | 115738 | RTE 262 NORTH BOUND WIDENING SAFETY IMPROVEMENTS | 0262 | Primary | Reconstruction w/ Added Capacity | VDOT | Augusta County | HARRISONBURG | Staunton | SAW:Augusta County | Infrastructure Investment Division | Donald F Komara | Donald.Komara@VDOT.Virginia.gov | (540) 434-2587 | David Robinson | David.Robinson@vdot.virginia.gov | (540) 332-7758 |  |  |  | 0 |  | 0 | FY2024 | 4446437 | 4446437 | NO DATES SET YET-PE OPEN | R | Determine Requirements milestone is 269 days past the expected completion date | G | Project is on budget | [5 empty] | 2019-06-17 | 2020-08-03 | 2019-06-28 | 2020-08-14 | R | 2019-07-01 | 2020-08-17 | 2020-05-28 |  | R | [5 empty] | 2021-04-05 |  | 2021-04-16 |  | G | 2022-07-22 |  | 2022-08-04 |  | G | 2023-01-03 |  | 2023-07-10 |  | G | 2022-08-22 |  | 2023-03-03 |  | G | 2022-01-10 |  | 2022-07-15 |  | G | [5 empty] | 2023-07-11 |  | 2023-07-11 |  | G | 2023-09-29 |  | 2023-09-29 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.092278
447 | 116833 | Visitor/Destination Center-High Knob Access Enhancements | 0018 | Miscellaneous | Facilities for Pedestrians and Bicycles | Locally | Norton | WISE | Bristol | NonMPO:NonMPO | Local Assistance Division | Kenneth R Plummer | KR.Plummer@VDOT.Virginia.gov | (276) 696-3261 | Kenneth R Plummer | KR.Plummer@VDOT.Virginia.gov | (276) 696-3261 | Fred Ramey | fredr@nortonva.org | (276) 679-1160 | 0 |  | 0 | FY2024 | 1859600 | 1859600 | NO DATES SET YET-PE OPEN | G | Start Development milestone finished 141 days early | G | Project is on budget | 2020-06-10 | 2020-04-29 | 2020-10-15 | 2020-04-29 | G | 2020-10-16 | 2020-05-21 | 2020-11-06 | 2020-06-18 | G | 2021-05-20 |  | 2021-09-13 |  | G | [25 empty] | 2022-09-08 |  | 2023-02-13 |  | G | [5 empty] | 2023-04-12 |  | 2023-05-09 |  | G | 2023-07-28 |  | 2023-07-28 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.13248
448 | 116963 | #SGR21LP ROUTE 340 PRIMARY EXTENSION PAVING |  | Primary | Resurfacing | VDOT | Luray | HARRISONBURG | Staunton | NonMPO:NonMPO | Infrastructure Investment Division | Joel D Denunzio | Joel.DeNunzio@VDOT.virginia.gov | (540) 332-9093 | Mark W Hisey | Mark.Hisey@VDOT.Virginia.gov | (540) 280-4820 |  |  |  | 0 |  | 1 | FY2021 | 60428 | 60428 | ACTIVITY DATES SET | Y | Solicit Bids milestone is 51 days ahead of the expected completion date and there is a risk of missing this milestone date | G | Project is on budget | [5 empty] | 2021-01-11 | 2020-11-03 | 2021-02-02 | 2020-11-24 | G | 2021-02-03 | 2020-11-25 | 2021-12-03 | 2021-01-11 | G | [5 empty] | 2021-01-12 | 2021-01-12 | 2021-01-12 | 2021-01-12 | G | [5 empty] | 2020-12-28 | 2021-01-14 | 2021-04-12 | 2021-01-19 | G | [15 empty] | 2021-04-13 |  | 2021-04-13 |  | Y | 2021-06-30 |  | 2021-06-30 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.060468
449 | 117772 | INSTALL GUARDRAIL - ROUTE 82 RUSSELL CO | 0082 | Primary | Safety | VDOT | Russell County | LEBANON | Bristol | NonMPO:NonMPO | Infrastructure Investment Division | Brian Holt | Brian.Holt@vdot.virginia.gov | (276) 696-3414 | Jeremy J Mullins | Jeremy.Mullins@vdot.virginia.gov | (276) 696-3259 |  |  |  | 0 |  | 0 | FY2023 | 11856 | 11856 | NO DATES SET YET-PE OPEN | G | Start Development milestone finished 7 days early | G | Project is on budget | [5 empty] | 2020-07-07 | 2020-07-07 | 2020-07-27 | 2020-07-20 | G | 2020-07-28 | 2020-07-21 | 2021-06-01 |  | G | [5 empty] | 2022-01-03 |  | 2022-02-01 |  | G | [5 empty] | 2022-09-21 |  | 2023-01-27 |  | G | [5 empty] | 2022-06-15 |  | 2022-11-14 |  | G | [5 empty] | 2023-02-14 |  | 2023-02-14 |  | G | 2023-05-04 |  | 2023-05-04 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | REGIONAL ON-CALL CONTRACT | 0 | 0 | 0.060853
450 | 109516 | ROUTE 711 - CROSSOVER MOVEMENT CONVERSION | 0711 | Secondary | Safety | VDOT | Spotsylvania County | FREDERICKSBURG | Fredericksburg | Fredericksburg:Spotsylvania County | Infrastructure Investment Division | Curtis B Holloway | Curtis.Holloway@vdot.virginia.gov | (540) 374-3367 | Curtis B Holloway | Curtis.Holloway@vdot.virginia.gov | (540) 374-3367 |  |  |  | 0 |  | 0 | FY2022 | 1433000 | 1957450 | ACTIVITY DATES SET | G | Obtained Permits milestone finished 7 days early | R | Project estimate is less than $5M and is 20% or more over budget | [5 empty] | 2017-10-02 | 2017-07-11 | 2017-10-16 | 2017-07-11 | G | 2017-10-17 | 2017-07-12 | 2018-09-13 | 2018-08-08 | G | [5 empty] | 2019-04-09 | 2019-03-19 | 2019-06-04 | 2019-05-31 | G | 2020-06-03 | 2020-04-28 | 2020-06-17 | 2020-06-03 | G | 2021-04-26 |  | 2022-01-06 |  | G | 2020-07-06 | 2020-06-23 | 2021-04-23 |  | G | 2019-12-30 | 2019-12-30 | 2020-12-29 | 2020-12-22 | G | [5 empty] | 2022-01-11 |  | 2022-01-11 |  | G | 2022-04-11 |  | 2022-06-06 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.069282
451 | 110795 | #SMART18 - Add lane to Rte. 107 under I-81 exit 35 | 0107 | Primary | Reconstruction w/ Added Capacity | VDOT | Smyth County | ABINGDON | Bristol | NonMPO:NonMPO | Infrastructure Investment Division | James R Jones | jamesr.jones@vdot.virginia.gov | (276) 696-3257 | Brandi Halloway | Brandi.Halloway@vdot.virginia.gov | (276) 696-3254 |  |  |  | 1 | 2018 | 0 | FY2021 | 2516000 | 1720980 | ACTIVITY DATES SET | Y | Solicit Bids milestone is 16 days ahead of the expected completion date and there is a risk of missing this milestone date | G | Project is on budget | [5 empty] | 2019-07-05 | 2019-07-03 | 2019-07-18 | 2019-07-18 | G | 2019-07-19 | 2019-07-19 | 2020-02-12 | 2020-02-12 | G | [5 empty] | 2020-05-19 | 2020-08-03 | 2020-06-16 | 2020-08-14 | R | [5 empty] | 2020-10-13 | 2020-10-29 | 2021-02-11 | 2021-01-22 | G | [5 empty] | 2020-09-29 | 2020-10-22 | 2021-01-04 | 2020-10-22 | G | [5 empty] | 2021-03-09 |  | 2021-03-09 |  | Y | 2021-04-23 |  | 2021-06-18 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.078671
452 | 111436 | #SGR18LB - BRIDGE REPLACEMENT RUSSELL FORK - (29801 Fed) | 0000 | Miscellaneous | Bridge Replacement w/o Added Capacity | Locally | Buchanan County | LEBANON | Bristol | NonMPO:NonMPO | Infrastructure Investment Division | Tabitha H Crowder | Tabitha.Crowder@vdot.virginia.gov | (276) 696-3482 | Roger L Musser | Roger.Musser@VDOT.Virginia.gov | (276) 696-3260 | Marcus Stiltner | marcus.stiltner@buchanancounty-va.gov | (276) 935-4013 | 0 |  | 1 | FY2021 | 180000 | 180000 | CONSTRUCTION STARTED | G | Start Delivery milestone finished on-time | G | Project is on budget | 2018-05-10 | 2018-02-01 | 2018-08-03 | 2018-04-02 | G | 2018-08-06 | 2018-04-03 | 2018-08-08 | 2018-04-05 | G | 2018-08-09 | 2018-04-06 | 2019-02-20 | 2019-02-19 | G | [35 empty] | 2020-01-14 | 2020-01-13 | 2020-04-09 | 2020-04-07 | G | 2020-04-10 | 2020-04-10 | 2020-07-06 | 2020-07-06 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.043537
453 | 113028 | #SGR19VB - RT 683 over Stallings Crk (Fed 10441) REPLACE | 0683 | Secondary | Bridge Replacement w/o Added Capacity | VDOT | Isle of Wight County | FRANKLIN | Hampton Roads | Hampton Roads:Isle of Wight County | Infrastructure Investment/Asset Management Division | Mark Wagner |  |  | Songjian Mao | Steve.Mao@VDOT.Virginia.gov | (757) 956-3211 |  |  |  | 0 |  | 1 | FY2023 | 3800000 | 3800000 | ACTIVITY DATES SET | R | Engage Public milestone finished 93 days late | G | Project is on budget | [5 empty] | 2018-10-08 | 2018-08-28 | 2018-10-22 | 2018-08-28 | G | 2018-10-23 | 2018-08-29 | 2019-09-19 | 2019-09-19 | G | [5 empty] | 2020-07-01 | 2020-07-01 | 2020-07-15 | 2020-10-16 | R | 2021-11-19 |  | 2021-11-19 |  | G | 2022-04-20 |  | 2022-10-24 |  | G | 2021-12-08 |  | 2022-06-15 |  | G | 2018-10-11 | 2018-10-11 | 2022-07-20 |  | G | [5 empty] | 2022-11-08 |  | 2022-11-08 |  | G | 2023-02-06 |  | 2023-02-06 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 |  | 0 | 0 | 0.14986
454 | 113692 | Kempsville Road, Segment 1 | 0190 | Urban | Resurfacing | Locally | Chesapeake | NORFOLK | Hampton Roads | Hampton Roads:Chesapeake | Infrastructure Investment Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Johndel A Alcaide | John.Alcaide@vdot.virginia.gov | (757) 956-3098 | Sam Sawan | sawan@cityofchesapeake.net | (757) 382-8263 | 0 |  | 1 | FY2019 | 408600 | 408600 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 29 days early | G | Project is on budget | 2018-09-04 | 2018-07-31 | 2018-11-30 | 2018-11-05 | G | 2018-12-03 | 2018-11-06 | 2018-12-05 | 2019-02-14 | R | 2018-12-06 | 2019-02-15 | 2019-06-13 | 2019-05-30 | G | [35 empty] | 2019-06-10 | 2019-05-30 | 2019-06-10 | 2019-05-30 | G | 2019-06-28 | 2019-05-30 | 2019-06-28 | 2019-05-30 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.11646
455 | 114326 | SPRIGGS RD AND RIVERSIDE DRIVE INSTALL NEW SIGNAL | 0643 | Secondary | Safety | VDOT | Prince William County | MANASSAS | Northern Virginia | Northern Virginia:Prince William County | Infrastructure Investment Division | Ivan M Horodyskyj | Ivan.Horodyskyj@VDOT.Virginia.gov | (703) 259-2330 | Jessica Paris | Jessica.Paris@vdot.virginia.gov | (703) 259-2409 |  |  |  | 0 |  | 0 | FY2020 | 600000 | 600000 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 168 days early | G | Project is on budget | [5 empty] | 2018-09-28 | 2018-10-29 | 2018-09-28 | 2018-11-05 | R | 2018-10-01 | 2018-07-16 | 2019-01-14 | 2019-01-14 | G | [5 empty] | 2019-08-20 | 2018-12-24 | 2019-09-03 | 2019-01-16 | G | [25 empty] | 2019-10-03 | 2019-04-26 | 2019-10-09 | 2019-04-26 | G | 2019-10-10 | 2019-05-01 | 2019-10-16 | 2019-05-01 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | WORK/TASK ORDER | 1 | 0 | 0.14375
456 | 115297 | #SGR20LP - PRIMARY EXT PAVING FY20 - SEMINARY ROAD E/B - 48 | 0420 | Urban | Resurfacing | Locally | Alexandria | FAIRFAX | Northern Virginia | Northern Virginia:Alexandria | Local Assistance Division | Amir Salahshoor | A.Salahshoor@VDOT.Virginia.gov | (703) 259-1957 | Rita Hockman | Rita.Hockman@vdot.virginia.gov | (804) 824-7421 | Mary Alice Winston | maryalice.winston@alexandriava.gov | (703) 746-4067 | 0 |  | 1 | FY2020 | 80000 | 80000 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 150 days early | G | Project is on budget | 2019-07-01 | 2019-07-01 | 2019-09-30 | 2019-09-26 | G | [5 empty] | 2019-10-01 | 2019-09-27 | 2019-10-31 | 2019-09-27 | G | [35 empty] | 2019-11-26 | 2019-06-28 | 2019-12-31 | 2019-06-28 | G | 2020-01-02 | 2019-09-30 | 2020-02-28 | 2019-10-01 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.19655
457 | 115793 | Primary Extension - C'burg - Radford St NW | 0011 | Urban | Reconstruction w/o Added Capacity | Locally | Christiansburg | CHRISTIANSBURG | Salem | New River Valley:Christiansburg | Local Assistance Division | Adam J Czesnowski | Adam.Czesnowski@vdot.virginia.gov | (540) 541-1216 | Adam J Czesnowski | Adam.Czesnowski@vdot.virginia.gov | (540) 541-1216 | Justin St. Clair | jstclair@christiansburg.org | (540) 382-6120 | 0 |  | 0 | FY2020 | 100175 | 100175 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 155 days early | G | Project is on budget | 2020-01-02 | 2019-07-01 | 2020-03-30 | 2019-08-07 | G | 2020-03-31 | 2019-09-03 | 2020-04-02 | 2019-09-05 | G | 2020-04-03 | 2019-09-19 | 2020-10-06 | 2019-09-20 | G | [35 empty] | 2019-12-31 | 2019-11-22 | 2019-12-31 | 2019-11-24 | G | 2020-01-27 | 2019-11-23 | 2020-06-30 | 2020-01-27 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.087616
458 | 116871 | EAST MAIN STREET - DELPHINE AVENUE ROUNDABOUT |  | Primary | Reconstruction w/ Added Capacity | Locally | Waynesboro | HARRISONBURG | Staunton | SAW:Waynesboro | Local Assistance Division | Jamison Brown | Jamison.Brown@vdot.virginia.gov | (540) 332-7389 | Jamison Brown | Jamison.Brown@vdot.virginia.gov | (540) 332-7389 | Jim Powers | powersJH@ci.waynesboro.va.us | (540) 241-2365 | 0 |  | 0 | FY2025 | 1108000 | 1108000 | NO DATES SET YET | G | Agreement with Locality milestone is 107 days ahead of the expected completion date | G | Project is on budget | 2021-02-01 |  | 2021-06-08 |  | G | 2021-06-09 |  | 2021-06-29 |  | G | 2021-07-29 |  | 2021-11-22 |  | G | [10 empty] | 2023-03-20 |  | 2023-04-21 |  | G | [5 empty] | 2023-04-24 |  | 2023-09-20 |  | G | 2024-03-27 |  | 2024-08-22 |  | G | [5 empty] | 2024-08-01 |  | 2024-08-28 |  | G | 2024-11-19 |  | 2024-11-19 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.19184
459 | 117150 | #SGR21LP City of Suffolk 1860 Whaleyville Blvd | 0013 | Urban | Resurfacing | Locally | Suffolk | NORFOLK | Hampton Roads | Hampton Roads:Suffolk | Infrastructure Investment/Asset Management Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Johndel A Alcaide | John.Alcaide@vdot.virginia.gov | (757) 956-3098 | Edward Heide | eheide@suffolkva.us | (757) 514-6715 | 0 |  | 1 | FY2022 | 241374 | 241374 | NO DATES SET YET | G | Agreement with Locality milestone is 80 days ahead of the expected completion date | G | Project is on budget | 2021-01-04 |  | 2021-05-12 |  | G | 2021-05-13 |  | 2021-06-03 |  | G | 2021-07-02 |  | 2021-08-04 |  | G | [25 empty] | 2021-07-08 |  | 2021-08-04 |  | G | [5 empty] | 2021-10-01 |  | 2021-10-29 |  | G | 2022-01-26 |  | 2022-01-26 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.067883
460 | 117967 | CENTERLINE RUMBLE STRIPS-BRISTOL DISTRICT WIDE | 9999 | Miscellaneous | Safety | VDOT | Bristol District-wide |  | Bristol | NonMPO:NonMPO | Infrastructure Investment Division | Brian Holt | Brian.Holt@vdot.virginia.gov | (276) 696-3414 | Jeremy J Mullins | Jeremy.Mullins@vdot.virginia.gov | (276) 696-3259 |  |  |  | 0 |  | 0 | FY2024 | 1814094 | 1814094 | NO DATES SET YET-PE OPEN | G | Obtained Permits milestone finished 734 days early | G | Project is on budget | [5 empty] | 2020-10-01 | 2020-10-01 | 2020-10-22 | 2020-10-22 | G | 2020-10-23 | 2020-10-23 | 2021-08-26 |  | G | [5 empty] | 2022-04-01 |  | 2022-04-28 |  | G | [5 empty] | 2022-12-21 |  | 2023-04-25 |  | G | [5 empty] | 2022-09-08 | 2021-02-09 | 2023-02-13 | 2021-02-09 | G | [5 empty] | 2023-05-09 |  | 2023-05-09 |  | G | 2023-07-28 |  | 2023-07-28 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.069129
461 | 118316 | #SGR21VB - Grove Av over I195 - Minor Rehab - FED ID 21310 |  | Urban | Bridge Rehab w/o Added Capacity | VDOT | Richmond | ASHLAND | Richmond | Richmond:Richmond | Infrastructure Investment/Asset Management Division | Roy Soto | Roy.Soto@vdot.virginia.gov | (804) 609-5239 | Roy Soto | Roy.Soto@vdot.virginia.gov | (804) 609-5239 |  |  |  | 0 |  | 0 | FY2026 | 11655719 | 11655719 | NO DATES SET YET | G | Start Development milestone is 578 days ahead of the expected completion date | G | Project is on budget | [5 empty] | 2022-09-01 |  | 2022-09-22 |  | G | 2022-09-23 |  | 2023-07-28 |  | G | [5 empty] | 2024-03-04 |  | 2024-03-29 |  | G | 2024-11-18 |  | 2024-12-24 |  | G | 2025-05-28 |  | 2025-09-25 |  | G | 2025-01-10 |  | 2025-06-11 |  | G | 2025-02-21 |  | 2025-07-21 |  | G | [5 empty] | 2025-10-14 |  | 2025-10-14 |  | G | 2026-01-08 |  | 2026-01-08 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.14298
462 | 98213 | #HB2.FY17 Construct Rural Roundabout at the Int of Rte 15/53 | 0015 | Primary | Reconstruction w/o Added Capacity | VDOT | Fluvanna County | CHARLOTTESVILLE | Culpeper | NonMPO:NonMPO | Infrastructure Investment Division | Dewitt D Sprinkel | Brent.Sprinkel@VDOT.Virginia.gov | (540) 829-7552 | Gabriel M Brown | Gabe.Brown@VDOT.Virginia.gov | (434) 422-9792 | - |  |  | 1 | 2017 | 0 | FY2017 | 2500600 | 2500600 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 14 days early | G | Project is on budget | [5 empty] | 2012-03-25 | 2012-12-05 | 2012-03-25 | 2012-12-05 | R | 2012-11-01 | 2012-11-01 | 2014-12-30 | 2015-03-31 | R | [10 empty] | 2015-08-01 | 2015-07-14 | 2015-08-01 | 2015-07-14 | G | 2015-08-17 | 2015-08-17 | 2015-12-04 | 2015-09-03 | G | 2015-08-17 | 2015-07-16 | 2015-12-04 | 2015-11-12 | G | [10 empty] | 2016-11-18 | 2016-06-14 | 2016-01-10 | 2016-06-14 | R | 2016-08-24 | 2016-08-24 | 2016-09-07 | 2016-08-24 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.15664
463 | 103007 | North End Greenway Extension and Associated Improvements |  | Urban | Reconstruction w/ Added Capacity | Locally | Harrisonburg | HARRISONBURG | Staunton | Harrisonburg:Harrisonburg | Local Assistance Division | Michael S Fulcher | Michael.Fulcher@VDOT.Virginia.gov | (540) 332-2243 | Michael S Fulcher | Michael.Fulcher@VDOT.Virginia.gov | (540) 332-2243 | Aaron Rhoney | Aaron.Rhoney@harrisonburgva.gov | (540) 434-5928 | 0 |  | 0 | FY2022 | 1662144 | 1662144 | NO DATES SET YET-PE OPEN | R | Start Purchasing Right-of-Way milestone is 663 days past the expected completion date | G | Project is on budget | [5 empty] | 2012-07-31 | 2013-04-18 | 2013-07-31 | 2013-04-18 | G | 2018-08-30 |  | 2020-02-28 |  | R | [10 empty] | 2019-03-01 |  | 2019-04-30 |  | R | [20 empty] | 2021-02-26 |  | 2021-03-31 |  | Y | 2021-04-30 |  | 2021-08-31 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.095274
464 | 106190 | RTE 865 (TIMBERLINE RD) - RURAL RUSTIC | 0865 | Secondary | Resurfacing | VDOT | Franklin County | BEDFORD | Salem | NonMPO:NonMPO | Infrastructure Investment Division | Todd K Daniel | Todd.Daniel@VDOT.Virginia.gov | (540) 682-7000 | Jason L Patrick | Jason.Patrick@vdot.virginia.gov | (540) 381-7178 |  |  |  | 0 |  | 0 | FY2023 | 1250000 | 1582530 | ACTIVITY DATES SET | G | Determine Requirements milestone finished 24 days early | R | Project estimate is less than $5M and is 20% or more over budget | [5 empty] | 2018-07-02 | 2020-02-11 | 2020-07-30 | 2020-02-20 | G | 2020-07-30 | 2020-02-21 | 2020-12-10 | 2020-11-16 | G | [10 empty] | 2020-07-06 |  | 2021-04-23 |  | G | [20 empty] | 2022-02-04 |  | 2022-02-04 |  | G | 2022-02-07 |  | 2022-07-27 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | SAAP CONTRACT | 0 | 0 | 0.12219
465 | 107063 | Rt. 221 Bedford Co. - Pedestrian Safety Improvements | 0221 | Primary | Safety | VDOT | Bedford County | BEDFORD | Salem | Roanoke:Bedford County | Infrastructure Investment Division | Bernard S Grinnell | Sean.Grinnell@VDOT.Virginia.gov | (540) 375-0148 | Christopher L Harrah | Chris.Harrah@VDOT.Virginia.gov | (540) 387-5395 |  |  |  | 0 |  | 0 | FY2023 | 2550000 | 2550000 | ACTIVITY DATES SET | R | Start Purchasing Right-of-Way milestone is 157 days past the expected completion date | G | Project is on budget | [5 empty] | 2019-06-04 | 2016-07-22 | 2019-06-17 | 2016-10-19 | G | 2019-06-18 | 2016-10-20 | 2020-05-14 | 2018-11-29 | G | [5 empty] | 2019-09-18 | 2019-05-22 | 2019-10-17 | 2019-05-23 | G | 2020-09-03 |  | 2020-09-17 |  | R | 2021-02-17 |  | 2022-07-25 |  | G | 2020-10-05 |  | 2022-03-28 |  | G | 2020-04-07 | 2019-01-14 | 2022-03-28 | 2019-01-14 | G | [5 empty] | 2022-09-13 |  | 2022-09-13 |  | G | 2022-11-03 |  | 2023-02-06 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 1 | 0.3309
467 | 111039 | #SGR18LB - Mineral Springs Road over Jones Swamp | 0616 | Urban | Bridge Replacement w/o Added Capacity | Locally | Suffolk | NORFOLK | Hampton Roads | Hampton Roads:Suffolk | Infrastructure Investment Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Johndel A Alcaide | John.Alcaide@vdot.virginia.gov | (757) 956-3098 | L Hansen | lhansen@suffolkva.us | (757) 514-7687 | 0 |  | 1 | FY2019 | 1815362 | 1815362 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 112 days early | G | Project is on budget | 2017-04-17 | 2017-04-17 | 2017-10-05 | 2017-10-05 | G | 2017-10-06 | 2017-10-06 | 2017-10-10 | 2017-10-10 | G | 2017-10-11 | 2017-10-11 | 2018-08-01 | 2018-07-17 | G | [10 empty] | 2019-01-31 | 2018-12-06 | 2019-01-31 | 2018-12-06 | G | [20 empty] | 2019-02-21 | 2018-12-28 | 2019-02-21 | 2018-12-28 | G | 2019-02-22 | 2018-12-31 | 2019-06-14 | 2019-02-22 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.11188
468 | 111650 | #SMART18 - ROUTE 670 CONNECTOR ROAD | 9999 | Secondary | New Construction Roadway | VDOT | Greene County | CHARLOTTESVILLE | Culpeper | NonMPO:NonMPO | Infrastructure Investment Division | Gregory J Cooley | Gregory.Cooley@vdot.virginia.gov | (434) 906-7979 | John Rose | John.Rose1@vdot.virginia.gov | (540) 829-7429 |  |  |  | 1 | 2018 | 0 | FY2022 | 5400000 | 5400000 | NO DATES SET YET-PE OPEN | R | Determine Requirements milestone is 704 days past the expected completion date | G | Project is on budget | [5 empty] | 2018-04-20 | 2018-04-20 | 2018-05-03 | 2018-04-25 | G | 2018-05-04 | 2018-05-04 | 2019-03-20 |  | R | [5 empty] | 2019-12-16 |  | 2019-12-30 |  | R | 2021-01-05 |  | 2021-01-20 |  | R | 2021-07-14 |  | 2022-01-06 |  | G | 2021-02-05 |  | 2021-07-13 |  | G | 2020-07-16 | 2019-03-25 | 2021-01-26 | 2019-03-25 | G | [5 empty] | 2022-01-11 |  | 2022-01-11 |  | G | 2022-03-01 |  | 2022-04-25 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.17171
469 | 113332 | SOUTH UNION STREET - RECONSTRUCTION | 9999 | Urban | Reconstruction w/o Added Capacity | Locally | Danville | HALIFAX | Lynchburg | Danville:Danville | Local Assistance Division | Gregg Allen | Gregg.Allen@vdot.virginia.gov | (434) 426-5575 | Sharon S White | Sharon.White@VDOT.Virginia.gov | (434) 856-8220 | Brian Dunevant, P.E. | dunevbl@danville.va.gov | (434) 799-5019 | 0 |  | 0 | FY2021 | 700000 | 700000 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 162 days early | G | Project is on budget | 2019-01-31 | 2018-11-05 | 2019-04-25 | 2018-11-05 | G | 2019-04-26 | 2018-11-06 | 2019-04-30 | 2018-11-08 | G | 2019-05-01 | 2018-11-09 | 2019-11-04 | 2020-06-17 | R | [10 empty] | 2020-06-17 | 2020-06-17 | 2020-06-17 | 2020-06-17 | G | [5 empty] | 2020-06-17 | 2020-06-17 | 2020-06-17 | 2020-06-17 | G | [10 empty] | 2020-07-24 | 2020-07-01 | 2020-08-20 | 2020-07-02 | G | 2020-12-18 | 2020-07-09 | 2020-12-18 | 2020-07-09 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.070176
470 | 117938 | #TAP21 AUDUBON DRIVE - CONSTRUCT SIDEWALK | 9999 | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Danville | HALIFAX | Lynchburg | Danville:Danville | Local Assistance Division | Gregg Allen | Gregg.Allen@vdot.virginia.gov | (434) 426-5575 | Gregg Allen | Gregg.Allen@vdot.virginia.gov | (434) 426-5575 | BRIAN DUNEVANT | dunevbl@danvilleva.gov | (434) 799-5019 | 0 |  | 0 | FY2025 | 394100 | 394100 | NO DATES SET YET | G | Agreement with Locality milestone is 106 days ahead of the expected completion date | G | Project is on budget | 2021-01-29 |  | 2021-06-07 |  | G | 2021-06-08 |  | 2021-06-28 |  | G | 2022-01-07 |  | 2022-05-03 |  | G | [10 empty] | 2023-08-22 |  | 2023-09-26 |  | G | [5 empty] | 2023-09-27 |  | 2024-03-04 |  | G | 2024-01-30 |  | 2024-06-26 |  | G | [5 empty] | 2024-06-05 |  | 2024-07-02 |  | G | 2024-09-20 |  | 2024-09-20 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.18899
471 | 118153 | Brook Road & Hilliard Road Trail | 0161 | Secondary | Facilities for Pedestrians and Bicycles | Locally | Henrico County | ASHLAND | Richmond | Richmond:Henrico County | Infrastructure Investment Division | Cynthia Crouch | Cynthia.Crouch@vdot.virginia.gov | (804) 609-5313 | Cynthia Crouch | Cynthia.Crouch@vdot.virginia.gov | (804) 609-5313 | Conner Barnes | bar136@henrico.us | (804) 501-4244 | 0 |  | 0 | FY2028 | 4757000 | 4757000 | NO DATES SET YET | G | Agreement with Locality milestone is 1179 days ahead of the expected completion date | G | Project is on budget | 2024-01-08 |  | 2024-05-15 |  | G | 2024-05-16 |  | 2024-06-06 |  | G | 2024-12-16 |  | 2025-04-11 |  | G | [10 empty] | 2026-07-31 |  | 2026-09-03 |  | G | [5 empty] | 2026-09-04 |  | 2027-02-10 |  | G | 2027-01-06 |  | 2027-06-07 |  | G | [5 empty] | 2027-05-14 |  | 2027-06-11 |  | G | 2027-08-31 |  | 2027-08-31 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 1 | 0.27482
472 | 90492 | Bridge Replacement of Rte 661 over Ogle Creek (Str. ID 1165) | 0661 | Secondary | Bridge Replacement w/o Added Capacity | VDOT | Alleghany County | LEXINGTON | Staunton | NonMPO:NonMPO | Infrastructure Investment Division | Keith P Weakley | Keith.Weakley@VDOT.Virginia.gov | (703) 298-8428 | Ashraf A Antonius | Ashraf.Antonius@vdot.virginia.gov | (540) 332-9107 |  |  |  | 0 |  | 0 | FY2024 | 3523704 | 670063 | WAITING FINANCIAL CLOSURE | G | Complete Purchasing Right-of-Way milestone finished 56 days early | G | Project is on budget | [5 empty] | 2010-07-01 | 2010-05-05 | 2010-07-01 | 2010-05-05 | G | 2011-12-06 | 2011-12-06 | 2012-06-14 | 2012-06-06 | G | [5 empty] | 2012-10-10 | 2012-12-11 | 2013-01-24 | 2013-01-30 | R | 2014-10-01 | 2014-11-12 | 2014-10-31 | 2014-12-09 | R | [5 empty] | 2015-01-15 | 2015-01-06 | 2016-08-01 | 2016-06-06 | G | 2021-03-04 |  | 2022-03-04 |  | G | [5 empty] | 2023-09-14 |  | 2023-10-10 |  | G | 2024-03-11 |  | 2024-05-10 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.059585
473 | 101062 | Rural Rustic- WIDENING AND PAVING - RTE. 652 | 0652 | Secondary | Reconstruction w/o Added Capacity | VDOT | Buchanan County | LEBANON | Bristol | NonMPO:NonMPO | Infrastructure Investment Division | Conrad Hill | Conrad.Hill@vdot.virginia.gov | (804) 773-0170 | Brandi Halloway | Brandi.Halloway@vdot.virginia.gov | (276) 696-3254 |  |  |  | 0 |  | 0 | FY2019 | 1000000 | 1000000 | WAITING FINANCIAL CLOSURE | R | Start Delivery milestone finished 61 days late | G | Project is on budget | [5 empty] | 2015-11-01 | 2015-07-22 | 2015-11-01 | 2015-07-24 | G | 2015-12-01 | 2015-11-02 | 2018-12-04 | 2018-11-06 | G | [35 empty] | 2019-01-24 | 2019-04-23 | 2019-01-28 | 2019-04-23 | R | 2019-03-04 | 2019-06-26 | 2019-04-26 | 2019-06-26 | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.088951
474 | 104901 | Bridge Repl-Skydusky Rd over Walker Crk (Fed ID 3071) | 0608 | Secondary | Bridge Replacement w/o Added Capacity | VDOT | Bland County | WYTHEVILLE | Bristol | NonMPO:NonMPO | Infrastructure Investment Division | Gary Lester |  |  | Ronald C Flanary | Ronald.Flanary@VDOT.Virginia.gov | (276) 696-3252 |  |  |  | 0 |  | 0 | FY2020 | 2030035 | 2700000 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 21 days early | R | Project estimate is less than $5M and is 20% or more over budget | [5 empty] | 2016-07-22 | 2016-07-08 | 2016-08-05 | 2016-08-08 | R | 2016-08-08 | 2016-08-05 | 2017-06-14 | 2017-06-14 | G | [5 empty] | 2017-10-02 | 2017-10-02 | 2017-10-02 | 2017-10-02 | G | 2018-02-22 | 2018-02-22 | 2018-04-25 | 2018-04-24 | G | [5 empty] | 2018-05-25 | 2018-05-14 | 2018-11-14 | 2018-10-09 | G | 2018-11-08 | 2018-10-10 | 2019-10-28 | 2018-11-28 | G | [5 empty] | 2019-05-16 | 2019-06-11 | 2019-06-11 | 2019-06-11 | G | 2019-07-18 | 2019-07-10 | 2019-07-31 | 2019-07-10 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.073691
475 | 106670 | #HB2.FY17 RTE 639 - LADYSMITH ROAD - WIDENING | 0639 | Secondary | Reconstruction w/ Added Capacity | VDOT | Caroline County | FREDERICKSBURG | Fredericksburg | NonMPO:NonMPO | Infrastructure Investment Division | Minwoo Ha | Minwoo.Ha@vdot.virginia.gov | (540) 899-4044 | Minwoo Ha | Minwoo.Ha@vdot.virginia.gov | (540) 899-4044 |  |  |  | 1 | 2017 | 0 | FY2022 | 26650000 | 26650000 | ACTIVITY DATES SET | R | Complete Purchasing Right-of-Way milestone finished 173 days late | G | Project is on budget | [5 empty] | 2015-08-14 | 2015-08-14 | 2015-08-21 | 2015-08-21 | G | 2015-08-14 | 2015-08-14 | 2017-09-27 | 2017-09-27 | G | [5 empty] | 2018-05-16 | 2018-05-17 | 2018-05-30 | 2019-01-22 | R | 2019-04-01 | 2019-03-20 | 2019-04-26 | 2019-03-26 | G | 2020-07-13 | 2020-08-05 | 2021-09-08 |  | G | 2019-05-14 | 2019-06-26 | 2020-07-10 | 2020-12-30 | R | 2016-12-05 | 2016-12-05 | 2019-06-03 | 2020-07-15 | R | [5 empty] | 2021-09-14 |  | 2021-09-14 |  | G | 2021-12-14 |  | 2022-02-11 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.1229
476 | 108793 | City of Suffolk Systemic Flashing Yellow Arrow | 0000 | Urban | Traffic Management/Engineering | Locally | Suffolk | NORFOLK | Hampton Roads | Hampton Roads:Suffolk | Infrastructure Investment Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Johndel A Alcaide | John.Alcaide@vdot.virginia.gov | (757) 956-3098 | Robert E Lewis | RELEWIS@suffolkva.us | (757) 514-7725 | 0 |  | 0 | FY2019 | 410000 | 378000 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 2 days early | G | Project is on budget | 2016-09-01 | 2016-12-01 | 2016-11-30 | 2016-12-09 | R | 2016-12-01 | 2016-11-09 | 2016-12-05 | 2016-11-09 | G | 2016-12-06 | 2017-09-01 | 2017-06-13 | 2017-09-20 | R | [35 empty] | 2018-04-25 | 2018-05-07 | 2018-05-22 | 2018-05-23 | R | 2018-05-24 | 2018-05-24 | 2018-12-14 | 2018-12-12 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.27623
477 | 111034 | Citywide Flashing Yellow Arrow Upgrades | 9999 | Urban | Traffic Management/Engineering | Locally | Newport News | WILLIAMSBURG | Hampton Roads | Hampton Roads:Newport News | Infrastructure Investment Division | Dawn Odom | Dawn.Odom@vdot.virginia.gov | (000) 000-0000 | Chessica Villaflores | Chessica.Villaflores@vdot.virginia.gov | (757) 956-3094 | Randy Cooper | rcooper@nnva.gov | (757) 926-8702 | 0 |  | 0 | FY2022 | 775750 | 775750 | NO DATES SET YET-PE OPEN | R | Determine Requirements milestone is 136 days past the expected completion date | G | Project is on budget | 2019-07-01 | 2019-07-01 | 2019-09-24 | 2019-12-02 | R | 2019-09-25 | 2019-12-02 | 2019-10-08 | 2019-12-06 | R | 2019-10-09 |  | 2020-10-08 |  | R | [35 empty] | 2021-08-20 |  | 2021-10-15 |  | G | 2021-10-19 |  | 2022-04-14 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.35015
478 | 111058 | #SMART18 - (ST) MILL PLACE PARKWAY IMPROVEMENTS | 0901 | Secondary | Reconstruction w/ Added Capacity | VDOT | Augusta County | HARRISONBURG | Staunton | SAW:Augusta County | Infrastructure Investment Division | Matthew P Dana | Matt.Dana@VDOT.Virginia.gov | (540) 332-7786 | Jethro Dienner | Jet.Dienner@vdot.virginia.gov | (540) 332-9290 |  |  |  | 1 | 2018 | 0 | FY2023 | 1789041 | 1789041 | ACTIVITY DATES SET | R | Engage Public milestone is 328 days past the expected completion date | G | Project is on budget | [5 empty] | 2018-08-01 | 2018-08-01 | 2018-08-14 | 2018-08-06 | G | 2018-08-15 | 2018-08-07 | 2019-07-15 | 2019-07-15 | G | [5 empty] | 2020-03-17 |  | 2020-03-30 |  | R | 2021-03-17 |  | 2021-03-30 |  | G | 2021-08-20 |  | 2022-03-03 |  | G | 2021-04-15 |  | 2021-10-19 |  | G | [10 empty] | 2022-03-08 |  | 2022-03-08 |  | G | 2022-04-21 |  | 2022-09-12 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.1106
479 | 112472 | BURKE LAKE RD & COFFER WOODS RD SIGNAL IMPROVEMENTS | 0645 | Primary | Safety | VDOT | Fairfax County | FAIRFAX | Northern Virginia | Northern Virginia:Fairfax County | Infrastructure Investment Division | Ivan M Horodyskyj | Ivan.Horodyskyj@VDOT.Virginia.gov | (703) 259-2330 | Jessica Paris | Jessica.Paris@vdot.virginia.gov | (703) 259-2409 | TBD |  |  | 0 |  | 0 | FY2022 | 492000 | 492000 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 939 days early | G | Project is on budget | [5 empty] | 2018-10-01 | 2018-06-28 | 2018-10-12 | 2018-07-16 | G | 2018-10-16 | 2018-06-28 | 2019-09-12 | 2018-11-16 | G | [5 empty] | 2018-06-29 | 2018-07-26 | 2018-07-27 | 2018-07-27 | G | 2018-12-11 | 2018-12-10 | 2018-12-11 | 2018-12-10 | G | 2018-10-11 | 2018-10-10 | 2018-10-11 | 2018-10-10 | G | 2018-12-11 | 2018-12-10 | 2018-12-11 | 2018-12-10 | G | [10 empty] | 2019-02-12 | 2019-01-08 | 2021-06-08 | 2019-01-17 | G | 2021-08-26 | 2019-02-05 | 2021-09-01 | 2019-02-05 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | WORK/TASK ORDER | 1 | 0 | 0.051454
480 | 113783 | RTE 633 - RURAL RUSTIC RD (SURFACE TREAT NON-HARDSURFACE RD) | 0633 | Secondary | Reconstruction w/o Added Capacity | VDOT | Albemarle County | CHARLOTTESVILLE | Culpeper | NonMPO:NonMPO | Infrastructure Investment Division | Ken Connors |  |  | Harold L Jones | Harold.Jones@VDOT.virginia.gov | (434) 422-9378 |  |  |  | 0 |  | 0 | FY2025 | 320000 | 320000 | NO DATES SET YET | G | Start Development milestone is 600 days ahead of the expected completion date | G | Project is on budget | [5 empty] | 2022-10-03 |  | 2022-10-14 |  | G | 2022-10-18 |  | 2023-06-13 |  | G | [5 empty] | 2024-02-22 |  | 2024-04-03 |  | G | [5 empty] | 2024-07-18 |  | 2024-11-08 |  | G | [5 empty] | 2024-07-02 |  | 2024-10-02 |  | G | [5 empty] | 2024-11-12 |  | 2024-11-12 |  | G | 2025-02-07 |  | 2025-02-07 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | SAAP CONTRACT | 0 | 0 | 0.15634
481 | 113894 | Main Street Pedestrian Safety Improvement - Bridgewater | 0042 | Urban | Facilities for Pedestrians and Bicycles | Locally | Bridgewater | HARRISONBURG | Staunton | NonMPO:NonMPO | Infrastructure Investment Division | David C Morris | David.Morris2@VDOT.Virginia.gov | (540) 332-8607 | Jeffery A Lineberry | Jeff.Lineberry@VDOT.Virginia.gov | (540) 332-2265 | Alex Wilmer | reuben.rhodes@vdot.virginia.gov | (540) 908-4212 | 0 |  | 0 | FY2021 | 88755 | 88755 | NO DATES SET YET-PE OPEN | R | Engage Public milestone baseline missing | G | Project is on budget | 2019-05-21 | 2018-10-19 | 2019-08-14 | 2019-04-16 | G | 2019-08-15 | 2019-07-10 | 2019-08-19 | 2019-07-30 | G | 2019-08-20 |  | 2020-03-02 |  | R | [9 empty] | R | [15 empty] | 2020-04-07 |  | 2020-12-09 |  | R | [5 empty] | 2021-01-08 |  | 2021-02-08 |  | R | 2021-04-28 |  | 2021-04-28 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.099952
482 | 114672 | RECTANGULAR RAPID FLASHING BEACON AT LEE HWY & N NELSON ST | 0029 | Primary | Safety | Locally | Arlington County | FAIRFAX | Northern Virginia | Northern Virginia:Arlington County | Infrastructure Investment Division | Terry Yates | Terry.Yates@vdot.virginia.gov | (703) 259-2118 | Rita Hockman | Rita.Hockman@vdot.virginia.gov | (804) 824-7421 | Dan Nabors | dnabors@arlingtonva.us | (703) 228-3726 | 0 |  | 0 | FY2020 | 40000 | 40000 | CONSTRUCTION COMPLETED | R | Start Delivery milestone finished 71 days late | G | Project is on budget | 2019-02-01 | 2019-02-01 | 2019-04-26 | 2019-04-17 | G | 2019-04-29 | 2019-04-18 | 2019-05-01 | 2019-05-01 | G | 2019-05-02 | 2019-05-02 | 2019-06-27 | 2019-05-24 | G | [35 empty] | 2019-09-06 | 2019-09-12 | 2019-09-12 | 2019-09-12 | G | 2019-12-05 | 2020-02-14 | 2019-12-05 | 2020-02-14 | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.16455
483 | 115801 | #I81CIP NB EXIT 205 EXTEND ACCELERATION LANE (ID #42) | 0081 | Interstate | Reconstruction w/o Added Capacity | VDOT | Rockbridge County | LEXINGTON | Staunton | NonMPO:NonMPO | Infrastructure Investment Division | John-Allen L Ennis | JohnAllen.Ennis@VDOT.Virginia.gov | (540) 332-9118 | Timothy Gregory | Tim.Gregory@vdot.virginia.gov | (540) 332-7891 |  |  |  | 0 |  | 0 | FY2024 | 2354000 | 2354000 | NO DATES SET YET-PE OPEN | R | Determine Requirements milestone is 187 days past the expected completion date | G | Project is on budget | [5 empty] | 2019-09-06 | 2019-08-26 | 2019-09-19 | 2019-08-26 | G | 2019-09-20 |  | 2020-08-18 |  | R | [5 empty] | 2021-06-24 |  | 2021-07-08 |  | G | 2022-10-12 |  | 2022-10-26 |  | G | 2023-03-28 |  | 2023-09-28 |  | G | 2022-11-14 |  | 2023-05-23 |  | G | 2022-04-04 | 2020-04-14 | 2022-10-05 | 2020-04-14 | G | [5 empty] | 2023-10-10 |  | 2023-10-10 |  | G | 2024-01-05 |  | 2024-01-05 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.071345
484 | 116331 | #I81CIP NWRO TOC FLOOR OPERATIONS | 0081 | Interstate | Safety | VDOT | Staunton District-wide |  | Staunton | NonMPO:NonMPO | Infrastructure Investment Division | Ricky A Via | Ricky.Via@vdot.virginia.gov | (804) 371-2396 | Kunal Kothawade | Kunal.Kothawade@vdot.virginia.gov | (540) 332-9259 |  |  |  | 0 |  | 0 | FY2020 | 970261 | 970261 | CONSTRUCTION STARTED | G | Start Delivery milestone finished on-time | G | Project is on budget | [10 empty] | 2019-11-01 | 2019-08-23 | 2020-03-17 | 2019-10-28 | G | [35 empty] | 2019-11-21 | 2019-11-21 | 2019-11-27 | 2019-11-27 | G | 2019-12-02 | 2019-12-02 | 2019-12-06 | 2019-12-06 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | WORK/TASK ORDER | 1 | 0 | 0.066043
485 | 117002 | #SGR21VP PM3B21 CAMPBELL COUNTY PLANT MIX (P) | 9999 | Primary | Resurfacing | VDOT | Campbell County | APPOMATTOX | Lynchburg | NonMPO:NonMPO | Infrastructure Investment Division | Kevin S Chisnell | Kevin.Chisnell@VDOT.Virginia.gov | (434) 856-8113 | Kevin S Chisnell | Kevin.Chisnell@VDOT.Virginia.gov | (434) 856-8113 |  |  |  | 0 |  | 1 | FY2022 | 830489 | 830489 | ADVERTISED | G | Solicit Bids milestone finished 28 days early | G | Project is on budget | [10 empty] | 2020-11-24 | 2020-10-15 | 2020-12-02 | 2020-11-20 | G | [35 empty] | 2020-12-08 | 2021-01-12 | 2021-02-09 | 2021-01-12 | G | 2021-04-30 |  | 2021-07-15 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.079318
486 | 117994 | 9th Street Multimodal Improvements |  | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Roanoke | SALEM | Salem | Roanoke:Roanoke City | Local Assistance Division | Cheryl B Becker | Cheryl.Becker@vdot.virginia.gov | (540) 492-2531 | Cheryl B Becker | Cheryl.Becker@vdot.virginia.gov | (540) 492-2531 | James Nuckles | james.nuckles@roanokeva.gov | (540) 853-2731 | 0 |  | 0 | FY2024 | 625000 | 625000 | NO DATES SET YET | G | Agreement with Locality milestone is 50 days ahead of the expected completion date | G | Project is on budget | 2020-12-01 |  | 2021-04-12 |  | G | 2021-04-13 |  | 2021-05-03 |  | G | 2021-11-08 |  | 2022-03-09 |  | G | [25 empty] | 2023-03-06 |  | 2023-08-01 |  | G | [5 empty] | 2023-09-28 |  | 2023-10-26 |  | G | 2024-01-23 |  | 2024-01-23 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.43994
487 | 118237 | ORANGE HUNT ES SRTS |  | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Fairfax County | FAIRFAX | Northern Virginia | Northern Virginia:Fairfax County | Local Assistance Division | Andrew G Beacher | Andrew.Beacher@vdot.virginia.gov | (703) 259-2239 | Saif-Ur Qargha | Saif.Qargha@vdot.virginia.gov | (703) 259-3223 | Lauren Delmare | lauren.delmare@fairfaxcounty.gov | (703) 877-5781 | 0 |  | 0 | FY2025 | 200000 | 200000 | NO DATES SET YET | G | Agreement with Locality milestone is 107 days ahead of the expected completion date | G | Project is on budget | 2021-02-01 |  | 2021-06-08 |  | G | 2021-06-09 |  | 2021-06-29 |  | G | 2021-07-29 |  | 2021-11-22 |  | G | [10 empty] | 2023-03-20 |  | 2023-04-21 |  | G | [5 empty] | 2023-04-24 |  | 2023-09-20 |  | G | 2023-12-14 |  | 2024-05-15 |  | G | [5 empty] | 2023-12-28 |  | 2024-06-17 |  | G | 2024-09-05 |  | 2025-02-13 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.25279
488 | 90931 | #SMART18 - ROUTE 711 - INTERSECTION IMPROVEMENTS | 0711 | Secondary | Reconstruction w/ Added Capacity | VDOT | Powhatan County | CHESTERFIELD | Richmond | Richmond:Powhatan County | Infrastructure Investment Division | Clayton M Thomas | Clay.Thomas@VDOT.Virginia.gov | (804) 609-5429 | Clayton M Thomas | Clay.Thomas@VDOT.Virginia.gov | (804) 609-5429 |  |  |  | 1 | 2018 | 0 | FY2022 | 3580773 | 3580773 | ACTIVITY DATES SET | R | Complete Purchasing Right-of-Way milestone finished 1 days late | G | Project is on budget | [5 empty] | 2017-06-20 | 2017-06-20 | 2017-07-15 | 2017-07-07 | G | 2017-07-07 | 2017-07-10 | 2018-03-26 | 2018-03-21 | G | [5 empty] | 2018-10-12 | 2018-10-12 | 2018-11-14 | 2018-11-14 | G | 2019-09-30 | 2019-09-24 | 2019-10-04 | 2019-09-24 | G | 2020-07-27 | 2020-08-19 | 2021-10-22 |  | G | 2019-10-23 | 2019-10-21 | 2020-07-28 | 2020-07-29 | R | [10 empty] | 2021-12-14 |  | 2021-12-14 |  | G | 2022-02-08 |  | 2022-04-18 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 1 | 0.23579
489 | 103084 | Ferry Road- Widening and Re-striping | 0606 | Secondary | Reconstruction w/ Added Capacity | VDOT | Stafford County | FREDERICKSBURG | Fredericksburg | Fredericksburg:Stafford County | Local Assistance Division | Khalil Minhas | Khalil.Minhas@vdot.virginia.gov | (540) 374-3369 | Sylvester C Okpala | Sylvester.Okpala@VDOT.Virginia.gov | (540) 907-8174 | Keith Dayton | kdayton@staffordcountyva.gov |  | 0 |  | 0 | FY2019 | 5115240 | 5091189 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 51 days early | G | Project is on budget | [5 empty] | 2014-09-01 | 2014-04-23 | 2014-09-01 | 2014-04-24 | G | 2014-09-02 | 2014-09-02 | 2015-04-01 | 2015-03-20 | G | [5 empty] | 2015-02-13 | 2015-02-13 | 2015-03-20 | 2015-03-20 | G | 2016-07-06 | 2016-07-06 | 2016-07-07 | 2016-07-07 | G | 2017-03-09 | 2017-03-09 | 2018-01-26 | 2018-01-26 | G | 2016-07-08 | 2016-07-08 | 2017-03-09 | 2017-03-09 | G | [10 empty] | 2018-11-27 | 2018-11-20 | 2018-11-27 | 2018-11-20 | G | 2019-01-02 | 2019-01-23 | 2019-03-15 | 2019-01-23 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.13264
490 | 113600 | Route 258 Rumble Stripes Southampton/Isle of Wight Counties | 0258 | Primary | Safety | VDOT | Southampton County | FRANKLIN | Hampton Roads | NonMPO:NonMPO | Infrastructure Investment Division | Christopher E Eggleston | Christopher.Eggleston@vdot.virginia.gov | (757) 857-8955 | Mark S Winslow | Mark.Winslow@VDOT.Virginia.gov | (757) 925-1528 |  |  |  | 0 |  | 0 | FY2025 | 352479 | 352479 | NO DATES SET YET | G | Start Development milestone is 617 days ahead of the expected completion date | G | Project is on budget | [5 empty] | 2022-10-18 |  | 2022-10-31 |  | G | 2022-11-01 |  | 2023-06-27 |  | G | [5 empty] | 2024-03-07 |  | 2024-04-17 |  | G | [5 empty] | 2024-08-01 |  | 2024-11-25 |  | G | [5 empty] | 2024-07-17 |  | 2024-10-16 |  | G | [5 empty] | 2024-12-10 |  | 2024-12-10 |  | G | 2025-03-06 |  | 2025-03-06 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.10886
491 | 113828 | Traffic Signal System Preemption Upgrade | 9999 | Urban | Traffic Management/Engineering | Locally | Chesapeake | NORFOLK | Hampton Roads | Hampton Roads:Chesapeake | Infrastructure Investment Division | Kelly Waldrop | Kelly.Waldrop@vdot.virginia.gov | (000) 000-0000 | Johndel A Alcaide | John.Alcaide@vdot.virginia.gov | (757) 956-3098 | Kevin Eppley | keppley@cityofchesapeake.net | (757) 382-6501 | 0 |  | 0 | FY2021 | 232380 | 209416 | AWARDED | G | Start Delivery milestone finished 6 days early | G | Project is on budget | 2018-10-01 | 2019-06-05 | 2018-12-28 | 2019-10-30 | R | 2018-12-31 | 2019-10-31 | 2019-01-03 | 2019-11-06 | R | 2019-01-04 | 2020-02-18 | 2019-07-11 | 2020-03-12 | R | [35 empty] | 2020-05-21 | 2020-05-07 | 2020-06-18 | 2020-07-30 | R | 2020-09-08 | 2020-09-02 | 2020-09-08 | 2020-09-02 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.29727
492 | 114060 | RICHMOND CANAL WALK - PH 2 & 3 | 9999 | Miscellaneous | Facilities for Pedestrians and Bicycles | Locally | Richmond | ASHLAND | Richmond | Richmond:Richmond | Local Assistance Division | Olena Fecek | Olena.Fecek@vdot.virginia.gov | (804) 524-6368 | Olena Fecek | Olena.Fecek@vdot.virginia.gov | (804) 524-6368 | LAMONT BENJAMIN | Lamont.Benjamin@RichmondGov.com | (804) 646-6339 | 0 |  | 0 | FY2021 | 2150000 | 2150000 | ACTIVITY DATES SET | R | Determine Requirements milestone finished 567 days late | G | Project is on budget | 2018-10-01 | 2018-05-16 | 2018-12-28 | 2018-08-16 | G | 2018-12-31 | 2019-01-18 | 2019-01-03 | 2019-01-22 | R | 2019-01-04 | 2019-01-23 | 2019-07-11 | 2021-01-28 | R | [10 empty] | 2021-02-17 | 2021-02-04 | 2021-03-10 |  | Y | [20 empty] | 2021-03-11 |  | 2021-03-11 |  | Y | 2021-05-28 |  | 2021-05-28 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.14999
493 | 115483 | #SMART20-US 58 Alt and US 23 NB Off-Ramp Mod (APP ID#3997) | 0023 | Urban | Reconstruction w/o Added Capacity | VDOT | Norton | WISE | Bristol | NonMPO:NonMPO | Infrastructure Investment Division | Dennis R Harris | Dennis.Harris@VDOT.Virginia.gov | (276) 696-3289 | Tamara D Pritchard | Tamara.Pritchard@VDOT.Virginia.gov | (276) 696-3249 |  |  |  | 1 | 2020 | 0 | FY2022 | 1276000 | 1276000 | ACTIVITY DATES SET | G | Determine Requirements milestone finished on-time | G | Project is on budget | [5 empty] | 2020-02-07 | 2019-11-15 | 2020-02-21 | 2019-12-02 | G | 2020-02-24 | 2019-12-03 | 2020-09-09 | 2020-09-09 | G | [5 empty] | 2021-05-14 |  | 2021-06-25 |  | G | [5 empty] | 2021-10-11 |  | 2022-02-09 |  | G | [5 empty] | 2021-09-24 |  | 2021-12-30 |  | G | [5 empty] | 2022-03-08 |  | 2022-03-08 |  | G | 2022-05-26 |  | 2022-05-26 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.084551
494 | 116323 | SYSTEMIC ROADWAY DEPARTURE TREATMENTS - DISTRICTWIDE | 9999 | Miscellaneous | Safety | VDOT | Richmond District-wide |  | Richmond | Richmond:Richmond District-wide | Infrastructure Investment/Asset Management Division | Adam S Brooks | Adam.Brooks@VDOT.Virginia.gov | (804) 609-5274 | Adam S Brooks | Adam.Brooks@VDOT.Virginia.gov | (804) 609-5274 | N\A |  |  | 0 |  | 0 | FY2022 | 2315363 | 2315363 | ACTIVITY DATES SET | G | Determine Requirements milestone finished on-time | G | Project is on budget | [10 empty] | 2020-08-05 | 2020-08-05 | 2020-12-15 | 2020-12-15 | G | [35 empty] | 2021-08-31 |  | 2021-09-07 |  | G | 2021-09-08 |  | 2021-09-14 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | WORK/TASK ORDER | 0 | 0 | 0.061448
495 | 116739 | I64 Toll Integration - Hampton Roads District Office | 0064 | Primary | Other | VDOT | Suffolk | NORFOLK | Hampton Roads | Hampton Roads:Suffolk | Infrastructure Investment Division | Dwayne K Cook | Dwayne.Cook@VDOT.Virginia.gov | (757) 956-3014 | Michael J Miller | Michael.Miller@VDOT.Virginia.gov | (757) 605-8741 |  |  |  | 0 |  | 0 | FY2023 | 199680 | 199680 | NO DATES SET YET-PE OPEN | R | Determine Requirements milestone is 75 days past the expected completion date | G | Project is on budget | [5 empty] | 2020-04-02 | 2020-07-22 | 2020-04-15 | 2020-07-31 | R | 2020-04-16 | 2020-08-03 | 2020-12-08 |  | R | [5 empty] | 2021-08-13 |  | 2021-09-24 |  | G | [5 empty] | 2022-01-18 |  | 2022-05-10 |  | G | [5 empty] | 2021-12-29 |  | 2022-04-04 |  | G | [5 empty] | 2022-06-14 |  | 2022-06-14 |  | G | 2022-09-02 |  | 2022-09-02 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | ADMINISTRATIVE SERVICES | 0 | 0 | 0.12053
496 | 117056 | Eastridge Road Sidewalk | 9999 | Secondary | Facilities for Pedestrians and Bicycles | Locally | Henrico County | ASHLAND | Richmond | Richmond:Henrico County | Local Assistance Division | Douglas L Orcutt | Doug.Orcutt@vdot.virginia.gov | (804) 609-5428 | Douglas L Orcutt | Doug.Orcutt@vdot.virginia.gov | (804) 609-5428 | TBD |  | TBD | 0 |  | 0 | FY2029 | 429100 | 429100 | NO DATES SET YET | G | Agreement with Locality milestone is 1543 days ahead of the expected completion date | G | Project is on budget | 2025-01-06 |  | 2025-05-14 |  | G | 2025-05-15 |  | 2025-06-05 |  | G | 2025-12-15 |  | 2026-04-10 |  | G | [10 empty] | 2027-07-30 |  | 2027-09-02 |  | G | [5 empty] | 2027-09-03 |  | 2028-02-09 |  | G | 2028-01-05 |  | 2028-06-05 |  | G | [5 empty] | 2028-05-12 |  | 2028-06-09 |  | G | 2028-08-29 |  | 2028-08-29 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.34714
497 | 118101 | #81 CIP DETOUR IMPROVEMENTS - EXIT 300 AND EXIT 313 | 9999 | Primary | Other | VDOT | Warren County | EDINBURG | Staunton | NonMPO:NonMPO | Infrastructure Investment Division | Keith M Rider | Keith.Rider@VDOT.Virginia.gov | (434) 856-8145 | Matthew Bond | Matthew.Bond@vdot.virginia.gov | (540) 332-9275 |  |  |  | 0 |  | 0 | FY2024 | 2850000 | 2850000 | NO DATES SET YET | R | Start Development milestone is 135 days past the expected completion date | G | Project is on budget | [5 empty] | 2020-09-21 |  | 2020-10-09 |  | R | 2020-10-12 |  | 2021-08-16 |  | G | [5 empty] | 2022-03-22 |  | 2022-04-18 |  | G | [5 empty] | 2022-12-09 |  | 2023-04-13 |  | G | [5 empty] | 2022-09-08 |  | 2023-02-13 |  | G | [5 empty] | 2023-05-09 |  | 2023-05-09 |  | G | 2023-07-28 |  | 2023-07-28 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.088437
498 | 15828 | Elbow Road Phase 2B |  | Urban | New Construction Roadway | Locally | Virginia Beach | NORFOLK | Hampton Roads | Hampton Roads:Virginia Beach | Infrastructure Investment Division | Susan Wilson | Susan.Wilson@vdot.virginia.gov | (757) 956-3099 | Marci Thompson | Marci.Thompson@vdot.virginia.gov | (757) 956-3093 | Annette B Hare, P.E. | ahare@vbgov.com | (757) 385-4131 | 0 |  | 0 | FY2021 | 45499000 | 46700000 | ACTIVITY DATES SET | R | Complete Purchasing Right-of-Way milestone baseline missing | Y | Project estimate is greater than $10M and is over budget by (a) up to 10% or (b) up to $5M | [5 empty] | 1996-03-25 | 1996-03-25 | 1996-03-26 | 1996-03-26 | G | 1996-03-27 | 1995-07-05 | 2018-10-22 | 2018-10-22 | G | [10 empty] | 2006-03-03 | 2006-03-03 | 2006-03-10 | 2006-03-10 | G | [9 empty] | R | 2003-07-24 | 2003-07-24 | 2003-08-20 | 2003-08-20 | G | [5 empty] | 2020-04-30 |  | 2020-05-28 |  | R | 2020-08-27 |  | 2021-01-08 |  | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.23175
499 | 103013 | Rte 11 - Improve Drainage, Add Sidewalks and C&G |  | Urban | Reconstruction w/o Added Capacity | Locally | Winchester | EDINBURG | Staunton | Winchester:Winchester | Infrastructure Investment Division | Kimberly Cameron | Kim.Cameron@vdot.virginia.gov | (540) 332-7886 | Kimberly Cameron | Kim.Cameron@vdot.virginia.gov | (540) 332-7886 | Perry Eisenach | perry.eisenach@winchesterva.gov | (540) 667-6165 | 0 |  | 0 | FY2020 | 7415978 | 7766908 | CONSTRUCTION STARTED | R | Start Delivery milestone finished 259 days late | Y | Project estimate is between $5M and $10M and is up to $1M over budget | [5 empty] | 2012-07-31 | 2013-07-15 | 2012-07-31 | 2013-07-15 | R | 2016-04-13 | 2016-04-12 | 2018-04-30 | 2016-05-20 | G | [10 empty] | 2017-10-30 | 2017-10-30 | 2018-01-31 | 2018-01-31 | G | [20 empty] | 2019-11-29 | 2020-05-29 | 2019-11-29 | 2020-05-29 | R | 2020-01-06 | 2020-11-12 | 2020-03-27 | 2020-12-11 | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.14126
500 | 105190 | RTE 211(WBL) BRIDGE OVER SF SHEN. RIVER | 0211 | Primary | Bridge Replacement w/o Added Capacity | VDOT | Page County | HARRISONBURG | Staunton | NonMPO:NonMPO | Infrastructure Investment Division | Rex L Pearce | Rex.Pearce@vdot.virginia.gov | (540) 332-9104 | Jean Uhl | Jean.Uhl@vdot.virginia.gov | (540) 332-9267 |  |  |  | 0 |  | 0 | FY2020 | 15452212 | 14706203 | CONSTRUCTION STARTED | G | Start Delivery milestone finished on-time | G | Project is on budget | [5 empty] | 2018-07-03 | 2018-07-02 | 2018-07-31 | 2018-07-30 | G | 2013-01-02 | 2018-08-06 | 2013-02-19 | 2019-02-06 | R | [10 empty] | 2018-07-09 | 2018-07-09 | 2018-07-31 | 2018-07-31 | G | 2018-05-14 | 2018-05-14 | 2019-09-26 | 2019-09-26 | G | 2018-09-04 | 2018-09-04 | 2018-12-18 | 2018-12-18 | G | 2018-02-21 | 2018-02-21 | 2019-04-29 | 2019-04-29 | G | [5 empty] | 2019-07-23 | 2019-07-23 | 2019-07-23 | 2019-07-23 | G | 2019-11-20 | 2019-11-20 | 2019-11-20 | 2019-11-20 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.060337
501 | 107021 | RTE 254 - SAFETY IMPROVEMENTS | 0254 | Primary | Safety | VDOT | Augusta County | HARRISONBURG | Staunton | SAW:Augusta County | Infrastructure Investment Division | Keith M Rider | Keith.Rider@VDOT.Virginia.gov | (434) 856-8145 | Kunal Kothawade | Kunal.Kothawade@vdot.virginia.gov | (540) 332-9259 |  |  |  | 0 |  | 0 | FY2020 | 1600000 | 1600000 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 26 days early | G | Project is on budget | [5 empty] | 2018-09-28 | 2018-04-17 | 2018-10-11 | 2018-04-20 | G | 2018-10-12 | 2018-05-01 | 2018-11-09 | 2018-07-03 | G | [35 empty] | 2020-01-16 | 2019-12-10 | 2020-01-16 | 2019-12-10 | G | 2020-03-04 | 2020-02-27 | 2020-03-24 | 2020-02-27 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.077982
502 | 108642 | Wyndham Forest Dr. and Nuckols Rd. sidewalk improvements | 9999 | Secondary | Facilities for Pedestrians and Bicycles | Locally | Henrico County | ASHLAND | Richmond | Richmond:Henrico County | Local Assistance Division | Brian J Lokker | Brian.Lokker@VDOT.Virginia.gov | (804) 524-6010 | Brian J Lokker | Brian.Lokker@VDOT.Virginia.gov | (804) 524-6010 | Todd Eure | eur@henrico.us | (804) 501-4617 | 0 |  | 0 | FY2020 | 280000 | 280000 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 225 days early | G | Project is on budget | 2016-07-25 | 2016-07-25 | 2016-10-18 | 2016-10-18 | G | 2016-10-25 | 2016-10-25 | 2016-10-27 | 2016-10-27 | G | 2017-09-01 | 2017-09-01 | 2018-07-02 | 2018-06-27 | G | [10 empty] | 2018-09-13 | 2018-07-17 | 2018-10-25 | 2018-07-25 | G | [5 empty] | 2018-10-29 | 2018-07-25 | 2019-08-01 | 2019-06-20 | G | [10 empty] | 2019-10-18 | 2019-08-22 | 2019-12-04 | 2019-08-22 | G | 2019-12-05 | 2019-08-22 | 2020-04-03 | 2019-08-22 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.34633
503 | 110110 | #SGR17VB - BRIDGE REHAB RT 17 SB DRAGON RUN ID 12086 | 0017 | Primary | Bridge Rehab w/o Added Capacity | VDOT | Middlesex County | SALUDA | Fredericksburg | NonMPO:NonMPO | Infrastructure Investment/Asset Management Division | Jeremy B Cobb | Jeremy.Cobb@vdot.virginia.gov | (804) 586-2255 | Jeremy B Cobb | Jeremy.Cobb@vdot.virginia.gov | (804) 586-2255 |  |  |  | 0 |  | 1 | FY2022 | 6200000 | 4100000 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 591 days early | G | Project is on budget | [5 empty] | 2016-11-01 | 2016-11-07 | 2016-11-15 | 2016-11-07 | G | 2016-11-16 | 2016-11-07 | 2017-12-28 | 2017-12-20 | G | [5 empty] | 2018-12-19 | 2018-06-19 | 2019-01-03 | 2018-06-19 | G | 2020-01-23 | 2018-09-14 | 2020-02-05 | 2018-09-14 | G | 2020-08-26 | 2019-04-04 | 2021-03-09 | 2019-05-21 | G | 2020-02-24 | 2018-09-14 | 2020-08-25 | 2018-09-14 | G | 2020-01-24 | 2018-07-23 | 2020-09-23 | 2018-11-09 | G | [5 empty] | 2021-04-13 | 2019-11-05 | 2021-04-13 | 2019-11-05 | G | 2021-07-09 | 2020-01-20 | 2021-09-02 | 2020-01-20 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.1356
504 | 110842 | SOUTH MESA DR - IMPROVE PEDESTRIAN ACCOMMODATIONS | 0000 | Urban | Safety | Locally | Hopewell | PETERSBURG | Richmond | Tri-Cities:Hopewell | Infrastructure Investment Division | James Shepherd | James.Shepherd@vdot.virginia.gov | (804) 609-5305 | James Shepherd | James.Shepherd@vdot.virginia.gov | (804) 609-5305 | Johnny Butler | jbutler@hopewellva.gov | (804) 541-2319 | 0 |  | 0 | FY2024 | 289000 | 289000 | NO DATES SET YET | G | Agreement with Locality milestone finished 77 days early | G | Project is on budget | 2020-12-01 | 2020-12-01 | 2021-04-12 | 2021-01-25 | G | 2021-04-13 |  | 2021-05-03 |  | G | 2021-06-02 |  | 2021-09-23 |  | G | [10 empty] | 2023-01-20 |  | 2023-02-24 |  | G | [5 empty] | 2023-02-27 |  | 2023-07-25 |  | G | 2023-06-21 |  | 2023-11-20 |  | G | [5 empty] | 2023-10-27 |  | 2023-11-28 |  | G | 2024-02-21 |  | 2024-02-21 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.081346
505 | 111808 | Smithfield to Nike Park Trl (Segment 3) PE Only | 0000 | Urban | Facilities for Pedestrians and Bicycles | Locally | Smithfield | FRANKLIN | Hampton Roads | Hampton Roads:Smithfield | Local Assistance Division | Todd M Halacy | Todd.Halacy@VDOT.Virginia.gov | (757) 956-3010 | Derrick Williams | Derrick.Williams@vdot.virginia.gov | (757) 956-3097 | Wayne Griffin P.E. | wgriffin@smithfield.gov | (757) 367-9933 | 0 |  | 0 | FY2023 | 237112 | 237112 | NO DATES SET YET-PE OPEN | R | Determine Requirements milestone is 163 days past the expected completion date | G | Project is on budget | 2019-06-04 | 2019-06-04 | 2019-08-27 | 2019-07-25 | G | 2019-08-28 | 2019-07-12 | 2019-09-11 | 2019-08-06 | G | 2019-09-12 |  | 2020-09-11 |  | R | [10 empty] | 2021-07-09 |  | 2021-07-29 |  | G | [5 empty] | 2021-08-02 |  | 2022-05-13 |  | G | [10 empty] | 2022-06-01 |  | 2022-06-28 |  | G | 2022-06-29 |  | 2022-08-10 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.15065
506 | 112709 | Wise Primary School Pedestrian Safety Project | 0000 | Urban | Safety | VDOT | Wise | WISE | Bristol | NonMPO:NonMPO | Infrastructure Investment Division | Tabitha H Crowder | Tabitha.Crowder@vdot.virginia.gov | (276) 696-3482 | Brandi Halloway | Brandi.Halloway@vdot.virginia.gov | (276) 696-3254 | Laura Mullins | planner@townofwise.org | (276) 328-6013 | 0 |  | 0 | FY2020 | 205000 | 155775 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished on-time | G | Project is on budget | [5 empty] | 2018-08-14 | 2018-08-14 | 2018-08-27 | 2018-08-14 | G | 2018-08-28 | 2018-08-14 | 2019-04-24 | 2018-08-14 | G | [5 empty] | 2019-12-18 | 2019-12-18 | 2019-12-18 | 2019-12-18 | G | [5 empty] | 2019-11-26 | 2019-11-26 | 2020-04-20 | 2020-04-20 | G | [5 empty] | 2019-12-19 | 2019-12-19 | 2019-12-21 | 2019-12-21 | G | [5 empty] | 2020-03-10 | 2020-03-10 | 2020-03-10 | 2020-03-10 | G | 2020-05-29 | 2020-05-29 | 2020-05-29 | 2020-05-29 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.075742
507 | 113026 | #SGR19VB - RT638 over Burnt Mill Swamp Fed 10417 REPLACE | 0638 | Secondary | Bridge Replacement w/o Added Capacity | VDOT | Isle of Wight County | FRANKLIN | Hampton Roads | Hampton Roads:Isle of Wight County | Infrastructure Investment/Asset Management Division | Mark Wagner |  |  | John G Harman | JohnG.Harman@vdot.virginia.gov | (757) 956-3269 |  |  |  | 0 |  | 1 | FY2022 | 2700000 | 1415441 | ACTIVITY DATES SET | G | Complete Purchasing Right-of-Way milestone finished 7 days early | G | Project is on budget | [10 empty] | 2020-05-26 | 2018-10-19 | 2020-06-01 | 2018-10-25 | G | [10 empty] | 2020-05-28 | 2020-05-28 | 2020-06-05 | 2020-06-05 | G | 2021-02-09 | 2021-02-01 | 2021-09-02 |  | G | 2020-06-29 | 2020-06-29 | 2021-01-14 | 2021-01-07 | G | 2018-12-11 | 2018-12-11 | 2020-06-18 | 2020-06-18 | G | [5 empty] | 2021-09-14 |  | 2021-09-14 |  | G | 2021-12-08 |  | 2021-12-08 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.14468
508 | 113280 | Pump Road Sidewalk Improvements | 7665 | Secondary | Facilities for Pedestrians and Bicycles | Locally | Henrico County | ASHLAND | Richmond | Richmond:Henrico County | Local Assistance Division | Cynthia Crouch | Cynthia.Crouch@vdot.virginia.gov | (804) 609-5313 | Cynthia Crouch | Cynthia.Crouch@vdot.virginia.gov | (804) 609-5313 | Kevin Newcomb | NEW038@henrico.us | (804) 501-5532 | 0 |  | 0 | FY2020 | 1600000 | 2229300 | ADVERTISED | R | Start Delivery milestone is 403 days past the expected completion date | R | Project estimate is less than $5M and is 20% or more over budget | 2018-07-02 | 2018-07-02 | 2018-10-31 | 2018-09-27 | G | 2018-11-01 | 2018-10-15 | 2018-11-15 | 2018-10-16 | G | 2018-11-16 | 2018-10-17 | 2019-01-15 | 2019-01-10 | G | [10 empty] | 2019-02-19 | 2019-02-13 | 2019-03-04 | 2019-02-15 | G | [5 empty] | 2019-03-06 | 2019-02-13 | 2019-07-31 | 2020-05-14 | R | 2019-02-19 | 2019-03-11 | 2019-07-31 | 2019-03-12 | G | [5 empty] | 2019-08-30 | 2021-01-15 | 2019-08-30 | 2021-01-15 | R | 2019-09-03 | 2021-01-19 | 2020-01-15 |  | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.3555
509 | 113482 | #SGR19LP - RT 10 - E. RANDOLPH ST. SGR | 0010 | Urban | Resurfacing | Locally | Hopewell | PETERSBURG | Richmond | Tri-Cities:Hopewell | Local Assistance Division | James Shepherd | James.Shepherd@vdot.virginia.gov | (804) 609-5305 | Brian J Lokker | Brian.Lokker@VDOT.Virginia.gov | (804) 524-6010 | Austin Anderson | aanderson@hopewellva.gov | (804) 541-2319 | 0 |  | 1 | FY2019 | 190000 | 190000 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 93 days early | G | Project is on budget | 2018-07-16 | 2018-07-16 | 2018-10-08 | 2018-10-04 | G | 2018-10-09 | 2018-10-04 | 2018-10-11 | 2018-10-04 | G | 2018-10-12 | 2018-10-05 | 2019-04-24 | 2019-01-02 | G | [25 empty] | 2019-01-03 | 2019-02-22 | 2019-01-16 | 2019-02-22 | R | [5 empty] | 2019-03-05 | 2019-03-14 | 2019-04-02 | 2019-03-18 | G | 2019-06-20 | 2019-03-18 | 2019-06-20 | 2019-03-19 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.049519
510 | 104128 | Town of Floyd - Heritage Pathways, Phases 3-4 |  | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Floyd | CHRISTIANSBURG | Salem | NonMPO:NonMPO | Local Assistance Division | Erica L Jeter | Erica.Jeter@VDOT.Virginia.gov | (804) 609-5215 | Cheryl B Becker | Cheryl.Becker@vdot.virginia.gov | (540) 492-2531 | Kayla Cox | kayla@townoffloyd.org | (540) 745-2565 | 0 |  | 0 | FY2019 | 742948 | 1057202 | CONSTRUCTION COMPLETED | R | Start Delivery milestone finished 200 days late | R | Project estimate is less than $5M and is 20% or more over budget | [10 empty] | 2015-02-02 | 2013-07-18 | 2015-06-02 | 2016-01-21 | R | [35 empty] | 2018-01-03 | 2018-04-29 | 2018-07-02 | 2018-05-31 | G | 2018-05-31 | 2018-06-01 | 2018-11-16 | 2019-06-04 | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.36525
511 | 105907 | #HB2.FY17 Constr. 2-Lane Roadway Connector | 0209 | Urban | New Construction Roadway | VDOT | Waynesboro | HARRISONBURG | Staunton | SAW:Waynesboro | Infrastructure Investment Division | John-Allen L Ennis | JohnAllen.Ennis@VDOT.Virginia.gov | (540) 332-9118 | David Robinson | David.Robinson@vdot.virginia.gov | (540) 332-7758 |  |  |  | 1 | 2017 | 0 | FY2022 | 16088466 | 17371386 | ACTIVITY DATES SET | R | Start Purchasing Right-of-Way milestone is 517 days past the expected completion date | Y | Project estimate is greater than $10M and is over budget by (a) up to 10% or (b) up to $5M | [5 empty] | 2016-07-29 | 2016-07-29 | 2016-07-29 | 2016-08-01 | R | 2017-08-01 | 2017-08-01 | 2018-12-30 | 2018-04-27 | G | [5 empty] | 2018-10-19 | 2018-10-19 | 2018-11-15 | 2018-12-05 | R | 2019-06-14 |  | 2019-09-23 |  | R | 2021-03-05 |  | 2021-11-02 |  | G | 2019-11-13 |  | 2021-03-04 |  | Y | 2018-01-08 | 2018-01-08 | 2021-06-07 |  | G | [5 empty] | 2021-10-07 |  | 2021-11-09 |  | G | 2022-01-04 |  | 2022-05-26 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.11155
512 | 107922 | VIRGINIA CREEPER TRAIL - CONSTRUCT RESTROOMS & PARKING |  | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Washington County | ABINGDON | Bristol | NonMPO:NonMPO | Local Assistance Division | Tabitha H Crowder | Tabitha.Crowder@vdot.virginia.gov | (276) 696-3482 | Tabitha H Crowder | Tabitha.Crowder@vdot.virginia.gov | (276) 696-3482 | Kevin Worley | kworley@abingdon-va.gov | (276) 492-2144 | 0 |  | 0 | FY2019 | 546096 | 546096 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 4 days early | G | Project is on budget | 2016-02-01 | 2016-02-01 | 2016-04-25 | 2016-04-25 | G | 2016-04-26 | 2016-04-26 | 2016-05-09 | 2016-05-09 | G | 2016-05-10 | 2016-05-10 | 2017-01-05 | 2017-01-05 | G | [10 empty] | 2017-11-22 | 2018-04-23 | 2017-12-07 | 2018-05-04 | R | [20 empty] | 2018-01-16 | 2019-02-14 | 2018-05-08 | 2019-02-14 | R | 2019-03-05 | 2019-02-15 | 2019-03-05 | 2019-03-01 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.24806
513 | 108666 | MMMBT Traffic & Safety Improvements | 0664 | Interstate | Traffic Management/Engineering | VDOT | Multi-jurisdictional: Hampton Roads MPO |  | Hampton Roads | Hampton Roads:Multi-jurisdictional: Hampton Roads MPO | Infrastructure Investment Division | Dwayne K Cook | Dwayne.Cook@VDOT.Virginia.gov | (757) 956-3014 | Jay Mohney | Jay.Mohney@vdot.virginia.gov | (757) 956-3168 |  |  |  | 0 |  | 0 | FY2021 | 6999999 | 6999999 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 126 days early | G | Project is on budget | [10 empty] | 2020-08-14 | 2020-06-22 | 2020-08-20 | 2020-06-22 | G | [25 empty] | 2020-07-01 | 2020-07-01 | 2021-01-08 | 2020-07-01 | G | [5 empty] | 2021-02-09 | 2020-10-08 | 2021-02-09 | 2020-10-08 | G | 2021-03-26 | 2021-01-12 | 2021-05-20 | 2021-01-14 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | ADMINISTRATIVE SERVICES | 1 | 1 | 0.2897
514 | 110799 | #SMART18 - Int. Improv. to US 11 at Old Airport Rd. | 0011 | Urban | Reconstruction w/o Added Capacity | Locally | Bristol | ABINGDON | Bristol | Bristol:Bristol | Infrastructure Investment Division | Tabitha H Crowder | Tabitha.Crowder@vdot.virginia.gov | (276) 696-3482 | Kenneth R Plummer | KR.Plummer@VDOT.Virginia.gov | (276) 696-3261 | W. McCulloch | wallace.mcculloch@bristolva.com | (276) 642-2316 | 1 | 2018 | 0 | FY2022 | 3279000 | 3182320 | NO DATES SET YET-PE OPEN | R | Determine Requirements milestone is 395 days past the expected completion date | G | Project is on budget | 2019-04-15 | 2018-01-23 | 2019-07-09 | 2018-04-23 | G | 2019-07-10 | 2018-08-30 | 2019-07-12 | 2018-08-30 | G | 2019-07-15 | 2019-07-15 | 2020-01-23 |  | R | [10 empty] | 2021-01-22 |  | 2021-02-11 |  | R | [5 empty] | 2021-02-15 |  | 2021-11-22 |  | G | [10 empty] | 2021-12-10 |  | 2022-01-10 |  | G | 2022-01-11 |  | 2022-02-23 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.096264
515 | 111373 | #SMART18 - I-81 SB Auxiliary Lane from Exit 143 to 141 | 0081 | Interstate | Reconstruction w/ Added Capacity | VDOT | Roanoke County | SALEM | Salem | Roanoke:Roanoke County | Infrastructure Investment Division | Thomas W Digiulian | Thomas.DiGiulian@VDOT.Virginia.gov | (540) 387-5356 | Jeffrey A Echols | Jeff.Echols@VDOT.Virginia.gov | (540) 375-3595 | Bryan Hill | billyhee@yahoo.com | (540) 343-4417 | 1 | 2018 | 0 | FY2021 | 32168111 | 32168111 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 377 days early | G | Project is on budget | [10 empty] | 2019-08-02 | 2017-11-01 | 2019-08-08 | 2017-11-01 | G | [35 empty] | 2020-08-11 | 2019-09-03 | 2020-08-11 | 2019-10-08 | G | 2020-10-26 | 2020-01-15 | 2021-01-26 | 2020-01-15 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.12925
516 | 112292 | Route 83 Shoulder Initiative - Dickenson Co.& Wise Co. | 0083 | Primary | Safety | VDOT | Dickenson County | WISE | Bristol | NonMPO:NonMPO | Infrastructure Investment Division | Brian Holt | Brian.Holt@vdot.virginia.gov | (276) 696-3414 | Jonathan A Henegar | Jonathan.Henegar@vdot.virginia.gov | (276) 206-0360 |  |  |  | 0 |  | 0 | FY2022 | 8710335 | 8310335 | ADVERTISED | R | Engage Public milestone is 136 days past the expected completion date | G | Project is on budget | [5 empty] | 2019-07-01 | 2019-07-01 | 2019-07-15 | 2019-07-10 | G | 2019-07-16 | 2019-07-11 | 2020-07-31 | 2020-07-24 | G | [5 empty] | 2020-09-25 |  | 2020-10-08 |  | R | [15 empty] | 2021-01-22 | 2020-12-02 | 2021-02-18 | 2021-01-25 | G | [5 empty] | 2021-05-11 | 2021-02-09 | 2021-05-11 | 2021-02-09 | G | 2021-08-06 |  | 2021-10-01 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.074841
517 | 112816 | GEORGE T. SNYDER TRAIL | 9999 | Urban | Facilities for Pedestrians and Bicycles | Locally | Fairfax | FAIRFAX | Northern Virginia | Northern Virginia:Fairfax | Infrastructure Investment Division | Amir Salahshoor | A.Salahshoor@VDOT.Virginia.gov | (703) 259-1957 | Robert J Strevell | Robert.Strevell@vdot.virginia.gov | (703) 259-1988 | Wendy Sanford | Wendy.Sanford@fairfaxva.gov |  | 0 |  | 0 | FY2024 | 13975000 | 13975000 | ACTIVITY DATES SET | R | Determine Requirements milestone finished 245 days late | G | Project is on budget | 2018-02-06 | 2018-02-06 | 2018-08-23 | 2018-07-02 | G | 2018-08-24 | 2018-07-03 | 2018-11-01 | 2018-07-26 | G | 2019-05-30 | 2019-01-10 | 2020-05-14 | 2021-01-14 | R | [5 empty] | 2021-09-30 |  | 2021-09-30 |  | G | 2021-10-01 |  | 2021-10-29 |  | G | [5 empty] | 2021-11-02 |  | 2022-10-31 |  | G | [10 empty] | 2022-11-16 |  | 2023-04-28 |  | G | 2023-05-02 |  | 2023-09-29 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.23121
519 | 113356 | Roanoke River Greenway, Parkway Crossing | 0618 | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Roanoke County | SALEM | Salem | Roanoke:Roanoke County | Local Assistance Division | Cheryl B Becker | Cheryl.Becker@vdot.virginia.gov | (540) 492-2531 | Cheryl B Becker | Cheryl.Becker@vdot.virginia.gov | (540) 492-2531 | Lindsay Webb | lwebb@roanokecountyva.gov | (540) 777-6328 | 0 |  | 0 | FY2023 | 708258 | 708258 | ACTIVITY DATES SET | G | Start Purchasing Right-of-Way milestone finished on-time | G | Project is on budget | 2018-10-01 | 2018-10-01 | 2018-12-28 | 2019-07-18 | R | 2018-12-31 | 2019-07-22 | 2019-01-03 | 2019-07-24 | R | 2019-01-04 | 2019-08-06 | 2019-08-01 | 2020-02-07 | R | [10 empty] | 2020-02-13 | 2020-02-13 | 2020-02-13 | 2020-02-13 | G | [5 empty] | 2021-12-30 |  | 2021-12-30 |  | G | 2021-04-27 |  | 2021-12-30 |  | G | [5 empty] | 2022-01-20 |  | 2022-02-16 |  | G | 2022-03-11 |  | 2022-08-01 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.33721
520 | 113513 | #SGR19LP - RT 144 (Temple Ave) Resurfacing (Blvd to Conduit) | 0144 | Urban | Resurfacing | Locally | Colonial Heights | CHESTERFIELD | Richmond | Tri-Cities:Colonial Heights | Local Assistance Division | Brian J Lokker | Brian.Lokker@VDOT.Virginia.gov | (804) 524-6010 | Brian J Lokker | Brian.Lokker@VDOT.Virginia.gov | (804) 524-6010 | Keith Chisolm | chisolmk@colonialheightsva.gov | (804) 520-9215 | 0 |  | 1 | FY2019 | 220000 | 220000 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 39 days early | G | Project is on budget | 2018-07-02 | 2018-07-02 | 2018-09-25 | 2018-08-14 | G | 2018-09-26 | 2018-08-23 | 2018-09-28 | 2018-08-27 | G | 2018-10-01 | 2018-09-04 | 2019-04-11 | 2018-10-24 | G | [35 empty] | 2018-11-26 | 2018-10-31 | 2018-12-31 | 2018-12-06 | G | 2019-03-25 | 2018-12-07 | 2019-04-01 | 2019-02-21 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.083826
521 | 114738 | INSTALL REFLECTIVE BACK PLATES - DISTRICTWIDE | 9999 | Primary | Safety | VDOT | Fredericksburg District-wide |  | Fredericksburg | NonMPO:NonMPO | Infrastructure Investment/Asset Management Division | Khalil Minhas | Khalil.Minhas@vdot.virginia.gov | (540) 374-3369 | Ronnie Hobson | Ron.Hobson@vdot.virginia.gov | (804) 840-5501 |  |  |  | 0 |  | 0 | FY2019 | 70928 | 70928 | AWARDED | G | Start Delivery milestone finished on-time | G | Project is on budget | [10 empty] | 2019-01-28 | 2019-01-28 | 2019-06-04 | 2019-02-28 | G | [35 empty] | 2019-03-01 | 2019-03-01 | 2019-03-01 | 2019-03-01 | G | 2019-03-01 | 2019-03-01 | 2019-03-01 | 2019-03-01 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | WORK/TASK ORDER | 1 | 0 | 0.089275
522 | 115235 | #SMART20 Ballentine Blvd Lane Improvements | 0405 | Primary | Reconstruction w/ Added Capacity | Locally | Norfolk | NORFOLK | Hampton Roads | Hampton Roads:Norfolk | Infrastructure Investment Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Derrick Williams | Derrick.Williams@vdot.virginia.gov | (757) 956-3097 | Christine Fuller | christine.armstrong@norfolk.gov | (757) 664-7459 | 1 | 2020 | 0 | FY2027 | 1067388 | 1067388 | NO DATES SET YET | G | Agreement with Locality milestone is 975 days ahead of the expected completion date | Y | Estimate not current | 2023-07-31 |  | 2023-10-24 |  | G | 2023-10-25 |  | 2023-11-07 |  | G | 2023-11-08 |  | 2024-10-24 |  | G | [10 empty] | 2025-10-28 |  | 2025-11-18 |  | G | [5 empty] | 2025-11-20 |  | 2026-10-02 |  | G | 2024-06-25 |  | 2025-03-04 |  | G | [5 empty] | 2026-10-21 |  | 2026-11-18 |  | G | 2027-02-12 |  | 2027-02-12 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.27677
523 | 116848 | BLUE VALLEY ROAD, PHASE I, RURAL ADDITION |  | Secondary | Reconstruction w/o Added Capacity | Locally | Warren County | EDINBURG | Staunton | NonMPO:NonMPO | Local Assistance Division | Kimberly Cameron | Kim.Cameron@vdot.virginia.gov | (540) 332-7886 | Kimberly Cameron | Kim.Cameron@vdot.virginia.gov | (540) 332-7886 | Bob Childress | rchildress@warrencountyva.net | (540) 636-4600 | 0 |  | 0 | FY2025 | 175000 | 175000 | NO DATES SET YET | G | Agreement with Locality milestone is 107 days ahead of the expected completion date | G | Project is on budget | 2021-02-01 |  | 2021-06-08 |  | G | 2021-06-09 |  | 2021-06-29 |  | G | 2021-07-29 |  | 2021-11-22 |  | G | [25 empty] | 2023-12-28 |  | 2024-05-29 |  | G | [5 empty] | 2024-07-26 |  | 2024-08-22 |  | G | 2024-11-13 |  | 2024-11-13 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.20423
524 | 117937 | STAFFORDBORO BOULEVARD SIDEWALK |  | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Stafford County | FREDERICKSBURG | Fredericksburg | Fredericksburg:Stafford County | Local Assistance Division | Catherine C Coffey | Catherine.Coffey@vdot.virginia.gov | (540) 899-4280 | Jessica Graves | Jessica.Graves@vdot.virginia.gov | (540) 899-4267 | Tom O'Connor | toconnor@staffordcountyva.gov | (540) 658-4610 | 0 |  | 0 | FY2025 | 1077500 | 1077500 | NO DATES SET YET | G | Agreement with Locality milestone is 80 days ahead of the expected completion date | G | Project is on budget | 2021-01-04 | 2020-11-17 | 2021-05-12 |  | G | 2021-05-13 |  | 2021-06-03 |  | G | 2021-12-13 |  | 2022-04-08 |  | G | [10 empty] | 2023-07-28 |  | 2023-08-31 |  | G | [5 empty] | 2023-09-01 |  | 2024-02-07 |  | G | 2024-01-03 |  | 2024-06-03 |  | G | [5 empty] | 2024-05-10 |  | 2024-06-07 |  | G | 2024-08-27 |  | 2024-08-27 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.27919
525 | 118490 | 121 CFX - 460 Corridor Q Route 460 Poplar Creek - Phase B | 0460 | Primary | New Construction Roadway | VDOT | Buchanan County | LEBANON | Bristol | NonMPO:NonMPO | Infrastructure Investment Division | Marty R Halloway | Marty.Halloway@VDOT.Virginia.gov | (276) 696-3367 | Laura B Hale | Laura.Hale@vdot.virginia.gov | (276) 698-0085 |  |  |  | 0 |  | 0 | FY2026 | 174326737 | 174326737 | NO DATES SET YET | G | Start Development milestone is 40 days ahead of the expected completion date | G | Project is on budget | [5 empty] | 2021-03-15 |  | 2021-04-02 |  | G | 2021-04-05 |  | 2022-06-15 |  | G | [5 empty] | 2023-07-13 |  | 2023-08-23 |  | G | 2024-09-13 |  | 2024-10-17 |  | G | 2025-05-14 |  | 2025-09-12 |  | G | 2024-11-12 |  | 2025-06-05 |  | G | 2024-11-13 |  | 2025-07-21 |  | G | [5 empty] | 2025-10-14 |  | 2025-10-14 |  | G | 2026-01-08 |  | 2026-01-08 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.11078
526 | 75267 | CITY OF POQUOSON - POQUOSON MUSEUM |  | Enhancement | Rehabilitation of Historic Bldgs/Facilities | Locally | Poquoson | WILLIAMSBURG | Hampton Roads | Hampton Roads:Poquoson | Local Assistance Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Chessica Villaflores | Chessica.Villaflores@vdot.virginia.gov | (757) 956-3094 | Tonya O'Connell | Tonya.OConnell@poquoson-va.gov | (757) 868-3030 | 0 |  | 0 | FY2019 | 227630 | 291469 | CONSTRUCTION STARTED | R | Start Delivery milestone finished 123 days late | R | Project estimate is less than $5M and is 20% or more over budget | 2005-10-19 | 2005-10-19 | 2005-10-19 | 2005-10-19 | G | 2005-10-25 | 2005-10-25 | 2005-10-26 | 2005-10-26 | G | 2014-09-11 | 2014-09-11 | 2018-07-02 | 2018-07-02 | G | [35 empty] | 2018-10-31 | 2018-10-31 | 2018-10-31 | 2019-05-13 | R | 2019-01-08 | 2019-07-12 | 2019-04-11 | 2019-08-12 | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.37894
527 | 100856 | OAKLAND INDUSTRIAL PARK SIDEWALK, PHASE 2 |  | Urban | Facilities for Pedestrians and Bicycles | Locally | Newport News | WILLIAMSBURG | Hampton Roads | Hampton Roads:Newport News | Infrastructure Investment Division | Daniel Mcbride | Daniel.McBride@vdot.virginia.gov | (804) 786-2987 | Chessica Villaflores | Chessica.Villaflores@vdot.virginia.gov | (757) 956-3094 | Daniel McBride | dmcbride@nngov.com | (757) 926-3977 | 0 |  | 0 | FY2019 | 927237 | 658449 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 322 days early | G | Project is on budget | [5 empty] | 2011-07-01 | 2013-10-07 | 2012-08-01 | 2013-10-07 | R | 2012-08-01 | 2012-08-01 | 2013-10-01 | 2013-11-01 | R | [10 empty] | 2016-05-10 | 2016-05-10 | 2016-07-26 | 2016-07-26 | G | [20 empty] | 2018-03-21 | 2018-03-21 | 2018-03-21 | 2018-03-21 | G | 2018-05-03 | 2018-04-19 | 2019-04-02 | 2018-05-15 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.25302
528 | 105510 | I-95 Rappahannock River Crossing - Northbound | 0095 | Interstate | Reconstruction w/ Added Capacity | VDOT | Fredericksburg | FREDERICKSBURG | Fredericksburg | Fredericksburg:Fredericksburg | Infrastructure Investment Division | William Arel |  |  | Robert Galen Ridgell | Robert.Ridgell@vdot.virginia.gov | (540) 372-3549 |  |  |  | 0 |  | 0 | FY2021 | 127000000 | 127000000 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 43 days early | G | Project is on budget | [5 empty] | 2019-08-02 | 2019-09-16 | 2019-08-02 | 2019-09-16 | R | 2019-08-05 | 2018-12-04 | 2019-08-05 | 2019-09-23 | R | [10 empty] | 2019-09-20 | 2019-09-16 | 2019-09-30 | 2019-09-16 | G | [20 empty] | 2019-10-01 | 2019-09-16 | 2019-10-09 | 2019-09-16 | G | 2020-05-29 | 2020-05-20 | 2020-07-02 | 2020-05-20 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | DESIGN BUILD/PPTA | 1 | 0 | 0.079691
529 | 106529 | CITY OF CHARLOTTESVILLE SIGNALS |  | Urban | Traffic Management/Engineering | Locally | Charlottesville | CHARLOTTESVILLE | Culpeper | Charlottesville:Charlottesville | Local Assistance Division | Ken Connors |  |  | Michael D Barnes | MichaelD.Barnes@vdot.virginia.gov | (434) 422-9861 | Kyle Kling | klingk@charlottesville.gov | (434) 970-3182 | 0 |  | 0 | FY2020 | 2000000 | 3668615 | ACTIVITY DATES SET | R | Start Purchasing Right-of-Way milestone baseline missing | R | Project estimate is less than $5M and is 20% or more over budget | [5 empty] | 2014-10-01 | 2014-10-01 | 2014-10-01 | 2015-02-18 | R | 2014-10-02 | 2015-02-19 | 2018-11-23 | 2019-01-07 | R | [11 empty] | 2020-03-10 |  | 2020-03-10 | R | [6 empty] | 2020-03-11 |  |  | R | [10 empty] | 2019-01-08 | 2019-01-08 | 2020-02-28 |  | R | 2020-03-02 |  | 2020-05-22 |  | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.15347
530 | 113484 | #SGR19LP - BUS 29 - RESURFACING (CENTRAL BOULEVARD) | 7029 | Urban | Resurfacing | Locally | Danville | HALIFAX | Lynchburg | Danville:Danville | Local Assistance Division | Sharon S White | Sharon.White@VDOT.Virginia.gov | (434) 856-8220 | Sharon S White | Sharon.White@VDOT.Virginia.gov | (434) 856-8220 | Brian Dunevant | dunevbl@danvilleva.gov | (434) 799-5019 | 0 |  | 1 | FY2019 | 312000 | 312000 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 3 days early | G | Project is on budget | 2019-01-31 | 2018-09-04 | 2019-04-25 | 2018-09-04 | G | [5 empty] | 2019-01-31 | 2018-09-04 | 2019-02-13 | 2018-09-17 | G | [25 empty] | 2018-09-18 | 2018-09-04 | 2018-12-14 | 2018-12-14 | G | [5 empty] | 2018-09-20 | 2018-09-20 | 2018-10-18 | 2018-10-18 | G | 2019-01-11 | 2019-01-08 | 2019-01-11 | 2019-01-08 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.050263
531 | 114096 | ROUTE US 360 - SHOULDER WIDENING, RUMBLE STRIPS, AND GR | 6360 | Primary | Safety | VDOT | Halifax County | HALIFAX | Lynchburg | NonMPO:NonMPO | Infrastructure Investment Division | Keith M Rider | Keith.Rider@VDOT.Virginia.gov | (434) 856-8145 | Keith M Rider | Keith.Rider@VDOT.Virginia.gov | (434) 856-8145 |  |  |  | 0 |  | 0 | FY2023 | 2910270 | 2910270 | NO DATES SET YET | G | Determine Requirements milestone is 515 days ahead of the expected completion date | G | Project is on budget | [10 empty] | 2022-07-15 |  | 2022-07-21 |  | G | [25 empty] | 2022-07-15 |  | 2023-01-25 |  | G | [5 empty] | 2023-02-14 |  | 2023-02-14 |  | G | 2023-05-05 |  | 2023-05-05 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.080166
532 | 115123 | #SMART20 LAFAYETTE BLVD/KENMORE AVE/CHARLES ST ROUNDABOUTS | 0001 | Primary | Reconstruction w/o Added Capacity | VDOT | Fredericksburg | FREDERICKSBURG | Fredericksburg | Fredericksburg:Fredericksburg | Infrastructure Investment Division | Curtis B Holloway | Curtis.Holloway@vdot.virginia.gov | (540) 374-3367 | Curtis B Holloway | Curtis.Holloway@vdot.virginia.gov | (540) 374-3367 | ERIK NELSON | ENELSON@FREDERICKSBURGVA.GOV | (540) 937-0572 | 1 | 2020 | 0 | FY2028 | 5800000 | 5800000 | NO DATES SET YET | G | Start Development milestone is 964 days ahead of the expected completion date | G | Project is on budget | [5 empty] | 2023-10-02 |  | 2023-10-13 |  | G | 2023-10-17 |  | 2024-09-12 |  | G | [5 empty] | 2025-07-21 |  | 2025-08-01 |  | G | 2026-11-06 |  | 2026-11-20 |  | G | 2027-04-21 |  | 2027-10-25 |  | G | 2026-12-10 |  | 2027-06-17 |  | G | 2026-04-28 |  | 2026-10-30 |  | G | [5 empty] | 2027-11-09 |  | 2027-11-09 |  | G | 2028-02-07 |  | 2028-02-07 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.11519
533 | 116746 | PEDESTRIAN IMPROVEMENTS - CITY WIDE - PHASE 1B |  | Primary | Safety | Locally | Richmond | ASHLAND | Richmond | Richmond:Richmond | Local Assistance Division | Evan Austin | Evan.Austin@vdot.virginia.gov | (804) 609-5384 | Evan Austin | Evan.Austin@vdot.virginia.gov | (804) 609-5384 | Jian Xu | Jian.Xu@richmondgov.com | (804) 646-5402 | 0 |  | 0 | FY2021 | 630803 | 678967 | ADVERTISED | G | Solicit Bids milestone finished 184 days early | Y | Project estimate is less than $5M and is up to 20% over budget | 2020-06-30 | 2020-03-11 | 2020-12-31 | 2020-03-26 | G | [5 empty] | 2021-01-04 | 2020-03-27 | 2021-04-30 | 2020-05-21 | G | [35 empty] | 2020-09-01 | 2020-06-23 | 2020-12-31 | 2020-06-30 | G | 2021-03-25 |  | 2021-04-30 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.18459
534 | 117072 | Ridge Road Reconstruction |  | Urban | Reconstruction w/o Added Capacity | Locally | Colonial Heights | CHESTERFIELD | Richmond | Tri-Cities:Colonial Heights | Local Assistance Division | Evan Austin | Evan.Austin@vdot.virginia.gov | (804) 609-5384 | Evan Austin | Evan.Austin@vdot.virginia.gov | (804) 609-5384 | Kieth Chisholm | chisolmk@colonialheightsva.gov | TBD | 0 |  | 0 | FY2028 | 661255 | 661255 | NO DATES SET YET | G | Agreement with Locality milestone is 1543 days ahead of the expected completion date | G | Project is on budget | 2025-01-06 |  | 2025-05-14 |  | G | 2025-05-15 |  | 2025-06-05 |  | G | 2025-07-07 |  | 2025-10-28 |  | G | [25 empty] | 2026-10-23 |  | 2027-03-30 |  | G | [5 empty] | 2027-05-26 |  | 2027-06-23 |  | G | 2027-09-13 |  | 2027-09-13 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.16457
535 | 118287 | #SGR21VB(FED ID10694) BRDG REPLACE-RTE 695 OVER OYSTER CREEK | 0695 | Secondary | Bridge Replacement w/o Added Capacity | VDOT | Lancaster County | NORTHERN NECK | Fredericksburg | NonMPO:NonMPO | Infrastructure Investment/Asset Management Division | Annette F Adams | Annette.Adams@VDOT.Virginia.gov | (540) 372-3583 | Annette F Adams | Annette.Adams@VDOT.Virginia.gov | (540) 372-3583 |  |  |  | 0 |  | 1 | FY2027 | 7603794 | 7603794 | NO DATES SET YET | G | Start Development milestone is 946 days ahead of the expected completion date | G | Project is on budget | [5 empty] | 2023-09-05 |  | 2023-09-25 |  | G | 2023-09-26 |  | 2024-07-30 |  | G | [5 empty] | 2025-03-05 |  | 2025-04-01 |  | G | 2025-11-19 |  | 2025-12-26 |  | G | 2026-05-29 |  | 2026-09-28 |  | G | 2026-01-13 |  | 2026-06-12 |  | G | 2026-02-20 |  | 2026-07-20 |  | G | [5 empty] | 2026-10-13 |  | 2026-10-13 |  | G | 2027-01-07 |  | 2027-01-07 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.061392
536 | 15955 | RTE 1 - INTERSECTION IMPROVEMENTS AT HOPKINS RD & HARWOOD ST | 0001 | Urban | Reconstruction w/o Added Capacity | VDOT | Richmond | ASHLAND | Richmond | Richmond:Richmond | Infrastructure Investment Division | Roy Soto | Roy.Soto@vdot.virginia.gov | (804) 609-5239 | Roy Soto | Roy.Soto@vdot.virginia.gov | (804) 609-5239 |  |  |  | 0 |  | 0 | FY2021 | 16194600 | 11602886 | ACTIVITY DATES SET | R | Complete Purchasing Right-of-Way milestone is 4066 days past the expected completion date | G | Project is on budget | [5 empty] | 1996-10-01 | 1997-03-31 | 1996-10-31 | 1997-04-01 | R | 1996-11-01 | 1997-04-23 | 1998-01-31 | 1997-08-21 | G | [5 empty] | 2006-03-03 | 2006-03-03 | 2006-08-03 | 2006-08-03 | G | 2006-09-22 | 2006-09-22 | 2008-01-03 | 2008-01-03 | G | 2019-04-29 | 2019-04-29 | 2019-10-16 |  | R | 2008-01-07 | 2008-01-07 | 2010-01-04 |  | R | 2008-02-19 | 2019-09-23 | 2008-02-25 | 2019-09-23 | R | [5 empty] | 2019-05-01 |  | 2019-11-27 |  | R | 2020-02-20 |  | 2020-12-31 |  | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.12001
537 | 97553 | C503, landscaping and amenities at Copper Creek overlook |  | Enhancement | Landscaping/Beautification | Locally | Scott County | WISE | Bristol | NonMPO:NonMPO | Local Assistance Division | Tabitha H Crowder | Tabitha.Crowder@vdot.virginia.gov | (276) 696-3482 | Tabitha H Crowder | Tabitha.Crowder@vdot.virginia.gov | (276) 696-3482 | John Kilgore, Scott County EDA | jkilgore@scottcountyva.com | (276) 386-2525 | 0 |  | 0 | FY2019 | 16801 | 16801 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 1 days early | G | Project is on budget | [10 empty] | 2017-04-03 | 2017-04-01 | 2018-01-18 | 2018-01-18 | G | [35 empty] | 2018-06-01 | 2018-05-25 | 2018-08-03 | 2018-08-02 | G | 2018-08-06 | 2018-08-06 | 2018-09-06 | 2018-09-05 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.32847
538 | 104281 | DEEPWATER TERMINAL RD - EXTEND EXISTING ROADWAY |  | Urban | New Construction Roadway | Locally | Richmond | ASHLAND | Richmond | Richmond:Richmond | Local Assistance Division | Cynthia Crouch | Cynthia.Crouch@vdot.virginia.gov | (804) 609-5313 | Cynthia Crouch | Cynthia.Crouch@vdot.virginia.gov | (804) 609-5313 | Adel Edward | adel.edward@Richmondgov.com | (804) 646-6584 | 0 |  | 0 | FY2021 | 2000001 | 5458000 | ACTIVITY DATES SET | R | Complete Purchasing Right-of-Way milestone is 452 days past the expected completion date | R | Project estimate is less than $5M and is 20% or more over budget | 2013-07-01 | 2013-07-01 | 2013-11-30 | 2013-11-08 | G | 2013-12-01 | 2013-11-14 | 2013-12-01 | 2013-11-14 | G | 2015-07-01 | 2014-06-26 | 2015-10-31 | 2015-10-23 | G | [10 empty] | 2018-08-01 | 2018-08-14 | 2018-08-31 | 2018-08-29 | G | [5 empty] | 2018-10-01 | 2020-02-27 | 2019-11-27 |  | R | [10 empty] | 2020-01-02 |  | 2020-01-31 |  | R | 2020-01-31 |  | 2021-01-20 |  | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.17404
539 | 105918 | Stanardsville Sidewalk - Main Street Pedestrian Improvements |  | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Stanardsville | CHARLOTTESVILLE | Culpeper | NonMPO:NonMPO | Local Assistance Division | Gregory J Cooley | Gregory.Cooley@vdot.virginia.gov | (434) 906-7979 | John P Price | John.Price@VDOT.Virginia.gov | (540) 347-6371 | Gary Lowe | elowe1@aol.com | (434) 985-8615 | 0 |  | 0 | FY2021 | 942229 | 1279619 | ACTIVITY DATES SET | R | Solicit Bids milestone is 304 days past the expected completion date | R | Project estimate is less than $5M and is 20% or more over budget | 2014-10-01 | 2014-10-01 | 2014-11-04 | 2014-11-04 | G | 2014-10-01 | 2014-10-01 | 2014-11-04 | 2014-11-04 | G | 2014-10-01 | 2014-10-01 | 2018-09-14 | 2018-08-20 | G | [10 empty] | 2018-06-06 | 2018-06-06 | 2019-05-21 | 2019-09-20 | R | [5 empty] | 2019-05-22 | 2019-09-20 | 2020-03-12 | 2020-08-12 | R | [10 empty] | 2020-03-13 | 2020-08-13 | 2020-04-23 |  | R | 2020-07-14 |  | 2020-07-14 |  | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.40556
540 | 108654 | RTE 5 - TURN LANES | 0005 | Primary | Other | VDOT | Henrico County | ASHLAND | Richmond | Richmond:Henrico County | Local Assistance Division | Noyan F Erermis | Noyan.Erermis@vdot.virginia.gov | (804) 819-9653 | Noyan F Erermis | Noyan.Erermis@vdot.virginia.gov | (804) 819-9653 | Todd Eure | eur@henrico.us | (804) 501-4617 | 0 |  | 0 | FY2022 | 2309033 | 2048341 | ACTIVITY DATES SET | G | Relocate Utilities milestone finished 268 days early | G | Project is on budget | [5 empty] | 2017-08-25 | 2017-08-25 | 2017-08-29 | 2017-08-29 | G | 2017-09-22 | 2017-09-22 | 2018-08-21 | 2018-08-21 | G | [5 empty] | 2019-06-20 | 2019-06-20 | 2019-07-18 | 2019-07-17 | G | 2020-07-28 | 2020-07-13 | 2020-08-10 | 2020-08-10 | G | 2021-04-06 | 2020-06-15 | 2021-10-07 | 2021-01-12 | G | 2020-08-26 | 2020-08-11 | 2021-03-09 | 2020-08-11 | G | 2020-01-15 | 2020-03-23 | 2021-01-14 | 2020-03-23 | G | [5 empty] | 2021-10-12 |  | 2021-10-12 |  | G | 2021-12-07 |  | 2022-03-07 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.17463
541 | 109440 | #HB2.FY17 I-81 Exit 19 Ramp Improvements | 0081 | Interstate | Reconstruction w/ Added Capacity | VDOT | Washington County | ABINGDON | Bristol | Bristol:Washington County | Infrastructure Investment Division | Allan D Sumpter | Allan.Sumpter@VDOT.virginia.gov | (276) 525-6461 | James R Jones | jamesr.jones@vdot.virginia.gov | (276) 696-3257 |  |  |  | 1 | 2017 | 0 | FY2021 | 9735983 | 6718910 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 97 days early | G | Project is on budget | [5 empty] | 2016-07-27 | 2016-07-27 | 2016-08-01 | 2016-12-19 | R | 2016-08-15 | 2016-08-15 | 2017-08-01 | 2017-07-18 | G | [5 empty] | 2018-08-07 | 2018-08-07 | 2018-08-20 | 2018-08-20 | G | 2019-06-18 | 2019-05-17 | 2019-07-01 | 2019-05-31 | G | 2019-12-13 | 2019-12-02 | 2020-07-20 | 2019-12-02 | G | 2019-07-05 | 2019-06-18 | 2020-03-26 | 2020-03-09 | G | 2018-08-22 | 2018-08-22 | 2019-08-22 | 2018-08-22 | G | [5 empty] | 2020-08-11 | 2020-06-09 | 2020-08-11 | 2020-06-09 | G | 2020-09-24 | 2020-09-02 | 2020-12-08 | 2020-09-02 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.094309
542 | 110710 | RTE 613 - MINOR WIDENING PHASE II | 0613 | Secondary | Reconstruction w/o Added Capacity | VDOT | New Kent County | ASHLAND | Richmond | Richmond:New Kent County | Infrastructure Investment Division | Lawrence Ramsey | Brian.Ramsey@VDOT.Virginia.gov | (804) 585-3579 | Lawrence Ramsey | Brian.Ramsey@VDOT.Virginia.gov | (804) 585-3579 |  |  |  | 0 |  | 0 | FY2019 | 831169 | 831169 | CONSTRUCTION COMPLETED | R | Start Delivery milestone finished 8 days late | G | Project is on budget | [5 empty] | 2017-10-09 | 2017-07-10 | 2017-10-23 | 2017-08-07 | G | 2017-10-24 | 2017-10-04 | 2018-09-20 | 2018-04-10 | G | [5 empty] | 2018-06-05 | 2018-06-05 | 2018-08-14 | 2018-08-14 | G | 2018-09-06 | 2018-07-18 | 2018-09-06 | 2018-07-20 | G | 2018-07-12 | 2018-07-12 | 2018-07-12 | 2018-07-12 | G | 2018-09-06 | 2018-07-20 | 2018-09-06 | 2018-07-20 | G | 2018-08-16 | 2018-05-01 | 2019-02-12 | 2018-05-01 | G | [5 empty] | 2019-04-09 | 2019-04-09 | 2019-04-09 | 2019-04-09 | G | 2019-05-30 | 2019-06-26 | 2019-06-19 | 2019-06-27 | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 1 | 0.24466
543 | 111066 | Pedestrian Bridge over Rt. 311 - Roanoke County | 0311 | Primary | Facilities for Pedestrians and Bicycles | VDOT | Roanoke County | SALEM | Salem | NonMPO:NonMPO | Infrastructure Investment Division | Anthony T Marshall | Todd.Marshall@VDOT.Virginia.gov | (540) 387-5460 | Leonard W Gisiner | Len.Gisiner@VDOT.Virginia.gov | (540) 387-5457 |  |  |  | 0 |  | 0 | FY2025 | 2880000 | 2880000 | ACTIVITY DATES SET | G | Determine Requirements milestone finished 271 days early | G | Project is on budget | [5 empty] | 2020-07-01 | 2018-06-11 | 2020-07-15 | 2018-06-22 | G | 2020-07-16 | 2019-06-25 | 2021-06-14 | 2020-09-16 | G | [5 empty] | 2021-12-13 |  | 2021-12-27 |  | G | 2023-06-13 |  | 2023-06-26 |  | G | 2023-11-20 |  | 2024-05-29 |  | G | 2023-07-12 |  | 2024-07-11 |  | G | [10 empty] | 2024-08-13 |  | 2024-08-13 |  | G | 2024-11-04 |  | 2024-11-04 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.18529
544 | 111220 | #SGR18LB - Sunray Overpass Superstructure Replacement |  | Urban | Bridge Rehab w/o Added Capacity | Locally | Chesapeake | NORFOLK | Hampton Roads | Hampton Roads:Chesapeake | Local Assistance Division | Kelly Waldrop | Kelly.Waldrop@vdot.virginia.gov | (000) 000-0000 | Johndel A Alcaide | John.Alcaide@vdot.virginia.gov | (757) 956-3098 | Earl Sorey, PE | easorey@cityofchesapeake.net | (757) 382-6101 | 0 |  | 1 | FY2019 | 3187000 | 3187000 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished on-time | G | Project is on budget | 2017-06-01 | 2017-06-01 | 2018-08-31 | 2018-08-01 | G | 2018-09-04 | 2018-08-24 | 2018-09-17 | 2018-08-28 | G | 2018-09-18 | 2018-08-29 | 2018-10-30 | 2018-09-11 | G | [35 empty] | 2018-08-17 | 2018-08-12 | 2018-09-28 | 2018-08-30 | G | 2018-10-01 | 2018-10-01 | 2018-10-30 | 2018-10-30 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.19663
545 | 111455 | RTE 1 - RECONSTRUCTION ROUTE 1 BYPASS/JEFF DAVIS HWY | 0001 | Urban | Reconstruction w/o Added Capacity | Locally | Fredericksburg | FREDERICKSBURG | Fredericksburg | NonMPO:NonMPO | Infrastructure Investment Division | Richard A Spurlock | Richard.Spurlock@VDOT.Virginia.gov | (540) 899-4302 | Richard A Spurlock | Richard.Spurlock@VDOT.Virginia.gov | (540) 899-4302 | Erik Nelson | enelson@fredericksburgva.gov | (540) 372-1080 | 0 |  | 0 | FY2019 | 117382 | 117382 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 316 days early | G | Project is on budget | 2017-08-01 | 2017-06-02 | 2017-10-25 | 2017-07-21 | G | [5 empty] | 2017-08-01 | 2017-06-02 | 2017-08-14 | 2017-09-18 | R | [35 empty] | 2017-09-19 | 2018-03-06 | 2018-12-04 | 2018-03-06 | G | 2018-12-05 | 2018-03-06 | 2019-01-16 | 2018-03-06 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.079025
547 | 113194 | Hampton Blvd and Azalea Ct. Intersection Improvements | 0337 | Urban | Reconstruction w/o Added Capacity | Locally | Norfolk | NORFOLK | Hampton Roads | Hampton Roads:Norfolk | Local Assistance Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Derrick Williams | Derrick.Williams@vdot.virginia.gov | (757) 956-3097 | Deborah Mangiaracina, P. E. | deborah.mangiaracina@norfolk.gov | (757) 664-7459 | 0 |  | 0 | FY2022 | 900800 | 900800 | ACTIVITY DATES SET | R | Start Purchasing Right-of-Way milestone is 31 days past the expected completion date | G | Project is on budget | 2018-09-21 | 2018-09-21 | 2018-12-19 | 2018-10-02 | G | 2018-12-20 | 2018-09-28 | 2018-12-24 | 2018-10-02 | G | 2018-12-26 | 2018-10-03 | 2019-07-02 | 2019-07-02 | G | [10 empty] | 2019-07-16 |  | 2021-01-21 |  | R | [5 empty] | 2021-01-25 |  | 2021-06-17 |  | G | 2018-12-27 | 2018-12-27 | 2019-08-29 | 2018-12-27 | G | [5 empty] | 2021-07-06 |  | 2021-08-16 |  | G | 2021-11-04 |  | 2022-02-04 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.12903
548 | 113436 | ROSEMARY DRIVE & ASTON AVENUE - INSTALL NEW TRAFFIC SIGNAL | 1600 | Secondary | Safety | VDOT | Prince William County | MANASSAS | Northern Virginia | Northern Virginia:Prince William County | Infrastructure Investment Division | Ivan M Horodyskyj | Ivan.Horodyskyj@VDOT.Virginia.gov | (703) 259-2330 | Jessica Paris | Jessica.Paris@vdot.virginia.gov | (703) 259-2409 |  |  |  | 0 |  | 0 | FY2019 | 500000 | 500000 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 176 days early | G | Project is on budget | [5 empty] | 2019-02-15 | 2018-10-22 | 2019-03-01 | 2018-10-22 | G | 2019-03-04 | 2018-10-24 | 2020-01-29 | 2018-10-24 | G | [5 empty] | 2018-08-23 | 2018-08-23 | 2018-08-23 | 2018-08-23 | G | 2018-10-22 | 2018-10-22 | 2018-10-22 | 2018-10-23 | R | 2018-10-22 | 2018-10-22 | 2018-10-22 | 2018-10-22 | G | 2018-10-22 | 2018-10-22 | 2018-10-22 | 2018-10-22 | G | [10 empty] | 2018-11-13 | 2018-10-09 | 2019-03-12 | 2018-10-09 | G | 2019-05-30 | 2018-12-04 | 2019-06-05 | 2018-12-11 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | WORK/TASK ORDER | 1 | 0 | 0.14356
549 | 113725 | #SGR19LP - Primary EXT Paving - Hampton Blvd/ BR/ 49St. | 0337 | Urban | Resurfacing | Locally | Norfolk | NORFOLK | Hampton Roads | Hampton Roads:Norfolk | Infrastructure Investment Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Derrick Williams | Derrick.Williams@vdot.virginia.gov | (757) 956-3097 | Deborah Mangiaracina, P.E.?? | deborah.mangiaracina@norfolk.gov | (757) 664-7459 | 0 |  | 1 | FY2019 | 356068 | 356068 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 82 days early | G | Project is on budget | 2018-09-04 | 2019-01-07 | 2018-11-30 | 2019-01-07 | R | 2018-12-03 | 2019-01-08 | 2018-12-05 | 2019-01-16 | R | 2018-12-06 | 2018-07-10 | 2019-06-13 | 2019-01-16 | G | [25 empty] | 2018-05-11 | 2019-01-16 | 2019-01-16 | 2019-01-16 | G | [5 empty] | 2018-12-18 | 2018-12-18 | 2019-01-16 | 2019-01-16 | G | 2019-04-09 | 2019-01-17 | 2019-04-09 | 2019-01-17 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.15156
550 | 106972 | MILITARY ROAD SIDEWALK & INTERSECTION IMPROVEMENTS | 9999 | Secondary | Facilities for Pedestrians and Bicycles | Locally | Arlington County | FAIRFAX | Northern Virginia | Northern Virginia:Arlington County | Local Assistance Division | Amir Salahshoor | A.Salahshoor@VDOT.Virginia.gov | (703) 259-1957 | Rita Hockman | Rita.Hockman@vdot.virginia.gov | (804) 824-7421 | Valerie Mosley | mvmosley@arlingtonva.us | (703) 927-1570 | 0 |  | 0 | FY2022 | 910000 | 1412185 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 373 days early | R | Project estimate is less than $5M and is 20% or more over budget | 2015-09-01 | 2015-09-01 | 2015-11-30 | 2015-11-30 | G | 2015-12-01 | 2016-12-01 | 2015-12-14 | 2016-12-15 | R | 2015-12-15 | 2016-12-16 | 2016-08-09 | 2017-08-11 | R | [10 empty] | 2016-11-04 | 2016-11-04 | 2016-11-04 | 2016-11-04 | G | [20 empty] | 2021-04-01 | 2020-04-06 | 2021-07-23 | 2020-04-06 | G | 2021-07-26 | 2020-07-18 | 2021-07-26 | 2020-07-18 | G | Design plans are being revised | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.23977
551 | 108705 | Main Street sidewalk maintenance | 9999 | Secondary | Facilities for Pedestrians and Bicycles | Locally | Blackstone | PETERSBURG | Richmond | NonMPO:NonMPO | Local Assistance Division | Brian J Lokker | Brian.Lokker@VDOT.Virginia.gov | (804) 524-6010 | Brian J Lokker | Brian.Lokker@VDOT.Virginia.gov | (804) 524-6010 | Phillip Vannoorbeeck |  |  | 0 |  | 0 | FY2019 | 52000 | 52000 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 350 days early | Y | Estimate not current | 2017-07-12 | 2016-09-09 | 2017-10-04 | 2016-09-19 | G | 2017-10-05 | 2016-10-23 | 2017-10-10 | 2016-10-23 | G | 2017-10-11 | 2017-04-07 | 2018-04-20 | 2017-04-17 | G | [35 empty] | 2018-05-04 | 2017-05-25 | 2018-05-22 | 2017-05-25 | G | 2018-05-23 | 2017-07-18 | 2018-07-03 | 2017-07-18 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.14475
552 | 110329 | #SMART18 - ROUTE 29 WIIDENING - PH II | 0029 | Primary | Reconstruction w/ Added Capacity | VDOT | Fairfax County | FAIRFAX | Northern Virginia | Northern Virginia:Fairfax County | Infrastructure Investment Division | Terry Yates | Terry.Yates@vdot.virginia.gov | (703) 259-2118 | Hong Ha | Hong.Ha@VDOT.Virginia.gov | (703) 259-2907 | Michael Guarino | michael.guarino@fairfaxcounty. | 703877571 | 1 | 2018 | 0 | FY2024 | 66973543 | 95008136 | ACTIVITY DATES SET | R | Start Purchasing Right-of-Way milestone is 257 days past the expected completion date | R | Project estimate is greater than $10M and is over budget by (a) 10% or more or (b) $5M or more | [5 empty] | 2017-06-26 | 2018-01-22 | 2017-07-10 | 2018-01-31 | R | 2017-07-11 | 2017-11-14 | 2018-05-21 | 2019-06-17 | R | [5 empty] | 2019-12-06 | 2019-10-10 | 2019-12-19 | 2019-10-30 | G | 2020-05-27 |  | 2020-06-09 |  | R | 2021-09-07 |  | 2023-06-12 |  | G | 2020-06-23 |  | 2022-05-05 |  | G | 2022-04-18 |  | 2023-01-05 |  | G | [5 empty] | 2023-06-13 |  | 2023-06-13 |  | G | 2023-08-25 |  | 2023-10-23 |  | G | Preliminary design and/or investigations are still underway | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 1 | 0.33719
553 | 111051 | #SMART18 - (St) RICHMOND AVE ROAD DIET AND ROUNDABOUT |  | Urban | Reconstruction w/o Added Capacity | Locally | Staunton | HARRISONBURG | Staunton | SAW:Staunton | Infrastructure Investment Division | Matthew P Dana | Matt.Dana@VDOT.Virginia.gov | (540) 332-7786 | Michael S Fulcher | Michael.Fulcher@VDOT.Virginia.gov | (540) 332-2243 | City of Stuanton |  |  | 1 | 2018 | 0 | FY2026 | 2245805 | 2245805 | NO DATES SET YET | G | Agreement with Locality milestone is 247 days ahead of the expected completion date | G | Project is on budget | 2021-08-02 |  | 2021-10-26 |  | G | 2021-10-27 |  | 2021-10-29 |  | G | 2021-11-01 |  | 2022-12-09 |  | G | [10 empty] | 2024-09-10 |  | 2024-09-30 |  | G | [5 empty] | 2024-10-02 |  | 2025-07-25 |  | G | [10 empty] | 2025-08-12 |  | 2025-09-09 |  | G | 2025-09-10 |  | 2025-12-30 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.09612
554 | 111083 | City of Suffolk Dowtown Railroad Warning System | 0000 | Urban | Rail/Highway Crossing | Locally | Suffolk | NORFOLK | Hampton Roads | Hampton Roads:Suffolk | Infrastructure Investment Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Johndel A Alcaide | John.Alcaide@vdot.virginia.gov | (757) 956-3098 | Robert Lewis | Relewis@suffolkva.us | (757) 514-7603 | 0 |  | 0 | FY2026 | 650000 | 650000 | NO DATES SET YET | G | Agreement with Locality milestone is 1072 days ahead of the expected completion date | Y | Estimate not current | 2023-10-27 |  | 2024-01-29 |  | G | 2024-01-30 |  | 2024-02-12 |  | G | 2024-02-13 |  | 2025-01-29 |  | G | [35 empty] | 2025-12-08 |  | 2026-01-06 |  | G | 2026-01-07 |  | 2026-06-29 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.15415
555 | 111391 | #SGR19VB - BRIDGE REHAB RT 3 W BURKE MILL STR EX STR 11834 | 0003 | Primary | Bridge Rehab w/o Added Capacity | VDOT | Mathews County | SALUDA | Fredericksburg | NonMPO:NonMPO | Infrastructure Investment/Asset Management Division | Khalil Minhas | Khalil.Minhas@vdot.virginia.gov | (540) 374-3369 | Khalil Minhas | Khalil.Minhas@vdot.virginia.gov | (540) 374-3369 |  |  |  | 0 |  | 1 | FY2026 | 5520000 | 5520000 | NO DATES SET YET-PE OPEN | G | Start Development milestone finished 765 days early | G | Project is on budget | [5 empty] | 2022-06-20 | 2020-05-27 | 2022-07-01 | 2020-05-27 | G | 2022-07-05 | 2020-06-01 | 2023-02-10 |  | G | [5 empty] | 2024-01-03 |  | 2024-01-18 |  | G | 2024-12-13 |  | 2024-12-27 |  | G | 2025-07-22 |  | 2026-01-30 |  | G | 2025-01-14 |  | 2025-07-21 |  | G | 2024-12-12 |  | 2025-08-15 |  | G | [5 empty] | 2026-02-10 |  | 2026-02-10 |  | G | 2026-04-02 |  | 2026-04-22 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.13641
556 | 111526 | Rte. 674 Reconstruct Non-Hardsurfaced Rd (R) | 0674 | Secondary | Reconstruction w/o Added Capacity | VDOT | Augusta County | HARRISONBURG | Staunton | NonMPO:NonMPO | Infrastructure Investment Division | Donald F Komara | Donald.Komara@VDOT.Virginia.gov | (540) 434-2587 | William B Clark | William3.Clark@VDOT.Virginia.gov | (540) 248-9330 |  |  |  | 0 |  | 0 | FY2026 | 500000 | 500000 | NO DATES SET YET | G | Start Development milestone is 638 days ahead of the expected completion date | G | Project is on budget | [5 empty] | 2022-10-31 |  | 2022-11-21 |  | G | 2022-11-22 |  | 2023-09-25 |  | G | [5 empty] | 2024-04-29 |  | 2024-05-24 |  | G | 2025-01-21 |  | 2025-02-25 |  | G | 2025-07-24 |  | 2025-11-24 |  | G | 2025-03-12 |  | 2025-08-07 |  | G | 2025-04-14 |  | 2025-09-10 |  | G | [5 empty] | 2025-12-09 |  | 2025-12-09 |  | G | 2026-03-04 |  | 2026-03-04 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | SAAP CONTRACT | 0 | 0 | 0.081925
557 | 112779 | POPLAR TREE ROAD BRIDGE | 4831 | Secondary | Bridge, New Construction | VDOT | Fairfax County | FAIRFAX | Northern Virginia | Northern Virginia:Fairfax County | Infrastructure Investment Division | Harinderbir S Warraich | HS.Warraich@VDOT.Virginia.gov | (571) 459-2362 | Harinderbir S Warraich | HS.Warraich@VDOT.Virginia.gov | (571) 459-2362 |  |  |  | 0 |  | 0 | FY2019 | 6000000 | 6000000 | AWARDED | G | Start Delivery milestone finished on-time | G | Project is on budget | [10 empty] | 2018-02-22 | 2018-02-22 | 2018-06-28 | 2018-06-28 | G | [35 empty] | 2018-07-02 | 2018-07-02 | 2018-07-09 | 2018-07-09 | G | 2018-07-10 | 2018-07-10 | 2018-07-18 | 2018-07-18 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | WORK/TASK ORDER | 1 | 0 | 0.096492
558 | 113252 | TRAFFIC SIGNAL UPGRADES FOR EAST FALLS CHURCH STREETS | 9999 | Miscellaneous | Traffic Management/Engineering | Locally | Arlington County | FAIRFAX | Northern Virginia | Northern Virginia:Arlington County | Local Assistance Division | Amir Salahshoor | A.Salahshoor@VDOT.Virginia.gov | (703) 259-1957 | Susie X Lue | Susie.Lue@vdot.virginia.gov | (703) 259-2918 | Amit Sidhaye |  |  | 0 |  | 0 | FY2023 | 2150000 | 1520515 | ACTIVITY DATES SET | G | Complete Purchasing Right-of-Way milestone finished 560 days early | G | Project is on budget | 2018-10-31 | 2018-08-15 | 2019-03-29 | 2018-11-26 | G | 2019-04-01 | 2018-11-27 | 2019-04-30 | 2018-12-27 | G | 2019-11-01 | 2019-03-27 | 2020-05-29 | 2020-04-30 | G | [10 empty] | 2019-08-01 | 2020-09-14 | 2021-06-28 | 2020-09-15 | G | [5 empty] | 2021-05-03 | 2020-09-15 | 2022-03-29 | 2020-09-15 | G | [10 empty] | 2022-03-30 |  | 2022-08-29 |  | G | 2022-08-30 |  | 2023-01-27 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.20013
559 | 113568 | Roanoke River Greenway Bridge across Barnhardt Creek | 0000 | Urban | Facilities for Pedestrians and Bicycles | Locally | Roanoke | SALEM | Salem | Roanoke:Roanoke City | Infrastructure Investment Division | Cheryl B Becker | Cheryl.Becker@vdot.virginia.gov | (540) 492-2531 | Cheryl B Becker | Cheryl.Becker@vdot.virginia.gov | (540) 492-2531 | Luke Pugh | Luke.Pugh@roanokeva.gov | (540) 853-5208 | 0 |  | 0 | FY2021 | 897770 | 897770 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 30 days early | G | Project is on budget | 2018-10-01 | 2018-10-01 | 2018-12-28 | 2019-01-14 | R | 2018-12-31 | 2019-01-16 | 2019-01-03 | 2019-01-24 | R | 2019-01-04 | 2019-01-25 | 2019-08-01 | 2019-04-25 | G | [25 empty] | 2019-02-05 | 2019-02-05 | 2019-02-27 | 2019-02-27 | G | [5 empty] | 2020-06-02 | 2020-01-06 | 2020-07-07 | 2020-02-16 | G | 2020-12-02 | 2020-09-21 | 2020-12-02 | 2020-11-02 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.32122
560 | 114771 | EVERGREEN MILLS RD & WATSON RD - ICWS SIGNAL FLASHER INSTALL | 0860 | Secondary | Safety | VDOT | Loudoun County | LEESBURG | Northern Virginia | Northern Virginia:Loudoun County | Infrastructure Investment Division | Ivan M Horodyskyj | Ivan.Horodyskyj@VDOT.Virginia.gov | (703) 259-2330 | Jessica Paris | Jessica.Paris@vdot.virginia.gov | (703) 259-2409 | Kelly Griffin, Loudoun County DTCI | kelly.griffin@loudoun.gov | (703) 737-8299 | 0 |  | 0 | FY2020 | 415000 | 415000 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 34 days early | G | Project is on budget | [5 empty] | 2019-03-01 | 2019-03-01 | 2019-03-01 | 2019-03-05 | R | 2019-03-04 | 2019-03-11 | 2019-06-10 | 2019-03-25 | G | [5 empty] | 2019-04-29 | 2019-03-28 | 2019-05-03 | 2019-03-28 | G | [25 empty] | 2019-06-26 | 2019-05-29 | 2019-07-02 | 2019-06-05 | G | 2019-07-03 | 2019-06-05 | 2019-07-10 | 2019-06-06 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | WORK/TASK ORDER | 1 | 0 | 0.14299
561 | 115303 | #SGR20LP - PRIMARY EXTENSION PAVING FY20 - DUKE ST WB | 0236 | Urban | Resurfacing | Locally | Alexandria | FAIRFAX | Northern Virginia | Northern Virginia:Alexandria | Local Assistance Division | Amir Salahshoor | A.Salahshoor@VDOT.Virginia.gov | (703) 259-1957 | Rita Hockman | Rita.Hockman@vdot.virginia.gov | (804) 824-7421 | Mary Alice Winston | maryalice.winston@alexandriava.gov | (703) 746-4067 | 0 |  | 1 | FY2020 | 290000 | 290000 | CONSTRUCTION COMPLETED | R | Start Delivery milestone finished 38 days late | G | Project is on budget | 2019-07-01 | 2019-07-01 | 2019-09-30 | 2019-09-26 | G | [5 empty] | 2019-10-01 | 2019-09-28 | 2019-10-31 | 2019-09-28 | G | [25 empty] | 2019-09-27 | 2019-05-13 | 2019-11-27 | 2019-05-13 | G | [5 empty] | 2019-11-26 | 2020-03-01 | 2019-12-31 | 2020-03-03 | R | 2020-01-02 | 2020-04-06 | 2020-02-28 | 2020-04-06 | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.19741
562 | 115362 | City of Norfolk 884 E Indian River Rd - Paving | 0407 | Urban | Restoration and Rehabilitation | Locally | Norfolk | NORFOLK | Hampton Roads | Hampton Roads:Norfolk | Local Assistance Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Joshua D Negovan | Joshua.Negovan@vdot.virginia.gov | (757) 956-3347 | Eric Berger | eric.berger@norfolk.gov | (757) 823-4039 | 0 |  | 0 | FY2020 | 384285 | 384285 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 65 days early | G | Project is on budget | 2019-10-03 | 2019-10-03 | 2020-01-02 | 2019-12-30 | G | [5 empty] | 2019-10-03 | 2019-10-03 | 2019-10-16 | 2020-01-06 | R | [35 empty] | 2020-01-22 | 2020-01-16 | 2020-02-19 | 2020-01-21 | G | 2020-05-07 | 2020-03-03 | 2020-05-07 | 2020-03-03 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.10854
563 | 116006 | District-wide Curve Delineation Installations | 9999 | Miscellaneous | Safety | VDOT | Culpeper District-wide |  | Culpeper | NonMPO:NonMPO | Infrastructure Investment/Asset Management Division | Gregory J Cooley | Gregory.Cooley@vdot.virginia.gov | (434) 906-7979 | Caroline Awua-Mensah | Caroline.Awua-Mensah@vdot.virginia.gov | (540) 829-7618 |  |  |  | 0 |  | 0 | FY2024 | 3294008 | 3294008 | ACTIVITY DATES SET | G | Determine Requirements milestone finished on-time | G | Project is on budget | [5 empty] | 2020-06-29 | 2020-06-29 | 2020-07-13 | 2020-07-13 | G | 2020-07-14 | 2020-07-14 | 2020-08-10 | 2020-08-10 | G | [35 empty] | 2021-11-09 |  | 2024-04-09 |  | G | 2024-06-28 |  | 2024-06-28 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.10706
564 | 117089 | #REVSH21 LINK ROAD INTERSECTION IMPROVEMENTS AT RTE 501 | 9999 | Urban | Safety | Locally | Lynchburg | APPOMATTOX | Lynchburg | Lynchburg:Lynchburg | Local Assistance Division | Gregg Allen | Gregg.Allen@vdot.virginia.gov | (434) 426-5575 | Gregg Allen | Gregg.Allen@vdot.virginia.gov | (434) 426-5575 | LEE NEWLAND | lee.newland@lynchburgva.us | (434) 455-3947 | 0 |  | 0 | FY2025 | 2000200 | 2000200 | NO DATES SET YET | G | Agreement with Locality milestone is 106 days ahead of the expected completion date | G | Project is on budget | 2021-01-29 |  | 2021-06-07 |  | G | 2021-06-08 |  | 2021-06-28 |  | G | 2022-01-07 |  | 2022-05-03 |  | G | [10 empty] | 2023-08-22 |  | 2023-09-26 |  | G | [5 empty] | 2023-09-27 |  | 2024-03-04 |  | G | 2024-01-30 |  | 2024-06-26 |  | G | [5 empty] | 2024-06-05 |  | 2024-07-02 |  | G | 2024-09-20 |  | 2024-09-20 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.15129
565 | 117247 | ROUTE 706 - RESURFACE UNPAVED ROAD | 0706 | Secondary | Resurfacing | VDOT | Montgomery County | CHRISTIANSBURG | Salem | NonMPO:NonMPO | Infrastructure Investment Division | David D Clarke | David.Clarke@VDOT.Virginia.gov | (540) 381-7190 | Christopher L Price | Christopher.Price@VDOT.Virginia.gov | (540) 381-7182 |  |  |  | 0 |  | 0 | FY2029 | 1300000 | 1300000 | NO DATES SET YET | G | Start Development milestone is 1545 days ahead of the expected completion date | G | Project is on budget | [5 empty] | 2025-04-28 |  | 2025-05-16 |  | G | 2025-05-19 |  | 2026-03-24 |  | G | [5 empty] | 2026-10-20 |  | 2026-11-17 |  | G | 2027-07-13 |  | 2027-08-16 |  | G | 2028-01-21 |  | 2028-05-19 |  | G | 2027-08-31 |  | 2028-02-04 |  | G | 2027-10-13 |  | 2028-03-20 |  | G | [5 empty] | 2028-06-13 |  | 2028-06-13 |  | G | 2028-08-31 |  | 2028-08-31 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | SAAP CONTRACT | 0 | 0 | 0.072829
566 | 118112 | #SGR21LP RTE 501 - (ID6619) RESURFACING (WILBORN AVE) | 6501 | Urban | Resurfacing | VDOT | South Boston | HALIFAX | Lynchburg | NonMPO:NonMPO | Local Assistance Division | Kevin S Chisnell | Kevin.Chisnell@VDOT.Virginia.gov | (434) 856-8113 | Kevin S Chisnell | Kevin.Chisnell@VDOT.Virginia.gov | (434) 856-8113 | C. T. CROWDER | ccrowder@southbostonva.us | (434) 575-4261 | 0 |  | 1 | FY2022 | 58461 | 58461 | ADVERTISED | G | Solicit Bids milestone finished 28 days early | G | Project is on budget | [10 empty] | 2021-01-29 | 2020-10-15 | 2021-02-11 | 2020-11-20 | G | [35 empty] | 2021-02-09 | 2021-01-12 | 2021-02-09 | 2021-01-12 | G | 2021-04-29 |  | 2021-07-15 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.061569
567 | 118301 | #SGR21VB - Rt 58 over Buffalo Ck - Brdge Repl - FED ID 11884 | 0058 | Primary | Bridge Replacement w/o Added Capacity | VDOT | Mecklenburg County | SOUTH HILL | Richmond | NonMPO:NonMPO | Infrastructure Investment/Asset Management Division | Raymond Chapman | Scott.Chapman@vdot.virginia.gov | (804) 609-5277 | Raymond Chapman | Scott.Chapman@vdot.virginia.gov | (804) 609-5277 |  |  |  | 0 |  | 0 | FY2026 | 17536497 | 17536497 | NO DATES SET YET | G | Start Development milestone is 61 days ahead of the expected completion date | G | Project is on budget | [5 empty] | 2021-04-05 |  | 2021-04-23 |  | G | 2021-04-26 |  | 2022-07-07 |  | G | [5 empty] | 2023-08-03 |  | 2023-09-14 |  | G | 2024-10-04 |  | 2024-11-08 |  | G | 2025-06-05 |  | 2025-10-03 |  | G | 2024-12-05 |  | 2025-06-26 |  | G | 2024-11-13 |  | 2025-07-21 |  | G | [5 empty] | 2025-10-14 |  | 2025-10-14 |  | G | 2026-01-08 |  | 2026-01-08 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.072146
568 | 55471 | RTE. 718 OVER PIGG RIVER (STR. 07926) - BRIDGE REPLACEMENT | 0718 | Secondary | Bridge Replacement w/o Added Capacity | VDOT | Franklin County | BEDFORD | Salem | NonMPO:NonMPO | Infrastructure Investment Division | Anthony T Marshall | Todd.Marshall@VDOT.Virginia.gov | (540) 387-5460 | Anthony L Handy | Tony.Handy@VDOT.Virginia.gov | (540) 352-9050 |  |  |  | 0 |  | 0 | FY2021 | 5349413 | 5349413 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 361 days early | G | Project is on budget | [5 empty] | 2008-05-14 | 2008-05-14 | 2008-05-14 | 2008-05-14 | G | 2015-07-29 | 2015-07-29 | 2016-05-23 | 2017-06-21 | R | 2016-03-15 | 2016-03-15 | 2016-05-23 | 2016-05-23 | G | [5 empty] | 2017-06-30 | 2017-06-30 | 2017-07-17 | 2017-07-17 | G | 2018-03-15 | 2018-03-15 | 2020-09-11 | 2018-12-24 | G | 2017-08-24 | 2017-08-24 | 2018-03-01 | 2018-03-01 | G | 2017-06-22 | 2017-06-22 | 2020-11-10 | 2019-09-18 | G | [5 empty] | 2018-09-13 | 2020-01-28 | 2020-11-10 | 2020-01-28 | G | 2020-11-30 | 2020-03-30 | 2021-03-26 | 2020-03-30 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.10321
569 | 78825 | Route 522, Fred. Co., Str. ID 08156 Brg Repl. Fed ID-08156 | 0522 | Primary | Bridge Replacement w/o Added Capacity | VDOT | Frederick County | EDINBURG | Staunton | Winchester:Frederick County | Infrastructure Investment Division | Eulogio A Javier | Eulogio.Javier@VDOT.Virginia.gov | (540) 332-9105 | James T Johnston | james.johnston@VDOT.virginia.gov | (540) 332-7795 |  |  |  | 0 |  | 0 | FY2022 | 6617111 | 4329248 | ACTIVITY DATES SET | G | Obtained Permits milestone finished 29 days early | G | Project is on budget | [5 empty] | 2008-12-15 | 2008-12-15 | 2009-07-29 | 2008-12-15 | G | 2013-07-15 | 2013-04-02 | 2013-08-15 | 2013-04-02 | G | [5 empty] | 2018-08-09 | 2018-08-29 | 2018-09-05 | 2018-09-18 | R | 2019-02-06 | 2019-02-06 | 2019-02-28 | 2019-02-28 | G | 2020-04-30 | 2019-03-05 | 2020-11-19 | 2019-03-05 | G | 2019-04-23 | 2019-03-05 | 2020-11-19 | 2019-03-05 | G | 2019-01-03 | 2019-09-23 | 2020-03-11 | 2020-02-11 | G | [5 empty] | 2021-10-28 |  | 2021-11-09 |  | G | 2022-01-20 |  | 2022-03-22 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.053711
570 | 114053 | COCHRAN MILL ROAD - RECONSTRUCT AND PAVE | 0653 | Secondary | Reconstruction w/o Added Capacity | VDOT | Loudoun County | LEESBURG | Northern Virginia | Northern Virginia:Loudoun County | Infrastructure Investment Division | Kimberly Mccool | Kimberly.McCool@vdot.virginia.gov | (703) 259-3220 | Kimberly Mccool | Kimberly.McCool@vdot.virginia.gov | (703) 259-3220 | Susan Glass, Loudoun County DTCI | susan.glass@loudoun.gov | (703) 777-0251 | 0 |  | 0 | FY2023 | 2689390 | 2689390 | NO DATES SET YET | G | Start Development milestone is 495 days ahead of the expected completion date | Y | Estimate not current | [5 empty] | 2022-07-01 |  | 2022-07-01 |  | G | 2022-07-05 |  | 2022-10-11 |  | G | [5 empty] | 2022-10-25 |  | 2022-11-07 |  | G | [25 empty] | 2022-11-28 |  | 2022-12-02 |  | G | 2022-12-05 |  | 2022-12-09 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | WORK/TASK ORDER | 0 | 1 | 0.21962
571 | 115245 | #SMART20 General Booth Blvd/Oceana Blvd Intersection Improve |  | Urban | Reconstruction w/ Added Capacity | Locally | Virginia Beach | NORFOLK | Hampton Roads | Hampton Roads:Virginia Beach | Infrastructure Investment Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Marci Thompson | Marci.Thompson@vdot.virginia.gov | (757) 956-3093 | Katie Shannon | kshannon@vbgov.com | (757) 385-1514 | 1 | 2020 | 0 | FY2027 | 4100277 | 4100277 | NO DATES SET YET | G | Agreement with Locality milestone is 914 days ahead of the expected completion date | G | Project is on budget | 2023-06-01 |  | 2023-08-24 |  | G | 2023-08-25 |  | 2023-09-08 |  | G | 2023-09-11 |  | 2024-08-26 |  | G | [10 empty] | 2025-06-09 |  | 2025-06-27 |  | G | [5 empty] | 2025-07-01 |  | 2026-07-16 |  | G | 2024-04-26 |  | 2024-12-31 |  | G | [5 empty] | 2026-08-03 |  | 2026-08-28 |  | G | 2026-11-19 |  | 2026-11-19 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.20155
572 | 115356 | #SGR20LP - Franklin Bypass | 0058 | Urban | Restoration and Rehabilitation | Locally | Suffolk | NORFOLK | Hampton Roads | Hampton Roads:Suffolk | Infrastructure Investment/Asset Management Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Johndel A Alcaide | John.Alcaide@vdot.virginia.gov | (757) 956-3098 | Edward Heide | eheide@suffolkva.us | (757) 514-7615 | 0 |  | 1 | FY2020 | 382758 | 382758 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 188 days early | G | Project is on budget | 2019-10-01 | 2019-10-01 | 2019-12-30 | 2019-10-25 | G | [5 empty] | 2019-10-01 | 2019-10-01 | 2019-10-14 | 2019-10-14 | G | [35 empty] | 2020-01-16 | 2019-10-25 | 2020-02-14 | 2019-10-30 | G | 2020-03-10 | 2019-10-25 | 2020-05-05 | 2019-10-30 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.081284
573 | 115490 | #SMART20 RTE 29 - CONSTRUCT RCUT AT INTERSECTION OF RTE 6 | 0029 | Primary | Safety | VDOT | Nelson County | DILLWYN | Lynchburg | NonMPO:NonMPO | Infrastructure Investment Division | Robert F Guercia | Robert.Guercia@VDOT.Virginia.gov | (434) 841-6864 | Raina A Rosado | Raina.Rosado@VDOT.Virginia.gov | (434) 856-8318 |  |  |  | 1 | 2020 | 0 | FY2024 | 2725677 | 2725677 | NO DATES SET YET-PE OPEN | R | Determine Requirements milestone is 66 days past the expected completion date | G | Project is on budget | [5 empty] | 2020-04-15 | 2020-03-31 | 2020-04-28 | 2020-03-31 | G | 2020-04-29 |  | 2020-12-17 |  | R | [5 empty] | 2021-09-15 |  | 2021-09-28 |  | G | 2023-01-05 |  | 2023-01-20 |  | G | 2023-08-10 |  | 2024-02-21 |  | G | 2023-02-07 |  | 2023-08-10 |  | G | [10 empty] | 2024-03-12 |  | 2024-03-12 |  | G | 2024-05-31 |  | 2024-05-31 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.095713
574 | 117057 | Dominion Blvd Intersection Improvements Phase 2 | 0250 | Secondary | Reconstruction w/o Added Capacity | Locally | Henrico County | ASHLAND | Richmond | Richmond:Henrico County | Local Assistance Division | Cynthia Crouch | Cynthia.Crouch@vdot.virginia.gov | (804) 609-5313 | Cynthia Crouch | Cynthia.Crouch@vdot.virginia.gov | (804) 609-5313 | TBD |  | TBD | 0 |  | 0 | FY2029 | 462540 | 462540 | NO DATES SET YET | G | Agreement with Locality milestone is 1543 days ahead of the expected completion date | G | Project is on budget | 2025-01-06 |  | 2025-05-14 |  | G | 2025-05-15 |  | 2025-06-05 |  | G | 2025-12-15 |  | 2026-04-10 |  | G | [10 empty] | 2027-07-30 |  | 2027-09-02 |  | G | [5 empty] | 2027-09-03 |  | 2028-02-09 |  | G | 2028-01-05 |  | 2028-06-05 |  | G | [5 empty] | 2028-05-12 |  | 2028-06-09 |  | G | 2028-08-29 |  | 2028-08-29 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.32268
575 | 117164 | #SGR21LP 131-City of Chesapeake 1539 Mount Pleasant Rd | 0165 | Urban | Resurfacing | Locally | Chesapeake | NORFOLK | Hampton Roads | Hampton Roads:Chesapeake | Infrastructure Investment/Asset Management Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Johndel A Alcaide | John.Alcaide@vdot.virginia.gov | (757) 956-3098 | Sam Sawan | ssawan@cityofchesapeake.net | (757) 382-8263 | 0 |  | 0 | FY2022 | 292517 | 292517 | NO DATES SET YET | G | Agreement with Locality milestone is 80 days ahead of the expected completion date | G | Project is on budget | 2021-01-04 |  | 2021-05-12 |  | G | 2021-05-13 |  | 2021-06-03 |  | G | 2021-07-02 |  | 2021-08-04 |  | G | [25 empty] | 2021-07-08 |  | 2021-08-04 |  | G | [5 empty] | 2021-10-01 |  | 2021-10-29 |  | G | 2022-01-26 |  | 2022-01-26 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.080982
576 | 118088 | IRA HOFFMAN LANE SIDEWALK EXTENSION | 0694 | Urban | Facilities for Pedestrians and Bicycles | Locally | Culpeper | WARRENTON | Culpeper | NonMPO:NonMPO | Local Assistance Division | Gregory J Cooley | Gregory.Cooley@vdot.virginia.gov | (434) 906-7979 | John P Price | John.Price@VDOT.Virginia.gov | (540) 347-6371 | SALEM BUSH | sbush@culpeperva.gov | (540) 829-8260 | 0 |  | 0 | FY2024 | 497036 | 497036 | NO DATES SET YET | G | Agreement with Locality milestone is 171 days ahead of the expected completion date | G | Project is on budget | 2021-04-06 |  | 2021-08-11 |  | G | 2021-08-12 |  | 2021-09-01 |  | G | 2022-03-17 |  | 2022-07-08 |  | G | [25 empty] | 2023-07-05 |  | 2023-12-05 |  | G | [5 empty] | 2024-02-06 |  | 2024-03-05 |  | G | 2024-05-22 |  | 2024-05-22 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.11446
577 | 118248 | APS RETROFITS NORTHERN VIRGINIA - PH2 | 9999 | Miscellaneous | Safety | VDOT | Northern Virginia District-wide |  | Northern Virginia | Northern Virginia:Northern Virginia District-wide | Infrastructure Investment Division | Nikolaos Dais | Nick.Dais@vdot.virginia.gov | (703) 259-2237 | Jessica Paris | Jessica.Paris@vdot.virginia.gov | (703) 259-2409 |  |  |  | 0 |  | 0 | FY2021 | 82245 | 82245 | AWARDED | G | Start Delivery milestone finished 93 days early | G | Project is on budget | [10 empty] | 2021-01-29 | 2020-09-18 | 2021-06-07 | 2021-01-05 | G | [35 empty] | 2021-05-10 | 2021-02-17 | 2021-05-14 | 2021-02-17 | G | 2021-05-17 | 2021-02-17 | 2021-05-21 | 2021-02-17 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | WORK/TASK ORDER | 1 | 0 | 0.07389
578 | 5559 | ROLLING ROAD - RTE 638 - WIDEN TO 4 LANES - PH II | 0638 | Secondary | Reconstruction w/ Added Capacity | VDOT | Fairfax County | FAIRFAX | Northern Virginia | Northern Virginia:Fairfax County | Infrastructure Investment Division | Andrew G Beacher | Andrew.Beacher@vdot.virginia.gov | (703) 259-2239 | Christopher Barksdale | Chris.Barksdale@vdot.virginia.gov | (703) 259-2768 |  |  |  | 0 |  | 0 | FY2023 | 56131877 | 73220039 | ACTIVITY DATES SET | R | Start Purchasing Right-of-Way milestone finished 116 days late | R | Project estimate is greater than $10M and is over budget by (a) 10% or more or (b) $5M or more | [5 empty] | 1987-07-13 | 1987-07-12 | 1987-07-13 | 1987-07-13 | G | 2015-11-02 | 2015-11-02 | 2018-06-29 | 2018-10-19 | R | [5 empty] | 2018-03-30 | 2018-03-30 | 2018-11-06 | 2019-07-25 | R | 2019-08-02 | 2019-10-31 | 2019-08-15 | 2019-12-09 | R | 2020-09-02 |  | 2022-06-08 |  | G | 2019-10-17 | 2020-02-05 | 2021-07-30 |  | G | 2020-12-01 |  | 2022-05-06 |  | G | [5 empty] | 2022-06-09 |  | 2022-07-12 |  | G | 2022-07-13 |  | 2022-12-30 |  | G | Design plans are being revised | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 1 | 0.27323
580 | 104377 | Traffic Signal Mast Arm conversion | 0143 | Primary | Traffic Management/Engineering | Locally | Newport News | WILLIAMSBURG | Hampton Roads | Hampton Roads:Newport News | Local Assistance Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Chessica Villaflores | Chessica.Villaflores@vdot.virginia.gov | (757) 956-3094 | Bridjette Parker | bjparker@nnva.gov | (757) 926-8314 | 0 |  | 0 | FY2020 | 447472 | 673932 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 206 days early | R | Project estimate is less than $5M and is 20% or more over budget | [5 empty] | 2013-11-05 | 2015-05-26 | 2013-11-05 | 2015-05-28 | R | 2014-05-01 | 2014-05-01 | 2014-09-01 | 2014-10-24 | R | [10 empty] | 2016-05-02 | 2016-05-02 | 2016-08-08 | 2016-08-08 | G | [20 empty] | 2014-10-01 | 2015-02-27 | 2018-08-31 | 2019-01-02 | R | 2019-03-28 | 2019-02-04 | 2019-09-16 | 2019-02-22 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.26402
581 | 105521 | #HB2.FY17 WIDEN EAST SPRING STREET | 0675 | Urban | Reconstruction w/ Added Capacity | VDOT | Herndon | FAIRFAX | Northern Virginia | Northern Virginia:Herndon | Infrastructure Investment Division | Terry Yates | Terry.Yates@vdot.virginia.gov | (703) 259-2118 | Hamid R Misaghian | H.Misaghian@VDOT.Virginia.gov | (703) 259-1795 | Dana Singer | dana.singer@herndon-va.gov | (703) 435-6853 | 1 | 2017 | 0 | FY2021 | 6705000 | 14602827 | ACTIVITY DATES SET | R | Complete Purchasing Right-of-Way milestone is 359 days past the expected completion date | R | Project estimate is between $5M and $10M and is a $1M or more over budget | [5 empty] | 2017-09-01 | 2017-09-01 | 2017-10-02 | 2017-09-01 | G | 2017-11-14 | 2017-09-01 | 2018-02-14 | 2018-02-14 | G | [5 empty] | 2018-03-30 | 2018-04-12 | 2018-06-28 | 2018-07-23 | R | 2018-12-27 | 2019-04-03 | 2019-03-29 | 2019-05-14 | R | 2019-08-01 | 2020-07-07 | 2020-07-31 |  | R | 2019-03-29 | 2019-06-18 | 2020-02-28 |  | R | [10 empty] | 2020-06-01 |  | 2020-08-03 |  | R | 2020-08-31 |  | 2020-12-17 |  | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 1 | 0.22564
582 | 106963 | SIDEWALKS TO METRORAIL - KINGSLEY RD SW | 9999 | Urban | Facilities for Pedestrians and Bicycles | Locally | Vienna | FAIRFAX | Northern Virginia | Northern Virginia:Vienna | Infrastructure Investment Division | Amir Salahshoor | A.Salahshoor@VDOT.Virginia.gov | (703) 259-1957 | Rhoderick M Undan | Rhoderick.Undan@vdot.virginia.gov | (703) 259-3347 | Michael Gallagher | Michael.Gallagher@viennava.gov | (703) 255-6382 | 0 |  | 0 | FY2023 | 487500 | 487500 | NO DATES SET YET | R | Agreement with Locality milestone is 438 days past the expected completion date | G | Project is on budget | 2019-08-01 |  | 2019-12-11 |  | R | 2019-12-12 |  | 2020-01-03 |  | R | 2020-07-13 |  | 2020-11-03 |  | R | [25 empty] | 2021-10-29 |  | 2022-04-05 |  | G | [5 empty] | 2022-06-02 |  | 2022-06-29 |  | G | 2022-09-19 |  | 2022-09-19 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.17907
583 | 108887 | #SMART18 - HARROWGATE ROAD/COUGAR TRAIL - PEDESTRIAN IMPROVE | 0144 | Urban | Safety | Locally | Chesterfield County | CHESTERFIELD | Richmond | Richmond:Chesterfield County | Infrastructure Investment Division | Michael S Gray | Mike.Gray@vdot.virginia.gov | (804) 609-5347 | Michael S Gray | Mike.Gray@vdot.virginia.gov | (804) 609-5347 | Barb Smith | smithbk@chesterfield.gov | (804) 748-1037 | 1 | 2018 | 0 | FY2022 | 890000 | 1694000 | ACTIVITY DATES SET | G | Complete Purchasing Right-of-Way milestone finished 70 days early | R | Project estimate is less than $5M and is 20% or more over budget | 2021-07-02 | 2018-08-01 | 2021-09-27 | 2018-11-05 | G | 2019-09-30 | 2018-11-22 | 2019-09-30 | 2018-11-29 | G | 2021-10-01 | 2018-11-30 | 2022-04-13 | 2020-01-22 | G | [5 empty] | 2020-05-01 | 2020-05-01 | 2020-05-29 | 2020-05-15 | G | 2020-06-08 | 2020-06-08 | 2020-06-29 | 2020-06-22 | G | 2021-02-01 | 2020-11-23 | 2021-04-30 |  | G | 2020-07-31 | 2020-06-29 | 2021-01-29 | 2020-11-20 | G | 2020-12-28 |  | 2021-08-30 |  | G | [5 empty] | 2021-08-31 |  | 2021-08-31 |  | G | 2021-11-30 |  | 2021-11-30 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.14406
584 | 108908 | #HB2.FY17 US220 Communications and Adaptive System Project | 0220 | Primary | Traffic Management/Engineering | VDOT | Roanoke | SALEM | Salem | Roanoke:Roanoke City | Infrastructure Investment Division | Anne C Booker | Anne.Booker@VDOT.Virginia.gov | (540) 375-0143 | John L Bisnett | John.Bisnett@vdot.virginia.gov | (540) 529-5742 | Christina Finch | cfinch@rvarc.org | (540) 343-4417 | 1 | 2017 | 0 | FY2017 | 422500 | 422500 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 26 days early | G | Project is on budget | [5 empty] | 2016-07-11 | 2016-07-11 | 2016-09-02 | 2016-09-02 | G | 2016-09-26 | 2016-09-26 | 2016-11-29 | 2016-11-29 | G | [5 empty] | 2016-11-29 | 2016-11-29 | 2016-11-29 | 2016-11-29 | G | [5 empty] | 2016-10-06 | 2016-11-14 | 2016-10-06 | 2016-11-14 | R | [15 empty] | 2017-03-14 | 2017-03-14 | 2017-03-14 | 2017-03-14 | G | 2017-05-03 | 2017-04-14 | 2017-05-23 | 2017-04-27 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | WORK/TASK ORDER | 1 | 1 | 0.27346
585 | 109376 | #HB2.FY17 I-81 Exit 323 SB Accel and NB Decel Lane Extension | 0081 | Interstate | Safety | VDOT | Frederick County | EDINBURG | Staunton | Winchester:Frederick County | Infrastructure Investment Division | Ronald L Tabor | Ronald.Tabor@vdot.virginia.gov | (540) 332-7887 | John-Allen L Ennis | JohnAllen.Ennis@VDOT.Virginia.gov | (540) 332-9118 |  |  |  | 1 | 2017 | 0 | FY2020 | 3450904 | 1887403 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 285 days early | G | Project is on budget | [5 empty] | 2017-08-01 | 2017-07-24 | 2017-08-14 | 2017-08-03 | G | 2017-08-15 | 2017-08-04 | 2018-04-11 | 2018-04-11 | G | [5 empty] | 2019-05-01 | 2018-06-06 | 2019-05-01 | 2018-06-06 | G | [5 empty] | 2019-06-19 | 2018-06-18 | 2019-10-10 | 2018-06-18 | G | [5 empty] | 2019-06-04 | 2018-08-13 | 2019-09-04 | 2018-08-13 | G | [5 empty] | 2019-11-12 | 2019-01-08 | 2019-11-12 | 2019-01-08 | G | 2020-01-07 | 2019-04-19 | 2020-01-29 | 2019-04-19 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.064728
586 | 109549 | #HB2.FY17 WARRENTON PARK AND RIDE LOT EXPANSION AT 29/605 | 0029 | Primary | Other | VDOT | Fauquier County | WARRENTON | Culpeper | NonMPO:NonMPO | Infrastructure Investment Division | Gregory J Cooley | Gregory.Cooley@vdot.virginia.gov | (434) 906-7979 | Satish K Airi | Satish.Airi@VDOT.virginia.gov | (540) 829-7395 |  |  |  | 1 | 2017 | 0 | FY2020 | 900000 | 930837 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 209 days early | Y | Project estimate is less than $5M and is up to 20% over budget | [5 empty] | 2016-08-19 | 2016-08-19 | 2016-09-07 | 2016-09-07 | G | 2016-09-21 | 2016-09-21 | 2017-08-18 | 2017-08-10 | G | [5 empty] | 2018-07-20 | 2018-03-23 | 2018-08-02 | 2018-04-16 | G | 2019-04-05 | 2018-12-06 | 2019-04-18 | 2018-12-19 | G | 2019-06-03 | 2018-11-05 | 2019-08-26 | 2018-11-05 | G | 2019-05-06 | 2019-01-07 | 2019-07-30 | 2019-01-07 | G | [10 empty] | 2019-10-08 | 2019-03-12 | 2019-10-08 | 2019-03-12 | G | 2019-12-03 | 2019-05-28 | 2019-12-23 | 2019-05-28 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.089883
587 | 109591 | PROVIDE SD ESMNT/SIGNAL AT WILLIAMSON BLVD STONEHOUSE DR | 1596 | Secondary | Safety | VDOT | Prince William County | MANASSAS | Northern Virginia | Northern Virginia:Prince William County | Infrastructure Investment Division | Ivan M Horodyskyj | Ivan.Horodyskyj@VDOT.Virginia.gov | (703) 259-2330 | Jessica Paris | Jessica.Paris@vdot.virginia.gov | (703) 259-2409 |  |  |  | 0 |  | 0 | FY2022 | 1060115 | 909000 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 806 days early | G | Project is on budget | [5 empty] | 2016-07-01 | 2016-07-01 | 2016-07-15 | 2016-07-13 | G | 2016-07-18 | 2017-02-08 | 2017-08-10 | 2018-02-07 | R | 2018-03-15 | 2018-03-14 | 2018-07-06 | 2018-04-19 | G | [5 empty] | 2019-11-22 | 2018-11-09 | 2019-12-09 | 2019-02-26 | G | 2021-02-18 | 2018-07-09 | 2021-10-11 | 2018-07-09 | G | 2019-12-12 | 2019-03-04 | 2020-08-06 | 2019-10-24 | G | [10 empty] | 2022-02-22 | 2019-12-24 | 2022-02-22 | 2020-01-27 | G | 2022-04-06 | 2020-02-04 | 2022-04-26 | 2020-02-10 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | WORK/TASK ORDER | 1 | 0 | 0.14443
588 | 110784 | RTE 634 - DECK REPLACEMENT ON MAIDENS RD-Bridge Only | 0634 | Secondary | Bridge Replacement w/o Added Capacity | VDOT | Goochland County | ASHLAND | Richmond | NonMPO:NonMPO | Infrastructure Investment/Asset Management Division | Phillip Frazer | Phillip.Frazer@vdot.virginia.gov | (804) 481-0906 | Lawrence Ramsey | Brian.Ramsey@VDOT.Virginia.gov | (804) 585-3579 |  |  |  | 0 |  | 0 | FY2020 | 782223 | 782223 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 142 days early | G | Project is on budget | [5 empty] | 2017-07-13 | 2017-07-13 | 2017-08-03 | 2017-08-03 | G | 2017-08-04 | 2017-08-04 | 2018-07-03 | 2018-09-11 | R | [5 empty] | 2018-09-12 | 2018-09-10 | 2018-10-05 | 2018-10-03 | G | 2018-10-31 | 2018-10-12 | 2018-10-31 | 2018-10-12 | G | 2018-09-05 | 2018-09-05 | 2018-09-05 | 2018-09-05 | G | 2018-10-31 | 2018-10-12 | 2018-10-31 | 2018-10-12 | G | [10 empty] | 2019-08-13 | 2019-04-23 | 2019-08-13 | 2019-04-23 | G | 2019-10-03 | 2019-06-26 | 2019-11-15 | 2019-06-26 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | REGIONAL ON-CALL CONTRACT | 1 | 0 | 0.068525
589 | 110864 | SHOULDER RUMBLE STRIPS - DISTRICT WIDE | 9999 | Primary | Safety | VDOT | Stafford County | FREDERICKSBURG | Fredericksburg | NonMPO:NonMPO | Infrastructure Investment Division | Peter A Hedrich | Peter.Hedrich@vdot.virginia.gov | (540) 899-4540 | Jessica Graves | Jessica.Graves@vdot.virginia.gov | (540) 899-4267 |  |  |  | 0 |  | 0 | FY2022 | 990000 | 990000 | NO DATES SET YET | G | Start Development milestone is 226 days ahead of the expected completion date | G | Project is on budget | [5 empty] | 2021-09-15 |  | 2021-10-05 |  | G | 2021-10-06 |  | 2022-01-21 |  | G | [5 empty] | 2022-02-03 |  | 2022-02-16 |  | G | [25 empty] | 2022-03-07 |  | 2022-03-11 |  | G | 2022-03-14 |  | 2022-03-18 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | WORK/TASK ORDER | 0 | 0 | 0.066881
590 | 101043 | #SGR17VB - RT 681 - BRIDGE REHAB OVER WILLIAMS RUN Fed 01524 | 0681 | Secondary | Bridge Rehab w/o Added Capacity | VDOT | Amherst County | APPOMATTOX | Lynchburg | Lynchburg:Amherst County | Infrastructure Investment/Asset Management Division | Lindsey S Hodges | Lindsey.Hodges@vdot.virginia.gov | (434) 856-8143 | Lindsey S Hodges | Lindsey.Hodges@vdot.virginia.gov | (434) 856-8143 |  |  |  | 0 |  | 1 | FY2021 | 1837039 | 1492258 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 15 days early | G | Project is on budget | [10 empty] | 2020-07-01 | 2020-04-30 | 2020-08-12 | 2020-04-30 | G | [35 empty] | 2020-09-08 | 2020-09-08 | 2020-09-08 | 2020-09-08 | G | 2020-12-02 | 2020-11-17 | 2020-12-02 | 2020-11-17 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.14921
591 | 105266 | RESTON BIKESHARE INFRASTRUCTURE SUPPORT |  | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Fairfax County | FAIRFAX | Northern Virginia | Northern Virginia:Fairfax County | Local Assistance Division | Amir Salahshoor | A.Salahshoor@VDOT.Virginia.gov | (703) 259-1957 | Rita Hockman | Rita.Hockman@vdot.virginia.gov | (804) 824-7421 | David Loss | David.Loss@fairfaxcounty.gov | (703) 877-5619 | 0 |  | 0 | FY2019 | 545380 | 989181 | CONSTRUCTION STARTED | R | Start Delivery milestone finished 433 days late | R | Project estimate is less than $5M and is 20% or more over budget | 2015-01-02 | 2014-12-19 | 2015-03-31 | 2015-03-18 | G | 2016-01-15 | 2015-04-01 | 2016-01-15 | 2015-04-01 | G | 2016-11-01 | 2016-11-15 | 2016-12-31 | 2016-12-16 | G | [35 empty] | 2018-10-01 | 2019-09-19 | 2018-12-28 | 2019-09-19 | R | 2019-01-02 | 2019-09-23 | 2019-05-30 | 2020-08-05 | R | Delay due to changes in scope of work, project management, plan designs, or resolution of public comments | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.25538
592 | 106143 | CINDER BED ROAD BIKEWAY |  | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Fairfax County | FAIRFAX | Northern Virginia | Northern Virginia:Fairfax County | Local Assistance Division | Amir Salahshoor | A.Salahshoor@VDOT.Virginia.gov | (703) 259-1957 | Jeffrey S Daily | Jeff.Daily@VDOT.Virginia.gov | (703) 259-2993 | Jeffrey Fasceski | Jeffrey.Fasceski@fairfaxcounty.gov |  | 0 |  | 0 | FY2023 | 2000000 | 2000000 | ACTIVITY DATES SET | R | Determine Requirements milestone finished 82 days late | G | Project is on budget | 2015-03-18 | 2015-03-18 | 2015-03-18 | 2015-03-18 | G | 2015-05-27 | 2014-10-01 | 2015-05-27 | 2015-05-27 | G | 2019-06-04 | 2018-10-09 | 2020-07-31 | 2020-10-21 | R | [35 empty] | 2021-12-27 |  | 2022-06-17 |  | G | 2022-07-11 |  | 2022-12-23 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.26034
593 | 108685 | MAIN STREET INTERSECTION IMPROVEMENT | 0236 | Urban | Safety | Locally | Fairfax | FAIRFAX | Northern Virginia | Northern Virginia:Fairfax | Local Assistance Division | Amir Salahshoor | A.Salahshoor@VDOT.Virginia.gov | (703) 259-1957 | Rita Hockman | Rita.Hockman@vdot.virginia.gov | (804) 824-7421 | Wendy Block Sanford | wendy.sanford@fairfaxva.gov | (703) 385-7889 | 0 |  | 0 | FY2019 | 600000 | 600000 | WAITING FINANCIAL CLOSURE | R | Start Delivery milestone finished 25 days late | G | Project is on budget | 2016-07-01 | 2016-07-01 | 2016-09-26 | 2016-09-26 | G | 2016-09-27 | 2016-09-27 | 2016-09-29 | 2016-09-29 | G | 2016-09-30 | 2016-09-30 | 2017-04-12 | 2017-04-12 | G | [10 empty] | 2018-02-07 | 2018-02-06 | 2018-02-28 | 2018-02-06 | G | [5 empty] | 2018-03-02 | 2018-02-07 | 2018-12-10 | 2018-02-07 | G | [10 empty] | 2018-12-27 | 2018-11-28 | 2019-01-28 | 2019-02-18 | R | 2019-01-29 | 2019-02-19 | 2019-03-11 | 2019-04-05 | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.2686
594 | 108897 | #HB2.FY17 US 58 East Turn Lane at US 58/220 Bypass | 0058 | Primary | Safety | VDOT | Henry County | MARTINSVILLE | Salem | NonMPO:NonMPO | Infrastructure Investment Division | David M Kiser | David.Kiser@VDOT.Virginia.gov | (276) 627-1501 | David M Kiser | David.Kiser@VDOT.Virginia.gov | (276) 627-1501 | Lee H Clark | leclark@co.henry.va.us | (276) 634-4620 | 1 | 2017 | 0 | FY2020 | 1654198 | 1654198 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 66 days early | G | Project is on budget | [5 empty] | 2016-07-05 | 2016-06-24 | 2016-07-18 | 2016-06-24 | G | 2016-07-18 | 2016-07-18 | 2017-03-15 | 2017-03-15 | G | [5 empty] | 2017-07-28 | 2017-05-11 | 2017-07-28 | 2017-05-24 | G | [5 empty] | 2018-06-08 | 2017-09-28 | 2018-10-01 | 2017-09-28 | G | [5 empty] | 2018-05-23 | 2017-08-16 | 2019-04-11 | 2018-01-26 | G | [5 empty] | 2019-06-11 | 2019-04-23 | 2019-06-11 | 2019-04-23 | G | 2019-08-01 | 2019-07-29 | 2019-10-03 | 2019-07-29 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | SAAP CONTRACT | 1 | 0 | 0.06759
595 | 109312 | #HB2.FY17 U.S. 58 Corridor Intersection Capacity & Safety | 0058 | Urban | Reconstruction w/ Added Capacity | Locally | Norfolk | NORFOLK | Hampton Roads | Hampton Roads:Norfolk | Infrastructure Investment Division | Stephen Rowan | Steve.Rowan@vdot.virginia.gov | (757) 790-9925 | Joshua D Negovan | Joshua.Negovan@vdot.virginia.gov | (757) 956-3347 | Keith Darrow, P.E.. | Keith.darrow@norfolk.gov | (757) 664-7305 | 1 | 2017 | 0 | FY2020 | 2336605 | 2695300 | CONSTRUCTION STARTED | R | Start Delivery milestone finished 169 days late | Y | Project estimate is less than $5M and is up to 20% over budget | 2016-11-02 | 2016-11-02 | 2017-02-02 | 2016-12-29 | G | 2017-02-03 | 2016-12-29 | 2017-02-07 | 2017-01-19 | G | 2017-02-08 | 2017-01-20 | 2017-08-11 | 2018-02-06 | R | [10 empty] | 2018-02-07 | 2018-02-07 | 2018-12-31 | 2018-12-31 | G | [5 empty] | 2019-01-03 | 2019-01-03 | 2019-02-15 | 2019-05-09 | R | 2018-08-27 | 2018-04-16 | 2018-10-08 | 2018-06-29 | G | [5 empty] | 2018-10-24 | 2019-09-08 | 2019-03-29 | 2019-09-08 | R | 2019-04-01 | 2019-09-09 | 2019-09-18 | 2020-03-05 | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.33714
596 | 109530 | #HB2.FY17 RTE 601 - IMPROVE ROADWAY ALIGNMENT | 0601 | Secondary | Safety | VDOT | Halifax County | HALIFAX | Lynchburg | NonMPO:NonMPO | Infrastructure Investment Division | Renard Yeatts |  |  | Gregory K Parsons | Gregory.Parsons@vdot.virginia.gov | (434) 856-8297 |  |  |  | 1 | 2017 | 0 | FY2021 | 3016656 | 3016656 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 31 days early | G | Project is on budget | [5 empty] | 2016-08-24 | 2016-08-24 | 2016-08-24 | 2016-08-24 | G | 2016-08-17 | 2016-08-17 | 2017-02-22 | 2017-02-22 | G | [5 empty] | 2017-10-25 | 2017-10-25 | 2017-11-07 | 2017-11-07 | G | 2018-12-19 | 2018-12-13 | 2019-01-03 | 2018-12-14 | G | 2019-10-08 | 2019-09-26 | 2020-04-17 | 2020-03-13 | G | 2019-01-23 | 2019-01-24 | 2019-10-07 | 2019-09-25 | G | 2018-05-22 | 2018-05-22 | 2019-01-15 | 2019-01-15 | G | [5 empty] | 2020-05-12 | 2020-05-05 | 2020-05-12 | 2020-05-05 | G | 2020-06-26 | 2020-07-21 | 2020-08-21 | 2020-07-21 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.085517
597 | 109550 | #HB2.FY17 RTE 682 - RECONSTRUCTION | 0682 | Secondary | Reconstruction w/o Added Capacity | VDOT | Amherst County | APPOMATTOX | Lynchburg | Lynchburg:Amherst County | Infrastructure Investment Division | Raina A Rosado | Raina.Rosado@VDOT.Virginia.gov | (434) 856-8318 | Raina A Rosado | Raina.Rosado@VDOT.Virginia.gov | (434) 856-8318 |  |  |  | 1 | 2017 | 0 | FY2021 | 7855088 | 7855088 | ADVERTISED | R | Relocate Utilities milestone is 97 days past the expected completion date | G | Project is on budget | [5 empty] | 2017-01-17 | 2016-08-16 | 2017-01-30 | 2017-01-30 | G | 2017-01-31 | 2017-01-31 | 2017-12-26 | 2017-06-28 | G | [5 empty] | 2018-05-04 | 2018-05-04 | 2018-05-17 | 2018-05-17 | G | 2019-04-25 | 2019-04-25 | 2019-05-08 | 2019-05-08 | G | 2020-05-12 | 2020-04-28 | 2020-11-16 |  | R | 2019-05-24 | 2019-06-12 | 2020-05-11 | 2020-05-08 | G | 2018-10-12 | 2018-10-12 | 2019-10-14 | 2019-10-09 | G | [5 empty] | 2020-12-08 | 2020-12-08 | 2020-12-08 | 2020-12-08 | G | 2021-02-02 |  | 2021-02-23 |  | Y |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.18001
598 | 110097 | #SGR17VB - BRIDGE REPLACE RT 14 POROPOTANK CREEK ID 10588 | 0014 | Primary | Bridge Replacement w/o Added Capacity | VDOT | King & Queen County | SALUDA | Fredericksburg | NonMPO:NonMPO | Infrastructure Investment/Asset Management Division | Wesley Foor | Wesley.Foor@vdot.virginia.gov | (540) 604-1370 | Wesley Foor | Wesley.Foor@vdot.virginia.gov | (540) 604-1370 |  |  |  | 0 |  | 1 | FY2021 | 3452000 | 3452000 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 97 days early | G | Project is on budget | [5 empty] | 2016-10-03 | 2016-10-03 | 2016-10-26 | 2016-10-26 | G | 2016-10-27 | 2016-10-27 | 2018-04-11 | 2018-04-10 | G | [5 empty] | 2018-10-16 | 2018-10-16 | 2018-10-29 | 2018-10-26 | G | 2019-10-03 | 2019-08-01 | 2019-10-16 | 2019-08-22 | G | 2020-03-18 | 2020-04-21 | 2020-09-18 | 2020-09-04 | G | 2019-11-01 | 2019-11-04 | 2020-05-12 | 2020-04-16 | G | 2019-11-01 | 2019-09-12 | 2020-07-09 | 2020-02-28 | G | [5 empty] | 2020-10-13 | 2020-10-06 | 2020-10-13 | 2020-10-06 | G | 2021-01-25 | 2020-12-15 | 2021-03-22 | 2020-12-15 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.060535
599 | 110794 | #SMART18 - INT. IMPROVEMENTS AND ACCESS MGMT. Rtes. 11 & 140 | 0011 | Primary | Reconstruction w/o Added Capacity | VDOT | Abingdon | ABINGDON | Bristol | Bristol:Abingdon | Infrastructure Investment Division | Tamara D Pritchard | Tamara.Pritchard@VDOT.Virginia.gov | (276) 696-3249 | Brandi Halloway | Brandi.Halloway@vdot.virginia.gov | (276) 696-3254 |  |  |  | 1 | 2018 | 0 | FY2023 | 1113000 | 1113000 | ACTIVITY DATES SET | G | Determine Requirements milestone finished 169 days early | G | Project is on budget | [5 empty] | 2020-07-10 | 2020-02-03 | 2020-07-23 | 2020-02-24 | G | 2020-07-24 | 2020-02-18 | 2021-01-20 | 2020-08-04 | G | [5 empty] | 2021-03-10 |  | 2021-04-06 |  | G | 2021-11-24 |  | 2022-01-03 |  | G | 2022-06-03 |  | 2022-10-03 |  | G | 2022-01-20 |  | 2022-06-17 |  | G | 2022-02-17 |  | 2022-07-18 |  | G | [5 empty] | 2022-10-11 |  | 2022-10-11 |  | G | 2023-01-05 |  | 2023-01-05 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.082725
600 | 110999 | Portsmouth Boulevard Sidewalk Segment 2 | 0000 | Urban | Facilities for Pedestrians and Bicycles | Locally | Suffolk | NORFOLK | Hampton Roads | Hampton Roads:Suffolk | Infrastructure Investment Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Johndel A Alcaide | John.Alcaide@vdot.virginia.gov | (757) 956-3098 | LJ Hansen | lhansen@suffolkva.us | (757) 514-7687 | 0 |  | 0 | FY2022 | 899893 | 854883 | ACTIVITY DATES SET | G | Start Purchasing Right-of-Way milestone finished 149 days early | G | Project is on budget | 2017-08-07 | 2017-08-07 | 2017-10-24 | 2017-10-24 | G | 2017-11-09 | 2017-11-09 | 2017-11-14 | 2017-11-14 | G | 2017-11-15 | 2017-11-15 | 2019-02-01 | 2019-04-05 | R | [10 empty] | 2020-04-09 | 2019-11-06 | 2020-04-29 | 2019-12-02 | G | [5 empty] | 2020-05-01 |  | 2021-05-17 |  | G | [10 empty] | 2021-06-03 |  | 2021-06-30 |  | G | 2021-07-01 |  | 2021-11-08 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.1556
601 | 111370 | #SMART18 - Hollins Rd & Orange Ave Intersection Improvements | 0460 | Urban | Reconstruction w/ Added Capacity | VDOT | Roanoke | SALEM | Salem | Roanoke:Roanoke City | Infrastructure Investment Division | Alex H Price | Alex.Price@VDOT.Virginia.gov | (540) 378-5053 | Brian H Becker | Brian.Becker@VDOT.Virginia.gov | (540) 204-7959 | Mark Jamison | mark.jamison@roanokeva.gov | (540) 853-5471 | 1 | 2018 | 0 | FY2020 | 3552247 | 4200847 | CONSTRUCTION STARTED | R | Relocate Utilities milestone is 549 days past the expected completion date | Y | Project estimate is less than $5M and is up to 20% over budget | [5 empty] | 2017-07-03 | 2017-07-07 | 2017-07-17 | 2017-07-07 | G | 2017-07-18 | 2017-07-10 | 2017-12-18 | 2017-12-08 | G | [5 empty] | 2017-12-15 | 2017-12-15 | 2017-12-15 | 2017-12-15 | G | 2018-05-14 | 2018-05-14 | 2018-05-25 | 2018-05-25 | G | 2018-07-11 | 2019-02-19 | 2019-08-22 |  | R | 2018-05-31 | 2018-05-30 | 2018-12-20 | 2018-05-30 | G | 2018-04-18 | 2018-01-25 | 2018-10-22 | 2018-01-25 | G | [5 empty] | 2019-09-10 | 2019-12-10 | 2019-09-10 | 2019-12-10 | R | 2019-10-25 | 2020-02-27 | 2020-03-24 | 2020-02-27 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 1 | 0.37118
602 | 111406 | #SGR17VB - BRIDGE REPLACE RT 1 CHOPAWAMSIC CREEK ID 18057 | 0001 | Primary | Bridge Replacement w/o Added Capacity | VDOT | Stafford County | FREDERICKSBURG | Fredericksburg | Fredericksburg:Stafford County | Infrastructure Investment/Asset Management Division | Jennifer L Ahlin | Jennifer.Ahlin@vdot.virginia.gov | (804) 786-6581 | Curtis B Holloway | Curtis.Holloway@vdot.virginia.gov | (540) 374-3367 |  |  |  | 0 |  | 1 | FY2024 | 7750000 | 7750000 | ACTIVITY DATES SET | G | Engage Public milestone finished on-time | G | Project is on budget | [5 empty] | 2018-07-23 | 2018-06-21 | 2018-08-03 | 2018-07-03 | G | 2018-08-06 | 2018-07-03 | 2019-07-03 | 2019-07-02 | G | [5 empty] | 2020-10-08 | 2020-10-08 | 2020-11-12 | 2020-11-12 | G | 2021-09-14 |  | 2021-10-11 |  | G | 2023-04-28 |  | 2024-01-03 |  | G | 2021-10-27 |  | 2023-04-27 |  | G | 2021-04-08 |  | 2022-11-10 |  | G | [5 empty] | 2023-12-12 |  | 2023-12-12 |  | G | 2024-02-06 |  | 2024-04-02 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.055711
603 | 111728 | US Rte. 15/29 & Rte. 215 Intersection & Signal Improvements | 0029 | Primary | Safety | VDOT | Fauquier County | WARRENTON | Culpeper | Northern Virginia:Fauquier | Infrastructure Investment Division | Gregory J Cooley | Gregory.Cooley@vdot.virginia.gov | (434) 906-7979 | James D Cubbage | David.Cubbage@VDOT.Virginia.gov | (540) 727-7129 |  |  |  | 0 |  | 0 | FY2024 | 3307372 | 3307372 | NO DATES SET YET-PE OPEN | R | Determine Requirements milestone is 61 days past the expected completion date | G | Project is on budget | [5 empty] | 2020-01-13 | 2017-08-16 | 2020-01-28 | 2017-08-29 | G | 2020-01-29 |  | 2020-12-22 |  | R | [5 empty] | 2021-10-26 |  | 2021-11-08 |  | G | 2023-02-21 |  | 2023-03-06 |  | G | 2023-07-27 |  | 2024-02-06 |  | G | 2023-03-22 |  | 2023-09-22 |  | G | 2022-08-03 | 2020-01-14 | 2023-02-13 | 2020-01-14 | G | [5 empty] | 2024-02-13 |  | 2024-02-13 |  | G | 2024-05-03 |  | 2024-05-03 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.10759
604 | 113366 | DISTRICTWIDE TRENCH WIDENING - VARIOUS LOCATIONS | 9999 | Primary | Safety | VDOT | Fredericksburg District-wide | NORTHERN NECK | Fredericksburg | NonMPO:NonMPO | Infrastructure Investment Division | Peter A Hedrich | Peter.Hedrich@vdot.virginia.gov | (540) 899-4540 | Sylvester C Okpala | Sylvester.Okpala@VDOT.Virginia.gov | (540) 907-8174 |  |  |  | 0 |  | 0 | FY2019 | 1300000 | 1300000 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 3 days early | G | Project is on budget | [10 empty] | 2018-08-01 | 2018-08-01 | 2018-08-07 | 2018-08-07 | G | [25 empty] | 2018-08-01 | 2018-08-01 | 2019-02-11 | 2018-08-01 | G | [5 empty] | 2019-03-12 | 2019-03-12 | 2019-03-12 | 2019-03-12 | G | 2019-05-31 | 2019-05-28 | 2019-05-31 | 2019-05-28 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.06232
605 | 113832 | Richmond Marine Terminal (RMT) Gate Impr. & New Drop-off Lot |  | Miscellaneous | Other | Locally | Richmond | ASHLAND | Richmond | Richmond:Richmond | Infrastructure Investment Division | Olena Fecek | Olena.Fecek@vdot.virginia.gov | (804) 524-6368 | Olena Fecek | Olena.Fecek@vdot.virginia.gov | (804) 524-6368 | Melissa Fularon | mfularon@portofvirginia.com | (757) 440-7220 | 0 |  | 0 | FY2021 | 2550000 | 3378607 | ACTIVITY DATES SET | R | Solicit Bids milestone is 26 days past the expected completion date | R | Project estimate is less than $5M and is 20% or more over budget | 2018-07-02 | 2018-07-31 | 2018-09-25 | 2018-11-06 | R | 2018-09-26 | 2018-12-03 | 2018-09-28 | 2018-12-06 | R | 2018-10-01 | 2019-01-17 | 2019-04-11 | 2019-04-10 | G | [10 empty] | 2020-02-04 | 2020-01-13 | 2020-02-04 | 2020-01-13 | G | [5 empty] | 2020-02-04 | 2020-01-13 | 2020-02-04 | 2020-01-13 | G | 2020-06-10 | 2020-09-29 | 2020-12-09 | 2020-09-29 | G | [5 empty] | 2020-12-24 |  | 2021-01-26 |  | R | 2021-04-15 |  | 2021-04-15 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.094855
606 | 114701 | PSAP - Pedestrian Facility Improvements in Richmond |  | Urban | Safety | Locally | Richmond | ASHLAND | Richmond | Richmond:Richmond | Local Assistance Division | Brian J Lokker | Brian.Lokker@VDOT.Virginia.gov | (804) 524-6010 | Brian J Lokker | Brian.Lokker@VDOT.Virginia.gov | (804) 524-6010 | Jian Xu | jian.xu@richmondgov.com | (804) 646-5402 | 0 |  | 0 | FY2021 | 1539985 | 1539985 | AWARDED | R | Start Delivery milestone finished 9 days late | G | Project is on budget | 2019-05-01 | 2019-02-19 | 2019-07-25 | 2019-07-09 | G | 2019-07-26 | 2019-07-15 | 2019-07-30 | 2019-07-22 | G | 2019-07-31 | 2019-07-23 | 2020-02-10 | 2019-12-18 | G | [35 empty] | 2020-03-31 | 2020-02-20 | 2020-03-31 | 2020-02-20 | G | 2020-09-30 | 2020-10-09 | 2020-09-30 | 2020-10-09 | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NOT APPLICABLE | 1 | 0 | 0.17793
607 | 115524 | #SMART20 Victory Blvd Enhancement App 2: Poquoson Segment | 0171 | Urban | Reconstruction w/ Added Capacity | Locally | Poquoson | WILLIAMSBURG | Hampton Roads | Hampton Roads:Poquoson | Infrastructure Investment Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Chessica Villaflores | Chessica.Villaflores@vdot.virginia.gov | (757) 956-3094 | Barret Feagans | garrett.feagans@poquoson-va.gov | (757) 868-3025 | 1 | 2020 | 0 | FY2027 | 3729000 | 3729000 | NO DATES SET YET | G | Agreement with Locality milestone is 976 days ahead of the expected completion date | Y | Estimate not current | 2023-08-01 |  | 2023-10-25 |  | G | 2023-10-26 |  | 2023-10-30 |  | G | 2023-10-31 |  | 2024-05-09 |  | G | [10 empty] | 2025-05-13 |  | 2025-06-03 |  | G | [5 empty] | 2025-06-05 |  | 2026-03-19 |  | G | 2024-06-17 |  | 2025-02-24 |  | G | [5 empty] | 2026-04-06 |  | 2026-05-01 |  | G | 2026-07-22 |  | 2026-07-22 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.28013
608 | 115719 | #SMART20 US 33 & ROUTE 620 TURN LANES | 0033 | Primary | Reconstruction w/ Added Capacity | VDOT | Rockingham County | HARRISONBURG | Staunton | Harrisonburg:Rockingham County | Infrastructure Investment Division | John-Allen L Ennis | JohnAllen.Ennis@VDOT.Virginia.gov | (540) 332-9118 | Alexander Alvarado | Alexander.Alvarado@vdot.virginia.gov | (540) 332-7372 |  |  |  | 1 | 2020 | 0 | FY2024 | 977984 | 977984 | NO DATES SET YET-PE OPEN | R | Determine Requirements milestone is 145 days past the expected completion date | G | Project is on budget | [5 empty] | 2019-10-22 | 2019-10-22 | 2019-10-31 | 2019-10-31 | G | 2019-11-01 |  | 2020-09-29 |  | R | [5 empty] | 2021-08-05 |  | 2021-08-18 |  | G | 2022-11-28 |  | 2022-12-09 |  | G | 2023-05-08 |  | 2023-11-09 |  | G | 2022-12-28 |  | 2023-07-05 |  | G | 2022-05-13 |  | 2022-11-17 |  | G | [5 empty] | 2023-11-14 |  | 2023-11-14 |  | G | 2024-02-09 |  | 2024-02-09 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.082821
609 | 116174 | #I81CIP MM 39.4 EXTEND DECEL LANE (ID #19) | 0081 | Interstate | Reconstruction w/o Added Capacity | VDOT | Smyth County | ABINGDON | Bristol | NonMPO:NonMPO | Infrastructure Investment Division | Donald A Necessary | Donald.Necessary@VDOT.Virginia.gov | (276) 696-3285 | Marvin E Holley | Gene.Holley@VDOT.Virginia.gov | (276) 696-3255 |  |  |  | 0 |  | 0 | FY2022 | 1465000 | 1465000 | ACTIVITY DATES SET | G | Determine Requirements milestone finished 179 days early | G | Project is on budget | [5 empty] | 2020-07-01 | 2020-01-02 | 2020-07-15 | 2020-01-09 | G | 2020-07-16 | 2020-01-10 | 2021-03-12 | 2020-09-14 | G | [5 empty] | 2021-04-15 |  | 2021-04-15 |  | G | [5 empty] | 2021-04-21 |  | 2021-04-21 |  | G | [5 empty] | 2021-06-16 |  | 2021-08-25 |  | G | [5 empty] | 2021-10-12 |  | 2021-10-12 |  | G | 2022-01-07 |  | 2022-01-07 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.080204
611 | 111105 | STRATTON PARK PED IMPROVEMENTS | 3259 | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Chesterfield County | CHESTERFIELD | Richmond | Richmond:Chesterfield County | Local Assistance Division | Jorg Huckabee-Mayfield | Jorg.Huckabee-Mayfield@VDOT.Virginia.gov | (804) 609-5292 | Jorg Huckabee-Mayfield | Jorg.Huckabee-Mayfield@VDOT.Virginia.gov | (804) 609-5292 | Nate Mathis | mathisn@chesterfield.gov | (804) 748-1037 | 0 |  | 0 | FY2021 | 1575000 | 1575000 | ADVERTISED | R | Solicit Bids milestone finished 5 days late | G | Project is on budget | 2017-06-20 | 2017-06-20 | 2017-10-02 | 2017-10-02 | G | 2017-12-01 | 2017-12-01 | 2017-12-15 | 2017-12-15 | G | 2017-12-18 | 2017-12-18 | 2018-12-28 | 2019-02-21 | R | [10 empty] | 2019-05-08 | 2019-07-02 | 2019-10-31 | 2019-09-18 | G | [5 empty] | 2019-11-04 | 2019-09-26 | 2020-08-14 | 2020-10-30 | R | 2020-02-03 | 2020-02-03 | 2020-08-12 | 2020-06-29 | G | [5 empty] | 2020-09-01 | 2020-11-10 | 2021-01-29 | 2021-02-03 | R | 2021-02-01 |  | 2021-06-04 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.35715
612 | 111385 | Town of Wise - Norton Road Ped Improvements |  | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Wise | WISE | Bristol | NonMPO:NonMPO | Local Assistance Division | Tabitha H Crowder | Tabitha.Crowder@vdot.virginia.gov | (276) 696-3482 | Roger L Musser | Roger.Musser@VDOT.Virginia.gov | (276) 696-3260 | Laura Craft | planner@townofwise.org | (276) 328-6013 | 0 |  | 0 | FY2022 | 701300 | 701300 | ACTIVITY DATES SET | G | Start Purchasing Right-of-Way milestone finished on-time | G | Project is on budget | 2018-05-21 | 2018-05-21 | 2018-09-12 | 2018-09-12 | G | 2018-09-13 | 2018-07-25 | 2018-09-17 | 2018-07-25 | G | 2018-09-18 | 2018-09-14 | 2019-03-15 | 2019-03-13 | G | [10 empty] | 2020-04-27 | 2020-04-27 | 2020-07-21 | 2020-07-21 | G | [5 empty] | 2020-07-23 |  | 2021-06-10 |  | G | [10 empty] | 2021-07-27 |  | 2021-10-20 |  | G | 2021-10-21 |  | 2021-12-03 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.3483
614 | 113291 | RTE 33 (Nine Mile Road) - Streetscape | 0033 | Primary | Landscaping/Beautification | Locally | Richmond | ASHLAND | Richmond | Richmond:Richmond | Local Assistance Division | Douglas L Orcutt | Doug.Orcutt@vdot.virginia.gov | (804) 609-5428 | Douglas L Orcutt | Doug.Orcutt@vdot.virginia.gov | (804) 609-5428 | Yongping Wang | yongping.wang@richmondgov.com | (804) 646-2467 | 0 |  | 0 | FY2021 | 3612073 | 3612073 | AWARDED | R | Start Delivery milestone finished 52 days late | G | Project is on budget | 2018-07-02 | 2018-07-10 | 2018-11-30 | 2018-07-10 | G | 2018-12-03 | 2018-12-14 | 2018-12-20 | 2018-12-17 | G | 2018-12-26 | 2018-12-20 | 2019-07-01 | 2019-07-01 | G | [25 empty] | 2019-03-19 | 2019-07-19 | 2020-01-02 | 2019-07-19 | G | [5 empty] | 2020-03-20 | 2020-10-19 | 2020-04-30 | 2020-10-19 | R | 2020-07-21 | 2020-10-20 | 2020-10-30 | 2020-12-21 | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.33301
615 | 113821 | Potters Road Road Diet | 9999 | Urban | Facilities for Pedestrians and Bicycles | Locally | Virginia Beach | NORFOLK | Hampton Roads | Hampton Roads:Virginia Beach | Infrastructure Investment Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Marci Thompson | Marci.Thompson@vdot.virginia.gov | (757) 956-3093 | Katie Shannon | kshannon@vbgov.com | (757) 385-1514 | 0 |  | 0 | FY2023 | 570000 | 570000 | NO DATES SET YET-PE OPEN | R | Determine Requirements milestone is 249 days past the expected completion date | G | Project is on budget | 2019-08-28 | 2019-08-28 | 2019-11-22 | 2019-10-25 | G | 2019-11-25 | 2019-10-28 | 2019-12-10 | 2019-11-05 | G | 2019-12-11 | 2019-11-06 | 2020-06-17 |  | R | [10 empty] | 2021-06-21 |  | 2021-07-12 |  | G | [5 empty] | 2021-07-14 |  | 2022-04-26 |  | G | 2020-07-24 |  | 2021-04-01 |  | Y | [5 empty] | 2022-05-12 |  | 2022-06-09 |  | G | 2022-08-29 |  | 2022-08-29 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.14274
616 | 113838 | RIVERSIDE MANOR CONNECTOR -- SIDEWALKS | 0639 | Primary | Facilities for Pedestrians and Bicycles | Locally | Fredericksburg | FREDERICKSBURG | Fredericksburg | Fredericksburg:Fredericksburg | Infrastructure Investment Division | Peter A Hedrich | Peter.Hedrich@vdot.virginia.gov | (540) 899-4540 | Anastasia Kapitan | Anastasia.Kapitan@vdot.virginia.gov | (540) 899-4292 | ERIK NELSON |  |  | 0 |  | 0 | FY2021 | 175000 | 175000 | NO DATES SET YET-PE OPEN | R | Determine Requirements milestone is 374 days past the expected completion date | G | Project is on budget | 2019-05-06 | 2018-08-01 | 2019-07-30 | 2018-10-12 | G | 2019-07-31 | 2019-06-18 | 2019-08-02 | 2019-07-29 | G | 2019-08-05 |  | 2020-02-13 |  | R | [25 empty] | 2020-03-23 | 2019-05-16 | 2020-11-20 | 2019-05-16 | G | [5 empty] | 2021-03-04 |  | 2021-03-31 |  | Y | 2021-06-18 |  | 2021-06-18 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.16179
617 | 115418 | #SMART20 Richmond Rd Signal Coordination & Ped. Improvements | 0060 | Primary | Safety | Locally | Williamsburg | WILLIAMSBURG | Hampton Roads | Hampton Roads:Williamsburg | Infrastructure Investment Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Chessica Villaflores | Chessica.Villaflores@vdot.virginia.gov | (757) 956-3094 | Aaron Small | asmall@williamsburgva.gov | (757) 220-6140 | 1 | 2020 | 0 | FY2026 | 203500 | 203500 | NO DATES SET YET | G | Agreement with Locality milestone is 1264 days ahead of the expected completion date | Y | Estimate not current | 2024-05-15 |  | 2024-08-08 |  | G | 2024-08-09 |  | 2024-08-13 |  | G | 2024-08-14 |  | 2025-02-25 |  | G | [25 empty] | 2025-04-02 |  | 2025-12-04 |  | G | [5 empty] | 2026-01-05 |  | 2026-02-03 |  | G | 2026-04-23 |  | 2026-04-23 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.17308
618 | 115531 | #SMART20 - SAFETY AND CAPACITY ENHANCEMENTS | 0236 | Urban | Safety | Locally | Alexandria | FAIRFAX | Northern Virginia | Northern Virginia:Alexandria | Infrastructure Investment Division | Bud Siegel |  |  | Robert J Strevell | Robert.Strevell@vdot.virginia.gov | (703) 259-1988 | Ryan Knight | ryan.knight@alexandriava.gov | (703) 746-4083 | 1 | 2020 | 0 | FY2026 | 5745460 | 5745459 | NO DATES SET YET-PE OPEN | G | Start Development milestone finished 511 days early | G | Project is on budget | 2020-08-03 | 2019-07-23 | 2021-02-26 | 2019-10-15 | G | 2021-03-01 | 2019-10-16 | 2021-03-31 | 2019-11-06 | G | 2021-12-01 |  | 2022-07-29 |  | G | [10 empty] | 2023-08-01 |  | 2023-08-31 |  | G | [5 empty] | 2023-09-05 |  | 2024-06-28 |  | G | 2023-08-01 |  | 2024-05-30 |  | G | [5 empty] | 2024-07-17 |  | 2024-12-31 |  | G | 2025-03-25 |  | 2025-08-29 |  | G | Awaiting authorization before work can proceed | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.28035
619 | 115726 | #SMART20 - ROUTE 206 AND ROUTE 218 RIGHT TURN LANE | 0206 | Primary | Safety | VDOT | King George County | FREDERICKSBURG | Fredericksburg | NonMPO:NonMPO | Infrastructure Investment Division | Catherine C Coffey | Catherine.Coffey@vdot.virginia.gov | (540) 899-4280 | Curtis B Holloway | Curtis.Holloway@vdot.virginia.gov | (540) 374-3367 |  |  |  | 1 | 2020 | 0 | FY2023 | 2000000 | 2000000 | ACTIVITY DATES SET | G | Engage Public milestone finished 171 days early | G | Project is on budget | [5 empty] | 2019-09-03 | 2019-09-02 | 2019-09-30 | 2019-09-13 | G | 2019-10-01 | 2019-09-15 | 2020-04-17 | 2020-04-17 | G | [5 empty] | 2021-02-02 | 2020-08-28 | 2021-02-15 | 2020-08-28 | G | 2021-09-09 |  | 2021-10-06 |  | G | 2022-05-05 |  | 2022-11-08 |  | G | 2021-10-25 |  | 2022-05-04 |  | G | 2021-04-30 |  | 2021-11-03 |  | G | [5 empty] | 2022-12-13 |  | 2022-12-13 |  | G | 2023-04-13 |  | 2023-04-13 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.067554
620 | 116864 | ROUTE 276 LEFT TURN LANES @ ROUTE 253 | 0276 | Primary | Reconstruction w/ Added Capacity | VDOT | Rockingham County | HARRISONBURG | Staunton | Harrisonburg:Rockingham County | Local Assistance Division | John-Allen L Ennis | JohnAllen.Ennis@VDOT.Virginia.gov | (540) 332-9118 | John-Allen L Ennis | JohnAllen.Ennis@VDOT.Virginia.gov | (540) 332-9118 |  |  |  | 0 |  | 0 | FY2024 | 1499062 | 1499062 | NO DATES SET YET | R | Start Development milestone is 142 days past the expected completion date | G | Project is on budget | [5 empty] | 2020-09-14 |  | 2020-10-02 |  | R | 2020-10-05 |  | 2021-08-09 |  | G | [5 empty] | 2022-03-15 |  | 2022-04-11 |  | G | 2022-12-01 |  | 2023-01-06 |  | G | 2023-06-08 |  | 2023-10-06 |  | G | 2023-01-25 |  | 2023-06-22 |  | G | 2023-02-16 |  | 2023-07-17 |  | G | [5 empty] | 2023-10-10 |  | 2023-10-10 |  | G | 2024-01-04 |  | 2024-01-04 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.1351
621 | 116962 | #SGR21LP SUNNYSIDE STREET |  | Primary | Resurfacing | Locally | Staunton | HARRISONBURG | Staunton | SAW:Staunton | Infrastructure Investment Division | Michael S Fulcher | Michael.Fulcher@VDOT.Virginia.gov | (540) 332-2243 | Michael S Fulcher | Michael.Fulcher@VDOT.Virginia.gov | (540) 332-2243 | Steve Yancey | yanceysc@ci.staunton.va.us | (540) 332-3852 | 0 |  | 1 | FY2024 | 154576 | 154576 | NO DATES SET YET | G | Agreement with Locality milestone is 107 days ahead of the expected completion date | G | Project is on budget | 2021-02-01 |  | 2021-06-08 |  | G | 2021-06-09 |  | 2021-06-29 |  | G | 2021-07-29 |  | 2021-11-22 |  | G | [25 empty] | 2022-11-17 |  | 2023-04-21 |  | G | [5 empty] | 2023-06-20 |  | 2023-07-18 |  | G | 2023-10-05 |  | 2023-10-05 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.077076
622 | 117211 | FY 21 Curve Delineation | 9999 | Primary | Safety | VDOT | Salem District-wide |  | Salem | Roanoke:Salem District-wide | Infrastructure Investment/Asset Management Division | Bernard S Grinnell | Sean.Grinnell@VDOT.Virginia.gov | (540) 375-0148 | Jason W Knight | Jay.Knight@vdot.virginia.gov | (540) 375-0152 | N/a |  |  | 0 |  | 0 | FY2022 | 1093432 | 853978 | ACTIVITY DATES SET | R | Determine Requirements milestone finished 62 days late | G | Project is on budget | [5 empty] | 2020-04-01 | 2020-05-16 | 2020-04-14 | 2020-05-16 | R | 2020-04-15 | 2020-05-18 | 2020-05-12 | 2020-07-13 | R | [35 empty] | 2021-10-12 |  | 2021-12-14 |  | G | 2022-03-10 |  | 2022-05-11 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.12224
623 | 117945 | RICHMOND COUNTY MULTI-USE TRAIL (PHASE I) |  | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Richmond County | NORTHERN NECK | Fredericksburg | NonMPO:NonMPO | Local Assistance Division | David L Beale | David.Beale@vdot.virginia.gov | (804) 333-7941 | Anastasia Kapitan | Anastasia.Kapitan@vdot.virginia.gov | (540) 899-4292 | Morgan Quick | rmquick3@co.richmond.va.us | (804) 333-3415 | 0 |  | 0 | FY2025 | 533992 | 533992 | NO DATES SET YET | G | Agreement with Locality milestone is 80 days ahead of the expected completion date | G | Project is on budget | 2021-01-04 |  | 2021-05-12 |  | G | 2021-05-13 |  | 2021-06-03 |  | G | 2021-12-13 |  | 2022-04-08 |  | G | [10 empty] | 2023-07-28 |  | 2023-08-31 |  | G | [5 empty] | 2023-09-01 |  | 2024-02-07 |  | G | 2024-01-03 |  | 2024-06-03 |  | G | [5 empty] | 2024-05-10 |  | 2024-06-07 |  | G | 2024-08-27 |  | 2024-08-27 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.35449
624 | 104229 | Realignment of curve Highland Avenue/High St. | 0000 | Urban | Reconstruction w/o Added Capacity | Locally | Bluefield | LEBANON | Bristol | NonMPO:NonMPO | Local Assistance Division | Tabitha H Crowder | Tabitha.Crowder@vdot.virginia.gov | (276) 696-3482 | Roger L Musser | Roger.Musser@VDOT.Virginia.gov | (276) 696-3260 | Billie Roberts | roberts@bluefieldva.org | (276) 322-4626 | 0 |  | 0 | FY2021 | 585118 | 585118 | CONSTRUCTION STARTED | G | Start Delivery milestone finished on-time | G | Project is on budget | [5 empty] | 2013-08-01 | 2013-01-01 | 2014-05-01 | 2014-05-01 | G | 2013-09-03 | 2013-08-31 | 2013-12-31 | 2013-12-31 | G | [10 empty] | 2019-04-10 | 2019-04-09 | 2019-05-01 | 2019-04-22 | G | [20 empty] | 2020-02-03 | 2020-05-11 | 2020-03-02 | 2020-06-04 | R | 2020-07-15 | 2020-07-15 | 2020-08-24 | 2020-08-24 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.065475
625 | 105734 | RTE 632 - ROUNDABOUT | 0632 | Secondary | New Construction Roadway | VDOT | Goochland County | ASHLAND | Richmond | NonMPO:NonMPO | Infrastructure Investment Division | Anthony S Haverly | Anthony.Haverly@vdot.virginia.gov | (804) 609-5225 | Anthony S Haverly | Anthony.Haverly@vdot.virginia.gov | (804) 609-5225 |  |  |  | 0 |  | 0 | FY2023 | 4124594 | 4124594 | ACTIVITY DATES SET | G | Complete Purchasing Right-of-Way milestone finished on-time | G | Project is on budget | [5 empty] | 2017-09-07 | 2017-09-07 | 2017-10-03 | 2017-09-11 | G | 2017-09-12 | 2017-09-12 | 2018-10-04 | 2018-10-03 | G | [5 empty] | 2019-06-14 | 2019-04-29 | 2019-06-27 | 2019-06-21 | G | 2020-04-24 | 2020-04-01 | 2020-05-07 | 2020-04-16 | G | 2020-12-31 | 2020-12-04 | 2022-01-03 |  | G | 2020-06-01 | 2020-05-27 | 2020-12-01 | 2020-12-01 | G | 2021-02-19 |  | 2021-08-23 |  | G | [5 empty] | 2022-02-08 |  | 2022-02-08 |  | G | 2022-07-12 |  | 2022-07-12 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.12317
626 | 108496 | ROUTE 50 SIDEWALK PATRICK HENRY DRIVE TO OLIN DR (SOUTHSIDE) | 0050 | Primary | Safety | Locally | Fairfax County | FAIRFAX | Northern Virginia | Northern Virginia:Fairfax County | Infrastructure Investment Division | Amir Salahshoor | A.Salahshoor@VDOT.Virginia.gov | (703) 259-1957 | Rita Hockman | Rita.Hockman@vdot.virginia.gov | (804) 824-7421 | Seyed Nabavi | seyd.Nabavi@fairfaxcounty.gov | (703) 877-5759 | 0 |  | 0 | FY2021 | 425000 | 335000 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 871 days early | G | Project is on budget | 2014-12-30 | 2014-12-30 | 2015-03-27 | 2015-03-27 | G | 2015-03-30 | 2015-03-30 | 2015-04-01 | 2015-04-01 | G | 2015-04-02 | 2015-04-01 | 2015-10-05 | 2016-09-19 | R | [10 empty] | 2016-07-29 | 2016-07-29 | 2016-08-18 | 2016-08-18 | G | [5 empty] | 2016-10-24 | 2016-10-24 | 2017-12-27 | 2017-12-27 | G | [10 empty] | 2019-12-05 | 2018-02-15 | 2020-06-30 | 2018-05-31 | G | 2020-07-01 | 2018-06-01 | 2020-11-30 | 2018-07-13 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.075835
627 | 109288 | #HB2.FY17 Transit Accessibility Improvements on Edgewood St | 0000 | Urban | Transit | Locally | Roanoke | SALEM | Salem | Roanoke:Roanoke City | Infrastructure Investment Division | James M Guy | james.guy@vdot.virginia.gov | (540) 387-5247 | Cheryl B Becker | Cheryl.Becker@vdot.virginia.gov | (540) 492-2531 | Luke Pugh | Luke.Pugh@roanokeva.gov | (540) 853-2035 | 1 | 2017 | 0 | FY2018 | 350811 | 423307 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 113 days early | Y | Project estimate is less than $5M and is up to 20% over budget | 2016-04-06 | 2016-04-06 | 2016-10-14 | 2016-10-14 | G | 2016-08-24 | 2016-08-24 | 2016-08-25 | 2016-08-25 | G | 2016-08-01 | 2016-08-01 | 2016-12-16 | 2016-12-16 | G | [35 empty] | 2017-10-31 | 2017-05-16 | 2017-11-30 | 2017-07-03 | G | 2017-12-01 | 2017-07-05 | 2018-01-16 | 2017-09-25 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.24414
628 | 110424 | #SGR18VB - RT 360 EBL - REPLACE BRIDGE (Fed 1226) | 0360 | Primary | Bridge Replacement w/o Added Capacity | VDOT | Amelia County | CHESTERFIELD | Richmond | NonMPO:NonMPO | Infrastructure Investment/Asset Management Division | Jeremy B Cobb | Jeremy.Cobb@vdot.virginia.gov | (804) 586-2255 | Jeremy B Cobb | Jeremy.Cobb@vdot.virginia.gov | (804) 586-2255 |  |  |  | 0 |  | 1 | FY2021 | 6165986 | 6165986 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 76 days early | G | Project is on budget | [10 empty] | 2017-09-20 | 2017-09-20 | 2017-09-26 | 2017-10-03 | R | [25 empty] | 2019-04-29 | 2017-11-14 | 2020-01-02 | 2017-11-14 | G | [5 empty] | 2020-07-14 | 2020-06-09 | 2020-07-14 | 2020-06-09 | G | 2020-09-02 | 2020-09-16 | 2020-12-01 | 2020-09-16 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.071557
629 | 110997 | RTE 155 - DECK REPLACEMENT OVER CHICKAHOMINY RIVER CANAL | 0155 | Primary | Bridge Replacement w/o Added Capacity | VDOT | New Kent County | ASHLAND | Richmond | Richmond:New Kent County | Infrastructure Investment/Asset Management Division | Phillip Frazer | Phillip.Frazer@vdot.virginia.gov | (804) 481-0906 | Lawrence Ramsey | Brian.Ramsey@VDOT.Virginia.gov | (804) 585-3579 |  |  |  | 0 |  | 0 | FY2020 | 795307 | 795307 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 142 days early | G | Project is on budget | [5 empty] | 2017-07-18 | 2017-07-12 | 2017-07-31 | 2017-07-31 | G | 2017-08-01 | 2017-08-01 | 2018-06-28 | 2018-09-11 | R | [5 empty] | 2018-09-12 | 2018-09-10 | 2018-10-05 | 2018-10-03 | G | 2018-10-31 | 2018-10-12 | 2018-10-31 | 2018-10-12 | G | 2018-09-05 | 2018-09-05 | 2018-09-05 | 2018-09-05 | G | 2018-10-31 | 2018-10-12 | 2018-10-31 | 2018-10-12 | G | [10 empty] | 2019-08-13 | 2019-04-23 | 2019-08-13 | 2019-04-23 | G | 2019-10-03 | 2019-06-26 | 2019-11-15 | 2019-06-26 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | REGIONAL ON-CALL CONTRACT | 1 | 0 | 0.076516
630 | 116580 | RURAL RUSTIC ROAD CONTRACT (PARENT UPC) | 9999 | Secondary | Reconstruction w/o Added Capacity | VDOT | Loudoun County | LEESBURG | Northern Virginia | Northern Virginia:Loudoun County | Infrastructure Investment Division | Kimberly Mccool | Kimberly.McCool@vdot.virginia.gov | (703) 259-3220 | Mehrdad Naderi | Mehrdad.Naderi@vdot.virginia.gov | (703) 259-2217 | James Zeller, Loudoun County DTCI | james.zeller@loudoun.gov | (571) 258-3548 | 0 |  | 0 | FY2020 | 6500000 | 6500000 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 46 days early | G | Project is on budget | [10 empty] | 2020-01-24 | 2020-01-24 | 2020-02-24 | 2020-01-27 | G | [35 empty] | 2020-02-25 | 2020-02-25 | 2020-04-21 | 2020-02-25 | G | 2020-04-22 | 2020-05-07 | 2020-06-22 | 2020-05-07 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | REGIONAL ON-CALL CONTRACT | 1 | 1 | 0.23006
631 | 116916 | DOWNTOWN PEDESTRIAN IMPROVEMENTS PHASE 1 |  | Secondary | Facilities for Pedestrians and Bicycles | VDOT | Scottsville | CHARLOTTESVILLE | Culpeper | NonMPO:NonMPO | Local Assistance Division | Gregory J Cooley | Gregory.Cooley@vdot.virginia.gov | (434) 906-7979 | Michael Jacobs | Mike.Jacobs@VDOT.Virginia.gov | (540) 829-7502 | Matt Lawless | mlawless@scottsville.org | 43428692 | 0 |  | 0 | FY2024 | 400000 | 400000 | NO DATES SET YET | R | Start Development milestone is 122 days past the expected completion date | G | Project is on budget | [5 empty] | 2020-10-01 |  | 2020-10-22 |  | R | 2020-10-23 |  | 2021-08-26 |  | G | [5 empty] | 2022-04-01 |  | 2022-04-28 |  | G | 2022-12-20 |  | 2023-01-27 |  | G | 2023-06-27 |  | 2023-10-26 |  | G | 2023-02-13 |  | 2023-07-12 |  | G | 2023-03-22 |  | 2023-08-17 |  | G | [5 empty] | 2023-11-14 |  | 2023-11-14 |  | G | 2024-02-08 |  | 2024-02-08 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.17927
632 | 117173 | Hatcher Rd (SR 807)/Lee Highway (US Rte 11) Improvements | 0011 | Primary | New Construction Roadway | Locally | Pulaski County | CHRISTIANSBURG | Salem | NonMPO:NonMPO | Local Assistance Division | Adam J Czesnowski | Adam.Czesnowski@vdot.virginia.gov | (540) 541-1216 | Adam J Czesnowski | Adam.Czesnowski@vdot.virginia.gov | (540) 541-1216 | Jared Linkous | jlinkous@pulaskicounty.org | (540) 980-7710 | 0 |  | 0 | FY2028 | 8405018 | 8405018 | NO DATES SET YET | G | Agreement with Locality milestone is 1422 days ahead of the expected completion date | G | Project is on budget | 2024-08-30 |  | 2025-01-13 |  | G | 2025-01-14 |  | 2025-02-05 |  | G | 2025-08-12 |  | 2025-12-08 |  | G | [10 empty] | 2027-04-01 |  | 2027-05-05 |  | G | [5 empty] | 2027-05-06 |  | 2027-10-04 |  | G | 2027-08-31 |  | 2028-02-04 |  | G | [5 empty] | 2028-01-12 |  | 2028-02-10 |  | G | 2028-05-01 |  | 2028-05-01 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.21352
633 | 117406 | District-wide Unsignalized Intersections Improvements | 9999 | Miscellaneous | Safety | VDOT | Culpeper District-wide |  | Culpeper | NonMPO:NonMPO | Infrastructure Investment/Asset Management Division | Gregory J Cooley | Gregory.Cooley@vdot.virginia.gov | (434) 906-7979 | Caroline Awua-Mensah | Caroline.Awua-Mensah@vdot.virginia.gov | (540) 829-7618 |  |  |  | 0 |  | 0 | FY2022 | 927778 | 927778 | NO DATES SET YET-PE OPEN | R | Determine Requirements milestone is 173 days past the expected completion date | G | Project is on budget | [5 empty] | 2020-06-09 | 2020-06-09 | 2020-06-22 | 2020-06-26 | R | 2020-06-23 | 2020-06-29 | 2020-09-01 |  | R | [35 empty] | 2021-04-13 |  | 2021-04-13 |  | Y | 2021-07-02 |  | 2021-07-02 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.10456
634 | 118164 | Glade Creek Drainage Improvements 2 | 0000 | Urban | Mitigation of Water Pollution Due to Highway Runof | Locally | Roanoke | SALEM | Salem | Roanoke:Roanoke City | Local Assistance Division | Cheryl B Becker | Cheryl.Becker@vdot.virginia.gov | (540) 492-2531 | Cheryl B Becker | Cheryl.Becker@vdot.virginia.gov | (540) 492-2531 | Joseph Arthur | Joseph.Arthur@roanokeva.gov | (540) 853-5901 | 0 |  | 0 | FY2028 | 1108000 | 1108000 | NO DATES SET YET | G | Agreement with Locality milestone is 1422 days ahead of the expected completion date | G | Project is on budget | 2024-08-30 |  | 2025-01-13 |  | G | 2025-01-14 |  | 2025-02-05 |  | G | 2025-08-12 |  | 2025-12-08 |  | G | [10 empty] | 2027-04-01 |  | 2027-05-05 |  | G | [5 empty] | 2027-05-06 |  | 2027-10-04 |  | G | 2027-08-31 |  | 2028-02-04 |  | G | [5 empty] | 2028-01-12 |  | 2028-02-10 |  | G | 2028-05-01 |  | 2028-05-01 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.20699
635 | 104936 | #SGR17VB - I81 STRUCTs 19596 & 19597 / Reed Creek-Wythe | 0081 | Interstate | Bridge Replacement w/o Added Capacity | VDOT | Wythe County | WYTHEVILLE | Bristol | NonMPO:NonMPO | Infrastructure Investment/Asset Management Division | Gary Lester |  |  | Jeffrey B Powell | Jeffrey.Powell@VDOT.Virginia.gov | (276) 696-3389 |  |  |  | 0 |  | 1 | FY2019 | 23500000 | 0 | CONSTRUCTION STARTED | G | Start Delivery milestone finished on-time | R | Critical information missing | [5 empty] | 2016-09-01 | 2016-09-01 | 2016-09-01 | 2016-09-01 | G | 2016-09-30 | 2016-09-30 | 2017-03-30 | 2017-03-30 | G | [35 empty] | 2018-05-22 | 2018-05-22 | 2018-05-22 | 2018-05-22 | G | 2018-07-30 | 2018-09-24 | 2018-09-24 | 2018-09-24 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.063263
636 | 107435 | Reconstruction & Drainage Improvements on Route 735 - Sussex | 0735 | Secondary | Reconstruction w/o Added Capacity | VDOT | Sussex County | FRANKLIN | Hampton Roads | NonMPO:NonMPO | Infrastructure Investment Division | Gerald W Kee | Jerry.Kee@VDOT.Virginia.gov | (757) 346-3076 | Charles T Catlett | Tommy.Catlett@vdot.virginia.gov | (757) 346-3078 |  |  |  | 0 |  | 0 | FY2027 | 2520000 | 2520000 | NO DATES SET YET | G | Start Development milestone is 438 days ahead of the expected completion date | Y | Estimate not current | [5 empty] | 2022-04-22 |  | 2022-05-05 |  | G | 2022-05-06 |  | 2023-03-20 |  | G | [5 empty] | 2023-12-12 |  | 2023-12-25 |  | G | 2025-07-23 |  | 2025-08-05 |  | G | 2025-12-24 |  | 2026-06-23 |  | G | 2025-08-21 |  | 2026-02-18 |  | G | 2024-12-06 |  | 2025-11-20 |  | G | [5 empty] | 2026-07-23 |  | 2026-07-23 |  | G | 2026-09-04 |  | 2026-09-24 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 1 | 0.19305
637 | 108959 | Traffic Adaptive Corridor Implementation | 0407 | Urban | Traffic Management/Engineering | Locally | Virginia Beach | NORFOLK | Hampton Roads | Hampton Roads:Virginia Beach | Infrastructure Investment Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Marci Thompson | Marci.Thompson@vdot.virginia.gov | (757) 956-3093 | Frank Hickman, PE |  |  | 0 |  | 0 | FY2024 | 390000 | 390000 | NO DATES SET YET | G | Agreement with Locality milestone is 220 days ahead of the expected completion date | G | Project is on budget | 2021-07-07 |  | 2021-09-29 |  | G | 2021-09-30 |  | 2021-10-13 |  | G | 2021-10-14 |  | 2022-10-14 |  | G | [35 empty] | 2023-10-05 |  | 2023-11-17 |  | G | 2023-11-20 |  | 2024-05-14 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.24267
639 | 110833 | INSTALL PEDESTRIAN ACCOMMODATIONS - DISTRICTWIDE | 9999 | Miscellaneous | Safety | VDOT | Richmond District-wide |  | Richmond | Richmond:Richmond District-wide | Infrastructure Investment Division | Adam S Brooks | Adam.Brooks@VDOT.Virginia.gov | (804) 609-5274 | Adam S Brooks | Adam.Brooks@VDOT.Virginia.gov | (804) 609-5274 |  |  |  | 0 |  | 0 | FY2025 | 1930000 | 1930000 | NO DATES SET YET | G | Start Development milestone is 661 days ahead of the expected completion date | G | Project is on budget | [5 empty] | 2022-12-01 |  | 2022-12-14 |  | G | 2022-12-15 |  | 2023-08-08 |  | G | [5 empty] | 2024-04-17 |  | 2024-05-29 |  | G | [5 empty] | 2024-09-11 |  | 2025-01-08 |  | G | [5 empty] | 2024-08-27 |  | 2024-11-27 |  | G | [5 empty] | 2025-02-11 |  | 2025-02-11 |  | G | 2025-04-03 |  | 2025-04-23 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.068587
640 | 111089 | Crittenden Road and Route 17 Intersection Realignment | 0000 | Urban | Reconstruction w/o Added Capacity | Locally | Suffolk | NORFOLK | Hampton Roads | Hampton Roads:Suffolk | Infrastructure Investment Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Johndel A Alcaide | John.Alcaide@vdot.virginia.gov | (757) 956-3098 | Robert Lewis | relewis@suffolkva.us | (757) 514-7621 | 0 |  | 0 | FY2025 | 8855232 | 10072191 | ACTIVITY DATES SET | R | Start Purchasing Right-of-Way milestone finished 317 days late | R | Project estimate is between $5M and $10M and is a $1M or more over budget | 2022-07-05 | 2018-10-04 | 2022-09-27 | 2018-11-05 | G | 2022-09-28 | 2018-01-05 | 2022-10-11 | 2019-01-22 | G | 2022-10-12 | 2019-01-23 | 2023-09-27 | 2019-09-04 | G | [10 empty] | 2020-02-10 | 2020-12-11 | 2020-03-02 | 2021-01-13 | R | [5 empty] | 2020-03-04 |  | 2024-08-19 |  | G | 2020-01-06 |  | 2024-09-03 |  | G | [5 empty] | 2024-10-31 |  | 2024-12-02 |  | G | 2024-12-03 |  | 2025-02-03 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.18057
641 | 111468 | #SMART18 - Cold Harbor (Rt 156) & Catlin Rd (Rt 1440)LT Lane | 0156 | Primary | Safety | VDOT | Hanover County | ASHLAND | Richmond | Richmond:Hanover County | Infrastructure Investment Division | Roy Soto | Roy.Soto@vdot.virginia.gov | (804) 609-5239 | Roy Soto | Roy.Soto@vdot.virginia.gov | (804) 609-5239 |  |  |  | 1 | 2018 | 0 | FY2022 | 1357200 | 1357200 | ADVERTISED | G | Solicit Bids milestone finished 28 days early | G | Project is on budget | [5 empty] | 2017-07-03 | 2017-06-26 | 2017-07-17 | 2017-07-07 | G | 2017-07-18 | 2017-07-10 | 2018-02-12 | 2018-01-31 | G | [5 empty] | 2018-07-02 | 2018-05-17 | 2018-07-16 | 2018-07-13 | G | 2019-05-31 | 2019-02-15 | 2019-06-13 | 2019-02-15 | G | 2020-11-02 | 2018-12-20 | 2021-02-04 | 2018-12-20 | G | 2019-07-01 | 2019-02-21 | 2020-10-01 | 2019-02-21 | G | 2020-03-11 | 2020-03-13 | 2020-09-25 | 2020-03-13 | G | [5 empty] | 2021-03-09 | 2021-02-09 | 2021-03-09 | 2021-02-09 | G | 2021-04-22 |  | 2021-07-01 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.059751
642 | 111725 | #SMART18 - VA 286 - POPES HEAD ROAD INTERCHANGE | 0286 | Primary | Reconstruction w/ Added Capacity | VDOT | Fairfax County | FAIRFAX | Northern Virginia | Northern Virginia:Fairfax County | Infrastructure Investment Division | Andrew Beach | Andrew.Beach@vdot.virginia.gov | (540) 347-6459 | Sitaram Kodali | Sitaram.Kodali@vdot.virginia.gov | (703) 691-6710 | Nick Alexandrow | Nikolai.Alexandrow@fairfaxcounty.gov | (703) 877-5600 | 1 | 2018 | 0 | FY2025 | 64303070 | 88573123 | NO DATES SET YET | R | Start Development milestone baseline missing | R | Project estimate is greater than $10M and is over budget by (a) 10% or more or (b) $5M or more | [9 empty] | R | 2019-03-01 | 2016-09-12 | 2019-03-07 |  | R | [5 empty] | 2022-04-05 | 2019-12-12 | 2022-05-16 | 2020-09-14 | G | 2023-06-07 |  | 2023-07-12 |  | G | 2024-02-06 |  | 2024-06-05 |  | G | 2023-08-03 |  | 2024-02-28 |  | G | 2023-07-11 |  | 2024-03-18 |  | G | [5 empty] | 2024-06-11 |  | 2024-06-11 |  | G | 2024-08-29 |  | 2024-08-29 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 1 | 0.32821
643 | 112664 | Multi-Use Connector Trail - High Knob Access Enhancements | 9999 | Miscellaneous | Facilities for Pedestrians and Bicycles | Locally | Norton | WISE | Bristol | NonMPO:NonMPO | Local Assistance Division | Tabitha H Crowder | Tabitha.Crowder@vdot.virginia.gov | (276) 696-3482 | Kenneth R Plummer | KR.Plummer@VDOT.Virginia.gov | (276) 696-3261 | Fred Ramey | fredr@nortonva.org | (276) 679-1160 | 0 |  | 0 | FY2022 | 981000 | 981000 | NO DATES SET YET-PE OPEN | R | Determine Requirements milestone is 591 days past the expected completion date | G | Project is on budget | 2018-10-01 | 2018-09-04 | 2018-12-28 | 2018-11-29 | G | 2018-12-31 | 2018-11-30 | 2019-01-03 | 2019-02-04 | R | 2019-01-04 | 2019-02-05 | 2019-07-11 |  | R | [10 empty] | 2020-07-14 |  | 2020-08-03 |  | R | [5 empty] | 2020-08-05 |  | 2021-05-18 |  | G | 2019-08-16 |  | 2020-04-23 |  | R | [5 empty] | 2021-06-04 |  | 2021-07-01 |  | G | 2021-09-21 |  | 2021-09-21 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.1301
644 | 112966 | #SGR19LP - Resurface Richmond Ave(RT 250) - Primary EXT | 0250 | Urban | Resurfacing | Locally | Staunton | HARRISONBURG | Staunton | SAW:Staunton | Local Assistance Division | Donald F Komara | Donald.Komara@VDOT.Virginia.gov | (540) 434-2587 | Michael S Fulcher | Michael.Fulcher@VDOT.Virginia.gov | (540) 332-2243 | Steve Yancey | yanceysc@ci.staunton.va.us | (540) 332-3892 | 0 |  | 1 | FY2020 | 163000 | 163000 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 412 days early | G | Project is on budget | 2018-12-31 | 2018-10-05 | 2019-03-28 | 2018-11-05 | G | 2019-03-29 | 2018-11-06 | 2019-04-02 | 2019-03-01 | G | 2019-04-03 | 2019-03-01 | 2019-10-04 | 2019-03-11 | G | [25 empty] | 2019-03-12 | 2019-03-12 | 2019-11-08 | 2019-03-12 | G | [5 empty] | 2020-01-21 | 2019-03-06 | 2020-02-18 | 2019-03-20 | G | 2020-05-06 | 2019-03-20 | 2020-05-06 | 2019-03-21 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.063169
645 | 113238 | RTE 20 SB - PRIMARY EXTENSION PAVEMENT OVERLAY | 0020 | Urban | Resurfacing | Locally | Charlottesville | CHARLOTTESVILLE | Culpeper | Charlottesville:Charlottesville | Local Assistance Division | Ken Connors |  |  | Michael D Barnes | MichaelD.Barnes@vdot.virginia.gov | (434) 422-9861 | Jonathan Dean | deanjo@charlottesville.org | (434) 970-3900 | 0 |  | 0 | FY2019 | 20388 | 20388 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 148 days early | G | Project is on budget | 2018-08-17 | 2018-08-13 | 2018-11-13 | 2018-10-24 | G | [5 empty] | 2018-08-17 | 2018-08-13 | 2018-08-30 | 2018-10-24 | R | [25 empty] | 2018-08-31 | 2018-08-31 | 2018-10-24 | 2018-10-24 | G | [5 empty] | 2018-11-09 | 2018-10-25 | 2019-04-09 | 2018-10-29 | G | 2019-06-27 | 2019-01-24 | 2019-06-27 | 2019-01-30 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.080421
646 | 113696 | #SGR19LB??- Number Ten Lane over Lindsey Drainage Canal | 9999 | Urban | Bridge Replacement w/o Added Capacity | Locally | Chesapeake | NORFOLK | Hampton Roads | Hampton Roads:Chesapeake | Infrastructure Investment Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Johndel A Alcaide | John.Alcaide@vdot.virginia.gov | (757) 956-3098 | Sam Sawan | sawan@cityofchesapeake.net | (757) 382-8263 | 0 |  | 1 | FY2024 | 1251000 | 1251000 | NO DATES SET YET-PE OPEN | G | Start Development milestone finished 1021 days early | Y | Estimate not current | 2021-09-15 | 2018-10-12 | 2021-12-13 | 2019-01-11 | G | 2021-12-14 | 2019-01-14 | 2021-12-16 | 2019-03-01 | G | 2021-12-17 |  | 2022-06-24 |  | G | [10 empty] | 2023-04-21 |  | 2023-05-11 |  | G | [5 empty] | 2023-05-15 |  | 2024-02-27 |  | G | 2022-08-02 |  | 2023-04-10 |  | G | [5 empty] | 2024-03-14 |  | 2024-04-10 |  | G | 2024-06-28 |  | 2024-06-28 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.1368
647 | 113786 | RTE 735 - RURAL RUSTIC RD (SURFACE TREAT NON-HARDSURFACE RD) | 0735 | Secondary | Reconstruction w/o Added Capacity | VDOT | Louisa County | LOUISA | Culpeper | NonMPO:NonMPO | Infrastructure Investment Division | Ken Connors |  |  | Bethel Kefyalew | Bethel.Kefyalew@vdot.virginia.gov | (540) 603-6015 |  |  |  | 0 |  | 0 | FY2024 | 125000 | 125000 | NO DATES SET YET | G | Start Development milestone is 235 days ahead of the expected completion date | Y | Estimate not current | [5 empty] | 2021-10-01 |  | 2021-10-14 |  | G | 2021-10-15 |  | 2022-06-13 |  | G | [5 empty] | 2023-03-22 |  | 2023-05-02 |  | G | [5 empty] | 2023-08-16 |  | 2023-12-12 |  | G | [5 empty] | 2023-08-01 |  | 2023-11-01 |  | G | [5 empty] | 2024-01-09 |  | 2024-01-09 |  | G | 2024-03-04 |  | 2024-03-22 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | SAAP CONTRACT | 0 | 0 | 0.094052
648 | 114670 | RECTANGULAR RAPID FLASHING BEACONS ON WASHINGTON BLVD | 6700 | Secondary | Safety | Locally | Arlington County | FAIRFAX | Northern Virginia | Northern Virginia:Arlington County | Infrastructure Investment Division | Terry Yates | Terry.Yates@vdot.virginia.gov | (703) 259-2118 | Rita Hockman | Rita.Hockman@vdot.virginia.gov | (804) 824-7421 | Dan Nabors | dnabors@arlingtonva.us | (703) 228-3726 | 0 |  | 0 | FY2020 | 80000 | 80000 | CONSTRUCTION STARTED | R | Start Delivery milestone finished 71 days late | G | Project is on budget | 2019-02-01 | 2019-02-01 | 2019-04-26 | 2019-04-17 | G | 2019-04-29 | 2019-04-18 | 2019-05-01 | 2019-05-01 | G | 2019-05-02 | 2019-05-02 | 2019-06-27 | 2019-05-24 | G | [35 empty] | 2019-09-06 | 2019-09-12 | 2019-09-12 | 2019-09-12 | G | 2019-12-05 | 2020-02-14 | 2019-12-05 | 2020-02-14 | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.27524
649 | 115269 | WATERLOO STREET - PRIMARY EXTENSION PAVING | 6211 | Urban | Resurfacing | Locally | Warrenton | WARRENTON | Culpeper | Northern Virginia:Warrenton | Local Assistance Division | Gregory J Cooley | Gregory.Cooley@vdot.virginia.gov | (434) 906-7979 | John P Price | John.Price@VDOT.Virginia.gov | (540) 347-6371 | PAUL BERNARD | PBERNARD@WARRENTONVA.GOV | (540) 347-1858 | 0 |  | 1 | FY2020 | 313958 | 313958 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 72 days early | G | Project is on budget | 2019-10-02 | 2019-07-09 | 2019-12-31 | 2019-08-07 | G | [5 empty] | 2019-10-02 | 2019-10-02 | 2019-10-15 | 2019-10-08 | G | [25 empty] | 2019-10-09 | 2019-10-10 | 2020-01-08 | 2019-10-22 | G | [5 empty] | 2020-01-21 | 2019-12-01 | 2020-02-18 | 2019-12-01 | G | 2020-05-06 | 2020-02-24 | 2020-05-06 | 2020-02-24 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.078826
650 | 111049 | #SMART18 - (St) WAYNESBORO TOWNE CENTER PARK & RIDE |  | Miscellaneous | Other | VDOT | Waynesboro | HARRISONBURG | Staunton | SAW:Waynesboro | Infrastructure Investment Division | Matthew P Dana | Matt.Dana@VDOT.Virginia.gov | (540) 332-7786 | Anthony E Pelina | Anthony.Pelina@vdot.virginia.gov | (540) 332-9575 |  |  |  | 1 | 2018 | 0 | FY2021 | 2197261 | 1781628 | AWARDED | G | Start Delivery milestone finished 7 days early | G | Project is on budget | [5 empty] | 2017-08-03 | 2017-07-24 | 2017-08-16 | 2017-08-03 | G | 2017-08-17 | 2017-09-01 | 2018-07-17 | 2018-07-17 | G | [5 empty] | 2019-01-04 | 2018-12-18 | 2019-01-17 | 2018-12-18 | G | 2019-09-17 | 2019-09-17 | 2019-09-30 | 2019-09-17 | G | 2020-02-14 | 2020-02-14 | 2020-08-18 | 2020-08-18 | G | 2019-10-16 | 2019-10-16 | 2020-04-13 | 2020-04-13 | G | [10 empty] | 2020-09-08 | 2020-10-06 | 2020-09-08 | 2020-10-06 | R | 2020-10-23 | 2020-12-15 | 2020-12-22 | 2020-12-15 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.072425
651 | 111467 | #SMART18 - SB Rt 288 to WB US 360 WB Off-Ramp, US360 PNRLot | 0288 | Primary | Reconstruction w/ Added Capacity | Locally | Chesterfield County | CHESTERFIELD | Richmond | Richmond:Chesterfield County | Infrastructure Investment Division | Michael S Gray | Mike.Gray@vdot.virginia.gov | (804) 609-5347 | Michael S Gray | Mike.Gray@vdot.virginia.gov | (804) 609-5347 | Chessa Faulkner | faulknerc@chesterfield.gov | (804) 748-1037 | 1 | 2018 | 0 | FY2022 | 14561500 | 14561500 | ACTIVITY DATES SET | R | Complete Purchasing Right-of-Way milestone is 115 days past the expected completion date | G | Project is on budget | 2019-07-01 | 2017-06-15 | 2019-09-24 | 2017-10-19 | G | 2017-09-29 | 2017-07-26 | 2017-09-29 | 2017-07-31 | G | 2019-09-30 | 2017-08-01 | 2020-07-20 | 2019-07-12 | G | [5 empty] | 2019-10-07 | 2019-09-19 | 2019-12-03 | 2020-03-13 | R | 2020-02-27 | 2020-06-03 | 2020-03-27 | 2020-07-08 | R | 2020-10-30 |  | 2021-04-30 |  | G | 2020-04-15 | 2020-07-27 | 2020-10-29 |  | R | 2020-07-01 |  | 2021-07-01 |  | G | [5 empty] | 2021-08-31 |  | 2021-08-31 |  | G | 2021-09-01 |  | 2021-12-30 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.15167
652 | 111707 | #SMART18 - Rtes 13, 852, & 695 Temperanceville/Saxis Rd | 0013 | Primary | Safety | VDOT | Accomack County | ACCOMAC | Hampton Roads | NonMPO:NonMPO | Infrastructure Investment Division | Peter G Reilly | Peter.Reilly@vdot.virginia.gov | (757) 858-6748 | John K Arms | John.Arms@vdot.virginia.gov | (757) 995-5156 | Rich Morrison | rmorrison@co.accomack.va.us | (757) 787-5726 | 1 | 2018 | 0 | FY2021 | 2065456 | 1535099 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 84 days early | G | Project is on budget | [5 empty] | 2017-09-01 | 2017-08-25 | 2017-09-15 | 2017-08-25 | G | 2017-09-18 | 2017-09-18 | 2018-01-17 | 2018-01-17 | G | [5 empty] | 2018-07-10 | 2018-07-10 | 2018-07-23 | 2018-07-12 | G | 2019-04-12 | 2019-03-12 | 2019-04-25 | 2019-03-26 | G | 2019-08-06 | 2019-08-06 | 2020-04-27 | 2020-04-20 | G | 2019-05-13 | 2019-04-04 | 2019-10-31 | 2019-10-11 | G | 2018-10-11 | 2018-10-11 | 2019-04-23 | 2018-10-19 | G | [5 empty] | 2020-05-12 | 2020-02-11 | 2020-05-12 | 2020-02-11 | G | 2020-06-26 | 2020-05-29 | 2020-08-21 | 2020-05-29 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.094606
653 | 112205 | PARK BLVD. - NEW SIDEWALK, CROSS WALKS | 0016 | Urban | Other | Locally | Marion | ABINGDON | Bristol | NonMPO:NonMPO | Infrastructure Investment Division | Tabitha H Crowder | Tabitha.Crowder@vdot.virginia.gov | (276) 696-3482 | Roger L Musser | Roger.Musser@VDOT.Virginia.gov | (276) 696-3260 | Bill Rush | brush@marionva.org | (276) 783-4113 | 0 |  | 0 | FY2020 | 286975 | 282836 | ACTIVITY DATES SET | R | Solicit Bids milestone is 474 days past the expected completion date | G | Project is on budget | 2017-09-01 | 2017-09-01 | 2017-12-01 | 2017-12-01 | G | 2017-12-14 | 2017-12-14 | 2018-01-09 | 2018-01-09 | G | 2017-12-04 | 2017-12-04 | 2018-07-24 | 2018-07-24 | G | [35 empty] | 2019-10-08 |  | 2019-11-05 |  | R | 2019-11-06 |  | 2020-01-07 |  | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.084348
654 | 112810 | ROUTE 211/229 INTERSECTION IMPROVEMENTS - PHASE I | 0211 | Primary | Safety | VDOT | Culpeper County | WARRENTON | Culpeper | NonMPO:NonMPO | Infrastructure Investment Division | Ken Connors |  |  | Caroline Awua-Mensah | Caroline.Awua-Mensah@vdot.virginia.gov | (540) 829-7618 |  |  |  | 0 |  | 0 | FY2019 | 966715 | 496830 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 55 days early | G | Project is on budget | [5 empty] | 2018-10-01 | 2018-04-13 | 2018-10-01 | 2018-04-25 | G | 2018-10-02 | 2018-04-26 | 2019-01-15 | 2019-01-15 | G | [5 empty] | 2019-04-09 | 2019-04-09 | 2019-05-13 | 2019-04-10 | G | [25 empty] | 2019-05-30 | 2019-04-10 | 2019-06-05 | 2019-04-15 | G | 2019-06-06 | 2019-04-18 | 2019-06-12 | 2019-04-18 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | WORK/TASK ORDER | 1 | 0 | 0.080588
655 | 112974 | RTE 668 (Woolridge Road, Rt 288-Old Hundred Road) Extension | 0668 | Secondary | New Construction Roadway | Locally | Chesterfield County | CHESTERFIELD | Richmond | Richmond:Chesterfield County | Local Assistance Division | Cynthia Crouch | Cynthia.Crouch@vdot.virginia.gov | (804) 609-5313 | Cynthia Crouch | Cynthia.Crouch@vdot.virginia.gov | (804) 609-5313 | Nate Mathis | mathisn@chesterfield.gov | (804) 748-1037 | 0 |  | 0 | FY2023 | 47000000 | 47000000 | NO DATES SET YET-PE OPEN | R | Determine Requirements milestone is 387 days past the expected completion date | G | Project is on budget | 2018-07-02 | 2018-07-02 | 2018-09-25 | 2020-07-18 | R | 2018-09-26 | 2018-08-07 | 2018-09-28 | 2018-08-14 | G | 2018-10-01 | 2018-08-15 | 2020-01-31 |  | R | [5 empty] | 2021-02-23 |  | 2021-06-29 |  | G | 2020-10-08 |  | 2020-10-29 |  | R | 2023-03-01 |  | 2024-03-29 |  | G | 2020-11-02 |  | 2022-06-29 |  | G | 2019-05-17 | 2020-10-20 | 2020-01-24 | 2020-10-20 | R | [5 empty] | 2022-07-18 |  | 2022-08-12 |  | G | 2022-08-15 |  | 2022-12-09 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.33762
656 | 113485 | #SGR19LP - BUS 58 - RESURFACING (RIVERSIDE DRIVE) | 7058 | Urban | Resurfacing | Locally | Danville | HALIFAX | Lynchburg | Danville:Danville | Local Assistance Division | Sharon S White | Sharon.White@VDOT.Virginia.gov | (434) 856-8220 | Sharon S White | Sharon.White@VDOT.Virginia.gov | (434) 856-8220 | Brian Dunevant | dunevbl@danvilleva.gov | (434) 799-5019 | 0 |  | 1 | FY2019 | 395000 | 395000 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 17 days early | G | Project is on budget | 2019-01-31 | 2018-09-04 | 2019-04-25 | 2018-09-04 | G | [5 empty] | 2019-01-31 | 2018-09-04 | 2019-02-13 | 2018-09-04 | G | [25 empty] | 2018-10-02 | 2018-09-18 | 2018-12-31 | 2018-12-31 | G | [5 empty] | 2018-10-02 | 2018-09-20 | 2018-10-30 | 2018-10-30 | G | 2019-01-25 | 2019-01-08 | 2019-01-25 | 2019-01-08 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.050361
657 | 113720 | #SGR19LP - Primary EXT Paving - Kecoughtan Rd/ Settlers Lnd | 0060 | Urban | Resurfacing | Locally | Hampton | WILLIAMSBURG | Hampton Roads | Hampton Roads:Hampton | Infrastructure Investment Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Derrick Williams | Derrick.Williams@vdot.virginia.gov | (757) 956-3097 | Sandon Rogers, P.E. | Sandon.rogers@hampton.gov | (757) 727-6786 | 0 |  | 1 | FY2019 | 240000 | 240000 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished on-time | G | Project is on budget | 2018-10-03 | 2018-10-03 | 2019-01-02 | 2019-01-14 | R | 2019-01-03 | 2019-01-10 | 2019-01-07 | 2019-01-14 | R | 2019-01-08 | 2018-07-06 | 2019-07-15 | 2019-01-14 | G | [25 empty] | 2018-05-09 | 2019-01-14 | 2019-01-14 | 2019-01-14 | G | [5 empty] | 2018-12-14 | 2018-12-14 | 2019-01-14 | 2019-01-14 | G | 2019-01-14 | 2019-01-14 | 2019-01-14 | 2019-01-14 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.13722
658 | 114631 | RICHMOND MARINE TERMINAL - EMERGENCY BULKHEAD REAPAIR |  | Miscellaneous | Other | Locally | Richmond | ASHLAND | Richmond | Richmond:Richmond | Infrastructure Investment Division | Brian J Lokker | Brian.Lokker@VDOT.Virginia.gov | (804) 524-6010 | Brian J Lokker | Brian.Lokker@VDOT.Virginia.gov | (804) 524-6010 | John Brady | jbrady@portofvirginia.com | (757) 683-2139 | 0 |  | 0 | FY2021 | 982000 | 909438 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 248 days early | G | Project is on budget | 2018-12-10 | 2018-12-05 | 2019-03-08 | 2019-02-14 | G | 2019-03-11 | 2019-02-13 | 2019-03-13 | 2019-02-20 | G | 2019-03-14 | 2019-03-14 | 2019-09-16 | 2019-09-16 | G | [25 empty] | 2019-09-16 | 2019-12-11 | 2020-06-29 | 2019-12-11 | G | [5 empty] | 2020-08-04 | 2019-12-22 | 2020-08-24 | 2019-12-23 | G | 2020-11-13 | 2020-03-10 | 2020-11-13 | 2020-03-10 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.091823
659 | 115250 | #SGR20LP - Chippenham Parkway N (Archdale) - Resurfacing | 0150 | Urban | Resurfacing | Locally | Richmond | ASHLAND | Richmond | Richmond:Richmond | Local Assistance Division | Brian J Lokker | Brian.Lokker@VDOT.Virginia.gov | (804) 524-6010 | Brian J Lokker | Brian.Lokker@VDOT.Virginia.gov | (804) 524-6010 | Kenny Horak | Kenneth.horak@richmondgov.com | (804) 646-4781 | 0 |  | 1 | FY2020 | 236522 | 236522 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 5 days early | G | Project is on budget | 2019-07-01 | 2019-04-16 | 2019-09-24 | 2020-01-30 | R | [5 empty] | 2019-09-25 | 2020-01-30 | 2019-11-27 | 2020-02-13 | R | [25 empty] | 2020-02-14 | 2020-03-04 | 2020-04-29 | 2020-03-04 | G | [5 empty] | 2020-05-01 | 2020-03-19 | 2020-05-01 | 2020-03-19 | G | 2020-06-30 | 2020-06-25 | 2020-06-30 | 2020-06-25 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 |  | 1 | 0 | 0.081938
660 | 115769 | Libbie Avenue Road Diet - Bethlehem Rd to W Broad St | 9999 | Secondary | Traffic Management/Engineering | Locally | Henrico County | ASHLAND | Richmond | Richmond:Henrico County | Infrastructure Investment Division | Douglas L Orcutt | Doug.Orcutt@vdot.virginia.gov | (804) 609-5428 | Douglas L Orcutt | Doug.Orcutt@vdot.virginia.gov | (804) 609-5428 | TBD | smi20@henrico.us | TBD | 0 |  | 0 | FY2025 | 1725000 | 1725000 | NO DATES SET YET | G | Agreement with Locality milestone is 285 days ahead of the expected completion date | G | Project is on budget | 2021-09-07 |  | 2021-12-03 |  | G | 2021-12-06 |  | 2022-01-18 |  | G | 2022-01-19 |  | 2022-07-22 |  | G | [10 empty] | 2023-05-18 |  | 2023-06-08 |  | G | [5 empty] | 2023-06-12 |  | 2024-03-25 |  | G | 2022-08-29 |  | 2023-05-05 |  | G | [5 empty] | 2024-04-10 |  | 2024-05-07 |  | G | 2024-07-26 |  | 2024-07-26 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.29679
661 | 115920 | HSIP HR Flashing Yellow Arrows | 9999 | Primary | Safety | VDOT | Hampton Roads District-wide |  | Hampton Roads | Hampton Roads:Hampton Roads District-wide | Infrastructure Investment/Asset Management Division | Todd M Halacy | Todd.Halacy@VDOT.Virginia.gov | (757) 956-3010 | Mark S Winslow | Mark.Winslow@VDOT.Virginia.gov | (757) 925-1528 |  |  |  | 0 |  | 0 | FY2020 | 102000 | 102000 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 33 days early | G | Project is on budget | [5 empty] | 2019-09-03 | 2019-09-03 | 2019-12-16 | 2019-12-16 | G | 2019-12-17 | 2019-12-17 | 2020-04-16 | 2020-04-14 | G | [5 empty] | 2020-04-14 | 2020-04-14 | 2020-04-14 | 2020-04-14 | G | [25 empty] | 2020-05-27 | 2020-04-30 | 2020-05-27 | 2020-04-30 | G | 2020-05-28 | 2020-05-01 | 2020-06-03 | 2020-05-01 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | WORK/TASK ORDER | 1 | 0 | 0.083303
662 | 116855 | NORTH STUART AVENUE SIDEWALK EXTENSION |  | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Elkton | HARRISONBURG | Staunton | NonMPO:NonMPO | Local Assistance Division | Kimberly Cameron | Kim.Cameron@vdot.virginia.gov | (540) 332-7886 | Kimberly Cameron | Kim.Cameron@vdot.virginia.gov | (540) 332-7886 | Greg Lunsford | glunsford@townofelkton.com | (540) 713-8837 | 0 |  | 0 | FY2025 | 484011 | 484011 | NO DATES SET YET | G | Agreement with Locality milestone is 57 days ahead of the expected completion date | G | Project is on budget | 2020-12-08 |  | 2021-04-19 |  | G | 2021-04-20 |  | 2021-05-10 |  | G | 2021-11-16 |  | 2022-03-16 |  | G | [10 empty] | 2023-07-05 |  | 2023-08-08 |  | G | [5 empty] | 2023-08-09 |  | 2024-01-11 |  | G | 2023-12-07 |  | 2024-05-08 |  | G | [5 empty] | 2024-04-17 |  | 2024-05-14 |  | G | 2024-08-02 |  | 2024-08-02 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.34
663 | 117028 | RURAL ADDITION - PAVE UNPAVED DEUX RUE | 9999 | Secondary | Resurfacing | VDOT | Westmoreland County | NORTHERN NECK | Fredericksburg | NonMPO:NonMPO | Local Assistance Division | David L Beale | David.Beale@vdot.virginia.gov | (804) 333-7941 | William C White | Carter.White@VDOT.Virginia.gov | (804) 333-7942 |  |  |  | 0 |  | 0 | FY2029 | 120000 | 120000 | NO DATES SET YET | G | Start Development milestone is 1704 days ahead of the expected completion date | G | Project is on budget | [5 empty] | 2025-10-01 |  | 2025-10-22 |  | G | 2025-10-23 |  | 2026-08-26 |  | G | [5 empty] | 2027-04-01 |  | 2027-04-28 |  | G | [5 empty] | 2027-12-21 |  | 2028-04-24 |  | G | [5 empty] | 2027-09-09 |  | 2028-02-14 |  | G | [5 empty] | 2028-05-09 |  | 2028-05-09 |  | G | 2028-07-28 |  | 2028-07-28 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | SAAP CONTRACT | 0 | 0 | 0.089561
664 | 118148 | Richmond Signal System ??? Phase IV | 9999 | Miscellaneous | Safety | Locally | Richmond | ASHLAND | Richmond | Richmond:Richmond | Infrastructure Investment Division | Olena Fecek | Olena.Fecek@vdot.virginia.gov | (804) 524-6368 | Olena Fecek | Olena.Fecek@vdot.virginia.gov | (804) 524-6368 | Enrique Burgos | enrique.burgos@richmondgov.com | (804) 646-6337 | 0 |  | 0 | FY2026 | 5488000 | 5488000 | NO DATES SET YET | G | Agreement with Locality milestone is 809 days ahead of the expected completion date | G | Project is on budget | 2023-01-03 |  | 2023-05-11 |  | G | 2023-05-12 |  | 2023-06-02 |  | G | 2023-12-12 |  | 2024-04-08 |  | G | [25 empty] | 2025-04-03 |  | 2025-08-29 |  | G | [5 empty] | 2025-10-29 |  | 2025-11-26 |  | G | 2026-02-23 |  | 2026-02-23 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.085907
665 | 87616 | Revenue Sharing - Tevis Street Extension | 0788 | Secondary | New Construction Roadway | Locally | Frederick County | EDINBURG | Staunton | Winchester:Frederick County | Local Assistance Division | Kimberly Cameron | Kim.Cameron@vdot.virginia.gov | (540) 332-7886 | Kimberly Cameron | Kim.Cameron@vdot.virginia.gov | (540) 332-7886 | Mike Stewart | mstewart@fcva.us | (540) 722-8218 | 0 |  | 0 | FY2019 | 9591404 | 13543656 | CONSTRUCTION STARTED | R | Start Delivery milestone finished 73 days late | R | Project estimate is between $5M and $10M and is a $1M or more over budget | [5 empty] | 2008-01-02 | 2013-07-01 | 2012-07-02 | 2013-07-01 | R | 2013-09-30 | 2013-09-30 | 2014-11-28 | 2014-11-06 | G | [35 empty] | 2018-07-02 | 2019-01-14 | 2018-07-02 | 2019-01-14 | R | 2018-09-04 | 2019-02-28 | 2018-12-31 | 2019-03-14 | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.3454
666 | 104300 | ROGUES ROAD - RECONSTRUCTION OF ROAD | 0602 | Secondary | Reconstruction w/o Added Capacity | VDOT | Fauquier County | WARRENTON | Culpeper | Northern Virginia:Fauquier | Infrastructure Investment Division | Gregory J Cooley | Gregory.Cooley@vdot.virginia.gov | (434) 906-7979 | James D Cubbage | David.Cubbage@VDOT.Virginia.gov | (540) 727-7129 |  |  |  | 0 |  | 0 | FY2022 | 5013644 | 5001908 | ACTIVITY DATES SET | R | Start Purchasing Right-of-Way milestone finished 115 days late | G | Project is on budget | [5 empty] | 2015-07-21 | 2015-07-21 | 2015-07-22 | 2015-07-22 | G | 2015-07-24 | 2015-07-24 | 2018-08-31 | 2019-05-28 | R | [5 empty] | 2019-10-04 | 2019-06-05 | 2019-10-17 | 2019-10-08 | G | 2020-05-13 | 2020-09-02 | 2020-05-26 | 2020-09-18 | R | 2021-04-05 |  | 2021-10-01 |  | G | 2020-06-29 | 2020-09-21 | 2021-04-02 |  | Y | [10 empty] | 2021-11-09 |  | 2021-11-09 |  | G | 2022-04-01 |  | 2022-04-01 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.15112
667 | 106299 | PEDESTRIAN & SIGNAL IMPROVEMENTS - VARIOUS LOCATIONS(AZALEA) | 7596 | Secondary | Facilities for Pedestrians and Bicycles | Locally | Henrico County | ASHLAND | Richmond | Richmond:Henrico County | Infrastructure Investment Division | Cynthia Crouch | Cynthia.Crouch@vdot.virginia.gov | (804) 609-5313 | Cynthia Crouch | Cynthia.Crouch@vdot.virginia.gov | (804) 609-5313 | Michael Aust | AUS019@henrico.us | (804) 501-4019 | 0 |  | 0 | FY2021 | 1615000 | 1615000 | ADVERTISED | R | Start Delivery milestone is 23 days past the expected completion date | G | Project is on budget | 2016-10-14 | 2016-03-22 | 2016-10-14 | 2016-06-03 | G | 2016-11-01 | 2016-08-10 | 2016-11-01 | 2016-08-30 | G | 2018-07-02 | 2018-07-02 | 2018-07-31 | 2018-07-24 | G | [5 empty] | 2019-04-30 | 2019-04-12 | 2019-06-11 | 2019-06-12 | R | 2019-02-15 | 2019-03-07 | 2019-07-09 | 2019-06-26 | G | 2020-02-10 | 2020-02-10 | 2020-05-18 | 2020-09-22 | R | 2019-08-07 | 2019-09-05 | 2020-07-23 | 2020-10-20 | R | [10 empty] | 2020-07-01 | 2020-12-18 | 2020-07-30 | 2020-12-18 | R | 2020-11-30 |  | 2021-01-29 |  | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.26319
668 | 106986 | HERNDON METRORAIL INTERMODAL ACCESS IMPROVEMENTS PH II | 9999 | Urban | Traffic Management/Engineering | Locally | Herndon | FAIRFAX | Northern Virginia | Northern Virginia:Herndon | Infrastructure Investment Division | Amir Salahshoor | A.Salahshoor@VDOT.Virginia.gov | (703) 259-1957 | Rhoderick M Undan | Rhoderick.Undan@vdot.virginia.gov | (703) 259-3347 | Dana Singer | dana.singer@herndon-va.gov | (703) 435-6800 | 0 |  | 0 | FY2027 | 1908000 | 1908000 | NO DATES SET YET | G | Agreement with Locality milestone is 768 days ahead of the expected completion date | Y | Estimate not current | 2022-09-15 |  | 2023-03-31 |  | G | 2023-04-03 |  | 2023-04-28 |  | G | 2024-02-01 |  | 2024-10-01 |  | G | [10 empty] | 2025-07-29 |  | 2025-09-02 |  | G | [5 empty] | 2025-09-04 |  | 2026-06-30 |  | G | 2026-02-27 |  | 2026-10-30 |  | G | [5 empty] | 2026-07-17 |  | 2026-12-30 |  | G | 2026-12-31 |  | 2027-06-30 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.28471
669 | 107458 | #HB2.FY17 RTE 64 - MAJOR WIDENING | 0064 | Interstate | Reconstruction w/ Added Capacity | VDOT | Henrico County | ASHLAND | Richmond | Richmond:Henrico County | Infrastructure Investment Division | Donna Prock |  |  | Scott J Fisher | Scott.Fisher@VDOT.Virginia.gov | (804) 674-2452 |  |  |  | 1 | 2017 | 0 | FY2018 | 59910388 | 50959084 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 41 days early | G | Project is on budget | [5 empty] | 2016-07-06 | 2016-07-06 | 2016-08-01 | 2016-08-01 | G | 2016-08-02 | 2016-08-02 | 2017-01-12 | 2017-01-12 | G | [5 empty] | 2017-01-17 | 2017-01-17 | 2017-02-23 | 2017-02-23 | G | 2017-03-10 | 2017-03-10 | 2017-03-13 | 2017-03-13 | G | [20 empty] | 2017-03-14 | 2017-03-17 | 2017-03-17 | 2017-03-17 | G | 2017-04-04 | 2017-07-19 | 2017-08-29 | 2017-07-19 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | DESIGN BUILD/PPTA | 1 | 0 | 0.11071
670 | 115511 | #SMART20 Route 31 Bicycle Accommodations | 0031 | Primary | Facilities for Pedestrians and Bicycles | VDOT | Surry County | WILLIAMSBURG | Hampton Roads | NonMPO:NonMPO | Infrastructure Investment Division | Hayden Hill | Hayden.Hill@volkert.com | (703) 642-8100 | John G Harman | JohnG.Harman@vdot.virginia.gov | (757) 956-3269 | Frances Bailey | fbailey@surrycountyva.gov | (757) 294-5210 | 1 | 2020 | 0 | FY2024 | 9600000 | 9600000 | NO DATES SET YET-PE OPEN | R | Determine Requirements milestone is 79 days past the expected completion date | G | Project is on budget | [5 empty] | 2019-09-26 | 2019-09-06 | 2019-12-02 | 2019-09-25 | G | 2019-12-03 |  | 2020-12-04 |  | R | [5 empty] | 2021-10-07 |  | 2021-10-21 |  | G | 2023-02-02 |  | 2023-02-15 |  | G | 2023-07-11 |  | 2024-01-19 |  | G | 2023-03-06 |  | 2023-09-06 |  | G | 2022-07-18 |  | 2023-01-26 |  | G | [5 empty] | 2024-02-13 |  | 2024-02-13 |  | G | 2024-05-03 |  | 2024-05-03 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.16207
671 | 115912 | INSTALL PEDESTRIAN ACCOMMODATIONS - BROOK RD AT PARHAM RD | 0001 | Primary | Safety | VDOT | Henrico County | ASHLAND | Richmond | Richmond:Henrico County | Infrastructure Investment/Asset Management Division | Ronnie Hobson | Ron.Hobson@vdot.virginia.gov | (804) 840-5501 | Ronnie Hobson | Ron.Hobson@vdot.virginia.gov | (804) 840-5501 | N\A |  |  | 0 |  | 0 | FY2021 | 100000 | 100000 | AWARDED | G | Start Delivery milestone finished 7 days early | G | Project is on budget | [10 empty] | 2020-03-02 | 2020-03-02 | 2020-07-07 | 2020-05-19 | G | [35 empty] | 2020-07-09 | 2020-07-15 | 2020-07-15 | 2020-07-15 | G | 2020-07-16 | 2020-07-15 | 2020-07-22 | 2020-07-15 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | WORK/TASK ORDER | 1 | 0 | 0.077463
672 | 116390 | ROUTE 28 NB WIDENING - AREA 4 | 0028 | Primary | Reconstruction w/ Added Capacity | VDOT | Fairfax County | FAIRFAX | Northern Virginia | Northern Virginia:Fairfax County | Infrastructure Investment Division | Sanjeev Suri | Sanjeev.Suri@VDOT.Virginia.gov | (703) 259-2232 | Sanjeev Suri | Sanjeev.Suri@VDOT.Virginia.gov | (703) 259-2232 |  |  |  | 0 |  | 0 | FY2020 |  |  | CONSTRUCTION STARTED | G | Start Delivery milestone finished 75 days early | R | Critical information missing | [10 empty] | 2019-09-03 | 2019-03-01 | 2020-01-14 | 2019-06-01 | G | [35 empty] | 2019-08-27 | 2019-06-17 | 2019-09-03 | 2019-06-25 | G | 2019-09-04 | 2019-06-26 | 2019-09-10 | 2019-06-27 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | WORK/TASK ORDER | 1 | 0 | 0.079349
673 | 116897 | ROUNDABOUT AT WALKER DRIVE AND EAST LEE STREET | 9999 | Urban | Reconstruction w/o Added Capacity | Locally | Warrenton | WARRENTON | Culpeper | Northern Virginia:Warrenton | Local Assistance Division | Gregory J Cooley | Gregory.Cooley@vdot.virginia.gov | (434) 906-7979 | John P Price | John.Price@VDOT.Virginia.gov | (540) 347-6371 | Paul Bernard | pbernard@warrentonva.gov | (540) 347-1858 | 0 |  | 0 | FY2024 | 1400000 | 1400000 | NO DATES SET YET | G | Agreement with Locality milestone is 50 days ahead of the expected completion date | G | Project is on budget | 2020-12-01 |  | 2021-04-12 |  | G | 2021-04-13 |  | 2021-05-03 |  | G | 2021-11-08 |  | 2022-03-09 |  | G | [25 empty] | 2023-03-06 |  | 2023-08-01 |  | G | [5 empty] | 2023-09-28 |  | 2023-10-26 |  | G | 2024-01-23 |  | 2024-01-23 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.11729
674 | 117066 | Wagner Ave and Hooker St Reconstruction |  | Urban | Reconstruction w/o Added Capacity | Locally | Hopewell | PETERSBURG | Richmond | Tri-Cities:Hopewell | Local Assistance Division | James Shepherd | James.Shepherd@vdot.virginia.gov | (804) 609-5305 | James Shepherd | James.Shepherd@vdot.virginia.gov | (804) 609-5305 | TBD |  | TBD | 0 |  | 0 | FY2028 | 451220 | 451220 | NO DATES SET YET | G | Agreement with Locality milestone is 1543 days ahead of the expected completion date | G | Project is on budget | 2025-01-06 |  | 2025-05-14 |  | G | 2025-05-15 |  | 2025-06-05 |  | G | 2025-07-07 |  | 2025-10-28 |  | G | [25 empty] | 2026-10-23 |  | 2027-03-30 |  | G | [5 empty] | 2027-05-26 |  | 2027-06-23 |  | G | 2027-09-13 |  | 2027-09-13 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.071431
675 | 86601 | #SGR21VB - 58 over Powell River Va struc 1045 | 0058 | Primary | Bridge Replacement w/o Added Capacity | VDOT | Lee County | WISE | Bristol | NonMPO:NonMPO | Infrastructure Investment Division | Jeffrey B Powell | Jeffrey.Powell@VDOT.Virginia.gov | (276) 696-3389 | James R Jones | jamesr.jones@vdot.virginia.gov | (276) 696-3257 |  |  |  | 0 |  | 0 | FY2020 | 8710000 | 9115580 | CONSTRUCTION STARTED | R | Start Delivery milestone finished 97 days late | Y | Project estimate is between $5M and $10M and is up to $1M over budget | [5 empty] | 2011-04-01 | 2011-04-01 | 2011-04-01 | 2011-04-01 | G | 2013-06-03 | 2011-09-22 | 2016-01-28 | 2016-04-26 | R | [5 empty] | 2016-07-01 | 2016-07-01 | 2016-08-01 | 2016-08-01 | G | 2017-01-27 | 2017-01-27 | 2017-02-10 | 2017-02-10 | G | 2017-08-16 | 2017-08-16 | 2019-03-28 | 2019-11-05 | R | 2017-05-01 | 2017-05-01 | 2019-02-08 | 2019-10-07 | R | 2012-07-31 | 2012-07-31 | 2019-02-11 | 2019-01-02 | G | [5 empty] | 2019-05-09 | 2019-11-05 | 2019-06-11 | 2019-11-05 | R | 2019-08-15 | 2020-01-20 | 2019-10-15 | 2020-01-20 | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.07434
676 | 91191 | Rnke River Grnwy - City of Roanoke to Route 618 |  | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Roanoke County | SALEM | Salem | Roanoke:Roanoke County | Local Assistance Division | Anthony W Ford | Anthony.Ford@VDOT.Virginia.gov | (540) 378-5040 | Cheryl B Becker | Cheryl.Becker@vdot.virginia.gov | (540) 492-2531 | Lindsay Webb | LWEBB@roanokecountyva.gov | (540) 777-6328 | 0 |  | 0 | FY2019 | 7105402 | 6935771 | ACTIVITY DATES SET | R | Solicit Bids milestone is 878 days past the expected completion date | Y | Estimate not current | [5 empty] | 2009-01-01 | 2009-02-25 | 2009-01-01 | 2009-02-25 | R | 2013-04-30 | 2013-07-10 | 2016-10-01 | 2016-10-01 | G | [10 empty] | 2018-01-16 | 2018-05-03 | 2018-08-30 | 2018-07-17 | G | [20 empty] | 2018-06-01 |  | 2018-09-27 |  | R | 2018-10-01 |  | 2019-02-14 |  | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.36181
677 | 106054 | Wentworth Drive SRTS Sidewalk |  | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Winchester | EDINBURG | Staunton | Winchester:Winchester | Local Assistance Division | Kimberly Cameron | Kim.Cameron@vdot.virginia.gov | (540) 332-7886 | Kimberly Cameron | Kim.Cameron@vdot.virginia.gov | (540) 332-7886 | Perry Eisenach | perry.eisenach@winchesterva.gov | (540) 667-1815 | 0 |  | 0 | FY2020 | 562500 | 3425564 | CONSTRUCTION STARTED | R | Start Delivery milestone finished 40 days late | R | Project estimate is less than $5M and is 20% or more over budget | [5 empty] | 2016-10-03 | 2016-09-21 | 2016-10-03 | 2016-10-03 | G | 2018-08-01 | 2018-08-01 | 2018-12-03 | 2018-12-03 | G | [35 empty] | 2019-10-03 | 2019-09-23 | 2019-10-03 | 2019-09-23 | G | 2019-10-23 | 2019-10-23 | 2019-12-18 | 2020-01-27 | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.38005
678 | 106742 | FRONTIER DRIVE EXTENSION AND BRAIDED RAMPS | 2677 | Secondary | Reconstruction w/ Added Capacity | VDOT | Fairfax County | FAIRFAX | Northern Virginia | Northern Virginia:Fairfax County | Infrastructure Investment Division | Andrew G Beacher | Andrew.Beacher@vdot.virginia.gov | (703) 259-2239 | Zamir A Mirza | Zamir.Mirza@VDOT.Virginia.gov | (703) 259-1794 | Audra Bandy | Audra.Bandy@fairfaxcounty.gov | (703) 877-5753 | 0 |  | 0 | FY2021 | 140000000 | 140000000 | NO DATES SET YET-PE OPEN | R | Determine Requirements milestone is 1825 days past the expected completion date | G | Project is on budget | 2014-12-14 | 2014-12-14 | 2015-03-27 | 2015-03-27 | G | 2015-01-05 | 2015-05-14 | 2015-01-20 | 2015-05-14 | R | 2015-01-21 | 2015-01-21 | 2016-02-23 |  | R | [5 empty] | 2017-02-03 |  | 2017-02-16 |  | R | 2018-12-28 |  | 2019-01-11 |  | R | 2020-03-17 |  | 2020-09-17 |  | R | 2019-01-31 |  | 2019-08-05 |  | R | 2018-05-03 |  | 2019-05-03 |  | R | [5 empty] | 2021-01-25 |  | 2021-01-25 |  | R | 2021-03-09 |  | 2021-03-29 |  | G | Delay due to changes in scope of work, project management, plan designs, or resolution of public comments | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.15719
679 | 107075 | DEAN DRIVE EXTENSION | 9999 | Urban | New Construction Roadway | Locally | Manassas | MANASSAS | Northern Virginia | Northern Virginia:Manassas | Local Assistance Division | Amir Salahshoor | A.Salahshoor@VDOT.Virginia.gov | (703) 259-1957 | Marlene Pinedo Fortich | Sofia.Pinedo@vdot.virginia.gov | (703) 259-1724 | Bryan Foster | bfoster@manassasva.gov | (703) 257-8226 | 0 |  | 0 | FY2019 | 2461000 | 4280000 | ACTIVITY DATES SET | R | Complete Purchasing Right-of-Way milestone is 724 days past the expected completion date | R | Project estimate is less than $5M and is 20% or more over budget | 2015-07-01 | 2015-07-01 | 2015-09-24 | 2015-09-01 | G | 2015-09-25 | 2015-10-29 | 2015-10-08 | 2015-10-29 | R | 2015-10-09 | 2015-10-30 | 2016-06-08 | 2016-06-28 | R | [10 empty] | 2017-05-18 | 2017-05-18 | 2017-06-01 | 2017-06-01 | G | [5 empty] | 2017-06-06 | 2017-06-06 | 2019-02-28 |  | R | [10 empty] | 2019-03-27 |  | 2019-03-27 |  | R | 2019-03-28 |  | 2019-03-28 |  | R | Delay due to unforeseen issues with utilities, railroad coordination, or right-of-way acquisition | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.15073
680 | 108798 | Portsmouth Systematic FYA | 0000 | Urban | Safety | Locally | Portsmouth | NORFOLK | Hampton Roads | Hampton Roads:Portsmouth | Infrastructure Investment Division | Susan Wilson | Susan.Wilson@vdot.virginia.gov | (757) 956-3099 | Marci Thompson | Marci.Thompson@vdot.virginia.gov | (757) 956-3093 | James Wright, P. E. | wrightj@portsmouthva.gov | (757) 393-8592 | 0 |  | 0 | FY2021 | 957437 | 960170 | ACTIVITY DATES SET | R | Solicit Bids milestone is 54 days past the expected completion date | Y | Project estimate is less than $5M and is up to 20% over budget | 2017-10-17 | 2017-02-14 | 2018-01-17 | 2017-05-08 | G | 2018-01-18 | 2017-05-08 | 2018-01-22 | 2017-05-08 | G | 2018-01-23 | 2018-03-27 | 2018-07-26 | 2019-10-11 | R | [25 empty] | 2020-08-04 | 2019-10-11 | 2020-10-21 | 2019-10-11 | G | [5 empty] | 2020-11-13 |  | 2020-12-29 |  | R | 2021-03-23 |  | 2021-06-15 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.19847
681 | 109076 | Amtrak Multimodal Station - Station, Platform, Parking Lot | 0000 | Public Transportation | Transit | Locally | Newport News | WILLIAMSBURG | Hampton Roads | Hampton Roads:Newport News | Infrastructure Investment Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Chessica Villaflores | Chessica.Villaflores@vdot.virginia.gov | (757) 956-3094 | Vincent Urbano, Assistant Chief of Design | vurbano@nnva.gov | (757) 926-8694 | 0 |  | 0 | FY2022 | 14632204 | 14151971 | AWARDED | G | Solicit Bids milestone finished 321 days early | G | Project is on budget | 2017-03-15 | 2016-10-04 | 2018-10-17 | 2017-04-21 | G | [5 empty] | 2018-10-18 | 2018-10-18 | 2019-11-01 | 2019-09-06 | G | [35 empty] | 2020-10-14 | 2020-03-05 | 2021-03-01 | 2020-04-14 | G | 2021-05-18 | 2020-04-15 | 2021-08-11 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.26646
682 | 109703 | #HB2.FY17 RTE 360 - TURN LANES & ENTR AT HEARTLAND BUS PARK | 0360 | Primary | Safety | VDOT | Charlotte County | DILLWYN | Lynchburg | NonMPO:NonMPO | Infrastructure Investment Division | Carrie Shepheard | Carrie.Shepheard@vdot.virginia.gov | (434) 422-9373 | John E Neblett | John.Neblett@VDOT.Virginia.gov | (434) 856-8202 |  |  |  | 1 | 2017 | 0 | FY2020 | 789197 | 210000 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 565 days early | G | Project is on budget | [5 empty] | 2017-04-03 | 2017-04-03 | 2017-04-14 | 2017-04-14 | G | 2017-04-17 | 2017-04-17 | 2017-10-19 | 2017-10-18 | G | [5 empty] | 2018-03-06 | 2018-06-26 | 2018-03-19 | 2018-06-26 | R | 2018-10-16 | 2018-05-17 | 2018-10-29 | 2018-05-17 | G | 2019-05-10 | 2018-05-17 | 2019-10-30 | 2018-05-17 | G | 2018-11-15 | 2018-05-17 | 2019-05-10 | 2018-05-17 | G | [10 empty] | 2019-11-12 | 2018-07-10 | 2019-11-12 | 2018-07-10 | G | 2020-01-07 | 2018-07-13 | 2020-01-29 | 2018-07-13 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | STATE FORCES/HIRED EQUIPMENT | 1 | 0 | 0.093433
683 | 110574 | #SGR18LB - Apperson Drive Bridge Replacement | 0011 | Urban | Bridge Replacement w/ Added Capacity | Locally | Salem | SALEM | Salem | Roanoke:Salem | Infrastructure Investment Division | Cheryl B Becker | Cheryl.Becker@vdot.virginia.gov | (540) 492-2531 | Cheryl B Becker | Cheryl.Becker@vdot.virginia.gov | (540) 492-2531 | Will Simpson | wsimpson@salemva.gov | (540) 375-3032 | 0 |  | 1 | FY2021 | 7100800 | 7100800 | NO DATES SET YET-PE OPEN | R | Determine Requirements milestone is 593 days past the expected completion date | G | Project is on budget | 2017-12-01 | 2017-03-21 | 2018-07-02 | 2018-10-24 | R | 2018-07-03 | 2018-11-05 | 2018-07-06 | 2018-11-05 | R | 2018-07-09 | 2018-11-06 | 2019-07-09 |  | R | [10 empty] | 2020-02-14 |  | 2020-03-05 |  | R | [5 empty] | 2020-03-09 |  | 2020-12-15 |  | R | [10 empty] | 2021-01-04 |  | 2021-02-02 |  | R | 2021-02-03 |  | 2021-06-24 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.28404
684 | 110969 | #SGR19LB??- Parham Rd/CSX Bridge | 9999 | Urban | Bridge Rehab w/o Added Capacity | Locally | Henrico County | ASHLAND | Richmond | Richmond:Henrico County | Local Assistance Division | Brian J Lokker | Brian.Lokker@VDOT.Virginia.gov | (804) 524-6010 | Brian J Lokker | Brian.Lokker@VDOT.Virginia.gov | (804) 524-6010 | Paul Smith | smi91@henrico.us | (804) 501-4617 | 0 |  | 1 | FY2020 | 1785000 | 1774000 | AWARDED | R | Start Delivery milestone finished 25 days late | G | Project is on budget | 2019-05-31 | 2017-08-01 | 2019-08-23 | 2018-01-04 | G | [5 empty] | 2019-05-31 | 2019-03-12 | 2019-06-13 | 2019-06-12 | G | [35 empty] | 2019-10-01 | 2019-12-13 | 2019-10-31 | 2019-12-13 | R | 2019-12-17 | 2019-12-17 | 2020-01-31 | 2020-02-25 | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.35014
685 | 111400 | OLD BRIDGE ROAD SIDEWALK | 0641 | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Prince William County | MANASSAS | Northern Virginia | Northern Virginia:Prince William County | Local Assistance Division | Bud Siegel |  |  | Saif-Ur Qargha | Saif.Qargha@vdot.virginia.gov | (703) 259-3223 | Prince William County | LKulczycki@pawgov.org | (703) 792-6347 | 0 |  | 0 | FY2022 | 830000 | 800587 | ACTIVITY DATES SET | R | Complete Purchasing Right-of-Way milestone is 72 days past the expected completion date | G | Project is on budget | 2017-10-02 | 2017-10-02 | 2018-02-14 | 2018-02-14 | G | 2018-02-15 | 2018-02-15 | 2018-03-23 | 2018-03-23 | G | 2018-06-07 | 2018-06-07 | 2019-03-01 | 2018-11-21 | G | [10 empty] | 2020-02-11 | 2019-10-01 | 2020-03-03 | 2019-10-15 | G | [5 empty] | 2020-03-05 | 2019-12-02 | 2020-12-11 |  | R | [10 empty] | 2020-12-30 |  | 2021-06-22 |  | G | 2021-06-23 |  | 2021-12-15 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.41121
686 | 111975 | Remington Depot - C502 Exterior Restoration |  | Enhancement | Rehabilitation of Historic Bldgs/Facilities | Locally | Remington | WARRENTON | Culpeper | NonMPO:NonMPO | Local Assistance Division | Dewitt D Sprinkel | Brent.Sprinkel@VDOT.Virginia.gov | (540) 829-7552 | John P Price | John.Price@VDOT.Virginia.gov | (540) 347-6371 | Sharon Lee | slee@remington-va.gov | (540) 439-3220 | 0 |  | 0 | FY2020 | 122723 | 116334 | ADVERTISED | R | Start Delivery milestone is 405 days past the expected completion date | G | Project is on budget | 2017-09-01 | 2017-09-01 | 2017-09-01 | 2017-09-01 | G | 2017-09-12 | 2017-09-12 | 2017-09-12 | 2017-09-12 | G | 2017-09-13 | 2017-09-13 | 2018-12-31 | 2019-03-21 | R | [35 empty] | 2019-10-30 | 2020-07-22 | 2019-11-27 | 2020-10-05 | R | 2019-12-02 |  | 2020-01-13 |  | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.25959
687 | 112468 | ROBERTS RD & SHENANDOAH RIVER LN, INSTALL NEW TRAFFIC SIGNAL | 0653 | Secondary | Safety | VDOT | Fairfax County | FAIRFAX | Northern Virginia | Northern Virginia:Fairfax County | Infrastructure Investment Division | Ivan M Horodyskyj | Ivan.Horodyskyj@VDOT.Virginia.gov | (703) 259-2330 | Jessica Paris | Jessica.Paris@vdot.virginia.gov | (703) 259-2409 | TBD |  |  | 0 |  | 0 | FY2020 | 557500 | 514326 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 124 days early | G | Project is on budget | [5 empty] | 2022-10-03 | 2018-11-09 | 2022-10-14 | 2018-11-19 | G | 2022-10-18 | 2018-11-27 | 2023-09-14 | 2019-05-08 | G | [5 empty] | 2018-11-27 | 2018-11-27 | 2018-12-28 | 2018-12-28 | G | 2019-06-24 | 2019-05-09 | 2019-06-24 | 2019-05-09 | G | 2019-04-29 | 2019-05-09 | 2019-05-09 | 2019-05-09 | G | 2019-06-25 | 2019-05-09 | 2019-06-25 | 2019-05-16 | G | [10 empty] | 2019-08-13 | 2019-07-09 | 2019-10-08 | 2019-07-09 | G | 2019-11-22 | 2019-07-31 | 2019-12-02 | 2019-07-31 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | WORK/TASK ORDER | 1 | 0 | 0.082395
688 | 112958 | Old Oak Ln., Phase IV Rural Addition - Warren County | 0709 | Secondary | Reconstruction w/o Added Capacity | Locally | Warren County | EDINBURG | Staunton | NonMPO:NonMPO | Local Assistance Division | Kimberly Cameron | Kim.Cameron@vdot.virginia.gov | (540) 332-7886 | Kimberly Cameron | Kim.Cameron@vdot.virginia.gov | (540) 332-7886 | Mike Berry | mberry@warrencountyva.net | (540) 636-1543 | 0 |  | 0 | FY2021 | 998250 | 975323 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 107 days early | G | Project is on budget | 2018-10-31 | 2018-07-11 | 2019-01-31 | 2018-09-21 | G | 2019-02-01 | 2018-09-24 | 2019-02-05 | 2019-02-05 | G | 2019-02-06 | 2019-02-06 | 2019-08-09 | 2019-02-12 | G | [25 empty] | 2019-02-13 | 2019-02-12 | 2019-10-14 | 2019-02-14 | G | [5 empty] | 2020-06-22 | 2020-04-01 | 2020-07-20 | 2020-04-25 | G | 2020-10-07 | 2020-05-29 | 2020-10-07 | 2020-06-22 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.20829
689 | 113073 | COLUMBIA ST - REPLACE STR |  | Urban | Bridge Replacement w/o Added Capacity | Locally | Richmond | ASHLAND | Richmond | Richmond:Richmond | Local Assistance Division | Olena Fecek | Olena.Fecek@vdot.virginia.gov | (804) 524-6368 | Olena Fecek | Olena.Fecek@vdot.virginia.gov | (804) 524-6368 | Thomas Westbrook | Thomas.Westbrook@richmondgov.com | (804) 646-3421 | 0 |  | 0 | FY2024 | 2173653 | 1928000 | ACTIVITY DATES SET | R | Determine Requirements milestone finished 39 days late | G | Project is on budget | 2019-09-19 | 2019-07-01 | 2019-12-17 | 2019-11-20 | G | 2019-12-18 | 2019-11-21 | 2019-12-20 | 2019-12-18 | G | 2019-12-23 | 2019-12-19 | 2020-06-29 | 2020-08-07 | R | [5 empty] | 2021-04-01 |  | 2021-06-30 |  | G | 2021-09-09 |  | 2021-09-30 |  | G | 2021-10-01 |  | 2022-03-31 |  | G | 2021-10-01 |  | 2022-03-31 |  | G | [10 empty] | 2022-07-29 |  | 2022-07-29 |  | G | 2022-10-19 |  | 2023-07-31 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.12069
690 | 107547 | Rte. 250 Bypass Commuter Trail |  | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Charlottesville | CHARLOTTESVILLE | Culpeper | Charlottesville:Charlottesville | Local Assistance Division | William E Stowe | William.Stowe@vdot.virginia.gov | (540) 827-7287 | Michael D Barnes | MichaelD.Barnes@vdot.virginia.gov | (434) 422-9861 | Chris Gensic | gensic@charlottesville.org | (434) 970-3656 | 0 |  | 0 | FY2019 | 1114949 | 946462 | WAITING FINANCIAL CLOSURE | R | Start Delivery milestone finished 210 days late | G | Project is on budget | 2015-10-01 | 2015-10-01 | 2015-12-30 | 2015-12-30 | G | 2015-12-31 | 2015-12-31 | 2016-01-14 | 2016-01-14 | G | 2016-01-19 | 2016-01-19 | 2018-06-12 | 2018-05-22 | G | [10 empty] | 2018-05-23 | 2018-05-23 | 2018-09-28 | 2018-06-05 | G | [20 empty] | 2018-10-01 | 2019-01-25 | 2018-11-13 | 2019-02-11 | R | 2018-11-14 | 2019-02-12 | 2018-11-14 | 2019-06-12 | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.37757
691 | 108946 | Extend accel. lane (exit 72) to decel lane (exit 73) | 0081 | Interstate | Safety | VDOT | Wythe County | WYTHEVILLE | Bristol | NonMPO:NonMPO | Infrastructure Investment Division | Dennis R Harris | Dennis.Harris@VDOT.Virginia.gov | (276) 696-3289 | Ronald C Flanary | Ronald.Flanary@VDOT.Virginia.gov | (276) 696-3252 |  |  |  | 0 |  | 0 | FY2019 | 1990000 | 1990000 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished on-time | G | Project is on budget | [5 empty] | 2016-09-06 | 2016-08-10 | 2016-09-19 | 2016-08-10 | G | 2016-09-20 | 2016-09-20 | 2017-05-16 | 2017-06-30 | R | [5 empty] | 2017-10-10 | 2017-09-25 | 2017-11-22 | 2017-10-02 | G | [5 empty] | 2018-04-05 | 2018-04-05 | 2018-07-27 | 2018-07-27 | G | [5 empty] | 2018-03-21 | 2018-03-05 | 2018-06-20 | 2018-03-05 | G | [5 empty] | 2018-08-14 | 2018-08-14 | 2018-08-14 | 2018-08-14 | G | 2018-10-04 | 2018-10-25 | 2018-10-25 | 2018-10-25 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.078889
692 | 109554 | #HB2.FY17 ODDFELLOWS ROAD SEGMENT B2 - RECONSTRUCTION | 9999 | Urban | Reconstruction w/ Added Capacity | VDOT | Lynchburg | APPOMATTOX | Lynchburg | Lynchburg:Lynchburg | Infrastructure Investment Division | Brian J Casto | Brian.Casto@VDOT.Virginia.gov | (434) 856-8276 | Lindsey S Hodges | Lindsey.Hodges@vdot.virginia.gov | (434) 856-8143 |  |  |  | 1 | 2017 | 0 | FY2018 | 17702165 | 17702165 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 37 days early | G | Project is on budget | [5 empty] | 2016-09-22 | 2016-09-22 | 2016-09-23 | 2016-09-23 | G | 2016-09-30 | 2016-09-30 | 2016-09-30 | 2016-09-30 | G | [10 empty] | 2016-12-28 | 2016-12-28 | 2017-02-01 | 2017-02-01 | G | 2017-10-03 | 2017-10-03 | 2018-06-29 | 2018-08-22 | R | 2017-03-02 | 2017-03-02 | 2017-10-10 | 2017-10-02 | G | [10 empty] | 2017-11-14 | 2017-11-07 | 2017-11-14 | 2017-11-07 | G | 2018-02-02 | 2018-02-21 | 2018-03-30 | 2018-02-21 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 1 | 0.20492
693 | 110477 | SCOTTS RUN TRAIL | 0123 | Urban | Other | Locally | Fairfax County | FAIRFAX | Northern Virginia | Northern Virginia:Fairfax County | Infrastructure Investment Division | Amir Salahshoor | A.Salahshoor@VDOT.Virginia.gov | (703) 259-1957 | Rita Hockman | Rita.Hockman@vdot.virginia.gov | (804) 824-7421 | John Dresser | John.Dresser@fairfaxcounty.gov | (703) 324-8629 | 0 |  | 0 | FY2019 | 2857229 | 4277929 | CONSTRUCTION STARTED | R | Start Delivery milestone finished 293 days late | R | Project estimate is less than $5M and is 20% or more over budget | 2015-11-19 | 2015-11-09 | 2016-02-19 | 2016-02-19 | G | 2016-02-22 | 2016-02-22 | 2016-02-24 | 2016-02-24 | G | 2016-02-25 | 2016-02-25 | 2016-08-26 | 2016-08-26 | G | [10 empty] | 2017-06-23 | 2017-06-23 | 2017-07-14 | 2018-04-13 | R | [5 empty] | 2017-07-18 | 2018-02-12 | 2018-04-30 | 2018-08-15 | R | [10 empty] | 2018-05-16 | 2018-11-26 | 2018-06-13 | 2019-01-31 | R | 2018-06-14 | 2019-02-01 | 2018-07-25 | 2019-05-14 | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.25235
694 | 110838 | PEDESTRIAN SAFETY ENHANCEMENTS ALONG THE CAPITAL TRAIL | 0005 | Primary | Safety | VDOT | Henrico County | ASHLAND | Richmond | Richmond:Henrico County | Infrastructure Investment Division | Adam S Brooks | Adam.Brooks@VDOT.Virginia.gov | (804) 609-5274 | Adam S Brooks | Adam.Brooks@VDOT.Virginia.gov | (804) 609-5274 |  |  |  | 0 |  | 0 | FY2020 | 576000 | 576000 | AWARDED | G | Start Delivery milestone finished 113 days early | G | Project is on budget | [5 empty] | 2017-08-16 | 2017-08-16 | 2017-08-22 | 2017-08-22 | G | 2017-08-23 | 2017-08-23 | 2018-04-19 | 2018-04-12 | G | [5 empty] | 2018-11-09 | 2018-05-07 | 2018-12-26 | 2018-05-07 | G | [5 empty] | 2019-02-01 | 2018-04-09 | 2019-02-01 | 2018-04-09 | G | [5 empty] | 2019-03-29 | 2018-11-30 | 2019-06-27 | 2018-11-30 | G | [5 empty] | 2019-10-08 | 2019-08-13 | 2019-10-08 | 2019-08-13 | G | 2020-02-04 | 2019-11-04 | 2020-02-25 | 2019-11-04 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.0714
695 | 111367 | #SMART18 - Mason Creek Greenway Ph3 - 419 Multimodal Imprv | 0419 | Primary | Facilities for Pedestrians and Bicycles | Locally | Salem | SALEM | Salem | Roanoke:Salem | Infrastructure Investment Division | Alex H Price | Alex.Price@VDOT.Virginia.gov | (540) 378-5053 | Cheryl B Becker | Cheryl.Becker@vdot.virginia.gov | (540) 492-2531 | Ben Tripp | btripp@salemva.gov | (540) 375-3032 | 1 | 2018 | 0 | FY2025 | 2610310 | 2610310 | NO DATES SET YET | G | Agreement with Locality milestone is 228 days ahead of the expected completion date | G | Project is on budget | 2021-07-15 |  | 2021-10-07 |  | G | 2021-10-08 |  | 2021-10-12 |  | G | 2021-10-13 |  | 2022-04-25 |  | G | 2023-05-12 |  | 2023-06-23 |  | G | [5 empty] | 2023-06-26 |  | 2023-07-14 |  | G | [5 empty] | 2023-07-18 |  | 2024-02-01 |  | G | [10 empty] | 2024-03-04 |  | 2024-03-29 |  | G | 2024-04-01 |  | 2024-07-16 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.31772
696 | 111804 | DOWNTOWN FREDERICKSBURG PEDESTRIAN IMPROVEMENTS |  | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Fredericksburg | FREDERICKSBURG | Fredericksburg | Fredericksburg:Fredericksburg | Local Assistance Division | Anastasia Kapitan | Anastasia.Kapitan@vdot.virginia.gov | (540) 899-4292 | Anastasia Kapitan | Anastasia.Kapitan@vdot.virginia.gov | (540) 899-4292 | Erik Nelson | ENELSON@FREDERICKSBURGVA.GOV | (540) 372-1080 | 0 |  | 0 | FY2021 | 2550000 | 2550000 | ACTIVITY DATES SET | R | Solicit Bids milestone is 298 days past the expected completion date | G | Project is on budget | 2017-09-29 | 2017-09-29 | 2017-09-29 | 2017-09-29 | G | 2017-11-05 | 2017-11-05 | 2017-11-15 | 2017-11-15 | G | 2017-11-16 | 2017-11-16 | 2019-03-12 | 2019-03-12 | G | [35 empty] | 2020-02-05 |  | 2020-04-29 |  | R | 2020-06-12 |  | 2020-09-04 |  | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.37722
697 | 112244 | SHARED USE PATH/PVMT. OVERLAY BONHAM RD./SIDEWALK SUNCREST | 0000 | Urban | Facilities for Pedestrians and Bicycles | Locally | Bristol | ABINGDON | Bristol | Bristol:Bristol | Infrastructure Investment Division | Tabitha H Crowder | Tabitha.Crowder@vdot.virginia.gov | (276) 696-3482 | Kenneth R Plummer | KR.Plummer@VDOT.Virginia.gov | (276) 696-3261 | Wallace McCulloch | wallace.mcculloch@bristolva.org | (276) 642-2316 | 0 |  | 0 | FY2020 | 666773 | 666157 | ACTIVITY DATES SET | R | Solicit Bids milestone is 410 days past the expected completion date | G | Project is on budget | 2017-10-02 | 2017-10-02 | 2017-12-08 | 2017-12-08 | G | 2017-12-09 | 2017-12-09 | 2017-12-15 | 2017-12-15 | G | 2017-12-18 | 2017-12-18 | 2019-01-17 | 2019-01-14 | G | [35 empty] | 2019-12-10 |  | 2020-01-08 |  | R | 2020-01-09 |  | 2020-02-21 |  | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.10329
698 | 112492 | UPGRADE EXISTING SIGNAL BURKE LAKE RD AND SHIPLETT BLVD | 0645 | Secondary | Safety | VDOT | Fairfax County | FAIRFAX | Northern Virginia | Northern Virginia:Fairfax County | Infrastructure Investment Division | Ivan M Horodyskyj | Ivan.Horodyskyj@VDOT.Virginia.gov | (703) 259-2330 | Tienjung Ho | Tien-Jung.Ho@VDOT.Virginia.gov | (703) 259-2752 |  |  |  | 0 |  | 0 | FY2023 | 590000 | 590000 | ACTIVITY DATES SET | G | Engage Public milestone finished 294 days early | G | Project is on budget | [5 empty] | 2019-02-01 | 2019-01-14 | 2019-02-14 | 2019-01-17 | G | 2019-02-15 | 2019-01-22 | 2020-01-13 | 2020-01-10 | G | [5 empty] | 2020-11-12 | 2020-02-03 | 2020-11-25 | 2020-02-05 | G | 2022-01-21 |  | 2022-02-03 |  | G | 2019-10-18 | 2019-10-18 | 2019-10-18 | 2019-10-18 | G | 2022-02-22 |  | 2022-08-24 |  | G | [10 empty] | 2022-11-08 |  | 2022-11-08 |  | G | 2023-01-04 |  | 2023-01-26 |  | G | Preliminary design and/or investigations are still underway | 2021-02-21 11:00 | 2021-02-21 06:04 | WORK/TASK ORDER | 0 | 0 | 0.082464
699 | 112961 | New Traffic Signal at Adams/Legge - Winchester | 0000 | Urban | Traffic Management/Engineering | Locally | Winchester | EDINBURG | Staunton | Winchester:Winchester | Local Assistance Division | Kimberly Cameron | Kim.Cameron@vdot.virginia.gov | (540) 332-7886 | Kimberly Cameron | Kim.Cameron@vdot.virginia.gov | (540) 332-7886 | Perry Eisenach | peisenach@ci.winchester.va.us | (540) 667-1815 | 0 |  | 0 | FY2021 | 300000 | 300000 | AWARDED | G | Start Delivery milestone finished 1 days early | G | Project is on budget | 2018-10-31 | 2018-10-31 | 2019-01-31 | 2019-03-14 | R | 2019-02-01 | 2019-03-15 | 2019-02-05 | 2019-03-29 | R | 2019-02-06 | 2019-04-01 | 2019-08-09 | 2019-08-09 | G | [25 empty] | 2019-11-08 | 2020-07-15 | 2020-07-16 | 2020-07-15 | G | [5 empty] | 2020-07-31 | 2020-07-16 | 2020-08-27 | 2020-08-27 | G | 2020-11-18 | 2020-08-28 | 2020-11-18 | 2020-11-17 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.16431
700 | 113216 | 12TH STREET DRAINAGE AND ROAD IMPROVEMENTS | 9999 | Urban | Facilities for Pedestrians and Bicycles | Locally | Purcellville | LEESBURG | Northern Virginia | Northern Virginia:Purcellville | Local Assistance Division | Kimberly Mccool | Kimberly.McCool@vdot.virginia.gov | (703) 259-3220 | Christer P Carshult | Christer.Carshult@vdot.virginia.gov | (703) 259-1765 | Dale Lehnig | dlehnig@purcellvilleva.gov |  | 0 |  | 0 | FY2020 | 2411731 | 2411731 | NO DATES SET YET-PE OPEN | R | Solicit Bids milestone is 695 days past the expected completion date | G | Project is on budget | 2018-10-31 | 2018-07-01 | 2019-03-29 | 2018-08-13 | G | 2018-08-14 | 2018-08-14 | 2018-09-14 | 2018-09-14 | G | 2018-10-31 |  | 2019-05-31 |  | R | [20 empty] | 2018-10-31 |  | 2019-08-30 |  | R | 2019-07-01 |  | 2020-03-30 |  | R | [5 empty] | 2018-12-03 |  | 2019-03-29 |  | R | 2019-06-18 |  | 2019-10-30 |  | R | Preliminary design and/or investigations are still underway | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.34268
701 | 113432 | 19 JEFF DAVIS HWY (N) - RESURFACING | 0001 | Primary | Resurfacing | Locally | Richmond | ASHLAND | Richmond | Richmond:Richmond | Local Assistance Division | Michael G Campbell | disabled-Michael.Campbell@vdot.virginia.gov | (804) 998-3960 | Brian J Lokker | Brian.Lokker@VDOT.Virginia.gov | (804) 524-6010 | Kenny Horak | kenny.horak@richmondgov.com | (804) 646-4781 | 0 |  | 1 | FY2020 | 356000 | 355955 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 111 days early | G | Project is on budget | 2019-02-01 | 2018-12-19 | 2019-04-26 | 2019-01-29 | G | [5 empty] | 2019-02-01 | 2019-01-30 | 2019-02-14 | 2019-02-12 | G | [25 empty] | 2019-02-13 | 2019-02-13 | 2019-05-10 | 2019-02-13 | G | [5 empty] | 2019-05-14 | 2019-04-17 | 2019-06-11 | 2019-04-17 | G | 2019-08-29 | 2019-05-10 | 2019-08-29 | 2019-05-10 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.10425
702 | 113566 | Elizabeth Greenway | 0000 | Urban | Facilities for Pedestrians and Bicycles | Locally | Salem | SALEM | Salem | Roanoke:Salem | Infrastructure Investment Division | Cheryl B Becker | Cheryl.Becker@vdot.virginia.gov | (540) 492-2531 | Cheryl B Becker | Cheryl.Becker@vdot.virginia.gov | (540) 492-2531 | WIll Simpson | wsimpson@salemva.gov | (540) 375-3032 | 0 |  | 0 | FY2023 | 1104400 | 1104400 | NO DATES SET YET-PE OPEN | R | Determine Requirements milestone is 202 days past the expected completion date | G | Project is on budget | 2019-10-01 | 2019-10-03 | 2019-12-30 | 2019-12-11 | G | 2019-12-31 | 2019-12-12 | 2020-01-03 | 2019-12-27 | G | 2020-01-06 |  | 2020-08-03 |  | R | [10 empty] | 2021-08-05 |  | 2021-08-25 |  | G | [5 empty] | 2021-08-27 |  | 2022-06-10 |  | G | 2021-10-04 |  | 2022-06-10 |  | G | [5 empty] | 2022-06-28 |  | 2022-07-26 |  | G | 2022-12-21 |  | 2022-12-21 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.34185
703 | 113762 | North Main Street Primary Extension Paving | 0011 | Urban | Resurfacing | Locally | Marion | ABINGDON | Bristol | NonMPO:NonMPO | Local Assistance Division | Tabitha H Crowder | Tabitha.Crowder@vdot.virginia.gov | (276) 696-3482 | Tabitha H Crowder | Tabitha.Crowder@vdot.virginia.gov | (276) 696-3482 | Bill Rush | brush@marionva.org | (276) 783-4113 | 0 |  | 0 | FY2019 | 276013 | 276013 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished on-time | G | Project is on budget | 2019-06-17 | 2018-08-10 | 2019-09-10 | 2018-09-10 | G | [5 empty] | 2019-06-17 | 2018-09-11 | 2019-06-28 | 2018-10-31 | G | [35 empty] | 2018-12-03 | 2018-12-03 | 2018-12-31 | 2018-12-31 | G | 2019-04-15 | 2019-04-15 | 2019-04-15 | 2019-04-15 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.047005
704 | 113861 | WASHINGTON PARK/MADISON AVENUE BICYCLE CONNECTOR TRAIL | 0000 | Urban | Facilities for Pedestrians and Bicycles | Locally | Charlottesville | CHARLOTTESVILLE | Culpeper | Charlottesville:Charlottesville | Infrastructure Investment Division | Ken Connors |  |  | Michael D Barnes | MichaelD.Barnes@vdot.virginia.gov | (434) 422-9861 | Chris Gensic | gensic@charlottesville.org | (434) 970-3656 | 0 |  | 0 | FY2022 | 88350 | 188350 | ACTIVITY DATES SET | G | Determine Requirements milestone finished on-time | R | Project estimate is less than $5M and is 20% or more over budget | 2019-10-01 | 2019-10-10 | 2019-12-30 | 2019-11-19 | G | 2019-12-31 | 2019-11-19 | 2020-01-03 | 2019-11-20 | G | 2020-01-06 | 2019-11-21 | 2020-07-10 | 2020-07-10 | G | [25 empty] | 2020-07-08 | 2020-07-08 | 2021-03-16 | 2020-07-08 | G | [5 empty] | 2021-07-29 |  | 2021-08-25 |  | G | 2021-11-16 |  | 2021-11-16 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.16289
705 | 114713 | US ROUTE 15/29 IMPROVEMENTS AT VINT HILL | 0029 | Primary | Safety | VDOT | Fauquier County | WARRENTON | Culpeper | NonMPO:NonMPO | Infrastructure Investment Division | Gregory J Cooley | Gregory.Cooley@vdot.virginia.gov | (434) 906-7979 | William E Stowe | William.Stowe@vdot.virginia.gov | (540) 827-7287 |  |  |  | 0 |  | 0 | FY2019 |  |  | CONSTRUCTION COMPLETED | G | Determine Requirements milestone finished 270 days early | R | Critical information missing | [5 empty] | 2019-02-04 | 2019-01-14 | 2019-02-15 | 2019-01-31 | G | 2019-02-19 | 2018-11-06 | 2020-01-14 | 2019-04-19 | G | [10 empty] | 2019-01-30 | 2019-01-30 | 2019-01-31 | 2019-01-31 | G | [20 empty] | 2019-01-31 | 2019-01-31 | 2019-02-04 | 2019-02-04 | G | 2019-04-10 | 2019-04-10 | 2019-04-10 | 2019-04-10 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | DESIGN BUILD/PPTA | 1 | 0 | 0.080728
706 | 115299 | PRIMARY EXTENSION PAVING FY20 - HILLWOOD AVE - 265 | 0338 | Urban | Resurfacing | Locally | Falls Church | FAIRFAX | Northern Virginia | Northern Virginia:Falls Church | Local Assistance Division | Andrew G Beacher | Andrew.Beacher@vdot.virginia.gov | (703) 259-2239 | Rita Hockman | Rita.Hockman@vdot.virginia.gov | (804) 824-7421 | Tara Puzin | tpuzin@fallschurchva.gov | (703) 405-0175 | 0 |  | 0 | FY2019 | 16682 | 16682 | WAITING FINANCIAL CLOSURE | R | Start Delivery milestone finished 159 days late | G | Project is on budget | 2019-07-01 | 2019-07-01 | 2019-09-30 | 2019-07-01 | G | [5 empty] | 2019-10-01 | 2019-10-07 | 2019-10-31 | 2019-10-07 | G | [35 empty] | 2019-05-14 | 2019-10-21 | 2019-05-14 | 2019-10-21 | R | 2019-05-15 | 2019-10-21 | 2019-05-15 | 2019-10-21 | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.36071
707 | 115803 | #I81CIP NB EXIT 304 EXTEND DECELERATION LANE (ID #49) | 0081 | Interstate | Reconstruction w/o Added Capacity | VDOT | Frederick County | EDINBURG | Staunton | NonMPO:NonMPO | Infrastructure Investment Division | John-Allen L Ennis | JohnAllen.Ennis@VDOT.Virginia.gov | (540) 332-9118 | Timothy Gregory | Tim.Gregory@vdot.virginia.gov | (540) 332-7891 |  |  |  | 0 |  | 0 | FY2022 | 2605000 | 1765655 | ADVERTISED | G | Solicit Bids milestone finished 308 days early | G | Project is on budget | [5 empty] | 2019-09-06 | 2019-09-06 | 2019-09-19 | 2019-09-10 | G | 2019-09-20 | 2019-09-11 | 2020-05-15 | 2020-05-15 | G | [5 empty] | 2020-06-01 | 2020-05-15 | 2020-07-27 | 2020-07-27 | G | [5 empty] | 2020-10-26 | 2020-08-06 | 2020-10-26 | 2020-09-06 | G | [5 empty] | 2020-12-24 | 2020-09-09 | 2021-04-12 | 2020-09-30 | G | [5 empty] | 2021-10-12 | 2020-12-08 | 2021-10-12 | 2020-12-08 | G | 2022-01-07 |  | 2022-02-22 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.064168
708 | 116411 | NOVA SYSTEMIC ENHANCED CURVE SIGNING AND MARKING | 9999 | Miscellaneous | Safety | VDOT | Northern Virginia District-wide |  | Northern Virginia | Northern Virginia:Northern Virginia District-wide | Infrastructure Investment/Asset Management Division | Michael J Oldham | Michael.Oldham@vdot.virginia.gov | (703) 259-1735 | Nikolaos Dais | Nick.Dais@vdot.virginia.gov | (703) 259-2237 |  |  |  | 0 |  | 0 | FY2023 | 1467079 | 1467079 | ACTIVITY DATES SET | G | Determine Requirements milestone finished on-time | G | Project is on budget | [5 empty] | 2020-02-03 | 2019-12-02 | 2020-02-14 | 2019-12-09 | G | 2020-02-18 | 2019-12-09 | 2020-09-02 | 2020-09-02 | G | [5 empty] | 2022-05-25 |  | 2022-06-08 |  | G | [25 empty] | 2022-06-24 |  | 2022-06-30 |  | G | 2022-07-01 |  | 2022-07-08 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | WORK/TASK ORDER | 0 | 0 | 0.06586
709 | 116946 | LEE HWY SHARED-USE PATH - PHASE I |  | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Bristol | ABINGDON | Bristol | Bristol:Bristol | Local Assistance Division | John W Bechtold | John.Bechtold@vdot.virginia.gov | (276) 696-3365 | Kenneth R Plummer | KR.Plummer@VDOT.Virginia.gov | (276) 696-3261 | JOSEPH DAFT | joseph.daft@bristolva.org | (276) 645-7427 | 0 |  | 0 | FY2024 | 253470 | 253470 | NO DATES SET YET | G | Agreement with Locality milestone is 107 days ahead of the expected completion date | G | Project is on budget | 2021-02-01 |  | 2021-06-08 |  | G | 2021-06-09 |  | 2021-06-29 |  | G | 2021-07-29 |  | 2021-11-22 |  | G | [10 empty] | 2023-03-20 |  | 2023-04-21 |  | G | [5 empty] | 2023-04-24 |  | 2023-09-20 |  | G | 2023-08-17 |  | 2024-01-23 |  | G | [5 empty] | 2023-12-28 |  | 2024-01-29 |  | G | 2024-04-17 |  | 2024-04-17 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.22753
710 | 113128 | FY19 RS - Roadway Hazard mitigation - Guardrail Installation | 0000 | Urban | Safety | Locally | Blacksburg | CHRISTIANSBURG | Salem | New River Valley:Blacksburg | Local Assistance Division | Adam J Czesnowski | Adam.Czesnowski@vdot.virginia.gov | (540) 541-1216 | Adam J Czesnowski | Adam.Czesnowski@vdot.virginia.gov | (540) 541-1216 | Randy Formica | rformica@blacksburg.gov | (540) 961-1121 | 0 |  | 0 | FY2020 | 60000 | 60000 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 399 days early | G | Project is on budget | 2018-08-01 | 2018-08-01 | 2018-10-25 | 2018-08-21 | G | 2018-10-26 | 2018-08-30 | 2018-10-30 | 2018-08-30 | G | 2018-10-31 | 2018-09-27 | 2019-08-01 | 2018-09-27 | G | [35 empty] | 2019-06-04 | 2018-10-03 | 2019-07-01 | 2018-10-03 | G | 2019-11-25 | 2018-10-04 | 2019-11-25 | 2018-10-22 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.1683
711 | 113323 | RTE 632 (Fairground Road) Extension | 0632 | Secondary | New Construction Roadway | VDOT | Goochland County | ASHLAND | Richmond | Richmond:Goochland County | Local Assistance Division | Anthony S Haverly | Anthony.Haverly@vdot.virginia.gov | (804) 609-5225 | Anthony S Haverly | Anthony.Haverly@vdot.virginia.gov | (804) 609-5225 | Tom Coleman | tcoleman@goochlandva.us | (804) 556-5865 | 0 |  | 0 | FY2024 | 6101343 | 6101343 | NO DATES SET YET-PE OPEN | R | Determine Requirements milestone is 241 days past the expected completion date | G | Project is on budget | [5 empty] | 2019-04-05 | 2018-12-17 | 2019-07-29 | 2018-12-19 | G | 2019-07-30 | 2018-12-12 | 2020-06-25 |  | R | [5 empty] | 2021-05-03 |  | 2021-05-14 |  | G | 2022-08-19 |  | 2022-09-01 |  | G | 2023-02-02 |  | 2023-08-07 |  | G | 2022-09-20 |  | 2023-03-31 |  | G | 2022-02-09 |  | 2022-08-12 |  | G | [5 empty] | 2023-08-08 |  | 2023-08-08 |  | G | 2023-10-30 |  | 2023-10-30 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 1 | 0.21194
712 | 113481 | #SGR19LB??- Sycamore St over Lieutenant Run - Rehab culvert | 0301 | Urban | Bridge Rehab w/o Added Capacity | Locally | Petersburg | PETERSBURG | Richmond | Tri-Cities:Petersburg | Local Assistance Division | James Shepherd | James.Shepherd@vdot.virginia.gov | (804) 609-5305 | James Shepherd | James.Shepherd@vdot.virginia.gov | (804) 609-5305 | Bill Riggleman | bill@petersburg-va.org | (804) 733-2355 | 0 |  | 1 | FY2022 | 616000 | 616000 | ACTIVITY DATES SET | G | Complete Purchasing Right-of-Way milestone finished 246 days early | G | Project is on budget | 2018-08-01 | 2019-02-14 | 2018-10-25 | 2019-09-19 | R | 2018-10-26 | 2019-09-19 | 2018-10-30 | 2019-09-24 | R | 2018-10-31 | 2020-01-28 | 2019-05-10 | 2020-06-05 | R | [10 empty] | 2020-10-09 | 2020-10-09 | 2020-11-20 | 2020-10-09 | G | [5 empty] | 2020-11-24 | 2020-10-12 | 2021-06-15 | 2020-10-12 | G | 2020-10-09 |  | 2021-06-21 |  | G | [5 empty] | 2021-08-31 |  | 2021-09-10 |  | G | 2021-12-03 |  | 2022-03-03 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.1578
713 | 113687 | VERONA PEDESTRIAN IMPROVEMENTS |  | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Augusta County | HARRISONBURG | Staunton | SAW:Augusta County | Local Assistance Division | Donald F Komara | Donald.Komara@VDOT.Virginia.gov | (540) 434-2587 | Jamison Brown | Jamison.Brown@vdot.virginia.gov | (540) 332-7389 | Doug Wolfe | dwolfe@co.augusta.va.us | (540) 245-5700 | 0 |  | 0 | FY2023 | 2092878 | 2092878 | ACTIVITY DATES SET | G | Start Purchasing Right-of-Way milestone finished 56 days early | G | Project is on budget | 2019-02-01 | 2019-02-01 | 2019-04-26 | 2019-04-26 | G | 2019-04-29 | 2019-04-29 | 2019-05-01 | 2019-05-01 | G | 2019-05-02 | 2019-06-19 | 2019-11-05 | 2019-11-05 | G | [10 empty] | 2020-11-04 | 2020-09-15 | 2020-11-25 | 2020-09-30 | G | [5 empty] | 2020-12-01 |  | 2022-11-01 |  | G | 2019-12-27 | 2019-12-27 | 2020-08-28 | 2019-12-27 | G | [5 empty] | 2022-11-18 |  | 2022-12-19 |  | G | 2023-03-14 |  | 2023-03-27 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.3666
714 | 113779 | RTE. 760 - RURAL RUSTIC RD (SURFACE TREAT NONHARDSURFACE RD) | 0760 | Secondary | Reconstruction w/o Added Capacity | VDOT | Albemarle County | CHARLOTTESVILLE | Culpeper | NonMPO:NonMPO | Infrastructure Investment Division | Ken Connors |  |  | Harold L Jones | Harold.Jones@VDOT.virginia.gov | (434) 422-9378 |  |  |  | 0 |  | 0 | FY2023 | 375000 | 375000 | NO DATES SET YET | R | Start Development milestone is 130 days past the expected completion date | G | Project is on budget | [5 empty] | 2020-10-01 |  | 2020-10-14 |  | R | 2020-10-15 |  | 2021-06-11 |  | G | [5 empty] | 2022-02-22 |  | 2022-04-04 |  | G | [5 empty] | 2022-07-19 |  | 2022-11-09 |  | G | [5 empty] | 2022-07-01 |  | 2022-10-03 |  | G | [5 empty] | 2022-12-13 |  | 2022-12-13 |  | G | 2023-03-09 |  | 2023-03-09 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | SAAP CONTRACT | 0 | 0 | 0.15647
715 | 113947 | Pedestrian Improvements on Route 11 (Williamson Road) | 0011 | Primary | Safety | VDOT | Roanoke County | SALEM | Salem | Roanoke:Roanoke County | Infrastructure Investment Division | Craig S Moore | Craig.Moore@vdot.virginia.gov | (540) 375-3556 | Mark C Mckissick | Mark.McKissick@VDOT.Virginia.gov | (540) 375-9416 |  |  |  | 0 |  | 0 | FY2025 | 1500000 | 1500000 | NO DATES SET YET | G | Start Development milestone is 509 days ahead of the expected completion date | G | Project is on budget | [5 empty] | 2022-07-01 |  | 2022-07-15 |  | G | 2022-07-18 |  | 2023-03-14 |  | G | [5 empty] | 2023-11-15 |  | 2023-12-29 |  | G | [5 empty] | 2024-04-17 |  | 2024-08-08 |  | G | [5 empty] | 2024-04-02 |  | 2024-07-02 |  | G | [5 empty] | 2024-08-13 |  | 2024-08-13 |  | G | 2024-11-04 |  | 2024-11-04 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.12863
716 | 114947 | RTE 641-RESURFACE NON-HARDSURFACED ROADWAY | 0641 | Secondary | Reconstruction w/o Added Capacity | VDOT | Floyd County | CHRISTIANSBURG | Salem | NonMPO:NonMPO | Infrastructure Investment Division | Christopher L Price | Christopher.Price@VDOT.Virginia.gov | (540) 381-7182 | Christopher L Price | Christopher.Price@VDOT.Virginia.gov | (540) 381-7182 |  |  |  | 0 |  | 0 | FY2023 | 586140 | 586140 | NO DATES SET YET-PE OPEN | R | Determine Requirements milestone is 104 days past the expected completion date | G | Project is on budget | [5 empty] | 2020-03-09 | 2019-09-09 | 2020-03-20 | 2019-09-10 | G | 2020-03-23 |  | 2020-11-09 |  | R | [5 empty] | 2021-07-20 |  | 2021-08-30 |  | G | [5 empty] | 2021-12-17 |  | 2022-04-14 |  | G | [5 empty] | 2021-12-02 |  | 2022-03-09 |  | G | [5 empty] | 2022-05-10 |  | 2022-05-10 |  | G | 2022-08-01 |  | 2022-08-01 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | SAAP CONTRACT | 0 | 0 | 0.10624
717 | 115381 | BUS 29 SBL - (ID 5465) RESURFACING (CENTRAL BLVD) | 0029 | Urban | Resurfacing | Locally | Danville | HALIFAX | Lynchburg | Danville:Danville | Local Assistance Division | Sharon S White | Sharon.White@VDOT.Virginia.gov | (434) 856-8220 | Sharon S White | Sharon.White@VDOT.Virginia.gov | (434) 856-8220 | Brian Dunevant | dunevbl@danvilleva.gov | (434) 799-5019 | 0 |  | 0 | FY2020 | 112000 | 112000 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 114 days early | G | Project is on budget | 2020-01-31 | 2019-07-01 | 2020-04-24 | 2019-09-20 | G | [5 empty] | 2020-01-31 | 2019-09-23 | 2020-02-13 | 2020-02-03 | G | [25 empty] | 2020-02-04 | 2020-02-06 | 2020-02-18 | 2020-02-06 | G | [5 empty] | 2020-02-19 | 2020-02-07 | 2020-03-17 | 2020-02-07 | G | 2020-06-04 | 2020-02-11 | 2020-06-04 | 2020-02-11 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.050029
718 | 116172 | #I81CIP SB MM 34.0 TRUCK CLIMBING LANE (ID #21) | 0081 | Interstate | Reconstruction w/ Added Capacity | VDOT | Washington County | ABINGDON | Bristol | NonMPO:NonMPO | Infrastructure Investment Division | Donald A Necessary | Donald.Necessary@VDOT.Virginia.gov | (276) 696-3285 | James R Jones | jamesr.jones@vdot.virginia.gov | (276) 696-3257 |  |  |  | 0 |  | 0 | FY2024 | 17821625 | 16938630 | ACTIVITY DATES SET | G | Determine Requirements milestone finished 362 days early | G | Project is on budget | [5 empty] | 2020-07-01 | 2020-01-03 | 2020-07-15 | 2020-01-16 | G | 2020-07-16 | 2020-01-21 | 2021-08-24 | 2020-08-27 | G | [5 empty] | 2021-05-11 |  | 2021-05-24 |  | G | 2022-05-11 |  | 2022-05-24 |  | G | 2022-10-19 |  | 2023-04-28 |  | G | 2022-06-10 |  | 2023-02-02 |  | G | [10 empty] | 2023-06-13 |  | 2023-06-13 |  | G | 2023-10-02 |  | 2023-10-02 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.093087
719 | 116696 | Jefferson Street - Downtown Drainage Improvements | 0000 | Urban | Mitigation of Water Pollution Due to Highway Runof | Locally | Roanoke | SALEM | Salem | Roanoke:Roanoke City | Local Assistance Division | Cheryl B Becker | Cheryl.Becker@vdot.virginia.gov | (540) 492-2531 | Cheryl B Becker | Cheryl.Becker@vdot.virginia.gov | (540) 492-2531 | Joseph Arthur | Joseph.Arthur@roanokeva.gov | (540) 853-5906 | 0 |  | 0 | FY2022 | 1200000 | 1200000 | NO DATES SET YET-PE OPEN | Y | Determine Requirements milestone is 24 days ahead of the expected completion date and there is a risk of missing this milestone date | G | Project is on budget | 2020-06-05 | 2020-06-05 | 2020-08-28 | 2020-06-18 | G | 2020-08-31 | 2020-06-19 | 2020-09-02 | 2020-06-19 | G | 2020-09-03 |  | 2021-03-17 |  | Y | [25 empty] | 2021-04-22 |  | 2021-12-27 |  | G | [5 empty] | 2022-01-27 |  | 2022-02-24 |  | G | 2022-05-13 |  | 2022-05-13 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.20743
720 | 117029 | RURAL ADDITION - PAVE UNPAVED ANCHOR COURT | 9999 | Secondary | Resurfacing | VDOT | Westmoreland County | NORTHERN NECK | Fredericksburg | NonMPO:NonMPO | Local Assistance Division | David L Beale | David.Beale@vdot.virginia.gov | (804) 333-7941 | William C White | Carter.White@VDOT.Virginia.gov | (804) 333-7942 |  |  |  | 0 |  | 0 | FY2029 | 40000 | 40000 | NO DATES SET YET | G | Start Development milestone is 1704 days ahead of the expected completion date | G | Project is on budget | [5 empty] | 2025-10-01 |  | 2025-10-22 |  | G | 2025-10-23 |  | 2026-08-26 |  | G | [5 empty] | 2027-04-01 |  | 2027-04-28 |  | G | [5 empty] | 2027-12-21 |  | 2028-04-24 |  | G | [5 empty] | 2027-09-09 |  | 2028-02-14 |  | G | [5 empty] | 2028-05-09 |  | 2028-05-09 |  | G | 2028-07-28 |  | 2028-07-28 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | SAAP CONTRACT | 0 | 0 | 0.089442
721 | 101288 | LAKEVIEW AVE - MINOR WIDENING | 9030 | Urban | Reconstruction w/o Added Capacity | Locally | Colonial Heights | CHESTERFIELD | Richmond | Tri-Cities:Colonial Heights | Infrastructure Investment Division | Evan Austin | Evan.Austin@vdot.virginia.gov | (804) 609-5384 | Evan Austin | Evan.Austin@vdot.virginia.gov | (804) 609-5384 | Keith A Chisolm | chisolmk@colonialheightsva.gov | (804) 520-9215 | 0 |  | 0 | FY2019 | 3314000 | 5248398 | ADVERTISED | R | Start Delivery milestone is 751 days past the expected completion date | R | Project estimate is less than $5M and is 20% or more over budget | [5 empty] | 2011-08-01 | 2011-09-09 | 2011-08-01 | 2011-09-09 | R | 2013-04-01 | 2012-04-16 | 2013-07-31 | 2013-05-02 | G | [10 empty] | 2014-07-11 | 2014-07-11 | 2014-12-16 | 2014-12-16 | G | [20 empty] | 2016-09-30 | 2020-09-18 | 2017-05-01 | 2020-10-23 | R | 2018-11-01 |  | 2019-02-01 |  | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.20393
722 | 104828 | #SGR21VB BR-Tayor Valley Rd over Laurel Creek Fed ID 19162 | 0725 | Secondary | Bridge Replacement w/o Added Capacity | VDOT | Washington County | ABINGDON | Bristol | NonMPO:NonMPO | Infrastructure Investment Division | Gary Lester |  |  | Ronald C Flanary | Ronald.Flanary@VDOT.Virginia.gov | (276) 696-3252 |  |  |  | 0 |  | 0 | FY2021 | 1767547 | 3294382 | ADVERTISED | R | Start Delivery milestone is 10 days past the expected completion date | R | Project estimate is less than $5M and is 20% or more over budget | [5 empty] | 2016-07-05 | 2016-07-05 | 2016-07-05 | 2016-07-05 | G | 2016-08-04 | 2016-08-04 | 2017-10-20 | 2017-10-20 | G | [5 empty] | 2018-08-29 | 2018-08-29 | 2018-10-26 | 2018-10-26 | G | 2019-05-08 | 2019-06-06 | 2019-05-22 | 2019-06-26 | R | 2020-05-08 | 2020-05-21 | 2020-09-01 | 2020-07-08 | G | 2019-04-23 | 2019-07-18 | 2020-05-07 | 2020-04-16 | G | 2019-01-30 | 2019-01-30 | 2020-01-14 | 2019-09-09 | G | [5 empty] | 2020-11-10 | 2021-01-12 | 2020-11-10 | 2021-01-12 | R | 2021-01-21 |  | 2021-02-11 |  | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.065004
723 | 105748 | FY15 RS - Construction of Pedestrian Bridge | 0040 | Primary | Facilities for Pedestrians and Bicycles | Locally | Franklin County | BEDFORD | Salem | NonMPO:NonMPO | Local Assistance Division | Anthony W Ford | Anthony.Ford@VDOT.Virginia.gov | (540) 378-5040 | Cheryl B Becker | Cheryl.Becker@vdot.virginia.gov | (540) 492-2531 | Lisa Cooper | lisa.cooper@franklincountyva.gov | (540) 483-6642 | 0 |  | 0 | FY2019 | 1416220 | 1893342 | CONSTRUCTION STARTED | R | Start Delivery milestone finished 52 days late | R | Project estimate is less than $5M and is 20% or more over budget | [5 empty] | 2014-08-01 | 2015-03-04 | 2014-08-01 | 2015-03-04 | R | 2014-09-02 | 2016-02-01 | 2014-12-31 | 2016-12-14 | R | [35 empty] | 2018-08-01 | 2018-10-22 | 2018-09-28 | 2018-11-11 | R | 2018-10-01 | 2018-11-13 | 2018-12-31 | 2019-02-21 | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.37148
724 | 106150 | Nat Turner Trail and Trailhead |  | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Southampton County | FRANKLIN | Hampton Roads | NonMPO:NonMPO | Local Assistance Division | Charles T Catlett | Tommy.Catlett@vdot.virginia.gov | (757) 346-3078 | Joshua D Negovan | Joshua.Negovan@vdot.virginia.gov | (757) 956-3347 | John V. Quarstein, Project Consultant | jvquarstein@aol.com | (757) 879-3420 | 0 |  | 0 | FY2021 | 275000 | 636567 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 46 days early | R | Project estimate is less than $5M and is 20% or more over budget | [10 empty] | 2013-06-28 | 2013-06-28 | 2013-06-28 | 2013-06-28 | G | [10 empty] | 2015-10-01 | 2015-10-01 | 2015-10-01 | 2015-10-01 | G | [20 empty] | 2019-01-15 | 2019-11-01 | 2019-04-15 | 2020-06-21 | R | 2020-10-16 | 2020-09-03 | 2020-12-01 | 2020-10-16 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.40353
725 | 107351 | Bruce Road Improvement Project |  | Urban | Reconstruction w/o Added Capacity | Locally | Chesapeake | NORFOLK | Hampton Roads | Hampton Roads:Chesapeake | Local Assistance Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Johndel A Alcaide | John.Alcaide@vdot.virginia.gov | (757) 956-3098 | Scott Frechem, P.E. | sfrechem@cityofchesapeake.net | (757) 382-6319 | 0 |  | 0 | FY2019 | 1285000 | 1519812 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 74 days early | Y | Project estimate is less than $5M and is up to 20% over budget | 2015-04-08 | 2015-08-25 | 2015-07-01 | 2015-09-29 | R | 2015-07-02 | 2015-09-29 | 2015-07-16 | 2015-09-29 | R | 2015-07-17 | 2016-04-19 | 2016-03-16 | 2016-04-20 | R | [10 empty] | 2017-02-03 | 2017-02-16 | 2017-02-16 | 2017-02-16 | G | [20 empty] | 2017-03-23 | 2018-07-06 | 2017-07-14 | 2018-08-01 | R | 2018-10-02 | 2018-08-02 | 2018-12-31 | 2018-10-18 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.11664
726 | 108641 | RTE 654 (Bailey Br Rd, Spring Rn-Sunday Sil) - SPOT WIDENING | 0654 | Secondary | Reconstruction w/o Added Capacity | Locally | Chesterfield County | CHESTERFIELD | Richmond | Richmond:Chesterfield County | Local Assistance Division | Brian J Lokker | Brian.Lokker@VDOT.Virginia.gov | (804) 524-6010 | Brian J Lokker | Brian.Lokker@VDOT.Virginia.gov | (804) 524-6010 | Nate Mathis | mathisn@chesterfield.gov | (804) 748-1037 | 0 |  | 0 | FY2020 | 3816205 | 3820207 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 17 days early | Y | Project estimate is less than $5M and is up to 20% over budget | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | G | 2016-12-08 | 2016-12-08 | 2016-12-08 | 2016-12-08 | G | 2017-05-01 | 2017-05-01 | 2017-09-15 | 2017-09-15 | G | [10 empty] | 2018-08-29 | 2018-05-16 | 2018-09-19 | 2018-05-25 | G | [5 empty] | 2018-09-21 | 2018-05-31 | 2019-07-05 | 2018-09-11 | G | [10 empty] | 2019-07-23 | 2019-02-27 | 2019-08-19 | 2019-02-27 | G | 2019-08-20 | 2019-09-20 | 2019-12-02 | 2019-11-15 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.32229
727 | 108720 | #HB2.FY17 WIDEN RT 28 FROM 4 TO 6 LANES DIVIDED | 0028 | Primary | Reconstruction w/ Added Capacity | Locally | Fairfax County | FAIRFAX | Northern Virginia | Northern Virginia:Fairfax County | Infrastructure Investment Division | Terry Yates | Terry.Yates@vdot.virginia.gov | (703) 259-2118 | Rhoderick M Undan | Rhoderick.Undan@vdot.virginia.gov | (703) 259-3347 | W. Todd Minnix, PE | wesley.minnix@fairfaxcounty.gov | (703) 877-5749 | 1 | 2017 | 0 | FY2020 | 68829273 | 86480000 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 7 days early | R | Project estimate is greater than $10M and is over budget by (a) 10% or more or (b) $5M or more | 2016-01-19 | 2016-09-09 | 2017-06-30 | 2017-03-16 | G | 2017-07-03 | 2016-09-09 | 2017-07-06 | 2016-11-14 | G | 2017-07-07 | 2016-11-14 | 2019-01-02 | 2019-07-09 | R | [10 empty] | 2019-06-03 | 2019-08-23 | 2019-09-10 | 2019-09-09 | G | [20 empty] | 2019-09-11 | 2019-09-23 | 2019-09-30 | 2019-09-23 | G | 2019-10-01 | 2019-09-24 | 2020-05-29 | 2020-05-22 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.28513
728 | 110129 | RTE 659 BAR RIDGE RD RURAL RUSTIC | 0659 | Secondary | Resurfacing | VDOT | Franklin County | BEDFORD | Salem | NonMPO:NonMPO | Infrastructure Investment Division | Todd K Daniel | Todd.Daniel@VDOT.Virginia.gov | (540) 682-7000 | Brian J Casella | Brian.Casella@vdot.virginia.gov | (540) 682-7001 |  |  |  | 0 |  | 0 | FY2029 | 905287 | 905287 | NO DATES SET YET | G | Start Development milestone is 1363 days ahead of the expected completion date | Y | Estimate not current | [5 empty] | 2024-11-04 |  | 2024-11-15 |  | G | 2024-11-18 |  | 2025-09-30 |  | G | [5 empty] | 2026-07-22 |  | 2026-08-04 |  | G | 2027-10-20 |  | 2027-11-02 |  | G | 2028-03-22 |  | 2028-09-19 |  | G | 2027-11-18 |  | 2028-05-17 |  | G | 2027-04-15 |  | 2027-12-08 |  | G | [5 empty] | 2028-09-20 |  | 2028-09-20 |  | G | 2028-11-09 |  | 2028-11-29 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | SAAP CONTRACT | 0 | 0 | 0.12113
729 | 111037 | #SGR18LB - Nansemond Parkway over Beamons Mill Pond | 0337 | Urban | Bridge Replacement w/o Added Capacity | Locally | Suffolk | NORFOLK | Hampton Roads | Hampton Roads:Suffolk | Infrastructure Investment Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Johndel A Alcaide | John.Alcaide@vdot.virginia.gov | (757) 956-3098 | L. Hansen | lhansen@suffolkva.us | (757) 514-7687 | 0 |  | 1 | FY2023 | 1121252 | 3961328 | ACTIVITY DATES SET | R | Determine Requirements milestone finished 220 days late | R | Project estimate is less than $5M and is 20% or more over budget | 2018-05-15 | 2017-07-13 | 2018-08-08 | 2017-10-05 | G | 2018-08-09 | 2017-10-06 | 2018-08-22 | 2019-02-14 | R | 2018-08-23 | 2019-02-15 | 2019-08-09 | 2020-03-16 | R | [10 empty] | 2022-01-07 |  | 2022-01-31 |  | G | [5 empty] | 2022-02-02 |  | 2022-12-13 |  | G | [10 empty] | 2022-12-30 |  | 2023-01-31 |  | G | 2023-02-01 |  | 2023-05-01 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.11491
730 | 118315 | MANSASSAS DRIVE OVER RUSSIA BRANCH | 0213 | Urban | Bridge Replacement w/o Added Capacity | Locally | Manassas Park | MANASSAS | Northern Virginia | Northern Virginia:Manassas Park | Local Assistance Division | Angel Tao | Angel.Tao@vdot.virginia.gov | (703) 259-2377 | Marlene Pinedo Fortich | Sofia.Pinedo@vdot.virginia.gov | (703) 259-1724 | Allan Rowley | a.rowley@manassasparkva.gov |  | 0 |  | 0 | FY2028 | 3134180 | 3134180 | NO DATES SET YET | G | Agreement with Locality milestone is 1458 days ahead of the expected completion date | G | Project is on budget | 2024-07-24 |  | 2025-02-18 |  | G | 2025-02-19 |  | 2025-03-11 |  | G | 2025-09-15 |  | 2026-04-09 |  | G | [25 empty] | 2027-05-04 |  | 2027-09-30 |  | G | [5 empty] | 2027-11-01 |  | 2027-12-30 |  | G | 2028-03-23 |  | 2028-05-17 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.12831
731 | 104599 | RTE 29 SBL & NBL - BR & APPR OVER NSRR FED ID 20579 & 20580 | 0029 | Urban | Bridge Replacement w/o Added Capacity | VDOT | Lynchburg | APPOMATTOX | Lynchburg | Lynchburg:Lynchburg | Infrastructure Investment Division | Laura J Walton | Laura.Walton@VDOT.Virginia.gov | (434) 856-8286 | Lindsey S Hodges | Lindsey.Hodges@vdot.virginia.gov | (434) 856-8143 |  |  |  | 0 |  | 0 | FY2020 | 10111438 | 15983296 | CONSTRUCTION STARTED | G | Start Delivery milestone finished on-time | R | Project estimate is greater than $10M and is over budget by (a) 10% or more or (b) $5M or more | [5 empty] | 2015-08-05 | 2015-08-18 | 2015-08-28 | 2015-08-24 | G | 2015-08-28 | 2015-08-28 | 2017-02-28 | 2017-02-09 | G | [5 empty] | 2017-02-09 | 2017-02-09 | 2017-03-09 | 2017-03-09 | G | 2018-03-01 | 2018-03-01 | 2018-04-27 | 2018-04-27 | G | 2019-03-18 | 2018-12-13 | 2019-12-04 | 2020-03-24 | R | 2018-05-29 | 2018-05-07 | 2019-03-15 | 2018-12-12 | G | 2018-08-06 | 2018-08-06 | 2019-08-06 | 2019-08-05 | G | [5 empty] | 2019-12-11 | 2020-01-13 | 2020-01-14 | 2020-01-13 | G | 2020-05-20 | 2020-05-20 | 2020-05-20 | 2020-05-20 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.1222
732 | 104946 | #HB2.FY17 RTE 501 - PASSING LANE (HALIFAX COUNTY) | 0501 | Primary | Safety | VDOT | Halifax County | HALIFAX | Lynchburg | NonMPO:NonMPO | Infrastructure Investment Division | Daniel J Brown | Daniel.Brown@VDOT.Virginia.gov | (434) 856-8265 | Daniel J Brown | Daniel.Brown@VDOT.Virginia.gov | (434) 856-8265 |  |  |  | 1 | 2017 | 0 | FY2021 | 20122087 | 20122087 | AWARDED | R | Relocate Utilities milestone is 17 days past the expected completion date | G | Project is on budget | [5 empty] | 2013-07-01 | 2013-07-03 | 2013-07-01 | 2013-07-03 | R | 2013-10-16 | 2013-10-16 | 2017-03-31 | 2017-03-16 | G | [5 empty] | 2017-09-14 | 2017-09-14 | 2017-10-04 | 2017-10-04 | G | 2018-11-06 | 2018-10-17 | 2018-11-19 | 2018-10-22 | G | 2020-05-20 | 2020-03-16 | 2021-02-04 |  | R | 2018-12-10 | 2019-01-09 | 2020-05-18 | 2020-06-05 | R | 2019-04-02 | 2019-04-02 | 2020-04-01 | 2020-04-01 | G | [5 empty] | 2020-10-13 | 2020-10-06 | 2020-10-13 | 2020-10-06 | G | 2021-02-23 | 2021-01-19 | 2021-03-19 | 2021-01-19 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.10053
733 | 105775 | FY15 RS - Research Center Drive improvements | 0000 | Urban | Reconstruction w/o Added Capacity | Locally | Blacksburg | CHRISTIANSBURG | Salem | New River Valley:Blacksburg | Local Assistance Division | Anthony W Ford | Anthony.Ford@VDOT.Virginia.gov | (540) 378-5040 | Adam J Czesnowski | Adam.Czesnowski@vdot.virginia.gov | (540) 541-1216 | Adele Schirmer | Aschirmer@blacksburg.gov |  | 0 |  | 0 | FY2019 | 600000 | 516000 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 239 days early | G | Project is on budget | [5 empty] | 2014-08-01 | 2014-07-18 | 2014-08-01 | 2014-07-18 | G | 2014-09-02 | 2014-07-21 | 2014-12-31 | 2017-01-18 | R | [10 empty] | 2017-07-03 | 2017-07-03 | 2017-09-01 | 2017-09-01 | G | [20 empty] | 2018-02-01 | 2018-02-01 | 2018-02-01 | 2018-02-01 | G | 2018-07-02 | 2018-05-09 | 2019-01-03 | 2018-05-09 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.1601
734 | 107297 | Price's Fork Road Turn Lane Construction | 0685 | Secondary | Safety | Locally | Montgomery County | CHRISTIANSBURG | Salem | NonMPO:NonMPO | Local Assistance Division | Adam J Czesnowski | Adam.Czesnowski@vdot.virginia.gov | (540) 541-1216 | Adam J Czesnowski | Adam.Czesnowski@vdot.virginia.gov | (540) 541-1216 | Emily Gibson | Gibsonej@montgomerycountyva.gov | (540) 394-2148 | 0 |  | 0 | FY2019 | 2303331 | 2303331 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 81 days early | G | Project is on budget | 2015-11-02 | 2015-12-08 | 2016-02-02 | 2015-12-08 | G | 2016-02-03 | 2015-12-30 | 2016-02-17 | 2016-01-04 | G | 2016-02-18 | 2016-01-04 | 2016-10-07 | 2016-12-07 | R | [10 empty] | 2017-10-13 | 2017-05-31 | 2017-10-27 | 2017-06-01 | G | [20 empty] | 2017-11-02 | 2018-07-30 | 2018-04-02 | 2018-08-05 | R | 2018-07-19 | 2018-10-12 | 2019-01-25 | 2018-11-05 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.14915
735 | 107459 | #HB2.FY17 RTE 64 - EXTEND ACCELERATION/DECELERATION LANES | 0064 | Interstate | Reconstruction w/ Added Capacity | VDOT | Henrico County | ASHLAND | Richmond | Richmond:Henrico County | Infrastructure Investment Division | Jason C Williams | Jason.Williams@VDOT.Virginia.gov | (804) 609-5337 | Scott J Fisher | Scott.Fisher@VDOT.Virginia.gov | (804) 674-2452 |  |  |  | 1 | 2017 | 0 | FY2018 | 4100000 | 4079786 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 34 days early | G | Project is on budget | [5 empty] | 2015-08-21 | 2015-08-21 | 2015-09-01 | 2015-09-01 | G | 2016-08-02 | 2016-08-02 | 2016-12-05 | 2016-12-05 | G | [35 empty] | 2017-08-01 | 2017-03-17 | 2017-08-01 | 2017-03-17 | G | 2017-08-29 | 2017-07-19 | 2017-08-29 | 2017-07-26 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.099282
736 | 108697 | Reconstruction - Poplar Street | 9999 | Secondary | Reconstruction w/o Added Capacity | Locally | Hopewell | PETERSBURG | Richmond | Tri-Cities:Hopewell | Local Assistance Division | James Shepherd | James.Shepherd@vdot.virginia.gov | (804) 609-5305 | Brian J Lokker | Brian.Lokker@VDOT.Virginia.gov | (804) 524-6010 | Austin Anderson | aanderson@hopewellva.gov | (804) 541-2379 | 0 |  | 0 | FY2019 | 504000 | 504000 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished on-time | G | Project is on budget | 2017-07-12 | 2016-09-12 | 2017-10-04 | 2016-09-13 | G | 2017-10-05 | 2017-06-08 | 2017-10-10 | 2017-06-12 | G | 2017-10-11 | 2017-06-13 | 2018-04-20 | 2018-03-09 | G | [35 empty] | 2018-04-25 | 2018-06-05 | 2018-06-29 | 2018-06-29 | G | 2018-07-02 | 2018-06-29 | 2018-08-20 | 2018-08-20 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.10552
737 | 108730 | Intersection Improvements at Granby St. and Bayview Blvd | 0460 | Urban | Safety | Locally | Norfolk | NORFOLK | Hampton Roads | Hampton Roads:Norfolk | Local Assistance Division | Stephen Rowan | Steve.Rowan@vdot.virginia.gov | (757) 790-9925 | Derrick Williams | Derrick.Williams@vdot.virginia.gov | (757) 956-3097 | Christine Armstrong, P.E. | Christine.armstrong@norfolk.go | (757) 664-7459 | 0 |  | 0 | FY2019 | 500000 | 500000 | WAITING FINANCIAL CLOSURE | G | Solicit Bids milestone finished 28 days early | Y | Estimate not current | 2016-10-04 | 2016-11-10 | 2017-01-03 | 2016-11-17 | G | 2017-01-04 | 2016-12-19 | 2017-01-06 | 2016-12-30 | G | 2017-01-09 | 2017-01-03 | 2017-07-14 | 2017-11-16 | R | [35 empty] | 2018-05-25 | 2018-05-25 | 2018-06-22 | 2018-05-25 | G | 2018-06-25 | 2018-01-02 | 2018-08-03 | 2018-01-02 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.15077
738 | 110888 | Shoulder Widening, Rumble Strip Install.& Guardrail upgrade | 0834 | Secondary | Safety | VDOT | Franklin County | BEDFORD | Salem | NonMPO:NonMPO | Infrastructure Investment Division | Alex H Price | Alex.Price@VDOT.Virginia.gov | (540) 378-5053 | Mark C Mckissick | Mark.McKissick@VDOT.Virginia.gov | (540) 375-9416 |  |  |  | 0 |  | 0 | FY2023 | 3174065 | 3174065 | ADVERTISED | G | Solicit Bids milestone finished 700 days early | G | Project is on budget | [5 empty] | 2018-07-02 | 2018-06-15 | 2018-08-20 | 2018-06-27 | G | 2018-08-21 | 2018-06-28 | 2019-07-19 | 2019-07-19 | G | [5 empty] | 2020-07-31 | 2020-01-10 | 2020-08-13 | 2020-03-09 | G | 2021-11-19 | 2020-02-28 | 2021-12-06 | 2020-02-28 | G | 2022-05-03 | 2019-12-31 | 2022-11-04 | 2019-12-31 | G | 2021-12-22 | 2020-02-28 | 2022-06-29 | 2020-02-28 | G | 2021-05-10 | 2020-02-18 | 2021-11-12 | 2020-02-18 | G | [5 empty] | 2022-11-08 | 2020-12-08 | 2022-11-08 | 2020-12-08 | G | 2023-01-04 |  | 2023-01-26 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.15239
739 | 111038 | #SGR18LB - East Washington Street over Jericho Canal | 0337 | Urban | Bridge Replacement w/o Added Capacity | Locally | Suffolk | NORFOLK | Hampton Roads | Hampton Roads:Suffolk | Infrastructure Investment Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Johndel A Alcaide | John.Alcaide@vdot.virginia.gov | (757) 956-3098 | L. Hansen | lhansen@suffolkva.us | (757) 514-7687 | 0 |  | 1 | FY2022 | 620900 | 620900 | ACTIVITY DATES SET | G | Complete Purchasing Right-of-Way milestone finished 314 days early | G | Project is on budget | 2019-04-05 | 2017-07-13 | 2019-06-28 | 2017-10-05 | G | 2019-07-01 | 2017-10-06 | 2019-07-03 | 2019-01-15 | G | 2019-07-05 | 2019-01-16 | 2020-01-13 | 2020-03-16 | R | [10 empty] | 2021-01-08 | 2021-01-08 | 2021-02-01 | 2021-01-08 | G | [5 empty] | 2021-02-03 | 2021-02-03 | 2021-12-14 | 2021-02-03 | G | 2019-05-28 | 2019-05-28 | 2019-05-29 | 2019-05-29 | G | [5 empty] | 2022-01-03 |  | 2022-02-01 |  | G | 2022-04-21 |  | 2022-05-02 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.10842
740 | 111059 | #SMART18 - (St) I-81 EXIT 296 ACCEL/DECEL LANE EXTENSIONS | 0081 | Interstate | Reconstruction w/o Added Capacity | VDOT | Shenandoah County | EDINBURG | Staunton | NonMPO:NonMPO | Infrastructure Investment Division | Matthew P Dana | Matt.Dana@VDOT.Virginia.gov | (540) 332-7786 | Anthony E Pelina | Anthony.Pelina@vdot.virginia.gov | (540) 332-9575 |  |  |  | 1 | 2018 | 0 | FY2019 | 997481 | 650353 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 31 days early | G | Project is on budget | [5 empty] | 2017-08-03 | 2017-07-17 | 2017-08-16 | 2017-07-26 | G | 2017-08-17 | 2017-07-27 | 2018-06-29 | 2018-05-16 | G | [5 empty] | 2018-06-19 | 2018-06-06 | 2018-06-20 | 2018-06-07 | G | [5 empty] | 2018-07-06 | 2018-04-17 | 2018-07-06 | 2018-04-17 | G | [15 empty] | 2019-01-08 | 2019-01-08 | 2019-01-08 | 2019-01-08 | G | 2019-02-26 | 2019-04-19 | 2019-05-20 | 2019-04-19 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.063187
741 | 112105 | Biotech Park Transportation Imp - Phase III |  | Urban | Landscaping/Beautification | Locally | Richmond | ASHLAND | Richmond | Richmond:Richmond | Infrastructure Investment Division | Olena Fecek | Olena.Fecek@vdot.virginia.gov | (804) 524-6368 | Olena Fecek | Olena.Fecek@vdot.virginia.gov | (804) 524-6368 | Yongping Wang | Yongping.Wang@Richmondgov.com | (804) 646-2467 | 0 |  | 0 | FY2020 | 1228000 | 1228000 | NO DATES SET YET-PE OPEN | R | Determine Requirements milestone is 839 days past the expected completion date | G | Project is on budget | 2018-02-01 | 2018-01-04 | 2018-04-26 | 2018-02-14 | G | 2018-04-27 | 2018-02-16 | 2018-05-01 | 2018-04-02 | G | 2018-05-02 |  | 2018-11-05 |  | R | [35 empty] | 2019-09-17 |  | 2019-10-14 |  | R | 2019-10-15 |  | 2019-11-26 |  | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.19138
742 | 113115 | WILSON STREET - RECONSTRUCTION | 9999 | Urban | Reconstruction w/o Added Capacity | Locally | Danville | HALIFAX | Lynchburg | Danville:Danville | Local Assistance Division | Gregg Allen | Gregg.Allen@vdot.virginia.gov | (434) 426-5575 | Gregg Allen | Gregg.Allen@vdot.virginia.gov | (434) 426-5575 | Brian Dunevant, P.E. | dunevbl@danvilleva.gov | (434) 799-5019 | 0 |  | 0 | FY2023 | 1079112 | 1079112 | NO DATES SET YET-PE OPEN | R | Determine Requirements milestone is 110 days past the expected completion date | G | Project is on budget | 2020-01-31 | 2019-08-01 | 2020-04-24 | 2019-08-23 | G | 2020-04-27 | 2019-08-26 | 2020-04-29 | 2019-08-28 | G | 2020-04-30 | 2019-08-29 | 2020-11-03 |  | R | [10 empty] | 2021-08-30 |  | 2021-09-20 |  | G | [5 empty] | 2021-09-22 |  | 2022-07-06 |  | G | 2020-12-14 | 2019-12-16 | 2021-08-17 | 2019-12-16 | G | [5 empty] | 2022-07-22 |  | 2022-08-18 |  | G | 2022-11-08 |  | 2022-11-08 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.070829
743 | 113746 | Systemic Retroreflective Backplate Improvements | 9999 | Urban | Safety | Locally | Norfolk | NORFOLK | Hampton Roads | Hampton Roads:Norfolk | Infrastructure Investment Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Derrick Williams | Derrick.Williams@vdot.virginia.gov | (757) 956-3097 | Deborah Mangiaracina, P.E. | Deborah.mangiaracina@norfolk.gov | (757) 664-7459 | 0 |  | 0 | FY2022 | 837000 | 837000 | ACTIVITY DATES SET | R | Determine Requirements milestone finished 238 days late | G | Project is on budget | 2019-09-10 | 2019-06-20 | 2019-12-06 | 2020-04-23 | R | 2019-12-09 | 2019-06-21 | 2019-12-11 | 2020-07-08 | R | 2019-12-12 | 2020-07-09 | 2020-06-18 | 2021-02-11 | R | [35 empty] | 2021-11-23 |  | 2021-12-22 |  | G | 2022-03-17 |  | 2022-03-17 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.25259
744 | 113885 | #SGR19LB??- Gov Plant Rd / NF Holst Saltv VA 5000 Fed 22611 | 0000 | Urban | Bridge Rehab w/o Added Capacity | VDOT | Saltville | ABINGDON | Bristol | NonMPO:NonMPO | Infrastructure Investment/Asset Management Division | Gary Lester |  |  | Emily V Collins | Emily.Collins@vdot.virginia.gov | (276) 696-3394 |  |  |  | 0 |  | 1 | FY2020 | 620000 | 620000 | ADVERTISED | R | Start Delivery milestone is 380 days past the expected completion date | G | Project is on budget | [5 empty] | 2018-11-13 | 2018-11-13 | 2018-11-28 | 2018-11-28 | G | 2018-11-29 | 2018-11-29 | 2019-02-27 | 2019-02-27 | G | [35 empty] | 2019-11-12 | 2019-11-05 | 2019-11-12 | 2019-11-05 | G | 2020-02-07 |  | 2020-02-07 |  | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 |  | 0 | 0 | 0.13153
745 | 115237 | #SMART20 J.Clyde Morris Blvd Intersection Improvements | 0017 | Urban | Safety | Locally | Newport News | WILLIAMSBURG | Hampton Roads | Hampton Roads:Newport News | Infrastructure Investment Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Chessica Villaflores | Chessica.Villaflores@vdot.virginia.gov | (757) 956-3094 | Bryan Stilley | bstilley@nnva.gov | (757) 926-8699 | 1 | 2020 | 0 | FY2027 | 1768528 | 1768528 | NO DATES SET YET | G | Agreement with Locality milestone is 977 days ahead of the expected completion date | Y | Estimate not current | 2023-08-02 |  | 2023-10-26 |  | G | 2023-10-27 |  | 2023-10-31 |  | G | 2023-11-01 |  | 2024-05-10 |  | G | [10 empty] | 2025-05-14 |  | 2025-06-04 |  | G | [5 empty] | 2025-06-06 |  | 2026-03-20 |  | G | 2024-06-18 |  | 2025-02-25 |  | G | [5 empty] | 2026-04-07 |  | 2026-05-04 |  | G | 2026-07-23 |  | 2026-07-23 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.30838
746 | 115514 | City of Norfolk 887 N Military Hwy - Paving | 0013 | Urban | Restoration and Rehabilitation | Locally | Norfolk | NORFOLK | Hampton Roads | Hampton Roads:Norfolk | Local Assistance Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Derrick Williams | Derrick.Williams@vdot.virginia.gov | (757) 956-3097 | Eric Berger | eric.berger@norfolk.gov | (757) 823-4039 | 0 |  | 0 | FY2020 | 295363 | 295363 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 106 days early | G | Project is on budget | 2019-10-03 | 2019-10-03 | 2020-01-02 | 2019-12-30 | G | [5 empty] | 2019-10-03 | 2019-10-03 | 2019-10-16 | 2020-01-06 | R | [35 empty] | 2020-01-16 | 2020-01-16 | 2020-02-19 | 2020-01-21 | G | 2020-05-07 | 2020-01-22 | 2020-05-07 | 2020-01-22 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.10824
747 | 115936 | COMPTON RD SHARED USE PATH - I-66 OTB UNDERPASS | 9999 | Secondary | Facilities for Pedestrians and Bicycles | VDOT | Fairfax County | FAIRFAX | Northern Virginia | Northern Virginia:Fairfax County | Infrastructure Investment Division | Susan N Shaw | Susan.Shaw@VDOT.Virginia.gov | (703) 259-1995 | Harinderbir S Warraich | HS.Warraich@VDOT.Virginia.gov | (571) 459-2362 | Lauren Delmare | Lauren.Delmare@fairfaxcounty.gov | (703) 877-5781 | 0 |  | 0 | FY2021 | 1075000 | 1075000 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 229 days early | G | Project is on budget | 2019-10-01 | 2019-10-01 | 2019-10-10 | 2019-10-10 | G | 2019-10-01 | 2019-10-28 | 2019-12-31 | 2019-10-28 | G | 2020-01-02 | 2019-10-29 | 2020-05-29 | 2019-10-30 | G | [5 empty] | 2019-10-31 | 2019-10-31 | 2019-11-05 | 2019-11-05 | G | [25 empty] | 2019-11-08 | 2019-11-20 | 2020-03-10 | 2019-11-20 | G | 2020-03-11 | 2019-11-21 | 2020-07-07 | 2019-11-21 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | WORK/TASK ORDER | 1 | 0 | 0.07773
748 | 118253 | DEVLIN RD WIDENING 2 TO 4 LANES (DEVLIN TO UNIVERSITY BLVD) | 0621 | Secondary | Reconstruction w/ Added Capacity | Locally | Prince William County | MANASSAS | Northern Virginia | Northern Virginia:Prince William County | Infrastructure Investment Division | Terry Yates | Terry.Yates@vdot.virginia.gov | (703) 259-2118 | Jeffrey S Daily | Jeff.Daily@VDOT.Virginia.gov | (703) 259-2993 | Mary Ankers | MAnkers@pwcgov.org | (703) 792-4228 | 0 |  | 0 | FY2026 | 25000000 | 25000000 | NO DATES SET YET | G | Agreement with Locality milestone is 50 days ahead of the expected completion date | G | Project is on budget | 2020-12-01 |  | 2021-04-12 |  | G | 2021-04-13 |  | 2021-05-03 |  | G | 2021-06-02 |  | 2022-02-08 |  | G | [10 empty] | 2024-05-08 |  | 2024-06-12 |  | G | [5 empty] | 2024-06-13 |  | 2025-01-06 |  | G | 2024-03-13 |  | 2024-11-12 |  | G | [5 empty] | 2025-04-11 |  | 2025-05-08 |  | G | 2025-07-29 |  | 2025-07-29 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.42153
749 | 98823 | Bridge Replacement Rte 601 over Diascund Creek, Fed ID 10516 | 0601 | Secondary | Bridge Replacement w/o Added Capacity | VDOT | James City County | WILLIAMSBURG | Hampton Roads | Hampton Roads:James City County | Infrastructure Investment Division | Nancy R Marshall | Nancy.Marshall@VDOT.Virginia.gov | (757) 956-3266 | Nancy R Marshall | Nancy.Marshall@VDOT.Virginia.gov | (757) 956-3266 |  |  |  | 0 |  | 0 | FY2020 | 3258241 | 5160834 | ACTIVITY DATES SET | R | Obtained Permits milestone is 843 days past the expected completion date | R | Project estimate is less than $5M and is 20% or more over budget | [5 empty] | 2012-09-03 | 2012-08-22 | 2012-09-03 | 2012-08-23 | G | 2015-01-29 | 2013-07-08 | 2017-08-22 | 2017-08-23 | R | [5 empty] | 2018-02-12 | 2018-02-12 | 2018-02-14 | 2018-02-14 | G | 2018-11-05 | 2019-12-18 | 2018-11-19 | 2019-12-27 | R | 2019-06-12 | 2020-08-18 | 2019-12-04 | 2020-12-15 | R | 2018-12-06 | 2020-01-28 | 2019-05-30 | 2020-06-15 | R | 2018-03-05 | 2018-03-05 | 2018-11-01 |  | R | [5 empty] | 2019-12-10 |  | 2019-12-10 |  | R | 2019-12-11 |  | 2020-03-10 |  | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.17447
750 | 111670 | #SMART18 - WESTWIND DRIVE (LOUDOUN COUNTY PKWY TO ROUTE 606) | 2988 | Secondary | New Construction Roadway | Locally | Loudoun County | LEESBURG | Northern Virginia | Northern Virginia:Loudoun County | Infrastructure Investment Division | Amir Salahshoor | A.Salahshoor@VDOT.Virginia.gov | (703) 259-1957 | Robert J Strevell | Robert.Strevell@vdot.virginia.gov | (703) 259-1988 | Yuliya Akhremenko | yuliya.akhremenko@loudoun.gov | (703) 771-5908 | 1 | 2018 | 0 | FY2021 | 43278410 | 43278410 | NO DATES SET YET-PE OPEN | R | Determine Requirements milestone is 808 days past the expected completion date | G | Project is on budget | 2017-09-01 | 2018-05-31 | 2017-11-30 | 2018-06-29 | R | 2017-12-01 | 2018-09-04 | 2017-12-05 | 2019-01-17 | R | 2017-12-06 |  | 2018-12-06 |  | R | [5 empty] | 2022-09-30 |  | 2022-12-30 |  | G | 2019-12-19 |  | 2020-01-10 |  | R | 2023-09-01 |  | 2024-04-30 |  | G | 2020-01-14 |  | 2020-10-21 |  | R | 2023-02-01 |  | 2024-02-29 |  | G | [5 empty] | 2020-11-06 |  | 2020-12-08 |  | R | 2020-12-09 |  | 2021-01-22 |  | R | Consultant contract is still in procurement | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.3421
752 | 113189 | BELMONT RIDGE ROAD (TRURO PARISH DRIVE TO CROSON LANE) | 0659 | Secondary | Reconstruction w/ Added Capacity | Locally | Loudoun County | LEESBURG | Northern Virginia | Northern Virginia:Loudoun County | Local Assistance Division | Kimberly Mccool | Kimberly.McCool@vdot.virginia.gov | (703) 259-3220 | Susie X Lue | Susie.Lue@vdot.virginia.gov | (703) 259-2918 | Marie Caraballo | marie.caraballo@loudoun.gov | (571) 258-3447 | 0 |  | 0 | FY2024 | 42736044 | 44305876 | ACTIVITY DATES SET | G | Obtained Permits milestone finished 1235 days early | Y | Project estimate is greater than $10M and is over budget by (a) up to 10% or (b) up to $5M | 2018-10-31 | 2018-10-04 | 2019-03-29 | 2019-02-19 | G | [5 empty] | 2019-09-03 | 2019-02-20 | 2020-06-30 | 2019-02-21 | G | [10 empty] | 2020-04-02 | 2019-06-18 | 2020-04-29 | 2019-06-18 | G | [5 empty] | 2020-04-30 | 2019-07-01 | 2022-10-07 |  | G | 2022-10-10 | 2019-08-12 | 2022-12-29 | 2019-08-12 | G | [5 empty] | 2022-11-08 |  | 2023-05-08 |  | G | 2023-05-09 |  | 2023-10-10 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.42227
753 | 113825 | S. Military Highway & George Washington Highway FYA | 0013 | Urban | Safety | Locally | Chesapeake | NORFOLK | Hampton Roads | Hampton Roads:Chesapeake | Infrastructure Investment Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Johndel A Alcaide | John.Alcaide@vdot.virginia.gov | (757) 956-3098 | Sam Sawan, PE | sawan@cityofchesapeake.net | (757) 382-8263 | 0 |  | 0 | FY2023 | 582500 | 582500 | NO DATES SET YET-PE OPEN | G | Obtained Permits milestone finished 659 days early | G | Project is on budget | 2020-06-01 | 2020-07-15 | 2020-10-06 | 2020-08-26 | G | 2020-10-07 | 2020-08-28 | 2020-10-28 | 2020-09-14 | G | 2020-12-01 |  | 2021-03-29 |  | G | [25 empty] | 2022-03-24 | 2020-10-29 | 2022-08-19 | 2020-10-29 | G | [5 empty] | 2022-10-19 |  | 2022-11-16 |  | G | 2023-02-10 |  | 2023-02-10 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.20577
754 | 114770 | #SGR20LB - CHATHAM BRIDGE DETOUR | 0003 | Primary | Reconstruction w/ Added Capacity | VDOT | Fredericksburg | FREDERICKSBURG | Fredericksburg | Fredericksburg:Fredericksburg | Infrastructure Investment/Asset Management Division | Robert Galen Ridgell | Robert.Ridgell@vdot.virginia.gov | (540) 372-3549 | Robert Galen Ridgell | Robert.Ridgell@vdot.virginia.gov | (540) 372-3549 |  |  |  | 0 |  | 1 | FY2019 | 500000 | 500000 | WAITING FINANCIAL CLOSURE | R | Start Delivery milestone finished 31 days late | G | Project is on budget | [10 empty] | 2018-10-01 | 2018-10-01 | 2018-10-05 | 2019-04-01 | R | [35 empty] | 2019-04-09 | 2019-04-09 | 2019-04-09 | 2019-04-09 | G | 2019-06-28 | 2019-07-29 | 2019-06-28 | 2019-07-29 | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.1859
755 | 115494 | #SMART20 RTE 360/501 - INTERSECTION IMPROVEMENTS | 0501 | Primary | Safety | VDOT | Halifax | HALIFAX | Lynchburg | NonMPO:NonMPO | Infrastructure Investment Division | Robert F Guercia | Robert.Guercia@VDOT.Virginia.gov | (434) 841-6864 | Lindsey S Hodges | Lindsey.Hodges@vdot.virginia.gov | (434) 856-8143 |  |  |  | 1 | 2020 | 0 | FY2020 | 738925 | 738925 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished on-time | G | Project is on budget | [5 empty] | 2019-10-18 | 2019-10-02 | 2019-11-01 | 2019-10-16 | G | 2019-11-04 | 2019-11-04 | 2019-11-04 | 2019-11-04 | G | [5 empty] | 2019-11-07 | 2019-08-30 | 2019-11-14 | 2019-09-10 | G | 2019-12-23 | 2019-12-17 | 2019-12-23 | 2019-12-17 | G | 2019-12-23 | 2019-12-17 | 2019-12-23 | 2019-12-17 | G | 2019-12-23 | 2019-12-17 | 2019-12-23 | 2019-12-17 | G | [10 empty] | 2020-03-10 | 2020-03-10 | 2020-03-10 | 2020-03-10 | G | 2020-05-29 | 2020-05-29 | 2020-05-29 | 2020-05-29 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.078305
756 | 115540 | #SMART20 - Progress Park Connector | 9999 | Secondary | New Construction Roadway | VDOT | Wythe County | WYTHEVILLE | Bristol | NonMPO:NonMPO | Infrastructure Investment Division | Marvin E Holley | Gene.Holley@VDOT.Virginia.gov | (276) 696-3255 | James R Jones | jamesr.jones@vdot.virginia.gov | (276) 696-3257 |  |  |  | 1 | 2020 | 0 | FY2024 | 23342554 | 23333554 | ACTIVITY DATES SET | G | Determine Requirements milestone finished on-time | G | Project is on budget | [5 empty] | 2019-07-09 | 2019-07-09 | 2019-07-22 | 2019-07-22 | G | 2019-07-23 | 2019-07-23 | 2020-08-31 | 2020-08-31 | G | [5 empty] | 2021-07-26 |  | 2021-08-06 |  | G | 2022-10-27 |  | 2022-11-09 |  | G | 2023-03-01 |  | 2023-07-20 |  | G | 2022-11-30 |  | 2023-08-17 |  | G | 2022-04-22 |  | 2022-12-27 |  | G | [5 empty] | 2023-12-12 |  | 2023-12-12 |  | G | 2024-04-04 |  | 2024-04-04 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.15321
757 | 117807 | 121/460 Corridor Q Intersection/Hawk's Nest Finish Grade | 0460 | Primary | New Construction Roadway | VDOT | Buchanan County | LEBANON | Bristol | NonMPO:NonMPO | Infrastructure Investment Division | Marty R Halloway | Marty.Halloway@VDOT.Virginia.gov | (276) 696-3367 | Stephen Warner Gray | Stephen.Gray@vdot.virginia.gov | (276) 619-1389 |  |  |  | 0 |  | 0 | FY2021 | 13277564 | 13277564 | NO DATES SET YET | R | Engage Public milestone is 174 days past the expected completion date | G | Project is on budget | [5 empty] | 2020-08-31 |  | 2021-02-01 |  | R | 2020-03-02 |  | 2021-01-29 |  | R | [5 empty] | 2020-07-30 |  | 2020-08-31 |  | R | [25 empty] | 2021-01-26 |  | 2021-02-01 |  | R | 2021-05-03 |  | 2021-05-03 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | DESIGN BUILD/PPTA | 0 | 0 | 0.089447
758 | 8753 | #HB2.FY17 Rte460 - Add'n of CTL w/ Bike Ln, Curb, Sidewalk | 0460 | Urban | Reconstruction w/o Added Capacity | VDOT | Salem | SALEM | Salem | Roanoke:Salem | Infrastructure Investment Division | Thomas W Digiulian | Thomas.DiGiulian@VDOT.Virginia.gov | (540) 387-5356 | Jeffrey A Echols | Jeff.Echols@VDOT.Virginia.gov | (540) 375-3595 |  |  |  | 1 | 2017 | 0 | FY2018 | 15223263 | 15223263 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 62 days early | G | Project is on budget | [5 empty] | 1990-02-15 | 1989-07-30 | 1990-02-28 | 1989-07-31 | G | 2010-11-03 | 2010-11-03 | 2012-07-20 | 2016-02-18 | R | [5 empty] | 2015-01-09 | 2015-01-09 | 2015-04-01 | 2015-04-01 | G | 2016-03-03 | 2016-03-03 | 2016-04-20 | 2016-04-20 | G | 2017-06-20 | 2017-06-20 | 2018-05-16 | 2018-05-30 | R | 2016-06-16 | 2016-06-16 | 2017-07-05 | 2017-07-05 | G | [10 empty] | 2017-12-12 | 2017-12-12 | 2017-12-12 | 2017-12-12 | G | 2018-06-06 | 2018-04-18 | 2018-06-19 | 2018-04-18 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 1 | 0.27118
759 | 100422 | REBUILDING MT. VERNON TRAIL PARALLEL TO ABINGDON DR. | 0001 | Urban | Facilities for Pedestrians and Bicycles | Locally | Alexandria | FAIRFAX | Northern Virginia | Northern Virginia:Alexandria | Infrastructure Investment Division | Andrew G Beacher | Andrew.Beacher@vdot.virginia.gov | (703) 259-2239 | Robert J Strevell | Robert.Strevell@vdot.virginia.gov | (703) 259-1988 | Brian Meli | Brian.Meli@alexandriava.gov | (703) 746-4110 | 0 |  | 0 | FY2023 | 804835 | 804835 | NO DATES SET YET | R | Determine Requirements milestone is 2730 days past the expected completion date | G | Project is on budget | 2013-04-01 | 2013-04-01 | 2013-04-01 | 2013-04-01 | G | 2019-10-20 |  | 2019-10-31 |  | R | 2013-07-25 | 2013-07-23 | 2013-09-01 |  | R | [10 empty] | 2020-01-25 |  | 2020-02-04 |  | R | [5 empty] | 2020-02-05 |  | 2022-07-14 |  | G | [10 empty] | 2022-07-15 |  | 2022-11-15 |  | G | 2022-11-23 |  | 2023-05-01 |  | G | Delay due to unforeseen issues with utilities, railroad coordination, or right-of-way acquisition | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.21671
760 | 102952 | RTE 10 (I-95 - Rt 1) - WIDENING | 0010 | Primary | Reconstruction w/ Added Capacity | Locally | Chesterfield County | CHESTERFIELD | Richmond | Richmond:Chesterfield County | Infrastructure Investment Division | Brian J Lokker | Brian.Lokker@VDOT.Virginia.gov | (804) 524-6010 | Brian J Lokker | Brian.Lokker@VDOT.Virginia.gov | (804) 524-6010 | STAN NEWCOMB | newcombs@chesterfield.gov | (804) 748-1037 | 0 |  | 0 | FY2020 | 8000000 | 9210588 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 66 days early | R | Project estimate is between $5M and $10M and is a $1M or more over budget | 2012-09-15 | 2012-09-13 | 2012-09-15 | 2012-09-13 | G | 2012-10-01 | 2012-12-03 | 2012-10-01 | 2012-12-03 | R | 2017-06-01 | 2015-08-18 | 2017-10-01 | 2015-11-12 | G | [5 empty] | 2016-10-06 | 2016-10-06 | 2016-10-06 | 2016-10-06 | G | 2016-12-22 | 2016-12-22 | 2016-12-29 | 2016-12-29 | G | [5 empty] | 2017-02-27 | 2017-02-27 | 2018-01-11 | 2018-01-11 | G | [10 empty] | 2019-07-01 | 2018-11-28 | 2019-07-01 | 2019-04-01 | G | 2019-09-30 | 2019-06-14 | 2019-09-30 | 2019-07-26 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.14171
761 | 105490 | RTE 609 - REPLACE BRIDGE (FED ID 3658) | 0609 | Secondary | Bridge Replacement w/o Added Capacity | VDOT | Brunswick County | SOUTH HILL | Richmond | NonMPO:NonMPO | Infrastructure Investment Division | Thomas Kendrick | Thomas.Kendrick@vdot.virginia.gov | (804) 609-5281 | Thomas Kendrick | Thomas.Kendrick@vdot.virginia.gov | (804) 609-5281 |  |  |  | 0 |  | 0 | FY2021 | 2390000 | 3367281 | ADVERTISED | R | Solicit Bids milestone finished 91 days late | R | Project estimate is less than $5M and is 20% or more over budget | [5 empty] | 2017-10-15 | 2017-08-25 | 2017-10-15 | 2017-08-25 | G | 2017-10-17 | 2017-10-11 | 2018-07-09 | 2018-07-09 | G | [5 empty] | 2018-12-12 | 2018-12-12 | 2019-01-03 | 2018-12-27 | G | 2019-07-23 | 2019-08-01 | 2019-09-10 | 2019-08-09 | G | 2020-05-19 | 2019-04-10 | 2020-08-19 | 2019-04-10 | G | 2019-10-09 | 2019-10-17 | 2020-04-20 | 2020-02-18 | G | 2019-06-24 | 2019-07-19 | 2020-03-02 | 2021-01-11 | R | [5 empty] | 2020-11-10 | 2021-02-09 | 2020-11-10 | 2021-02-09 | R | 2020-12-30 |  | 2021-03-01 |  | Y |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.075622
762 | 106291 | PHASE V - DILLWYN STREETSCAPES |  | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Dillwyn | DILLWYN | Lynchburg | NonMPO:NonMPO | Local Assistance Division | Sharon S White | Sharon.White@VDOT.Virginia.gov | (434) 856-8220 | Sharon S White | Sharon.White@VDOT.Virginia.gov | (434) 856-8220 | Todd Fortune, Community Development Planner | TFortune@virginiasheartland.org | (434) 392-6104 | 0 |  | 0 | FY2020 | 1662830 | 1662830 | CONSTRUCTION STARTED | R | Start Delivery milestone finished 335 days late | G | Project is on budget | [10 empty] | 2018-03-01 | 2018-03-01 | 2018-05-01 | 2018-05-01 | G | [35 empty] | 2019-04-30 | 2019-07-09 | 2019-06-10 | 2019-07-09 | R | 2019-06-12 | 2020-05-12 | 2019-07-09 | 2020-06-08 | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.34801
763 | 107036 | INSTALL PEDESTRIAN SIGNALS - DISTRICTWIDE | 9999 | Miscellaneous | Safety | VDOT | Richmond District-wide |  | Richmond | Richmond:Richmond District-wide | Infrastructure Investment Division | Adam S Brooks | Adam.Brooks@VDOT.Virginia.gov | (804) 609-5274 | Adam S Brooks | Adam.Brooks@VDOT.Virginia.gov | (804) 609-5274 |  |  |  | 0 |  | 0 | FY2021 | 1500000 | 1500000 | ADVERTISED | G | Solicit Bids milestone finished on-time | G | Project is on budget | [5 empty] | 2017-10-13 | 2017-08-15 | 2017-10-27 | 2017-08-25 | G | 2017-10-30 | 2017-10-26 | 2018-09-26 | 2018-07-30 | G | [5 empty] | 2019-02-20 | 2018-12-07 | 2019-04-16 | 2018-12-20 | G | 2020-04-06 | 2020-04-02 | 2020-04-17 | 2020-04-02 | G | 2020-03-23 | 2020-03-23 | 2020-03-23 | 2020-03-23 | G | 2020-05-05 | 2020-07-09 | 2020-11-06 | 2020-09-16 | G | 2020-01-07 | 2019-12-23 | 2020-05-29 | 2019-12-23 | G | [5 empty] | 2021-01-12 | 2021-01-12 | 2021-01-12 | 2021-01-12 | G | 2021-04-01 |  | 2021-05-12 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.068308
764 | 108966 | Rosemont Rd/South Plaza Trail Intersection Improvements | 0411 | Urban | Traffic Management/Engineering | Locally | Virginia Beach | NORFOLK | Hampton Roads | Hampton Roads:Virginia Beach | Infrastructure Investment Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Marci Thompson | Marci.Thompson@vdot.virginia.gov | (757) 956-3093 | Dempsey Bruton |  |  | 0 |  | 0 | FY2025 | 363000 | 363000 | NO DATES SET YET | G | Agreement with Locality milestone is 220 days ahead of the expected completion date | G | Project is on budget | 2021-07-07 |  | 2021-09-29 |  | G | 2021-09-30 |  | 2021-10-13 |  | G | 2021-10-14 |  | 2022-09-30 |  | G | [10 empty] | 2023-07-28 |  | 2023-08-17 |  | G | [5 empty] | 2023-08-21 |  | 2024-06-03 |  | G | [10 empty] | 2024-06-19 |  | 2024-07-17 |  | G | 2024-07-18 |  | 2024-10-17 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.24253
765 | 109025 | SPOTSWOOD ELEMENTARY SRTS |  | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Harrisonburg | HARRISONBURG | Staunton | Harrisonburg:Harrisonburg | Local Assistance Division | Michael S Fulcher | Michael.Fulcher@VDOT.Virginia.gov | (540) 332-2243 | Michael S Fulcher | Michael.Fulcher@VDOT.Virginia.gov | (540) 332-2243 | Aaron Rhoney | aaron.rhoney@harrisonburgva.gov | (540) 434-5928 | 0 |  | 0 | FY2019 | 189980 | 199752 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 86 days early | Y | Project estimate is less than $5M and is up to 20% over budget | 2016-10-03 | 2016-10-03 | 2016-12-30 | 2017-01-03 | R | 2017-01-03 | 2017-01-04 | 2017-01-05 | 2017-03-03 | R | 2017-01-06 | 2017-03-06 | 2017-07-13 | 2017-10-04 | R | [10 empty] | 2017-11-01 | 2017-11-01 | 2017-11-07 | 2017-11-07 | G | [5 empty] | 2017-11-09 | 2017-11-09 | 2018-08-29 | 2018-05-17 | G | [10 empty] | 2018-12-28 | 2018-07-01 | 2019-01-29 | 2018-07-19 | G | 2019-01-30 | 2018-07-20 | 2019-06-06 | 2019-03-12 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.2115
766 | 109504 | #SGR17VB - RT 19 STR 1135 NSRR & WRIGHTS VALLEY CK - 18461 | 0019 | Primary | Bridge Replacement w/o Added Capacity | VDOT | Tazewell County | LEBANON | Bristol | NonMPO:NonMPO | Infrastructure Investment/Asset Management Division | Gary Lester |  |  | John E Sproles | John.Sproles@VDOT.Virginia.gov | (276) 696-3391 |  |  |  | 0 |  | 1 | FY2022 | 2800000 | 3810235 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 614 days early | R | Project estimate is less than $5M and is 20% or more over budget | [5 empty] | 2016-09-01 | 2017-03-06 | 2016-09-15 | 2017-03-06 | R | 2016-09-16 | 2017-03-03 | 2017-08-15 | 2018-02-28 | R | [5 empty] | 2019-09-19 | 2019-09-19 | 2019-10-02 | 2019-10-02 | G | 2020-12-07 | 2019-10-29 | 2020-12-18 | 2019-11-12 | G | 2021-05-17 |  | 2021-11-19 |  | G | 2021-01-06 |  | 2021-07-13 |  | G | [10 empty] | 2021-12-14 | 2020-03-10 | 2021-12-14 | 2020-03-10 | G | 2022-02-08 | 2020-06-25 | 2022-03-01 | 2020-06-25 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.061196
767 | 110012 | #SGR17VB -RT 658 Str 6104 over SF Holston River Fed 17648 | 0658 | Secondary | Bridge Rehab w/o Added Capacity | VDOT | Smyth County | ABINGDON | Bristol | NonMPO:NonMPO | Infrastructure Investment/Asset Management Division | Gary Lester |  |  | David L Lively | David.Lively@VDOT.Virginia.gov | (276) 696-3388 |  |  |  | 0 |  | 1 | FY2019 | 1180000 | 1180000 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished on-time | G | Project is on budget | [5 empty] | 2016-09-01 | 2016-09-01 | 2016-09-15 | 2016-12-29 | R | 2016-09-16 | 2016-12-30 | 2017-08-15 | 2017-03-21 | G | [5 empty] | 2017-09-07 | 2017-09-14 | 2017-09-07 | 2017-09-14 | R | 2017-12-28 | 2017-11-06 | 2017-12-28 | 2017-11-06 | G | 2018-05-10 | 2018-05-10 | 2018-11-14 | 2019-04-10 | R | 2017-12-28 | 2017-11-06 | 2017-12-28 | 2017-11-06 | G | 2017-12-07 | 2017-12-01 | 2018-08-10 | 2018-04-10 | G | [5 empty] | 2019-04-09 | 2019-04-09 | 2019-04-09 | 2019-04-09 | G | 2019-05-30 | 2019-06-19 | 2019-06-19 | 2019-06-19 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.14687
768 | 110913 | #SMART18 - LAFAYETTE BLVD AND HARRISON RD INTERSECT. IMPROVE | 0001 | Primary | Safety | VDOT | Spotsylvania County | FREDERICKSBURG | Fredericksburg | Fredericksburg:Spotsylvania County | Infrastructure Investment Division | Khalil Minhas | Khalil.Minhas@vdot.virginia.gov | (540) 374-3369 | Khalil Minhas | Khalil.Minhas@vdot.virginia.gov | (540) 374-3369 | Paul Agnello | pagnello@spotsylvania.va.us | (540) 507-7398 | 1 | 2018 | 0 | FY2022 | 1200000 | 1217825 | ACTIVITY DATES SET | G | Complete Purchasing Right-of-Way milestone finished 73 days early | Y | Project estimate is less than $5M and is up to 20% over budget | [5 empty] | 2018-07-19 | 2018-06-12 | 2018-08-01 | 2018-06-25 | G | 2018-08-02 | 2018-06-26 | 2019-02-12 | 2019-01-03 | G | [5 empty] | 2019-08-06 | 2019-06-24 | 2019-08-19 | 2019-06-24 | G | 2020-07-20 | 2020-02-14 | 2020-07-31 | 2020-02-20 | G | 2020-12-30 | 2020-03-27 | 2021-10-07 | 2020-09-01 | G | 2020-08-18 | 2020-03-11 | 2021-03-01 | 2020-12-18 | G | [10 empty] | 2021-10-12 |  | 2021-10-12 |  | G | 2022-01-24 |  | 2022-03-21 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.063367
769 | 111024 | Systemic Flashing Yellow Arrow Improvements | 0000 | Urban | Safety | Locally | Norfolk | NORFOLK | Hampton Roads | Hampton Roads:Norfolk | Infrastructure Investment Division | Todd M Halacy | Todd.Halacy@VDOT.Virginia.gov | (757) 956-3010 | Derrick Williams | Derrick.Williams@vdot.virginia.gov | (757) 956-3097 | 'Deborah Mangiaracina, P.E. | Deborah.Mangiaracina@norfolk.gov | (757) 664-7459 | 0 |  | 0 | FY2024 | 565505 | 565505 | NO DATES SET YET-PE OPEN | G | Start Development milestone finished 134 days early | G | Project is on budget | 2020-10-15 | 2020-10-15 | 2021-03-02 | 2020-10-20 | G | 2021-03-03 | 2020-10-21 | 2021-03-23 | 2020-11-09 | G | 2021-09-27 |  | 2022-01-26 |  | G | [25 empty] | 2023-01-23 |  | 2023-06-20 |  | G | [5 empty] | 2023-08-17 |  | 2023-09-14 |  | G | 2023-12-07 |  | 2023-12-07 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.25112
770 | 104295 | RTE 123 - CHAIN BRIDGE RD PED & DRAINAGE IMPROVEMENTS | 0123 | Urban | Facilities for Pedestrians and Bicycles | Locally | Fairfax | FAIRFAX | Northern Virginia | Northern Virginia:Fairfax | Infrastructure Investment Division | Terry Yates | Terry.Yates@vdot.virginia.gov | (703) 259-2118 | Rita Hockman | Rita.Hockman@vdot.virginia.gov | (804) 824-7421 | Peter Millard | peter.millard@fairfaxva.gov | (703) 385-7889 | 0 |  | 0 | FY2020 | 4587227 | 6293158 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 174 days early | R | Project estimate is less than $5M and is 20% or more over budget | 2013-10-17 | 2013-10-17 | 2013-10-17 | 2013-10-17 | G | 2014-02-01 | 2014-09-22 | 2014-02-01 | 2014-09-22 | R | 2016-08-01 | 2015-07-31 | 2017-06-30 | 2017-06-30 | G | [10 empty] | 2017-08-09 | 2017-08-09 | 2017-08-24 | 2017-08-24 | G | [20 empty] | 2018-07-02 | 2018-07-02 | 2018-12-31 | 2018-12-10 | G | 2019-05-23 | 2019-04-02 | 2019-09-23 | 2019-04-02 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.20555
771 | 106157 | Portsmouth Rail to Trail |  | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Portsmouth | NORFOLK | Hampton Roads | Hampton Roads:Portsmouth | Local Assistance Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Marci Thompson | Marci.Thompson@vdot.virginia.gov | (757) 956-3093 | Susan Wilson | wilsons@portsmouthva.gov | (757) 393-8836 | 0 |  | 0 | FY2021 | 1231527 | 1255000 | ACTIVITY DATES SET | R | Solicit Bids milestone is 96 days past the expected completion date | Y | Project estimate is less than $5M and is up to 20% over budget | [5 empty] | 2016-10-25 | 2016-10-25 | 2016-10-28 | 2016-10-28 | G | 2017-10-20 | 2017-10-20 | 2019-10-23 | 2019-10-18 | G | [35 empty] | 2020-08-21 |  | 2020-11-17 |  | R | 2020-11-18 |  | 2021-05-13 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.37194
772 | 106573 | RTE 7 INTERCHANGE AT BATTLEFIELD PKWY | 0007 | Primary | Bridge, New Construction | VDOT | Leesburg | LEESBURG | Northern Virginia | Northern Virginia:Leesburg | Infrastructure Investment Division | Kimberly Mccool | Kimberly.McCool@vdot.virginia.gov | (703) 259-3220 | Sanjeev Suri | Sanjeev.Suri@VDOT.Virginia.gov | (703) 259-2232 | Terry Yates, Capital Projects Manager | tyates@leesburgva.gov | (703) 771-6671 | 0 |  | 0 | FY2019 | 77288541 | 77288541 | CONSTRUCTION STARTED | R | Solicit Bids milestone is 513 days past the expected completion date | G | Project is on budget | [5 empty] | 2016-03-09 | 2016-03-09 | 2016-03-09 | 2016-03-09 | G | 2015-10-26 | 2015-10-01 | 2018-07-19 | 2019-03-15 | R | [5 empty] | 2015-10-01 | 2015-10-01 | 2020-02-03 |  | R | 2018-06-08 | 2018-06-08 | 2018-06-08 | 2018-06-08 | G | [20 empty] | 2019-09-23 |  | 2019-09-27 |  | R | 2019-03-21 | 2019-03-21 | 2019-03-21 | 2019-03-21 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | DESIGN BUILD/PPTA | 1 | 1 | 0.36134
773 | 108904 | #HB2.FY17 Route 311 / Route 419 Int. Safety & Congestion Imp | 0311 | Primary | Reconstruction w/o Added Capacity | VDOT | Roanoke County | SALEM | Salem | Roanoke:Roanoke County | Infrastructure Investment Division | Brian K Blevins | Brian.Blevins@VDOT.Virginia.gov | (540) 387-5502 | Brian K Blevins | Brian.Blevins@VDOT.Virginia.gov | (540) 387-5502 | Megan Cronise | mcronise@roanokecountyva.gov | (540) 772-2080 | 1 | 2017 | 0 | FY2021 | 1957006 | 3775000 | ACTIVITY DATES SET | R | Relocate Utilities milestone is 104 days past the expected completion date | R | Project estimate is less than $5M and is 20% or more over budget | [5 empty] | 2016-06-29 | 2016-06-29 | 2016-08-25 | 2016-08-25 | G | 2016-08-26 | 2016-08-26 | 2018-02-02 | 2017-09-28 | G | [5 empty] | 2018-08-06 | 2018-07-01 | 2018-08-17 | 2018-07-01 | G | 2019-11-25 | 2020-06-18 | 2019-12-10 | 2020-06-18 | R | 2020-05-06 | 2020-08-03 | 2020-11-09 |  | R | 2019-12-27 | 2020-07-15 | 2020-07-02 | 2020-09-23 | R | 2019-05-14 | 2020-05-12 | 2020-02-12 | 2020-05-12 | R | [5 empty] | 2020-11-10 |  | 2020-11-10 |  | R | 2021-01-06 |  | 2021-01-28 |  | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.1354
774 | 108982 | Suffolk Transportation Operation Center | 0000 | Urban | Other | Locally | Suffolk | NORFOLK | Hampton Roads | Hampton Roads:Suffolk | Infrastructure Investment Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Johndel A Alcaide | John.Alcaide@vdot.virginia.gov | (757) 956-3098 | Robert Lewis | relewis@suffolkva.us | (757) 514-7603 | 0 |  | 0 | FY2025 | 2050000 | 2050000 | NO DATES SET YET | G | Agreement with Locality milestone is 312 days ahead of the expected completion date | Y | Estimate not current | 2021-10-01 |  | 2021-12-30 |  | G | 2022-01-03 |  | 2022-01-18 |  | G | 2022-01-19 |  | 2022-12-30 |  | G | [35 empty] | 2023-11-08 |  | 2023-12-08 |  | G | 2023-12-11 |  | 2024-07-01 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.18497
775 | 109321 | #HB2.FY17 RTE 95 - IMPROVE INTERCHANGE AT MAURY ST | 0095 | Interstate | Safety | VDOT | Richmond | ASHLAND | Richmond | Richmond:Richmond | Infrastructure Investment Division | Jeremy B Cobb | Jeremy.Cobb@vdot.virginia.gov | (804) 586-2255 | Jeremy B Cobb | Jeremy.Cobb@vdot.virginia.gov | (804) 586-2255 | Adel Edward | Adel.Edward@richmondgov.com | (804) 646-6584 | 1 | 2017 | 0 | FY2021 | 9191250 | 8553801 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 18 days early | G | Project is on budget | [5 empty] | 2016-07-01 | 2016-07-01 | 2016-10-14 | 2016-10-14 | G | 2016-10-17 | 2016-10-17 | 2017-11-28 | 2017-07-20 | G | [5 empty] | 2018-01-09 | 2018-01-09 | 2018-02-22 | 2018-02-22 | G | 2018-08-17 | 2018-07-11 | 2018-09-13 | 2018-08-28 | G | 2019-04-29 | 2019-02-04 | 2020-04-14 | 2020-07-31 | R | 2018-10-02 | 2018-09-17 | 2019-03-29 | 2019-04-01 | R | 2019-03-14 | 2019-03-14 | 2020-03-13 | 2019-03-14 | G | [5 empty] | 2020-07-14 | 2020-08-11 | 2020-07-14 | 2020-08-11 | R | 2020-08-26 | 2020-11-02 | 2020-11-20 | 2020-11-02 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.074862
776 | 109610 | WATER STREET SHARED USE PATH |  | Urban | Facilities for Pedestrians and Bicycles | Locally | Charlottesville | CHARLOTTESVILLE | Culpeper | Charlottesville:Charlottesville | Local Assistance Division | Robert J Strevell | Robert.Strevell@vdot.virginia.gov | (703) 259-1988 | Michael D Barnes | MichaelD.Barnes@vdot.virginia.gov | (434) 422-9861 | Chris Gensic | gensic@charlottesville.org | (434) 970-3656 | 0 |  | 0 | FY2019 | 353572 | 433986 | WAITING FINANCIAL CLOSURE | R | Start Delivery milestone finished 351 days late | Y | Project estimate is less than $5M and is up to 20% over budget | 2016-10-03 | 2016-10-03 | 2016-12-30 | 2016-10-06 | G | 2017-01-03 | 2016-10-07 | 2017-01-05 | 2017-02-07 | R | 2017-01-06 | 2017-02-08 | 2017-07-13 | 2017-07-13 | G | [35 empty] | 2018-05-24 | 2019-01-25 | 2018-06-21 | 2019-02-11 | R | 2018-06-22 | 2019-02-12 | 2018-08-02 | 2019-07-19 | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.13896
777 | 110865 | ACTUATED FLASHER AT VARIOUS LOCATIONS -- DISTRICTWIDE | 9999 | Miscellaneous | Safety | VDOT | Spotsylvania County | FREDERICKSBURG | Fredericksburg | Fredericksburg:Spotsylvania County | Infrastructure Investment/Asset Management Division | Jessica Graves | Jessica.Graves@vdot.virginia.gov | (540) 899-4267 | Benjamin Ernst | Benjamin.Ernst@vdot.virginia.gov | (571) 585-0902 |  |  |  | 0 |  | 0 | FY2023 | 701000 | 480408 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 924 days early | G | Project is on budget | [5 empty] | 2018-07-23 | 2018-06-07 | 2018-08-03 | 2018-06-21 | G | 2018-08-06 | 2018-06-22 | 2019-04-02 | 2019-04-01 | G | [5 empty] | 2020-07-17 | 2019-08-25 | 2020-08-27 | 2019-08-25 | G | [5 empty] | 2021-02-15 | 2019-06-28 | 2021-06-08 | 2019-06-28 | G | [5 empty] | 2021-02-01 | 2019-06-18 | 2021-04-30 | 2019-06-18 | G | [5 empty] | 2022-09-13 | 2020-05-16 | 2022-09-13 | 2020-05-16 | G | 2022-11-03 | 2020-05-18 | 2022-11-28 | 2020-05-18 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | WORK/TASK ORDER | 1 | 0 | 0.062955
779 | 111425 | WAYNESBORO SOUTH RIVER GREENWAY TRAIL PHASE 3 |  | Miscellaneous | Facilities for Pedestrians and Bicycles | Locally | Waynesboro | HARRISONBURG | Staunton | SAW:Waynesboro | Local Assistance Division | Matthew P Dana | Matt.Dana@VDOT.Virginia.gov | (540) 332-7786 | Jamison Brown | Jamison.Brown@vdot.virginia.gov | (540) 332-7389 | Logan Borror | borrorLT@ci.waynesboro.va.us | (540) 942-6624 | 0 |  | 0 | FY2021 | 1091563 | 1091563 | NO DATES SET YET-PE OPEN | R | Determine Requirements milestone is 647 days past the expected completion date | G | Project is on budget | 2018-02-01 | 2017-11-20 | 2018-04-26 | 2017-12-20 | G | 2018-04-27 | 2017-12-21 | 2018-05-01 | 2018-02-05 | G | 2018-05-02 | 2018-02-05 | 2019-05-16 |  | R | [10 empty] | 2020-05-20 |  | 2020-06-09 |  | R | [5 empty] | 2020-06-11 |  | 2021-03-25 |  | Y | [10 empty] | 2021-04-12 |  | 2021-05-07 |  | G | 2021-05-10 |  | 2021-06-18 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.12204
780 | 111615 | RTE. 340 Clarke Co. VA and WV STATE LINE | 0340 | Primary | Reconstruction w/ Added Capacity | VDOT | Clarke County | EDINBURG | Staunton | NonMPO:NonMPO | Infrastructure Investment Division | Terry Jackson |  |  | Jeffery A Lineberry | Jeff.Lineberry@VDOT.Virginia.gov | (540) 332-2265 |  |  |  | 0 |  | 0 | FY2021 | 2000000 | 2000000 | AWARDED | G | Start Delivery milestone finished on-time | G | Project is on budget | [5 empty] | 2017-08-01 | 2017-08-01 | 2017-08-23 | 2017-08-23 | G | 2017-08-24 | 2017-08-24 | 2019-03-01 | 2020-10-01 | R | [5 empty] | 2020-10-01 | 2020-10-01 | 2020-10-01 | 2020-10-01 | G | 2020-10-02 | 2020-10-02 | 2020-10-02 | 2020-10-02 | G | 2020-10-06 | 2020-10-06 | 2020-10-06 | 2020-10-06 | G | 2020-10-05 | 2020-10-05 | 2020-10-05 | 2020-10-05 | G | [10 empty] | 2020-10-07 | 2020-10-07 | 2020-10-08 | 2020-10-08 | G | 2020-10-08 | 2020-10-08 | 2020-10-08 | 2020-10-08 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | DESIGN BUILD/PPTA | 1 | 0 | 0.075913
781 | 112493 | UPGRADE EXISTING SIGNAL BACKLICK RD AND LEESVILLE BLVD | 0617 | Secondary | Safety | VDOT | Fairfax County | FAIRFAX | Northern Virginia | Northern Virginia:Fairfax County | Infrastructure Investment Division | Ivan M Horodyskyj | Ivan.Horodyskyj@VDOT.Virginia.gov | (703) 259-2330 | Tienjung Ho | Tien-Jung.Ho@VDOT.Virginia.gov | (703) 259-2752 |  |  |  | 0 |  | 0 | FY2023 | 675000 | 675000 | ACTIVITY DATES SET | G | Engage Public milestone finished 294 days early | G | Project is on budget | [5 empty] | 2019-02-01 | 2019-01-15 | 2019-02-14 | 2019-01-17 | G | 2019-02-15 | 2019-01-22 | 2020-01-13 | 2020-01-10 | G | [5 empty] | 2020-11-12 | 2020-02-03 | 2020-11-25 | 2020-02-05 | G | 2022-01-21 |  | 2022-02-03 |  | G | 2019-10-18 | 2019-10-18 | 2019-10-18 | 2019-10-18 | G | 2022-02-22 |  | 2022-08-24 |  | G | [10 empty] | 2022-11-08 |  | 2022-11-08 |  | G | 2023-01-04 |  | 2023-01-26 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | WORK/TASK ORDER | 0 | 0 | 0.082561
782 | 113517 | ROUTE 50 AND WAPLES MILL ROAD INTERSECTION IMPROVEMENTS | 0050 | Primary | Traffic Management/Engineering | VDOT | Fairfax County | FAIRFAX | Northern Virginia | Northern Virginia:Fairfax County | Infrastructure Investment Division | Andrew G Beacher | Andrew.Beacher@vdot.virginia.gov | (703) 259-2239 | Zamir A Mirza | Zamir.Mirza@VDOT.Virginia.gov | (703) 259-1794 |  |  |  | 0 |  | 0 | FY2023 | 2000000 | 2510746 | ACTIVITY DATES SET | G | Engage Public milestone finished 50 days early | R | Project estimate is less than $5M and is 20% or more over budget | [5 empty] | 2018-07-02 | 2018-06-21 | 2018-07-16 | 2018-06-21 | G | 2018-07-17 | 2018-07-17 | 2019-06-13 | 2019-06-13 | G | [5 empty] | 2020-04-20 | 2020-03-12 | 2020-05-01 | 2020-03-12 | G | 2021-11-09 |  | 2021-12-09 |  | G | 2022-04-22 |  | 2022-09-27 |  | G | 2022-01-12 |  | 2022-08-09 |  | G | [10 empty] | 2022-10-11 |  | 2022-10-11 |  | G | 2023-01-06 |  | 2023-01-06 |  | G | Preliminary design and/or investigations are still underway | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.074731
783 | 113915 | PEDESTRIAN IMPROVEMENTS MONTICELLO/RIDGE | 3405 | Urban | Safety | Locally | Charlottesville | CHARLOTTESVILLE | Culpeper | Charlottesville:Charlottesville | Infrastructure Investment Division | Ken Connors |  |  | Michael D Barnes | MichaelD.Barnes@vdot.virginia.gov | (434) 422-9861 | Tim Motsch | motscht@charlottesville.gov | (434) 970-3182 | 0 |  | 0 | FY2021 | 209500 | 209106 | ACTIVITY DATES SET | R | Solicit Bids milestone is 48 days past the expected completion date | G | Project is on budget | 2019-10-01 | 2018-11-01 | 2019-12-30 | 2018-12-07 | G | 2019-12-31 | 2018-12-10 | 2020-01-03 | 2019-02-15 | G | 2020-01-06 | 2019-01-10 | 2020-07-10 | 2019-01-11 | G | [10 empty] | 2020-01-15 | 2019-09-26 | 2020-02-06 | 2020-02-12 | R | [5 empty] | 2020-02-10 | 2020-02-13 | 2020-11-16 | 2020-11-20 | R | [10 empty] | 2020-12-04 |  | 2021-01-04 |  | R | 2021-03-26 |  | 2021-03-26 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.16742
784 | 114944 | HARRISON ROAD SIDEWALK | 0620 | Secondary | Safety | VDOT | Spotsylvania County | FREDERICKSBURG | Fredericksburg | Fredericksburg:Spotsylvania County | Infrastructure Investment Division | Peter A Hedrich | Peter.Hedrich@vdot.virginia.gov | (540) 899-4540 | Gina M Pelchat | Gina.Pelchat@vdot.virginia.gov | (504) 899-4010 |  |  |  | 0 |  | 0 | FY2029 | 260100 | 260100 | NO DATES SET YET | G | Start Development milestone is 1270 days ahead of the expected completion date | Y | Estimate not current | [5 empty] | 2024-08-01 |  | 2024-08-14 |  | G | 2024-08-15 |  | 2025-07-15 |  | G | [5 empty] | 2026-05-20 |  | 2026-06-03 |  | G | 2027-09-08 |  | 2027-09-21 |  | G | 2028-02-22 |  | 2028-08-23 |  | G | 2027-10-07 |  | 2028-04-18 |  | G | 2027-03-01 |  | 2027-08-31 |  | G | [5 empty] | 2028-09-12 |  | 2028-09-12 |  | G | 2028-12-06 |  | 2028-12-06 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.068181
785 | 115370 | Traffic Signal Detection Upgrades |  | Urban | Traffic Management/Engineering | Locally | Norfolk | NORFOLK | Hampton Roads | Hampton Roads:Norfolk | Infrastructure Investment Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Derrick Williams | Derrick.Williams@vdot.virginia.gov | (757) 956-3097 | Rob Brown | Robert.Brown@norfolk.gov | (757) 664-7305 | 0 |  | 0 | FY2027 | 1000000 | 1000000 | NO DATES SET YET | G | Agreement with Locality milestone is 1432 days ahead of the expected completion date | Y | Estimate not current | 2024-10-23 |  | 2025-01-23 |  | G | 2025-01-24 |  | 2025-01-28 |  | G | 2025-01-29 |  | 2025-08-01 |  | G | [25 empty] | 2025-09-09 |  | 2026-05-15 |  | G | [5 empty] | 2026-08-20 |  | 2026-09-17 |  | G | 2026-12-10 |  | 2026-12-10 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.41095
786 | 115545 | #SMART20 - FAIRFAX BLVD/WARRICK AVE. INTERSECTION IMPROVE | 0050 | Urban | Reconstruction w/o Added Capacity | Locally | Fairfax | FAIRFAX | Northern Virginia | Northern Virginia:Fairfax | Infrastructure Investment Division | Nassre Y Obeed | Nassre.Obeed@VDOT.Virginia.gov | (703) 259-1723 | Marlene Pinedo Fortich | Sofia.Pinedo@vdot.virginia.gov | (703) 259-1724 | Wendy Block-Sanford |  | (703) 385-7889 | 1 | 2020 | 0 | FY2029 | 8839327 | 8839327 | NO DATES SET YET-PE OPEN | G | Obtained Permits milestone finished 1871 days early | G | Project is on budget | 2023-08-01 | 2019-10-01 | 2024-02-29 | 2019-10-15 | G | 2024-03-01 | 2020-01-23 | 2024-03-29 | 2020-02-02 | G | 2025-01-02 |  | 2025-09-30 |  | G | [10 empty] | 2026-10-01 |  | 2026-10-30 |  | G | [5 empty] | 2026-11-03 |  | 2027-08-31 |  | G | 2024-11-08 | 2020-06-02 | 2025-07-17 | 2020-06-02 | G | [5 empty] | 2027-10-01 |  | 2028-02-01 |  | G | 2028-04-20 |  | 2028-08-31 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.25029
787 | 117003 | #SGR21VP PM3F21 PITTSYLVANIA COUNTY PLANT MIX (P) | 9999 | Primary | Resurfacing | VDOT | Pittsylvania County | HALIFAX | Lynchburg | NonMPO:NonMPO | Infrastructure Investment Division | Kevin S Chisnell | Kevin.Chisnell@VDOT.Virginia.gov | (434) 856-8113 | Kevin S Chisnell | Kevin.Chisnell@VDOT.Virginia.gov | (434) 856-8113 |  |  |  | 0 |  | 1 | FY2022 | 1919400 | 1919400 | ADVERTISED | G | Solicit Bids milestone finished 28 days early | G | Project is on budget | [10 empty] | 2020-11-24 | 2020-10-15 | 2020-12-02 | 2020-11-20 | G | [35 empty] | 2020-12-08 | 2021-01-12 | 2021-02-09 | 2021-01-12 | G | 2021-04-30 |  | 2021-07-15 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.069574
788 | 117151 | #SGR21LP City of Newport News 749 J. Clyde Morris Blvd | 0017 | Urban | Resurfacing | Locally | Newport News | WILLIAMSBURG | Hampton Roads | Hampton Roads:Newport News | Infrastructure Investment/Asset Management Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Chessica Villaflores | Chessica.Villaflores@vdot.virginia.gov | (757) 956-3094 | Bridjette Parker | parkerbj1@nnva.gov | (757) 926-8314 | 0 |  | 1 | FY2022 | 681380 | 681380 | NO DATES SET YET | G | Agreement with Locality milestone is 47 days ahead of the expected completion date | G | Project is on budget | 2021-03-01 |  | 2021-04-09 |  | G | 2021-04-12 |  | 2021-04-30 |  | G | 2021-06-01 |  | 2021-07-13 |  | G | [25 empty] | 2021-03-15 |  | 2021-08-10 |  | G | [5 empty] | 2021-10-07 |  | 2021-11-04 |  | G | 2022-02-01 |  | 2022-02-01 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.12089
789 | 118087 | TOWN OF MADISON MAIN STREET SIDEWALK | 6029 | Primary | Facilities for Pedestrians and Bicycles | Locally | Madison | CHARLOTTESVILLE | Culpeper | NonMPO:NonMPO | Local Assistance Division | Gregory J Cooley | Gregory.Cooley@vdot.virginia.gov | (434) 906-7979 | John P Price | John.Price@VDOT.Virginia.gov | (540) 347-6371 | BARBARA ROACH | MAYNARD@BOYDANDSIPE.COM | (540) 948-3202 | 0 |  | 0 | FY2025 | 288223 | 288223 | NO DATES SET YET | G | Start Development milestone is 64 days ahead of the expected completion date | G | Project is on budget | [5 empty] | 2021-04-06 |  | 2021-04-26 |  | G | 2021-04-27 |  | 2022-03-02 |  | G | [5 empty] | 2022-09-27 |  | 2022-10-25 |  | G | 2023-06-20 |  | 2023-07-25 |  | G | 2023-12-27 |  | 2024-04-29 |  | G | 2023-08-09 |  | 2024-01-11 |  | G | 2023-09-14 |  | 2024-02-20 |  | G | [5 empty] | 2024-05-14 |  | 2024-05-14 |  | G | 2024-08-02 |  | 2024-08-02 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.24792
790 | 112065 | #SGR19LP - RT 147 WB (N HUGUENOT RD) - RESURFACE | 0147 | Urban | Resurfacing | Locally | Richmond | ASHLAND | Richmond | Richmond:Richmond | Local Assistance Division | Brian J Lokker | Brian.Lokker@VDOT.Virginia.gov | (804) 524-6010 | Brian J Lokker | Brian.Lokker@VDOT.Virginia.gov | (804) 524-6010 | Kenneth Horak | Kenneth.Horak@Richmondgov.com | (804) 646-4781 | 0 |  | 1 | FY2019 | 210000 | 210000 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 4 days early | G | Project is on budget | 2017-06-01 | 2018-01-04 | 2017-08-24 | 2018-02-07 | R | 2017-08-25 | 2018-02-16 | 2017-08-29 | 2018-02-22 | R | 2017-08-30 | 2018-02-23 | 2018-03-13 | 2018-03-12 | G | [35 empty] | 2018-04-25 | 2018-04-02 | 2018-06-29 | 2018-05-25 | G | 2018-07-02 | 2018-07-02 | 2018-08-10 | 2018-08-06 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.081887
791 | 112759 | Citywide Pedestrian Safety Improvements ??? Corridors | 0000 | Urban | Facilities for Pedestrians and Bicycles | Locally | Norfolk | NORFOLK | Hampton Roads | Hampton Roads:Norfolk | Infrastructure Investment Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Derrick Williams | Derrick.Williams@vdot.virginia.gov | (757) 956-3097 | L. Keith Darrow, P. E. | Keith.Darrow@norfolk.gov | (757) 664-7857 | 0 |  | 0 | FY2022 | 3000000 | 3000000 | ACTIVITY DATES SET | Y | Start Purchasing Right-of-Way milestone is 30 days ahead of the expected completion date and there is a risk of missing this milestone date | G | Project is on budget | 2018-06-04 | 2018-05-01 | 2018-08-27 | 2018-06-08 | G | 2018-08-28 | 2018-05-04 | 2018-09-11 | 2018-06-08 | G | 2018-09-12 | 2018-06-11 | 2019-09-12 | 2019-06-11 | G | [10 empty] | 2020-08-25 |  | 2021-03-23 |  | Y | [5 empty] | 2021-03-24 |  | 2021-03-24 |  | Y | [10 empty] | 2021-05-20 |  | 2021-07-01 |  | G | 2021-07-02 |  | 2021-12-27 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.24426
792 | 113829 | Primary Extension Paving - Victoria Blvd(eastbound) | 0143 | Urban | Resurfacing | Locally | Hampton | WILLIAMSBURG | Hampton Roads | Hampton Roads:Hampton | Local Assistance Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Derrick Williams | Derrick.Williams@vdot.virginia.gov | (757) 956-3097 | Sandon Rogers, L. S. P. E., | Sandon.rogers@hampton.gov | (757) 727-6786 | 0 |  | 1 | FY2019 | 325000 | 325000 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished on-time | G | Project is on budget | 2018-10-03 | 2018-10-03 | 2019-01-02 | 2019-01-17 | R | 2019-01-03 | 2019-01-15 | 2019-01-07 | 2019-01-17 | R | 2019-01-08 | 2018-07-11 | 2019-07-15 | 2019-01-17 | G | [25 empty] | 2018-05-14 | 2019-01-17 | 2019-01-17 | 2019-01-17 | G | [5 empty] | 2018-12-19 | 2018-12-19 | 2019-01-17 | 2019-01-17 | G | 2019-01-17 | 2019-01-17 | 2019-01-17 | 2019-01-17 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.089898
793 | 113916 | 10TH & GRADY AVENUE BIKE PED | 0250 | Urban | Safety | Locally | Charlottesville | CHARLOTTESVILLE | Culpeper | Charlottesville:Charlottesville | Infrastructure Investment Division | Ken Connors |  |  | Michael D Barnes | MichaelD.Barnes@vdot.virginia.gov | (434) 422-9861 | AMANDA PONCY | PONCY@CHARLOTTESVILLE.ORG | (434) 970-3720 | 0 |  | 0 | FY2026 | 291000 | 291000 | NO DATES SET YET | G | Agreement with Locality milestone is 677 days ahead of the expected completion date | G | Project is on budget | 2022-10-03 |  | 2022-12-30 |  | G | 2023-01-03 |  | 2023-01-05 |  | G | 2023-01-06 |  | 2023-07-13 |  | G | [10 empty] | 2024-07-16 |  | 2024-08-05 |  | G | [5 empty] | 2024-08-07 |  | 2025-05-20 |  | G | 2023-08-18 |  | 2024-04-25 |  | G | [5 empty] | 2025-06-06 |  | 2025-07-03 |  | G | 2025-09-23 |  | 2025-09-23 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.16766
794 | 115294 | #SGR20LP - PRIMARY EXT FY20 JOINT REPAIR & PANEL REPLACE | 0007 | Urban | Resurfacing | Locally | Alexandria | FAIRFAX | Northern Virginia | Northern Virginia:Alexandria | Local Assistance Division | Amir Salahshoor | A.Salahshoor@VDOT.Virginia.gov | (703) 259-1957 | Rita Hockman | Rita.Hockman@vdot.virginia.gov | (804) 824-7421 | Mary Alice Winston | maryalice.winston@alexandriava.gov | (703) 746-4067 | 0 |  | 1 | FY2020 | 420000 | 420000 | AWARDED | G | Start Delivery milestone finished 29 days early | G | Project is on budget | 2019-07-01 | 2019-07-01 | 2019-09-30 | 2019-10-03 | R | [5 empty] | 2019-10-01 | 2019-10-05 | 2019-10-31 | 2019-10-05 | G | [35 empty] | 2019-12-05 | 2019-12-30 | 2019-12-31 | 2019-12-30 | G | 2020-01-02 | 2020-01-30 | 2020-02-28 | 2020-01-30 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.19794
795 | 115380 | RTE 129 - (ID 5482) RESURFACING (NORTH MAIN STREET) | 0129 | Urban | Resurfacing | Locally | South Boston | HALIFAX | Lynchburg | NonMPO:NonMPO | Local Assistance Division | Gregg Allen | Gregg.Allen@vdot.virginia.gov | (434) 426-5575 | Sharon S White | Sharon.White@VDOT.Virginia.gov | (434) 856-8220 | C. W. CROWDER | ccrowder@souhtbostonva.us | (434) 575-4261 | 0 |  | 0 | FY2021 | 500000 | 500000 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 99 days early | Y | Estimate not current | 2020-01-31 | 2019-09-02 | 2020-04-24 | 2019-09-19 | G | [5 empty] | 2020-01-31 | 2020-01-31 | 2020-02-13 | 2020-02-13 | G | [35 empty] | 2020-05-12 | 2020-05-12 | 2020-06-09 | 2020-05-15 | G | 2020-08-27 | 2020-05-18 | 2020-08-27 | 2020-05-20 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.052395
796 | 115848 | #I81CIP SOUTH BOUND CURVE IMPROVEMENTS MM273 (ID #54) | 0081 | Interstate | Safety | VDOT | Shenandoah County | EDINBURG | Staunton | NonMPO:NonMPO | Infrastructure Investment Division | John-Allen L Ennis | JohnAllen.Ennis@VDOT.Virginia.gov | (540) 332-9118 | Michael L Surratt | Michael.Surratt@VDOT.Virginia.gov | (540) 332-9325 |  |  |  | 0 |  | 0 | FY2020 | 163000 | 163000 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished on-time | G | Project is on budget | [5 empty] | 2019-08-01 | 2019-08-01 | 2019-08-14 | 2019-08-05 | G | 2019-08-15 | 2019-08-05 | 2020-04-10 | 2019-08-05 | G | [5 empty] | 2019-08-06 | 2019-08-06 | 2019-08-06 | 2019-08-06 | G | [5 empty] | 2019-06-17 | 2019-06-17 | 2019-06-17 | 2019-06-17 | G | [15 empty] | 2019-08-27 | 2019-08-27 | 2019-08-27 | 2019-08-27 | G | 2019-09-13 | 2019-09-13 | 2019-09-13 | 2019-09-13 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.058877
797 | 117130 | Downtown Pedestrian Improvements |  | Urban | Facilities for Pedestrians and Bicycles | Locally | Newport News | WILLIAMSBURG | Hampton Roads | Hampton Roads:Newport News | Local Assistance Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Chessica Villaflores | Chessica.Villaflores@vdot.virginia.gov | (757) 956-3094 | Bridjette Parker | parkerbj1@nnva.gov | (757) 926-8314 | 0 |  | 0 | FY2024 | 250000 | 250000 | NO DATES SET YET | Y | Agreement with Locality milestone is 11 days ahead of the expected completion date and there is a risk of missing this milestone date | G | Project is on budget | 2020-10-20 |  | 2021-03-04 |  | Y | 2021-03-05 |  | 2021-03-25 |  | G | 2021-09-29 |  | 2022-01-28 |  | G | [25 empty] | 2023-01-25 |  | 2023-06-22 |  | G | [5 empty] | 2023-08-21 |  | 2023-09-18 |  | G | 2023-12-11 |  | 2023-12-11 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.20382
798 | 117771 | INSTALL GUARDRAIL UPGRADES - ROUTE 16 TAZWELL CO | 0016 | Primary | Safety | VDOT | Tazewell County | LEBANON | Bristol | NonMPO:NonMPO | Infrastructure Investment Division | Brian Holt | Brian.Holt@vdot.virginia.gov | (276) 696-3414 | Jeremy J Mullins | Jeremy.Mullins@vdot.virginia.gov | (276) 696-3259 |  |  |  | 0 |  | 0 | FY2023 | 100836 | 100836 | NO DATES SET YET-PE OPEN | G | Start Development milestone finished 7 days early | G | Project is on budget | [5 empty] | 2020-07-07 | 2020-07-07 | 2020-07-27 | 2020-07-20 | G | 2020-07-28 | 2020-07-21 | 2021-06-01 |  | G | [5 empty] | 2022-01-03 |  | 2022-02-01 |  | G | [5 empty] | 2022-09-21 |  | 2023-01-27 |  | G | [5 empty] | 2022-06-15 | 2020-07-16 | 2022-11-14 | 2020-07-16 | G | [5 empty] | 2023-02-14 |  | 2023-02-14 |  | G | 2023-05-04 |  | 2023-05-04 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | REGIONAL ON-CALL CONTRACT | 0 | 0 | 0.060921
799 | 118175 | #SGR21LP - Radford FKEY 1168 W Main St | 0000 | Urban | Resurfacing | Locally | Radford | CHRISTIANSBURG | Salem | NonMPO:NonMPO | Infrastructure Investment/Asset Management Division | Adam J Czesnowski | Adam.Czesnowski@vdot.virginia.gov | (540) 541-1216 | Adam J Czesnowski | Adam.Czesnowski@vdot.virginia.gov | (540) 541-1216 | Basil Edwards | basil.edwards@radfordva.gov | (540) 267-3168 | 0 |  | 1 | FY2024 | 170029 | 170029 | NO DATES SET YET | G | Agreement with Locality milestone is 50 days ahead of the expected completion date | G | Project is on budget | 2020-12-01 |  | 2021-04-12 |  | G | 2021-04-13 |  | 2021-05-03 |  | G | 2021-11-08 |  | 2022-03-09 |  | G | [25 empty] | 2023-03-06 |  | 2023-08-01 |  | G | [5 empty] | 2023-09-28 |  | 2023-10-26 |  | G | 2024-01-23 |  | 2024-01-23 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.066407
800 | 118289 | #SGR21VB(FED ID04400) BRDG SUP REPL RTE 207EB MATTAPONI RVR | 0207 | Primary | Bridge Rehab w/o Added Capacity | VDOT | Caroline County | FREDERICKSBURG | Fredericksburg | NonMPO:NonMPO | Infrastructure Investment/Asset Management Division | Annette F Adams | Annette.Adams@VDOT.Virginia.gov | (540) 372-3583 | Annette F Adams | Annette.Adams@VDOT.Virginia.gov | (540) 372-3583 |  |  |  | 0 |  | 0 | FY2027 | 7818804 | 7818804 | NO DATES SET YET | G | Start Development milestone is 982 days ahead of the expected completion date | G | Project is on budget | [5 empty] | 2023-10-10 |  | 2023-10-31 |  | G | 2023-11-01 |  | 2024-09-04 |  | G | [5 empty] | 2025-04-09 |  | 2025-05-06 |  | G | 2025-12-29 |  | 2026-02-04 |  | G | 2026-07-06 |  | 2026-11-03 |  | G | 2026-02-20 |  | 2026-07-20 |  | G | 2026-03-19 |  | 2026-08-14 |  | G | [5 empty] | 2026-11-10 |  | 2026-11-10 |  | G | 2027-02-05 |  | 2027-02-05 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.15042
801 | 98813 | #SGR17VB - BR RT 189 (Southquay Road) over BlackWater River | 0189 | Primary | Bridge Replacement w/o Added Capacity | VDOT | Multi-jurisdictional: Hampton Roads MPO |  | Hampton Roads | Hampton Roads:Multi-jurisdictional: Hampton Roads MPO | Infrastructure Investment/Asset Management Division | Mohamed A Ali | Mohamed.Ali@VDOT.Virginia.gov | (757) 956-3206 | Andrew B Scott | Andrew.Scott@VDOT.Virginia.gov | (757) 956-3273 |  |  |  | 0 |  | 1 | FY2021 | 24448260 | 19477554 | CONSTRUCTION STARTED | R | Start Delivery milestone finished 34 days late | G | Project is on budget | [5 empty] | 2011-06-06 | 2011-06-04 | 2011-07-04 | 2011-06-30 | G | 2011-06-01 | 2011-06-01 | 2016-09-30 | 2016-09-30 | G | [5 empty] | 2017-02-06 | 2017-02-06 | 2017-03-30 | 2017-03-30 | G | 2018-07-06 | 2018-05-09 | 2018-08-02 | 2018-05-17 | G | 2019-05-28 | 2018-12-03 | 2020-03-27 | 2020-04-03 | R | 2018-10-31 | 2018-06-20 | 2019-05-10 | 2019-05-09 | G | 2019-04-10 | 2018-11-26 | 2020-04-09 | 2019-10-21 | G | [5 empty] | 2020-08-11 | 2020-08-11 | 2020-08-11 | 2020-08-11 | G | 2020-08-12 | 2020-12-09 | 2020-11-05 | 2020-12-09 | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.13697
802 | 104809 | Rural Rustic Paving Project (Rattlesnake Trail) | 0646 | Secondary | Resurfacing | Locally | Isle of Wight County | FRANKLIN | Hampton Roads | Hampton Roads:Isle of Wight County | Infrastructure Investment Division | Charles T Catlett | Tommy.Catlett@vdot.virginia.gov | (757) 346-3078 | Sherry L Parker | Sherry.Parker@vdot.virginia.gov | (757) 346-3080 | Jamie Oliver | joliver@isleofwightus.net | (757) 365-7653 | 0 |  | 0 | FY2023 | 906818 | 906818 | NO DATES SET YET | G | Agreement with Locality milestone is 73 days ahead of the expected completion date | G | Project is on budget | 2021-02-10 |  | 2021-05-05 |  | G | 2021-05-06 |  | 2021-05-10 |  | G | 2021-05-11 |  | 2021-11-15 |  | G | [25 empty] | 2021-12-23 |  | 2022-08-26 |  | G | [5 empty] | 2022-12-06 |  | 2023-01-04 |  | G | 2023-03-28 |  | 2023-03-28 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.19341
803 | 107096 | INSTALL CENTERLINE RUMBLE STRIPS - PRIMARY - DISTRICTWIDE | 9999 | Primary | Safety | VDOT | Fredericksburg District-wide |  | Fredericksburg | Fredericksburg:Fredericksburg District-wide | Infrastructure Investment Division | Sylvester C Okpala | Sylvester.Okpala@VDOT.Virginia.gov | (540) 907-8174 | Sylvester C Okpala | Sylvester.Okpala@VDOT.Virginia.gov | (540) 907-8174 |  |  |  | 0 |  | 0 | FY2019 | 700000 | 974484 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 32 days early | R | Project estimate is less than $5M and is 20% or more over budget | [5 empty] | 2017-10-13 | 2017-08-29 | 2017-10-27 | 2017-08-29 | G | 2017-10-30 | 2017-10-24 | 2017-11-29 | 2017-11-17 | G | [35 empty] | 2018-05-08 | 2018-05-08 | 2018-05-08 | 2018-05-08 | G | 2018-06-22 | 2018-07-16 | 2018-08-17 | 2018-07-16 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.067503
805 | 111021 | #SMART18 - Granby Street Bike Lanes | 0460 | Urban | Other | Locally | Norfolk | NORFOLK | Hampton Roads | Hampton Roads:Norfolk | Infrastructure Investment Division | Todd M Halacy | Todd.Halacy@VDOT.Virginia.gov | (757) 956-3010 | Derrick Williams | Derrick.Williams@vdot.virginia.gov | (757) 956-3097 | Deborah A. Mangiaracina, PE | deborah.mangiaracina@norfolk.gov | (757) 664-7459 | 1 | 2018 | 0 | FY2025 | 822000 | 822000 | NO DATES SET YET | R | Agreement with Locality milestone is 194 days past the expected completion date | G | Project is on budget | 2020-05-18 |  | 2020-08-11 |  | R | 2020-08-12 |  | 2020-08-17 |  | R | 2020-08-18 |  | 2021-03-01 |  | Y | [25 empty] | 2024-01-24 |  | 2024-06-20 |  | G | [5 empty] | 2024-08-19 |  | 2024-09-16 |  | G | 2024-12-09 |  | 2024-12-09 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.2754
806 | 111404 | FREEMAN STORE PEDESTRIAN BRIDGE |  | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Vienna | FAIRFAX | Northern Virginia | Northern Virginia:Vienna | Local Assistance Division | Bud Siegel |  |  | Saif-Ur Qargha | Saif.Qargha@vdot.virginia.gov | (703) 259-3223 | Town of Vienna |  |  | 0 |  | 0 | FY2022 | 148940 | 171115 | ACTIVITY DATES SET | G | Determine Requirements milestone finished 19 days early | Y | Project estimate is less than $5M and is up to 20% over budget | 2017-10-02 | 2017-10-02 | 2017-11-06 | 2017-11-06 | G | 2017-11-07 | 2017-11-07 | 2017-11-30 | 2017-11-30 | G | 2018-10-01 | 2018-09-13 | 2019-07-22 | 2019-07-03 | G | [35 empty] | 2020-08-26 |  | 2021-05-18 |  | G | 2021-05-19 |  | 2021-11-23 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.31812
808 | 112923 | I-64 Express Lanes- Segment 2 | 0064 | Interstate | Traffic Management/Engineering | VDOT | Multi-jurisdictional: Hampton Roads MPO |  | Hampton Roads | Hampton Roads:Multi-jurisdictional: Hampton Roads MPO | Infrastructure Investment Division | Salvija Hofheimer | Salvija.Hofheimer@vdot.virginia.gov | (757) 956-3082 | Salvija Hofheimer | Salvija.Hofheimer@vdot.virginia.gov | (757) 956-3082 |  |  |  | 0 |  | 0 | FY2021 | 25000000 | 25000000 | CONSTRUCTION STARTED | R | Start Delivery milestone finished 44 days late | G | Project is on budget | [5 empty] | 2018-07-02 | 2018-07-02 | 2018-07-16 | 2018-07-11 | G | 2018-07-17 | 2018-07-12 | 2019-08-02 | 2019-12-11 | R | [5 empty] | 2019-12-12 | 2020-01-03 | 2020-01-03 | 2020-01-08 | R | [15 empty] | 2018-12-04 | 2018-12-04 | 2019-09-05 | 2019-09-05 | G | [5 empty] | 2020-04-14 | 2020-06-23 | 2020-04-14 | 2020-06-23 | R | 2020-08-03 | 2020-09-16 | 2020-08-03 | 2020-09-16 | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NOT APPLICABLE | 1 | 1 | 0.33871
809 | 113295 | Hey Road Improvements |  | Primary | Reconstruction w/o Added Capacity | Locally | Richmond | ASHLAND | Richmond | Richmond:Richmond | Local Assistance Division | Olena Fecek | Olena.Fecek@vdot.virginia.gov | (804) 524-6368 | Olena Fecek | Olena.Fecek@vdot.virginia.gov | (804) 524-6368 | Winston Phillips | Winston.Phillips@Richmondgov.com | (804) 646-5994 | 0 |  | 0 | FY2022 | 8150000 | 8150000 | NO DATES SET YET | R | Start Development milestone is 746 days past the expected completion date | G | Project is on budget | 2018-07-02 | 2018-07-10 | 2019-01-15 | 2018-07-10 | G | 2019-01-16 |  | 2019-02-06 |  | R | 2019-02-11 |  | 2019-08-13 |  | R | [10 empty] | 2020-10-20 |  | 2020-11-09 |  | R | [5 empty] | 2020-11-12 |  | 2021-08-24 |  | G | 2019-07-01 | 2020-04-27 | 2020-03-09 |  | R | [5 empty] | 2021-09-10 |  | 2021-10-07 |  | G | 2022-01-03 |  | 2022-02-04 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.22449
810 | 93091 | RTE 715 - BRIDGE REHABILITATION (Bridge Only) | 0715 | Secondary | Bridge Replacement w/o Added Capacity | VDOT | Brunswick County | SOUTH HILL | Richmond | NonMPO:NonMPO | Infrastructure Investment Division | Clayton M Thomas | Clay.Thomas@VDOT.Virginia.gov | (804) 609-5429 | Clayton M Thomas | Clay.Thomas@VDOT.Virginia.gov | (804) 609-5429 |  |  |  | 0 |  | 0 | FY2021 | 4000140 | 4000140 | ACTIVITY DATES SET | R | Solicit Bids milestone is 103 days past the expected completion date | G | Project is on budget | [5 empty] | 2012-09-01 | 2012-09-01 | 2012-09-11 | 2012-09-11 | G | 2017-02-17 | 2017-02-17 | 2017-09-08 | 2017-09-08 | G | [5 empty] | 2018-12-14 | 2018-12-11 | 2019-01-03 | 2018-12-17 | G | 2019-08-23 | 2019-08-09 | 2019-09-06 | 2019-08-22 | G | 2020-05-05 | 2020-03-18 | 2020-11-06 | 2020-03-18 | G | 2019-09-23 | 2019-09-10 | 2020-04-02 | 2020-02-14 | G | 2019-07-09 | 2018-11-19 | 2020-06-22 | 2020-07-28 | R | [5 empty] | 2020-11-10 |  | 2020-11-10 |  | R | 2021-01-06 |  | 2021-04-02 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.076797
811 | 104177 | #SGR18VB - RT 33 over I-81 Exit 247 Impr EBL; STR No. 20443 | 0033 | Primary | Reconstruction w/o Added Capacity | VDOT | Rockingham County | HARRISONBURG | Staunton | Harrisonburg:Rockingham County | Infrastructure Investment/Asset Management Division | Rex L Pearce | Rex.Pearce@vdot.virginia.gov | (540) 332-9104 | John-Allen L Ennis | JohnAllen.Ennis@VDOT.Virginia.gov | (540) 332-9118 |  |  |  | 0 |  | 1 | FY2023 | 12900164 | 16546425 | ACTIVITY DATES SET | R | Start Purchasing Right-of-Way milestone is 27 days past the expected completion date | R | Project estimate is greater than $10M and is over budget by (a) 10% or more or (b) $5M or more | [5 empty] | 2014-05-15 | 2014-01-02 | 2014-05-15 | 2014-01-07 | G | 2015-11-02 | 2014-01-02 | 2018-11-30 | 2019-10-18 | R | [5 empty] | 2019-12-24 | 2019-12-24 | 2020-04-07 | 2020-03-26 | G | 2021-01-08 |  | 2021-01-25 |  | R | 2021-10-12 |  | 2022-10-11 |  | G | 2021-02-09 |  | 2021-10-11 |  | G | [10 empty] | 2022-10-06 |  | 2022-11-08 |  | G | 2022-11-09 |  | 2023-06-15 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.11929
812 | 107039 | Campostella Bridge Rehabilitation | 0168 | Urban | Bridge Rehab w/o Added Capacity | Locally | Norfolk | NORFOLK | Hampton Roads | Hampton Roads:Norfolk | Infrastructure Investment Division | Stephen Rowan | Steve.Rowan@vdot.virginia.gov | (757) 790-9925 | Derrick Williams | Derrick.Williams@vdot.virginia.gov | (757) 956-3097 | Deborah Mangiaracina, P.E. | deborah.mangiaracina@norfolk.gov | (757) 664-7459 | 0 |  | 0 | FY2023 | 7590000 | 7590000 | NO DATES SET YET | R | Start Development milestone is 25 days past the expected completion date | G | Project is on budget | [5 empty] | 2021-01-12 |  | 2021-01-27 |  | R | 2021-01-28 |  | 2022-01-28 |  | G | [35 empty] | 2022-10-25 |  | 2022-12-08 |  | G | 2023-01-26 |  | 2023-04-20 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.41566
813 | 108873 | Bike Ped Improvement on Garbers Church Rd w/ Park Connection | 4119 | Urban | Facilities for Pedestrians and Bicycles | Locally | Harrisonburg | HARRISONBURG | Staunton | Harrisonburg:Harrisonburg | Local Assistance Division | Michael S Fulcher | Michael.Fulcher@VDOT.Virginia.gov | (540) 332-2243 | Michael S Fulcher | Michael.Fulcher@VDOT.Virginia.gov | (540) 332-2243 | Tom Hartman |  | (540) 434-5928 | 0 |  | 0 | FY2022 | 4200000 | 5941400 | ADVERTISED | G | Solicit Bids milestone finished 307 days early | R | Project estimate is less than $5M and is 20% or more over budget | 2016-07-29 | 2016-07-29 | 2016-08-24 | 2016-08-24 | G | 2016-08-25 | 2016-08-25 | 2016-12-14 | 2016-12-14 | G | 2016-12-15 | 2016-12-15 | 2018-07-24 | 2018-07-24 | G | [10 empty] | 2020-03-26 | 2019-12-01 | 2020-05-06 | 2019-12-31 | G | [5 empty] | 2020-05-08 | 2020-06-30 | 2021-08-25 | 2020-12-30 | G | [10 empty] | 2021-10-11 | 2020-12-07 | 2021-11-08 | 2021-01-05 | G | 2021-11-09 |  | 2022-03-24 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.08851
814 | 110318 | RTE 729 - Grade,Drain,Stabilize and SurfaceTreat unpaved Rd | 0729 | Secondary | Resurfacing | VDOT | Pulaski County | CHRISTIANSBURG | Salem | NonMPO:NonMPO | Infrastructure Investment Division | Christopher L Price | Christopher.Price@VDOT.Virginia.gov | (540) 381-7182 | Marvin D Mann | M.Mann@VDOT.Virginia.gov | (540) 378-5055 |  |  |  | 0 |  | 0 | FY2019 | 742000 | 550000 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 69 days early | G | Project is on budget | [5 empty] | 2018-08-31 | 2017-04-10 | 2018-09-14 | 2017-04-10 | G | 2018-09-17 | 2017-04-11 | 2019-08-14 | 2017-04-24 | G | [5 empty] | 2017-09-20 | 2017-09-20 | 2017-09-20 | 2017-09-20 | G | 2017-10-11 | 2017-10-11 | 2017-10-11 | 2017-10-11 | G | 2017-08-16 | 2016-08-16 | 2017-08-16 | 2016-08-16 | G | 2017-10-11 | 2017-10-11 | 2017-10-11 | 2017-10-11 | G | [10 empty] | 2018-03-13 | 2018-02-27 | 2018-03-13 | 2018-02-27 | G | 2018-05-02 | 2018-04-27 | 2018-07-05 | 2018-04-27 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | SAAP CONTRACT | 1 | 0 | 0.07211
815 | 111363 | #SMART18 - Virginia Ave Pedestrian Safety Accommodation | 0220 | Primary | Facilities for Pedestrians and Bicycles | VDOT | Henry County | MARTINSVILLE | Salem | NonMPO:NonMPO | Infrastructure Investment Division | Alex H Price | Alex.Price@VDOT.Virginia.gov | (540) 378-5053 | Elias Mannon | Eli.Mannon@vdot.virginia.gov | (540) 387-5370 | Lee Clark | leclark@co.henry.va.us | (276) 634-4620 | 1 | 2018 | 0 | FY2022 | 639915 | 724141 | ACTIVITY DATES SET | G | Start Purchasing Right-of-Way milestone finished 74 days early | Y | Project estimate is less than $5M and is up to 20% over budget | [5 empty] | 2017-08-02 | 2017-06-22 | 2017-08-15 | 2017-06-27 | G | 2017-08-16 | 2017-06-28 | 2018-02-27 | 2018-02-26 | G | [5 empty] | 2019-07-17 | 2019-07-06 | 2019-07-30 | 2019-07-11 | G | 2020-11-03 | 2020-08-04 | 2020-11-17 | 2020-09-04 | G | 2021-04-16 |  | 2021-10-20 |  | G | 2020-12-07 | 2020-10-09 | 2021-06-14 |  | G | 2020-04-23 | 2020-06-17 | 2020-10-27 | 2020-06-17 | G | [5 empty] | 2021-11-09 |  | 2021-11-09 |  | G | 2021-12-29 |  | 2022-02-28 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.095347
816 | 111448 | #SGR18LB - REPLACE DECK AND SUPER. & REPAIR SUB. (29731 Fed) | 0000 | Miscellaneous | Bridge Rehab w/o Added Capacity | Locally | Buchanan County | LEBANON | Bristol | NonMPO:NonMPO | Infrastructure Investment Division | John W Bechtold | John.Bechtold@vdot.virginia.gov | (276) 696-3365 | Roger L Musser | Roger.Musser@VDOT.Virginia.gov | (276) 696-3260 | Marcus Stiltner | marcus.stiltner@buchanancounty-va.gov | (276) 935-4013 | 0 |  | 1 | FY2021 | 170000 | 170000 | ACTIVITY DATES SET | Y | Solicit Bids milestone is 24 days ahead of the expected completion date and there is a risk of missing this milestone date | G | Project is on budget | 2019-07-01 | 2018-02-01 | 2019-09-24 | 2018-04-02 | G | 2019-09-25 | 2018-04-03 | 2019-09-27 | 2018-04-05 | G | 2019-09-30 | 2018-04-06 | 2020-04-09 | 2020-04-07 | G | [35 empty] | 2021-02-17 |  | 2021-03-17 |  | Y | 2021-03-18 |  | 2021-04-27 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.10043
817 | 112027 | RTE 154 EAST RIVERSID STREET - FY18 PRIMARY EXT | 0154 | Urban | Restoration and Rehabilitation | Locally | Covington | LEXINGTON | Staunton | NonMPO:NonMPO | Local Assistance Division | Michael L Branscome | Michael.Branscome@VDOT.Virginia.gov | (540) 332-2377 | Michael L Branscome | Michael.Branscome@VDOT.Virginia.gov | (540) 332-2377 | City of Covington | adressler@covington.va.us | (540) 965-6300 | 0 |  | 0 | FY2019 | 180500 | 180500 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 47 days early | Y | Estimate not current | 2018-11-30 | 2018-11-20 | 2019-02-28 | 2018-11-26 | G | 2019-03-01 | 2018-11-26 | 2019-03-05 | 2018-11-26 | G | 2019-03-06 | 2018-11-20 | 2019-09-06 | 2018-12-06 | G | [35 empty] | 2018-12-24 | 2018-12-10 | 2019-01-24 | 2019-01-23 | G | 2019-04-15 | 2019-01-25 | 2019-04-15 | 2019-02-27 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.085306
818 | 113247 | PHASE I - BUS 58 - RECONSTRUCTION (AUDUBON TO ARNETT) | 0058 | Urban | Reconstruction w/o Added Capacity | Locally | Danville | HALIFAX | Lynchburg | Danville:Danville | Local Assistance Division | Sharon S White | Sharon.White@VDOT.Virginia.gov | (434) 856-8220 | Sharon S White | Sharon.White@VDOT.Virginia.gov | (434) 856-8220 | Brian Dunevant, P.E. | dunevbl@danville.va.gov | (434) 799-5019 | 0 |  | 0 | FY2021 | 1052628 | 1052628 | AWARDED | G | Start Delivery milestone finished 1 days early | G | Project is on budget | 2019-01-31 | 2018-11-05 | 2019-04-25 | 2018-11-05 | G | 2019-04-26 | 2018-11-06 | 2019-04-30 | 2018-11-08 | G | 2019-05-01 | 2018-11-09 | 2019-11-04 | 2020-06-17 | R | [10 empty] | 2020-06-17 | 2020-06-17 | 2020-06-17 | 2020-06-17 | G | [5 empty] | 2020-06-18 | 2020-06-18 | 2020-06-18 | 2020-06-18 | G | [10 empty] | 2020-08-04 | 2020-08-04 | 2020-08-31 | 2020-08-31 | G | 2020-12-30 | 2020-12-29 | 2020-12-30 | 2020-12-29 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.070783
819 | 113375 | #SGR19VB - REPLACE SUPERSTRUCTURE BROAD STREET OVER I-95 | 0250 | Primary | Bridge Rehab w/o Added Capacity | VDOT | Richmond | ASHLAND | Richmond | Richmond:Richmond | Infrastructure Investment/Asset Management Division | Anthony S Haverly | Anthony.Haverly@vdot.virginia.gov | (804) 609-5225 | Anthony S Haverly | Anthony.Haverly@vdot.virginia.gov | (804) 609-5225 |  |  |  | 0 |  | 0 | FY2022 | 9556190 | 9556190 | NO DATES SET YET-PE OPEN | G | Start Development milestone finished on-time | G | Project is on budget | [5 empty] | 2018-08-16 | 2018-08-16 | 2018-08-23 | 2018-08-23 | G | 2018-08-24 | 2019-12-23 | 2021-06-30 |  | G | [10 empty] | 2021-06-25 |  | 2021-07-16 |  | G | [20 empty] | 2021-07-19 |  | 2021-08-16 |  | G | 2022-02-16 |  | 2022-03-16 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | DESIGN BUILD/PPTA | 0 | 0 | 0.12003
820 | 113511 | FKEY 538 BUS 29 - RESURFACING (WARDS ROAD) | 7029 | Urban | Resurfacing | Locally | Lynchburg | APPOMATTOX | Lynchburg | Lynchburg:Lynchburg | Local Assistance Division | Gregg Allen | Gregg.Allen@vdot.virginia.gov | (434) 426-5575 | Gregg Allen | Gregg.Allen@vdot.virginia.gov | (434) 426-5575 | LEE NEWLAND | lee.newland@lynchburgva.gov | (434) 455-3947 | 0 |  | 0 | FY2020 | 315489 | 315489 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 7 days early | G | Project is on budget | 2019-01-31 | 2019-01-31 | 2019-04-25 | 2019-04-24 | G | [5 empty] | 2019-01-31 | 2019-01-31 | 2019-02-13 | 2019-02-13 | G | [35 empty] | 2019-05-13 | 2019-05-07 | 2019-06-10 | 2019-06-04 | G | 2019-08-28 | 2019-08-21 | 2019-08-28 | 2019-08-21 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.07552
821 | 114378 | Cove Road & Dansbury Drive Drainage Improvements | 0000 | Urban | Mitigation of Water Pollution Due to Highway Runof | Locally | Roanoke | SALEM | Salem | Roanoke:Roanoke City | Local Assistance Division | Cheryl B Becker | Cheryl.Becker@vdot.virginia.gov | (540) 492-2531 | Cheryl B Becker | Cheryl.Becker@vdot.virginia.gov | (540) 492-2531 | Joseph Arthur | Joseph.Arthur@roanokeva.gov | (540) 853-5901 | 0 |  | 0 | FY2021 | 775130 | 840130 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 607 days early | Y | Project estimate is less than $5M and is up to 20% over budget | 2018-10-01 | 2018-10-01 | 2018-12-28 | 2018-11-27 | G | 2018-12-31 | 2018-11-28 | 2019-01-03 | 2018-11-28 | G | 2019-01-04 | 2018-11-26 | 2019-07-11 | 2018-11-30 | G | [25 empty] | 2019-01-07 | 2019-01-07 | 2019-09-09 | 2019-01-08 | G | [5 empty] | 2020-05-21 | 2018-11-01 | 2020-06-18 | 2018-12-03 | G | 2020-09-08 | 2018-12-04 | 2020-09-08 | 2019-01-10 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.20558
822 | 115138 | #SMART20 Traffic Signal Improvements, Valley and Gerrard St. |  | Urban | Safety | Locally | Winchester | EDINBURG | Staunton | Winchester:Winchester | Infrastructure Investment Division | Randolph S Kiser | Randy.Kiser@VDOT.Virginia.gov | (540) 332-9092 | Kimberly Cameron | Kim.Cameron@vdot.virginia.gov | (540) 332-7886 | Winchester City | perry.eisenach@winchesterva.gov | (540) 667-1815 | 1 | 2020 | 0 | FY2026 | 1227000 | 1227000 | NO DATES SET YET | G | Agreement with Locality milestone is 976 days ahead of the expected completion date | G | Project is on budget | 2023-08-01 |  | 2023-10-25 |  | G | 2023-10-26 |  | 2023-10-30 |  | G | 2023-10-31 |  | 2024-05-09 |  | G | [25 empty] | 2024-05-10 |  | 2025-01-15 |  | G | [5 empty] | 2025-03-24 |  | 2025-04-18 |  | G | 2025-07-09 |  | 2025-07-09 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.12772
823 | 115366 | City of Hampton 366 Fox Hill Rd - Paving | 0169 | Urban | Restoration and Rehabilitation | Locally | Hampton | WILLIAMSBURG | Hampton Roads | Hampton Roads:Hampton | Local Assistance Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Joshua D Negovan | Joshua.Negovan@vdot.virginia.gov | (757) 956-3347 | Angela Rico | angela.rico@hampton.gov | (757) 209-1245 | 0 |  | 0 | FY2020 |  |  | WAITING FINANCIAL CLOSURE | G | Solicit Bids milestone finished 104 days early | R | Critical information missing | 2019-10-03 | 2019-10-03 | 2020-01-02 | 2019-11-06 | G | [5 empty] | 2019-10-03 | 2019-10-03 | 2019-10-16 | 2019-10-16 | G | [35 empty] | 2020-01-22 | 2019-10-10 | 2020-02-19 | 2019-11-07 | G | 2020-05-07 | 2019-08-19 | 2020-05-07 | 2019-08-19 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.10864
824 | 115525 | #SMART20 Seaboard Coastline Trail Segment 1 |  | Urban | Facilities for Pedestrians and Bicycles | Locally | Suffolk | NORFOLK | Hampton Roads | Hampton Roads:Suffolk | Infrastructure Investment Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Johndel A Alcaide | John.Alcaide@vdot.virginia.gov | (757) 956-3098 | Sherry Earley | searly@suffolkva.us | (757) 514-7700 | 1 | 2020 | 0 | FY2026 | 4223089 | 4223089 | NO DATES SET YET | G | Agreement with Locality milestone is 884 days ahead of the expected completion date | Y | Estimate not current | 2023-05-01 |  | 2023-07-25 |  | G | 2023-07-26 |  | 2023-07-28 |  | G | 2023-07-31 |  | 2024-02-08 |  | G | [10 empty] | 2025-02-11 |  | 2025-03-04 |  | G | [5 empty] | 2025-03-06 |  | 2025-12-12 |  | G | 2024-03-18 |  | 2024-11-15 |  | G | [5 empty] | 2025-12-31 |  | 2026-01-30 |  | G | 2026-04-21 |  | 2026-04-21 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.16801
825 | 115757 | Curve Advisory Sign Installation | 9999 | Miscellaneous | Safety | VDOT | Hampton Roads District-wide |  | Hampton Roads | Hampton Roads:Hampton Roads District-wide | Infrastructure Investment Division | Charles Dixon | Charles.Dixon@VDOT.Virginia.gov | (757) 925-1679 | Jesse Alan Williams | Alan.Williams@vdot.virginia.gov | (757) 925-1574 |  |  |  | 0 |  | 0 | FY2020 | 550000 | 550000 | CONSTRUCTION STARTED | G | Start Delivery milestone finished on-time | G | Project is on budget | [10 empty] | 2019-08-20 | 2019-09-16 | 2019-12-31 | 2019-12-09 | G | [35 empty] | 2020-01-13 | 2020-01-13 | 2020-01-21 | 2020-01-21 | G | 2020-01-22 | 2020-01-22 | 2020-01-28 | 2020-01-28 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | WORK/TASK ORDER | 1 | 0 | 0.097841
826 | 117091 | #REVSH21 BUS 58 - PEDESTRIAN IMPROVEMENTS AT PINEY FOREST RD | 0058 | Urban | Facilities for Pedestrians and Bicycles | Locally | Danville | HALIFAX | Lynchburg | Danville:Danville | Local Assistance Division | Gregg Allen | Gregg.Allen@vdot.virginia.gov | (434) 426-5575 | Gregg Allen | Gregg.Allen@vdot.virginia.gov | (434) 426-5575 | BRIAN DUNEVANT | dunevbl@danvilleva.gov | (434) 799-5019 | 0 |  | 0 | FY2025 | 280400 | 280400 | NO DATES SET YET | G | Agreement with Locality milestone is 106 days ahead of the expected completion date | G | Project is on budget | 2021-01-29 |  | 2021-06-07 |  | G | 2021-06-08 |  | 2021-06-28 |  | G | 2022-01-07 |  | 2022-05-03 |  | G | [10 empty] | 2023-08-22 |  | 2023-09-26 |  | G | [5 empty] | 2023-09-27 |  | 2024-03-04 |  | G | 2024-01-30 |  | 2024-06-26 |  | G | [5 empty] | 2024-06-05 |  | 2024-07-02 |  | G | 2024-09-20 |  | 2024-09-20 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.073178
827 | 98960 | Br. Replacement Rte 921 over N.F. Shenand Fed ID 16239 | 0921 | Secondary | Bridge Replacement w/ Added Capacity | VDOT | Rockingham County | HARRISONBURG | Staunton | NonMPO:NonMPO | Infrastructure Investment Division | Eulogio A Javier | Eulogio.Javier@VDOT.Virginia.gov | (540) 332-9105 | Amedebrhan Asfaw | Amedebrhan.Asfaw@vdot.virginia.gov | (540) 332-9541 |  |  |  | 0 |  | 0 | FY2019 | 1749070 | 2678265 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 54 days early | R | Project estimate is less than $5M and is 20% or more over budget | [5 empty] | 2012-07-02 | 2012-07-02 | 2012-07-02 | 2012-07-02 | G | 2012-09-25 | 2012-09-20 | 2012-12-01 | 2012-12-01 | G | [10 empty] | 2018-04-25 | 2018-04-25 | 2018-05-08 | 2018-05-08 | G | [5 empty] | 2018-05-09 | 2018-05-09 | 2018-09-25 | 2018-09-19 | G | 2017-06-21 | 2017-06-21 | 2018-06-15 | 2018-06-04 | G | [5 empty] | 2018-08-01 | 2018-08-01 | 2018-11-06 | 2018-11-06 | G | 2019-01-17 | 2019-01-17 | 2019-03-18 | 2019-01-23 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.062913
828 | 106961 | INT IMP. / UPGRADE SIGNAL AND LTLS @ INT. RTES.3 AND 20 | 0003 | Primary | Safety | VDOT | Orange County | WARRENTON | Culpeper | NonMPO:NonMPO | Infrastructure Investment Division | Dewitt D Sprinkel | Brent.Sprinkel@VDOT.Virginia.gov | (540) 829-7552 | Caroline Awua-Mensah | Caroline.Awua-Mensah@vdot.virginia.gov | (540) 829-7618 |  |  |  | 0 |  | 0 | FY2021 | 506426 | 474242 | WAITING FINANCIAL CLOSURE | G | Solicit Bids milestone finished 894 days early | G | Project is on budget | [5 empty] | 2017-07-03 | 2017-06-30 | 2017-07-17 | 2017-07-12 | G | 2017-07-18 | 2017-07-13 | 2018-08-10 | 2017-10-27 | G | [5 empty] | 2018-12-05 | 2018-07-30 | 2018-12-18 | 2018-08-10 | G | 2020-05-07 | 2018-08-15 | 2020-05-20 | 2018-08-15 | G | 2020-08-04 | 2018-08-15 | 2020-09-15 | 2018-08-15 | G | 2020-06-05 | 2018-08-15 | 2020-06-05 | 2018-08-15 | G | [10 empty] | 2021-01-26 | 2018-08-16 | 2021-01-26 | 2018-08-16 | G | 2021-03-11 | 2018-08-17 | 2021-03-31 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | WORK/TASK ORDER | 0 | 0 | 0.080413
829 | 107517 | Rte. 42 Bicycle / Pedestrian / Buggy Lanes |  | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Rockingham County | HARRISONBURG | Staunton | Harrisonburg:Rockingham County | Local Assistance Division | Michael S Fulcher | Michael.Fulcher@VDOT.Virginia.gov | (540) 332-2243 | Michael S Fulcher | Michael.Fulcher@VDOT.Virginia.gov | (540) 332-2243 | Stephen King | sking@rockinghamcountyva.gov | (540) 564-3015 | 0 |  | 0 | FY2020 | 500000 | 533928 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 138 days early | Y | Project estimate is less than $5M and is up to 20% over budget | 2015-10-01 | 2015-10-01 | 2015-11-02 | 2015-11-02 | G | 2015-11-03 | 2015-11-03 | 2017-11-21 | 2017-11-21 | G | 2017-11-22 | 2017-11-22 | 2018-09-11 | 2018-09-11 | G | [10 empty] | 2019-08-01 | 2019-05-17 | 2019-08-14 | 2019-05-31 | G | [20 empty] | 2019-10-15 | 2019-09-09 | 2020-02-13 | 2019-10-09 | G | 2020-02-14 | 2020-01-02 | 2020-06-22 | 2020-02-05 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.26739
830 | 113717 | RTE 614 - RURAL RUSTIC SURFACE TREAT NON-HARDSURFACE ROAD | 0614 | Secondary | Reconstruction w/o Added Capacity | VDOT | Rappahannock County | WARRENTON | Culpeper | NonMPO:NonMPO | Infrastructure Investment Division | Ken Connors |  |  | Benjamin Davison | Ben.Davison@vdot.virginia.gov | (540) 347-6446 |  |  |  | 0 |  | 0 | FY2023 | 137750 | 137750 | NO DATES SET YET-PE OPEN | G | Start Development milestone finished 41 days early | G | Project is on budget | [5 empty] | 2020-10-01 | 2020-08-21 | 2020-10-14 | 2020-09-03 | G | 2020-10-15 | 2020-09-04 | 2021-06-11 |  | G | [5 empty] | 2022-02-22 |  | 2022-04-04 |  | G | [5 empty] | 2022-07-19 |  | 2022-11-09 |  | G | [5 empty] | 2022-07-01 |  | 2022-10-03 |  | G | [5 empty] | 2022-12-13 |  | 2022-12-13 |  | G | 2023-03-09 |  | 2023-03-09 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | SAAP CONTRACT | 0 | 0 | 0.10327
831 | 114718 | SIGNALIZED CROSSWALKS AT RT 1 BETWEEN MILLS DR AND RT 17 | 0001 | Primary | Safety | VDOT | Spotsylvania County | FREDERICKSBURG | Fredericksburg | Fredericksburg:Spotsylvania County | Infrastructure Investment Division | Wesley Foor | Wesley.Foor@vdot.virginia.gov | (540) 604-1370 | Benjamin Ernst | Benjamin.Ernst@vdot.virginia.gov | (571) 585-0902 |  |  |  | 0 |  | 0 | FY2021 | 200000 | 281396 | AWARDED | G | Start Delivery milestone finished 250 days early | R | Project estimate is less than $5M and is 20% or more over budget | [5 empty] | 2019-01-07 | 2019-02-13 | 2019-01-07 | 2019-02-13 | R | 2019-01-08 | 2019-02-14 | 2019-04-18 | 2019-03-26 | G | [5 empty] | 2020-06-26 | 2019-11-13 | 2020-09-04 | 2019-11-13 | G | [25 empty] | 2020-09-23 | 2020-01-29 | 2020-09-29 | 2020-01-29 | G | 2020-09-30 | 2020-01-30 | 2020-10-06 | 2020-01-30 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | WORK/TASK ORDER | 1 | 0 | 0.062878
832 | 115248 | #SGR20LP - US HWY 1 (Boulevard) Resurfacing |  | Primary | Resurfacing | Locally | Colonial Heights | CHESTERFIELD | Richmond | Tri-Cities:Colonial Heights | Local Assistance Division | Brian J Lokker | Brian.Lokker@VDOT.Virginia.gov | (804) 524-6010 | Brian J Lokker | Brian.Lokker@VDOT.Virginia.gov | (804) 524-6010 | Keith Chisolm | chisolmk@colonialheightsva.gov | (804) 520-9215 | 0 |  | 1 | FY2020 | 993273 | 993273 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 90 days early | G | Project is on budget | 2019-07-01 | 2019-04-16 | 2019-09-24 | 2019-07-25 | G | [5 empty] | 2019-09-25 | 2019-07-26 | 2019-11-27 | 2019-11-19 | G | [35 empty] | 2019-11-19 | 2019-11-19 | 2019-11-19 | 2019-11-19 | G | 2020-01-02 | 2019-10-02 | 2020-03-30 | 2019-12-31 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.10708
833 | 115407 | #SMART20 - Route 600/ Route 601 Roundabout | 0600 | Secondary | Safety | VDOT | Dinwiddie County | PETERSBURG | Richmond | Tri-Cities:Dinwiddie County | Infrastructure Investment Division | William Wheeler | William.Wheeler@vdot.virginia.gov | (804) 609-5280 | William Wheeler | William.Wheeler@vdot.virginia.gov | (804) 609-5280 | Mark Bassett |  |  | 1 | 2020 | 0 | FY2028 | 3700000 | 3700000 | NO DATES SET YET-PE OPEN | G | Start Development milestone finished 1138 days early | G | Project is on budget | [5 empty] | 2023-09-01 | 2020-07-21 | 2023-09-15 | 2020-08-03 | G | 2023-09-18 | 2020-08-04 | 2024-08-14 |  | G | [5 empty] | 2025-06-20 |  | 2025-07-03 |  | G | 2026-10-08 |  | 2026-10-22 |  | G | 2027-03-24 |  | 2027-09-24 |  | G | 2026-11-09 |  | 2027-05-19 |  | G | 2026-03-31 |  | 2026-10-01 |  | G | [5 empty] | 2027-10-12 |  | 2027-10-12 |  | G | 2028-01-07 |  | 2028-01-07 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.093289
834 | 115633 | #SMART20 KILMARNOCK RIGHT TURN LANE | 0003 | Primary | Reconstruction w/ Added Capacity | VDOT | Lancaster County | NORTHERN NECK | Fredericksburg | NonMPO:NonMPO | Infrastructure Investment Division | Catherine C Coffey | Catherine.Coffey@vdot.virginia.gov | (540) 899-4280 | Anastasia Kapitan | Anastasia.Kapitan@vdot.virginia.gov | (540) 899-4292 |  |  |  | 1 | 2020 | 0 | FY2028 | 1100000 | 1100000 | NO DATES SET YET | G | Start Development milestone is 918 days ahead of the expected completion date | G | Project is on budget | [5 empty] | 2023-08-15 |  | 2023-08-28 |  | G | 2023-08-29 |  | 2024-07-26 |  | G | [5 empty] | 2025-06-03 |  | 2025-06-16 |  | G | 2026-09-21 |  | 2026-10-02 |  | G | 2027-03-05 |  | 2027-09-07 |  | G | 2026-10-21 |  | 2027-04-30 |  | G | 2026-03-12 |  | 2026-09-14 |  | G | [5 empty] | 2027-09-14 |  | 2027-09-14 |  | G | 2027-12-08 |  | 2027-12-08 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.080511
835 | 116857 | ROUTE 800 PEDESTRIAN ACCESS IMROVEMENTS |  | Enhancement | Facilities for Pedestrians and Bicycles | VDOT | Timberville | HARRISONBURG | Staunton | NonMPO:NonMPO | Local Assistance Division | John-Allen L Ennis | JohnAllen.Ennis@VDOT.Virginia.gov | (540) 332-9118 | Ronald L Tabor | Ronald.Tabor@vdot.virginia.gov | (540) 332-7887 |  |  |  | 0 |  | 0 | FY2024 | 385945 | 385945 | NO DATES SET YET-PE OPEN | G | Start Development milestone finished on-time | G | Project is on budget | [5 empty] | 2020-12-29 | 2020-12-29 | 2021-01-21 | 2021-01-21 | G | 2021-01-22 |  | 2021-11-19 |  | G | [5 empty] | 2022-06-23 |  | 2022-07-21 |  | G | 2023-03-17 |  | 2023-04-20 |  | G | 2023-09-19 |  | 2024-01-25 |  | G | 2023-05-05 |  | 2023-10-03 |  | G | 2023-06-14 |  | 2023-11-13 |  | G | [5 empty] | 2024-02-13 |  | 2024-02-13 |  | G | 2024-05-02 |  | 2024-05-02 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 1 | 0.23541
836 | 97688 | RTE 155 - SHARED-USE PATH | 0155 | Primary | Safety | VDOT | Charles City County | ASHLAND | Richmond | Richmond:Charles City County | Infrastructure Investment Division | Lawrence Ramsey | Brian.Ramsey@VDOT.Virginia.gov | (804) 585-3579 | Lawrence Ramsey | Brian.Ramsey@VDOT.Virginia.gov | (804) 585-3579 |  |  |  | 0 |  | 0 | FY2020 | 1962000 | 1962000 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 18 days early | G | Project is on budget | [5 empty] | 2011-06-01 | 2011-05-10 | 2011-06-30 | 2011-05-10 | G | 2016-04-11 | 2016-04-11 | 2017-05-26 | 2017-05-26 | G | [5 empty] | 2017-09-08 | 2017-09-08 | 2017-12-18 | 2017-12-18 | G | 2018-06-20 | 2018-07-09 | 2018-07-18 | 2018-07-25 | R | 2019-02-25 | 2019-05-15 | 2019-08-21 | 2019-10-07 | R | 2018-08-10 | 2018-09-27 | 2019-02-14 | 2019-03-05 | R | 2018-06-06 | 2018-07-27 | 2019-01-04 | 2018-12-17 | G | [5 empty] | 2019-10-08 | 2019-10-08 | 2019-10-08 | 2019-10-08 | G | 2019-12-03 | 2020-01-20 | 2020-02-07 | 2020-01-20 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.06413
837 | 105677 | RTE 1 - IMPROVE INTERSECTION | 0001 | Urban | Reconstruction w/o Added Capacity | Locally | Ashland | ASHLAND | Richmond | Richmond:Ashland | Infrastructure Investment Division | Scott D Gagnon | Scott.Gagnon@VDOT.Virginia.gov | (804) 286-3124 | Brian J Lokker | Brian.Lokker@VDOT.Virginia.gov | (804) 524-6010 | Ingrid Stenbjorn | istenbjorn@town.ashland.va.us | (804) 798-9219 | 0 |  | 0 | FY2019 | 700000 | 950000 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 923 days early | R | Project estimate is less than $5M and is 20% or more over budget | 2014-09-30 | 2014-09-09 | 2014-09-30 | 2014-09-09 | G | 2014-11-01 | 2014-10-15 | 2014-11-01 | 2014-10-15 | G | 2014-12-31 | 2014-12-09 | 2015-04-01 | 2014-12-19 | G | [10 empty] | 2016-11-01 | 2015-12-26 | 2016-11-01 | 2015-12-26 | G | [20 empty] | 2018-07-01 | 2015-12-27 | 2018-07-01 | 2015-12-27 | G | 2018-07-15 | 2016-02-03 | 2018-08-14 | 2016-02-03 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.11658
838 | 107262 | Rural Area Drainage Improvements | 0000 | Urban | Other | Locally | Suffolk | NORFOLK | Hampton Roads | Hampton Roads:Suffolk | Local Assistance Division | Stephen Rowan | Steve.Rowan@vdot.virginia.gov | (757) 790-9925 | Johndel A Alcaide | John.Alcaide@vdot.virginia.gov | (757) 956-3098 | Robert Lewis | relewis@suffolkva.us | (757) 514-7621 | 0 |  | 0 | FY2019 | 1000000 | 1000000 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 112 days early | G | Project is on budget | 2015-05-18 | 2015-05-18 | 2015-08-11 | 2015-08-11 | G | 2016-04-27 | 2016-04-27 | 2016-05-03 | 2016-05-03 | G | 2016-05-04 | 2016-05-04 | 2018-08-01 | 2018-07-17 | G | [10 empty] | 2018-10-09 | 2018-09-13 | 2018-10-11 | 2018-09-17 | G | [20 empty] | 2019-02-21 | 2018-12-28 | 2019-02-21 | 2018-12-28 | G | 2019-02-22 | 2018-12-31 | 2019-06-14 | 2019-02-22 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.11743
839 | 108502 | ROUTE 50 AND WOODLAWN AVENUE INTERSECTION | 0050 | Primary | Safety | Locally | Fairfax County | FAIRFAX | Northern Virginia | Northern Virginia:Fairfax County | Infrastructure Investment Division | Amir Salahshoor | A.Salahshoor@VDOT.Virginia.gov | (703) 259-1957 | Rita Hockman | Rita.Hockman@vdot.virginia.gov | (804) 824-7421 | Jeanmarie Roberson | jeanmarie.roberson@fairfaxcoun | (703) 877-5740 | 0 |  | 0 | FY2020 | 1175001 | 1475000 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 756 days early | R | Project estimate is less than $5M and is 20% or more over budget | 2015-03-06 | 2015-03-06 | 2015-05-29 | 2015-05-29 | G | 2015-06-01 | 2015-06-01 | 2015-06-03 | 2015-06-03 | G | 2015-06-04 | 2015-12-11 | 2015-12-10 | 2015-12-11 | R | [10 empty] | 2016-10-03 | 2016-10-03 | 2016-10-24 | 2016-10-24 | G | [5 empty] | 2016-10-26 | 2016-10-26 | 2019-11-14 | 2017-05-23 | G | [10 empty] | 2019-12-04 | 2017-09-06 | 2020-01-02 | 2017-09-06 | G | 2020-01-03 | 2017-09-07 | 2020-02-14 | 2018-01-19 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.077087
840 | 108675 | Rural Addition - Tomahawk Way- Warren County | 0000 | Secondary | Reconstruction w/o Added Capacity | Locally | Warren County | EDINBURG | Staunton | NonMPO:NonMPO | Local Assistance Division | Kimberly Cameron | Kim.Cameron@vdot.virginia.gov | (540) 332-7886 | Kimberly Cameron | Kim.Cameron@vdot.virginia.gov | (540) 332-7886 | Douglas P. Stanley | edaley@warrencountyva.net | (540) 636-4600 | 0 |  | 0 | FY2020 | 280000 | 280000 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 217 days early | G | Project is on budget | 2016-10-26 | 2016-10-26 | 2016-10-26 | 2016-10-26 | G | 2016-10-27 | 2016-10-27 | 2016-10-31 | 2016-10-31 | G | 2016-11-01 | 2016-11-01 | 2018-07-18 | 2018-07-18 | G | [35 empty] | 2019-05-30 | 2019-05-30 | 2019-10-04 | 2019-07-03 | G | 2019-10-07 | 2019-07-08 | 2020-04-02 | 2019-08-29 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.20475
841 | 108984 | #SGR18LB - Speights Spillway Bridge Replacement | 0000 | Urban | Bridge Replacement w/o Added Capacity | Locally | Suffolk | NORFOLK | Hampton Roads | Hampton Roads:Suffolk | Infrastructure Investment Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Johndel A Alcaide | John.Alcaide@vdot.virginia.gov | (757) 956-3098 | LJ Hansen | lhansen@suffolkva.us | (757) 514-7687 | 0 |  | 1 | FY2025 | 2128000 | 2128000 | NO DATES SET YET-PE OPEN | G | Start Development milestone finished 538 days early | G | Project is on budget | 2020-08-03 | 2017-10-26 | 2020-10-27 | 2018-01-26 | G | 2020-10-28 | 2018-01-29 | 2020-11-10 | 2019-05-22 | G | 2020-11-12 |  | 2021-11-10 |  | G | [10 empty] | 2023-03-21 |  | 2023-04-10 |  | G | [5 empty] | 2023-04-12 |  | 2024-08-05 |  | G | 2021-06-29 |  | 2022-03-08 |  | G | [5 empty] | 2024-08-21 |  | 2024-09-18 |  | G | 2024-09-19 |  | 2025-03-18 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.11281
842 | 109378 | #HB2.FY17 Route 33 Rawley Pike Roadway Improvements | 0033 | Primary | Safety | VDOT | Rockingham County | HARRISONBURG | Staunton | NonMPO:NonMPO | Infrastructure Investment Division | John-Allen L Ennis | JohnAllen.Ennis@VDOT.Virginia.gov | (540) 332-9118 | Ronald L Tabor | Ronald.Tabor@vdot.virginia.gov | (540) 332-7887 |  |  |  | 1 | 2017 | 0 | FY2021 | 9366944 | 9366943 | ACTIVITY DATES SET | R | Complete Purchasing Right-of-Way milestone is 279 days past the expected completion date | G | Project is on budget | [5 empty] | 2016-10-03 | 2016-10-03 | 2016-10-17 | 2016-10-17 | G | 2016-10-18 | 2016-10-18 | 2019-09-16 | 2018-01-31 | G | [5 empty] | 2018-07-19 | 2018-07-19 | 2018-08-15 | 2018-08-14 | G | 2019-09-10 | 2020-04-30 | 2019-09-23 | 2020-05-05 | R | 2019-08-13 | 2019-08-12 | 2019-08-13 | 2019-08-12 | G | 2019-10-09 | 2020-05-05 | 2020-05-18 |  | R | 2017-03-21 | 2017-03-21 | 2017-03-22 | 2017-03-22 | G | [5 empty] | 2020-09-08 |  | 2020-09-08 |  | R | 2020-10-22 |  | 2020-12-30 |  | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.074841
843 | 110626 | RTE 1208 - PEDESTRIAN IMPROVEMENT (GREATE ROAD) | 1208 | Urban | Facilities for Pedestrians and Bicycles | VDOT | Gloucester County | SALUDA | Fredericksburg | Hampton Roads:Gloucester County | Infrastructure Investment Division | Khalil Minhas | Khalil.Minhas@vdot.virginia.gov | (540) 374-3369 | Khalil Minhas | Khalil.Minhas@vdot.virginia.gov | (540) 374-3369 | Brian D. Lewis, P.E. | blewis@gloucesterva.info | (804) 693-5480 | 0 |  | 0 | FY2027 | 2390140 | 2390140 | NO DATES SET YET-PE OPEN | G | Start Development milestone finished 892 days early | G | Project is on budget | [5 empty] | 2022-04-01 | 2019-10-29 | 2022-04-14 | 2019-11-04 | G | 2022-04-15 |  | 2023-03-15 |  | G | [5 empty] | 2024-01-19 |  | 2024-02-01 |  | G | 2025-05-07 |  | 2025-05-20 |  | G | 2025-10-13 |  | 2026-04-23 |  | G | 2025-06-06 |  | 2025-12-12 |  | G | 2024-10-18 |  | 2025-04-30 |  | G | [5 empty] | 2026-05-12 |  | 2026-05-12 |  | G | 2026-07-02 |  | 2026-07-23 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.096979
845 | 111162 | GREENE ES SIDEWALKS |  | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Richmond | ASHLAND | Richmond | Richmond:Richmond | Local Assistance Division | Jorg Huckabee-Mayfield | Jorg.Huckabee-Mayfield@VDOT.Virginia.gov | (804) 609-5292 | Jorg Huckabee-Mayfield | Jorg.Huckabee-Mayfield@VDOT.Virginia.gov | (804) 609-5292 | Ishoc Salaam | ishoc.salaam@richmondgov.com | (804) 646-6319 | 0 |  | 0 | FY2022 | 380000 | 380000 | ACTIVITY DATES SET | G | Obtained Permits milestone finished 116 days early | G | Project is on budget | 2017-10-02 | 2017-10-02 | 2017-12-29 | 2019-06-26 | R | 2018-01-02 | 2018-07-16 | 2018-01-04 | 2018-07-25 | R | 2018-01-05 | 2019-06-27 | 2018-07-12 | 2020-06-03 | R | [25 empty] | 2020-03-27 | 2020-08-20 | 2020-12-14 | 2020-08-20 | G | [5 empty] | 2021-02-24 |  | 2021-04-24 |  | G | 2021-02-25 |  | 2021-09-21 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.35217
846 | 111394 | N. Main Street Roundabout Sidewalk Extension | 0015 | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Culpeper | WARRENTON | Culpeper | NonMPO:NonMPO | Local Assistance Division | Kimberly Cameron | Kim.Cameron@vdot.virginia.gov | (540) 332-7886 | John P Price | John.Price@VDOT.Virginia.gov | (540) 347-6371 | Salem Bush | SBush@culpeperva.gov | (540) 829-8260 | 0 |  | 0 | FY2020 | 596884 | 405720 | ADVERTISED | R | Start Delivery milestone is 276 days past the expected completion date | G | Project is on budget | 2017-10-24 | 2017-10-24 | 2017-10-24 | 2017-10-24 | G | 2017-11-14 | 2017-11-14 | 2017-11-14 | 2017-11-14 | G | 2017-11-14 | 2018-10-01 | 2019-01-31 | 2019-05-02 | R | [35 empty] | 2020-03-16 | 2020-05-19 | 2020-04-10 | 2020-07-09 | R | 2020-04-13 |  | 2020-05-21 |  | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.35865
847 | 111703 | #SMART18 - US360 Hull St Streetscape, 9th St - Mayo Bridge | 0360 | Urban | Safety | Locally | Richmond | ASHLAND | Richmond | Richmond:Richmond | Infrastructure Investment Division | Olena Fecek | Olena.Fecek@vdot.virginia.gov | (804) 524-6368 | Olena Fecek | Olena.Fecek@vdot.virginia.gov | (804) 524-6368 | Winston Phillips | winston.phillips@richmondgov.com | 6465994 | 1 | 2018 | 0 | FY2021 | 4060829 | 4060794 | NO DATES SET YET-PE OPEN | R | Determine Requirements milestone is 318 days past the expected completion date | G | Project is on budget | 2019-07-01 | 2019-02-21 | 2019-09-24 | 2020-01-30 | R | 2019-09-25 | 2020-01-31 | 2021-09-30 | 2020-02-24 | G | 2019-09-30 | 2020-02-25 | 2020-04-09 |  | R | [25 empty] | 2022-11-08 |  | 2023-08-31 |  | G | [5 empty] | 2021-02-19 |  | 2021-03-19 |  | Y | 2021-03-22 |  | 2021-04-29 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.13296
848 | 112489 | COLTS NECK RD & GLADE DR SIGNAL IMPROVEMENTS | 4701 | Secondary | Safety | VDOT | Fairfax County | FAIRFAX | Northern Virginia | Northern Virginia:Fairfax County | Infrastructure Investment Division | Ivan M Horodyskyj | Ivan.Horodyskyj@VDOT.Virginia.gov | (703) 259-2330 | Jessica Paris | Jessica.Paris@vdot.virginia.gov | (703) 259-2409 |  |  |  | 0 |  | 0 | FY2020 | 602317 | 602317 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 199 days early | G | Project is on budget | [5 empty] | 2019-02-01 | 2018-09-06 | 2019-02-14 | 2018-09-19 | G | 2019-02-15 | 2018-09-20 | 2020-01-13 | 2019-04-23 | G | [5 empty] | 2018-09-20 | 2018-09-20 | 2018-12-04 | 2018-12-04 | G | 2019-05-16 | 2019-04-24 | 2019-05-16 | 2019-04-24 | G | 2019-04-24 | 2019-04-24 | 2019-04-24 | 2019-04-24 | G | 2019-05-17 | 2019-04-24 | 2019-05-17 | 2019-04-24 | G | [10 empty] | 2019-07-09 | 2019-05-31 | 2019-11-12 | 2019-06-11 | G | 2019-12-20 | 2019-06-11 | 2019-12-27 | 2019-06-11 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | WORK/TASK ORDER | 1 | 0 | 0.082478
849 | 112813 | RTE 621 BALLS FORD ROAD WIDEN TO 4 LANES | 0621 | Secondary | Reconstruction w/ Added Capacity | Locally | Prince William County | MANASSAS | Northern Virginia | Northern Virginia:Prince William County | Infrastructure Investment Division | Claudia H Llana | Claudia.Llana@VDOT.Virginia.gov | (703) 259-1768 | Jeffrey S Daily | Jeff.Daily@VDOT.Virginia.gov | (703) 259-2993 | Mary Ankers | mankers@pwcgov.org | (703) 792-4228 | 0 |  | 0 | FY2024 | 67405000 | 49214854 | ACTIVITY DATES SET | G | Determine Requirements milestone finished on-time | Y | Estimate not current | 2018-04-02 | 2018-04-02 | 2018-05-07 | 2018-05-07 | G | 2018-05-08 | 2018-05-08 | 2018-05-14 | 2018-05-14 | G | 2018-05-15 | 2018-05-15 | 2019-11-27 | 2019-11-27 | G | [10 empty] | 2021-12-23 | 2020-01-08 | 2022-02-23 |  | G | [5 empty] | 2022-02-25 |  | 2023-02-28 |  | G | [10 empty] | 2023-03-03 |  | 2023-07-27 |  | G | 2023-07-28 |  | 2024-01-31 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.32088
850 | 108756 | CHARLOTTESVILLE / NEW BICYCLE PROJECTS IN VARIOUS LOCATIONS | 0000 | Urban | Safety | Locally | Charlottesville | CHARLOTTESVILLE | Culpeper | Charlottesville:Charlottesville | Local Assistance Division | Ken Connors |  |  | Michael D Barnes | MichaelD.Barnes@vdot.virginia.gov | (434) 422-9861 | Chris Gensic | gensic@charlottesville.org | (434) 970-3656 | 0 |  | 0 | FY2019 | 200000 | 200000 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished on-time | G | Project is on budget | 2017-02-15 | 2017-02-10 | 2017-05-10 | 2017-05-10 | G | 2017-05-11 | 2017-05-11 | 2017-05-15 | 2017-05-15 | G | 2017-05-16 | 2017-05-16 | 2017-11-20 | 2018-05-31 | R | [35 empty] | 2018-06-01 | 2018-06-01 | 2018-06-20 | 2018-06-20 | G | 2018-07-10 | 2018-07-10 | 2018-09-28 | 2018-09-28 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.14391
851 | 109296 | #HB2.FY17 BROADBAND LINK FOR EISENHOWER AVENUE | 6588 | Urban | Traffic Management/Engineering | Locally | Alexandria | FAIRFAX | Northern Virginia | Northern Virginia:Alexandria | Infrastructure Investment Division | Amir Salahshoor | A.Salahshoor@VDOT.Virginia.gov | (703) 259-1957 | Robert J Strevell | Robert.Strevell@vdot.virginia.gov | (703) 259-1988 | Daphne Kott | Daphne.Kott@alexandriava.gov | (703) 746-4055 | 1 | 2017 | 0 | FY2019 | 1000000 | 975926 | NO DATES SET YET-PE OPEN | R | Determine Requirements milestone is 1083 days past the expected completion date | G | Project is on budget | 2016-11-30 | 2016-11-30 | 2017-02-28 | 2017-03-20 | R | 2017-03-01 | 2016-09-06 | 2017-03-03 | 2016-09-08 | G | 2017-03-06 | 2017-06-29 | 2018-03-06 |  | R | [35 empty] | 2019-01-14 |  | 2019-02-12 |  | R | 2019-02-13 |  | 2019-03-26 |  | R | Consultant contract is still in procurement | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.31489
852 | 109519 | #HB2.FY17 INTERSECTION IMPROVEMENT @ RTE 33/29 RUCKERSVILLE | 0033 | Primary | Reconstruction w/ Added Capacity | VDOT | Greene County | CHARLOTTESVILLE | Culpeper | NonMPO:NonMPO | Infrastructure Investment Division | Gregory J Cooley | Gregory.Cooley@vdot.virginia.gov | (434) 906-7979 | John Rose | John.Rose1@vdot.virginia.gov | (540) 829-7429 |  |  |  | 1 | 2017 | 0 | FY2022 | 10100000 | 10100000 | ACTIVITY DATES SET | R | Obtained Permits milestone is 397 days past the expected completion date | G | Project is on budget | [5 empty] | 2016-07-19 | 2016-07-19 | 2016-08-01 | 2016-08-01 | G | 2016-08-25 | 2016-08-25 | 2017-06-29 | 2017-06-23 | G | [5 empty] | 2018-05-10 | 2018-07-18 | 2018-05-23 | 2018-07-18 | R | 2019-07-31 | 2019-10-30 | 2019-08-13 | 2019-10-30 | R | 2020-08-28 | 2021-01-26 | 2021-03-11 |  | Y | 2019-08-29 |  | 2021-08-24 |  | G | 2019-01-17 |  | 2020-01-21 |  | R | [5 empty] | 2021-11-09 |  | 2021-11-09 |  | G | 2022-01-05 |  | 2022-02-17 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.16964
853 | 110841 | SYSTEMIC PEDESTAL TO MAST ARM SIGNAL IMPROVEMENTS - URBAN |  | Urban | Safety | Locally | Richmond | ASHLAND | Richmond | Richmond:Richmond | Infrastructure Investment Division | Evan Austin | Evan.Austin@vdot.virginia.gov | (804) 609-5384 | Evan Austin | Evan.Austin@vdot.virginia.gov | (804) 609-5384 | Sandra Christian | Sandra.christian@richmondgov.com | (804) 646-3777 | 0 |  | 0 | FY2022 | 1310000 | 1309931 | ACTIVITY DATES SET | R | Solicit Bids milestone is 20 days past the expected completion date | G | Project is on budget | 2019-07-01 | 2019-02-21 | 2019-09-24 | 2019-07-10 | G | 2019-09-25 | 2019-07-17 | 2019-09-27 | 2019-07-23 | G | 2019-09-30 | 2019-10-24 | 2020-04-09 | 2020-02-04 | G | [25 empty] | 2020-08-11 | 2020-08-20 | 2020-11-30 | 2020-08-20 | G | [5 empty] | 2021-01-04 |  | 2021-02-01 |  | R | 2021-02-02 |  | 2021-07-01 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.12704
854 | 111055 | #SMART18 - (St) I-81 EXIT 235 ACCESS IMPROVEMENTS | 0256 | Primary | Reconstruction w/o Added Capacity | VDOT | Augusta County | HARRISONBURG | Staunton | SAW:Augusta County | Infrastructure Investment Division | Matthew P Dana | Matt.Dana@VDOT.Virginia.gov | (540) 332-7786 | Jethro Dienner | Jet.Dienner@vdot.virginia.gov | (540) 332-9290 |  |  |  | 1 | 2018 | 0 | FY2021 | 1787244 | 1787243 | ACTIVITY DATES SET | Y | Relocate Utilities milestone is 10 days ahead of the expected completion date and there is a risk of missing this milestone date | G | Project is on budget | [5 empty] | 2017-08-03 | 2017-07-17 | 2017-08-16 | 2017-07-26 | G | 2017-08-17 | 2017-07-27 | 2018-07-17 | 2018-07-17 | G | [5 empty] | 2019-03-06 | 2019-03-06 | 2019-03-19 | 2019-06-13 | R | 2020-03-17 | 2020-03-16 | 2020-03-30 | 2020-03-27 | G | 2020-08-20 |  | 2021-03-03 |  | Y | 2020-04-15 | 2020-04-14 | 2020-10-16 | 2020-10-16 | G | 2019-09-25 | 2019-09-26 | 2020-04-06 | 2019-09-26 | G | [5 empty] | 2021-03-09 |  | 2021-03-09 |  | Y | 2021-04-22 |  | 2021-06-17 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.089984
855 | 111267 | #SGR18LB - SUPERSTRUCTURE REPLACE BENGES BRANCH (22441 FED.) | 0000 | Urban | Bridge Rehab w/o Added Capacity | Locally | Norton | WISE | Bristol | NonMPO:NonMPO | Infrastructure Investment Division | Tabitha H Crowder | Tabitha.Crowder@vdot.virginia.gov | (276) 696-3482 | Kenneth R Plummer | KR.Plummer@VDOT.Virginia.gov | (276) 696-3261 | Fred Ramey | fredr@nortonva.org | (276) 679-1160 | 0 |  | 1 | FY2022 | 316000 | 316000 | NO DATES SET YET-PE OPEN | G | Start Development milestone finished on-time | G | Project is on budget | 2020-07-01 | 2018-02-05 | 2020-09-24 | 2018-02-05 | G | 2020-09-25 | 2020-09-25 | 2020-09-29 | 2020-09-29 | G | 2020-09-30 | 2020-09-30 | 2021-04-12 |  | G | [35 empty] | 2022-02-23 |  | 2022-03-22 |  | G | 2022-03-23 |  | 2022-05-02 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.16625
856 | 111539 | FALLS CHURCH PRIMARY EXTENSION PAVING FY18 - W. BROAD ST | 0007 | Urban | Resurfacing | Locally | Falls Church | FAIRFAX | Northern Virginia | Northern Virginia:Falls Church | Local Assistance Division | Amir Salahshoor | A.Salahshoor@VDOT.Virginia.gov | (703) 259-1957 | Rita Hockman | Rita.Hockman@vdot.virginia.gov | (804) 824-7421 | TBD |  |  | 0 |  | 0 | FY2019 |  |  | WAITING FINANCIAL CLOSURE | R | Determine Requirements milestone finished 148 days late | R | Critical information missing | 2017-07-03 | 2017-07-03 | 2017-10-25 | 2017-07-24 | G | [5 empty] | 2017-07-03 | 2017-11-09 | 2017-07-17 | 2017-12-12 | R | [35 empty] | 2017-12-13 | 2017-12-07 | 2018-06-29 | 2017-12-07 | G | 2018-07-02 | 2017-12-07 | 2018-08-10 | 2017-12-07 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.36524
858 | 112715 | Route 600 and Route 601 - Intersection improvement | 0600 | Secondary | Reconstruction w/o Added Capacity | VDOT | Dinwiddie County | PETERSBURG | Richmond | Tri-Cities:Dinwiddie County | Infrastructure Investment Division | Dianna M Bryant | Dianna.Bryant@VDOT.Virginia.gov | (804) 863-4004 | Dianna M Bryant | Dianna.Bryant@VDOT.Virginia.gov | (804) 863-4004 |  |  |  | 0 |  | 0 | FY2030 | 3550000 | 3550000 | NO DATES SET YET | G | Start Development milestone is 1524 days ahead of the expected completion date | Y | Estimate not current | [5 empty] | 2025-04-14 |  | 2025-04-25 |  | G | 2025-04-28 |  | 2026-03-26 |  | G | [5 empty] | 2027-02-01 |  | 2027-02-12 |  | G | 2028-05-18 |  | 2028-06-01 |  | G | 2028-10-25 |  | 2029-05-04 |  | G | 2028-06-19 |  | 2028-12-26 |  | G | 2027-11-02 |  | 2028-05-11 |  | G | [5 empty] | 2029-05-08 |  | 2029-05-08 |  | G | 2029-06-22 |  | 2029-08-17 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.12438
859 | 112937 | Extend Grace Street to Carrier Drive | 4109 | Urban | New Construction Roadway | Locally | Harrisonburg | HARRISONBURG | Staunton | Harrisonburg:Harrisonburg | Local Assistance Division | Michael S Fulcher | Michael.Fulcher@VDOT.Virginia.gov | (540) 332-2243 | Michael S Fulcher | Michael.Fulcher@VDOT.Virginia.gov | (540) 332-2243 | Aaron Rhoney | Aaron.Rhoney@harrisonburgva.gov | (540) 434-5928 | 0 |  | 0 | FY2020 | 2875000 | 2875000 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 246 days early | G | Project is on budget | 2018-10-31 | 2018-10-07 | 2019-01-31 | 2018-11-07 | G | [5 empty] | 2018-10-31 | 2018-11-01 | 2019-04-12 | 2018-11-15 | G | [35 empty] | 2018-12-04 | 2018-11-19 | 2019-06-10 | 2018-12-19 | G | 2019-08-28 | 2019-01-25 | 2019-10-09 | 2019-02-05 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.086054
860 | 112981 | SHANNON HILLS DRIVE - MILLING, PAVING & RECONSTRUCTION | 9999 | Urban | Resurfacing | Locally | Orange | LOUISA | Culpeper | NonMPO:NonMPO | Local Assistance Division | Ken Connors |  |  | John P Price | John.Price@VDOT.Virginia.gov | (540) 347-6371 | JOHN COOLEY | townplanner@townoforangeva.org | (540) 672-6917 | 0 |  | 0 | FY2019 | 42472 | 42472 | WAITING FINANCIAL CLOSURE | G | Obtained Permits milestone finished on-time | G | Project is on budget | 2020-02-24 | 2018-06-01 | 2020-05-15 | 2018-07-09 | G | [5 empty] | 2020-02-24 | 2018-11-01 | 2020-03-06 | 2018-11-30 | G | [25 empty] | 2019-07-18 | 2019-07-18 | 2019-07-19 | 2019-07-19 | G | [5 empty] | 2018-12-06 | 2018-12-06 | 2019-01-15 | 2019-01-15 | G | 2019-01-16 | 2019-01-16 | 2019-02-01 | 2019-02-01 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.047874
861 | 114665 | ELECTRIC VEHICLE CHARGING STATIONS - PURCHASE & INSTALL | 9999 | Urban | Other | Locally | Fairfax | FAIRFAX | Northern Virginia | Northern Virginia:Fairfax | Infrastructure Investment Division | Amir Salahshoor | A.Salahshoor@VDOT.Virginia.gov | (703) 259-1957 | Rita Hockman | Rita.Hockman@vdot.virginia.gov | (804) 824-7421 | Wendy Sanford | Wendy.Sanford@fairfaxva.gov | (703) 385-7889 | 0 |  | 0 | FY2022 | 45000 | 44977 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 594 days early | G | Project is on budget | 2019-01-30 | 2018-09-01 | 2019-04-24 | 2019-01-07 | G | 2019-04-25 | 2019-01-03 | 2019-06-06 | 2019-01-23 | G | 2019-06-07 | 2019-01-24 | 2019-12-13 | 2019-07-29 | G | [25 empty] | 2020-04-28 | 2019-12-17 | 2021-03-30 | 2019-12-17 | G | [5 empty] | 2021-04-14 | 2019-10-20 | 2021-08-05 | 2020-03-20 | G | 2021-08-06 | 2020-03-31 | 2021-12-02 | 2020-04-17 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.28751
862 | 115361 | City of Hampton 333 Armistead Ave N - Paving | 0134 | Urban | Restoration and Rehabilitation | Locally | Hampton | WILLIAMSBURG | Hampton Roads | Hampton Roads:Hampton | Infrastructure Investment/Asset Management Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Joshua D Negovan | Joshua.Negovan@vdot.virginia.gov | (757) 956-3347 | Sandon Rogers, L. S., P.E. | sandon.rogers@hampton.gov | (757) 727-6786 | 0 |  | 0 | FY2020 | 76000 | 76000 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 93 days early | G | Project is on budget | 2019-10-03 | 2019-10-03 | 2020-01-02 | 2019-11-06 | G | [5 empty] | 2019-10-03 | 2019-10-03 | 2019-10-16 | 2019-11-06 | R | [35 empty] | 2020-01-22 | 2019-10-10 | 2020-02-19 | 2019-11-07 | G | 2020-05-07 | 2020-02-04 | 2020-05-07 | 2020-02-04 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.10351
863 | 117041 | Thalbro Street/ Maywill Street Sidewalk | 9999 | Secondary | Facilities for Pedestrians and Bicycles | Locally | Henrico County | ASHLAND | Richmond | Richmond:Henrico County | Local Assistance Division | Cynthia Crouch | Cynthia.Crouch@vdot.virginia.gov | (804) 609-5313 | Cynthia Crouch | Cynthia.Crouch@vdot.virginia.gov | (804) 609-5313 | TBD |  | TBD | 0 |  | 0 | FY2029 | 782700 | 782700 | NO DATES SET YET | G | Agreement with Locality milestone is 1543 days ahead of the expected completion date | G | Project is on budget | 2025-01-06 |  | 2025-05-14 |  | G | 2025-05-15 |  | 2025-06-05 |  | G | 2025-12-15 |  | 2026-04-10 |  | G | [10 empty] | 2027-07-30 |  | 2027-09-02 |  | G | [5 empty] | 2027-09-03 |  | 2028-02-09 |  | G | 2028-01-05 |  | 2028-06-05 |  | G | [5 empty] | 2028-05-12 |  | 2028-06-09 |  | G | 2028-08-29 |  | 2028-08-29 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.34905
864 | 117215 | FY 21 Edgeline Rumblestrips | 9999 | Primary | Safety | VDOT | Salem District-wide |  | Salem | Roanoke:Salem District-wide | Infrastructure Investment/Asset Management Division | Bernard S Grinnell | Sean.Grinnell@VDOT.Virginia.gov | (540) 375-0148 | Jason W Knight | Jay.Knight@vdot.virginia.gov | (540) 375-0152 | N/a |  |  | 0 |  | 0 | FY2022 | 791322 | 791322 | ADVERTISED | G | Solicit Bids milestone finished 399 days early | G | Project is on budget | [5 empty] | 2020-06-01 | 2020-06-01 | 2020-06-12 | 2020-06-01 | G | 2020-06-15 | 2020-06-01 | 2020-08-24 | 2020-07-13 | G | [35 empty] | 2022-01-11 | 2020-12-08 | 2022-01-11 | 2020-12-08 | G | 2022-04-05 |  | 2022-06-28 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.12204
865 | 117454 | STAUNTON DISTRICT HVBP TASK 31 | 9999 | Miscellaneous | Traffic Management/Engineering | VDOT | Staunton District-wide |  | Staunton | NonMPO:NonMPO | Infrastructure Investment Division | Matthew Bond | Matthew.Bond@vdot.virginia.gov | (540) 332-9275 | Michael L Surratt | Michael.Surratt@VDOT.Virginia.gov | (540) 332-9325 |  |  |  | 0 |  | 0 | FY2021 | 60000 | 60000 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished on-time | G | Project is on budget | [10 empty] | 2020-06-01 | 2020-06-01 | 2020-10-06 | 2020-10-06 | G | [35 empty] | 2020-10-08 | 2020-10-08 | 2020-10-14 | 2020-10-14 | G | 2020-10-15 | 2020-10-15 | 2020-10-22 | 2020-10-22 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | WORK/TASK ORDER | 1 | 0 | 0.097508
866 | 118431 | #SGR21VB - RTE. 749 - REPLACE STR. 6120 OVER HUGHES RIVER | 0749 | Secondary | Bridge Replacement w/ Added Capacity | VDOT | Madison County | CHARLOTTESVILLE | Culpeper | NonMPO:NonMPO | Infrastructure Investment/Asset Management Division | Teresa A Gothard | Teresa.Gothard@VDOT.Virginia.gov | (540) 829-7635 | Brian A Arnold | Brian.Arnold@VDOT.Virginia.gov | (540) 829-7557 |  |  |  | 0 |  | 0 | FY2025 | 5600100 | 5600100 | NO DATES SET YET | G | Start Development milestone is 257 days ahead of the expected completion date | G | Project is on budget | [5 empty] | 2021-10-15 |  | 2021-11-05 |  | G | 2021-11-08 |  | 2022-09-12 |  | G | [5 empty] | 2023-04-17 |  | 2023-05-12 |  | G | 2024-01-05 |  | 2024-02-12 |  | G | 2024-07-11 |  | 2024-11-08 |  | G | 2024-02-28 |  | 2024-07-25 |  | G | 2024-03-20 |  | 2024-08-15 |  | G | [5 empty] | 2024-11-12 |  | 2024-11-12 |  | G | 2025-02-06 |  | 2025-02-06 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.099451
867 | 101246 | ROUTE 681 - BRIDGE REPAIR (SCOUR) OVER APPOMATTOX RIVER | 0681 | Secondary | Bridge Rehab w/o Added Capacity | VDOT | Powhatan County | CHESTERFIELD | Richmond | NonMPO:NonMPO | Infrastructure Investment Division | Jeremy B Cobb | Jeremy.Cobb@vdot.virginia.gov | (804) 586-2255 | Jeremy B Cobb | Jeremy.Cobb@vdot.virginia.gov | (804) 586-2255 |  |  |  | 0 |  | 0 | FY2020 | 1275152 | 2040078 | CONSTRUCTION STARTED | R | Start Delivery milestone finished 98 days late | R | Project estimate is less than $5M and is 20% or more over budget | [5 empty] | 2016-07-01 | 2016-06-28 | 2016-07-01 | 2016-06-28 | G | 2016-09-14 | 2016-09-14 | 2018-01-26 | 2018-01-26 | G | [5 empty] | 2018-04-16 | 2018-04-16 | 2018-04-27 | 2018-04-23 | G | 2018-08-16 | 2018-08-14 | 2018-08-31 | 2018-08-14 | G | [5 empty] | 2018-09-18 | 2018-08-28 | 2019-03-15 | 2018-08-28 | G | 2019-01-16 | 2019-04-26 | 2019-06-10 | 2019-07-08 | R | [5 empty] | 2019-12-10 | 2020-05-05 | 2019-12-10 | 2020-05-05 | R | 2020-02-04 | 2020-07-21 | 2020-04-14 | 2020-07-21 | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 1 | 0.3033
868 | 104950 | #HB2.FY17 RTE 501-CONSTRUCT LEFT/RIGHT TURN LANES AT RTE 633 | 0501 | Primary | Safety | VDOT | Campbell County | APPOMATTOX | Lynchburg | NonMPO:NonMPO | Infrastructure Investment Division | Raina A Rosado | Raina.Rosado@VDOT.Virginia.gov | (434) 856-8318 | Gregory K Parsons | Gregory.Parsons@vdot.virginia.gov | (434) 856-8297 |  |  |  | 1 | 2017 | 0 | FY2019 | 2543998 | 2722274 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 2 days early | Y | Project estimate is less than $5M and is up to 20% over budget | [5 empty] | 2013-08-06 | 2013-07-03 | 2013-08-06 | 2013-07-03 | G | 2013-09-05 | 2013-09-05 | 2014-07-16 | 2014-07-16 | G | 2014-07-31 | 2014-07-31 | 2014-09-11 | 2014-09-11 | G | [5 empty] | 2017-04-04 | 2017-04-04 | 2017-04-06 | 2017-04-06 | G | 2018-01-24 | 2018-01-24 | 2018-07-05 | 2018-07-05 | G | 2017-04-24 | 2017-04-24 | 2018-01-26 | 2018-01-26 | G | [10 empty] | 2018-06-14 | 2018-07-10 | 2018-07-10 | 2018-07-10 | G | 2018-09-27 | 2018-09-26 | 2018-10-18 | 2018-10-16 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.099982
869 | 107245 | Rural Addition - Shangri-La Road - Warren County | 0730 | Secondary | Reconstruction w/o Added Capacity | Locally | Warren County | EDINBURG | Staunton | NonMPO:NonMPO | Local Assistance Division | Kimberly Cameron | Kim.Cameron@vdot.virginia.gov | (540) 332-7886 | Kimberly Cameron | Kim.Cameron@vdot.virginia.gov | (540) 332-7886 | Doug Stanley (Warren County Admin.) | Dstanley@warrencountyva.net | (540) 636-4600 | 0 |  | 0 | FY2019 | 236918 | 236918 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 256 days early | G | Project is on budget | 2015-09-30 | 2015-08-21 | 2015-12-29 | 2015-08-21 | G | 2015-12-30 | 2015-08-24 | 2016-01-13 | 2015-09-21 | G | 2016-01-14 | 2015-09-22 | 2016-09-07 | 2016-12-06 | R | [10 empty] | 2018-02-23 | 2018-03-05 | 2018-03-08 | 2018-03-05 | G | [20 empty] | 2018-04-25 | 2018-04-18 | 2018-08-16 | 2018-05-18 | G | 2018-10-26 | 2018-05-21 | 2019-03-12 | 2018-06-29 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.20454
870 | 113139 | FY19 RS Citywide Curb, Gutter, & Sidewalk Improvements | 0000 | Urban | Reconstruction w/o Added Capacity | Locally | Roanoke | SALEM | Salem | Roanoke:Roanoke City | Local Assistance Division | Cheryl B Becker | Cheryl.Becker@vdot.virginia.gov | (540) 492-2531 | Cheryl B Becker | Cheryl.Becker@vdot.virginia.gov | (540) 492-2531 | Luke Pugh | Luke.Pugh@RoanokeVa.gov | (540) 853-5208 | 0 |  | 0 | FY2021 | 4800000 | 4800000 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 340 days early | G | Project is on budget | 2018-08-01 | 2018-08-01 | 2018-10-25 | 2018-11-27 | R | 2018-10-26 | 2018-11-28 | 2018-10-30 | 2018-11-28 | R | 2018-10-31 | 2018-11-29 | 2019-08-01 | 2019-01-30 | G | [35 empty] | 2020-02-24 | 2019-12-15 | 2020-05-01 | 2020-01-12 | G | 2020-09-24 | 2020-01-13 | 2021-01-25 | 2020-02-20 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.19191
871 | 115273 | RTE 163 - (ID 5543) RESURFACING (MEMORIAL AVE) | 0163 | Urban | Resurfacing | Locally | Lynchburg | APPOMATTOX | Lynchburg | Lynchburg:Lynchburg | Local Assistance Division | Gregg Allen | Gregg.Allen@vdot.virginia.gov | (434) 426-5575 | Sharon S White | Sharon.White@VDOT.Virginia.gov | (434) 856-8220 | Lee Newland | lee.newland@lynchburgva.gov | (434) 455-3947 | 0 |  | 0 | FY2021 | 285000 | 285000 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 38 days early | G | Project is on budget | 2020-01-31 | 2019-09-02 | 2020-04-24 | 2019-09-19 | G | [5 empty] | 2020-01-31 | 2020-01-31 | 2020-02-13 | 2020-02-13 | G | [35 empty] | 2020-05-12 | 2020-05-12 | 2020-06-09 | 2020-05-20 | G | 2020-08-27 | 2020-07-20 | 2020-08-27 | 2020-07-20 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.075473
872 | 115815 | I-64 Express Barge Service Expansion | 9999 | Miscellaneous | Other | Locally | Richmond | ASHLAND | Richmond | Richmond:Richmond | Infrastructure Investment Division | Bhavesh Shah | Bhavesh.Shah@vdot.virginia.gov | (804) 524-6149 | Bhavesh Shah | Bhavesh.Shah@vdot.virginia.gov | (804) 524-6149 | TBD |  |  | 0 |  | 0 | FY2024 | 3000000 | 3000000 | NO DATES SET YET | G | Agreement with Locality milestone is 649 days ahead of the expected completion date | G | Project is on budget | 2022-09-06 |  | 2022-12-02 |  | G | [5 empty] | 2022-12-05 |  | 2023-08-22 |  | G | [25 empty] | 2023-08-23 |  | 2023-11-17 |  | G | [5 empty] | 2024-02-01 |  | 2024-02-29 |  | G | 2024-05-17 |  | 2024-06-28 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.094755
873 | 117165 | #SGR21LP 137-City of Williamsburg 2188 Jamestown Rd | 0031 | Urban | Resurfacing | Locally | Williamsburg | WILLIAMSBURG | Hampton Roads | Hampton Roads:Williamsburg | Infrastructure Investment/Asset Management Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Chessica Villaflores | Chessica.Villaflores@vdot.virginia.gov | (757) 956-3094 | Aaron Small | asmall@williamsburgva.gov | (757) 220-6140 | 0 |  | 1 | FY2022 | 407150 | 407150 | NO DATES SET YET | G | Agreement with Locality milestone is 54 days ahead of the expected completion date | G | Project is on budget | 2021-03-01 |  | 2021-04-16 |  | G | 2021-04-19 |  | 2021-05-07 |  | G | 2021-06-08 |  | 2021-07-13 |  | G | [25 empty] | 2021-06-29 |  | 2021-08-10 |  | G | [5 empty] | 2021-10-07 |  | 2021-11-04 |  | G | 2022-02-01 |  | 2022-02-01 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.092838
874 | 117436 | ITTF I-64 Afton Mountain Safety Improvements | 0064 | Interstate | Safety | VDOT | Albemarle County | CHARLOTTESVILLE | Culpeper | NonMPO:NonMPO | Infrastructure Investment Division | Nathran T Austin | Nathran.Austin@vdot.virginia.gov | (540) 280-0150 | Nathran T Austin | Nathran.Austin@vdot.virginia.gov | (540) 280-0150 |  |  |  | 0 |  | 0 | FY2024 | 5000000 | 5000000 | NO DATES SET YET-PE OPEN | R | Start Development milestone finished 78 days late | G | Project is on budget | [5 empty] | 2020-06-29 | 2020-09-24 | 2020-07-20 | 2020-10-06 | R | 2020-07-21 |  | 2021-05-24 |  | G | [5 empty] | 2021-12-23 |  | 2022-01-25 |  | G | 2022-09-13 |  | 2022-10-18 |  | G | 2023-03-24 |  | 2023-07-24 |  | G | 2022-11-02 |  | 2023-04-07 |  | G | 2022-12-12 |  | 2023-05-12 |  | G | [5 empty] | 2023-08-08 |  | 2023-08-08 |  | G | 2023-10-27 |  | 2023-10-27 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.14656
875 | 118114 | #SGR21LP BUS 58 EBL - (ID6590) RESURFACING (RIVERSIDE DR) | 7058 | Urban | Resurfacing | Locally | Danville | HALIFAX | Lynchburg | Danville:Danville | Local Assistance Division | Gregg Allen | Gregg.Allen@vdot.virginia.gov | (434) 426-5575 | Gregg Allen | Gregg.Allen@vdot.virginia.gov | (434) 426-5575 | BRIAN DUNEVANT | dunevbl@danvilleva.gov | (434) 799-5019 | 0 |  | 1 | FY2024 | 523182 | 523182 | NO DATES SET YET | G | Agreement with Locality milestone is 106 days ahead of the expected completion date | G | Project is on budget | 2021-01-29 |  | 2021-06-07 |  | G | 2021-06-08 |  | 2021-06-28 |  | G | 2022-01-07 |  | 2022-05-03 |  | G | [25 empty] | 2023-04-28 |  | 2023-09-26 |  | G | [5 empty] | 2023-11-28 |  | 2023-12-26 |  | G | 2024-03-19 |  | 2024-03-19 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.050513
876 | 88616 | RTE. 772 OVER SPOON CREEK (STR. 13399) - BRIDGE REPLACEMENT | 0772 | Secondary | Bridge Replacement w/o Added Capacity | VDOT | Patrick County | MARTINSVILLE | Salem | NonMPO:NonMPO | Infrastructure Investment Division | Anthony T Marshall | Todd.Marshall@VDOT.Virginia.gov | (540) 387-5460 | Anthony L Handy | Tony.Handy@VDOT.Virginia.gov | (540) 352-9050 |  |  |  | 0 |  | 0 | FY2020 | 3304953 | 3304953 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 62 days early | G | Project is on budget | [5 empty] | 2008-07-29 | 2008-08-05 | 2008-08-29 | 2008-08-05 | G | 2015-08-31 | 2015-08-31 | 2016-08-29 | 2016-05-25 | G | 2016-03-15 | 2016-03-15 | 2016-05-25 | 2016-05-25 | G | [5 empty] | 2017-07-05 | 2017-07-05 | 2017-09-18 | 2017-09-18 | G | 2018-09-17 | 2018-09-13 | 2019-03-11 | 2018-09-15 | G | 2017-09-22 | 2017-09-22 | 2019-03-06 | 2018-09-20 | G | 2018-03-01 | 2018-06-21 | 2019-03-11 | 2019-01-22 | G | [5 empty] | 2019-02-14 | 2019-03-12 | 2019-03-12 | 2019-03-12 | G | 2019-03-29 | 2019-05-28 | 2019-07-29 | 2019-05-28 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.057601
877 | 104266 | Extension of Hope Dr Realignment of Papermill Rd Tevis St | 0000 | Urban | New Construction Roadway | Locally | Winchester | EDINBURG | Staunton | Winchester:Winchester | Local Assistance Division | Kimberly Cameron | Kim.Cameron@vdot.virginia.gov | (540) 332-7886 | Kimberly Cameron | Kim.Cameron@vdot.virginia.gov | (540) 332-7886 | Perry Eisenach | peisenach@ci.winchester.va.us | (540) 667-1815 | 0 |  | 0 | FY2020 | 9500000 | 9500000 | CONSTRUCTION STARTED | R | Start Delivery milestone finished 228 days late | G | Project is on budget | [5 empty] | 2014-03-31 | 2014-02-10 | 2014-03-31 | 2014-02-10 | G | 2014-08-01 | 2014-07-31 | 2018-05-31 | 2015-03-31 | G | [10 empty] | 2018-04-30 | 2018-04-30 | 2018-10-31 | 2018-10-17 | G | [20 empty] | 2019-12-02 | 2020-05-01 | 2019-12-02 | 2020-05-29 | R | 2020-01-06 | 2020-06-01 | 2020-03-27 | 2020-11-10 | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.19363
878 | 105527 | PORTNER AVENUE SIDEWALK | 9999 | Urban | Facilities for Pedestrians and Bicycles | Locally | Manassas | MANASSAS | Northern Virginia | Northern Virginia:Manassas | Local Assistance Division | Amir Salahshoor | A.Salahshoor@VDOT.Virginia.gov | (703) 259-1957 | Veljibhai M Desai | Veljibhai.Desai@vdot.virginia.gov | (703) 259-2927 | Bryan Foster | bfoster@manassasva.gov | (703) 257-8226 | 0 |  | 0 | FY2021 | 298000 | 298000 | AWARDED | G | Start Delivery milestone finished 12 days early | G | Project is on budget | 2014-06-20 | 2014-06-20 | 2014-06-20 | 2014-06-20 | G | 2017-07-05 | 2017-07-05 | 2017-07-05 | 2017-07-05 | G | 2017-08-01 | 2017-08-01 | 2018-12-31 | 2018-12-31 | G | [10 empty] | 2018-07-02 | 2018-07-02 | 2018-08-24 | 2018-08-24 | G | [20 empty] | 2019-11-01 | 2019-11-01 | 2020-06-30 | 2020-10-30 | R | 2020-07-01 | 2020-11-02 | 2020-12-30 | 2020-12-18 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.13119
879 | 108708 | Reconstruction - Pine Ave. | 9999 | Secondary | Reconstruction w/o Added Capacity | Locally | Hopewell | PETERSBURG | Richmond | Tri-Cities:Hopewell | Local Assistance Division | James Shepherd | James.Shepherd@vdot.virginia.gov | (804) 609-5305 | Brian J Lokker | Brian.Lokker@VDOT.Virginia.gov | (804) 524-6010 | Austin Anderson | aanderson@hopewellva.gov | (804) 541-2379 | 0 |  | 0 | FY2019 | 400000 | 400000 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished on-time | G | Project is on budget | 2017-07-12 | 2016-09-13 | 2017-10-04 | 2016-09-13 | G | 2017-10-05 | 2017-08-08 | 2017-10-10 | 2017-08-10 | G | 2017-10-11 | 2017-08-11 | 2018-04-20 | 2018-03-09 | G | [35 empty] | 2018-04-17 | 2018-06-05 | 2018-06-29 | 2018-06-29 | G | 2018-07-02 | 2018-06-29 | 2018-08-20 | 2018-08-20 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.10527
880 | 108709 | Reconstruction - Hummel Ross Rd. | 9999 | Secondary | Reconstruction w/o Added Capacity | Locally | Hopewell | PETERSBURG | Richmond | Tri-Cities:Hopewell | Local Assistance Division | Brian J Lokker | Brian.Lokker@VDOT.Virginia.gov | (804) 524-6010 | Brian J Lokker | Brian.Lokker@VDOT.Virginia.gov | (804) 524-6010 | Austin Anderson | aanderson@hopewellva.gov | (804) 541-2319 | 0 |  | 0 | FY2020 | 1252000 | 1252000 | AWARDED | G | Start Delivery milestone finished on-time | G | Project is on budget | 2017-07-12 | 2016-09-12 | 2017-10-04 | 2016-09-13 | G | 2017-10-05 | 2017-09-05 | 2017-10-10 | 2017-09-05 | G | 2017-10-11 | 2017-09-06 | 2018-04-20 | 2018-04-18 | G | [10 empty] | 2019-04-24 | 2019-03-25 | 2019-05-14 | 2019-06-28 | R | [5 empty] | 2019-05-16 | 2019-07-02 | 2020-02-28 | 2019-07-02 | G | 2019-11-15 | 2019-11-18 | 2020-03-06 | 2019-11-18 | G | [5 empty] | 2020-03-17 | 2020-02-27 | 2020-04-13 | 2020-04-09 | G | 2020-04-14 | 2020-04-10 | 2020-05-22 | 2020-05-22 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.1074
881 | 108886 | CURVE REALIGNMENT - RTE 675 - LUNENBURG COUNTY | 0675 | Secondary | Safety | VDOT | Lunenburg County | SOUTH HILL | Richmond | NonMPO:NonMPO | Infrastructure Investment/Asset Management Division | Thomas Kendrick | Thomas.Kendrick@vdot.virginia.gov | (804) 609-5281 | Thomas Kendrick | Thomas.Kendrick@vdot.virginia.gov | (804) 609-5281 |  |  |  | 0 |  | 0 | FY2023 | 1360000 | 1360000 | ACTIVITY DATES SET | R | Engage Public milestone finished 139 days late | G | Project is on budget | [5 empty] | 2018-11-01 | 2018-11-01 | 2018-11-15 | 2018-11-06 | G | 2018-11-16 | 2018-11-07 | 2019-10-15 | 2019-10-15 | G | [5 empty] | 2020-06-18 | 2020-07-17 | 2020-08-13 | 2020-12-30 | R | 2021-07-12 |  | 2021-07-23 |  | G | 2022-03-14 |  | 2022-09-14 |  | G | 2021-08-10 |  | 2022-02-10 |  | G | 2021-03-10 | 2020-11-19 | 2022-02-22 | 2020-11-19 | G | [5 empty] | 2022-10-11 |  | 2022-10-11 |  | G | 2023-01-19 |  | 2023-03-16 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.081503
882 | 109260 | POLE GREEN RD WIDENING | 0627 | Secondary | Preliminary Engineering | Locally | Hanover County | ASHLAND | Richmond | Richmond:Hanover County | Infrastructure Investment Division | Cynthia Crouch | Cynthia.Crouch@vdot.virginia.gov | (804) 609-5313 | Cynthia Crouch | Cynthia.Crouch@vdot.virginia.gov | (804) 609-5313 | Joe Vidunas | jevidunas@co.hanover.va.us | (804) 365-6176 | 0 |  | 0 | FY2029 | 20000000 | 20000000 | NO DATES SET YET-PE OPEN | G | Start Development milestone finished 1187 days early | G | Project is on budget | 2023-07-03 | 2019-11-18 | 2023-09-26 | 2020-01-28 | G | 2023-09-27 | 2020-06-29 | 2023-09-29 | 2020-06-29 | G | 2023-10-02 | 2020-06-30 | 2025-02-28 |  | G | [5 empty] | 2025-08-29 |  | 2025-08-29 |  | G | 2025-10-22 |  | 2026-03-31 |  | G | [5 empty] | 2026-04-01 |  | 2027-01-12 |  | G | 2024-05-17 |  | 2025-01-24 |  | G | [5 empty] | 2027-02-03 |  | 2029-02-15 |  | G | 2029-02-16 |  | 2029-06-15 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.19458
883 | 109543 | #HB2.FY17 PITTSYLVANIA - WIDEN & OVERLAY(HALIFAX RESIDENCY) | 9999 | Secondary | Restoration and Rehabilitation | VDOT | Pittsylvania County | HALIFAX | Lynchburg | NonMPO:NonMPO | Infrastructure Investment Division | Kenneth T Bolling | Todd.Bolling@vdot.virginia.gov | (276) 346-1913 | Lindsey S Hodges | Lindsey.Hodges@vdot.virginia.gov | (434) 856-8143 |  |  |  | 1 | 2017 | 0 | FY2017 | 1317000 | 1419845 | PROJECT CLOSEOUT COMPLETE | G | Start Delivery milestone finished 14 days early | Y | Project estimate is less than $5M and is up to 20% over budget | [10 empty] | 2016-09-19 | 2016-09-19 | 2016-09-19 | 2016-09-19 | G | [35 empty] | 2016-07-26 | 2016-07-26 | 2016-07-26 | 2016-07-26 | G | 2016-10-03 | 2016-10-03 | 2016-10-17 | 2016-10-03 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.098463
884 | 109672 | Route 72 Structure 1017 over Laurel Branch Fed ID 5798 | 0072 | Primary | Bridge Replacement w/o Added Capacity | VDOT | Dickenson County | WISE | Bristol | NonMPO:NonMPO | Infrastructure Investment Division | Gary Lester |  |  | Emily V Collins | Emily.Collins@vdot.virginia.gov | (276) 696-3394 |  |  |  | 0 |  | 0 | FY2019 | 623000 | 621000 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 61 days early | G | Project is on budget | [5 empty] | 2016-07-01 | 2016-07-01 | 2016-07-15 | 2016-07-15 | G | 2016-07-18 | 2016-07-18 | 2017-03-14 | 2017-10-02 | R | [5 empty] | 2017-06-09 | 2017-06-09 | 2017-06-09 | 2017-06-09 | G | [5 empty] | 2017-06-26 | 2017-06-26 | 2017-10-18 | 2017-10-18 | G | [5 empty] | 2017-07-11 | 2017-09-11 | 2017-10-10 | 2017-09-11 | G | [5 empty] | 2019-04-09 | 2019-01-08 | 2019-04-09 | 2019-01-08 | G | 2019-05-30 | 2019-04-19 | 2019-06-19 | 2019-04-19 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.064028
885 | 110689 | #SGR18LB - Colorado St Bridge Replacement | 0011 | Urban | Bridge Replacement w/o Added Capacity | Locally | Salem | SALEM | Salem | Roanoke:Salem | Local Assistance Division | James M Guy | james.guy@vdot.virginia.gov | (540) 387-5247 | Cheryl B Becker | Cheryl.Becker@vdot.virginia.gov | (540) 492-2531 | Will Simpson | wsimpson@salemva.gov | (540) 375-3032 | 0 |  | 1 | FY2024 | 6450000 | 6450000 | ACTIVITY DATES SET | G | Determine Requirements milestone finished 347 days early | G | Project is on budget | 2021-03-01 | 2018-01-23 | 2021-06-14 | 2018-05-07 | G | 2021-06-15 | 2019-03-29 | 2021-06-17 | 2019-04-04 | G | 2021-06-18 | 2019-04-05 | 2021-12-27 | 2021-01-14 | G | [35 empty] | 2023-01-18 |  | 2023-02-14 |  | G | 2023-02-15 |  | 2023-07-07 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.18084
886 | 111275 | #SGR18VB - RT. 703 OVER CSX ROW BRIDGE REHABILITATION | 0703 | Secondary | Bridge Rehab w/o Added Capacity | VDOT | Dinwiddie County | PETERSBURG | Richmond | Tri-Cities:Dinwiddie County | Infrastructure Investment/Asset Management Division | Thomas Kendrick | Thomas.Kendrick@vdot.virginia.gov | (804) 609-5281 | Thomas Kendrick | Thomas.Kendrick@vdot.virginia.gov | (804) 609-5281 |  |  |  | 0 |  | 1 | FY2024 | 2500000 | 2500000 | ACTIVITY DATES SET | G | Determine Requirements milestone finished 1 days early | G | Project is on budget | [5 empty] | 2019-09-03 | 2019-09-03 | 2019-09-16 | 2019-09-11 | G | 2019-09-17 | 2019-09-12 | 2020-08-13 | 2020-08-12 | G | [5 empty] | 2021-06-04 |  | 2021-06-17 |  | G | 2022-08-18 |  | 2022-08-31 |  | G | 2023-02-01 |  | 2023-08-04 |  | G | 2022-09-16 |  | 2023-03-29 |  | G | 2022-08-11 |  | 2023-04-19 |  | G | [5 empty] | 2023-08-08 |  | 2023-08-08 |  | G | 2023-10-30 |  | 2023-10-30 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.13025
887 | 112667 | Gilmerton Bridge Auxliary Counterweight |  | Urban | Bridge Rehab w/o Added Capacity | Locally | Chesapeake | NORFOLK | Hampton Roads | Hampton Roads:Chesapeake | Local Assistance Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Johndel A Alcaide | John.Alcaide@vdot.virginia.gov | (757) 956-3098 | Sam Sawan, PE | sawan@cityofchesapeake.net | (757) 382-8263 | 0 |  | 0 | FY2021 | 1514413 | 1514413 | ADVERTISED | R | Start Delivery milestone is 59 days past the expected completion date | G | Project is on budget | 2018-07-02 | 2018-03-01 | 2018-09-25 | 2018-03-21 | G | 2018-09-26 | 2018-03-21 | 2018-10-09 | 2018-07-19 | G | 2018-10-10 | 2018-07-20 | 2019-09-26 | 2020-07-09 | R | [35 empty] | 2020-07-10 | 2020-07-11 | 2020-07-13 | 2020-07-13 | G | 2020-07-14 |  | 2020-12-24 |  | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.18839
888 | 113199 | Elbow Road Widening, Phase 2 |  | Urban | Reconstruction w/ Added Capacity | Locally | Chesapeake | NORFOLK | Hampton Roads | Hampton Roads:Chesapeake | Local Assistance Division | Johndel A Alcaide | John.Alcaide@vdot.virginia.gov | (757) 956-3098 | Johndel A Alcaide | John.Alcaide@vdot.virginia.gov | (757) 956-3098 | Sam Sawan, PE | sawan@cityofchesapeake.net |  | 0 |  | 0 | FY2022 | 20200000 | 20200000 | NO DATES SET YET-PE OPEN | R | Determine Requirements milestone is 653 days past the expected completion date | G | Project is on budget | 2018-08-01 | 2018-08-01 | 2018-10-25 | 2018-10-05 | G | 2018-10-26 | 2018-10-08 | 2018-10-30 | 2018-10-31 | R | 2018-10-31 |  | 2019-05-10 |  | R | [10 empty] | 2020-05-13 |  | 2020-06-03 |  | R | [5 empty] | 2020-06-05 |  | 2021-03-19 |  | Y | 2019-06-18 | 2020-10-09 | 2020-02-25 | 2020-10-09 | R | [5 empty] | 2021-04-06 |  | 2021-05-03 |  | G | 2021-07-22 |  | 2021-07-22 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.24796
889 | 113465 | Virginia Beach Blvd at Chapel Street | 0058 | Urban | Facilities for Pedestrians and Bicycles | Locally | Norfolk | NORFOLK | Hampton Roads | Hampton Roads:Norfolk | Local Assistance Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Derrick Williams | Derrick.Williams@vdot.virginia.gov | (757) 956-3097 | Deborah.Mangiaracina, P.E. | 'Deborah.Mangiaracina@norfolk.gov' | (757) 664-7459 | 0 |  | 0 | FY2022 | 150000 | 148664 | ACTIVITY DATES SET | R | Solicit Bids milestone is 122 days past the expected completion date | G | Project is on budget | 2018-10-09 | 2018-10-09 | 2019-01-08 | 2018-12-26 | G | 2019-01-09 | 2018-12-27 | 2019-01-11 | 2019-01-07 | G | 2019-01-14 | 2019-04-03 | 2019-07-19 | 2019-04-03 | G | [35 empty] | 2020-09-10 |  | 2020-10-22 |  | R | 2021-01-19 |  | 2021-07-08 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.13515
890 | 108723 | Habersham Area Improvements |  | Urban | Reconstruction w/o Added Capacity | Locally | Newport News | WILLIAMSBURG | Hampton Roads | Hampton Roads:Newport News | Local Assistance Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Chessica Villaflores | Chessica.Villaflores@vdot.virginia.gov | (757) 956-3094 | Bryan Stilley | bstilley@nnva.gov | (757) 926-8699 | 0 |  | 0 | FY2020 | 3306693 | 2685431 | ACTIVITY DATES SET | R | Complete Purchasing Right-of-Way milestone is 472 days past the expected completion date | G | Project is on budget | 2016-10-25 | 2016-10-25 | 2016-10-25 | 2016-10-25 | G | 2016-10-25 | 2016-10-25 | 2016-10-25 | 2016-10-25 | G | 2016-10-26 | 2016-10-26 | 2018-10-29 | 2019-02-01 | R | [10 empty] | 2018-06-11 | 2018-06-11 | 2018-06-11 | 2018-06-11 | G | [5 empty] | 2019-04-08 | 2019-04-08 | 2019-11-07 |  | R | [10 empty] | 2019-11-18 |  | 2020-01-16 |  | R | 2020-01-21 |  | 2020-05-27 |  | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.24684
891 | 108981 | Warwick Boulevard Sidewalk Widening | 0000 | Urban | Facilities for Pedestrians and Bicycles | Locally | Newport News | WILLIAMSBURG | Hampton Roads | Hampton Roads:Newport News | Infrastructure Investment Division | Stephen Rowan | Steve.Rowan@vdot.virginia.gov | (757) 790-9925 | Chessica Villaflores | Chessica.Villaflores@vdot.virginia.gov | (757) 956-3094 | Bryan Stilley | bstilley@nnva.gov | (757) 926-8699 | 0 |  | 0 | FY2025 | 1116821 | 1116821 | NO DATES SET YET-PE OPEN | G | Start Development milestone finished 644 days early | G | Project is on budget | 2021-10-04 | 2019-12-09 | 2022-01-03 | 2020-01-22 | G | 2022-01-04 | 2020-01-27 | 2022-01-06 | 2020-04-02 | G | 2022-01-07 |  | 2022-07-14 |  | G | [10 empty] | 2023-05-10 |  | 2023-05-31 |  | G | [5 empty] | 2023-06-02 |  | 2024-03-15 |  | G | 2022-08-19 |  | 2023-04-27 |  | G | [5 empty] | 2024-04-02 |  | 2024-04-29 |  | G | 2024-07-18 |  | 2024-07-18 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.25545
892 | 109261 | I-64 EAST RICHMOND ATMS PROJECT | 0064 | Interstate | Safety | VDOT | Henrico County | ASHLAND | Richmond | Richmond:Henrico County | Infrastructure Investment Division | Lawrence Ramsey | Brian.Ramsey@VDOT.Virginia.gov | (804) 585-3579 | Ronnie Hobson | Ron.Hobson@vdot.virginia.gov | (804) 840-5501 |  |  |  | 0 |  | 0 | FY2019 | 4563340 | 4563340 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 145 days early | G | Project is on budget | [5 empty] | 2016-09-29 | 2016-09-29 | 2016-10-14 | 2016-10-14 | G | 2016-10-18 | 2016-10-18 | 2018-10-31 | 2018-06-15 | G | [5 empty] | 2018-10-22 | 2018-06-04 | 2018-11-02 | 2018-06-04 | G | [5 empty] | 2018-09-11 | 2018-04-09 | 2018-09-11 | 2018-04-09 | G | [5 empty] | 2018-11-07 | 2018-11-07 | 2018-12-21 | 2018-11-07 | G | [5 empty] | 2019-03-12 | 2018-10-09 | 2019-03-12 | 2018-10-09 | G | 2019-05-01 | 2018-12-27 | 2019-05-21 | 2018-12-27 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.079917
893 | 109600 | #SGR17VB - RT 667 - REPLACE BRIDGE STR. 6056 | 0667 | Secondary | Bridge Replacement w/o Added Capacity | VDOT | Albemarle County | CHARLOTTESVILLE | Culpeper | Charlottesville:Albemarle County | Infrastructure Investment/Asset Management Division | Braden C Chapman | Braden.Chapman@VDOT.Virginia.gov | (540) 829-7421 | Brian A Arnold | Brian.Arnold@VDOT.Virginia.gov | (540) 829-7557 |  |  |  | 0 |  | 1 | FY2023 | 1923500 | 1923500 | ACTIVITY DATES SET | R | Obtained Permits milestone is 311 days past the expected completion date | G | Project is on budget | [5 empty] | 2019-01-15 | 2017-03-20 | 2019-01-30 | 2017-03-20 | G | 2019-01-31 | 2017-02-16 | 2019-12-26 | 2018-05-21 | G | [5 empty] | 2020-06-25 | 2020-05-09 | 2020-07-09 | 2020-05-27 | G | 2022-02-02 | 2020-11-10 | 2022-02-08 | 2020-12-28 | G | [5 empty] | 2022-02-24 | 2020-12-28 | 2022-08-16 |  | G | 2019-04-17 | 2020-08-05 | 2020-04-16 |  | R | [5 empty] | 2023-01-10 |  | 2023-01-10 |  | G | 2023-03-06 |  | 2023-03-24 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.16219
894 | 110448 | ROUTE 693-SAFETY IMPROVEMENTS | 0693 | Secondary | Safety | VDOT | Pulaski County | CHRISTIANSBURG | Salem | NonMPO:NonMPO | Infrastructure Investment Division | Alex H Price | Alex.Price@VDOT.Virginia.gov | (540) 378-5053 | Jason L Patrick | Jason.Patrick@vdot.virginia.gov | (540) 381-7178 |  |  |  | 0 |  | 0 | FY2021 | 1221438 | 1221438 | ACTIVITY DATES SET | R | Engage Public milestone is 499 days past the expected completion date | G | Project is on budget | [5 empty] | 2017-12-01 | 2017-11-03 | 2017-12-14 | 2017-11-03 | G | 2017-12-15 | 2017-11-06 | 2018-08-08 | 2018-08-07 | G | [5 empty] | 2019-08-30 |  | 2019-10-11 |  | R | [5 empty] | 2020-02-04 |  | 2020-07-23 |  | R | [5 empty] | 2020-01-22 | 2019-07-18 | 2020-07-14 | 2019-07-18 | G | [5 empty] | 2020-06-09 |  | 2020-07-14 |  | R | 2020-09-16 |  | 2020-12-14 |  | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.083683
895 | 111272 | #SMART18 - Rte. 58 Truck Climbing Lane Phase 2 | 0058 | Primary | Reconstruction w/o Added Capacity | VDOT | Lee County | WISE | Bristol | NonMPO:NonMPO | Infrastructure Investment Division | Marvin E Holley | Gene.Holley@VDOT.Virginia.gov | (276) 696-3255 | Ronald C Flanary | Ronald.Flanary@VDOT.Virginia.gov | (276) 696-3252 |  |  |  | 1 | 2018 | 0 | FY2021 | 4970000 | 3228902 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 177 days early | G | Project is on budget | [5 empty] | 2017-07-14 | 2017-07-07 | 2017-07-27 | 2017-07-27 | G | 2017-07-28 | 2017-07-28 | 2017-12-21 | 2017-08-24 | G | [5 empty] | 2018-06-18 | 2018-06-18 | 2018-07-16 | 2018-07-16 | G | 2019-09-11 | 2019-04-02 | 2019-09-24 | 2019-04-16 | G | 2020-01-27 | 2019-08-23 | 2020-05-18 | 2020-02-21 | G | 2019-10-10 | 2019-05-29 | 2020-06-03 | 2019-09-09 | G | 2018-12-28 | 2017-11-27 | 2019-06-06 | 2017-11-27 | G | [5 empty] | 2020-08-11 | 2020-05-05 | 2020-08-11 | 2020-05-05 | G | 2020-11-16 | 2020-07-21 | 2021-01-14 | 2020-07-21 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.092698
896 | 111667 | #SMART18 - PARK AVENUE MULTIMODAL IMPROVEMENTS | 9999 | Urban | Traffic Management/Engineering | Locally | Falls Church | FAIRFAX | Northern Virginia | Northern Virginia:Falls Church | Infrastructure Investment Division | Amir Salahshoor | A.Salahshoor@VDOT.Virginia.gov | (703) 259-1957 | Christer P Carshult | Christer.Carshult@vdot.virginia.gov | (703) 259-1765 | Caitlin Sobsey | csobsey@fallschurchva.gov | (703) 248-5467 | 1 | 2018 | 0 | FY2022 | 2000000 | 10300000 | NO DATES SET YET-PE OPEN | R | Start Purchasing Right-of-Way milestone is 355 days past the expected completion date | R | Project estimate is less than $5M and is 20% or more over budget | 2018-02-01 | 2018-02-01 | 2018-08-01 | 2018-07-24 | G | 2018-08-01 | 2018-08-01 | 2020-07-02 | 2020-09-17 | R | 2020-07-06 |  | 2021-04-01 |  | G | [10 empty] | 2020-02-03 |  | 2020-03-03 |  | R | [5 empty] | 2020-03-03 |  | 2021-03-03 |  | Y | [10 empty] | 2021-04-23 |  | 2021-04-23 |  | G | 2021-04-26 |  | 2021-08-12 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.449
897 | 112891 | Hydraulic Rd and Lambs Rd/Whitewood Rd_ Signal Reconst | 0743 | Secondary | Safety | VDOT | Albemarle County | CHARLOTTESVILLE | Culpeper | Charlottesville:Albemarle County | Infrastructure Investment Division | Ken Connors |  |  | Caroline Awua-Mensah | Caroline.Awua-Mensah@vdot.virginia.gov | (540) 829-7618 |  |  |  | 0 |  | 0 | FY2019 | 384364 | 384364 | CONSTRUCTION STARTED | R | Start Delivery milestone finished 51 days late | G | Project is on budget | [10 empty] | 2018-09-04 | 2018-03-30 | 2019-01-15 | 2018-08-06 | G | [35 empty] | 2018-08-15 | 2018-10-11 | 2018-08-21 | 2018-10-11 | R | 2018-08-22 | 2018-10-18 | 2018-08-28 | 2018-10-18 | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | WORK/TASK ORDER | 1 | 1 | 0.35874
898 | 113276 | Sidewalk(Phs 2) Merrimac, Penniman, Old Wmsbg, Big Bethel Rd | 9999 | Primary | Reconstruction w/o Added Capacity | Locally | York County | WILLIAMSBURG | Hampton Roads | Hampton Roads:York County | Local Assistance Division | Christopher R Carroll | C.Carroll@VDOT.Virginia.gov | (757) 253-5140 | Keisha Wilkins | Keisha.Wilkins@vdot.virginia.gov | (757) 956-3110 | Tim Cross | tcross@yorkcounty.gov | (757) 890-3496 | 0 |  | 0 | FY2022 | 917581 | 917581 | ACTIVITY DATES SET | R | Determine Requirements milestone finished 166 days late | G | Project is on budget | 2019-10-01 | 2019-09-01 | 2019-12-30 | 2019-10-07 | G | 2019-12-31 | 2019-10-11 | 2020-01-03 | 2019-10-16 | G | 2020-01-06 | 2020-06-01 | 2020-07-10 | 2020-12-23 | R | [25 empty] | 2020-01-15 | 2020-01-30 | 2020-04-10 | 2020-01-30 | G | [5 empty] | 2021-08-05 |  | 2021-10-29 |  | G | 2022-01-26 |  | 2022-02-23 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.1603
899 | 113518 | LEE HIGHWAY PEDESTRIAN IMPROVEMENTS | 0029 | Primary | Facilities for Pedestrians and Bicycles | VDOT | Fairfax County | FAIRFAX | Northern Virginia | Northern Virginia:Fairfax County | Infrastructure Investment Division | Andrew G Beacher | Andrew.Beacher@vdot.virginia.gov | (703) 259-2239 | Hong Ha | Hong.Ha@VDOT.Virginia.gov | (703) 259-2907 |  |  |  | 0 |  | 0 | FY2023 | 2083474 | 2584535 | ACTIVITY DATES SET | G | Engage Public milestone finished 212 days early | Y | Project estimate is less than $5M and is up to 20% over budget | [5 empty] | 2018-06-11 | 2018-06-11 | 2018-06-22 | 2018-06-11 | G | 2018-06-25 | 2018-06-25 | 2019-05-22 | 2019-05-22 | G | [5 empty] | 2020-02-24 | 2019-07-02 | 2020-03-06 | 2019-08-07 | G | 2021-05-06 |  | 2021-05-19 |  | G | 2021-10-12 |  | 2022-04-22 |  | G | 2021-06-04 |  | 2021-12-10 |  | G | 2021-04-29 |  | 2022-01-04 |  | G | [5 empty] | 2022-05-10 |  | 2022-05-10 |  | G | 2022-08-01 |  | 2022-08-01 |  | G | Preliminary design and/or investigations are still underway | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.05444
900 | 113659 | I-81 Median Barrier Safety Initiative - Wythe/Smyth Co. | 0081 | Interstate | Safety | VDOT | Bristol District-wide | WYTHEVILLE | Bristol | NonMPO:NonMPO | Infrastructure Investment Division | Tamara D Pritchard | Tamara.Pritchard@VDOT.Virginia.gov | (276) 696-3249 | Chase R Buchanan | Chase.Buchanan@VDOT.Virginia.gov | (276) 696-3251 |  |  |  | 0 |  | 0 | FY2022 | 1371500 | 1371500 | ACTIVITY DATES SET | R | Relocate Utilities milestone is 24 days past the expected completion date | G | Project is on budget | [5 empty] | 2020-11-16 | 2020-11-16 | 2020-12-08 | 2020-11-16 | G | 2020-12-09 | 2020-11-17 | 2021-10-08 | 2021-02-02 | G | [5 empty] | 2021-02-05 |  | 2021-02-05 |  | R | [5 empty] | 2021-01-28 |  | 2021-01-28 |  | R | [15 empty] | 2021-04-13 |  | 2021-04-13 |  | Y | 2021-07-01 |  | 2021-07-01 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.078507
901 | 114575 | Mt Jackson Sidewalks - Phase II | 0011 | Primary | Reconstruction w/o Added Capacity | Locally | Mt. Jackson | EDINBURG | Staunton | NonMPO:NonMPO | Local Assistance Division | Jeffery A Lineberry | Jeff.Lineberry@VDOT.Virginia.gov | (540) 332-2265 | Jeffery A Lineberry | Jeff.Lineberry@VDOT.Virginia.gov | (540) 332-2265 | Neil Showalter | townmanager@mountjackson.com | (540) 477-2121 | 0 |  | 0 | FY2021 | 675680 | 793500 | ACTIVITY DATES SET | R | Solicit Bids milestone is 209 days past the expected completion date | Y | Project estimate is less than $5M and is up to 20% over budget | 2018-12-03 | 2018-12-03 | 2019-03-01 | 2019-01-31 | G | 2019-03-04 | 2019-02-01 | 2019-03-06 | 2019-09-06 | R | 2019-03-07 | 2019-03-07 | 2019-09-09 | 2019-09-09 | G | [25 empty] | 2019-08-14 | 2019-09-05 | 2020-04-22 | 2019-09-05 | G | [5 empty] | 2020-06-29 | 2019-09-17 | 2020-07-27 |  | R | 2020-10-14 |  | 2020-10-14 |  | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.28042
902 | 115707 | ALEXANDRIA MAINTENANCE RS - MILL AND OVERLAY | 9999 | Urban | Resurfacing | Locally | Alexandria | FAIRFAX | Northern Virginia | Northern Virginia:Alexandria | Local Assistance Division | Amir Salahshoor | A.Salahshoor@VDOT.Virginia.gov | (703) 259-1957 | Rita Hockman | Rita.Hockman@vdot.virginia.gov | (804) 824-7421 | Mary Alice Winston | maryalice.winston@alexandriava.gov | (703) 746-4067 | 0 |  | 0 | FY2021 | 6394000 | 6394000 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 225 days early | G | Project is on budget | 2019-07-01 | 2020-05-01 | 2020-03-31 | 2020-05-18 | R | 2020-04-01 | 2020-05-19 | 2020-04-30 | 2020-05-29 | R | 2020-05-01 | 2020-06-02 | 2020-08-31 | 2020-06-02 | G | [35 empty] | 2020-06-17 | 2020-08-18 | 2020-09-01 | 2020-08-18 | G | 2020-11-23 | 2020-08-19 | 2021-04-01 | 2020-08-19 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.2229
903 | 116923 | #SGR21LP Commonwealth Avenue Primary Extension Paving | 0381 | Urban | Resurfacing | Locally | Bristol | ABINGDON | Bristol | Bristol:Bristol | Infrastructure Investment/Asset Management Division | John W Bechtold | John.Bechtold@vdot.virginia.gov | (276) 696-3365 | John W Bechtold | John.Bechtold@vdot.virginia.gov | (276) 696-3365 | Jay Detrick |  |  | 0 |  | 1 | FY2024 | 90875 | 90875 | NO DATES SET YET | G | Agreement with Locality milestone is 50 days ahead of the expected completion date | G | Project is on budget | 2020-12-01 |  | 2021-04-12 |  | G | 2021-04-13 |  | 2021-05-03 |  | G | 2021-06-02 |  | 2021-09-23 |  | G | [25 empty] | 2022-09-20 |  | 2023-02-24 |  | G | [5 empty] | 2023-04-24 |  | 2023-05-19 |  | G | 2023-08-09 |  | 2023-08-09 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.057763
904 | 117054 | Pemberton Road Sidewalk | 9999 | Secondary | Facilities for Pedestrians and Bicycles | Locally | Henrico County | ASHLAND | Richmond | Richmond:Henrico County | Local Assistance Division | Douglas L Orcutt | Doug.Orcutt@vdot.virginia.gov | (804) 609-5428 | Douglas L Orcutt | Doug.Orcutt@vdot.virginia.gov | (804) 609-5428 | TBD |  | TBD | 0 |  | 0 | FY2028 | 65000 | 65000 | NO DATES SET YET | G | Agreement with Locality milestone is 1543 days ahead of the expected completion date | G | Project is on budget | 2025-01-06 |  | 2025-05-14 |  | G | 2025-05-15 |  | 2025-06-05 |  | G | 2025-12-15 |  | 2026-04-10 |  | G | [25 empty] | 2027-04-07 |  | 2027-09-02 |  | G | [5 empty] | 2027-11-02 |  | 2027-12-02 |  | G | 2028-02-25 |  | 2028-02-25 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.34516
905 | 118376 | Hampton Roads Express Lanes - Segment 3 | 0064 | Interstate | Reconstruction w/ Added Capacity | VDOT | Multi-jurisdictional: Hampton Roads MPO |  | Hampton Roads | Hampton Roads:Multi-jurisdictional: Hampton Roads MPO | Infrastructure Investment Division | Bruce L Duvall | Bruce.Duvall@VDOT.Virginia.gov | (757) 956-3054 | Erin M Foley | Erin.Foley@vdot.virginia.gov | (757) 956-3061 |  |  |  | 0 |  | 0 | FY2026 | 24630792 | 24630792 | NO DATES SET YET | G | Start Development milestone is 109 days ahead of the expected completion date | G | Project is on budget | [5 empty] | 2021-05-20 |  | 2021-06-10 |  | G | 2021-06-11 |  | 2022-08-23 |  | G | [5 empty] | 2023-09-20 |  | 2023-11-01 |  | G | [15 empty] | 2024-07-12 |  | 2025-03-20 |  | G | [5 empty] | 2025-06-10 |  | 2025-06-13 |  | G | 2025-09-03 |  | 2025-09-03 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 1 | 0.22903
906 | 17633 | Sidewalk and Bikeway on Rte 60 from Croaker to Old Church Rd | 0060 | Primary | Facilities for Pedestrians and Bicycles | VDOT | James City County | WILLIAMSBURG | Hampton Roads | Hampton Roads:James City County | Infrastructure Investment Division | Stephen Rowan | Steve.Rowan@vdot.virginia.gov | (757) 790-9925 | Nancy R Marshall | Nancy.Marshall@VDOT.Virginia.gov | (757) 956-3266 |  |  |  | 0 |  | 0 | FY2023 | 2737360 | 3484633 | ACTIVITY DATES SET | G | Start Purchasing Right-of-Way milestone finished 362 days early | R | Project estimate is less than $5M and is 20% or more over budget | [5 empty] | 1998-01-02 | 1997-09-24 | 1998-01-09 | 1997-09-30 | G | 2018-04-10 | 2018-04-10 | 2018-07-10 | 2019-01-28 | R | [5 empty] | 2019-10-01 | 2019-06-07 | 2020-01-30 | 2019-06-07 | G | 2021-09-09 | 2020-09-17 | 2021-09-22 | 2020-09-25 | G | 2021-10-25 |  | 2022-04-20 |  | G | 2021-10-08 | 2020-11-03 | 2022-04-06 |  | G | 2014-03-11 | 2014-03-11 | 2018-12-12 | 2014-03-11 | G | [5 empty] | 2022-12-13 |  | 2022-12-13 |  | G | 2023-01-12 |  | 2023-03-09 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.16355
907 | 98954 | #SGR17VB - BR & Approach REPLACE - RT 698 Over Mill Creek | 0698 | Secondary | Bridge Replacement w/o Added Capacity | VDOT | Shenandoah County | EDINBURG | Staunton | NonMPO:NonMPO | Infrastructure Investment/Asset Management Division | Edwin Z Carter | Edwin.Carter@vdot.virginia.gov | (540) 534-3204 | Jean Uhl | Jean.Uhl@vdot.virginia.gov | (540) 332-9267 |  |  |  | 0 |  | 1 | FY2020 | 2687717 | 2467554 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 29 days early | G | Project is on budget | [5 empty] | 2012-07-02 | 2012-07-02 | 2012-08-03 | 2012-07-19 | G | 2012-08-01 | 2012-08-01 | 2014-06-30 | 2014-09-17 | R | [10 empty] | 2016-09-27 | 2018-12-17 | 2017-02-06 | 2018-12-18 | R | 2014-09-23 | 2014-09-23 | 2019-10-31 | 2019-06-27 | G | 2019-02-12 | 2018-12-18 | 2019-10-10 | 2019-03-14 | G | 2018-07-09 | 2018-08-16 | 2019-03-11 | 2019-06-05 | R | [5 empty] | 2018-10-09 | 2019-10-08 | 2019-11-12 | 2019-10-08 | G | 2018-10-18 | 2019-12-16 | 2020-01-14 | 2019-12-16 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.061002
908 | 101274 | Victory Industrial Pk /Add culverts (Rte 17) | 0017 | Primary | Reconstruction w/o Added Capacity | Locally | York County | WILLIAMSBURG | Hampton Roads | Hampton Roads:York County | Local Assistance Division | Dawn Odom | Dawn.Odom@vdot.virginia.gov | (000) 000-0000 | Keisha Wilkins | Keisha.Wilkins@vdot.virginia.gov | (757) 956-3110 | Joe Brogan | bellamy@YorkCounty.gov | (757) 890-3320 | 0 |  | 0 | FY2019 | 1083001 | 1083001 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 61 days early | Y | Estimate not current | [5 empty] | 2014-06-23 | 2014-06-23 | 2014-07-01 | 2014-06-23 | G | 2014-08-01 | 2014-07-23 | 2018-12-03 | 2018-11-19 | G | [10 empty] | 2017-08-29 | 2017-08-29 | 2017-09-26 | 2017-09-26 | G | [20 empty] | 2019-04-12 | 2018-12-07 | 2019-04-12 | 2018-12-07 | G | 2019-04-29 | 2019-04-10 | 2019-06-10 | 2019-04-10 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.16109
909 | 103577 | Pierce Elementary School Connector Trail |  | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Fauquier County | WARRENTON | Culpeper | NonMPO:NonMPO | Local Assistance Division | John P Price | John.Price@VDOT.Virginia.gov | (540) 347-6371 | John P Price | John.Price@VDOT.Virginia.gov | (540) 347-6371 | Gary Rzepecki | Gary.Rzepecki@fauquiercounty.gov | (540) 422-8550 | 0 |  | 0 | FY2019 | 347000 | 521208 | CONSTRUCTION STARTED | R | Start Delivery milestone finished 64 days late | R | Project estimate is less than $5M and is 20% or more over budget | [5 empty] | 2012-10-01 | 2013-08-20 | 2012-10-01 | 2013-08-20 | R | 2014-05-01 | 2014-01-13 | 2014-05-01 | 2014-01-13 | G | [35 empty] | 2018-04-16 | 2018-03-23 | 2018-08-02 | 2018-06-06 | G | 2018-08-03 | 2018-11-09 | 2018-09-06 | 2018-11-09 | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.35852
910 | 113830 | Install Emergency Vehicle Preemption Software & Hardware | 9999 | Urban | Safety | Locally | Portsmouth | NORFOLK | Hampton Roads | Hampton Roads:Portsmouth | Infrastructure Investment Division | Susan Wilson | Susan.Wilson@vdot.virginia.gov | (757) 956-3099 | Marci Thompson | Marci.Thompson@vdot.virginia.gov | (757) 956-3093 | James Wright, P.E. | wrightj@portsmouthva.gov | (757) 393-8592 | 0 |  | 0 | FY2021 | 301809 | 301809 | NO DATES SET YET-PE OPEN | R | Determine Requirements milestone is 619 days past the expected completion date | G | Project is on budget | 2018-09-04 | 2018-09-04 | 2018-11-30 | 2019-04-18 | R | 2018-12-03 | 2019-04-26 | 2018-12-05 | 2019-05-08 | R | 2018-12-06 |  | 2019-06-13 |  | R | [25 empty] | 2019-06-14 |  | 2020-02-21 |  | R | [5 empty] | 2020-04-24 |  | 2020-05-21 |  | R | 2020-08-11 |  | 2020-08-11 |  | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.19541
911 | 115414 | #SMART20 - Jude's Ferry Road & Route 60 | 0060 | Primary | Safety | VDOT | Powhatan County | CHESTERFIELD | Richmond | Richmond:Powhatan County | Infrastructure Investment Division | Evan Roberts | Evan.Roberts@vdot.virginia.gov | (804) 609-5427 | Evan Roberts | Evan.Roberts@vdot.virginia.gov | (804) 609-5427 |  |  |  | 1 | 2020 | 0 | FY2028 | 2471870 | 2471870 | NO DATES SET YET | G | Start Development milestone is 922 days ahead of the expected completion date | G | Project is on budget | [5 empty] | 2023-08-21 |  | 2023-09-01 |  | G | 2023-09-05 |  | 2024-08-01 |  | G | [5 empty] | 2025-06-09 |  | 2025-06-20 |  | G | 2026-09-25 |  | 2026-10-08 |  | G | 2027-03-11 |  | 2027-09-13 |  | G | 2026-10-27 |  | 2027-05-06 |  | G | 2026-03-18 |  | 2026-09-18 |  | G | [5 empty] | 2027-09-14 |  | 2027-09-14 |  | G | 2027-12-08 |  | 2027-12-08 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.092106
912 | 116845 | GROVE FARM ROAD RURAL ADDITION |  | Secondary | Reconstruction w/o Added Capacity | Locally | Warren County | EDINBURG | Staunton | NonMPO:NonMPO | Local Assistance Division | Kimberly Cameron | Kim.Cameron@vdot.virginia.gov | (540) 332-7886 | Kimberly Cameron | Kim.Cameron@vdot.virginia.gov | (540) 332-7886 | Bob Childress | rchildress@warrencountyva.net | (540) 636-4600 | 0 |  | 0 | FY2025 | 100000 | 100000 | NO DATES SET YET | G | Agreement with Locality milestone is 107 days ahead of the expected completion date | G | Project is on budget | 2021-02-01 |  | 2021-06-08 |  | G | 2021-06-09 |  | 2021-06-29 |  | G | 2021-07-29 |  | 2021-11-22 |  | G | [25 empty] | 2023-12-28 |  | 2024-05-29 |  | G | [5 empty] | 2024-07-26 |  | 2024-08-22 |  | G | 2024-11-13 |  | 2024-11-13 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.20386
913 | 116943 | GREENBELT RIVER BEND |  | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Big Stone Gap | WISE | Bristol | NonMPO:NonMPO | Local Assistance Division | John W Bechtold | John.Bechtold@vdot.virginia.gov | (276) 696-3365 | Roger L Musser | Roger.Musser@VDOT.Virginia.gov | (276) 696-3260 | Stephan Lawson | slawson@bigstonegap.org | (276) 523-0115 | 0 |  | 0 | FY2025 | 642629 | 642629 | NO DATES SET YET | G | Agreement with Locality milestone is 359 days ahead of the expected completion date | G | Project is on budget | 2021-10-01 |  | 2022-02-15 |  | G | 2022-02-16 |  | 2022-03-09 |  | G | 2022-09-13 |  | 2023-01-10 |  | G | [10 empty] | 2024-05-01 |  | 2024-06-05 |  | G | [5 empty] | 2024-06-06 |  | 2024-11-04 |  | G | 2024-10-01 |  | 2025-03-07 |  | G | [5 empty] | 2025-02-13 |  | 2025-03-13 |  | G | 2025-06-02 |  | 2025-06-02 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.348
914 | 117944 | #81 CIP DETOUR IMPROVEMENTS - EXIT 310 AND EXIT 317 | 0011 | Primary | Other | VDOT | Frederick County | EDINBURG | Staunton | NonMPO:NonMPO | Infrastructure Investment Division | Keith M Rider | Keith.Rider@VDOT.Virginia.gov | (434) 856-8145 | Matthew Bond | Matthew.Bond@vdot.virginia.gov | (540) 332-9275 |  |  |  | 0 |  | 0 | FY2024 | 900000 | 900000 | NO DATES SET YET | R | Start Development milestone is 135 days past the expected completion date | G | Project is on budget | [5 empty] | 2020-09-21 |  | 2020-10-09 |  | R | 2020-10-12 |  | 2021-08-16 |  | G | [5 empty] | 2022-03-22 |  | 2022-04-18 |  | G | [5 empty] | 2022-12-09 |  | 2023-04-13 |  | G | [5 empty] | 2022-09-08 |  | 2023-02-13 |  | G | [5 empty] | 2023-05-09 |  | 2023-05-09 |  | G | 2023-07-28 |  | 2023-07-28 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.085973
915 | 15829 | #HB2.FY17 INDIAN RIVER ROAD Ph 7A |  | Urban | Reconstruction w/ Added Capacity | Locally | Virginia Beach | NORFOLK | Hampton Roads | Hampton Roads:Virginia Beach | Infrastructure Investment Division | Susan Wilson | Susan.Wilson@vdot.virginia.gov | (757) 956-3099 | Marci Thompson | Marci.Thompson@vdot.virginia.gov | (757) 956-3093 | Katie E. Shannon | KShannon@vbgov.com | (757) 385-1514 | 1 | 2017 | 0 | FY2024 | 43566697 | 54465000 | ACTIVITY DATES SET | R | Obtained Permits milestone is 628 days past the expected completion date | R | Project estimate is greater than $10M and is over budget by (a) 10% or more or (b) $5M or more | [5 empty] | 1995-10-02 | 1996-03-25 | 1995-10-31 | 1996-03-26 | R | 1999-10-19 | 1999-10-19 | 2001-12-31 | 2000-12-20 | G | [5 empty] | 2005-01-14 | 2005-01-14 | 2005-09-01 | 2005-09-01 | G | 2006-03-03 | 2006-03-03 | 2006-03-10 | 2006-03-10 | G | [5 empty] | 2006-04-04 | 2006-04-04 | 2021-02-02 |  | R | 2018-09-04 | 2020-06-18 | 2019-06-04 |  | R | [5 empty] | 2021-07-01 |  | 2021-07-01 |  | G | 2024-03-04 |  | 2024-05-03 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.22098
916 | 98815 | #HB2.FY17 Godwin Blvd/Route 58 Park & Ride Lot | 0000 | Urban | Safety | Locally | Suffolk | NORFOLK | Hampton Roads | Hampton Roads:Suffolk | Infrastructure Investment Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Johndel A Alcaide | John.Alcaide@vdot.virginia.gov | (757) 956-3098 | Shandon Rogers | srogers@suffolkva.us | 5147683 | 1 | 2017 | 0 | FY2018 | 1130000 | 1017433 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished on-time | G | Project is on budget | [5 empty] | 2012-06-01 | 2012-08-22 | 2012-06-01 | 2012-08-23 | R | 2012-06-01 | 2012-08-01 | 2012-12-31 | 2014-03-07 | R | 2014-03-07 | 2014-03-07 | 2014-03-07 | 2014-03-07 | G | [30 empty] | 2017-05-11 | 2017-05-11 | 2017-06-02 | 2017-06-02 | G | 2017-08-15 | 2017-08-15 | 2017-09-27 | 2017-09-27 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.16567
918 | 102991 | Bridge Road Traffic Signal Upgrades | 0017 | Urban | Traffic Management/Engineering | Locally | Suffolk | NORFOLK | Hampton Roads | Hampton Roads:Suffolk | Infrastructure Investment Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Johndel A Alcaide | John.Alcaide@vdot.virginia.gov | (757) 956-3098 | Jason Souders | jsouders@suffolkva.us | (757) 514-7649 | 0 |  | 0 | FY2020 | 1257000 | 2308868 | AWARDED | R | Start Delivery milestone finished 227 days late | R | Project estimate is less than $5M and is 20% or more over budget | 2017-08-07 | 2017-08-07 | 2017-08-07 | 2017-08-07 | G | 2018-04-11 | 2018-04-11 | 2018-04-19 | 2018-04-19 | G | 2018-05-01 | 2018-05-01 | 2019-05-01 | 2019-11-12 | R | [35 empty] | 2020-01-29 | 2020-07-31 | 2020-02-28 | 2020-11-19 | R | 2020-03-02 | 2021-01-11 | 2020-05-29 | 2021-01-11 | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.28532
919 | 104183 | RTE. 100 (STR. 14513 AND 14515) - BRIDGE REHAB/REPLACE | 0100 | Primary | Bridge Replacement w/o Added Capacity | VDOT | Pulaski County | CHRISTIANSBURG | Salem | NonMPO:NonMPO | Infrastructure Investment Division | Anthony T Marshall | Todd.Marshall@VDOT.Virginia.gov | (540) 387-5460 | Leslie T Repass | Todd.Repass@VDOT.Virginia.gov | (540) 381-7195 |  |  |  | 0 |  | 0 | FY2019 | 7959481 | 7186449 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 82 days early | G | Project is on budget | [5 empty] | 2017-06-12 | 2013-06-21 | 2017-06-12 | 2013-06-21 | G | 2014-09-02 | 2014-09-01 | 2016-10-03 | 2016-10-03 | G | [5 empty] | 2015-02-13 | 2015-02-13 | 2015-05-28 | 2015-05-28 | G | 2016-02-11 | 2016-02-11 | 2016-03-30 | 2016-03-30 | G | 2016-11-28 | 2016-11-28 | 2018-02-01 | 2018-02-01 | G | 2016-03-30 | 2016-03-30 | 2016-09-22 | 2016-09-22 | G | [10 empty] | 2018-03-13 | 2018-03-13 | 2018-03-13 | 2018-03-13 | G | 2018-04-02 | 2018-05-25 | 2018-08-15 | 2018-05-25 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.064239
920 | 105783 | STERLING BOULEVARD - 4 LANE CONSTRUCTION ON NEW ALIGNMENT | 0846 | Secondary | New Construction Roadway | Locally | Loudoun County | LEESBURG | Northern Virginia | Northern Virginia:Loudoun County | Local Assistance Division | Susie X Lue | Susie.Lue@vdot.virginia.gov | (703) 259-2918 | Susie X Lue | Susie.Lue@vdot.virginia.gov | (703) 259-2918 | Bruce Thornberry | Bruce.Thornberry@loudoun.gov | (571) 258-3548 | 0 |  | 0 | FY2024 | 21100000 | 35252513 | ACTIVITY DATES SET | G | Start Purchasing Right-of-Way milestone finished 177 days early | R | Project estimate is greater than $10M and is over budget by (a) 10% or more or (b) $5M or more | 2014-03-15 | 2014-03-15 | 2014-08-26 | 2014-08-26 | G | 2014-09-01 | 2014-09-01 | 2014-10-16 | 2014-10-16 | G | 2015-03-31 | 2015-03-31 | 2019-10-23 | 2019-10-23 | G | [5 empty] | 2019-10-24 | 2019-10-24 | 2020-03-23 | 2020-06-15 | R | 2021-02-04 | 2020-10-27 | 2021-05-27 | 2020-12-01 | G | [5 empty] | 2021-05-28 | 2020-12-02 | 2023-04-26 |  | G | [10 empty] | 2023-05-22 |  | 2023-10-26 |  | G | 2023-10-27 |  | 2024-04-29 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.41209
921 | 106072 | CHILHOWIE SIDEWALKS - TRANSPORTATION ALTERNATIVES |  | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Chilhowie | ABINGDON | Bristol | NonMPO:NonMPO | Local Assistance Division | Chase R Buchanan | Chase.Buchanan@VDOT.Virginia.gov | (276) 696-3251 | Kenneth R Plummer | KR.Plummer@VDOT.Virginia.gov | (276) 696-3261 | John Clark | chilhowie.townmgr@chilhowie.org | (276) 646-3232 | 0 |  | 0 | FY2019 | 643975 | 643975 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 94 days early | G | Project is on budget | [5 empty] | 2014-10-01 | 2016-12-18 | 2014-10-01 | 2016-12-19 | R | 2014-10-31 | 2014-10-01 | 2018-07-28 | 2018-05-24 | G | [10 empty] | 2018-06-20 | 2018-05-11 | 2018-07-03 | 2018-05-24 | G | [20 empty] | 2018-08-30 | 2018-07-24 | 2018-09-07 | 2018-09-04 | G | 2018-10-29 | 2018-09-14 | 2018-12-27 | 2018-09-24 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.24847
922 | 108864 | North Franklin Street Drainage Improvements | 0460 | Urban | Mitigation of Water Pollution Due to Highway Runof | Locally | Christiansburg | CHRISTIANSBURG | Salem | New River Valley:Christiansburg | Local Assistance Division | Adam J Czesnowski | Adam.Czesnowski@vdot.virginia.gov | (540) 541-1216 | Adam J Czesnowski | Adam.Czesnowski@vdot.virginia.gov | (540) 541-1216 | Wayne Nelson | wnelson@christiansburg.org | (540) 382-6120 | 0 |  | 0 | FY2019 | 621000 | 1306100 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 12 days early | R | Project estimate is less than $5M and is 20% or more over budget | 2016-07-01 | 2016-07-01 | 2016-09-26 | 2016-08-29 | G | 2016-09-27 | 2016-10-05 | 2016-09-29 | 2016-10-12 | R | 2016-09-30 | 2016-10-13 | 2017-04-12 | 2017-04-07 | G | [10 empty] | 2018-04-11 | 2018-04-24 | 2018-05-01 | 2018-04-24 | G | [5 empty] | 2018-05-03 | 2018-04-24 | 2018-06-18 | 2018-04-24 | G | [10 empty] | 2018-07-05 | 2018-06-29 | 2018-08-01 | 2018-07-01 | G | 2018-08-02 | 2019-01-22 | 2019-02-04 | 2019-01-23 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.092482
923 | 109057 | AIRPORT DRIVE - NORTHSIDE MULTI-USE TRAIL EXTENSION | 9999 | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Danville | HALIFAX | Lynchburg | Danville:Danville | Local Assistance Division | Sharon S White | Sharon.White@VDOT.Virginia.gov | (434) 856-8220 | Sharon S White | Sharon.White@VDOT.Virginia.gov | (434) 856-8220 | Brian Dunevant | dunevbl@danvilleva.gov | (434) 799-5019 | 0 |  | 0 | FY2022 | 332824 | 332824 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 682 days early | G | Project is on budget | 2017-12-08 | 2017-12-08 | 2017-12-29 | 2017-12-29 | G | 2018-01-02 | 2018-01-02 | 2018-01-25 | 2018-01-25 | G | 2018-01-26 | 2018-01-26 | 2019-01-28 | 2019-01-28 | G | [35 empty] | 2021-02-03 | 2019-09-19 | 2021-03-17 | 2019-09-24 | G | 2021-03-18 | 2019-09-25 | 2021-12-03 | 2020-01-21 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.1888
924 | 110101 | Tinker Creek Trail Extension | 9999 | Miscellaneous | Facilities for Pedestrians and Bicycles | Locally | Roanoke | SALEM | Salem | Roanoke:Roanoke City | Infrastructure Investment Division | Cheryl B Becker | Cheryl.Becker@vdot.virginia.gov | (540) 492-2531 | Cheryl B Becker | Cheryl.Becker@vdot.virginia.gov | (540) 492-2531 | Donnie Underwood | Donnie.Underwood@Roanokeva.gov | (540) 853-1166 | 0 |  | 0 | FY2022 | 7251474 | 7251474 | ACTIVITY DATES SET | G | Start Purchasing Right-of-Way milestone finished on-time | Y | Estimate not current | 2016-10-11 | 2016-10-11 | 2017-02-07 | 2017-02-07 | G | 2017-08-01 | 2017-08-01 | 2017-08-02 | 2017-08-02 | G | 2017-08-03 | 2018-02-07 | 2018-11-01 | 2018-11-01 | G | [10 empty] | 2020-05-26 | 2020-06-12 | 2020-06-12 | 2020-06-12 | G | [5 empty] | 2020-06-16 |  | 2021-06-16 |  | G | [10 empty] | 2021-08-12 |  | 2021-09-09 |  | G | 2021-09-10 |  | 2022-02-08 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.27613
925 | 111291 | #SGR18VB -REHAB BRIDGE, HENRICO COUNTY, STR 9875 CN ONLY | 0157 | Primary | Bridge Rehab w/o Added Capacity | VDOT | Henrico County | ASHLAND | Richmond | Richmond:Henrico County | Infrastructure Investment/Asset Management Division | Clayton M Thomas | Clay.Thomas@VDOT.Virginia.gov | (804) 609-5429 | Clayton M Thomas | Clay.Thomas@VDOT.Virginia.gov | (804) 609-5429 |  |  |  | 0 |  | 1 | FY2023 | 4300000 | 5737104 | ACTIVITY DATES SET | G | Determine Requirements milestone finished 1 days early | R | Project estimate is less than $5M and is 20% or more over budget | [10 empty] | 2018-08-06 | 2018-10-10 | 2019-08-06 | 2019-08-05 | G | [35 empty] | 2022-05-10 |  | 2022-05-10 |  | G | 2022-08-26 |  | 2022-10-24 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.13581
926 | 112204 | SOUTH CHURCH ST. - DRAINAGE ONLY PROJECT | 0000 | Urban | Other | Locally | Marion | ABINGDON | Bristol | NonMPO:NonMPO | Infrastructure Investment Division | John W Bechtold | John.Bechtold@vdot.virginia.gov | (276) 696-3365 | John W Bechtold | John.Bechtold@vdot.virginia.gov | (276) 696-3365 | Jeff Spickard | jspickard@marionva.org | (276) 783-4113 | 0 |  | 0 | FY2020 | 453317 | 554708 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 100 days early | Y | Project estimate is less than $5M and is up to 20% over budget | 2017-10-13 | 2017-10-13 | 2017-12-13 | 2017-12-13 | G | 2017-12-14 | 2017-12-14 | 2018-02-21 | 2018-02-21 | G | 2018-04-26 | 2018-04-26 | 2019-01-15 | 2019-01-15 | G | [35 empty] | 2019-10-28 | 2019-03-18 | 2019-11-25 | 2019-09-16 | G | 2019-11-26 | 2019-09-17 | 2020-01-09 | 2019-10-01 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.08474
927 | 113144 | #SMART22 - Starkey Road/Buck Mtn Rd Int Improvements | 0904 | Secondary | Reconstruction w/o Added Capacity | VDOT | Roanoke County | SALEM | Salem | Roanoke:Roanoke County | Infrastructure Investment Division | Alex H Price | Alex.Price@VDOT.Virginia.gov | (540) 378-5053 | Timothy M Dowdy | Tim.Dowdy@VDOT.Virginia.gov | (540) 387-5332 | Megan Cronise | MCronise@roanokecountyva.gov | (540) 772-2094 | 1 | 2022 | 0 | FY2025 |  | 5634363 | ACTIVITY DATES SET | G | Engage Public milestone finished 147 days early | R | Critical information missing | [5 empty] | 2019-03-01 | 2019-01-16 | 2019-03-14 | 2019-01-16 | G | 2019-03-15 | 2019-01-17 | 2020-02-11 | 2020-02-11 | G | [5 empty] | 2021-03-29 | 2020-11-06 | 2021-04-09 | 2020-11-13 | G | 2022-11-02 |  | 2022-11-16 |  | G | 2023-07-26 |  | 2024-05-14 |  | G | 2022-12-06 |  | 2023-12-06 |  | G | 2022-03-04 |  | 2022-10-04 |  | G | [5 empty] | 2024-11-12 |  | 2024-11-12 |  | G | 2025-04-11 |  | 2025-04-11 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.15359
928 | 113266 | Hunton Park Blvd - Sidewalk | 9999 | Urban | Facilities for Pedestrians and Bicycles | Locally | Henrico County | ASHLAND | Richmond | Richmond:Henrico County | Local Assistance Division | Douglas L Orcutt | Doug.Orcutt@vdot.virginia.gov | (804) 609-5428 | Douglas L Orcutt | Doug.Orcutt@vdot.virginia.gov | (804) 609-5428 | Conner Barnes | bar136@henrico.us | (804) 501-4244 | 0 |  | 0 | FY2022 | 490000 | 490000 | ACTIVITY DATES SET | R | Complete Purchasing Right-of-Way milestone is 44 days past the expected completion date | G | Project is on budget | 2018-08-01 | 2018-07-02 | 2018-10-25 | 2018-09-27 | G | 2018-10-26 | 2018-10-15 | 2018-11-08 | 2018-10-16 | G | 2018-11-09 | 2018-10-02 | 2019-01-10 | 2019-01-10 | G | [10 empty] | 2019-10-18 | 2019-10-18 | 2019-11-01 | 2019-10-18 | G | [5 empty] | 2019-11-05 | 2019-10-21 | 2021-01-08 |  | R | 2018-10-23 | 2021-01-26 | 2021-02-01 | 2021-01-26 | G | [5 empty] | 2021-03-31 |  | 2021-03-31 |  | Y | 2021-04-01 |  | 2021-08-31 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.23586
929 | 113318 | Primary Extension - Roanoke St - Mt Pleasant Rd to Woodland | 0000 | Urban | Resurfacing | Locally | Christiansburg | CHRISTIANSBURG | Salem | New River Valley:Christiansburg | Local Assistance Division | Adam J Czesnowski | Adam.Czesnowski@vdot.virginia.gov | (540) 541-1216 | Adam J Czesnowski | Adam.Czesnowski@vdot.virginia.gov | (540) 541-1216 | Wayne Nelson |  | (540) 382-6120 | 0 |  | 0 | FY2019 | 246247 | 246247 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 163 days early | G | Project is on budget | 2018-10-01 | 2018-08-01 | 2018-12-28 | 2018-08-16 | G | 2018-12-31 | 2018-09-26 | 2019-01-03 | 2018-10-02 | G | 2019-01-04 | 2018-10-01 | 2019-03-22 | 2018-10-02 | G | [35 empty] | 2018-12-03 | 2018-12-03 | 2018-12-31 | 2018-12-12 | G | 2019-05-28 | 2019-01-02 | 2019-06-28 | 2019-01-16 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.06004
930 | 106049 | OLD COURTHOUSE ROAD SRTS SIDEWALK - VIENNA |  | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Vienna | FAIRFAX | Northern Virginia | Northern Virginia:Vienna | Local Assistance Division | Jeffrey S Daily | Jeff.Daily@VDOT.Virginia.gov | (703) 259-2993 | Jeffrey S Daily | Jeff.Daily@VDOT.Virginia.gov | (703) 259-2993 | Mike Gallaghar | mgallaghar@viennava.gov | (703) 255-6380 | 0 |  | 0 | FY2021 | 132708 | 2337839 | ADVERTISED | G | Solicit Bids milestone finished on-time | R | Project estimate is less than $5M and is 20% or more over budget | 2014-10-31 | 2014-10-31 | 2014-11-04 | 2014-11-04 | G | 2014-10-01 | 2015-02-06 | 2014-10-01 | 2015-02-06 | R | 2014-10-31 | 2014-10-31 | 2015-02-28 | 2015-02-28 | G | [35 empty] | 2020-06-01 | 2020-06-01 | 2020-11-05 | 2020-11-05 | G | 2020-11-06 | 2020-11-06 | 2021-06-30 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.3279
931 | 108792 | Virginia Beach Systemic FYA |  | Urban | Safety | Locally | Virginia Beach | NORFOLK | Hampton Roads | Hampton Roads:Virginia Beach | Infrastructure Investment Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Marci Thompson | Marci.Thompson@vdot.virginia.gov | (757) 956-3093 | Katie Shannon | kshannon@vbgov.com | (757) 385-1514 | 0 |  | 0 | FY2019 | 600500 | 501444 | ACTIVITY DATES SET | R | Solicit Bids milestone is 1067 days past the expected completion date | G | Project is on budget | 2016-07-01 | 2016-08-04 | 2016-09-26 | 2016-09-09 | G | 2016-09-27 | 2016-09-02 | 2016-09-29 | 2016-09-09 | G | 2016-09-30 | 2016-09-12 | 2017-04-12 | 2017-05-30 | R | [35 empty] | 2018-02-23 |  | 2018-03-22 |  | R | 2018-09-04 |  | 2019-03-01 |  | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.15224
932 | 108882 | #SMART18 - West Main Street Sidewalk Installation | 0011 | Primary | Facilities for Pedestrians and Bicycles | VDOT | Roanoke County | SALEM | Salem | Roanoke:Roanoke County | Infrastructure Investment Division | Phillip V Hammack | Phillip.Hammack@VDOT.Virginia.gov | (540) 378-5041 | Phillip V Hammack | Phillip.Hammack@VDOT.Virginia.gov | (540) 378-5041 | David Holladay |  |  | 1 | 2018 | 0 | FY2021 | 1036699 | 1191298 | ACTIVITY DATES SET | R | Solicit Bids milestone is 313 days past the expected completion date | Y | Project estimate is less than $5M and is up to 20% over budget | [5 empty] | 2016-06-16 | 2017-03-31 | 2017-07-18 | 2017-04-01 | G | 2017-07-19 | 2017-07-19 | 2017-08-29 | 2017-08-29 | G | [5 empty] | 2018-08-27 | 2018-08-27 | 2018-09-10 | 2018-09-10 | G | 2019-02-12 | 2020-01-22 | 2019-04-05 | 2020-01-30 | R | 2019-08-28 | 2019-12-26 | 2020-03-10 | 2019-12-26 | G | 2019-04-23 | 2020-02-24 | 2019-10-25 | 2020-05-19 | R | 2018-11-26 | 2019-04-23 | 2019-12-16 | 2019-04-23 | G | [5 empty] | 2020-04-14 |  | 2020-04-14 |  | R | 2020-05-29 |  | 2020-08-21 |  | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | SAAP CONTRACT | 0 | 0 | 0.14853
933 | 109889 | High Friction Pavement Initiative | 9999 | Miscellaneous | Safety | VDOT | Bristol District-wide |  | Bristol | NonMPO:NonMPO | Infrastructure Investment Division | Jeffrey Buchanan | Jeff.Buchanan@vdot.virginia.gov | (276) 415-3440 | Brandi Halloway | Brandi.Halloway@vdot.virginia.gov | (276) 696-3254 |  |  |  | 0 |  | 0 | FY2019 | 512000 | 959827 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 7 days early | R | Project estimate is less than $5M and is 20% or more over budget | [5 empty] | 2016-08-01 | 2016-08-01 | 2016-08-12 | 2017-06-15 | R | 2016-08-15 | 2017-07-05 | 2017-04-11 | 2017-08-14 | R | [5 empty] | 2018-03-16 | 2018-04-02 | 2018-03-16 | 2018-04-02 | R | [5 empty] | 2018-06-01 | 2018-06-01 | 2018-06-01 | 2018-06-01 | G | [5 empty] | 2018-06-14 | 2018-04-17 | 2018-09-21 | 2018-04-17 | G | [5 empty] | 2018-11-13 | 2018-11-13 | 2018-11-13 | 2018-11-13 | G | 2019-01-08 | 2019-01-23 | 2019-01-30 | 2019-01-23 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.068327
934 | 110332 | #HB2.FY17 BROAD STREET PEDESTRIAN CROSSINGS | 0007 | Urban | Facilities for Pedestrians and Bicycles | Locally | Falls Church | FAIRFAX | Northern Virginia | Northern Virginia:Falls Church | Infrastructure Investment Division | Amir Salahshoor | A.Salahshoor@VDOT.Virginia.gov | (703) 259-1957 | Saif-Ur Qargha | Saif.Qargha@vdot.virginia.gov | (703) 259-3223 | Alireza (Ali) Khavari, PE, PTOE | akhavari@fallschurchva.gov | (571) 319-3558 | 1 | 2017 | 0 | FY2022 | 1000000 | 1049000 | ACTIVITY DATES SET | R | Complete Purchasing Right-of-Way milestone is 157 days past the expected completion date | Y | Project estimate is less than $5M and is up to 20% over budget | 2017-07-17 | 2016-11-15 | 2017-10-10 | 2017-02-14 | G | 2017-10-11 | 2017-02-15 | 2017-10-13 | 2017-07-26 | G | 2017-10-16 | 2017-07-27 | 2018-04-25 | 2018-11-14 | R | [10 empty] | 2019-11-14 | 2019-11-14 | 2019-12-06 | 2020-02-11 | R | [5 empty] | 2019-12-10 | 2020-02-14 | 2020-09-17 |  | R | [10 empty] | 2020-10-05 |  | 2021-03-04 |  | Y | 2021-03-05 |  | 2021-07-26 |  | G | Delay due to changes in scope of work, project management, plan designs, or resolution of public comments | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.30096
935 | 111688 | #SGR18VB - VAN BUREN RD OVER QUANTICO CREEK - Fed 14320 | 0627 | Secondary | Bridge Rehab w/o Added Capacity | VDOT | Prince William County | MANASSAS | Northern Virginia | Northern Virginia:Prince William County | Infrastructure Investment/Asset Management Division | Gary Runco | Gary.Runco@vdot.virginia.gov | (703) 259-3341 | Mehrdad Naderi | Mehrdad.Naderi@vdot.virginia.gov | (703) 259-2217 |  |  |  | 0 |  | 1 | FY2021 | 1280849 | 1294787 | AWARDED | G | Start Delivery milestone finished 15 days early | Y | Project estimate is less than $5M and is up to 20% over budget | [10 empty] | 2020-02-03 | 2019-09-02 | 2020-02-07 | 2020-03-27 | R | [25 empty] | 2020-02-03 | 2020-04-15 | 2020-08-05 | 2020-04-20 | G | [5 empty] | 2020-09-08 | 2020-09-08 | 2020-09-08 | 2020-09-08 | G | 2020-12-02 | 2020-11-17 | 2020-12-02 | 2020-11-17 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 1 | 0.19537
936 | 112894 | PEDESTRIAN CROSSINGS & SIGNAL SAFETY MODIFICATIONS | 9999 | Primary | Safety | VDOT | Fredericksburg District-wide |  | Fredericksburg | Fredericksburg:Fredericksburg District-wide | Infrastructure Investment Division | Emmett T Newton | Tommy.Newton@VDOT.Virginia.gov | (540) 899-4541 | Benjamin Ernst | Benjamin.Ernst@vdot.virginia.gov | (571) 585-0902 |  |  |  | 0 |  | 0 | FY2019 | 148983 | 148983 | AWARDED | G | Start Delivery milestone finished on-time | G | Project is on budget | [5 empty] | 2018-05-01 | 2018-04-01 | 2018-05-01 | 2018-04-20 | G | 2018-05-02 | 2018-04-23 | 2018-08-09 | 2018-08-09 | G | [5 empty] | 2018-09-13 | 2018-08-23 | 2018-09-26 | 2018-08-23 | G | [25 empty] | 2018-10-12 | 2018-10-19 | 2018-10-19 | 2018-10-19 | G | 2018-10-22 | 2018-10-22 | 2018-10-26 | 2018-10-26 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | WORK/TASK ORDER | 1 | 0 | 0.067014
937 | 113197 | 32ND AND MAIN STREET INTERSECTION IMPROVEMENT | 0007 | Urban | Facilities for Pedestrians and Bicycles | Locally | Purcellville | LEESBURG | Northern Virginia | Northern Virginia:Purcellville | Local Assistance Division | Kimberly Mccool | Kimberly.McCool@vdot.virginia.gov | (703) 259-3220 | Christer P Carshult | Christer.Carshult@vdot.virginia.gov | (703) 259-1765 | Dale Lehning |  |  | 0 |  | 0 | FY2024 | 1704874 | 1704874 | ACTIVITY DATES SET | G | Complete Purchasing Right-of-Way milestone finished 764 days early | G | Project is on budget | 2018-10-31 | 2018-07-01 | 2019-03-29 | 2018-08-13 | G | 2018-08-14 | 2018-08-14 | 2018-09-11 | 2018-09-11 | G | 2018-10-31 | 2019-02-19 | 2019-05-30 | 2020-10-23 | R | [10 empty] | 2022-11-29 | 2020-10-26 | 2022-11-29 | 2020-10-26 | G | [5 empty] | 2022-11-29 | 2020-10-26 | 2022-11-29 | 2020-10-26 | G | 2022-08-31 |  | 2023-07-03 |  | G | [5 empty] | 2023-03-03 |  | 2023-08-31 |  | G | 2023-09-01 |  | 2024-01-31 |  | G | Preliminary design and/or investigations are still underway | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.33874
938 | 113283 | VAR LOC - RESURFACE |  | Urban | Resurfacing | Locally | Hopewell | PETERSBURG | Richmond | Tri-Cities:Hopewell | Local Assistance Division | James Shepherd | James.Shepherd@vdot.virginia.gov | (804) 609-5305 | Brian J Lokker | Brian.Lokker@VDOT.Virginia.gov | (804) 524-6010 | Austin Anderson | AANDERSON@HOPEWELLVA.GOV | (804) 541-2319 | 0 |  | 0 | FY2019 | 800000 | 800000 | CONSTRUCTION COMPLETED | G | Obtained Permits milestone finished 7 days early | G | Project is on budget | 2018-07-02 | 2018-08-13 | 2018-09-25 | 2018-08-14 | G | 2018-09-26 | 2018-09-25 | 2018-11-07 | 2018-09-26 | G | 2018-11-08 | 2018-09-27 | 2019-05-20 | 2019-04-09 | G | [25 empty] | 2019-07-18 | 2019-07-24 | 2019-07-31 | 2019-07-24 | G | [5 empty] | 2019-05-22 | 2019-04-19 | 2019-05-31 | 2019-04-24 | G | 2019-06-03 | 2019-04-23 | 2019-06-28 | 2019-04-24 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.050264
939 | 113487 | #SGR19VB - RT 33 OVER I-81 EXIT 247 IMPR WBL (STR 20441) | 0033 | Primary | Bridge Replacement w/o Added Capacity | VDOT | Rockingham County | HARRISONBURG | Staunton | Harrisonburg:Rockingham County | Infrastructure Investment/Asset Management Division | Randolph S Kiser | Randy.Kiser@VDOT.Virginia.gov | (540) 332-9092 | John-Allen L Ennis | JohnAllen.Ennis@VDOT.Virginia.gov | (540) 332-9118 |  |  |  | 0 |  | 1 | FY2023 | 11928824 | 15552374 | ACTIVITY DATES SET | R | Start Purchasing Right-of-Way milestone is 27 days past the expected completion date | R | Project estimate is greater than $10M and is over budget by (a) 10% or more or (b) $5M or more | [10 empty] | 2018-08-06 | 2018-08-06 | 2018-11-30 | 2019-10-18 | R | [10 empty] | 2021-01-08 |  | 2021-01-25 |  | R | 2021-08-16 |  | 2022-10-11 |  | G | 2021-02-10 |  | 2021-10-11 |  | G | 2020-11-23 |  | 2022-04-21 |  | G | [5 empty] | 2022-11-08 |  | 2022-11-08 |  | G | 2022-11-09 |  | 2023-06-15 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.075767
940 | 113490 | GILLIES CREEK GREENWAY PH II |  | Primary | Facilities for Pedestrians and Bicycles | Locally | Richmond | ASHLAND | Richmond | Richmond:Richmond | Local Assistance Division | Jorg Huckabee-Mayfield | Jorg.Huckabee-Mayfield@VDOT.Virginia.gov | (804) 609-5292 | Jorg Huckabee-Mayfield | Jorg.Huckabee-Mayfield@VDOT.Virginia.gov | (804) 609-5292 | Adel Edward | Adel.Edward@RichmondGov.com | (804) 646-6584 | 0 |  | 0 | FY2023 | 525000 | 525000 | NO DATES SET YET-PE OPEN | Y | Determine Requirements milestone is 18 days ahead of the expected completion date and there is a risk of missing this milestone date | G | Project is on budget | 2019-10-02 | 2019-10-02 | 2020-02-14 | 2019-10-16 | G | 2020-02-25 | 2019-09-15 | 2020-03-09 | 2019-10-16 | G | 2020-08-28 |  | 2021-03-11 |  | Y | [25 empty] | 2020-11-09 |  | 2021-07-16 |  | G | [5 empty] | 2022-03-30 |  | 2022-04-26 |  | G | 2022-10-10 |  | 2022-10-10 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.21506
941 | 113943 | Renaissance Drive Phase II | 0873 | Secondary | New Construction Roadway | Locally | Frederick County | EDINBURG | Staunton | NonMPO:NonMPO | Local Assistance Division | Steven K Damron | Steven.Damron@VDOT.Virginia.gov | (804) 786-1172 | Jamison Brown | Jamison.Brown@vdot.virginia.gov | (540) 332-7389 | John Bishop | jbishop@fcva.us | (540) 665-5651 | 0 |  | 0 | FY2022 | 4621525 | 4216561 | ACTIVITY DATES SET | G | Start Purchasing Right-of-Way milestone finished 18 days early | G | Project is on budget | 2018-08-01 | 2019-04-22 | 2018-10-25 | 2019-06-19 | R | 2018-10-26 | 2019-06-24 | 2018-10-30 | 2019-08-01 | R | 2018-10-31 | 2019-04-18 | 2019-05-10 | 2019-11-14 | R | [10 empty] | 2020-11-13 | 2020-10-29 | 2020-12-07 | 2020-11-19 | G | [5 empty] | 2020-12-09 |  | 2021-09-17 |  | G | [10 empty] | 2021-10-05 |  | 2021-11-02 |  | G | 2022-01-28 |  | 2022-01-28 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.24333
942 | 114190 | SHOULDER WIDENING AND RUMBLE STRIPS - ORANGE COUNTY | 0003 | Primary | Safety | VDOT | Orange County | LOUISA | Culpeper | NonMPO:NonMPO | Infrastructure Investment Division | Ken Connors |  |  | Caroline Awua-Mensah | Caroline.Awua-Mensah@vdot.virginia.gov | (540) 829-7618 |  |  |  | 0 |  | 0 | FY2020 | 513600 | 513600 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 63 days early | G | Project is on budget | [10 empty] | 2019-03-11 | 2019-03-11 | 2019-03-15 | 2019-03-15 | G | [25 empty] | 2018-09-12 | 2018-09-12 | 2018-09-27 | 2018-09-27 | G | [5 empty] | 2018-12-04 | 2019-03-12 | 2018-12-04 | 2019-03-12 | R | 2019-07-11 | 2019-05-15 | 2019-07-17 | 2019-05-15 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.072362
943 | 115304 | #SGR20LP - Primary Extension - Blacksburg - S Main St | 0460 | Urban | Reconstruction w/o Added Capacity | Locally | Blacksburg | CHRISTIANSBURG | Salem | New River Valley:Blacksburg | Local Assistance Division | Adam J Czesnowski | Adam.Czesnowski@vdot.virginia.gov | (540) 541-1216 | Adam J Czesnowski | Adam.Czesnowski@vdot.virginia.gov | (540) 541-1216 | John Boyer | jboyer@blacksburg.gov | (540) 443-1204 | 0 |  | 0 | FY2020 | 39846 | 39846 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 193 days early | G | Project is on budget | 2020-01-02 | 2019-07-01 | 2020-03-30 | 2019-07-25 | G | 2020-03-31 | 2019-09-02 | 2020-04-02 | 2019-09-05 | G | 2020-04-03 | 2019-09-18 | 2020-10-06 | 2019-09-19 | G | [35 empty] | 2019-12-31 | 2019-11-22 | 2019-12-31 | 2019-11-22 | G | 2020-01-27 | 2019-11-25 | 2020-06-30 | 2019-12-20 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.15818
944 | 115506 | #SMART20 Shoulder Widening Rte13 | 0013 | Urban | Safety | VDOT | Northampton County | ACCOMAC | Hampton Roads | NonMPO:NonMPO | Infrastructure Investment Division | John G Harman | JohnG.Harman@vdot.virginia.gov | (757) 956-3269 | John G Harman | JohnG.Harman@vdot.virginia.gov | (757) 956-3269 | Susan McGhee | smcghee@co.northampton.va.us | (757) 678-0443 | 1 | 2020 | 0 | FY2022 | 2923357 | 3019249 | NO DATES SET YET-PE OPEN | R | Determine Requirements milestone is 212 days past the expected completion date | Y | Project estimate is less than $5M and is up to 20% over budget | [5 empty] | 2019-11-15 | 2019-12-02 | 2019-12-02 | 2019-12-02 | G | 2019-12-03 | 2019-12-03 | 2020-07-24 |  | R | [5 empty] | 2021-04-05 |  | 2021-05-14 |  | G | [5 empty] | 2021-08-30 |  | 2021-12-27 |  | G | [5 empty] | 2021-08-13 | 2020-06-18 | 2021-11-16 |  | G | [5 empty] | 2022-01-11 |  | 2022-01-11 |  | G | 2022-04-05 |  | 2022-04-05 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.1184
945 | 116170 | #I81CIP SB MM 8.1 WIDEN TO THREE LANES (ID #27) | 0081 | Interstate | Reconstruction w/ Added Capacity | VDOT | Washington County | ABINGDON | Bristol | Bristol:Washington County | Infrastructure Investment Division | Donald A Necessary | Donald.Necessary@VDOT.Virginia.gov | (276) 696-3285 | Marvin E Holley | Gene.Holley@VDOT.Virginia.gov | (276) 696-3255 |  |  |  | 0 |  | 0 | FY2025 | 33100000 | 33100000 | ACTIVITY DATES SET | G | Determine Requirements milestone finished 196 days early | G | Project is on budget | [5 empty] | 2020-07-01 | 2019-12-02 | 2020-07-15 | 2019-12-11 | G | 2020-07-16 | 2019-12-12 | 2021-08-24 | 2021-02-09 | G | [5 empty] | 2022-08-23 |  | 2022-09-06 |  | G | 2023-12-05 |  | 2023-12-18 |  | G | 2024-05-15 |  | 2024-11-19 |  | G | 2024-01-05 |  | 2024-07-11 |  | G | 2023-05-22 |  | 2024-01-29 |  | G | [5 empty] | 2024-12-10 |  | 2024-12-10 |  | G | 2025-04-03 |  | 2025-04-03 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.10885
946 | 116723 | NOVA SYSTEMIC PEDESTRIAN CROSSINGS PH3 | 9999 | Miscellaneous | Safety | VDOT | Northern Virginia District-wide |  | Northern Virginia | Northern Virginia:Northern Virginia District-wide | Infrastructure Investment/Asset Management Division | Waqar A Siddiqui | Sid.Siddiqui@VDOT.Virginia.gov | (703) 259-3225 | Tienjung Ho | Tien-Jung.Ho@VDOT.Virginia.gov | (703) 259-2752 |  |  |  | 0 |  | 0 | FY2025 | 3762488 | 3762488 | NO DATES SET YET | G | Start Development milestone is 981 days ahead of the expected completion date | G | Project is on budget | [5 empty] | 2023-10-30 |  | 2023-10-30 |  | G | 2023-10-31 |  | 2024-06-07 |  | G | [5 empty] | 2024-06-10 |  | 2024-06-21 |  | G | [25 empty] | 2024-07-10 |  | 2024-07-16 |  | G | 2024-07-17 |  | 2024-07-23 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | WORK/TASK ORDER | 0 | 0 | 0.067544
947 | 116887 | SPICERS MILL ROAD - MILLING, PAVEMENT & RECONSTRUCTION | 9999 | Urban | Resurfacing | Locally | Orange | LOUISA | Culpeper | NonMPO:NonMPO | Local Assistance Division | Gregory J Cooley | Gregory.Cooley@vdot.virginia.gov | (434) 906-7979 | John P Price | John.Price@VDOT.Virginia.gov | (540) 347-6371 | John Cooley | townplanner@townoforangeva.org | (540) 672-6917 | 0 |  | 0 | FY2023 | 105140 | 105140 | NO DATES SET YET | G | Agreement with Locality milestone is 326 days ahead of the expected completion date | G | Project is on budget | 2021-09-01 |  | 2022-01-13 |  | G | [5 empty] | 2022-01-18 |  | 2022-01-31 |  | G | [25 empty] | 2021-09-30 |  | 2022-03-08 |  | G | [5 empty] | 2022-05-04 |  | 2022-06-01 |  | G | 2022-08-19 |  | 2022-08-19 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.04795
948 | 116965 | #SGR21LP WEST MAIN STREET PRIMARY EXTENSION PAVING |  | Primary | Resurfacing | VDOT | Luray | HARRISONBURG | Staunton | NonMPO:NonMPO | Infrastructure Investment Division | Joel D Denunzio | Joel.DeNunzio@VDOT.virginia.gov | (540) 332-9093 | Mark W Hisey | Mark.Hisey@VDOT.Virginia.gov | (540) 280-4820 |  |  |  | 0 |  | 1 | FY2021 | 228139 | 228139 | ACTIVITY DATES SET | Y | Solicit Bids milestone is 51 days ahead of the expected completion date and there is a risk of missing this milestone date | G | Project is on budget | [5 empty] | 2021-01-11 | 2020-11-03 | 2021-02-02 | 2020-11-24 | G | 2021-02-03 | 2020-11-25 | 2021-12-03 | 2021-01-11 | G | [5 empty] | 2021-01-12 | 2021-01-12 | 2021-01-12 | 2021-01-12 | G | [5 empty] | 2020-12-28 | 2021-01-14 | 2021-04-12 | 2021-01-19 | G | [15 empty] | 2021-04-13 |  | 2021-04-13 |  | Y | 2021-06-30 |  | 2021-06-30 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.060601
949 | 117034 | S. Laburnum Ave SB Sidewalk | 9999 | Secondary | Facilities for Pedestrians and Bicycles | Locally | Henrico County | ASHLAND | Richmond | Richmond:Henrico County | Local Assistance Division | Douglas L Orcutt | Doug.Orcutt@vdot.virginia.gov | (804) 609-5428 | Douglas L Orcutt | Doug.Orcutt@vdot.virginia.gov | (804) 609-5428 | TBD |  | TBD | 0 |  | 0 | FY2029 | 2992440 | 2992440 | NO DATES SET YET | G | Agreement with Locality milestone is 1543 days ahead of the expected completion date | G | Project is on budget | 2025-01-06 |  | 2025-05-14 |  | G | 2025-05-15 |  | 2025-06-05 |  | G | 2025-12-15 |  | 2026-04-10 |  | G | [10 empty] | 2027-07-30 |  | 2027-09-02 |  | G | [5 empty] | 2027-09-03 |  | 2028-02-09 |  | G | 2028-01-05 |  | 2028-06-05 |  | G | [5 empty] | 2028-05-12 |  | 2028-06-09 |  | G | 2028-08-29 |  | 2028-08-29 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.36074
950 | 113685 | PARK ROAD PEDESTRIAN IMPROVEMENTS |  | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Harrisonburg | HARRISONBURG | Staunton | Harrisonburg:Harrisonburg | Local Assistance Division | Donald F Komara | Donald.Komara@VDOT.Virginia.gov | (540) 434-2587 | Michael S Fulcher | Michael.Fulcher@VDOT.Virginia.gov | (540) 332-2243 | Aaron Rhoney | Aaron.Rhoney@harrisonburgva.gov | (540) 434-5928 | 0 |  | 0 | FY2021 | 125874 | 171374 | AWARDED | G | Start Delivery milestone finished 1 days early | R | Project estimate is less than $5M and is 20% or more over budget | 2018-11-01 | 2018-11-01 | 2019-02-01 | 2018-12-04 | G | 2019-02-04 | 2019-02-01 | 2019-02-06 | 2019-02-01 | G | 2019-02-07 | 2019-02-04 | 2019-08-12 | 2019-08-12 | G | [35 empty] | 2020-08-26 | 2020-08-26 | 2020-09-23 | 2020-09-23 | G | 2020-12-16 | 2020-12-15 | 2020-12-16 | 2020-12-15 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.21134
951 | 114064 | GRAVES MILL ROAD - INSTALL ADAPTIVE SIGNAL CONTROLS | 6009 | Urban | Safety | Locally | Lynchburg | APPOMATTOX | Lynchburg | Lynchburg:Lynchburg | Infrastructure Investment Division | Gregg Allen | Gregg.Allen@vdot.virginia.gov | (434) 426-5575 | Jay S Brown | Jay.Brown@VDOT.Virginia.gov | (434) 856-8246 | Lee Newland | lee.newland@lynchburgva.gov | (434) 455-3935 | 0 |  | 0 | FY2022 | 462500 | 462500 | ACTIVITY DATES SET | G | Determine Requirements milestone finished on-time | Y | Estimate not current | 2020-01-31 | 2019-08-01 | 2020-04-24 | 2019-08-15 | G | 2020-04-27 | 2019-10-23 | 2020-04-29 | 2019-10-30 | G | 2020-04-30 | 2020-04-30 | 2020-11-03 | 2020-11-03 | G | [10 empty] | 2021-04-19 |  | 2021-05-07 |  | G | [5 empty] | 2021-05-11 |  | 2021-10-29 |  | G | [10 empty] | 2021-11-17 |  | 2021-12-16 |  | G | 2022-03-11 |  | 2022-06-17 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.19142
952 | 114864 | MOUNT VERNON AVE N MULTI-MODAL & SAFETY IMPV | 6591 | Urban | Facilities for Pedestrians and Bicycles | Locally | Alexandria | FAIRFAX | Northern Virginia | Northern Virginia:Alexandria | Infrastructure Investment Division | Amir Salahshoor | A.Salahshoor@VDOT.Virginia.gov | (703) 259-1957 | Robert J Strevell | Robert.Strevell@vdot.virginia.gov | (703) 259-1988 | Christopher Ziemann | christopher.ziemann@alexandriava.gov | (703) 746-4083 | 0 |  | 0 | FY2023 | 750000 | 750000 | NO DATES SET YET-PE OPEN | R | Determine Requirements milestone is 83 days past the expected completion date | G | Project is on budget | 2019-07-08 | 2019-07-08 | 2020-01-31 | 2020-06-26 | R | 2020-02-03 | 2020-06-29 | 2020-02-28 | 2020-07-08 | R | 2020-03-02 |  | 2020-11-30 |  | R | [25 empty] | 2020-10-08 |  | 2021-06-16 |  | G | [5 empty] | 2022-01-04 |  | 2022-05-31 |  | G | 2022-08-18 |  | 2023-02-28 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.21651
953 | 115359 | #SGR20LP - Atlantic Avenue | 0060 | Urban | Restoration and Rehabilitation | Locally | Virginia Beach | NORFOLK | Hampton Roads | Hampton Roads:Virginia Beach | Infrastructure Investment/Asset Management Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Marci Thompson | Marci.Thompson@vdot.virginia.gov | (757) 956-3093 | Jimmy Evans | jrevans@vbgov.com | (757) 385-1505 | 0 |  | 1 | FY2020 | 214811 | 214811 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 213 days early | G | Project is on budget | 2019-08-05 | 2019-07-03 | 2019-10-29 | 2019-08-07 | G | [5 empty] | 2019-08-05 | 2019-07-18 | 2019-08-16 | 2019-08-08 | G | [35 empty] | 2019-12-03 | 2019-09-20 | 2019-12-31 | 2019-09-20 | G | 2020-03-24 | 2019-09-20 | 2020-04-20 | 2019-09-20 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.076395
955 | 116369 | FRED-EX - I95 EXPRESS LANES EXTENSION; EXIT 143 TO EXIT 133 | 0095 | Interstate | Reconstruction w/ Added Capacity | VDOT | Stafford County | FREDERICKSBURG | Fredericksburg | Fredericksburg:Stafford County | Infrastructure Investment Division | Michelle A Shropshire | Michelle.Shropshire@VDOT.Virginia.gov | (540) 899-4278 | Robert Galen Ridgell | Robert.Ridgell@vdot.virginia.gov | (540) 372-3549 |  |  |  | 0 |  | 0 | FY2020 | 5000000 | 5000000 | CONSTRUCTION STARTED | G | Start Delivery milestone finished on-time | G | Project is on budget | [10 empty] | 2019-09-27 | 2019-09-27 | 2019-10-03 | 2019-10-03 | G | [35 empty] | 2019-12-13 | 2019-12-13 | 2019-12-13 | 2019-12-13 | G | 2019-12-13 | 2019-12-13 | 2019-12-13 | 2019-12-13 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | DESIGN BUILD/PPTA | 1 | 0 | 0.069554
956 | 116854 | RTE 11 MAIN STREET BIKE PED CONNECTIONS |  | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Woodstock | EDINBURG | Staunton | NonMPO:NonMPO | Local Assistance Division | Kimberly Cameron | Kim.Cameron@vdot.virginia.gov | (540) 332-7886 | Jamison Brown | Jamison.Brown@vdot.virginia.gov | (540) 332-7389 | Lemuel Hancock | lemuel.hancock@townofwoodstockva.gov | (540) 459-3621 | 0 |  | 0 | FY2025 | 678875 | 678875 | NO DATES SET YET | G | Agreement with Locality milestone is 57 days ahead of the expected completion date | G | Project is on budget | 2020-12-08 |  | 2021-04-19 |  | G | 2021-04-20 |  | 2021-05-10 |  | G | 2021-11-16 |  | 2022-03-16 |  | G | [10 empty] | 2023-07-05 |  | 2023-08-08 |  | G | [5 empty] | 2023-08-09 |  | 2024-01-11 |  | G | 2023-12-07 |  | 2024-05-08 |  | G | [5 empty] | 2024-04-17 |  | 2024-05-14 |  | G | 2024-08-02 |  | 2024-08-02 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.42925
957 | 116896 | WARRENTON MAIN ST PED CROSSINGS SIDEWALKS & TRAFFIC CALMING | 0015 | Urban | Facilities for Pedestrians and Bicycles | Locally | Warrenton | WARRENTON | Culpeper | NonMPO:NonMPO | Local Assistance Division | Gregory J Cooley | Gregory.Cooley@vdot.virginia.gov | (434) 906-7979 | John P Price | John.Price@VDOT.Virginia.gov | (540) 347-6371 | Paul Bernard | pbernard@warrentonva.gov | 540347858 | 0 |  | 0 | FY2024 | 1471126 | 1471126 | NO DATES SET YET | G | Agreement with Locality milestone is 50 days ahead of the expected completion date | G | Project is on budget | 2020-12-01 |  | 2021-04-12 |  | G | 2021-04-13 |  | 2021-05-03 |  | G | 2021-11-08 |  | 2022-03-09 |  | G | [25 empty] | 2023-03-06 |  | 2023-08-01 |  | G | [5 empty] | 2023-09-28 |  | 2023-10-26 |  | G | 2024-01-23 |  | 2024-01-23 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.11709
958 | 117016 | #SGR21VB - RTE 764 OVER GREASY CR (STR. 4762)-SUPER REPLACE | 0764 | Secondary | Bridge Rehab w/o Added Capacity | VDOT | Carroll County | MARTINSVILLE | Salem | NonMPO:NonMPO | Infrastructure Investment Division | Anthony T Marshall | Todd.Marshall@VDOT.Virginia.gov | (540) 387-5460 | Dana E Pauley | Dana.Pauley@VDOT.Virginia.gov | (540) 387-5476 |  |  |  | 0 |  | 1 | FY2025 | 2103329 | 2103329 | NO DATES SET YET | G | Start Development milestone is 516 days ahead of the expected completion date | G | Project is on budget | [5 empty] | 2022-07-01 |  | 2022-07-22 |  | G | 2022-07-25 |  | 2023-05-26 |  | G | [5 empty] | 2023-10-20 |  | 2023-11-17 |  | G | [15 empty] | 2024-06-17 |  | 2024-11-14 |  | G | [5 empty] | 2025-02-11 |  | 2025-02-14 |  | G | 2025-05-06 |  | 2025-05-06 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.16726
959 | 117050 | Lake Brook Drive Sidewalk | 9999 | Secondary | Facilities for Pedestrians and Bicycles | Locally | Henrico County | ASHLAND | Richmond | Richmond:Henrico County | Local Assistance Division | Douglas L Orcutt | Doug.Orcutt@vdot.virginia.gov | (804) 609-5428 | Douglas L Orcutt | Doug.Orcutt@vdot.virginia.gov | (804) 609-5428 | TBD |  | TBD | 0 |  | 0 | FY2029 | 218900 | 218900 | NO DATES SET YET | G | Agreement with Locality milestone is 1543 days ahead of the expected completion date | G | Project is on budget | 2025-01-06 |  | 2025-05-14 |  | G | 2025-05-15 |  | 2025-06-05 |  | G | 2025-12-15 |  | 2026-04-10 |  | G | [10 empty] | 2027-07-30 |  | 2027-09-02 |  | G | [5 empty] | 2027-09-03 |  | 2028-02-09 |  | G | 2028-01-05 |  | 2028-06-05 |  | G | [5 empty] | 2028-05-12 |  | 2028-06-09 |  | G | 2028-08-29 |  | 2028-08-29 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.346
960 | 117137 | ADA Ramps Phase 5 | 0000 | Urban | Facilities for Pedestrians and Bicycles | Locally | Norfolk | NORFOLK | Hampton Roads | Hampton Roads:Norfolk | Local Assistance Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Derrick Williams | Derrick.Williams@vdot.virginia.gov | (757) 956-3097 | Robert Brown | robert.brown@norfolk.gov | (757) 664-7305 | 0 |  | 0 | FY2027 | 1000000 | 1000000 | NO DATES SET YET | G | Agreement with Locality milestone is 1213 days ahead of the expected completion date | G | Project is on budget | 2024-02-12 |  | 2024-06-18 |  | G | 2024-06-19 |  | 2024-07-10 |  | G | 2025-01-22 |  | 2025-05-14 |  | G | [25 empty] | 2026-05-11 |  | 2026-10-07 |  | G | [5 empty] | 2026-12-09 |  | 2027-01-07 |  | G | 2027-03-31 |  | 2027-03-31 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.13856
961 | 117184 | #SGR21LP 131-City of Chesapeake 1522 Mount Pleasant Rd | 0165 | Urban | Resurfacing | Locally | Chesapeake | NORFOLK | Hampton Roads | Hampton Roads:Chesapeake | Infrastructure Investment/Asset Management Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Johndel A Alcaide | John.Alcaide@vdot.virginia.gov | (757) 956-3098 | Sam Sawan | ssawan@cityofchesapeake.net | (757) 382-8263 | 0 |  | 0 | FY2022 | 308403 | 308403 | NO DATES SET YET | G | Agreement with Locality milestone is 80 days ahead of the expected completion date | G | Project is on budget | 2021-01-04 |  | 2021-05-12 |  | G | 2021-05-13 |  | 2021-06-03 |  | G | 2021-07-02 |  | 2021-08-04 |  | G | [25 empty] | 2021-07-08 |  | 2021-08-04 |  | G | [5 empty] | 2021-10-01 |  | 2021-10-29 |  | G | 2022-01-26 |  | 2022-01-26 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.081011
962 | 93089 | RTE 684 - BRIDGE-ONLY REPLACEMENT (FED ID 13863) | 0684 | Secondary | Bridge Replacement w/o Added Capacity | VDOT | Powhatan County | CHESTERFIELD | Richmond | NonMPO:NonMPO | Infrastructure Investment Division | Thomas Kendrick | Thomas.Kendrick@vdot.virginia.gov | (804) 609-5281 | Jeremy B Cobb | Jeremy.Cobb@vdot.virginia.gov | (804) 586-2255 |  |  |  | 0 |  | 0 | FY2021 | 3564973 | 3564973 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 28 days early | G | Project is on budget | [5 empty] | 2014-03-17 | 2013-07-12 | 2015-12-05 | 2013-07-12 | G | 2016-03-29 | 2016-03-28 | 2018-01-08 | 2018-01-05 | G | [5 empty] | 2018-04-23 | 2018-04-23 | 2018-04-23 | 2018-04-23 | G | 2018-12-19 | 2018-12-11 | 2019-01-09 | 2018-12-21 | G | 2019-08-30 | 2019-01-17 | 2020-03-11 | 2019-05-22 | G | 2019-01-29 | 2019-01-29 | 2019-07-31 | 2019-01-29 | G | 2019-05-07 | 2019-04-17 | 2019-11-27 | 2019-11-05 | G | [5 empty] | 2020-05-12 | 2020-04-07 | 2020-05-12 | 2020-04-07 | G | 2020-07-21 | 2020-06-25 | 2020-07-23 | 2020-06-25 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.12007
963 | 102763 | Meadow Creek Road (Rt. 658) realignment. FY13 RS | 0658 | Secondary | Reconstruction w/o Added Capacity | Locally | Montgomery County | CHRISTIANSBURG | Salem | New River Valley:Montgomery County | Local Assistance Division | Anthony W Ford | Anthony.Ford@VDOT.Virginia.gov | (540) 378-5040 | Adam J Czesnowski | Adam.Czesnowski@vdot.virginia.gov | (540) 541-1216 | F. Craig Meadows | meadowsfc@montgomerycountyva.gov | (540) 382-6954 | 0 |  | 0 | FY2019 | 1285000 | 1346846 | CONSTRUCTION STARTED | G | Start Delivery milestone finished on-time | Y | Project estimate is less than $5M and is up to 20% over budget | [5 empty] | 2012-10-01 | 2015-08-12 | 2014-02-28 | 2015-08-12 | R | 2012-10-31 | 2016-01-25 | 2013-02-28 | 2016-12-07 | R | [10 empty] | 2018-08-30 | 2018-07-27 | 2018-10-01 | 2018-07-27 | G | [20 empty] | 2018-12-03 | 2018-12-14 | 2018-12-03 | 2018-12-14 | R | 2018-12-04 | 2019-01-04 | 2019-06-03 | 2019-06-03 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.18177
964 | 104661 | RTE 1 - ADD TRAFFIC SIGNAL AND TURN LANES | 0001 | Primary | Safety | VDOT | Chesterfield County | CHESTERFIELD | Richmond | Tri-Cities:Chesterfield County | Infrastructure Investment Division | Xuesong Zhang | Jason.Zhang@vdot.virginia.gov | (804) 609-5248 | Jeremy B Cobb | Jeremy.Cobb@vdot.virginia.gov | (804) 586-2255 |  |  |  | 0 |  | 0 | FY2019 | 7627163 | 8011243 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 34 days early | Y | Project estimate is between $5M and $10M and is up to $1M over budget | [5 empty] | 2013-10-08 | 2013-07-12 | 2013-10-08 | 2013-10-01 | G | 2013-10-01 | 2014-09-09 | 2016-09-30 | 2016-09-30 | G | [5 empty] | 2016-10-31 | 2016-10-31 | 2017-04-05 | 2017-04-05 | G | 2017-03-31 | 2017-03-31 | 2017-04-06 | 2017-04-06 | G | 2018-02-23 | 2018-02-23 | 2019-02-26 | 2019-04-09 | R | 2017-04-24 | 2017-04-24 | 2018-02-22 | 2018-02-22 | G | 2018-03-05 | 2018-03-05 | 2018-03-15 | 2018-03-05 | G | [5 empty] | 2018-10-25 | 2018-11-06 | 2019-01-08 | 2018-11-06 | G | 2019-02-05 | 2019-01-23 | 2019-02-26 | 2019-01-23 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.1308
965 | 106145 | Chesapeake Bike Trail |  | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Chesapeake | NORFOLK | Hampton Roads | Hampton Roads:Chesapeake | Local Assistance Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Johndel A Alcaide | John.Alcaide@vdot.virginia.gov | (757) 956-3098 | Scott Frechem, PE | sfrechem@cityofchesapeake.net | (757) 382-6319 | 0 |  | 0 | FY2019 | 722600 | 709825 | AWARDED | R | Start Delivery milestone finished 649 days late | G | Project is on budget | [5 empty] | 2014-10-01 | 2015-04-15 | 2014-10-01 | 2015-04-23 | R | 2014-10-31 | 2015-04-24 | 2015-02-28 | 2017-06-05 | R | [10 empty] | 2017-08-28 | 2017-08-28 | 2017-08-28 | 2017-08-28 | G | [20 empty] | 2018-10-01 | 2018-10-01 | 2018-10-01 | 2019-09-27 | R | 2019-03-04 | 2021-01-20 | 2019-04-12 | 2021-01-20 | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.38311
966 | 107656 | Appalachian Trail Connector |  | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Warren County | EDINBURG | Staunton | NonMPO:NonMPO | Local Assistance Division | Kimberly Cameron | Kim.Cameron@vdot.virginia.gov | (540) 332-7886 | Kimberly Cameron | Kim.Cameron@vdot.virginia.gov | (540) 332-7886 | Warren County |  |  | 0 |  | 0 | FY2021 | 465368 | 465368 | ACTIVITY DATES SET | R | Solicit Bids milestone is 108 days past the expected completion date | G | Project is on budget | 2015-12-01 | 2015-12-01 | 2016-03-01 | 2016-03-01 | G | 2016-01-21 | 2016-01-21 | 2016-01-21 | 2016-01-21 | G | 2018-06-28 | 2018-06-28 | 2018-11-20 | 2018-11-19 | G | [10 empty] | 2020-05-13 | 2020-05-13 | 2020-05-27 | 2020-05-27 | G | [20 empty] | 2020-06-30 |  | 2020-11-05 |  | R | 2020-11-06 |  | 2021-05-04 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.42796
967 | 108914 | #HB2.FY17 Route 221 Congestion and Safety Improvements | 0221 | Primary | Safety | VDOT | Bedford County | BEDFORD | Salem | Lynchburg:Bedford County | Infrastructure Investment Division | Alex H Price | Alex.Price@VDOT.Virginia.gov | (540) 378-5053 | Christopher L Harrah | Chris.Harrah@VDOT.Virginia.gov | (540) 387-5395 | Philipp Gabathuler | pgabathuler@region2000.org | (434) 845-3491 | 1 | 2017 | 0 | FY2022 | 8137995 | 8137995 | ACTIVITY DATES SET | G | Complete Purchasing Right-of-Way milestone finished 105 days early | G | Project is on budget | [5 empty] | 2018-07-03 | 2017-07-20 | 2018-07-17 | 2017-09-08 | G | 2018-07-18 | 2017-09-11 | 2019-08-26 | 2017-12-08 | G | [5 empty] | 2018-12-06 | 2018-02-06 | 2019-01-11 | 2018-03-28 | G | 2020-06-25 | 2019-04-29 | 2020-07-09 | 2019-05-21 | G | 2020-12-07 | 2020-10-08 | 2021-08-10 |  | G | 2020-07-27 | 2019-07-19 | 2021-02-26 | 2020-11-13 | G | [10 empty] | 2021-09-14 |  | 2021-09-14 |  | G | 2021-10-28 |  | 2022-03-14 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 1 | 0.2229
968 | 109295 | 29TH STREET BIKE-WALK BOULEVARD |  | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Richmond | ASHLAND | Richmond | Richmond:Richmond | Local Assistance Division | Brian J Lokker | Brian.Lokker@VDOT.Virginia.gov | (804) 524-6010 | Brian J Lokker | Brian.Lokker@VDOT.Virginia.gov | (804) 524-6010 | Jian Xu | jian.xu@richmondgov.com | (804) 646-5402 | 0 |  | 0 | FY2020 | 650000 | 782427 | CONSTRUCTION STARTED | G | Start Delivery milestone finished on-time | Y | Project estimate is less than $5M and is up to 20% over budget | 2017-07-07 | 2017-07-07 | 2017-09-05 | 2017-09-05 | G | 2017-09-06 | 2017-09-06 | 2017-09-19 | 2017-09-19 | G | 2017-12-12 | 2017-12-12 | 2018-07-12 | 2018-01-16 | G | [35 empty] | 2019-03-18 | 2019-04-12 | 2019-04-26 | 2019-06-19 | R | 2019-04-29 | 2019-06-19 | 2019-10-16 | 2019-10-16 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.35382
969 | 109512 | I-77 Wythe Co. Median Barrier | 0077 | Interstate | Safety | VDOT | Wythe County | WYTHEVILLE | Bristol | NonMPO:NonMPO | Infrastructure Investment Division | Jeffrey Buchanan | Jeff.Buchanan@vdot.virginia.gov | (276) 415-3440 | Chase R Buchanan | Chase.Buchanan@VDOT.Virginia.gov | (276) 696-3251 |  |  |  | 0 |  | 0 | FY2019 | 925000 | 1158138 | WAITING FINANCIAL CLOSURE | R | Start Delivery milestone finished 23 days late | R | Project estimate is less than $5M and is 20% or more over budget | [5 empty] | 2016-08-16 | 2016-08-16 | 2016-08-29 | 2017-07-05 | R | 2016-08-30 | 2017-07-06 | 2017-04-26 | 2017-07-06 | R | [5 empty] | 2018-04-13 | 2018-04-13 | 2018-04-13 | 2018-04-13 | G | [5 empty] | 2018-02-23 | 2018-02-23 | 2018-02-23 | 2018-02-23 | G | [5 empty] | 2018-04-19 | 2018-04-17 | 2018-07-20 | 2018-04-17 | G | [5 empty] | 2018-11-13 | 2018-12-18 | 2018-11-13 | 2018-12-18 | R | 2019-01-08 | 2019-02-22 | 2019-01-30 | 2019-02-22 | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.078334
970 | 117148 | #SGR21LP 109-City of Emporia 275 Main St N | 0301 | Urban | Resurfacing | Locally | Emporia | FRANKLIN | Hampton Roads | Hampton Roads:Emporia | Infrastructure Investment/Asset Management Division | Susan Wilson | Susan.Wilson@vdot.virginia.gov | (757) 956-3099 | Marci Thompson | Marci.Thompson@vdot.virginia.gov | (757) 956-3093 | Alton Mason | alton.mason@ci.emporia.va.us | (434) 634-4500 | 0 |  | 1 | FY2024 | 348089 | 348089 | NO DATES SET YET | R | Agreement with Locality milestone is 39 days past the expected completion date | G | Project is on budget | 2020-09-01 |  | 2021-01-13 |  | R | 2021-01-14 |  | 2021-02-05 |  | R | 2021-08-12 |  | 2021-12-08 |  | G | [25 empty] | 2022-12-05 |  | 2023-05-05 |  | G | [5 empty] | 2023-07-05 |  | 2023-08-01 |  | G | 2023-10-20 |  | 2023-10-20 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.10048
971 | 117808 | CFX - 121/460 Poplar Creek Phase B - PE/RW | 0460 | Primary | New Construction Roadway | VDOT | Buchanan County | LEBANON | Bristol | NonMPO:NonMPO | Infrastructure Investment Division | Marty R Halloway | Marty.Halloway@VDOT.Virginia.gov | (276) 696-3367 | Laura B Hale | Laura.Hale@vdot.virginia.gov | (276) 698-0085 |  |  |  | 0 |  | 0 | FY2022 | 488 | 488 | NO DATES SET YET | R | Start Development milestone is 243 days past the expected completion date | G | Project is on budget | [5 empty] | 2020-06-03 | 2020-06-03 | 2020-06-23 |  | R | 2020-06-08 | 2020-06-08 | 2020-11-30 |  | R | [5 empty] | 2021-10-12 |  | 2021-11-15 |  | G | 2021-07-21 |  | 2021-08-10 |  | G | [20 empty] | 2021-08-11 |  | 2021-08-11 |  | G | 2021-11-16 |  | 2021-12-15 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | DESIGN BUILD/PPTA | 0 | 0 | 0.073023
972 | 102555 | S WASHINGTON ST AND MAPLE AVENUE IMPROVEMENTS | 0029 | Urban | Traffic Management/Engineering | Locally | Falls Church | FAIRFAX | Northern Virginia | Northern Virginia:Falls Church | Infrastructure Investment Division | Terry Yates | Terry.Yates@vdot.virginia.gov | (703) 259-2118 | Christer P Carshult | Christer.Carshult@vdot.virginia.gov | (703) 259-1765 | James Mak | jmak@fallschurchva.gov |  | 0 |  | 0 | FY2020 | 1433000 | 1468182 | ACTIVITY DATES SET | R | Solicit Bids milestone is 403 days past the expected completion date | Y | Project estimate is less than $5M and is up to 20% over budget | 2012-01-22 | 2012-01-22 | 2012-01-22 | 2012-01-22 | G | 2012-05-15 | 2012-02-23 | 2013-05-15 | 2012-02-23 | G | 2013-07-15 | 2013-07-12 | 2013-07-15 | 2013-07-12 | G | [10 empty] | 2018-12-03 | 2018-12-03 | 2019-01-15 | 2019-05-31 | R | [20 empty] | 2019-10-15 |  | 2020-01-15 |  | R | 2020-03-16 |  | 2020-06-15 |  | R | Design plans are being revised | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.42322
973 | 103560 | BICYCLE PARKING AT TRANSIT | 0236 | Urban | Facilities for Pedestrians and Bicycles | Locally | Alexandria | FAIRFAX | Northern Virginia | Northern Virginia:Alexandria | Infrastructure Investment Division | Andrew G Beacher | Andrew.Beacher@vdot.virginia.gov | (703) 259-2239 | Marlene Pinedo Fortich | Sofia.Pinedo@vdot.virginia.gov | (703) 259-1724 | Christine E. Mayeur | christine.mayeur@alexandriava.gov | (703) 746-4190 | 0 |  | 0 | FY2022 | 505000 | 505000 | ACTIVITY DATES SET | G | Determine Requirements milestone finished 280 days early | G | Project is on budget | 2016-04-18 | 2016-04-18 | 2016-04-18 | 2016-04-18 | G | 2016-05-11 | 2016-05-11 | 2016-05-11 | 2016-05-11 | G | 2017-11-08 | 2017-11-08 | 2019-04-30 | 2018-07-24 | G | [35 empty] | 2021-08-02 |  | 2021-12-30 |  | G | 2022-01-03 |  | 2022-06-30 |  | G | Final design is still underway | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.2156
974 | 105584 | ROUTE 7/GEORGE WASHINGTON BLVD OVERPASS | 0007 | Primary | Bridge, New Construction | VDOT | Loudoun County | LEESBURG | Northern Virginia | Northern Virginia:Loudoun County | Infrastructure Investment Division | Kimberly Mccool | Kimberly.McCool@vdot.virginia.gov | (703) 259-3220 | Christopher Barksdale | Chris.Barksdale@vdot.virginia.gov | (703) 259-2768 | Joe Kroboth, Loudoun County Dept. of Transportation & Capital Infrastructure | joe.kroboth@loudoun.gov | (703) 771-5107 | 0 |  | 0 | FY2021 | 28000000 | 33249055 | ACTIVITY DATES SET | R | Relocate Utilities milestone is 367 days past the expected completion date | R | Project estimate is greater than $10M and is over budget by (a) 10% or more or (b) $5M or more | [5 empty] | 2014-11-15 | 2014-12-10 | 2014-11-15 | 2014-12-10 | R | 2014-12-15 | 2015-03-11 | 2016-01-15 | 2016-02-08 | R | [5 empty] | 2016-12-15 | 2016-12-15 | 2017-08-11 | 2017-08-11 | G | 2018-05-25 | 2018-05-25 | 2018-08-17 | 2018-07-26 | G | 2019-05-20 | 2019-03-20 | 2020-02-20 |  | R | 2018-08-20 | 2018-08-21 | 2019-05-17 | 2019-03-20 | G | 2018-12-18 | 2016-08-01 | 2019-12-05 | 2020-01-08 | R | [5 empty] | 2020-04-10 |  | 2020-05-12 |  | R | 2020-08-24 |  | 2020-08-24 |  | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.19079
975 | 107287 | #SGR19LB??- Bridge Replacement - Paradise Creek Bridge | 0239 | Urban | Bridge Replacement w/o Added Capacity | Locally | Portsmouth | NORFOLK | Hampton Roads | Hampton Roads:Portsmouth | Local Assistance Division | Susan Wilson | Susan.Wilson@vdot.virginia.gov | (757) 956-3099 | Marci Thompson | Marci.Thompson@vdot.virginia.gov | (757) 956-3093 | James Wright | wrightj@portsmouthva.gov | (757) 393-8592 | 0 |  | 0 | FY2026 | 10367928 | 10367928 | ACTIVITY DATES SET | R | Determine Requirements milestone finished 1121 days late | G | Project is on budget | 2015-10-01 | 2016-01-26 | 2015-12-30 | 2016-01-26 | R | 2015-12-31 | 2016-01-27 | 2016-01-14 | 2016-01-27 | R | 2016-01-19 | 2017-01-28 | 2016-09-08 | 2019-10-04 | R | 2021-04-05 |  | 2021-05-14 |  | G | [5 empty] | 2023-11-16 |  | 2023-12-01 |  | G | [20 empty] | 2025-02-06 |  | 2025-05-30 |  | G | 2025-08-19 |  | 2026-02-13 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.12023
976 | 108700 | Reconstruction - Stewart Street | 9999 | Secondary | Reconstruction w/o Added Capacity | Locally | Hopewell | PETERSBURG | Richmond | Tri-Cities:Hopewell | Local Assistance Division | James Shepherd | James.Shepherd@vdot.virginia.gov | (804) 609-5305 | Brian J Lokker | Brian.Lokker@VDOT.Virginia.gov | (804) 524-6010 | Austin Anderson | aanderson@hopewellva.gov | (804) 541-2379 | 0 |  | 0 | FY2019 | 330000 | 330000 | CONSTRUCTION STARTED | G | Start Delivery milestone finished on-time | G | Project is on budget | 2017-07-12 | 2016-07-12 | 2017-10-04 | 2016-09-13 | G | 2017-10-05 | 2017-08-08 | 2017-10-10 | 2017-08-10 | G | 2017-10-11 | 2017-08-11 | 2018-04-20 | 2018-03-09 | G | [35 empty] | 2018-04-18 | 2018-06-05 | 2018-06-29 | 2018-06-29 | G | 2018-07-02 | 2018-06-29 | 2018-08-20 | 2018-08-20 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.10509
977 | 109055 | West Great Neck Sidewalk |  | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Virginia Beach | NORFOLK | Hampton Roads | Hampton Roads:Virginia Beach | Local Assistance Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Marci Thompson | Marci.Thompson@vdot.virginia.gov | (757) 956-3093 | Katie Shannon | kshannon@vbgov.com | (757) 385-1514 | 0 |  | 0 | FY2020 | 924000 | 768178 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 28 days early | G | Project is on budget | 2016-10-03 | 2016-10-03 | 2017-04-17 | 2017-04-17 | G | 2017-01-03 | 2017-01-03 | 2017-04-26 | 2017-04-26 | G | 2017-04-27 | 2017-04-27 | 2018-07-31 | 2018-07-18 | G | [10 empty] | 2019-01-07 | 2018-12-19 | 2019-01-07 | 2018-12-19 | G | [5 empty] | 2019-01-09 | 2018-12-19 | 2019-07-31 | 2018-12-19 | G | [10 empty] | 2019-08-16 | 2019-08-06 | 2019-09-27 | 2019-11-08 | R | 2019-09-30 | 2020-02-05 | 2020-03-26 | 2020-02-27 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.27631
978 | 109305 | #HB2.FY17 W BROADWAY ST - UPGRADE SIGNAL & PED IMPROVEMENTS | 0000 | Urban | Safety | Locally | Hopewell | PETERSBURG | Richmond | Tri-Cities:Hopewell | Infrastructure Investment Division | Brian J Lokker | Brian.Lokker@VDOT.Virginia.gov | (804) 524-6010 | Brian J Lokker | Brian.Lokker@VDOT.Virginia.gov | (804) 524-6010 | Austin Anderson | aanderson@hopewellva.gov | (804) 541-2379 | 1 | 2017 | 0 | FY2019 | 500000 | 559963 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished on-time | Y | Project estimate is less than $5M and is up to 20% over budget | 2016-10-03 | 2016-10-03 | 2016-12-30 | 2017-01-04 | R | 2017-01-03 | 2017-01-04 | 2017-01-05 | 2017-01-04 | G | 2017-01-06 | 2017-01-25 | 2017-07-13 | 2017-06-28 | G | [5 empty] | 2017-09-05 | 2017-09-05 | 2017-09-18 | 2017-09-15 | G | [25 empty] | 2018-05-24 | 2018-05-15 | 2018-06-21 | 2018-06-21 | G | 2018-06-22 | 2018-06-22 | 2018-08-02 | 2018-08-02 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.081698
979 | 109551 | #HB2.FY17 EMMET STREET CORRIDOR STREETSCAPE & INTERSECTIONS | 0000 | Urban | Reconstruction w/o Added Capacity | Locally | Charlottesville | CHARLOTTESVILLE | Culpeper | Charlottesville:Charlottesville | Infrastructure Investment Division | Ken Connors |  |  | Michael D Barnes | MichaelD.Barnes@vdot.virginia.gov | (434) 422-9861 | Jeanette Janiczek | poncy@charlottesville.org | (434) 970-3720 | 1 | 2017 | 0 | FY2022 | 12114721 | 12098063 | ACTIVITY DATES SET | R | Start Purchasing Right-of-Way milestone is 247 days past the expected completion date | Y | Estimate not current | 2016-09-28 | 2016-09-28 | 2017-02-24 | 2016-09-28 | G | 2017-02-27 | 2017-02-01 | 2017-03-01 | 2017-02-15 | G | 2017-03-02 | 2017-02-16 | 2018-03-02 | 2019-04-29 | R | [10 empty] | 2020-06-01 |  | 2020-06-19 |  | R | [5 empty] | 2020-06-23 |  | 2021-06-30 |  | G | [10 empty] | 2021-09-07 |  | 2021-11-22 |  | G | 2021-11-23 |  | 2022-02-08 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.17415
980 | 109603 | OPITZ BOULEVARD SIDEWALK | 2000 | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Prince William County | MANASSAS | Northern Virginia | Northern Virginia:Prince William County | Local Assistance Division | Bud Siegel |  |  | Veljibhai M Desai | Veljibhai.Desai@vdot.virginia.gov | (703) 259-2927 | Gladis E. Arboleta | GArboleda@pwcgov.org | (703) 792-5276 | 0 |  | 0 | FY2019 | 1254120 | 1288564 | CONSTRUCTION COMPLETED | R | Start Delivery milestone finished 248 days late | Y | Project estimate is less than $5M and is up to 20% over budget | 2016-10-03 | 2016-10-03 | 2016-12-30 | 2017-01-12 | R | 2017-01-03 | 2017-01-13 | 2017-01-05 | 2017-02-17 | R | 2017-01-06 | 2017-02-20 | 2017-07-13 | 2017-07-13 | G | [10 empty] | 2018-05-09 | 2018-05-09 | 2018-05-30 | 2018-12-26 | R | [5 empty] | 2018-06-01 | 2018-12-27 | 2019-03-15 | 2019-10-28 | R | [10 empty] | 2019-04-02 | 2019-12-13 | 2019-04-29 | 2019-12-13 | R | 2019-04-30 | 2019-12-16 | 2019-06-10 | 2020-02-13 | R | Delay due to unforeseen issues with utilities, railroad coordination, or right-of-way acquisition | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.41366
981 | 109791 | #HB2.FY17 RTE 360 - INTERSECTION IMPROVEMENTS AT RTE 47 | 0360 | Primary | Safety | VDOT | Charlotte County | DILLWYN | Lynchburg | NonMPO:NonMPO | Infrastructure Investment Division | Anthony D Rago | anthony.rago@vdot.virginia.gov | (434) 856-8308 | Anthony D Rago | anthony.rago@vdot.virginia.gov | (434) 856-8308 |  |  |  | 1 | 2017 | 0 | FY2017 | 255691 | 255691 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished on-time | G | Project is on budget | [5 empty] | 2016-08-31 | 2016-08-31 | 2016-09-02 | 2016-09-02 | G | 2016-09-05 | 2016-09-05 | 2016-10-10 | 2016-10-10 | G | [5 empty] | 2016-11-04 | 2016-11-04 | 2016-11-04 | 2016-11-04 | G | [25 empty] | 2016-12-15 | 2016-12-15 | 2016-12-15 | 2016-12-15 | G | 2016-12-22 | 2016-12-22 | 2016-12-22 | 2016-12-22 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | WORK/TASK ORDER | 1 | 0 | 0.09327
983 | 111403 | PARK STREET SIDEWALK |  | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Vienna | FAIRFAX | Northern Virginia | Northern Virginia:Vienna | Local Assistance Division | Bud Siegel |  |  | Saif-Ur Qargha | Saif.Qargha@vdot.virginia.gov | (703) 259-3223 | Town of Vienna |  |  | 0 |  | 0 | FY2023 | 351257 | 418600 | ACTIVITY DATES SET | R | Start Purchasing Right-of-Way milestone is 83 days past the expected completion date | Y | Project estimate is less than $5M and is up to 20% over budget | 2017-10-02 | 2017-10-02 | 2017-12-18 | 2017-12-18 | G | 2017-12-19 | 2017-12-19 | 2018-01-25 | 2018-01-25 | G | 2018-09-27 | 2018-09-13 | 2019-09-27 | 2019-08-01 | G | [10 empty] | 2020-08-04 | 2020-02-01 | 2020-11-30 |  | R | [5 empty] | 2020-12-02 |  | 2021-12-28 |  | G | [10 empty] | 2022-01-18 |  | 2022-08-04 |  | G | 2022-08-05 |  | 2023-02-01 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.31922
984 | 111814 | #SMART18 - EXIT 124 (INTERSTATE 64) | 0250 | Primary | Safety | VDOT | Albemarle County | CHARLOTTESVILLE | Culpeper | Charlottesville:Albemarle County | Infrastructure Investment Division | Gregory J Cooley | Gregory.Cooley@vdot.virginia.gov | (434) 906-7979 | William E Stowe | William.Stowe@vdot.virginia.gov | (540) 827-7287 |  |  |  | 1 | 2018 | 0 | FY2019 | 18400000 | 18102653 | CONSTRUCTION STARTED | R | Start Delivery milestone finished 34 days late | G | Project is on budget | [5 empty] | 2018-07-16 | 2017-10-12 | 2018-07-27 | 2017-10-26 | G | 2018-07-30 | 2017-10-27 | 2019-09-06 | 2017-10-27 | G | [10 empty] | 2018-11-01 | 2018-11-01 | 2018-11-14 | 2018-11-14 | G | [20 empty] | 2018-10-30 | 2018-10-30 | 2018-11-27 | 2018-11-27 | G | 2019-05-28 | 2019-06-26 | 2019-06-19 | 2019-07-23 | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | DESIGN BUILD/PPTA | 1 | 1 | 0.38673
985 | 112878 | #SGR19VB - RT 58 OVER DAN RIVER (STR 13221) - BRIDGE REPLACE | 0058 | Primary | Bridge Replacement w/o Added Capacity | VDOT | Patrick County | MARTINSVILLE | Salem | NonMPO:NonMPO | Infrastructure Investment/Asset Management Division | Anthony T Marshall | Todd.Marshall@VDOT.Virginia.gov | (540) 387-5460 | Brian Sarver | Brian.Sarver@vdot.virginia.gov | (540) 375-4797 |  |  |  | 0 |  | 1 | FY2024 | 6550000 | 6550000 | ACTIVITY DATES SET | R | Determine Requirements milestone finished 266 days late | G | Project is on budget | [5 empty] | 2018-09-04 | 2019-07-03 | 2018-09-17 | 2019-07-18 | R | 2018-09-18 | 2019-07-19 | 2019-08-15 | 2020-05-07 | R | [5 empty] | 2021-09-14 |  | 2021-09-27 |  | G | 2022-12-01 |  | 2022-12-14 |  | G | 2023-05-11 |  | 2023-11-15 |  | G | 2022-12-30 |  | 2023-07-07 |  | G | 2022-11-22 |  | 2023-07-28 |  | G | [5 empty] | 2023-12-12 |  | 2023-12-12 |  | G | 2024-03-07 |  | 2024-03-07 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.062953
986 | 112939 | TAYLOR STREET RECONSTRUCTION |  | Secondary | Reconstruction w/o Added Capacity | Locally | Lexington | LEXINGTON | Staunton | NonMPO:NonMPO | Local Assistance Division | Susan E Hammond | Susan.Hammond@VDOT.Virginia.gov | (540) 462-6990 | Michael L Branscome | Michael.Branscome@VDOT.Virginia.gov | (540) 332-2377 | Jeff Martone | jmartone@lexingtonva.gov | (540) 463-3154 | 0 |  | 0 | FY2019 | 780000 | 780000 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 35 days early | G | Project is on budget | 2018-12-10 | 2018-07-13 | 2019-03-08 | 2018-09-21 | G | [5 empty] | 2018-12-10 | 2018-07-13 | 2018-12-21 | 2018-11-20 | G | [35 empty] | 2018-11-21 | 2018-11-21 | 2019-01-23 | 2019-01-23 | G | 2019-04-12 | 2019-04-12 | 2019-05-23 | 2019-04-18 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.16114
987 | 113448 | Bicycle lane Connections in Hopewell - TAP |  | Urban | Facilities for Pedestrians and Bicycles | Locally | Hopewell | PETERSBURG | Richmond | Tri-Cities:Hopewell | Local Assistance Division | James Shepherd | James.Shepherd@vdot.virginia.gov | (804) 609-5305 | James Shepherd | James.Shepherd@vdot.virginia.gov | (804) 609-5305 | Johnnie Butler | jbutler@hopewellVA.gov | (804) 541-2319 | 0 |  | 0 | FY2021 | 933358 | 949579 | ACTIVITY DATES SET | R | Obtained Permits milestone is 306 days past the expected completion date | Y | Project estimate is less than $5M and is up to 20% over budget | 2018-07-05 | 2018-08-06 | 2018-09-27 | 2018-10-23 | R | 2018-09-28 | 2018-11-16 | 2018-10-02 | 2018-11-29 | R | 2018-10-03 | 2018-12-17 | 2019-04-15 | 2019-04-09 | G | [25 empty] | 2019-08-14 |  | 2020-04-21 |  | R | [5 empty] | 2020-05-06 |  | 2020-06-02 |  | R | 2020-08-20 |  | 2020-12-31 |  | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.08377
988 | 113686 | FEDERAL STREET SHARED USE PATH |  | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Harrisonburg | HARRISONBURG | Staunton | Harrisonburg:Harrisonburg | Local Assistance Division | Donald F Komara | Donald.Komara@VDOT.Virginia.gov | (540) 434-2587 | Jamison Brown | Jamison.Brown@vdot.virginia.gov | (540) 332-7389 | Aaron Rhoney | Aaron.Rhoney@harrisonburgva.gov | (540) 434-5928 | 0 |  | 0 | FY2021 | 419644 | 419644 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 398 days early | G | Project is on budget | 2018-11-01 | 2018-11-01 | 2019-02-01 | 2018-12-04 | G | 2019-02-04 | 2018-12-17 | 2019-02-06 | 2018-12-17 | G | 2019-02-07 | 2018-12-18 | 2019-08-12 | 2019-08-12 | G | [35 empty] | 2020-08-26 | 2019-09-27 | 2020-09-23 | 2019-10-21 | G | 2020-12-16 | 2019-11-14 | 2020-12-16 | 2019-11-14 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.21235
989 | 113797 | RTE 621- RURAL RUSTIC RD (SURFACE TREAT NON-HARDSURFACE RD) | 0621 | Secondary | Reconstruction w/o Added Capacity | VDOT | Greene County | CHARLOTTESVILLE | Culpeper | NonMPO:NonMPO | Infrastructure Investment Division | Ken Connors |  |  | Harold L Jones | Harold.Jones@VDOT.virginia.gov | (434) 422-9378 |  |  |  | 0 |  | 0 | FY2025 | 158000 | 158000 | NO DATES SET YET | G | Start Development milestone is 600 days ahead of the expected completion date | G | Project is on budget | [5 empty] | 2022-10-03 |  | 2022-10-14 |  | G | 2022-10-18 |  | 2023-06-13 |  | G | [5 empty] | 2024-02-22 |  | 2024-04-03 |  | G | [5 empty] | 2024-07-18 |  | 2024-11-08 |  | G | [5 empty] | 2024-07-02 |  | 2024-10-02 |  | G | [5 empty] | 2024-11-12 |  | 2024-11-12 |  | G | 2025-02-07 |  | 2025-02-07 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | SAAP CONTRACT | 0 | 0 | 0.15595
990 | 109628 | SYSTEMIC ROADWAY DEPARTURE TREATMENTS - RTE 460 CORRIDOR | 9999 | Miscellaneous | Safety | VDOT | Richmond District-wide |  | Richmond | Richmond:Richmond District-wide | Infrastructure Investment/Asset Management Division | Adam S Brooks | Adam.Brooks@VDOT.Virginia.gov | (804) 609-5274 | Adam S Brooks | Adam.Brooks@VDOT.Virginia.gov | (804) 609-5274 |  |  |  | 0 |  | 0 | FY2023 | 1207640 | 1207640 | ACTIVITY DATES SET | G | Determine Requirements milestone finished on-time | G | Project is on budget | [5 empty] | 2020-02-28 | 2019-12-09 | 2020-03-12 | 2019-12-26 | G | 2020-03-13 | 2019-12-27 | 2020-10-30 | 2020-10-30 | G | [5 empty] | 2021-05-26 |  | 2021-07-08 |  | G | [5 empty] | 2021-10-22 |  | 2022-04-05 |  | G | [5 empty] | 2021-10-06 |  | 2022-01-12 |  | G | [5 empty] | 2022-04-12 |  | 2022-04-12 |  | G | 2022-07-01 |  | 2022-07-01 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.060808
992 | 111088 | City of Suffolk Dowtown Signal System Upgrade | 0000 | Urban | Safety | Locally | Suffolk | NORFOLK | Hampton Roads | Hampton Roads:Suffolk | Infrastructure Investment Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Johndel A Alcaide | John.Alcaide@vdot.virginia.gov | (757) 956-3098 | Robert Lewis | relewis@suffolkva.us | (757) 514-7603 | 0 |  | 0 | FY2026 | 1650000 | 1650000 | NO DATES SET YET | G | Agreement with Locality milestone is 1072 days ahead of the expected completion date | Y | Estimate not current | 2023-10-27 |  | 2024-01-29 |  | G | 2024-01-30 |  | 2024-02-12 |  | G | 2024-02-13 |  | 2025-01-29 |  | G | [35 empty] | 2025-12-08 |  | 2026-01-06 |  | G | 2026-01-07 |  | 2026-06-29 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.16785
993 | 111416 | Maple Avenue Streetscape Extension Phase II |  | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Covington | LEXINGTON | Staunton | NonMPO:NonMPO | Local Assistance Division | Michael S Fulcher | Michael.Fulcher@VDOT.Virginia.gov | (540) 332-2243 | Michael S Fulcher | Michael.Fulcher@VDOT.Virginia.gov | (540) 332-2243 | Allen Dressler | adressler@covington.va.us | (540) 965-6321 | 0 |  | 0 | FY2021 | 590708 | 590708 | AWARDED | G | Start Delivery milestone finished 188 days early | G | Project is on budget | 2018-03-30 | 2018-03-30 | 2018-08-20 | 2019-03-18 | R | 2018-08-21 | 2018-07-01 | 2018-11-15 | 2018-07-25 | G | 2018-11-16 | 2018-07-26 | 2019-05-28 | 2019-08-14 | R | [35 empty] | 2020-02-13 | 2019-11-05 | 2020-05-21 | 2019-12-08 | G | 2020-08-18 | 2020-04-23 | 2020-11-30 | 2020-05-26 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.38985
994 | 111947 | #SGR19LP - Boulevard (RT 1/301) Planning and Overlay | 0001 | Urban | Resurfacing | Locally | Colonial Heights | CHESTERFIELD | Richmond | Tri-Cities:Colonial Heights | Infrastructure Investment Division | Brian J Lokker | Brian.Lokker@VDOT.Virginia.gov | (804) 524-6010 | Brian J Lokker | Brian.Lokker@VDOT.Virginia.gov | (804) 524-6010 | Todd Flippen, PE | flippent@colonialheightsva.gov | (804) 520-9334 | 0 |  | 1 | FY2020 |  |  | CONSTRUCTION COMPLETED | G | Determine Requirements milestone finished 76 days early | R | Critical information missing | 2017-10-30 | 2017-09-01 | 2018-01-30 | 2017-11-16 | G | 2018-01-31 | 2017-12-05 | 2018-02-02 | 2017-12-07 | G | 2018-02-05 | 2018-05-20 | 2018-08-08 | 2018-05-24 | G | [35 empty] | 2019-04-29 | 2018-02-07 | 2019-05-24 | 2018-02-08 | G | 2019-05-28 | 2018-03-18 | 2019-07-08 | 2018-03-19 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.10143
995 | 112880 | #SGR19VB - RT 707 REPLACE BRIDGE STR. 6003 | 0707 | Secondary | Bridge Replacement w/o Added Capacity | VDOT | Madison County | CHARLOTTESVILLE | Culpeper | NonMPO:NonMPO | Infrastructure Investment/Asset Management Division | Braden C Chapman | Braden.Chapman@VDOT.Virginia.gov | (540) 829-7421 | Brian A Arnold | Brian.Arnold@VDOT.Virginia.gov | (540) 829-7557 |  |  |  | 0 |  | 0 | FY2023 | 4700000 | 4700000 | NO DATES SET YET-PE OPEN | R | Determine Requirements milestone is 453 days past the expected completion date | G | Project is on budget | [5 empty] | 2018-12-17 | 2018-09-10 | 2018-12-31 | 2018-09-14 | G | 2019-01-02 | 2020-08-26 | 2019-11-26 |  | R | [5 empty] | 2020-10-29 |  | 2020-11-12 |  | R | 2022-01-20 |  | 2022-02-02 |  | G | 2022-06-27 |  | 2023-01-04 |  | G | 2022-02-17 |  | 2022-08-22 |  | G | 2021-08-06 |  | 2022-08-08 |  | G | [5 empty] | 2023-01-10 |  | 2023-01-10 |  | G | 2023-03-06 |  | 2023-03-24 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.082748
996 | 113274 | Rural Add. - Oakwood Subdivision Streets | 9999 | Secondary | Reconstruction w/o Added Capacity | Locally | York County | WILLIAMSBURG | Hampton Roads | Hampton Roads:York County | Local Assistance Division | Christopher R Carroll | C.Carroll@VDOT.Virginia.gov | (757) 253-5140 | Joshua D Negovan | Joshua.Negovan@vdot.virginia.gov | (757) 956-3347 | Tim Cross | tcross@yorkcounty.gov | (757) 890-3496 | 0 |  | 0 | FY2023 | 544611 | 589219 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 931 days early | Y | Project estimate is less than $5M and is up to 20% over budget | 2018-11-01 | 2018-07-02 | 2019-02-01 | 2018-08-21 | G | 2019-02-04 | 2018-09-13 | 2019-02-06 | 2018-09-14 | G | 2019-02-07 | 2018-09-17 | 2019-08-12 | 2019-09-06 | R | [25 empty] | 2019-07-10 | 2020-01-16 | 2020-03-17 | 2020-01-16 | G | [5 empty] | 2021-09-10 | 2020-01-24 | 2022-07-14 | 2020-02-12 | G | 2022-10-03 | 2020-04-27 | 2022-11-15 | 2020-04-28 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.17508
997 | 113469 | Violet Bank Trail | 0000 | Urban | Facilities for Pedestrians and Bicycles | Locally | Virginia Beach | NORFOLK | Hampton Roads | Hampton Roads:Virginia Beach | Local Assistance Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Marci Thompson | Marci.Thompson@vdot.virginia.gov | (757) 956-3093 | Katie Shannon | kshannon@vbgov.com | (757) 385-1514 | 0 |  | 0 | FY2022 | 462099 | 462099 | NO DATES SET YET-PE OPEN | R | Determine Requirements milestone is 583 days past the expected completion date | G | Project is on budget | 2018-10-09 | 2018-10-09 | 2019-01-08 | 2019-04-04 | R | 2019-01-09 | 2019-04-17 | 2019-01-11 | 2019-05-08 | R | 2019-01-14 |  | 2019-07-19 |  | R | [10 empty] | 2020-05-14 |  | 2020-06-04 |  | R | [5 empty] | 2020-06-08 |  | 2021-03-22 |  | Y | 2019-08-26 | 2020-05-06 | 2020-05-01 |  | R | [5 empty] | 2021-04-07 |  | 2021-05-04 |  | G | 2021-07-23 |  | 2021-07-23 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.094448
998 | 113740 | RTE 1162 - RURAL RUSTIC (SURFACE TREAT NON-HARDSURFACE ROAD) | 1162 | Secondary | Reconstruction w/o Added Capacity | VDOT | Culpeper County | WARRENTON | Culpeper | NonMPO:NonMPO | Infrastructure Investment Division | Ken Connors |  |  | Benjamin Davison | Ben.Davison@vdot.virginia.gov | (540) 347-6446 |  |  |  | 0 |  | 0 | FY2025 | 112500 | 112500 | NO DATES SET YET | G | Start Development milestone is 600 days ahead of the expected completion date | Y | Estimate not current | [5 empty] | 2022-10-03 |  | 2022-10-14 |  | G | 2022-10-18 |  | 2023-06-13 |  | G | [5 empty] | 2024-02-22 |  | 2024-04-03 |  | G | [5 empty] | 2024-07-18 |  | 2024-11-08 |  | G | [5 empty] | 2024-07-02 |  | 2024-10-02 |  | G | [5 empty] | 2024-11-12 |  | 2024-11-12 |  | G | 2025-02-07 |  | 2025-02-07 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 |  | 0 | 0 | 0.10323
999 | 113875 | #SGR19LB??- Fincastle Farm Rd Bluest Rv Taz VA 5001 Fed 2967 | 0000 | Urban | Bridge Replacement w/o Added Capacity | VDOT | Tazewell County | LEBANON | Bristol | NonMPO:NonMPO | Infrastructure Investment/Asset Management Division | Gary Lester |  |  | Daniel B Cannon | Daniel.Cannon@VDOT.Virginia.gov | (276) 696-3376 |  |  |  | 0 |  | 0 | FY2021 | 1183239 | 620000 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 102 days early | G | Project is on budget | [5 empty] | 2019-11-18 | 2018-10-01 | 2019-12-03 | 2018-10-12 | G | 2019-12-04 | 2018-10-16 | 2020-02-03 | 2019-07-08 | G | [35 empty] | 2020-10-13 | 2020-07-07 | 2020-10-13 | 2020-07-07 | G | 2021-01-08 | 2020-09-28 | 2021-01-08 | 2020-09-28 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.05327
1000 | 114093 | RTE 29 - SHOULDER WIDENING AND RUMBLE STRIPS (AMHERST) | 0029 | Primary | Safety | VDOT | Amherst County | APPOMATTOX | Lynchburg | Lynchburg:Amherst County | Infrastructure Investment Division | Lindsey S Hodges | Lindsey.Hodges@vdot.virginia.gov | (434) 856-8143 | Lindsey S Hodges | Lindsey.Hodges@vdot.virginia.gov | (434) 856-8143 |  |  |  | 0 |  | 0 | FY2020 | 2929832 | 2483775 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 7 days early | G | Project is on budget | [10 empty] | 2019-07-15 | 2019-02-04 | 2019-07-19 | 2019-07-10 | G | [35 empty] | 2019-12-10 | 2019-12-10 | 2019-12-10 | 2019-12-10 | G | 2020-03-05 | 2020-02-27 | 2020-03-05 | 2020-02-27 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.17152
1001 | 115492 | #SMART20 RTE 29 - CONSTRUCT RCUT AT INTERSECTION OF RTE 151 | 0029 | Primary | Safety | VDOT | Amherst County | APPOMATTOX | Lynchburg | NonMPO:NonMPO | Infrastructure Investment Division | Robert F Guercia | Robert.Guercia@VDOT.Virginia.gov | (434) 841-6864 | Daniel J Brown | Daniel.Brown@VDOT.Virginia.gov | (434) 856-8265 |  |  |  | 1 | 2020 | 0 | FY2024 | 3300027 | 3300027 | NO DATES SET YET-PE OPEN | R | Determine Requirements milestone is 66 days past the expected completion date | G | Project is on budget | [5 empty] | 2020-04-15 | 2020-03-26 | 2020-04-28 | 2020-03-26 | G | 2020-04-29 | 2020-08-18 | 2020-12-17 |  | R | [5 empty] | 2021-09-15 |  | 2021-09-28 |  | G | 2023-01-05 |  | 2023-01-20 |  | G | 2023-08-10 |  | 2024-02-21 |  | G | 2023-02-07 |  | 2023-08-10 |  | G | 2022-05-11 |  | 2022-11-15 |  | G | [5 empty] | 2024-03-12 |  | 2024-03-12 |  | G | 2024-05-31 |  | 2024-05-31 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.10055
1002 | 115862 | #SGR20LP - RECONSTRUCTION - WILLIAM ST | 0003 | Urban | Reconstruction w/o Added Capacity | Locally | Fredericksburg | FREDERICKSBURG | Fredericksburg | Fredericksburg:Fredericksburg | Infrastructure Investment Division | Richard A Spurlock | Richard.Spurlock@VDOT.Virginia.gov | (540) 899-4302 | Richard A Spurlock | Richard.Spurlock@VDOT.Virginia.gov | (540) 899-4302 | Erik Nelson | enelson@fredericksburgva.gov | (540) 372-1080 | 0 |  | 0 | FY2022 | 350000 | 350000 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 397 days early | G | Project is on budget | 2019-07-15 | 2018-08-15 | 2019-10-07 | 2018-10-23 | G | [5 empty] | 2019-07-15 | 2019-07-15 | 2019-07-26 | 2019-07-26 | G | [25 empty] | 2019-07-29 | 2019-07-29 | 2019-10-22 | 2019-07-29 | G | [5 empty] | 2021-04-08 | 2020-04-08 | 2021-05-05 | 2020-04-08 | G | 2021-07-26 | 2020-06-24 | 2021-07-26 | 2020-06-24 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.12113
1003 | 116157 | #I81CIP NB MM 39.5 ADD TRUCK CLIMBING LANE (ID #4) | 0081 | Interstate | Reconstruction w/ Added Capacity | VDOT | Smyth County | ABINGDON | Bristol | NonMPO:NonMPO | Infrastructure Investment Division | Donald A Necessary | Donald.Necessary@VDOT.Virginia.gov | (276) 696-3285 | James R Jones | jamesr.jones@vdot.virginia.gov | (276) 696-3257 |  |  |  | 0 |  | 0 | FY2024 | 20656625 | 13943193 | ACTIVITY DATES SET | G | Determine Requirements milestone finished 362 days early | G | Project is on budget | [5 empty] | 2020-07-01 | 2020-01-03 | 2020-07-15 | 2020-01-16 | G | 2020-07-16 | 2020-01-21 | 2021-08-24 | 2020-08-27 | G | [5 empty] | 2021-05-11 |  | 2021-05-24 |  | G | 2022-05-11 |  | 2022-05-24 |  | G | 2022-10-19 |  | 2023-04-28 |  | G | 2022-06-10 |  | 2023-02-02 |  | G | 2021-10-29 |  | 2023-04-13 |  | G | [5 empty] | 2023-06-13 |  | 2023-06-13 |  | G | 2023-10-02 |  | 2023-10-02 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.092202
1004 | 117064 | Hill Ave and Hooker St Reconstruction |  | Secondary | Reconstruction w/o Added Capacity | Locally | Hopewell | PETERSBURG | Richmond | Tri-Cities:Hopewell | Local Assistance Division | James Shepherd | James.Shepherd@vdot.virginia.gov | (804) 609-5305 | James Shepherd | James.Shepherd@vdot.virginia.gov | (804) 609-5305 | TBD |  | TBD | 0 |  | 0 | FY2028 | 451220 | 451220 | NO DATES SET YET | G | Agreement with Locality milestone is 1543 days ahead of the expected completion date | G | Project is on budget | 2025-01-06 |  | 2025-05-14 |  | G | 2025-05-15 |  | 2025-06-05 |  | G | 2025-07-07 |  | 2025-10-28 |  | G | [25 empty] | 2026-10-23 |  | 2027-03-30 |  | G | [5 empty] | 2027-05-26 |  | 2027-06-23 |  | G | 2027-09-13 |  | 2027-09-13 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.10539
1005 | 117119 | Parliament Drive Phase I Sidewalk |  | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Virginia Beach | NORFOLK | Hampton Roads | Hampton Roads:Virginia Beach | Local Assistance Division | Susan Wilson | Susan.Wilson@vdot.virginia.gov | (757) 956-3099 | Marci Thompson | Marci.Thompson@vdot.virginia.gov | (757) 956-3093 | Katie Shannon | kshannon@vbgov.com | (757) 385-1514 | 0 |  | 0 | FY2024 | 1083386 | 1083386 | NO DATES SET YET | G | Agreement with Locality milestone is 81 days ahead of the expected completion date | G | Project is on budget | 2021-01-05 |  | 2021-05-13 |  | G | 2021-05-14 |  | 2021-06-04 |  | G | 2021-12-14 |  | 2022-04-11 |  | G | [10 empty] | 2022-06-08 |  | 2022-07-13 |  | G | [5 empty] | 2022-07-14 |  | 2022-12-14 |  | G | 2022-11-08 |  | 2023-04-13 |  | G | [5 empty] | 2023-03-23 |  | 2023-04-19 |  | G | 2023-07-10 |  | 2023-07-10 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.27762
1006 | 117966 | EDGE LINE RUMBLE STRIPS - BRISTOL DISTRICT WIDE | 9999 | Miscellaneous | Safety | VDOT | Bristol District-wide |  | Bristol | NonMPO:NonMPO | Infrastructure Investment Division | Brian Holt | Brian.Holt@vdot.virginia.gov | (276) 696-3414 | Jeremy J Mullins | Jeremy.Mullins@vdot.virginia.gov | (276) 696-3259 |  |  |  | 0 |  | 0 | FY2024 | 1423982 | 1423982 | NO DATES SET YET-PE OPEN | G | Obtained Permits milestone finished 734 days early | G | Project is on budget | [5 empty] | 2020-10-01 | 2020-10-01 | 2020-10-22 | 2020-10-22 | G | 2020-10-23 | 2020-10-23 | 2021-08-26 |  | G | [5 empty] | 2022-04-01 |  | 2022-04-28 |  | G | [5 empty] | 2022-12-21 |  | 2023-04-25 |  | G | [5 empty] | 2022-09-08 | 2021-02-09 | 2023-02-13 | 2021-02-09 | G | [5 empty] | 2023-05-09 |  | 2023-05-09 |  | G | 2023-07-28 |  | 2023-07-28 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.068817
1007 | 118305 | SAGER AVE DRAINAGE AND PED IMPROVEMENTS | 9999 | Urban | Facilities for Pedestrians and Bicycles | Locally | Fairfax | FAIRFAX | Northern Virginia | Northern Virginia:Fairfax | Local Assistance Division | Andrew G Beacher | Andrew.Beacher@vdot.virginia.gov | (703) 259-2239 | Marlene Pinedo Fortich | Sofia.Pinedo@vdot.virginia.gov | (703) 259-1724 | Wendy Sanford | wendy.sanford@fairfaxva.gov | (703) 385-7889 | 0 |  | 0 | FY2028 | 1760000 | 1760000 | NO DATES SET YET | G | Agreement with Locality milestone is 1480 days ahead of the expected completion date | G | Project is on budget | 2024-08-15 |  | 2025-03-12 |  | G | 2025-03-13 |  | 2025-04-02 |  | G | 2025-10-07 |  | 2026-04-03 |  | G | [25 empty] | 2027-04-28 |  | 2027-09-24 |  | G | [5 empty] | 2027-10-26 |  | 2027-12-23 |  | G | 2028-03-17 |  | 2028-05-11 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.18487
1008 | 77296 | RTE 221-BRDG OVR MIRA FORK CREEK (STR. 07486) - BRDG RPLCMNT | 0221 | Primary | Bridge Replacement w/o Added Capacity | VDOT | Floyd County | CHRISTIANSBURG | Salem | NonMPO:NonMPO | Infrastructure Investment Division | Anthony T Marshall | Todd.Marshall@VDOT.Virginia.gov | (540) 387-5460 | Marvin D Mann | M.Mann@VDOT.Virginia.gov | (540) 378-5055 |  |  |  | 0 |  | 0 | FY2019 | 2960000 | 2960000 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 98 days early | G | Project is on budget | [5 empty] | 2008-04-30 | 2008-06-12 | 2008-05-30 | 2008-06-12 | R | 2014-12-01 | 2014-11-28 | 2016-09-13 | 2016-09-13 | G | 2016-10-25 | 2016-10-25 | 2017-02-13 | 2017-02-13 | G | [5 empty] | 2017-06-13 | 2017-06-13 | 2017-07-20 | 2017-07-20 | G | 2018-02-20 | 2018-02-20 | 2018-11-16 | 2018-07-06 | G | 2017-10-04 | 2017-10-04 | 2018-02-21 | 2018-02-21 | G | 2017-09-01 | 2017-09-01 | 2018-07-10 | 2018-06-08 | G | [5 empty] | 2018-06-14 | 2018-07-10 | 2018-07-10 | 2018-07-10 | G | 2018-08-16 | 2018-09-07 | 2018-12-14 | 2018-09-07 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.0598
1009 | 86294 | Route 811, Super Str Replacement, Fed ID 10995, Va str 6507 | 0811 | Secondary | Bridge, New Construction | VDOT | Lee County | WISE | Bristol | NonMPO:NonMPO | Infrastructure Investment Division | Jackie Christian | Jackie.Christian@VDOT.Virginia.gov | (276) 321-6452 | Daniel B Cannon | Daniel.Cannon@VDOT.Virginia.gov | (276) 696-3376 |  |  |  | 0 |  | 0 | FY2019 | 1134920 | 1000000 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished on-time | G | Project is on budget | [5 empty] | 2011-04-01 | 2011-06-15 | 2011-04-01 | 2011-06-15 | R | 2013-05-02 | 2011-09-22 | 2013-09-02 | 2012-01-09 | G | [35 empty] | 2018-11-14 | 2018-12-04 | 2018-12-11 | 2018-12-11 | G | 2019-01-29 | 2019-02-22 | 2019-02-22 | 2019-02-22 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.094471
1010 | 115306 | #SGR20LP - Primary Extension - Galax - E StuaRT Dr | 0058 | Urban | Reconstruction w/o Added Capacity | Locally | Galax | MARTINSVILLE | Salem | NonMPO:NonMPO | Local Assistance Division | Jessie Nester | Jessie.Nester@vdot.virginia.gov | (540) 613-4115 | Jessie Nester | Jessie.Nester@vdot.virginia.gov | (540) 613-4115 | Keith Barker | kbarker@galaxva.com | (276) 236-5773 | 0 |  | 0 | FY2020 | 198338 | 198338 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 202 days early | G | Project is on budget | 2020-01-02 | 2019-07-02 | 2020-03-30 | 2019-08-07 | G | 2020-03-31 | 2019-08-07 | 2020-04-02 | 2019-08-07 | G | 2020-04-03 | 2019-08-13 | 2020-10-06 | 2019-08-14 | G | [35 empty] | 2019-12-11 | 2019-10-22 | 2019-12-31 | 2019-11-15 | G | 2020-03-24 | 2019-12-06 | 2020-06-30 | 2019-12-11 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.08448
1011 | 115716 | #SMART20 ORANDA ROAD PARK AND RIDE EXPANSION | 0629 | Secondary | Reconstruction w/ Added Capacity | VDOT | Shenandoah County | EDINBURG | Staunton | NonMPO:NonMPO | Infrastructure Investment Division | John-Allen L Ennis | JohnAllen.Ennis@VDOT.Virginia.gov | (540) 332-9118 | Jethro Dienner | Jet.Dienner@vdot.virginia.gov | (540) 332-9290 |  |  |  | 1 | 2020 | 0 | FY2025 | 2553730 | 2553730 | NO DATES SET YET-PE OPEN | R | Determine Requirements milestone is 97 days past the expected completion date | G | Project is on budget | [5 empty] | 2019-10-31 | 2019-10-31 | 2019-11-14 | 2019-11-13 | G | 2019-11-15 | 2019-11-14 | 2020-11-16 |  | R | [5 empty] | 2021-09-21 |  | 2021-10-04 |  | G | 2023-01-17 |  | 2023-01-30 |  | G | 2023-06-22 |  | 2023-12-29 |  | G | 2023-02-15 |  | 2023-08-18 |  | G | 2022-06-29 |  | 2023-01-06 |  | G | [5 empty] | 2024-01-09 |  | 2024-01-09 |  | G | 2024-04-02 |  | 2024-08-21 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.083751
1012 | 115882 | ROUTE 1 MULTIMODAL CORRIDOR IMPROVEMENTS | 0001 | Primary | Reconstruction w/o Added Capacity | VDOT | Arlington County | FAIRFAX | Northern Virginia | Northern Virginia:Arlington County | Infrastructure Investment Division | Andrew G Beacher | Andrew.Beacher@vdot.virginia.gov | (703) 259-2239 | E Daniel Reinhard | Dan.Reinhard@vdot.virginia.gov | (703) 259-2599 |  |  |  | 0 |  | 0 | FY2027 | 250000000 | 250000000 | NO DATES SET YET-PE OPEN | G | Obtained Permits milestone finished 2200 days early | G | Project is on budget | [5 empty] | 2019-10-01 | 2019-10-01 | 2019-11-13 | 2019-11-13 | G | 2019-11-14 |  | 2023-11-20 |  | G | [5 empty] | 2024-11-18 |  | 2024-12-03 |  | G | 2026-02-26 |  | 2026-03-11 |  | G | 2026-08-04 |  | 2027-02-12 |  | G | 2026-03-27 |  | 2026-09-29 |  | G | 2025-08-14 | 2020-04-13 | 2026-04-22 | 2020-04-13 | G | [5 empty] | 2027-03-09 |  | 2027-03-09 |  | G | 2027-06-25 |  | 2027-06-25 |  | G | Preliminary design and/or investigations are still underway | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.13221
1013 | 117017 | #SGR21VB - RTE 666 OVER ELK CREEK (STR. 2781) - TOTAL REHAB | 0666 | Secondary | Bridge Rehab w/o Added Capacity | VDOT | Bedford County | BEDFORD | Salem | Roanoke:Bedford County | Infrastructure Investment Division | Anthony T Marshall | Todd.Marshall@VDOT.Virginia.gov | (540) 387-5460 | Jack D Bayne | Jack.Bayne@VDOT.Virginia.gov | (540) 387-5451 |  |  |  | 0 |  | 1 | FY2026 | 6282608 | 6282608 | NO DATES SET YET | G | Start Development milestone is 516 days ahead of the expected completion date | G | Project is on budget | [5 empty] | 2022-07-01 |  | 2022-07-22 |  | G | 2022-07-25 |  | 2023-05-26 |  | G | [5 empty] | 2023-12-28 |  | 2024-01-29 |  | G | 2024-09-16 |  | 2024-10-18 |  | G | 2025-03-27 |  | 2025-07-25 |  | G | 2024-11-05 |  | 2025-04-10 |  | G | 2024-12-16 |  | 2025-05-16 |  | G | [5 empty] | 2025-08-12 |  | 2025-08-12 |  | G | 2025-10-31 |  | 2025-10-31 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 1 | 0.43324
1014 | 117092 | #REVSH21 RTE 413 (MEMORIAL DRIVE) - RECONSTRUCTION | 0413 | Urban | Safety | Locally | Danville | HALIFAX | Lynchburg | Danville:Danville | Local Assistance Division | Gregg Allen | Gregg.Allen@vdot.virginia.gov | (434) 426-5575 | Gregg Allen | Gregg.Allen@vdot.virginia.gov | (434) 426-5575 | BRIAN DUNEVANT | dunevbl@danvilleva.gov | (434) 799-5019 | 0 |  | 0 | FY2029 | 1576470 | 1576470 | NO DATES SET YET | G | Agreement with Locality milestone is 1569 days ahead of the expected completion date | G | Project is on budget | 2025-01-31 |  | 2025-06-09 |  | G | 2025-06-10 |  | 2025-06-30 |  | G | 2026-01-09 |  | 2026-05-05 |  | G | [10 empty] | 2027-08-24 |  | 2027-09-28 |  | G | [5 empty] | 2027-09-29 |  | 2028-03-06 |  | G | 2028-02-01 |  | 2028-06-28 |  | G | [5 empty] | 2028-06-07 |  | 2028-07-05 |  | G | 2028-09-22 |  | 2028-09-22 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.084417
1015 | 117650 | #HRRR - TRENCH WIDENING (CN ONLY) | 9999 | Miscellaneous | Safety | VDOT | Fredericksburg District-wide |  | Fredericksburg | Fredericksburg:Fredericksburg District-wide | Infrastructure Investment Division | Jessica Graves | Jessica.Graves@vdot.virginia.gov | (540) 899-4267 | Sylvester C Okpala | Sylvester.Okpala@VDOT.Virginia.gov | (540) 907-8174 |  |  |  | 0 |  | 0 | FY2021 | 988000 | 988000 | AWARDED | G | Start Delivery milestone finished 51 days early | G | Project is on budget | [10 empty] | 2020-06-29 | 2020-06-29 | 2020-07-13 | 2020-07-13 | G | [25 empty] | 2020-06-29 | 2020-06-29 | 2020-11-30 | 2020-06-29 | G | [5 empty] | 2020-10-13 | 2020-09-22 | 2020-10-13 | 2020-09-22 | G | 2021-01-07 | 2020-11-17 | 2021-01-07 | 2020-11-17 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.070568
1016 | 117996 | W. Main Pedestrian Improvements South - Pulaski |  | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Pulaski | CHRISTIANSBURG | Salem | NonMPO:NonMPO | Local Assistance Division | Adam J Czesnowski | Adam.Czesnowski@vdot.virginia.gov | (540) 541-1216 | Adam J Czesnowski | Adam.Czesnowski@vdot.virginia.gov | (540) 541-1216 | Bill Pedigo | bpedigo@pulaskitown.org | (540) 994-8616 | 0 |  | 0 | FY2024 | 486051 | 486051 | NO DATES SET YET | G | Agreement with Locality milestone is 50 days ahead of the expected completion date | G | Project is on budget | 2020-12-01 |  | 2021-04-12 |  | G | 2021-04-13 |  | 2021-05-03 |  | G | 2021-11-08 |  | 2022-03-09 |  | G | [25 empty] | 2023-03-06 |  | 2023-08-01 |  | G | [5 empty] | 2023-09-28 |  | 2023-10-26 |  | G | 2024-01-23 |  | 2024-01-23 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.36301
1017 | 118491 | #SGR21LP DUKE STREET EB PRIMARY EXTENSION PAVING | 0236 | Primary | Resurfacing | VDOT | Alexandria | FAIRFAX | Northern Virginia | Northern Virginia:Alexandria | Infrastructure Investment/Asset Management Division | Edmund A Okerchiri | Edmund.Okerchiri@VDOT.Virginia.gov | (703) 259-1726 | Sharif Ramsis | Sharif.Ramsis@vdot.virginia.gov | (703) 259-2607 | Mary Alice Winston |  | (703) 746-4067 | 0 |  | 1 | FY2021 | 750000 | 749972 | ACTIVITY DATES SET | Y | Solicit Bids milestone is 2 days ahead of the expected completion date and there is a risk of missing this milestone date | G | Project is on budget | [5 empty] | 2020-12-28 | 2020-12-21 | 2021-01-11 | 2020-12-21 | G | 2021-01-12 | 2020-12-23 | 2021-03-25 | 2020-12-23 | G | [35 empty] | 2021-02-23 |  | 2021-02-23 |  | Y | 2021-06-30 |  | 2021-06-30 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.1027
1018 | 80485 | IMPROVE DOWNTOWN STAUNTON, VA, STREETSCAPE |  | Enhancement | Landscaping/Beautification | Locally | Staunton | HARRISONBURG | Staunton | SAW:Staunton | Local Assistance Division | Michael S Fulcher | Michael.Fulcher@VDOT.Virginia.gov | (540) 332-2243 | Michael S Fulcher | Michael.Fulcher@VDOT.Virginia.gov | (540) 332-2243 | Lyle Hartt | harttlm@ci.staunton.va.us | (540) 332-3804 | 0 |  | 0 | FY2021 | 1779019 | 2139623 | AWARDED | G | Start Delivery milestone finished 4 days early | Y | Project estimate is less than $5M and is up to 20% over budget | [5 empty] | 2007-06-01 | 2007-09-14 | 2007-06-29 | 2007-09-14 | R | 2013-04-01 | 2013-04-01 | 2016-03-23 | 2016-03-23 | G | [10 empty] | 2016-03-23 | 2016-03-23 | 2016-05-10 | 2016-05-10 | G | [20 empty] | 2020-03-31 | 2019-07-29 | 2020-06-26 | 2019-09-16 | G | 2020-06-26 | 2020-08-10 | 2020-10-30 | 2020-10-26 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.28503
1019 | 101001 | #SGR18VB - RT 8 OVER MAYO RIVER (STR 13191) - BR REPLACE | 0008 | Primary | Bridge Replacement w/o Added Capacity | VDOT | Patrick County | MARTINSVILLE | Salem | NonMPO:NonMPO | Infrastructure Investment/Asset Management Division | Anthony T Marshall | Todd.Marshall@VDOT.Virginia.gov | (540) 387-5460 | Dana E Pauley | Dana.Pauley@VDOT.Virginia.gov | (540) 387-5476 |  |  |  | 0 |  | 1 | FY2026 | 3756340 | 3756340 | NO DATES SET YET | G | Determine Requirements milestone is 445 days ahead of the expected completion date | G | Project is on budget | [10 empty] | 2021-06-15 |  | 2022-05-12 |  | G | [20 empty] | 2024-07-30 |  | 2025-02-07 |  | G | [10 empty] | 2025-07-08 |  | 2025-07-08 |  | G | 2025-08-27 |  | 2025-09-17 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.060622
1020 | 102936 | #SGR19VB - RT 1 over Potomac Creek Bridge Replacement | 0001 | Primary | Bridge Replacement w/o Added Capacity | VDOT | Stafford County | FREDERICKSBURG | Fredericksburg | Fredericksburg:Stafford County | Infrastructure Investment/Asset Management Division | Khalil Minhas | Khalil.Minhas@vdot.virginia.gov | (540) 374-3369 | Michael T Coffey | MichaelT.Coffey@vdot.virginia.gov | (540) 899-4225 |  |  |  | 0 |  | 0 | FY2021 | 6576870 | 6961673 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 400 days early | Y | Project estimate is between $5M and $10M and is up to $1M over budget | [5 empty] | 2013-07-01 | 2013-07-01 | 2013-08-05 | 2013-08-05 | G | 2014-04-02 | 2014-04-02 | 2017-08-31 | 2017-08-31 | G | [5 empty] | 2017-10-19 | 2017-10-19 | 2017-10-27 | 2017-10-27 | G | 2019-01-17 | 2018-08-17 | 2019-02-01 | 2018-09-10 | G | 2020-02-05 | 2019-04-03 | 2020-12-07 | 2020-01-02 | G | 2019-02-19 | 2018-09-20 | 2020-02-04 | 2019-04-02 | G | 2014-02-25 | 2015-02-25 | 2019-12-11 | 2019-06-10 | G | [5 empty] | 2020-12-08 | 2020-01-07 | 2020-12-08 | 2020-01-07 | G | 2021-03-10 | 2020-02-28 | 2021-05-04 | 2020-03-30 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.055067
1021 | 104262 | Airport Road and Warrior Drive Extension | 0896 | Secondary | New Construction Roadway | Locally | Frederick County | EDINBURG | Staunton | Winchester:Frederick County | Local Assistance Division | Kimberly Cameron | Kim.Cameron@vdot.virginia.gov | (540) 332-7886 | Kimberly Cameron | Kim.Cameron@vdot.virginia.gov | (540) 332-7886 | Mike Stewart | mstewart@fcva.us | (540) 722-8218 | 0 |  | 0 | FY2020 | 5600000 | 8431764 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 323 days early | R | Project estimate is between $5M and $10M and is a $1M or more over budget | [5 empty] | 2014-05-01 | 2016-10-04 | 2017-05-31 | 2016-10-11 | G | 2014-06-30 | 2014-06-30 | 2016-12-30 | 2016-12-05 | G | [35 empty] | 2019-09-30 | 2019-01-14 | 2019-09-30 | 2019-01-14 | G | 2019-11-01 | 2019-02-28 | 2020-01-31 | 2019-03-14 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.31578
1022 | 107083 | RTE 621 (Winterpock, 360-Royal Birkdale) - MAJOR WIDENING | 0621 | Secondary | Reconstruction w/ Added Capacity | Locally | Chesterfield County | CHESTERFIELD | Richmond | Richmond:Chesterfield County | Local Assistance Division | Cynthia Crouch | Cynthia.Crouch@vdot.virginia.gov | (804) 609-5313 | Cynthia Crouch | Cynthia.Crouch@vdot.virginia.gov | (804) 609-5313 | BARB SMITH | SMITHBK@CHESTERFIELD.GOV | (804) 748-1037 | 0 |  | 0 | FY2021 | 18000000 | 21477592 | ADVERTISED | R | Relocate Utilities milestone is 235 days past the expected completion date | R | Project estimate is greater than $10M and is over budget by (a) 10% or more or (b) $5M or more | 2015-07-15 | 2015-09-29 | 2015-10-07 | 2015-09-29 | G | 2015-10-08 | 2015-12-29 | 2015-10-22 | 2015-12-29 | R | 2015-10-23 | 2015-12-18 | 2016-06-21 | 2017-12-20 | R | [10 empty] | 2018-09-20 | 2018-01-11 | 2018-10-03 | 2018-02-02 | G | 2019-07-08 | 2019-07-08 | 2020-07-01 |  | R | 2018-10-08 | 2018-05-30 | 2019-10-31 | 2019-06-24 | G | [10 empty] | 2020-08-04 | 2021-01-12 | 2020-11-30 | 2021-01-12 | R | 2020-12-01 | 2021-01-13 | 2021-03-01 |  | Y |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.36698
1023 | 109544 | #HB2.FY17 RTE 460 - LEFT & RIGHT TURN LANES AT RTE 630 | 0460 | Primary | Safety | VDOT | Appomattox County | APPOMATTOX | Lynchburg | NonMPO:NonMPO | Infrastructure Investment Division | Laura J Walton | Laura.Walton@VDOT.Virginia.gov | (434) 856-8286 | Gregory K Parsons | Gregory.Parsons@vdot.virginia.gov | (434) 856-8297 |  |  |  | 1 | 2017 | 0 | FY2019 | 721625 | 721625 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 23 days early | G | Project is on budget | [5 empty] | 2016-08-05 | 2016-08-05 | 2016-08-17 | 2016-08-17 | G | 2016-08-17 | 2016-08-17 | 2017-03-02 | 2017-03-01 | G | [5 empty] | 2017-07-10 | 2017-07-10 | 2017-07-21 | 2017-07-21 | G | 2017-12-01 | 2017-12-01 | 2017-12-14 | 2017-12-14 | G | 2018-07-31 | 2018-04-02 | 2019-02-20 | 2019-02-20 | G | 2018-01-25 | 2018-01-25 | 2018-07-30 | 2018-03-27 | G | 2018-01-25 | 2018-01-25 | 2018-09-25 | 2018-02-21 | G | [5 empty] | 2019-03-12 | 2019-03-12 | 2019-03-12 | 2019-03-12 | G | 2019-04-25 | 2019-05-28 | 2019-06-20 | 2019-05-28 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.098335
1024 | 110507 | US 258 Right Turn Lane at JWL, Jr. Sport Complex | 0258 | Urban | New Construction Roadway | Locally | Smithfield | FRANKLIN | Hampton Roads | NonMPO:NonMPO | Infrastructure Investment Division | Bryant H Porter | Bryant.Porter@VDOT.Virginia.gov | (757) 956-3092 | Joshua D Negovan | Joshua.Negovan@vdot.virginia.gov | (757) 956-3347 | William G. Saunders IV, AICP, CZA | Wsaunders@smithfieldva.gov | (757) 365-4266 | 0 |  | 0 | FY2020 | 878300 | 852800 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 426 days early | G | Project is on budget | 2017-01-03 | 2017-01-03 | 2017-03-30 | 2017-03-17 | G | 2017-03-31 | 2017-03-20 | 2017-04-04 | 2017-03-21 | G | 2017-04-05 | 2017-04-04 | 2017-10-06 | 2017-09-22 | G | [10 empty] | 2018-07-20 | 2018-07-20 | 2018-08-23 | 2018-08-23 | G | [5 empty] | 2018-08-27 | 2018-08-27 | 2019-06-10 | 2018-08-27 | G | [10 empty] | 2019-06-26 | 2018-10-01 | 2019-07-24 | 2018-10-29 | G | 2019-07-25 | 2018-10-30 | 2020-03-18 | 2019-01-17 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.17636
1025 | 111390 | #SGR18VB - RT 14 N END BRANCH, BRIDGE REHAB, EX STR 11835 | 0014 | Primary | Bridge Rehab w/o Added Capacity | VDOT | Mathews County | SALUDA | Fredericksburg | NonMPO:NonMPO | Infrastructure Investment/Asset Management Division | Annette F Adams | Annette.Adams@VDOT.Virginia.gov | (540) 372-3583 | Khalil Minhas | Khalil.Minhas@vdot.virginia.gov | (540) 374-3369 |  |  |  | 0 |  | 1 | FY2025 | 3245000 | 3245000 | NO DATES SET YET-PE OPEN | G | Start Development milestone finished 16 days early | G | Project is on budget | [5 empty] | 2020-07-13 | 2020-06-29 | 2020-07-24 | 2020-07-08 | G | 2020-07-27 | 2020-06-01 | 2021-06-23 |  | G | [5 empty] | 2022-05-27 |  | 2022-06-10 |  | G | 2023-08-11 |  | 2023-08-24 |  | G | 2024-01-25 |  | 2024-07-29 |  | G | 2023-09-11 |  | 2024-03-21 |  | G | 2023-08-04 |  | 2024-04-11 |  | G | [5 empty] | 2024-08-13 |  | 2024-08-13 |  | G | 2024-11-04 |  | 2024-11-04 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.13365
1026 | 112892 | SIGNAL REBUILDS | 9999 | Primary | Safety | VDOT | Fredericksburg District-wide |  | Fredericksburg | Fredericksburg:Fredericksburg District-wide | Infrastructure Investment Division | Peter A Hedrich | Peter.Hedrich@vdot.virginia.gov | (540) 899-4540 | Wesley Foor | Wesley.Foor@vdot.virginia.gov | (540) 604-1370 |  |  |  | 0 |  | 0 | FY2021 | 1300000 | 1300000 | CONSTRUCTION STARTED | G | Start Delivery milestone finished on-time | G | Project is on budget | [5 empty] | 2018-05-01 | 2018-05-01 | 2018-05-21 | 2018-05-03 | G | 2018-05-22 | 2018-05-04 | 2019-03-27 | 2019-03-13 | G | [5 empty] | 2018-10-05 | 2018-10-05 | 2018-10-12 | 2018-10-12 | G | 2020-02-24 | 2020-02-24 | 2020-02-24 | 2020-02-24 | G | 2020-02-19 | 2020-02-19 | 2020-02-19 | 2020-02-19 | G | 2020-02-28 | 2020-02-28 | 2020-07-06 | 2020-07-06 | G | [10 empty] | 2020-12-02 | 2020-12-02 | 2020-12-02 | 2020-12-02 | G | 2020-12-06 | 2020-12-06 | 2020-12-06 | 2020-12-06 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | WORK/TASK ORDER | 1 | 0 | 0.067803
1027 | 113435 | INDEPENDENT HILL DRIVE & BRISTOW ROAD - INSTALL NEW SIGNAL | 0619 | Secondary | Safety | VDOT | Prince William County | MANASSAS | Northern Virginia | Northern Virginia:Prince William County | Infrastructure Investment Division | Ivan M Horodyskyj | Ivan.Horodyskyj@VDOT.Virginia.gov | (703) 259-2330 | Anwar A Ansari | Anwar.Ansari@VDOT.Virginia.gov | (703) 334-0204 |  |  |  | 0 |  | 0 | FY2020 | 512683 | 512683 | AWARDED | G | Start Delivery milestone finished 178 days early | G | Project is on budget | [5 empty] | 2019-01-15 | 2018-08-29 | 2019-01-30 | 2018-11-06 | G | 2019-01-31 | 2018-11-07 | 2019-12-26 | 2019-04-30 | G | [5 empty] | 2019-05-30 | 2019-05-30 | 2019-06-12 | 2019-06-06 | G | 2019-08-12 | 2019-06-06 | 2019-08-12 | 2019-06-06 | G | 2019-06-17 | 2019-06-06 | 2019-06-17 | 2019-06-06 | G | 2019-08-12 | 2019-06-06 | 2019-08-12 | 2019-06-06 | G | [10 empty] | 2019-10-08 | 2019-06-11 | 2019-10-08 | 2019-07-02 | G | 2020-01-03 | 2019-07-09 | 2020-01-03 | 2019-07-09 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | WORK/TASK ORDER | 1 | 0 | 0.14358
1028 | 113595 | RTE 3 & 20 INT. IMPROVEMENT - GUARDRAIL TASK ORDER | 0003 | Primary | Safety | VDOT | Orange County | LOUISA | Culpeper | NonMPO:NonMPO | Infrastructure Investment Division | Ken Connors |  |  | Bethel Kefyalew | Bethel.Kefyalew@vdot.virginia.gov | (540) 603-6015 |  |  |  | 0 |  | 0 | FY2020 | 5841 | 5841 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 4 days early | G | Project is on budget | [10 empty] | 2019-02-26 | 2019-02-26 | 2019-07-02 | 2019-06-19 | G | [35 empty] | 2019-02-01 | 2019-07-18 | 2019-07-15 | 2019-07-18 | R | 2019-07-16 | 2019-07-18 | 2019-07-22 | 2019-07-18 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | WORK/TASK ORDER | 1 | 0 | 0.071918
1029 | 115308 | Windsor Road Drianage Improvements | 0000 | Urban | Mitigation of Water Pollution Due to Highway Runof | Locally | Roanoke | SALEM | Salem | Roanoke:Roanoke City | Local Assistance Division | Cheryl B Becker | Cheryl.Becker@vdot.virginia.gov | (540) 492-2531 | Cheryl B Becker | Cheryl.Becker@vdot.virginia.gov | (540) 492-2531 | Joseph Arthur | Joseph.Arthur@roanokeva.gov | (540) 853-5906 | 0 |  | 0 | FY2021 | 800000 | 800000 | AWARDED | G | Start Delivery milestone finished 137 days early | G | Project is on budget | 2019-05-31 | 2019-05-31 | 2019-08-23 | 2020-06-18 | R | 2019-08-26 | 2020-06-18 | 2019-08-28 | 2020-06-18 | R | 2019-08-29 | 2020-06-18 | 2020-03-11 | 2020-06-18 | R | [35 empty] | 2020-07-08 | 2020-06-18 | 2020-07-08 | 2020-06-18 | G | 2020-09-25 | 2020-06-18 | 2020-11-02 | 2020-06-18 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.20552
1030 | 103725 | #HB2.FY17 TURN LANE EXTENSION DAHLGREN NAVAL BASE | 0301 | Primary | Reconstruction w/o Added Capacity | VDOT | King George County | NORTHERN NECK | Fredericksburg | NonMPO:NonMPO | Infrastructure Investment Division | Michael T Coffey | MichaelT.Coffey@vdot.virginia.gov | (540) 899-4225 | Michael T Coffey | MichaelT.Coffey@vdot.virginia.gov | (540) 899-4225 |  |  |  | 1 | 2017 | 0 | FY2018 | 730000 | 730000 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 38 days early | G | Project is on budget | [5 empty] | 2013-03-25 | 2013-03-25 | 2013-02-05 | 2013-03-25 | R | 2013-03-07 | 2013-03-07 | 2016-10-03 | 2016-09-23 | G | [5 empty] | 2016-07-28 | 2016-07-28 | 2016-09-23 | 2016-09-23 | G | 2016-08-16 | 2016-08-16 | 2016-11-29 | 2016-11-22 | G | 2016-12-15 | 2016-12-14 | 2017-04-11 | 2017-03-23 | G | [5 empty] | 2016-11-16 | 2016-11-16 | 2016-12-01 | 2016-12-01 | G | [5 empty] | 2017-04-11 | 2017-04-11 | 2017-04-11 | 2017-04-11 | G | 2017-06-01 | 2017-06-19 | 2017-07-27 | 2017-06-19 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.077057
1031 | 106970 | N. CARLIN SPRINGS ROAD BIKE & INTERSECTION IMPROVEMENTS | 9999 | Secondary | Facilities for Pedestrians and Bicycles | Locally | Arlington County | FAIRFAX | Northern Virginia | Northern Virginia:Arlington County | Local Assistance Division | Amir Salahshoor | A.Salahshoor@VDOT.Virginia.gov | (703) 259-1957 | Rita Hockman | Rita.Hockman@vdot.virginia.gov | (804) 824-7421 | Glenn Page | GPage@ArlingtonVA.us | (703) 228-7525 | 0 |  | 0 | FY2023 | 490000 | 490000 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 773 days early | G | Project is on budget | 2015-09-01 | 2015-09-01 | 2015-11-30 | 2015-11-30 | G | 2015-12-01 | 2015-12-01 | 2015-12-14 | 2015-12-14 | G | 2015-12-15 | 2015-12-15 | 2016-08-09 | 2016-08-09 | G | [10 empty] | 2016-08-10 | 2016-08-10 | 2016-08-10 | 2016-08-10 | G | [20 empty] | 2021-09-13 | 2020-04-08 | 2022-03-11 | 2020-04-08 | G | 2022-03-11 | 2020-07-18 | 2022-08-30 | 2020-07-18 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.2366
1032 | 108789 | Chesapeake Portsmouth Blvd/Taylor Road FYA | 0337 | Urban | Safety | Locally | Chesapeake | NORFOLK | Hampton Roads | Hampton Roads:Chesapeake | Infrastructure Investment Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Johndel A Alcaide | John.Alcaide@vdot.virginia.gov | (757) 956-3098 | Kevin A. Eppley | keppley@cityofchesapeake.net | (757) 382-6501 | 0 |  | 0 | FY2019 | 280646 | 280646 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 73 days early | G | Project is on budget | 2016-07-01 | 2016-07-01 | 2016-09-26 | 2017-03-21 | R | 2016-09-27 | 2016-09-16 | 2016-09-29 | 2016-09-23 | G | 2016-09-30 | 2016-09-26 | 2017-04-12 | 2017-05-30 | R | [35 empty] | 2018-02-23 | 2018-07-23 | 2018-03-22 | 2018-11-04 | R | 2018-09-04 | 2018-11-05 | 2019-03-01 | 2018-12-18 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.20447
1033 | 110476 | NIXON ROAD - PAVE AS A RURAL RUSTIC ROAD | 0697 | Secondary | Reconstruction w/o Added Capacity | VDOT | Loudoun County | LEESBURG | Northern Virginia | Northern Virginia:Loudoun County | Infrastructure Investment Division | Tara L Atkins | Tara.Atkins@VDOT.Virginia.gov | (703) 259-1931 | Mehrdad Naderi | Mehrdad.Naderi@vdot.virginia.gov | (703) 259-2217 | Joe Kroboth, Loudoun County Dept. of Transportation & Capital Infrastructure | joe.kroboth@loudoun.gov | (571) 771-5710 | 0 |  | 0 | FY2023 | 1100010 | 1100010 | ACTIVITY DATES SET | G | Engage Public milestone finished on-time | Y | Estimate not current | [5 empty] | 2018-10-01 | 2018-10-01 | 2018-10-01 | 2018-10-01 | G | 2018-10-02 | 2018-10-02 | 2019-02-14 | 2019-01-22 | G | [5 empty] | 2018-11-06 | 2018-11-06 | 2019-01-22 | 2019-01-22 | G | [25 empty] | 2022-01-03 |  | 2022-08-31 |  | G | 2022-09-01 |  | 2023-03-31 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | WORK/TASK ORDER | 0 | 1 | 0.21516
1034 | 111273 | Wytheville Heritage Walk, Phase 3 |  | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Wytheville | WYTHEVILLE | Bristol | NonMPO:NonMPO | Local Assistance Division | Tabitha H Crowder | Tabitha.Crowder@vdot.virginia.gov | (276) 696-3482 | Kenneth R Plummer | KR.Plummer@VDOT.Virginia.gov | (276) 696-3261 | Steve Moore |  |  | 0 |  | 0 | FY2022 | 700337 | 700337 | ACTIVITY DATES SET | R | Start Purchasing Right-of-Way milestone is 13 days past the expected completion date | G | Project is on budget | 2018-01-05 | 2018-01-05 | 2018-02-20 | 2018-02-20 | G | 2018-02-21 | 2018-06-08 | 2018-02-23 | 2018-06-22 | R | 2018-02-26 | 2018-06-11 | 2018-12-11 | 2019-11-27 | R | [10 empty] | 2020-12-02 |  | 2021-02-08 |  | R | [5 empty] | 2021-02-10 |  | 2021-09-13 |  | G | [10 empty] | 2021-09-29 |  | 2021-10-27 |  | G | 2021-10-28 |  | 2021-12-10 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.29311
1035 | 111392 | #SGR19VB - LEGACY REPLACE RT 743 SOUTH RIVER EX (STR 04505) | 0743 | Secondary | Bridge Replacement w/o Added Capacity | VDOT | Caroline County | FREDERICKSBURG | Fredericksburg | NonMPO:NonMPO | Infrastructure Investment/Asset Management Division | Annette F Adams | Annette.Adams@VDOT.Virginia.gov | (540) 372-3583 | Benjamin Ernst | Benjamin.Ernst@vdot.virginia.gov | (571) 585-0902 |  |  |  | 0 |  | 0 | FY2021 | 1760460 | 1947735 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 161 days early | Y | Project estimate is less than $5M and is up to 20% over budget | [5 empty] | 2017-07-06 | 2017-07-06 | 2017-07-19 | 2017-07-19 | G | 2017-07-20 | 2017-09-28 | 2018-12-14 | 2018-10-03 | G | [5 empty] | 2019-01-04 | 2018-11-15 | 2019-01-17 | 2018-11-26 | G | 2019-10-11 | 2019-06-27 | 2019-10-25 | 2019-07-26 | G | 2020-03-26 | 2020-04-09 | 2020-11-10 | 2020-05-27 | G | 2019-11-12 | 2019-08-13 | 2020-05-13 | 2020-04-08 | G | 2019-10-10 | 2019-10-01 | 2020-06-17 | 2020-03-25 | G | [5 empty] | 2020-12-08 | 2020-09-08 | 2020-12-08 | 2020-09-08 | G | 2021-03-03 | 2020-11-17 | 2021-04-27 | 2020-11-17 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.058247
1036 | 113316 | Primary Extension - W Main St - NB - FKEY 1188 | 0000 | Urban | Resurfacing | Locally | Radford | CHRISTIANSBURG | Salem | NonMPO:NonMPO | Local Assistance Division | Adam J Czesnowski | Adam.Czesnowski@vdot.virginia.gov | (540) 541-1216 | Adam J Czesnowski | Adam.Czesnowski@vdot.virginia.gov | (540) 541-1216 | Basil Edwards | basil.edwards@radfordva.gov | (540) 731-3603 | 0 |  | 0 | FY2019 | 42614 | 42614 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 246 days early | G | Project is on budget | 2018-10-01 | 2018-08-01 | 2018-12-28 | 2018-09-13 | G | 2018-12-31 | 2018-09-14 | 2019-01-03 | 2018-09-18 | G | 2019-01-04 | 2018-10-01 | 2019-03-22 | 2018-10-02 | G | [35 empty] | 2018-12-03 | 2018-10-09 | 2018-12-31 | 2018-10-09 | G | 2019-05-28 | 2018-10-10 | 2019-06-28 | 2018-10-25 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.066077
1037 | 113478 | Sidewalk Improvement - Phase 2 | 9999 | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Blackstone | PETERSBURG | Richmond | NonMPO:NonMPO | Local Assistance Division | James Shepherd | James.Shepherd@vdot.virginia.gov | (804) 609-5305 | James Shepherd | James.Shepherd@vdot.virginia.gov | (804) 609-5305 | Philip Vannoorbeeck | philipv@townofblackstoneva.com | (434) 292-7251 | 0 |  | 0 | FY2022 | 460001 | 460001 | ACTIVITY DATES SET | R | Determine Requirements milestone finished 482 days late | G | Project is on budget | 2018-10-01 | 2018-10-01 | 2018-12-28 | 2019-05-24 | R | 2018-12-31 | 2019-07-01 | 2019-01-03 | 2019-07-09 | R | 2019-01-04 | 2019-07-10 | 2019-07-11 | 2020-11-04 | R | [35 empty] | 2021-05-21 |  | 2021-05-21 |  | G | 2021-08-11 |  | 2021-10-29 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.28039
1038 | 113817 | Yorktown Road 729 Milling and Overlay | 0238 | Urban | Resurfacing | Locally | Newport News | WILLIAMSBURG | Hampton Roads | Hampton Roads:Newport News | Infrastructure Investment Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Chessica Villaflores | Chessica.Villaflores@vdot.virginia.gov | (757) 956-3094 | Bryan Stilley, P.E. | bstilley@nnva.gov | (757) 926-8699 | 0 |  | 1 | FY2019 | 165836 | 165836 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 3 days early | G | Project is on budget | 2018-09-04 | 2018-09-04 | 2018-11-30 | 2018-12-06 | R | 2018-12-03 | 2018-12-06 | 2018-12-05 | 2018-12-06 | R | 2018-12-06 | 2018-12-07 | 2019-06-13 | 2019-04-08 | G | [25 empty] | 2019-03-26 | 2019-03-26 | 2019-05-20 | 2019-03-26 | G | [5 empty] | 2019-06-07 | 2019-06-03 | 2019-06-07 | 2019-06-04 | G | 2019-06-28 | 2019-06-25 | 2019-06-28 | 2019-06-25 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.16075
1039 | 115363 | City of Hampton 426 Mercury Blvd W - Paving | 0258 | Urban | Restoration and Rehabilitation | Locally | Hampton | WILLIAMSBURG | Hampton Roads | Hampton Roads:Hampton | Local Assistance Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Joshua D Negovan | Joshua.Negovan@vdot.virginia.gov | (757) 956-3347 | Sandon Rogers, L. S., P.E. | sandon.rogers@hampton.gov | (757) 727-6786 | 0 |  | 0 | FY2020 | 133000 | 133000 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 93 days early | G | Project is on budget | 2019-10-03 | 2019-10-03 | 2020-01-02 | 2019-11-06 | G | [5 empty] | 2019-10-03 | 2019-10-03 | 2019-10-16 | 2019-10-16 | G | [35 empty] | 2020-01-22 | 2019-10-10 | 2020-02-19 | 2019-11-07 | G | 2020-05-07 | 2020-02-04 | 2020-05-07 | 2020-02-04 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.10604
1040 | 115510 | #SMART20 Bicycle Lane on US Business 13 | 0013 | Primary | Safety and Education of Pedestrians /Bicyclisits | VDOT | Northampton County | ACCOMAC | Hampton Roads | NonMPO:NonMPO | Infrastructure Investment Division | John G Harman | JohnG.Harman@vdot.virginia.gov | (757) 956-3269 | John G Harman | JohnG.Harman@vdot.virginia.gov | (757) 956-3269 | Susan McGhee | smcghee@co.northampton.va.us | (757) 678-0443 | 1 | 2020 | 0 | FY2028 | 2360061 | 2360061 | NO DATES SET YET | G | Start Development milestone is 968 days ahead of the expected completion date | Y | Estimate not current | [5 empty] | 2023-08-15 |  | 2023-10-17 |  | G | 2023-10-18 |  | 2024-10-18 |  | G | [5 empty] | 2025-08-26 |  | 2025-09-09 |  | G | 2026-12-17 |  | 2026-12-31 |  | G | 2027-05-27 |  | 2027-12-03 |  | G | 2027-01-21 |  | 2027-07-26 |  | G | 2026-06-04 |  | 2026-12-10 |  | G | [5 empty] | 2027-12-14 |  | 2027-12-14 |  | G | 2028-03-09 |  | 2028-03-09 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.11325
1041 | 116330 | #I81CIP SWRO TOC FLOOR OPERATIONS |  | Interstate | Safety | VDOT | Roanoke County | SALEM | Salem | NonMPO:NonMPO | Infrastructure Investment Division | Ricky A Via | Ricky.Via@vdot.virginia.gov | (804) 371-2396 | Timothy L Martin | TimL.Martin@VDOT.Virginia.gov | (540) 375-0113 |  |  |  | 0 |  | 0 | FY2020 |  |  | CONSTRUCTION STARTED | G | Determine Requirements milestone finished 29 days early | R | Critical information missing | [10 empty] | 2019-09-20 | 2019-08-23 | 2020-02-04 | 2020-01-06 | G | [35 empty] | 2019-11-21 | 2019-11-21 | 2019-11-27 | 2019-11-27 | G | 2019-12-02 | 2019-12-02 | 2019-12-06 | 2019-12-06 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | WORK/TASK ORDER | 1 | 0 | 0.13216
1042 | 116842 | ROUTE 211 LEE HIGHWAY SIDEWALK | 0211 | Primary | Reconstruction w/o Added Capacity | Locally | Shenandoah County | EDINBURG | Staunton | NonMPO:NonMPO | Local Assistance Division | Kimberly Cameron | Kim.Cameron@vdot.virginia.gov | (540) 332-7886 | Jamison Brown | Jamison.Brown@vdot.virginia.gov | (540) 332-7389 | Todd Walters | t.walters@newmarketvirginia.com | (540) 740-3432 | 0 |  | 0 | FY2025 | 341400 | 341400 | NO DATES SET YET | G | Agreement with Locality milestone is 107 days ahead of the expected completion date | G | Project is on budget | 2021-02-01 |  | 2021-06-08 |  | G | 2021-06-09 |  | 2021-06-29 |  | G | 2022-01-10 |  | 2022-05-04 |  | G | [10 empty] | 2023-08-23 |  | 2023-09-27 |  | G | [5 empty] | 2023-09-28 |  | 2024-03-05 |  | G | 2024-03-21 |  | 2024-08-16 |  | G | [5 empty] | 2024-07-26 |  | 2024-08-22 |  | G | 2024-11-13 |  | 2024-11-13 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.27813
1043 | 116990 | #SGR21VP FY21 Plant Mix Districtwide Primaries | 9999 | Primary | Resurfacing | VDOT | Salem District-wide |  | Salem | NonMPO:NonMPO | Infrastructure Investment/Asset Management Division | Robert P Williams | Robbie.Williams@VDOT.Virginia.gov | (276) 229-9954 | Ibrahim M Abuawad | Ibrahim.Abuawad@vdot.virginia.gov | (217) 418-8827 |  |  |  | 0 |  | 0 | FY2021 | 2484885 | 2484885 | ADVERTISED | G | Solicit Bids milestone finished 28 days early | G | Project is on budget | [10 empty] | 2020-11-18 | 2020-11-18 | 2020-11-24 | 2020-11-24 | G | [35 empty] | 2020-12-08 | 2021-02-09 | 2021-03-09 | 2021-02-09 | G | 2021-05-27 |  | 2021-06-30 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.11957
1044 | 117122 | Curlew Drive Multi-Use Path |  | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Norfolk | NORFOLK | Hampton Roads | Hampton Roads:Norfolk | Local Assistance Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Derrick Williams | Derrick.Williams@vdot.virginia.gov | (757) 956-3097 | Deborah Mangiaracina | Deborah.Mangiaracina@norfolk.gov | (757) 664-7459 | 0 |  | 0 | FY2024 | 958000 | 958000 | NO DATES SET YET | G | Agreement with Locality milestone is 80 days ahead of the expected completion date | G | Project is on budget | 2021-01-04 |  | 2021-05-12 |  | G | 2021-05-13 |  | 2021-06-07 |  | G | 2021-10-25 |  | 2022-02-23 |  | G | [25 empty] | 2023-01-23 |  | 2023-06-20 |  | G | [5 empty] | 2023-08-17 |  | 2023-09-14 |  | G | 2023-12-07 |  | 2023-12-07 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.39954
1045 | 117157 | #SGR21LP City of Suffolk 1813 Carolina Rd | 0032 | Urban | Resurfacing | Locally | Suffolk | NORFOLK | Hampton Roads | Hampton Roads:Suffolk | Infrastructure Investment/Asset Management Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Johndel A Alcaide | John.Alcaide@vdot.virginia.gov | (757) 956-3098 | Edward Heide | eheide@suffolkva.us | (757) 514-7615 | 0 |  | 1 | FY2022 | 242572 | 242572 | NO DATES SET YET | G | Agreement with Locality milestone is 80 days ahead of the expected completion date | G | Project is on budget | 2021-01-04 |  | 2021-05-12 |  | G | 2021-05-13 |  | 2021-06-03 |  | G | 2021-07-02 |  | 2021-08-04 |  | G | [25 empty] | 2021-07-08 |  | 2021-08-04 |  | G | [5 empty] | 2021-10-01 |  | 2021-10-29 |  | G | 2022-01-26 |  | 2022-01-26 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.067885
1046 | 117770 | INSTALL GUARDRAIL UPGRADES - RTE 67 TAZEWELL CO | 0067 | Primary | Safety | VDOT | Tazewell County | LEBANON | Bristol | NonMPO:NonMPO | Infrastructure Investment Division | Brian Holt | Brian.Holt@vdot.virginia.gov | (276) 696-3414 | Jeremy J Mullins | Jeremy.Mullins@vdot.virginia.gov | (276) 696-3259 |  |  |  | 0 |  | 0 | FY2023 | 130148 | 130148 | NO DATES SET YET-PE OPEN | G | Obtained Permits milestone finished 851 days early | G | Project is on budget | [5 empty] | 2020-06-22 | 2020-06-22 | 2020-07-13 | 2020-07-13 | G | 2020-07-14 | 2020-07-21 | 2021-05-17 |  | G | [5 empty] | 2021-12-16 |  | 2022-01-18 |  | G | [5 empty] | 2022-09-07 |  | 2023-01-11 |  | G | [5 empty] | 2022-06-15 | 2020-07-16 | 2022-11-14 | 2020-07-16 | G | [5 empty] | 2023-02-14 |  | 2023-02-14 |  | G | 2023-05-04 |  | 2023-05-04 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | REGIONAL ON-CALL CONTRACT | 0 | 0 | 0.060944
1047 | 19036 | FOREST HILL AVENUE IMPROVEMENTS |  | Urban | Reconstruction w/o Added Capacity | Locally | Richmond | ASHLAND | Richmond | Richmond:Richmond | Infrastructure Investment Division | Brian J Lokker | Brian.Lokker@VDOT.Virginia.gov | (804) 524-6010 | Brian J Lokker | Brian.Lokker@VDOT.Virginia.gov | (804) 524-6010 | Kevin Newcomb | Kevin.Newcomb@richmondgov.com | (804) 646-1847 | 0 |  | 0 | FY2019 | 4070000 | 12700956 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 119 days early | R | Project estimate is less than $5M and is 20% or more over budget | [5 empty] | 2005-01-17 | 2004-08-23 | 2005-01-31 | 2004-10-12 | G | 2005-02-01 | 2005-01-18 | 2005-06-30 | 2005-05-27 | G | [10 empty] | 2013-08-19 | 2013-08-19 | 2013-09-06 | 2013-09-06 | G | [20 empty] | 2017-10-13 | 2017-10-13 | 2018-02-15 | 2018-02-15 | G | 2018-02-16 | 2018-02-16 | 2018-08-30 | 2018-05-03 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.1403
1048 | 80486 | CONSTRUCT ACCESS ROAD & ROADWAY IMPROVEMENTS CHESSIE SITE |  | Urban | New Construction Roadway | VDOT | Clifton Forge | LEXINGTON | Staunton | NonMPO:NonMPO | Infrastructure Investment Division | Ronald L Tabor | Ronald.Tabor@vdot.virginia.gov | (540) 332-7887 | Ronald L Tabor | Ronald.Tabor@vdot.virginia.gov | (540) 332-7887 | Tracey Shiflett |  |  | 0 |  | 0 | FY2025 | 1362220 | 971320 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 2029 days early | G | Project is on budget | [5 empty] | 2007-06-01 | 2007-09-11 | 2007-06-29 | 2007-09-11 | R | 2018-02-05 | 2018-02-05 | 2018-03-15 | 2018-02-27 | G | [10 empty] | 2018-08-22 | 2018-08-22 | 2018-12-03 | 2018-12-03 | G | [5 empty] | 2019-02-20 | 2019-02-20 | 2019-05-31 | 2019-05-31 | G | [10 empty] | 2024-09-12 | 2019-04-26 | 2025-11-26 | 2019-06-25 | G | 2025-01-15 | 2019-08-23 | 2025-03-13 | 2019-08-23 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.073765
1049 | 101238 | RTE 618 - BRIDGE REPLACEMENT (Bridge Only) | 0618 | Secondary | Bridge Replacement w/o Added Capacity | VDOT | Nottoway County | PETERSBURG | Richmond | NonMPO:NonMPO | Infrastructure Investment Division | Susan Warr | Susan.Warr@VDOT.Virginia.gov | (804) 720-5478 | Susan Warr | Susan.Warr@VDOT.Virginia.gov | (804) 720-5478 |  |  |  | 0 |  | 0 | FY2021 | 2527605 | 2527604 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 73 days early | G | Project is on budget | [5 empty] | 2013-07-26 | 2013-09-18 | 2013-07-26 | 2013-09-18 | R | 2013-09-19 | 2013-09-19 | 2018-02-23 | 2018-02-21 | G | [5 empty] | 2018-07-30 | 2018-07-30 | 2018-08-14 | 2018-08-14 | G | 2019-06-03 | 2019-05-22 | 2019-06-28 | 2019-05-30 | G | 2020-02-03 | 2019-08-19 | 2020-08-05 | 2019-08-19 | G | 2019-06-24 | 2019-06-18 | 2019-12-31 | 2019-12-04 | G | [10 empty] | 2020-09-08 | 2020-09-08 | 2020-09-08 | 2020-09-08 | G | 2020-10-29 | 2020-11-17 | 2021-01-29 | 2020-11-17 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.061616
1050 | 115721 | INSTALLATION OF FLASHING YELLOW ARROWS - DW (CN-ONLY) | 9999 | Primary | Safety | VDOT | Richmond District-wide |  | Richmond | NonMPO:NonMPO | Infrastructure Investment Division | Adam S Brooks | Adam.Brooks@VDOT.Virginia.gov | (804) 609-5274 | Adam S Brooks | Adam.Brooks@VDOT.Virginia.gov | (804) 609-5274 |  |  |  | 0 |  | 0 | FY2022 | 1800000 | 1800000 | NO DATES SET YET | G | Determine Requirements milestone is 295 days ahead of the expected completion date | G | Project is on budget | [10 empty] | 2021-08-03 |  | 2021-12-13 |  | G | [35 empty] | 2021-12-15 |  | 2021-12-21 |  | G | 2021-12-22 |  | 2021-12-29 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | WORK/TASK ORDER | 0 | 0 | 0.07287
1051 | 116648 | EDGE LINE RUMBLE STRIPS - BRISTOL DISTRICT WIDE | 9999 | Miscellaneous | Safety | VDOT | Bristol District-wide |  | Bristol | NonMPO:NonMPO | Infrastructure Investment Division | Jeremy J Mullins | Jeremy.Mullins@vdot.virginia.gov | (276) 696-3259 | Chase R Buchanan | Chase.Buchanan@VDOT.Virginia.gov | (276) 696-3251 |  |  |  | 0 |  | 0 | FY2023 | 1119210 | 1119210 | NO DATES SET YET-PE OPEN | R | Determine Requirements milestone is 12 days past the expected completion date | G | Project is on budget | [5 empty] | 2020-06-01 | 2020-06-01 | 2020-06-12 | 2020-06-01 | G | 2020-06-15 |  | 2021-02-09 |  | R | [5 empty] | 2021-10-12 |  | 2021-11-24 |  | G | [5 empty] | 2022-03-17 |  | 2022-07-08 |  | G | [5 empty] | 2022-03-02 |  | 2022-06-01 |  | G | [5 empty] | 2022-07-12 |  | 2022-07-12 |  | G | 2022-09-30 |  | 2022-09-30 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.068577
1052 | 116856 | GARBERS CHURCH ROAD BIKE-BUGGY LANE |  | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Rockingham County | HARRISONBURG | Staunton | Harrisonburg:Rockingham County | Local Assistance Division | Kimberly Cameron | Kim.Cameron@vdot.virginia.gov | (540) 332-7886 | Michael S Fulcher | Michael.Fulcher@VDOT.Virginia.gov | (540) 332-2243 | Stephen King | sking@rockinghamcountyva.gov | (540) 564-3033 | 0 |  | 0 | FY2024 | 2036303 | 2036303 | NO DATES SET YET | G | Agreement with Locality milestone is 57 days ahead of the expected completion date | G | Project is on budget | 2020-12-08 |  | 2021-04-19 |  | G | 2021-04-20 |  | 2021-05-10 |  | G | 2021-06-09 |  | 2021-09-30 |  | G | [10 empty] | 2023-01-27 |  | 2023-03-03 |  | G | [5 empty] | 2023-03-06 |  | 2023-08-01 |  | G | 2023-06-28 |  | 2023-11-29 |  | G | [5 empty] | 2023-11-03 |  | 2023-12-05 |  | G | 2024-02-28 |  | 2024-02-28 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.27406
1053 | 117042 | S. Laburnum Ave NB Sidewalk | 9999 | Secondary | Facilities for Pedestrians and Bicycles | Locally | Henrico County | ASHLAND | Richmond | Richmond:Henrico County | Local Assistance Division | Douglas L Orcutt | Doug.Orcutt@vdot.virginia.gov | (804) 609-5428 | Douglas L Orcutt | Doug.Orcutt@vdot.virginia.gov | (804) 609-5428 | TBD |  | TBD | 0 |  | 0 | FY2029 | 1892700 | 1892700 | NO DATES SET YET | G | Agreement with Locality milestone is 1543 days ahead of the expected completion date | G | Project is on budget | 2025-01-06 |  | 2025-05-14 |  | G | 2025-05-15 |  | 2025-06-05 |  | G | 2025-12-15 |  | 2026-04-10 |  | G | [10 empty] | 2027-07-30 |  | 2027-09-02 |  | G | [5 empty] | 2027-09-03 |  | 2028-02-09 |  | G | 2028-01-05 |  | 2028-06-05 |  | G | [5 empty] | 2028-05-12 |  | 2028-06-09 |  | G | 2028-08-29 |  | 2028-08-29 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.35498
1054 | 117156 | #SGR21LP City of Virginia Beach 2095 VA Beach Blvd | 0058 | Urban | Resurfacing | Locally | Virginia Beach | NORFOLK | Hampton Roads | Hampton Roads:Virginia Beach | Infrastructure Investment/Asset Management Division | Susan Wilson | Susan.Wilson@vdot.virginia.gov | (757) 956-3099 | Marci Thompson | Marci.Thompson@vdot.virginia.gov | (757) 956-3093 | Jimmy Evans | jrevans@vbgov.com | (757) 385-1505 | 0 |  | 1 | FY2022 | 621461 | 621461 | NO DATES SET YET | G | Agreement with Locality milestone is 80 days ahead of the expected completion date | G | Project is on budget | 2021-01-04 |  | 2021-05-12 |  | G | 2021-05-13 |  | 2021-06-03 |  | G | 2021-07-02 |  | 2021-07-30 |  | G | [25 empty] | 2021-07-02 |  | 2021-07-30 |  | G | [5 empty] | 2021-09-28 |  | 2021-10-26 |  | G | 2022-01-21 |  | 2022-01-21 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.065685
1055 | 117195 | Siege Lane Sidewalk |  | Urban | Facilities for Pedestrians and Bicycles | Locally | York County | WILLIAMSBURG | Hampton Roads | Hampton Roads:York County | Local Assistance Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Keisha Wilkins | Keisha.Wilkins@vdot.virginia.gov | (757) 956-3110 | Timothy Cross | tcross@yorkcounty.gov | (757) 890-3496 | 0 |  | 0 | FY2024 | 356650 | 356650 | NO DATES SET YET | R | Agreement with Locality milestone is 72 days past the expected completion date | G | Project is on budget | 2020-08-03 |  | 2020-12-11 |  | R | 2020-12-14 |  | 2021-01-05 |  | R | 2021-07-14 |  | 2021-11-04 |  | G | [10 empty] | 2023-03-03 |  | 2023-04-06 |  | G | [5 empty] | 2023-04-07 |  | 2023-09-05 |  | G | 2023-08-02 |  | 2024-01-04 |  | G | [5 empty] | 2023-12-12 |  | 2024-01-10 |  | G | 2024-04-02 |  | 2024-04-02 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.12285
1056 | 117942 | #TAP21 KEMPER ROAD - CONSTRUCT SIDEWALK | 9999 | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Danville | HALIFAX | Lynchburg | Danville:Danville | Local Assistance Division | Gregg Allen | Gregg.Allen@vdot.virginia.gov | (434) 426-5575 | Gregg Allen | Gregg.Allen@vdot.virginia.gov | (434) 426-5575 | BRIAN DUNEVANT | dunevbl@danvilleva.gov | (434) 799-5019 | 0 |  | 0 | FY2025 | 437000 | 437000 | NO DATES SET YET | G | Agreement with Locality milestone is 106 days ahead of the expected completion date | G | Project is on budget | 2021-01-29 |  | 2021-06-07 |  | G | 2021-06-08 |  | 2021-06-28 |  | G | 2022-01-07 |  | 2022-05-03 |  | G | [10 empty] | 2023-08-22 |  | 2023-09-26 |  | G | [5 empty] | 2023-09-27 |  | 2024-03-04 |  | G | 2024-01-30 |  | 2024-06-26 |  | G | [5 empty] | 2024-06-05 |  | 2024-07-02 |  | G | 2024-09-20 |  | 2024-09-20 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.18913
1057 | 59259 | RTE 655 - RECONSTRUCTION | 0655 | Secondary | Reconstruction w/o Added Capacity | VDOT | Frederick County | EDINBURG | Staunton | Winchester:Frederick County | Infrastructure Investment Division | Scott A Alexander | Scott.Alexander@VDOT.Virginia.gov | (540) 332-9030 | Scott A Alexander | Scott.Alexander@VDOT.Virginia.gov | (540) 332-9030 |  |  |  | 0 |  | 0 | FY2019 | 5761136 | 6101063 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 44 days early | Y | Project estimate is between $5M and $10M and is up to $1M over budget | [5 empty] | 2007-10-01 | 2007-06-04 | 2007-10-31 | 2007-06-04 | G | 2007-08-20 | 2007-08-20 | 2010-04-30 | 2010-05-11 | R | [5 empty] | 2012-02-14 | 2012-02-14 | 2012-02-14 | 2012-02-14 | G | 2012-08-20 | 2012-08-20 | 2012-09-11 | 2012-09-11 | G | 2017-11-07 | 2017-11-07 | 2018-09-18 | 2018-09-13 | G | 2013-03-01 | 2013-03-01 | 2017-10-31 | 2017-10-31 | G | 2017-08-01 | 2017-08-01 | 2018-05-09 | 2018-07-23 | R | [5 empty] | 2018-07-02 | 2018-11-06 | 2018-11-13 | 2018-11-06 | G | 2019-01-02 | 2019-01-16 | 2019-03-01 | 2019-01-16 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.093943
1058 | 100583 | RTE 121 CFX - POUND CONNECTOR - VDOT FINAL WORK | 0121 | Primary | New Construction Roadway | VDOT | Wise County | WISE | Bristol | NonMPO:NonMPO | Infrastructure Investment Division | Marty R Halloway | Marty.Halloway@VDOT.Virginia.gov | (276) 696-3367 | Robert C Leonard | Robert.Leonard@VDOT.Virginia.gov | (276) 696-3258 |  |  |  | 0 |  | 0 | FY2025 | 61000000 | 61000000 | NO DATES SET YET | G | Start Development milestone is 892 days ahead of the expected completion date | G | Project is on budget | [5 empty] | 2023-06-30 |  | 2023-08-02 |  | G | 2023-09-29 |  | 2023-11-30 |  | G | [35 empty] | 2024-07-01 |  | 2024-12-02 |  | G | 2025-01-28 |  | 2025-02-17 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | DESIGN BUILD/PPTA | 0 | 1 | 0.19453
1059 | 103320 | #HB2.FY17 Add merging lane on I-77N in Ft. Chiswell | 0077 | Interstate | Reconstruction w/ Added Capacity | VDOT | Wythe County | WYTHEVILLE | Bristol | NonMPO:NonMPO | Infrastructure Investment Division | Ronald C Flanary | Ronald.Flanary@VDOT.Virginia.gov | (276) 696-3252 | Ronald C Flanary | Ronald.Flanary@VDOT.Virginia.gov | (276) 696-3252 |  |  |  | 1 | 2017 | 0 | FY2018 | 9100000 | 8300000 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished on-time | G | Project is on budget | [5 empty] | 2013-06-25 | 2013-06-25 | 2013-07-10 | 2013-07-10 | G | 2013-07-10 | 2013-07-10 | 2013-10-01 | 2013-09-26 | G | 2016-11-10 | 2016-11-10 | 2017-01-11 | 2017-01-11 | G | [30 empty] | 2017-06-13 | 2017-06-13 | 2017-06-13 | 2017-06-13 | G | 2017-08-17 | 2017-08-17 | 2017-08-17 | 2017-08-17 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.093345
1060 | 104359 | Rte 58/Manning Bridge Rd Intersection Improvements | 9999 | Urban | New Construction Roadway | Locally | Suffolk | NORFOLK | Hampton Roads | Hampton Roads:Suffolk | Local Assistance Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Johndel A Alcaide | John.Alcaide@vdot.virginia.gov | (757) 956-3098 | Mark Velasquez | mvelasquez@suffolkva.us | (757) 514-7626 | 0 |  | 0 | FY2019 | 5370817 | 8138065 | ADVERTISED | R | Start Delivery milestone is 660 days past the expected completion date | R | Project estimate is between $5M and $10M and is a $1M or more over budget | 2013-09-24 | 2013-09-24 | 2013-09-24 | 2013-09-24 | G | 2013-08-01 | 2013-08-01 | 2013-08-01 | 2013-08-01 | G | 2014-03-03 | 2014-04-01 | 2014-07-01 | 2014-09-22 | R | [10 empty] | 2015-07-27 | 2015-07-27 | 2015-07-29 | 2015-07-29 | G | [20 empty] | 2018-08-31 | 2020-09-30 | 2018-08-31 | 2020-09-30 | R | 2018-10-02 |  | 2019-05-03 |  | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.12829
1061 | 105648 | RTE 618 (Old Bermuda Hundred/Permilla Sp.) - RECONSTRUCTION | 0618 | Secondary | Reconstruction w/o Added Capacity | Locally | Chesterfield County | CHESTERFIELD | Richmond | Richmond:Chesterfield County | Local Assistance Division | Brian J Lokker | Brian.Lokker@VDOT.Virginia.gov | (804) 524-6010 | Brian J Lokker | Brian.Lokker@VDOT.Virginia.gov | (804) 524-6010 | Nate Mathis | mathisn@chesterfield.gov | (804) 748-1037 | 0 |  | 0 | FY2019 | 8000000 | 4222000 | CONSTRUCTION STARTED | R | Start Delivery milestone finished 63 days late | G | Project is on budget | 2014-07-07 | 2014-07-07 | 2014-07-07 | 2014-07-07 | G | 2014-11-01 | 2014-07-07 | 2014-11-01 | 2014-07-15 | G | 2015-08-31 | 2015-08-04 | 2015-10-31 | 2015-10-16 | G | [10 empty] | 2017-06-14 | 2017-06-14 | 2017-06-14 | 2017-06-14 | G | [5 empty] | 2017-06-27 | 2017-06-27 | 2018-08-31 | 2018-03-30 | G | [10 empty] | 2018-10-31 | 2018-10-17 | 2018-10-31 | 2018-10-17 | G | 2019-02-28 | 2019-02-13 | 2019-02-28 | 2019-05-02 | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.33616
1062 | 107085 | RTE 641 - REPLACE SD BRIDGE FED ID 5280 (Now a Tier 1 Proj) | 0641 | Secondary | Bridge Replacement w/o Added Capacity | VDOT | Chesterfield County | CHESTERFIELD | Richmond | Richmond:Chesterfield County | Local Assistance Division | Raymond Chapman | Scott.Chapman@vdot.virginia.gov | (804) 609-5277 | Raymond Chapman | Scott.Chapman@vdot.virginia.gov | (804) 609-5277 |  |  |  | 0 |  | 0 | FY2022 | 7500000 | 6019000 | ACTIVITY DATES SET | R | Complete Purchasing Right-of-Way milestone is 114 days past the expected completion date | G | Project is on budget | [5 empty] | 2017-02-09 | 2017-02-09 | 2017-02-21 | 2017-02-21 | G | 2017-02-22 | 2017-02-22 | 2018-05-03 | 2018-05-03 | G | [5 empty] | 2019-02-13 | 2019-02-13 | 2019-02-27 | 2019-02-21 | G | 2019-09-24 | 2020-05-14 | 2019-09-30 | 2020-05-29 | R | 2020-12-04 |  | 2021-08-09 |  | G | 2019-10-16 | 2020-08-06 | 2020-10-30 |  | R | 2020-04-07 | 2020-04-07 | 2021-04-07 | 2021-01-26 | G | [5 empty] | 2021-08-10 |  | 2021-08-10 |  | G | 2021-09-23 |  | 2021-12-21 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 1 | 0.19886
1063 | 108657 | Main Street sidewalk reconstruction | 0040 | Urban | Reconstruction w/o Added Capacity | Locally | Blackstone | PETERSBURG | Richmond | NonMPO:NonMPO | Local Assistance Division | Brian J Lokker | Brian.Lokker@VDOT.Virginia.gov | (804) 524-6010 | Brian J Lokker | Brian.Lokker@VDOT.Virginia.gov | (804) 524-6010 | Phillip Vannoorbeeck |  |  | 0 |  | 0 | FY2019 | 460000 | 460000 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 399 days early | G | Project is on budget | 2017-07-12 | 2016-09-19 | 2017-10-04 | 2017-04-10 | G | 2017-10-05 | 2017-02-08 | 2017-10-10 | 2017-02-08 | G | 2017-10-11 | 2017-04-01 | 2018-04-20 | 2017-04-17 | G | [35 empty] | 2018-06-13 | 2017-05-25 | 2018-07-11 | 2017-05-26 | G | 2018-07-12 | 2017-07-18 | 2018-08-21 | 2017-07-18 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.07891
1064 | 110793 | #SMART18 - Intersection improvements - Routes 11 and 19 | 0019 | Primary | Reconstruction w/ Added Capacity | VDOT | Abingdon | ABINGDON | Bristol | Bristol:Abingdon | Infrastructure Investment Division | Allan D Sumpter | Allan.Sumpter@VDOT.virginia.gov | (276) 525-6461 | Brandi Halloway | Brandi.Halloway@vdot.virginia.gov | (276) 696-3254 |  |  |  | 1 | 2018 | 0 | FY2022 | 1704000 | 1704000 | ACTIVITY DATES SET | G | Engage Public milestone finished on-time | G | Project is on budget | [5 empty] | 2019-07-05 | 2019-07-05 | 2019-07-18 | 2019-07-18 | G | 2019-07-19 | 2019-07-19 | 2020-02-10 | 2020-02-10 | G | [5 empty] | 2020-07-13 | 2020-07-13 | 2020-08-21 | 2020-08-21 | G | [5 empty] | 2021-01-08 | 2021-01-08 | 2021-05-04 |  | G | [15 empty] | 2021-05-11 |  | 2021-05-17 |  | G | 2021-07-01 |  | 2021-08-26 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.087007
1065 | 111317 | #SMART20 - Williamson Road Sidewalk Improvements |  | Enhancement | Facilities for Pedestrians and Bicycles | VDOT | Roanoke County | SALEM | Salem | Roanoke:Roanoke County | Infrastructure Investment Division | Alex H Price | Alex.Price@VDOT.Virginia.gov | (540) 378-5053 | Bradley Sampson | Bradley.Sampson@vdot.virginia.gov | (540) 387-5391 | Roanoke County |  |  | 1 | 2020 | 0 | FY2024 | 1934000 | 1934000 | ACTIVITY DATES SET | G | Determine Requirements milestone finished on-time | G | Project is on budget | [5 empty] | 2019-06-25 | 2019-06-25 | 2019-07-23 | 2019-07-23 | G | 2019-07-24 | 2019-07-23 | 2020-06-19 | 2020-06-19 | G | [5 empty] | 2021-06-21 | 2020-10-16 | 2021-07-19 |  | G | 2022-06-17 |  | 2022-06-30 |  | G | 2022-11-28 |  | 2023-05-03 |  | G | 2022-07-19 |  | 2023-03-13 |  | G | [10 empty] | 2023-06-13 |  | 2023-06-13 |  | G | 2023-06-14 |  | 2023-11-03 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 1 | 0.25201
1066 | 111776 | #SGR18VB - RT 601 SUPERSTRUCTURE REPLACE. STR. 6261 | 0601 | Secondary | Bridge Rehab w/o Added Capacity | VDOT | Albemarle County | CHARLOTTESVILLE | Culpeper | Charlottesville:Albemarle County | Infrastructure Investment Division | Braden C Chapman | Braden.Chapman@VDOT.Virginia.gov | (540) 829-7421 | Brian A Arnold | Brian.Arnold@VDOT.Virginia.gov | (540) 829-7557 |  |  |  | 0 |  | 1 | FY2024 | 3038026 | 3038026 | ACTIVITY DATES SET | R | Engage Public milestone finished 110 days late | G | Project is on budget | [5 empty] | 2020-04-10 | 2019-02-01 | 2020-04-23 | 2019-02-12 | G | 2020-04-24 | 2019-02-01 | 2021-03-24 | 2020-03-09 | G | [5 empty] | 2020-03-12 | 2020-03-12 | 2020-07-02 | 2020-10-20 | R | 2022-09-28 |  | 2022-10-11 |  | G | 2023-03-14 |  | 2023-09-14 |  | G | 2022-10-27 |  | 2023-05-08 |  | G | [10 empty] | 2023-10-10 |  | 2023-10-10 |  | G | 2024-02-06 |  | 2024-02-06 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 1 | 0.43175
1067 | 113195 | HATCHER AVENUE SIDEWALK IMPROVEMENTS | 9999 | Urban | Facilities for Pedestrians and Bicycles | Locally | Purcellville | LEESBURG | Northern Virginia | Northern Virginia:Purcellville | Local Assistance Division | Kimberly Mccool | Kimberly.McCool@vdot.virginia.gov | (703) 259-3220 | Christer P Carshult | Christer.Carshult@vdot.virginia.gov | (703) 259-1765 | Dale Lehning |  |  | 0 |  | 0 | FY2023 | 620000 | 1328020 | ACTIVITY DATES SET | G | Complete Purchasing Right-of-Way milestone finished 269 days early | R | Project estimate is less than $5M and is 20% or more over budget | 2018-10-31 | 2018-07-01 | 2019-03-29 | 2018-08-13 | G | 2018-08-14 | 2018-08-14 | 2018-09-11 | 2018-09-11 | G | 2018-10-31 | 2019-02-26 | 2019-05-29 | 2019-05-28 | G | [10 empty] | 2021-02-02 | 2020-11-02 | 2021-02-26 | 2020-11-30 | G | [5 empty] | 2021-03-01 | 2020-12-01 | 2021-10-25 | 2021-01-29 | G | 2021-08-27 | 2019-08-20 | 2022-06-02 | 2019-08-20 | G | [5 empty] | 2022-06-03 | 2021-01-05 | 2022-09-29 |  | G | 2022-09-30 |  | 2023-02-28 |  | G | Preliminary design and/or investigations are still underway | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.33499
1068 | 113257 | Ridgefield Pkwy Sidewalk at Glen Eagles Dr. | 9999 | Secondary | Facilities for Pedestrians and Bicycles | Locally | Henrico County | ASHLAND | Richmond | Richmond:Henrico County | Local Assistance Division | Douglas L Orcutt | Doug.Orcutt@vdot.virginia.gov | (804) 609-5428 | Douglas L Orcutt | Doug.Orcutt@vdot.virginia.gov | (804) 609-5428 | John Luff | LUF001@henrico.us | (804) 501-7332 | 0 |  | 0 | FY2021 | 389000 | 389000 | ADVERTISED | R | Solicit Bids milestone finished 76 days late | G | Project is on budget | 2018-07-02 | 2018-07-02 | 2018-10-31 | 2018-09-27 | G | 2018-11-01 | 2018-10-15 | 2018-12-17 | 2018-10-16 | G | 2018-12-18 | 2018-10-16 | 2019-03-18 | 2019-03-15 | G | [10 empty] | 2019-03-18 | 2019-09-26 | 2019-10-01 | 2019-09-26 | G | [5 empty] | 2019-10-03 | 2019-10-01 | 2020-10-01 | 2020-12-02 | R | 2019-02-21 | 2020-09-16 | 2020-10-01 | 2020-09-16 | G | [5 empty] | 2020-10-05 | 2020-12-20 | 2020-10-05 | 2020-12-20 | R | 2020-10-06 |  | 2021-04-05 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.34692
1069 | 113297 | RTE 58 - RECONSTRUCT TURN LANES | 0058 | Primary | Safety | Locally | Mecklenburg County | SOUTH HILL | Richmond | NonMPO:NonMPO | Local Assistance Division | James Shepherd | James.Shepherd@vdot.virginia.gov | (804) 609-5305 | James Shepherd | James.Shepherd@vdot.virginia.gov | (804) 609-5305 | Wayne Carter | wayne.carter@mecklenburgva.com | (434) 738-6191 | 0 |  | 0 | FY2022 | 2125215 | 2125416 | ACTIVITY DATES SET | R | Obtained Permits milestone is 174 days past the expected completion date | Y | Project estimate is less than $5M and is up to 20% over budget | 2018-07-02 | 2018-08-08 | 2018-09-25 | 2018-08-15 | G | 2018-09-26 | 2018-10-18 | 2018-11-15 | 2018-10-23 | G | 2018-11-16 | 2018-10-24 | 2019-05-28 | 2019-05-24 | G | [10 empty] | 2020-03-23 | 2020-03-23 | 2020-06-12 | 2020-04-01 | G | [5 empty] | 2020-06-16 | 2020-04-03 | 2021-01-29 |  | R | 2019-02-28 |  | 2020-08-31 |  | R | [5 empty] | 2021-02-16 |  | 2021-06-30 |  | G | 2021-07-01 |  | 2021-09-30 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.15658
1070 | 104881 | JOHN ROLFE PKWY - ADD SIDEWALK | 9999 | Secondary | Facilities for Pedestrians and Bicycles | Locally | Henrico County | ASHLAND | Richmond | Richmond:Henrico County | Infrastructure Investment Division | Brian J Lokker | Brian.Lokker@VDOT.Virginia.gov | (804) 524-6010 | Brian J Lokker | Brian.Lokker@VDOT.Virginia.gov | (804) 524-6010 | Paul Smith | smi91@henrico.us | (804) 501-5092 | 0 |  | 0 | FY2019 | 1004000 | 716000 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 136 days early | G | Project is on budget | 2014-06-30 | 2014-06-11 | 2014-06-30 | 2014-06-11 | G | 2014-03-31 | 2014-07-16 | 2014-03-31 | 2014-07-16 | R | 2015-12-31 | 2015-12-31 | 2017-09-08 | 2017-09-22 | R | [10 empty] | 2017-01-10 | 2017-01-10 | 2017-08-02 | 2017-08-02 | G | [5 empty] | 2017-02-01 | 2017-02-01 | 2017-07-12 | 2017-07-12 | G | [10 empty] | 2018-01-30 | 2018-01-30 | 2018-02-28 | 2018-04-15 | R | 2018-08-30 | 2018-08-14 | 2018-12-28 | 2018-08-14 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.26013
1071 | 106936 | VESPER STREET TRAIL | 3838 | Secondary | Facilities for Pedestrians and Bicycles | Locally | Fairfax County | FAIRFAX | Northern Virginia | Northern Virginia:Fairfax County | Infrastructure Investment Division | Amir Salahshoor | A.Salahshoor@VDOT.Virginia.gov | (703) 259-1957 | Rita Hockman | Rita.Hockman@vdot.virginia.gov | (804) 824-7421 | Brook Khorashadi | fereshteh.khorashadi@fairfaxco.gov | (703) 877-5737 | 0 |  | 0 | FY2019 | 1390000 | 1910000 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 513 days early | R | Project estimate is less than $5M and is 20% or more over budget | [10 empty] | 2013-03-20 | 2013-03-20 | 2015-04-20 | 2015-04-20 | G | [10 empty] | 2015-04-26 | 2015-04-26 | 2015-04-27 | 2015-04-27 | G | 2016-09-14 | 2016-09-14 | 2017-03-27 | 2017-09-20 | R | 2015-08-25 | 2016-05-18 | 2016-03-07 | 2016-11-22 | R | [10 empty] | 2018-09-27 | 2016-06-07 | 2018-10-11 | 2017-04-18 | G | 2018-11-29 | 2017-07-24 | 2018-12-19 | 2017-07-24 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.12845
1072 | 107937 | RTE 286 (FAIRFAX COUNTY PARWAY) - WIDEN FROM 4 TO 6 LANES | 0286 | Primary | Reconstruction w/ Added Capacity | VDOT | Fairfax County | FAIRFAX | Northern Virginia | Northern Virginia:Fairfax County | Infrastructure Investment Division | Andrew G Beacher | Andrew.Beacher@vdot.virginia.gov | (703) 259-2239 | Sitaram Kodali | Sitaram.Kodali@vdot.virginia.gov | (703) 691-6710 | Nick Alexandrow | Nikolai.Alexandrow@fairfaxcounty.gov | (703) 877-5600 | 0 |  | 0 | FY2026 | 205888759 | 205888759 | ACTIVITY DATES SET | G | Engage Public milestone finished on-time | G | Project is on budget | [5 empty] | 2016-02-01 | 2016-08-25 | 2016-02-12 | 2016-08-25 | R | 2016-02-16 | 2016-09-12 | 2017-03-03 | 2020-07-21 | R | [5 empty] | 2019-12-12 | 2019-12-12 | 2020-09-14 | 2020-09-14 | G | 2022-11-30 |  | 2022-12-28 |  | G | 2023-12-18 |  | 2024-09-11 |  | G | 2023-01-18 |  | 2024-01-18 |  | G | 2024-06-07 |  | 2025-02-13 |  | G | [5 empty] | 2025-04-07 |  | 2025-04-08 |  | G | 2025-07-28 |  | 2025-07-28 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.1139
1073 | 108707 | Paving (Route 642) | 0642 | Secondary | Resurfacing | VDOT | Brunswick County | SOUTH HILL | Richmond | NonMPO:NonMPO | Local Assistance Division | Todd E Wilson | Todd.Wilson@vdot.virginia.gov | (434) 774-2313 | Todd E Wilson | Todd.Wilson@vdot.virginia.gov | (434) 774-2313 | Charlette T. Woolridge |  |  | 0 |  | 0 | FY2019 | 50000 | 50000 | WAITING FINANCIAL CLOSURE | G | Engage Public milestone finished 368 days early | G | Project is on budget | [5 empty] | 2017-07-12 | 2017-02-24 | 2017-07-25 | 2017-02-24 | G | 2017-07-26 | 2017-03-01 | 2018-03-22 | 2017-03-01 | G | [5 empty] | 2018-06-19 | 2017-06-16 | 2018-07-31 | 2017-07-28 | G | [5 empty] | 2018-11-14 | 2017-06-15 | 2019-03-14 | 2017-06-15 | G | [15 empty] | 2019-04-09 | 2017-05-09 | 2019-04-09 | 2017-05-31 | G | 2019-05-30 | 2017-06-16 | 2019-06-19 | 2017-06-16 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.093681
1074 | 111048 | #SMART18 - (St) STAUNTON CROSSING STREET EXTENSION |  | Urban | New Construction Roadway | VDOT | Staunton | HARRISONBURG | Staunton | SAW:Staunton | Infrastructure Investment Division | Matthew P Dana | Matt.Dana@VDOT.Virginia.gov | (540) 332-7786 | David Robinson | David.Robinson@vdot.virginia.gov | (540) 332-7758 |  |  |  | 1 | 2018 | 0 | FY2022 | 8764970 | 8764970 | ACTIVITY DATES SET | G | Engage Public milestone finished 29 days early | G | Project is on budget | [5 empty] | 2017-08-03 | 2017-07-24 | 2017-08-16 | 2017-08-03 | G | 2017-08-17 | 2017-08-04 | 2018-09-05 | 2019-03-22 | R | [5 empty] | 2020-02-04 | 2020-02-12 | 2020-03-31 | 2020-03-02 | G | [15 empty] | 2020-09-23 | 2020-10-05 | 2021-06-01 |  | G | [5 empty] | 2021-11-09 |  | 2021-11-09 |  | G | 2021-12-23 |  | 2022-02-23 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.097527
1075 | 111637 | #SMART18 - BROAD ST PEDESTRIAN & TRANSIT STOP IMPROVEMENTS | 0250 | Primary | Safety | VDOT | Henrico County | ASHLAND | Richmond | Richmond:Henrico County | Infrastructure Investment Division | William Wheeler | William.Wheeler@vdot.virginia.gov | (804) 609-5280 | William Wheeler | William.Wheeler@vdot.virginia.gov | (804) 609-5280 |  |  |  | 1 | 2018 | 0 | FY2026 | 1367000 | 1367000 | NO DATES SET YET-PE OPEN | G | Obtained Permits milestone finished 1852 days early | G | Project is on budget | [5 empty] | 2021-06-18 | 2019-12-02 | 2021-07-15 | 2019-12-09 | G | 2021-07-16 | 2019-12-10 | 2021-12-09 |  | G | [5 empty] | 2022-09-02 |  | 2022-09-16 |  | G | 2023-06-15 |  | 2023-06-28 |  | G | 2024-08-13 |  | 2025-05-12 |  | G | 2023-07-17 |  | 2024-07-17 |  | G | 2024-03-22 | 2020-02-13 | 2025-03-10 | 2020-02-13 | G | [5 empty] | 2025-07-08 |  | 2025-07-08 |  | G | 2025-08-21 |  | 2025-10-31 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.071939
1076 | 112856 | #SGR19VP - F19/C19 PM1K Wise Lee Dickenson Primary | 9999 | Primary | Resurfacing | VDOT | Bristol District-wide |  | Bristol | NonMPO:NonMPO | Infrastructure Investment/Asset Management Division | Leslie T Repass | Todd.Repass@VDOT.Virginia.gov | (540) 381-7195 | Kenneth E Turner | Kenneth.Turner@VDOT.Virginia.gov | (804) 225-3940 |  |  |  | 0 |  | 1 | FY2019 | 999375 | 999375 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished on-time | G | Project is on budget | [10 empty] | 2019-02-12 | 2018-07-02 | 2019-02-19 | 2018-07-09 | G | [35 empty] | 2018-07-10 | 2018-07-10 | 2018-07-10 | 2018-07-10 | G | 2018-09-28 | 2018-09-28 | 2018-09-28 | 2018-09-28 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.083365
1077 | 113200 | Church St/Shiloh Dr Sidewalk Construction |  | Secondary | Facilities for Pedestrians and Bicycles | Locally | Isle of Wight County | FRANKLIN | Hampton Roads | Hampton Roads:Isle of Wight County | Local Assistance Division | Charles T Catlett | Tommy.Catlett@vdot.virginia.gov | (757) 346-3078 | Joshua D Negovan | Joshua.Negovan@vdot.virginia.gov | (757) 956-3347 | Jamie Oliver | joliver@isleofwightus.net | (757) 365-1653 | 0 |  | 0 | FY2020 | 670523 | 521105 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 85 days early | G | Project is on budget | 2018-09-04 | 2018-09-04 | 2018-11-30 | 2018-10-02 | G | 2018-12-03 | 2018-10-03 | 2018-12-05 | 2019-02-06 | R | 2018-12-06 | 2019-02-07 | 2019-06-13 | 2019-09-25 | R | 2019-11-05 | 2019-12-05 | 2019-12-19 | 2019-12-05 | G | [30 empty] | 2020-03-16 | 2020-01-24 | 2020-04-10 | 2020-02-26 | G | 2020-06-30 | 2020-03-20 | 2020-06-30 | 2020-04-06 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.24913
1078 | 113268 | John Rolfe Parkway - Sidewalk | 9999 | Secondary | Facilities for Pedestrians and Bicycles | Locally | Henrico County | ASHLAND | Richmond | Richmond:Henrico County | Local Assistance Division | Douglas L Orcutt | Doug.Orcutt@vdot.virginia.gov | (804) 609-5428 | Douglas L Orcutt | Doug.Orcutt@vdot.virginia.gov | (804) 609-5428 | Steve Bandura | ban03@henrico.us | (804) 501-5985 | 0 |  | 0 | FY2022 | 415000 | 415000 | ACTIVITY DATES SET | G | Complete Purchasing Right-of-Way milestone finished 6 days early | G | Project is on budget | 2018-07-02 | 2018-07-02 | 2018-10-31 | 2018-09-27 | G | 2018-11-01 | 2018-10-15 | 2018-12-17 | 2018-10-16 | G | 2018-12-18 | 2018-10-16 | 2019-02-26 | 2019-02-21 | G | [10 empty] | 2019-06-17 | 2019-10-22 | 2020-11-02 | 2019-10-24 | G | 2020-11-04 |  | 2021-09-22 |  | G | 2020-11-03 | 2020-10-28 | 2020-11-03 | 2020-10-28 | G | 2019-02-21 |  | 2021-10-07 |  | G | [5 empty] | 2021-11-01 |  | 2021-11-01 |  | G | 2021-12-13 |  | 2022-05-02 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.34706
1079 | 113473 | Francis Street Sidewalk/Trail | 0000 | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Williamsburg | WILLIAMSBURG | Hampton Roads | Hampton Roads:Williamsburg | Local Assistance Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Chessica Villaflores | Chessica.Villaflores@vdot.virginia.gov | (757) 956-3094 | Aaron Small | asmall@williamsburgva.gov | (757) 220-6140 | 0 |  | 0 | FY2023 | 298250 | 298250 | ACTIVITY DATES SET | R | Determine Requirements milestone finished 173 days late | G | Project is on budget | 2019-09-03 | 2018-09-27 | 2019-11-27 | 2018-12-26 | G | 2019-12-02 | 2019-03-04 | 2019-12-04 | 2019-03-11 | G | 2019-12-05 | 2019-03-12 | 2020-06-11 | 2020-12-01 | R | [35 empty] | 2021-10-08 |  | 2021-11-05 |  | G | 2022-02-02 |  | 2022-07-22 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.40242
1080 | 113622 | #SGR19LP - ALEXANDRIA PRIMARY EXT PAVING FY19 - DUKE ST WB | 0236 | Urban | Resurfacing | Locally | Alexandria | FAIRFAX | Northern Virginia | Northern Virginia:Alexandria | Local Assistance Division | Amir Salahshoor | A.Salahshoor@VDOT.Virginia.gov | (703) 259-1957 | Rita Hockman | Rita.Hockman@vdot.virginia.gov | (804) 824-7421 | Mary Winston | maryalice.winston@alexandriava.gov | (703) 746-4067 | 0 |  | 1 | FY2019 | 500000 | 500000 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 147 days early | G | Project is on budget | 2018-07-02 | 2018-07-02 | 2018-09-25 | 2018-09-13 | G | [5 empty] | 2018-09-26 | 2018-09-14 | 2018-11-28 | 2018-09-17 | G | [25 empty] | 2018-09-19 | 2018-09-18 | 2018-11-16 | 2018-09-18 | G | [5 empty] | 2018-11-19 | 2018-09-21 | 2018-12-18 | 2018-09-21 | G | 2018-12-19 | 2018-09-21 | 2019-02-15 | 2018-09-21 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.19827
1081 | 113697 | #SGR19LB??- Indian River Road (RT 407) over Indian River | 0407 | Urban | Bridge Rehab w/o Added Capacity | Locally | Chesapeake | NORFOLK | Hampton Roads | Hampton Roads:Chesapeake | Infrastructure Investment Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Johndel A Alcaide | John.Alcaide@vdot.virginia.gov | (757) 956-3098 | Sam Sawan | sawan@cityofchesapeake.net | (757) 382-8263 | 0 |  | 1 | FY2023 | 5128000 | 5128000 | NO DATES SET YET-PE OPEN | G | Start Development milestone finished 185 days early | G | Project is on budget | 2020-09-01 | 2020-02-04 | 2021-01-13 | 2020-07-22 | G | 2021-01-14 | 2020-07-28 | 2021-02-05 | 2020-08-04 | G | 2021-03-09 |  | 2021-06-29 |  | G | [25 empty] | 2022-06-24 |  | 2022-11-23 |  | G | [5 empty] | 2023-01-27 |  | 2023-02-24 |  | G | 2023-05-15 |  | 2023-05-15 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.30889
1082 | 114401 | Signal Performance Metric - ATSC | 0029 | Primary | Traffic Management/Engineering | VDOT | Albemarle County | CHARLOTTESVILLE | Culpeper | Charlottesville:Albemarle County | Infrastructure Investment Division | Ken Connors |  |  | Rowes Hanna | Rowes.Hanna@vdot.virginia.gov | (540) 727-7054 |  |  |  | 0 |  | 0 | FY2020 | 600000 | 600000 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 62 days early | G | Project is on budget | [5 empty] | 2018-10-29 | 2018-11-26 | 2018-10-29 | 2019-02-07 | R | 2018-10-30 | 2019-02-08 | 2019-02-13 | 2019-03-29 | R | [5 empty] | 2019-09-25 | 2019-09-24 | 2020-01-24 | 2019-12-17 | G | [25 empty] | 2020-02-25 | 2020-02-14 | 2020-04-06 | 2020-02-17 | G | 2020-04-07 | 2020-02-18 | 2020-04-20 | 2020-02-18 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | WORK/TASK ORDER | 1 | 1 | 0.33365
1083 | 115200 | Hull Street Improvement Project Phase III | 0360 | Primary | Reconstruction w/ Added Capacity | Locally | Richmond | ASHLAND | Richmond | Richmond:Richmond | Infrastructure Investment Division | Melinda G Baicy | Melinda.Baicy@vdot.virginia.gov | (804) 609-5390 | Melinda G Baicy | Melinda.Baicy@vdot.virginia.gov | (804) 609-5390 | TBD |  |  | 0 |  | 0 | FY2026 | 11664209 | 11664209 | NO DATES SET YET | G | Agreement with Locality milestone is 948 days ahead of the expected completion date | G | Project is on budget | 2023-07-05 |  | 2023-09-27 |  | G | 2023-09-28 |  | 2023-10-02 |  | G | 2023-10-03 |  | 2024-04-12 |  | G | [10 empty] | 2025-04-16 |  | 2025-05-06 |  | G | [5 empty] | 2025-05-08 |  | 2026-02-20 |  | G | 2024-05-20 |  | 2025-01-27 |  | G | [5 empty] | 2026-03-10 |  | 2026-04-06 |  | G | 2026-06-24 |  | 2026-06-24 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.13947
1084 | 115369 | Citywide Traffic Signal System Upgrade |  | Urban | Traffic Management/Engineering | Locally | Chesapeake | NORFOLK | Hampton Roads | Hampton Roads:Chesapeake | Infrastructure Investment Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Johndel A Alcaide | John.Alcaide@vdot.virginia.gov | (757) 956-3098 | Troy Einsenberger | teisenberger@cityofchesapeake.net | (757) 382-6383 | 0 |  | 0 | FY2027 | 875000 | 875000 | NO DATES SET YET | G | Agreement with Locality milestone is 1408 days ahead of the expected completion date | Y | Estimate not current | 2024-10-01 |  | 2024-12-30 |  | G | 2024-12-31 |  | 2025-01-03 |  | G | 2025-01-06 |  | 2025-07-11 |  | G | [25 empty] | 2025-08-18 |  | 2026-04-24 |  | G | [5 empty] | 2026-07-30 |  | 2026-08-26 |  | G | 2026-11-17 |  | 2026-11-17 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.30137
1085 | 115714 | Pearisburg - Mt. Lake Avenue/Curve Rd Improvements | 0000 | Urban | Resurfacing | Locally | Pearisburg | CHRISTIANSBURG | Salem | NonMPO:NonMPO | Local Assistance Division | Adam J Czesnowski | Adam.Czesnowski@vdot.virginia.gov | (540) 541-1216 | Adam J Czesnowski | Adam.Czesnowski@vdot.virginia.gov | (540) 541-1216 | Rodney Wilson | rwilson@pearisburg.org | (540) 921-0340 | 0 |  | 0 | FY2021 | 240000 | 240000 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 406 days early | G | Project is on budget | 2019-10-01 | 2019-07-01 | 2019-12-30 | 2019-10-22 | G | [5 empty] | 2019-10-01 | 2019-07-01 | 2019-10-14 | 2019-10-08 | G | [25 empty] | 2019-10-09 | 2019-11-04 | 2020-04-06 | 2019-11-04 | G | [5 empty] | 2020-04-07 | 2019-11-05 | 2020-06-30 | 2019-11-05 | G | 2020-07-23 | 2019-11-06 | 2020-12-16 | 2019-11-06 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.066398
1086 | 116329 | #I81CIP NWRO MGMT FEE FOR NEW CMS & CAMERAS FY20-25 | 0081 | Interstate | Safety | VDOT | Staunton District-wide |  | Staunton | NonMPO:NonMPO | Infrastructure Investment Division | Ricky A Via | Ricky.Via@vdot.virginia.gov | (804) 371-2396 | Kunal Kothawade | Kunal.Kothawade@vdot.virginia.gov | (540) 332-9259 |  |  |  | 0 |  | 0 | FY2020 | 94128 | 94128 | CONSTRUCTION STARTED | G | Start Delivery milestone finished on-time | G | Project is on budget | [10 empty] | 2019-11-01 | 2019-08-29 | 2020-03-17 | 2020-01-10 | G | [35 empty] | 2020-01-14 | 2020-01-14 | 2020-01-22 | 2020-01-22 | G | 2020-01-23 | 2020-01-23 | 2020-01-29 | 2020-01-29 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | WORK/TASK ORDER | 1 | 0 | 0.065559
1087 | 117027 | RURAL ADDITION - HOLLY WAY (PHASE III) PAVE UNPAVED | 9999 | Secondary | Resurfacing | VDOT | Westmoreland County | NORTHERN NECK | Fredericksburg | NonMPO:NonMPO | Local Assistance Division | David L Beale | David.Beale@vdot.virginia.gov | (804) 333-7941 | William C White | Carter.White@VDOT.Virginia.gov | (804) 333-7942 |  |  |  | 0 |  | 0 | FY2029 | 427000 | 427000 | NO DATES SET YET | G | Start Development milestone is 1704 days ahead of the expected completion date | G | Project is on budget | [5 empty] | 2025-10-01 |  | 2025-10-22 |  | G | 2025-10-23 |  | 2026-08-26 |  | G | [5 empty] | 2027-04-01 |  | 2027-04-28 |  | G | [5 empty] | 2027-12-21 |  | 2028-04-24 |  | G | [5 empty] | 2027-09-09 |  | 2028-02-14 |  | G | [5 empty] | 2028-05-09 |  | 2028-05-09 |  | G | 2028-07-28 |  | 2028-07-28 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | SAAP CONTRACT | 0 | 0 | 0.090021
1088 | 118159 | Cambria Trail | 0000 | Urban | Facilities for Pedestrians and Bicycles | Locally | Christiansburg | CHRISTIANSBURG | Salem | New River Valley:Christiansburg | Local Assistance Division | Adam J Czesnowski | Adam.Czesnowski@vdot.virginia.gov | (540) 541-1216 | Adam J Czesnowski | Adam.Czesnowski@vdot.virginia.gov | (540) 541-1216 | Wayne Nelson | wnelson@christiansburg.org | (540) 382-9120 | 0 |  | 0 | FY2028 | 2443000 | 2443000 | NO DATES SET YET | G | Agreement with Locality milestone is 1422 days ahead of the expected completion date | G | Project is on budget | 2024-08-30 |  | 2025-01-13 |  | G | 2025-01-14 |  | 2025-02-05 |  | G | 2025-08-12 |  | 2025-12-08 |  | G | [10 empty] | 2027-04-01 |  | 2027-05-05 |  | G | [5 empty] | 2027-05-06 |  | 2027-10-04 |  | G | 2027-08-31 |  | 2028-02-04 |  | G | [5 empty] | 2028-01-12 |  | 2028-02-10 |  | G | 2028-05-01 |  | 2028-05-01 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.10078
1089 | 118230 | ITTF SIGNAL COMMUNICATIONS - SALEM DISTRICT | 0460 | Primary | Traffic Management/Engineering | VDOT | Bedford County | BEDFORD | Salem | Roanoke:Bedford County | Infrastructure Investment Division | Bernard S Grinnell | Sean.Grinnell@VDOT.Virginia.gov | (540) 375-0148 | Michael Dalmolin | Michael.Dalmolin@vdot.virginia.gov | (540) 375-0157 |  |  |  | 0 |  | 0 | FY2021 | 246248 | 246248 | ACTIVITY DATES SET | G | Determine Requirements milestone finished 29 days early | G | Project is on budget | [10 empty] | 2020-11-02 | 2020-12-08 | 2021-03-17 | 2021-02-16 | G | [35 empty] | 2021-02-18 |  | 2021-05-13 |  | G | 2021-05-14 |  | 2021-05-20 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | WORK/TASK ORDER | 0 | 1 | 0.3415
1090 | 113689 | LYLBURN DOWNING MIDDLE SCHOOL SRTS |  | Enhancement | Facilities for Pedestrians and Bicycles | VDOT | Lexington | LEXINGTON | Staunton | NonMPO:NonMPO | Local Assistance Division | Susan E Hammond | Susan.Hammond@VDOT.Virginia.gov | (540) 462-6990 | Ronald L Tabor | Ronald.Tabor@vdot.virginia.gov | (540) 332-7887 |  |  |  | 0 |  | 0 | FY2021 | 94360 | 94360 | CONSTRUCTION COMPLETED | R | Relocate Utilities milestone is 2 days past the expected completion date | G | Project is on budget | [5 empty] | 2019-02-01 | 2019-01-02 | 2019-02-14 | 2019-01-28 | G | 2019-02-15 | 2019-01-29 | 2019-10-04 | 2019-09-17 | G | [5 empty] | 2020-05-27 | 2019-09-09 | 2020-07-08 | 2019-09-09 | G | [5 empty] | 2020-10-22 |  | 2021-02-19 |  | R | [15 empty] | 2021-03-09 | 2019-12-10 | 2021-03-09 | 2019-12-10 | G | 2021-05-27 | 2020-02-27 | 2021-05-27 | 2020-02-27 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 1 | 0.25949
1091 | 113719 | #SGR19LP - Virginia Beach Blvd Westbound Mill and Overlay | 0058 | Urban | Resurfacing | Locally | Virginia Beach | NORFOLK | Hampton Roads | Hampton Roads:Virginia Beach | Infrastructure Investment Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Marci Thompson | Marci.Thompson@vdot.virginia.gov | (757) 956-3093 | Katie Shannon, P.E. | kshannon@vbgov.com | (757) 385-1514 | 0 |  | 1 | FY2019 | 584000 | 584000 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 245 days early | G | Project is on budget | 2018-09-04 | 2018-09-04 | 2018-11-30 | 2018-10-23 | G | 2018-12-03 | 2018-10-24 | 2018-12-05 | 2018-10-25 | G | 2018-12-06 | 2018-04-23 | 2019-06-13 | 2018-10-25 | G | [35 empty] | 2019-04-10 | 2018-10-25 | 2019-05-07 | 2018-10-25 | G | 2019-06-28 | 2018-10-26 | 2019-06-28 | 2018-10-26 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.090714
1092 | 114722 | Pacific Avenue Pedestrian Improvements (PSAP) | 0060 | Urban | Facilities for Pedestrians and Bicycles | Locally | Virginia Beach | NORFOLK | Hampton Roads | Hampton Roads:Virginia Beach | Infrastructure Investment Division | Susan Wilson | Susan.Wilson@vdot.virginia.gov | (757) 956-3099 | Marci Thompson | Marci.Thompson@vdot.virginia.gov | (757) 956-3093 | Katie E. Shannon, PE | kshannon@vbgov.com | (757) 385-1514 | 0 |  | 0 | FY2021 | 1800000 | 1800000 | ACTIVITY DATES SET | R | Solicit Bids milestone is 88 days past the expected completion date | G | Project is on budget | 2019-05-14 | 2019-05-06 | 2019-08-07 | 2019-07-09 | G | 2019-08-08 | 2019-07-10 | 2019-08-12 | 2019-07-23 | G | 2019-08-13 | 2019-07-24 | 2020-08-06 | 2020-08-05 | G | [35 empty] | 2020-10-28 | 2020-08-26 | 2020-11-25 |  | R | 2021-02-19 |  | 2021-02-19 |  | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.14657
1093 | 115310 | Deyerle Road Drainage Improvements | 0000 | Urban | Mitigation of Water Pollution Due to Highway Runof | Locally | Roanoke | SALEM | Salem | Roanoke:Roanoke City | Local Assistance Division | Cheryl B Becker | Cheryl.Becker@vdot.virginia.gov | (540) 492-2531 | Cheryl B Becker | Cheryl.Becker@vdot.virginia.gov | (540) 492-2531 | Joseph Arthur | Joseph.Arthur@roanokeva.gov | (540) 853-5906 | 0 |  | 0 | FY2022 | 510000 | 510000 | ACTIVITY DATES SET | G | Obtained Permits milestone finished 312 days early | G | Project is on budget | 2019-05-31 | 2019-05-31 | 2019-08-23 | 2020-06-18 | R | 2019-08-26 | 2020-06-18 | 2019-08-28 | 2020-06-18 | R | 2019-08-29 | 2020-06-18 | 2020-03-11 | 2020-06-18 | R | [25 empty] | 2021-02-05 | 2020-07-20 | 2021-05-28 | 2020-07-20 | G | [5 empty] | 2021-06-15 |  | 2021-07-13 |  | G | 2021-09-30 |  | 2021-09-30 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.20413
1094 | 115459 | #SMART20 - Claudville Highway Intersection Improvement | 0103 | Primary | Safety | VDOT | Patrick County | MARTINSVILLE | Salem | NonMPO:NonMPO | Infrastructure Investment Division | Alex H Price | Alex.Price@VDOT.Virginia.gov | (540) 378-5053 | Jesse N Weitzenfeld | Jesse.Weitzenfeld@VDOT.Virginia.gov | (540) 378-5050 |  |  |  | 1 | 2020 | 0 | FY2028 | 2104000 | 2104000 | NO DATES SET YET | G | Start Development milestone is 904 days ahead of the expected completion date | G | Project is on budget | [5 empty] | 2023-08-01 |  | 2023-08-14 |  | G | 2023-08-15 |  | 2024-07-12 |  | G | [5 empty] | 2025-05-19 |  | 2025-06-02 |  | G | 2026-09-04 |  | 2026-09-18 |  | G | 2027-02-19 |  | 2027-08-23 |  | G | 2026-10-06 |  | 2027-04-16 |  | G | 2026-02-26 |  | 2026-08-28 |  | G | [5 empty] | 2027-09-14 |  | 2027-09-14 |  | G | 2027-12-08 |  | 2027-12-08 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.067983
1095 | 116164 | #I81CIP NB MM 73.0 DECEL AND LOOP (ID #11) | 0081 | Interstate | Reconstruction w/o Added Capacity | VDOT | Wytheville | WYTHEVILLE | Bristol | NonMPO:NonMPO | Infrastructure Investment Division | Donald A Necessary | Donald.Necessary@VDOT.Virginia.gov | (276) 696-3285 | Marvin E Holley | Gene.Holley@VDOT.Virginia.gov | (276) 696-3255 |  |  |  | 0 |  | 0 | FY2024 | 22100000 | 22100000 | ACTIVITY DATES SET | G | Determine Requirements milestone finished 308 days early | G | Project is on budget | [5 empty] | 2020-07-01 | 2020-01-03 | 2020-07-15 | 2020-01-09 | G | 2020-07-16 | 2020-01-10 | 2021-08-24 | 2020-10-20 | G | [5 empty] | 2021-09-13 |  | 2021-09-24 |  | G | 2022-12-19 |  | 2023-01-03 |  | G | 2023-05-31 |  | 2023-12-06 |  | G | 2023-01-23 |  | 2023-07-26 |  | G | 2022-06-10 |  | 2023-09-20 |  | G | [5 empty] | 2023-12-12 |  | 2023-12-12 |  | G | 2024-04-04 |  | 2024-04-04 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.10641
1096 | 116649 | CENTERLINE RUMBLE STRIPS-BRISTOL DISTRICT WIDE | 9999 | Miscellaneous | Safety | VDOT | Bristol District-wide |  | Bristol | NonMPO:NonMPO | Infrastructure Investment Division | Jeremy J Mullins | Jeremy.Mullins@vdot.virginia.gov | (276) 696-3259 | Chase R Buchanan | Chase.Buchanan@VDOT.Virginia.gov | (276) 696-3251 |  |  |  | 0 |  | 0 | FY2023 | 423372 | 423372 | NO DATES SET YET-PE OPEN | R | Determine Requirements milestone is 12 days past the expected completion date | G | Project is on budget | [5 empty] | 2020-06-01 | 2020-06-01 | 2020-06-12 | 2020-06-01 | G | 2020-06-15 |  | 2021-02-09 |  | R | [5 empty] | 2021-10-12 |  | 2021-11-24 |  | G | [5 empty] | 2022-03-17 |  | 2022-07-08 |  | G | [5 empty] | 2022-03-02 |  | 2022-06-01 |  | G | [5 empty] | 2022-07-12 |  | 2022-07-12 |  | G | 2022-09-30 |  | 2022-09-30 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.068042
1097 | 118004 | RT 17 & SHORT ST (RT 1034) SIGNAL REMOVAL / MEDIAN CONSTR | 0017 | Primary | Safety | VDOT | Stafford County | FREDERICKSBURG | Fredericksburg | Fredericksburg:Stafford County | Infrastructure Investment Division | Michelle A Shropshire | Michelle.Shropshire@VDOT.Virginia.gov | (540) 899-4278 | Benjamin Ernst | Benjamin.Ernst@vdot.virginia.gov | (571) 585-0902 |  |  |  | 0 |  | 0 | FY2021 | 250000 | 199256 | AWARDED | G | Start Delivery milestone finished 47 days early | G | Project is on budget | [10 empty] | 2020-11-02 | 2020-09-10 | 2021-03-17 | 2020-10-01 | G | [35 empty] | 2021-02-09 | 2020-12-27 | 2021-02-15 | 2020-12-27 | G | 2021-02-16 | 2021-01-07 | 2021-02-23 | 2021-01-07 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | WORK/TASK ORDER | 1 | 0 | 0.060833
1098 | 118185 | #SGR21VP - Martinsville FKEY 648 S Memorial Blvd | 0000 | Urban | Resurfacing | VDOT | Martinsville | MARTINSVILLE | Salem | NonMPO:NonMPO | Infrastructure Investment/Asset Management Division | Ibrahim M Abuawad | Ibrahim.Abuawad@vdot.virginia.gov | (217) 418-8827 | Ibrahim M Abuawad | Ibrahim.Abuawad@vdot.virginia.gov | (217) 418-8827 | Randy Gregory | dgregory@ci.martinsville.va.us | (276) 403-5159 | 0 |  | 0 | FY2021 | 295000 | 295000 | NO DATES SET YET | R | Determine Requirements milestone is 9 days past the expected completion date | G | Project is on budget | [10 empty] | 2021-02-01 |  | 2021-02-12 |  | R | [35 empty] | 2021-03-09 |  | 2021-03-09 |  | Y | 2021-05-27 |  | 2021-05-27 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.061541
1099 | 118336 | #SGR21VP FY21 Plant Mix Districtwide Primaries |  | Primary | Resurfacing | VDOT | Salem District-wide |  | Salem | New River Valley:Salem District-wide | Infrastructure Investment/Asset Management Division | Robert P Williams | Robbie.Williams@VDOT.Virginia.gov | (276) 229-9954 | Ibrahim M Abuawad | Ibrahim.Abuawad@vdot.virginia.gov | (217) 418-8827 |  |  |  | 0 |  | 0 | FY2021 | 5545115 | 5545115 | NO DATES SET YET | R | Determine Requirements milestone is 6 days past the expected completion date | G | Project is on budget | [10 empty] | 2021-02-09 |  | 2021-02-15 |  | R | [35 empty] | 2021-03-09 | 2021-02-09 | 2021-03-09 | 2021-02-09 | G | 2021-05-27 |  | 2021-05-27 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.11214
1100 | 118581 | #I-64/664 CIP-I-95 SB Lane Re-alloc/ Arthur Ashe Ramp Wid | 0095 | Interstate | Safety | VDOT | Richmond | ASHLAND | Richmond | Richmond:Richmond | Infrastructure Investment Division | Jason C Williams | Jason.Williams@VDOT.Virginia.gov | (804) 609-5337 | Jason C Williams | Jason.Williams@VDOT.Virginia.gov | (804) 609-5337 |  |  |  | 0 |  | 0 | FY2025 | 5223000 | 5223000 | NO DATES SET YET | G | Start Development milestone is 89 days ahead of the expected completion date | G | Project is on budget | [5 empty] | 2021-05-03 |  | 2021-05-21 |  | G | 2021-05-24 |  | 2022-03-29 |  | G | [5 empty] | 2022-10-25 |  | 2022-11-22 |  | G | 2023-07-18 |  | 2023-08-21 |  | G | 2024-01-26 |  | 2024-05-24 |  | G | 2023-09-06 |  | 2024-02-09 |  | G | 2023-10-11 |  | 2024-03-18 |  | G | [5 empty] | 2024-06-11 |  | 2024-06-11 |  | G | 2024-08-29 |  | 2024-08-29 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.073101
1101 | 107088 | RTE 636 - NASH ROAD EXTENSION | 0636 | Secondary | New Construction Roadway | Locally | Chesterfield County | CHESTERFIELD | Richmond | Richmond:Chesterfield County | Local Assistance Division | Michael S Gray | Mike.Gray@vdot.virginia.gov | (804) 609-5347 | Michael S Gray | Mike.Gray@vdot.virginia.gov | (804) 609-5347 | Chessa Faulkner | faulknerc@chesterfield.gov | (804) 748-1037 | 0 |  | 0 | FY2022 | 30052000 | 30052000 | ACTIVITY DATES SET | R | Engage Public milestone is 394 days past the expected completion date | G | Project is on budget | 2015-07-01 | 2015-09-29 | 2015-09-24 | 2015-09-29 | R | 2015-09-25 | 2016-01-28 | 2015-09-29 | 2016-01-28 | R | 2015-09-30 | 2016-01-13 | 2016-09-29 | 2019-01-28 | R | [5 empty] | 2019-10-28 |  | 2020-01-24 |  | R | 2020-01-27 |  | 2020-03-25 |  | R | 2020-12-22 |  | 2021-06-22 |  | G | 2020-03-30 |  | 2020-12-21 |  | R | [10 empty] | 2021-09-15 |  | 2021-09-15 |  | G | 2022-01-31 |  | 2022-01-31 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.36328
1102 | 108646 | Intersection Improvements (Conduit Rd and Ellerslie Ave) |  | Miscellaneous | Safety | Locally | Colonial Heights | CHESTERFIELD | Richmond | Tri-Cities:Colonial Heights | Local Assistance Division | Brian J Lokker | Brian.Lokker@VDOT.Virginia.gov | (804) 524-6010 | Brian J Lokker | Brian.Lokker@VDOT.Virginia.gov | (804) 524-6010 | Keith Chisolm | chisolmk@colonialheightsva.gov | (804) 520-9215 | 0 |  | 0 | FY2020 | 655000 | 737547 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 349 days early | Y | Project estimate is less than $5M and is up to 20% over budget | 2017-04-03 | 2016-07-05 | 2017-06-26 | 2016-07-05 | G | 2017-06-27 | 2017-02-16 | 2017-06-29 | 2017-02-16 | G | 2017-06-30 | 2017-07-07 | 2018-01-09 | 2017-07-07 | G | [10 empty] | 2019-01-11 | 2018-09-14 | 2019-02-04 | 2018-09-17 | G | [5 empty] | 2019-02-06 | 2018-06-05 | 2019-11-13 | 2018-07-09 | G | [10 empty] | 2019-12-03 | 2018-12-07 | 2019-12-31 | 2018-12-28 | G | 2020-01-02 | 2019-01-25 | 2020-02-13 | 2019-03-01 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.11428
1103 | 108778 | REPLACE SWINGING FOOT BRIDGE STR. #9009 OVER CLINCH RIVER | 0662 | Secondary | Bridge Replacement w/o Added Capacity | VDOT | Scott County | WISE | Bristol | NonMPO:NonMPO | Local Assistance Division | Allan D Sumpter | Allan.Sumpter@VDOT.virginia.gov | (276) 525-6461 | Jeffrey B Powell | Jeffrey.Powell@VDOT.Virginia.gov | (276) 696-3389 |  |  |  | 0 |  | 0 | FY2024 | 125700 | 125700 | NO DATES SET YET | G | Start Development milestone is 144 days ahead of the expected completion date | Y | Estimate not current | [5 empty] | 2021-07-01 |  | 2021-07-15 |  | G | 2021-07-16 |  | 2022-03-14 |  | G | [5 empty] | 2022-12-15 |  | 2023-01-31 |  | G | [5 empty] | 2023-05-16 |  | 2023-09-07 |  | G | [5 empty] | 2023-05-01 |  | 2023-08-01 |  | G | [5 empty] | 2023-10-10 |  | 2023-10-10 |  | G | 2023-12-05 |  | 2023-12-26 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.11112
1104 | 109075 | Amtrak Multimodal Station - Site Grading and Drainage | 0000 | Public Transportation | Transit | Locally | Newport News | WILLIAMSBURG | Hampton Roads | Hampton Roads:Newport News | Infrastructure Investment Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Chessica Villaflores | Chessica.Villaflores@vdot.virginia.gov | (757) 956-3094 | Vincent Urbano, Assistant Chief of Design | urbanovp@nnva.gov | (757) 926-8694 | 0 |  | 0 | FY2021 | 8142550 | 8142550 | AWARDED | G | Start Delivery milestone finished 177 days early | G | Project is on budget | 2016-10-04 | 2016-10-04 | 2017-04-21 | 2017-04-21 | G | [5 empty] | 2017-04-24 | 2017-04-24 | 2018-12-13 | 2019-07-23 | R | [35 empty] | 2020-03-18 | 2020-01-17 | 2020-06-09 | 2020-02-25 | G | 2020-06-10 | 2020-03-17 | 2020-12-02 | 2020-06-08 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.23691
1105 | 109471 | #HB2.FY17 - INT. IMPROVEMENTS ROUTES 17B/14/3 | 0003 | Primary | Reconstruction w/o Added Capacity | VDOT | Gloucester County | SALUDA | Fredericksburg | Hampton Roads:Gloucester County | Infrastructure Investment Division | Jeremy B Cobb | Jeremy.Cobb@vdot.virginia.gov | (804) 586-2255 | Jeremy B Cobb | Jeremy.Cobb@vdot.virginia.gov | (804) 586-2255 |  |  |  | 1 | 2017 | 0 | FY2021 | 1500000 | 1500000 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 146 days early | G | Project is on budget | [5 empty] | 2017-01-03 | 2017-01-03 | 2017-01-18 | 2017-01-12 | G | 2017-01-19 | 2017-01-17 | 2017-12-13 | 2017-12-12 | G | [5 empty] | 2018-07-06 | 2018-06-25 | 2018-07-19 | 2018-07-13 | G | 2019-04-26 | 2019-02-07 | 2019-05-09 | 2019-02-21 | G | 2019-10-02 | 2019-12-13 | 2020-04-13 | 2019-12-13 | G | 2019-05-28 | 2019-03-05 | 2020-05-27 | 2019-09-18 | G | [10 empty] | 2020-08-11 | 2020-03-24 | 2020-08-11 | 2020-03-24 | G | 2020-10-01 | 2020-05-29 | 2020-10-22 | 2020-05-29 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.081143
1106 | 110914 | #SMART18 - I-95 EXIT 126, RTE 1 SB ONTO SOUTHPOINT PKWY | 0001 | Primary | Reconstruction w/ Added Capacity | VDOT | Spotsylvania County | FREDERICKSBURG | Fredericksburg | Fredericksburg:Spotsylvania County | Infrastructure Investment Division | Curtis B Holloway | Curtis.Holloway@vdot.virginia.gov | (540) 374-3367 | Curtis B Holloway | Curtis.Holloway@vdot.virginia.gov | (540) 374-3367 |  |  |  | 1 | 2018 | 0 | FY2022 | 14495000 | 14495000 | ACTIVITY DATES SET | Y | Complete Purchasing Right-of-Way milestone is 60 days ahead of the expected completion date and there is a risk of missing this milestone date | G | Project is on budget | [5 empty] | 2017-10-04 | 2017-08-25 | 2017-10-18 | 2017-08-31 | G | 2017-10-19 | 2017-09-19 | 2018-08-08 | 2018-08-08 | G | [5 empty] | 2019-04-09 | 2019-03-19 | 2019-06-04 | 2019-05-31 | G | 2020-06-03 | 2020-05-12 | 2020-06-16 | 2020-05-12 | G | 2021-04-23 | 2020-10-30 | 2022-01-05 |  | G | 2020-07-02 | 2020-06-23 | 2021-04-22 |  | Y | 2019-12-30 | 2019-12-30 | 2020-12-29 | 2020-12-22 | G | [5 empty] | 2022-01-11 |  | 2022-01-11 |  | G | 2022-04-11 |  | 2022-06-06 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.09071
1107 | 111042 | #SGR18LB - Lake Cahoon Rd over S.C.L(CSX) & N&W(abandoned)RR | 0639 | Urban | Bridge Rehab w/o Added Capacity | Locally | Suffolk | NORFOLK | Hampton Roads | Hampton Roads:Suffolk | Infrastructure Investment Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Johndel A Alcaide | John.Alcaide@vdot.virginia.gov | (757) 956-3098 | L. Hansen | Lhansen@suffolkva.us | (757) 514-7687 | 0 |  | 1 | FY2021 | 3440000 | 2972669 | ADVERTISED | G | Solicit Bids milestone finished 83 days early | G | Project is on budget | 2020-04-03 | 2017-07-13 | 2020-06-26 | 2017-10-05 | G | 2020-06-29 | 2020-03-24 | 2020-07-13 | 2020-05-27 | G | 2020-07-14 | 2020-05-28 | 2021-06-28 | 2020-10-05 | G | [35 empty] | 2020-12-03 | 2020-10-09 | 2020-12-31 | 2020-10-09 | G | 2021-01-04 |  | 2021-03-31 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.25977
1108 | 111634 | #SMART18 - Rte 1 & Courthouse Rd. (Rte 627) Int. Realignment | 0001 | Primary | Safety | VDOT | Dinwiddie County | PETERSBURG | Richmond | NonMPO:NonMPO | Infrastructure Investment Division | Clayton M Thomas | Clay.Thomas@VDOT.Virginia.gov | (804) 609-5429 | Clayton M Thomas | Clay.Thomas@VDOT.Virginia.gov | (804) 609-5429 |  |  |  | 1 | 2018 | 0 | FY2023 | 921876 | 921876 | ACTIVITY DATES SET | G | Start Purchasing Right-of-Way milestone finished on-time | G | Project is on budget | [5 empty] | 2018-07-02 | 2018-06-21 | 2018-07-16 | 2018-06-25 | G | 2018-07-17 | 2018-06-26 | 2019-02-26 | 2019-02-26 | G | [5 empty] | 2019-10-29 | 2019-10-28 | 2020-01-13 | 2020-01-13 | G | 2020-09-04 | 2020-10-30 | 2020-11-02 | 2020-11-02 | G | 2021-07-13 |  | 2022-04-19 |  | G | 2020-12-07 | 2020-12-16 | 2021-06-14 |  | G | [10 empty] | 2022-06-14 |  | 2022-06-14 |  | G | 2022-07-29 |  | 2022-10-07 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.054589
1109 | 112881 | RTE. 631 - EMERGENCY CONTRACT REPLACE STR. 6054 | 0631 | Secondary | Bridge Replacement w/o Added Capacity | VDOT | Greene County | CHARLOTTESVILLE | Culpeper | NonMPO:NonMPO | Asset Management Division | Braden C Chapman | Braden.Chapman@VDOT.Virginia.gov | (540) 829-7421 | Howard M Tomlinson | Howard.Tomlinson@VDOT.virginia.gov | (540) 829-7436 |  |  |  | 0 |  | 0 | FY2019 | 2940000 | 2940000 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished on-time | G | Project is on budget | [10 empty] | 2018-07-27 | 2017-03-02 | 2018-08-09 | 2017-03-23 | G | [35 empty] | 2018-06-12 | 2018-06-12 | 2018-06-28 | 2018-06-28 | G | 2018-07-13 | 2018-07-13 | 2018-07-13 | 2018-07-13 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.077574
1110 | 81517 | RTE 1 - IMPROVEMENTS TO MAIN STREET | 0001 | Urban | Reconstruction w/o Added Capacity | Locally | Dumfries | MANASSAS | Northern Virginia | Northern Virginia:Dumfries | Infrastructure Investment Division | Nassre Y Obeed | Nassre.Obeed@VDOT.Virginia.gov | (703) 259-1723 | Christer P Carshult | Christer.Carshult@vdot.virginia.gov | (703) 259-1765 | Greg Tkac | gtkac@dumfriesva.gov | (703) 221-3400 | 0 |  | 0 | FY2020 | 2932560 | 1686186 | ACTIVITY DATES SET | R | Solicit Bids milestone is 618 days past the expected completion date | G | Project is on budget | 2007-11-14 | 2007-11-14 | 2007-11-14 | 2007-11-14 | G | 2007-06-19 | 2007-07-05 | 2007-06-19 | 2007-07-05 | R | 2013-03-30 | 2013-01-25 | 2013-03-30 | 2013-01-25 | G | [10 empty] | 2014-08-13 | 2014-08-13 | 2014-08-13 | 2014-08-13 | G | [20 empty] | 2019-03-15 |  | 2019-06-14 |  | R | 2019-09-16 |  | 2019-12-13 |  | R | Delay due to unforeseen issues with utilities, railroad coordination, or right-of-way acquisition | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.20949
1111 | 108145 | RTE 676 AZURE LANE-GRADE, DRAIN, SURFACE TREAT - PHASE II | 0676 | Secondary | Reconstruction w/o Added Capacity | VDOT | Washington County | ABINGDON | Bristol | NonMPO:NonMPO | Infrastructure Investment Division | Conrad Hill | Conrad.Hill@vdot.virginia.gov | (804) 773-0170 | Brandi Halloway | Brandi.Halloway@vdot.virginia.gov | (276) 696-3254 |  |  |  | 0 |  | 0 | FY2020 | 881277 | 1010000 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 300 days early | Y | Project estimate is less than $5M and is up to 20% over budget | [5 empty] | 2014-05-01 | 2013-02-14 | 2014-05-14 | 2013-02-14 | G | 2014-05-15 | 2013-08-01 | 2015-01-08 | 2014-08-05 | G | [5 empty] | 2015-07-08 | 2015-07-08 | 2015-07-08 | 2015-07-08 | G | [5 empty] | 2017-06-27 | 2017-06-27 | 2018-01-04 | 2017-06-27 | G | [5 empty] | 2017-03-02 | 2015-12-15 | 2019-08-09 | 2015-12-16 | G | [5 empty] | 2019-10-08 | 2018-12-04 | 2019-10-08 | 2018-12-04 | G | 2019-11-27 | 2019-02-22 | 2019-12-19 | 2019-02-22 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.096295
1112 | 108686 | SIDEWALK SPOT WIDENING CITY OF FAIRFAX | 9999 | Urban | Facilities for Pedestrians and Bicycles | Locally | Fairfax | FAIRFAX | Northern Virginia | Northern Virginia:Fairfax | Local Assistance Division | Amir Salahshoor | A.Salahshoor@VDOT.Virginia.gov | (703) 259-1957 | Rhoderick M Undan | Rhoderick.Undan@vdot.virginia.gov | (703) 259-3347 | Christina Alexander | Christina.Alexander@fairfaxva.gov |  | 0 |  | 0 | FY2023 | 500000 | 500000 | ACTIVITY DATES SET | G | Start Purchasing Right-of-Way milestone finished 58 days early | G | Project is on budget | 2016-07-01 | 2016-07-01 | 2016-07-26 | 2016-07-26 | G | 2016-07-27 | 2016-07-27 | 2016-07-27 | 2016-07-27 | G | 2018-07-27 | 2018-09-12 | 2019-07-29 | 2020-05-11 | R | [10 empty] | 2020-10-30 | 2020-09-01 | 2020-10-30 | 2020-09-02 | G | [5 empty] | 2020-11-03 | 2020-09-03 | 2021-08-30 |  | G | [10 empty] | 2021-09-16 |  | 2022-02-28 |  | G | 2022-03-01 |  | 2022-08-31 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.18003
1113 | 108797 | Cheseapeake Blvd/ Cromwell Drive Int. Improvements | 0247 | Urban | Safety | Locally | Norfolk | NORFOLK | Hampton Roads | Hampton Roads:Norfolk | Infrastructure Investment Division | Stephen Rowan | Steve.Rowan@vdot.virginia.gov | (757) 790-9925 | Derrick Williams | Derrick.Williams@vdot.virginia.gov | (757) 956-3097 | Keith Darrow, P. E. | Keith.darrow@norfolk.gov | (757) 664-7305 | 0 |  | 0 | FY2021 | 637500 | 990000 | ACTIVITY DATES SET | R | Solicit Bids milestone is 135 days past the expected completion date | R | Project estimate is less than $5M and is 20% or more over budget | 2016-12-19 | 2016-12-19 | 2017-03-17 | 2017-03-17 | G | 2017-03-16 | 2017-03-16 | 2017-03-20 | 2017-03-20 | G | 2017-03-27 | 2017-03-21 | 2018-10-29 | 2018-11-16 | R | [35 empty] | 2020-08-28 |  | 2020-10-09 |  | R | 2020-10-12 |  | 2021-04-08 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.25266
1114 | 109085 | NORTH MAIN STREET SIDEWALKS |  | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Lawrenceville | SOUTH HILL | Richmond | NonMPO:NonMPO | Local Assistance Division | Brian J Lokker | Brian.Lokker@VDOT.Virginia.gov | (804) 524-6010 | Brian J Lokker | Brian.Lokker@VDOT.Virginia.gov | (804) 524-6010 | Ashleigh Zincone - SPDC | azincone@southsidepdc.org | (434) 447-7101 | 0 |  | 0 | FY2020 | 381302 | 538210 | CONSTRUCTION STARTED | R | Start Delivery milestone finished 134 days late | R | Project estimate is less than $5M and is 20% or more over budget | 2016-05-31 | 2016-05-31 | 2016-08-23 | 2016-08-23 | G | 2016-10-31 | 2016-10-31 | 2016-11-03 | 2016-11-03 | G | 2017-10-31 | 2017-10-31 | 2018-04-06 | 2018-04-02 | G | [10 empty] | 2018-05-29 | 2018-06-22 | 2018-06-26 | 2018-06-22 | G | [5 empty] | 2018-06-28 | 2018-06-25 | 2019-04-11 | 2019-02-08 | G | [10 empty] | 2019-04-29 | 2019-07-10 | 2019-05-24 | 2019-07-22 | R | 2019-05-28 | 2019-07-23 | 2019-07-08 | 2019-11-19 | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.34836
1115 | 110112 | #SGR17VB - BRIDGE REPLACE RT 632 HARRISONS CREEK ID 10674 | 0632 | Secondary | Bridge Replacement w/o Added Capacity | VDOT | King William County | SALUDA | Fredericksburg | NonMPO:NonMPO | Infrastructure Investment/Asset Management Division | Jeremy B Cobb | Jeremy.Cobb@vdot.virginia.gov | (804) 586-2255 | Jeremy B Cobb | Jeremy.Cobb@vdot.virginia.gov | (804) 586-2255 |  |  |  | 0 |  | 1 | FY2021 | 1950000 | 1750000 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 349 days early | G | Project is on budget | [5 empty] | 2016-11-07 | 2016-11-07 | 2016-11-07 | 2016-11-07 | G | 2016-11-08 | 2016-11-09 | 2018-06-19 | 2018-06-14 | G | [5 empty] | 2018-06-13 | 2018-06-13 | 2018-06-28 | 2018-06-28 | G | 2018-08-27 | 2018-08-07 | 2018-09-10 | 2018-08-07 | G | 2019-09-26 | 2019-01-04 | 2020-01-29 | 2019-05-14 | G | 2018-09-25 | 2018-08-30 | 2019-09-25 | 2019-04-16 | G | 2018-03-12 | 2018-03-12 | 2019-02-22 | 2018-10-22 | G | [5 empty] | 2020-04-14 | 2019-07-09 | 2020-04-14 | 2019-07-09 | G | 2020-07-15 | 2019-09-25 | 2020-09-08 | 2019-09-25 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.059791
1116 | 111016 | #SMART18 - POWER PLANT PARKWAY SIDEWALKS | 0415 | Urban | Safety | Locally | Hampton | WILLIAMSBURG | Hampton Roads | Hampton Roads:Hampton | Infrastructure Investment Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Derrick Williams | Derrick.Williams@vdot.virginia.gov | (757) 956-3097 | Philippe Fenouil, P.E. | philippe.fenouil@hampton.gov | (757) 727-6197 | 1 | 2018 | 0 | FY2025 | 753500 | 753500 | NO DATES SET YET | G | Agreement with Locality milestone is 219 days ahead of the expected completion date | Y | Estimate not current | 2021-07-06 |  | 2021-09-28 |  | G | 2021-09-29 |  | 2021-10-01 |  | G | 2021-10-04 |  | 2022-04-14 |  | G | [10 empty] | 2023-03-15 |  | 2023-04-04 |  | G | [5 empty] | 2023-04-06 |  | 2024-02-16 |  | G | [10 empty] | 2024-03-06 |  | 2024-04-16 |  | G | 2024-04-17 |  | 2024-10-04 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.24253
1117 | 111369 | #SMART18 - Intersection Realignment/Improvement US220B/SR 40 | 0040 | Primary | Reconstruction w/o Added Capacity | VDOT | Rocky Mount | BEDFORD | Salem | NonMPO:NonMPO | Infrastructure Investment Division | Alex H Price | Alex.Price@VDOT.Virginia.gov | (540) 378-5053 | Elias Mannon | Eli.Mannon@vdot.virginia.gov | (540) 387-5370 | Joshua Gibson | jgibson@rockymountva.org | (540) 483-0907 | 1 | 2018 | 0 | FY2025 | 4936472 | 6108048 | NO DATES SET YET | G | Start Development milestone is 144 days ahead of the expected completion date | Y | Estimate not current | [5 empty] | 2021-07-01 |  | 2021-07-15 |  | G | 2021-07-16 |  | 2022-03-10 |  | G | [5 empty] | 2023-01-09 |  | 2023-01-24 |  | G | 2023-12-19 |  | 2024-01-03 |  | G | 2024-05-29 |  | 2024-12-04 |  | G | 2024-01-23 |  | 2024-12-05 |  | G | 2023-06-05 |  | 2023-12-11 |  | G | [5 empty] | 2025-03-11 |  | 2025-03-11 |  | G | 2025-04-24 |  | 2025-06-27 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 1 | 0.24749
1118 | 112770 | I-66 LANDSCAPING @ RTE 15 INTERCHANGE | 0015 | Primary | Landscaping/Beautification | VDOT | Prince William County | MANASSAS | Northern Virginia | Northern Virginia:Prince William County | Infrastructure Investment Division | Christiana M Briganti-Dunn | Christiana.Briganti@VDOT.Virginia.gov | (703) 259-2960 | Mehrdad Naderi | Mehrdad.Naderi@vdot.virginia.gov | (703) 259-2217 |  |  |  | 0 |  | 0 | FY2019 | 1520000 | 1074000 | CONSTRUCTION COMPLETED | R | Start Delivery milestone finished 9 days late | G | Project is on budget | [5 empty] | 2018-02-06 | 2018-04-09 | 2018-02-20 | 2018-04-09 | R | 2018-02-21 | 2011-04-01 | 2018-03-06 | 2011-04-18 | G | [35 empty] | 2018-10-09 | 2018-11-06 | 2018-10-09 | 2018-11-06 | R | 2018-11-15 | 2019-01-23 | 2019-01-14 | 2019-01-23 | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 1 | 0.26778
1119 | 112944 | Borden Mowery Drive Phase III - Strasburg | 0848 | Secondary | New Construction Roadway | Locally | Strasburg | EDINBURG | Staunton | NonMPO:NonMPO | Local Assistance Division | Steven K Damron | Steven.Damron@VDOT.Virginia.gov | (804) 786-1172 | Jamison Brown | Jamison.Brown@vdot.virginia.gov | (540) 332-7389 | Wyatt Pearson | wpearson@strasburgva.com | (540) 465-9197 | 0 |  | 0 | FY2022 | 2783671 | 2783671 | ACTIVITY DATES SET | Y | Complete Purchasing Right-of-Way milestone is 50 days ahead of the expected completion date and there is a risk of missing this milestone date | Y | Estimate not current | 2018-10-31 | 2018-07-11 | 2019-01-31 | 2018-09-21 | G | 2019-02-01 | 2018-09-24 | 2019-02-05 | 2019-02-05 | G | 2019-02-06 | 2019-02-06 | 2019-08-09 | 2019-08-09 | G | [10 empty] | 2020-06-05 | 2020-01-24 | 2020-06-25 | 2020-02-04 | G | [5 empty] | 2020-06-29 |  | 2021-04-12 |  | Y | 2019-05-09 | 2019-05-09 | 2020-01-14 | 2019-10-11 | G | [5 empty] | 2021-04-28 |  | 2021-05-25 |  | G | 2021-08-13 |  | 2021-08-13 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.23499
1120 | 112964 | #SGR19LB??- LIME KILN ROAD BRIDGE REPLACEMENT |  | Urban | Bridge Rehab w/o Added Capacity | VDOT | Lexington | LEXINGTON | Staunton | NonMPO:NonMPO | Infrastructure Investment Division | Susan E Hammond | Susan.Hammond@VDOT.Virginia.gov | (540) 462-6990 | Alexander Bellido | Alexander.Bellido@vdot.virginia.gov | (540) 569-4520 |  |  |  | 0 |  | 1 | FY2024 | 1662561 | 1662561 | NO DATES SET YET | G | Start Development milestone is 173 days ahead of the expected completion date | G | Project is on budget | [5 empty] | 2021-08-02 |  | 2021-08-13 |  | G | 2021-08-16 |  | 2022-04-12 |  | G | [5 empty] | 2022-07-25 |  | 2022-09-02 |  | G | [15 empty] | 2023-02-24 |  | 2023-05-25 |  | G | [5 empty] | 2023-08-08 |  | 2023-08-08 |  | G | 2023-10-30 |  | 2023-10-30 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.14158
1121 | 113272 | FLORIDA AVENUE - CONSTRUCT SIDEWALK | 9999 | Urban | Facilities for Pedestrians and Bicycles | Locally | Lynchburg | APPOMATTOX | Lynchburg | Lynchburg:Lynchburg | Local Assistance Division | Gregg Allen | Gregg.Allen@vdot.virginia.gov | (434) 426-5575 | Gregg Allen | Gregg.Allen@vdot.virginia.gov | (434) 426-5575 | Lee Newland | lee.newland@lynchburg.gov | (434) 455-3947 | 0 |  | 0 | FY2027 | 9850000 | 9850000 | NO DATES SET YET-PE OPEN | G | Obtained Permits milestone finished 2145 days early | G | Project is on budget | 2024-01-31 | 2019-03-29 | 2024-04-24 | 2019-06-21 | G | 2024-04-25 | 2019-06-24 | 2024-04-29 | 2019-06-26 | G | 2024-04-30 | 2019-06-27 | 2024-11-01 |  | G | [10 empty] | 2025-08-28 |  | 2025-09-18 |  | G | [5 empty] | 2025-09-22 |  | 2026-07-06 |  | G | 2024-12-12 | 2019-10-01 | 2025-08-15 | 2019-10-01 | G | [5 empty] | 2026-07-22 |  | 2026-08-18 |  | G | 2026-11-06 |  | 2026-11-06 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.13771
1122 | 113580 | PRIMARY EXTENSION RECONSTRUCTION - 324 DIXON STREET | 0002 | Urban | Reconstruction w/o Added Capacity | Locally | Fredericksburg | FREDERICKSBURG | Fredericksburg | NonMPO:NonMPO | Infrastructure Investment Division | Richard A Spurlock | Richard.Spurlock@VDOT.Virginia.gov | (540) 899-4302 | Richard A Spurlock | Richard.Spurlock@VDOT.Virginia.gov | (540) 899-4302 | Erik Nelson | enelson@fredericksburgva.gov | (540) 937-0572 | 0 |  | 1 | FY2020 | 206473 | 206473 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 103 days early | G | Project is on budget | 2019-02-06 | 2018-07-30 | 2019-05-01 | 2018-10-23 | G | [5 empty] | 2019-02-06 | 2019-01-10 | 2019-02-20 | 2019-01-25 | G | [35 empty] | 2019-06-05 | 2019-01-07 | 2019-07-02 | 2019-01-07 | G | 2019-07-03 | 2019-03-12 | 2019-07-03 | 2019-03-22 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.079165
1123 | 113858 | RTE 736 - RURAL RUSTIC - SURFACE TREAT NON-HARDSURFACE ROAD | 0736 | Secondary | Reconstruction w/o Added Capacity | VDOT | Albemarle County | CHARLOTTESVILLE | Culpeper | NonMPO:NonMPO | Infrastructure Investment Division | Ken Connors |  |  | Harold L Jones | Harold.Jones@VDOT.virginia.gov | (434) 422-9378 |  |  |  | 0 |  | 0 | FY2026 | 455000 | 455000 | NO DATES SET YET | G | Start Development milestone is 964 days ahead of the expected completion date | Y | Estimate not current | [5 empty] | 2023-10-02 |  | 2023-10-13 |  | G | 2023-10-17 |  | 2024-06-11 |  | G | [5 empty] | 2025-02-20 |  | 2025-04-02 |  | G | [5 empty] | 2025-07-17 |  | 2025-11-07 |  | G | [5 empty] | 2025-07-01 |  | 2025-10-01 |  | G | [5 empty] | 2025-11-10 |  | 2025-11-10 |  | G | 2026-02-06 |  | 2026-02-06 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | SAAP CONTRACT | 0 | 0 | 0.15667
1124 | 113999 | SIDEWALK AND RAMP ACCOMMODATION - DISTRICTWIDE | 9999 | Miscellaneous | Safety | VDOT | Richmond District-wide |  | Richmond | Richmond:Richmond District-wide | Infrastructure Investment Division | Raymond Chapman | Scott.Chapman@vdot.virginia.gov | (804) 609-5277 | Raymond Chapman | Scott.Chapman@vdot.virginia.gov | (804) 609-5277 |  |  |  | 0 |  | 0 | FY2027 | 3603800 | 3603800 | NO DATES SET YET | G | Start Development milestone is 661 days ahead of the expected completion date | Y | Estimate not current | [5 empty] | 2022-12-01 |  | 2022-12-14 |  | G | 2022-12-15 |  | 2023-11-09 |  | G | [5 empty] | 2024-09-16 |  | 2024-09-27 |  | G | 2026-01-08 |  | 2026-01-23 |  | G | 2026-06-17 |  | 2026-12-23 |  | G | 2026-02-10 |  | 2026-08-13 |  | G | 2025-06-24 |  | 2025-12-31 |  | G | [5 empty] | 2027-01-12 |  | 2027-01-12 |  | G | 2027-04-06 |  | 2027-04-06 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.069727
1125 | 115268 | #SGR20LP - EMMET ST. SOUTH - PRIMARY EXTENSION PAVING | 6029 | Urban | Resurfacing | Locally | Charlottesville | CHARLOTTESVILLE | Culpeper | Charlottesville:Charlottesville | Local Assistance Division | Gregory J Cooley | Gregory.Cooley@vdot.virginia.gov | (434) 906-7979 | Michael D Barnes | MichaelD.Barnes@vdot.virginia.gov | (434) 422-9861 | MARTY SILMAN | SILMANM@CHARLOTTESVILLE.ORG | (434) 970-3071 | 0 |  | 1 | FY2020 | 290995 | 290995 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 3 days early | G | Project is on budget | 2019-10-02 | 2019-09-20 | 2019-12-31 | 2019-10-10 | G | [5 empty] | 2019-10-02 | 2019-09-22 | 2019-10-15 | 2019-09-25 | G | [25 empty] | 2019-09-26 | 2019-12-06 | 2019-12-24 | 2019-12-09 | G | [5 empty] | 2020-01-13 | 2020-01-13 | 2020-03-11 | 2020-03-11 | G | 2020-05-29 | 2020-05-29 | 2020-06-11 | 2020-06-08 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.080936
1126 | 115412 | #SMART20 - Superstreet - Rt 60 at Woolridge/Old Buck. Rd | 0060 | Primary | Safety | VDOT | Chesterfield County | CHESTERFIELD | Richmond | Richmond:Chesterfield County | Infrastructure Investment Division | Jason C Williams | Jason.Williams@VDOT.Virginia.gov | (804) 609-5337 | Jason C Williams | Jason.Williams@VDOT.Virginia.gov | (804) 609-5337 | Chessa Faulkner |  |  | 1 | 2020 | 0 | FY2025 | 13239000 | 13239000 | NO DATES SET YET-PE OPEN | G | Start Development milestone finished 211 days early | G | Project is on budget | [5 empty] | 2020-09-17 | 2020-03-02 | 2020-09-30 | 2020-03-03 | G | 2020-10-01 | 2020-03-04 | 2021-08-30 |  | G | [5 empty] | 2022-07-07 |  | 2022-07-20 |  | G | 2023-10-25 |  | 2023-11-07 |  | G | 2024-04-08 |  | 2024-10-09 |  | G | 2023-11-28 |  | 2024-06-04 |  | G | 2023-04-14 |  | 2023-10-18 |  | G | [5 empty] | 2024-11-12 |  | 2024-11-12 |  | G | 2025-02-07 |  | 2025-02-07 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.098612
1127 | 116169 | #I81CIP SB MM 54.1 EXTEND RAMP TO REST AREA (ID #15) | 0081 | Interstate | Reconstruction w/ Added Capacity | VDOT | Smyth County | ABINGDON | Bristol | NonMPO:NonMPO | Infrastructure Investment Division | Marvin E Holley | Gene.Holley@VDOT.Virginia.gov | (276) 696-3255 | Marvin E Holley | Gene.Holley@VDOT.Virginia.gov | (276) 696-3255 |  |  |  | 0 |  | 0 | FY2023 | 4500000 | 4500000 | ACTIVITY DATES SET | G | Determine Requirements milestone finished 164 days early | G | Project is on budget | [5 empty] | 2020-07-01 | 2020-01-02 | 2020-07-15 | 2020-01-09 | G | 2020-07-16 | 2020-01-10 | 2021-03-12 | 2020-09-29 | G | [5 empty] | 2021-05-17 |  | 2021-05-17 |  | G | [5 empty] | 2021-10-13 |  | 2022-02-11 |  | G | [5 empty] | 2019-10-16 | 2019-10-16 | 2022-05-06 |  | G | [5 empty] | 2022-06-14 |  | 2022-06-14 |  | G | 2022-09-02 |  | 2022-09-02 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.084912
1128 | 116607 | NOVA SYSTEMIC FLASHING YELLOW ARROWS PH1 | 9999 | Miscellaneous | Safety | VDOT | Northern Virginia District-wide |  | Northern Virginia | Northern Virginia:Northern Virginia District-wide | Infrastructure Investment/Asset Management Division | Waqar A Siddiqui | Sid.Siddiqui@VDOT.Virginia.gov | (703) 259-3225 | Tienjung Ho | Tien-Jung.Ho@VDOT.Virginia.gov | (703) 259-2752 |  |  |  | 0 |  | 0 | FY2020 | 1600000 | 1600000 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 29 days early | G | Project is on budget | [5 empty] | 2019-10-23 | 2019-10-23 | 2020-02-14 | 2020-02-14 | G | 2020-02-18 | 2020-02-18 | 2020-03-30 | 2020-02-27 | G | [5 empty] | 2020-02-27 | 2020-02-27 | 2020-02-27 | 2020-02-27 | G | [25 empty] | 2020-05-01 | 2020-04-07 | 2020-05-07 | 2020-04-07 | G | 2020-05-08 | 2020-04-08 | 2020-05-08 | 2020-04-09 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | WORK/TASK ORDER | 1 | 0 | 0.065952
1129 | 116692 | SYSTEMIC RUMBLE STRIPS - DISTRICTWIDE | 9999 | Miscellaneous | Safety | VDOT | Richmond District-wide |  | Richmond | Richmond:Richmond District-wide | Infrastructure Investment/Asset Management Division | Adam S Brooks | Adam.Brooks@VDOT.Virginia.gov | (804) 609-5274 | Adam S Brooks | Adam.Brooks@VDOT.Virginia.gov | (804) 609-5274 | N\A |  |  | 0 |  | 0 | FY2025 | 8941701 | 8941701 | NO DATES SET YET | G | Start Development milestone is 366 days ahead of the expected completion date | G | Project is on budget | [5 empty] | 2022-02-01 |  | 2022-02-22 |  | G | 2022-02-23 |  | 2022-12-22 |  | G | [5 empty] | 2023-07-25 |  | 2023-08-21 |  | G | [5 empty] | 2024-04-17 |  | 2024-08-15 |  | G | [5 empty] | 2024-01-18 |  | 2024-06-14 |  | G | [5 empty] | 2024-09-10 |  | 2024-09-10 |  | G | 2024-12-03 |  | 2024-12-03 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.063196
1130 | 113173 | I-81 Exit 137 SB Safety Improvements | 0081 | Interstate | Safety | VDOT | Roanoke County | SALEM | Salem | Roanoke:Roanoke County | Infrastructure Investment Division | Bernard S Grinnell | Sean.Grinnell@VDOT.Virginia.gov | (540) 375-0148 | Francis Scarpinato | Francis.Scarpinato@vdot.virginia.gov | (540) 375-3593 |  |  |  | 0 |  | 0 | FY2026 | 1720000 | 1720000 | NO DATES SET YET | G | Start Development milestone is 887 days ahead of the expected completion date | G | Project is on budget | [5 empty] | 2023-07-17 |  | 2023-07-28 |  | G | 2023-07-31 |  | 2024-03-26 |  | G | [5 empty] | 2024-11-27 |  | 2025-01-13 |  | G | [5 empty] | 2025-04-30 |  | 2025-08-21 |  | G | [5 empty] | 2025-04-15 |  | 2025-07-16 |  | G | [5 empty] | 2025-09-09 |  | 2025-09-09 |  | G | 2025-12-03 |  | 2025-12-03 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.13061
1131 | 113533 | Rte 657, Red Valley Rd - Rural Rustic | 0657 | Secondary | Resurfacing | VDOT | Franklin County | BEDFORD | Salem | NonMPO:NonMPO | Infrastructure Investment Division | Todd K Daniel | Todd.Daniel@VDOT.Virginia.gov | (540) 682-7000 | Lisa D Lewis | Lisa.Lewis@VDOT.Virginia.gov | (540) 493-4127 |  |  |  | 0 |  | 0 | FY2028 | 990000 | 990000 | NO DATES SET YET | G | Start Development milestone is 1061 days ahead of the expected completion date | G | Project is on budget | [5 empty] | 2024-01-03 |  | 2024-01-18 |  | G | 2024-01-19 |  | 2024-12-12 |  | G | [5 empty] | 2025-10-15 |  | 2025-10-29 |  | G | 2027-02-10 |  | 2027-02-24 |  | G | 2027-07-19 |  | 2028-01-27 |  | G | 2027-03-12 |  | 2027-09-14 |  | G | 2026-07-24 |  | 2027-02-03 |  | G | [5 empty] | 2028-02-08 |  | 2028-02-08 |  | G | 2028-04-28 |  | 2028-04-28 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | SAAP CONTRACT | 0 | 0 | 0.1213
1132 | 113630 | I-95 REST AREA TRUCK PARKING EXPANSION | 0095 | Interstate | Other | VDOT | Caroline County | FREDERICKSBURG | Fredericksburg | NonMPO:NonMPO | Asset Management Division | Richard A Spurlock | Richard.Spurlock@VDOT.Virginia.gov | (540) 899-4302 | Curtis B Holloway | Curtis.Holloway@vdot.virginia.gov | (540) 374-3367 |  |  |  | 0 |  | 0 | FY2021 | 4000000 | 5049712 | ADVERTISED | G | Solicit Bids milestone finished on-time | R | Project estimate is less than $5M and is 20% or more over budget | [5 empty] | 2019-11-01 | 2019-06-28 | 2019-11-22 | 2019-07-17 | G | 2019-11-25 | 2019-07-18 | 2020-09-25 | 2019-12-17 | G | [5 empty] | 2021-04-30 | 2020-04-15 | 2021-05-27 | 2020-11-04 | G | 2020-06-22 | 2020-06-22 | 2020-06-26 | 2020-06-22 | G | 2020-08-24 | 2020-09-10 | 2020-10-20 | 2021-01-11 | R | 2020-07-14 | 2020-06-22 | 2020-09-08 | 2020-06-22 | G | [10 empty] | 2021-01-12 | 2021-01-12 | 2021-01-12 | 2021-01-12 | G | 2021-04-05 |  | 2021-04-05 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.079366
1133 | 113886 | Tidewater Drive and Easy Street Safety Improvements | 0168 | Primary | Facilities for Pedestrians and Bicycles | Locally | Norfolk | NORFOLK | Hampton Roads | Hampton Roads:Norfolk | Infrastructure Investment Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Derrick Williams | Derrick.Williams@vdot.virginia.gov | (757) 956-3097 | Robert Brown, P.E. | rob.brown@norfolk.gov | (757) 664-7305 | 0 |  | 0 | FY2025 | 658100 | 658100 | NO DATES SET YET | G | Agreement with Locality milestone is 947 days ahead of the expected completion date | Y | Estimate not current | 2023-07-03 |  | 2023-09-26 |  | G | 2023-09-27 |  | 2023-09-29 |  | G | 2023-10-02 |  | 2024-04-11 |  | G | [25 empty] | 2024-05-17 |  | 2025-01-24 |  | G | [5 empty] | 2025-02-24 |  | 2025-03-21 |  | G | 2025-06-10 |  | 2025-06-10 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.23356
1134 | 115215 | Appalachia-Big Stone Gap Trail Amenities | 9999 | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Appalachia | WISE | Bristol | NonMPO:NonMPO | Local Assistance Division | John W Bechtold | John.Bechtold@vdot.virginia.gov | (276) 696-3365 | Kenneth R Plummer | KR.Plummer@VDOT.Virginia.gov | (276) 696-3261 | Fred Luntsford | fluntsford@townofappalachiava.us |  | 0 |  | 0 | FY2021 | 465375 | 128451 | ACTIVITY DATES SET | Y | Solicit Bids milestone is 30 days ahead of the expected completion date and there is a risk of missing this milestone date | Y | Estimate not current | 2019-05-01 | 2019-05-01 | 2019-07-25 | 2019-07-25 | G | [5 empty] | 2019-05-01 | 2019-05-01 | 2019-05-14 | 2019-05-14 | G | [35 empty] | 2021-02-24 |  | 2021-03-23 |  | Y | 2021-06-10 |  | 2021-06-10 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.34606
1135 | 115376 | Permanent Message Boards |  | Urban | Traffic Management/Engineering | Locally | Newport News | WILLIAMSBURG | Hampton Roads | Hampton Roads:Newport News | Infrastructure Investment Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Chessica Villaflores | Chessica.Villaflores@vdot.virginia.gov | (757) 956-3094 | Jacqueline Kassel | jkassel@nnva.gov | (757) 926-8666 | 0 |  | 0 | FY2028 | 500000 | 500000 | NO DATES SET YET | G | Agreement with Locality milestone is 1739 days ahead of the expected completion date | Y | Estimate not current | 2025-09-02 |  | 2025-11-26 |  | G | 2025-12-01 |  | 2025-12-03 |  | G | 2025-12-04 |  | 2026-06-11 |  | G | [25 empty] | 2026-07-20 |  | 2027-03-26 |  | G | [5 empty] | 2027-06-30 |  | 2027-07-28 |  | G | 2027-10-15 |  | 2027-10-15 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.34783
1136 | 115527 | #SMART20 Little Back River Peak Directional & 2Way Left Turn |  | Urban | Reconstruction w/ Added Capacity | Locally | Hampton | WILLIAMSBURG | Hampton Roads | Hampton Roads:Hampton | Infrastructure Investment Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Derrick Williams | Derrick.Williams@vdot.virginia.gov | (757) 956-3097 | Sandon Rogers, P.E. | Sandon.rogers@hampton.gov | (757) 727-6786 | 1 | 2020 | 0 | FY2029 | 8835000 | 8835000 | NO DATES SET YET | G | Agreement with Locality milestone is 1313 days ahead of the expected completion date | Y | Estimate not current | 2024-07-03 |  | 2024-09-26 |  | G | 2024-09-27 |  | 2024-10-10 |  | G | 2024-10-11 |  | 2025-09-29 |  | G | [10 empty] | 2026-10-02 |  | 2026-10-23 |  | G | [5 empty] | 2026-10-27 |  | 2027-08-09 |  | G | 2025-05-30 |  | 2026-02-05 |  | G | [5 empty] | 2028-08-22 |  | 2028-10-03 |  | G | 2028-12-27 |  | 2029-05-07 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.33601
1137 | 116190 | Median U Turn construction at the intersection of Rte 460 & | 0460 | Primary | Safety | VDOT | Dinwiddie County | PETERSBURG | Richmond | Tri-Cities:Dinwiddie County | Infrastructure Investment Division | Dianna M Bryant | Dianna.Bryant@VDOT.Virginia.gov | (804) 863-4004 | Dianna M Bryant | Dianna.Bryant@VDOT.Virginia.gov | (804) 863-4004 |  |  |  | 0 |  | 0 | FY2021 | 354396 | 354396 | AWARDED | G | Start Delivery milestone finished 98 days early | G | Project is on budget | [5 empty] | 2019-09-03 | 2019-09-03 | 2019-09-16 | 2019-09-16 | G | 2019-09-17 | 2019-09-17 | 2020-05-12 | 2020-04-30 | G | [5 empty] | 2019-11-21 | 2019-10-18 | 2020-01-07 | 2020-01-07 | G | [5 empty] | 2019-11-08 | 2019-11-08 | 2019-11-08 | 2019-11-08 | G | [15 empty] | 2020-05-20 | 2020-05-04 | 2020-05-20 | 2020-05-04 | G | 2020-08-11 | 2020-05-05 | 2020-08-11 | 2020-05-05 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | SAAP CONTRACT | 1 | 0 | 0.061748
1138 | 116665 | Templeton Avenue Drainage Improvements | 0000 | Urban | Mitigation of Water Pollution Due to Highway Runof | Locally | Roanoke | SALEM | Salem | Roanoke:Roanoke City | Local Assistance Division | Cheryl B Becker | Cheryl.Becker@vdot.virginia.gov | (540) 492-2531 | Cheryl B Becker | Cheryl.Becker@vdot.virginia.gov | (540) 492-2531 | Joseph Arthur | Joseph.Arthur@roanokeva.gov | (540) 853-5906 | 0 |  | 0 | FY2021 | 920000 | 920000 | AWARDED | G | Start Delivery milestone finished 137 days early | G | Project is on budget | 2020-03-30 | 2020-03-30 | 2020-06-22 | 2020-06-18 | G | 2020-06-23 | 2020-06-18 | 2020-06-25 | 2020-06-18 | G | 2020-06-26 | 2020-06-18 | 2021-01-05 | 2020-06-18 | G | [35 empty] | 2020-07-08 | 2020-06-18 | 2020-07-08 | 2020-06-18 | G | 2020-09-25 | 2020-06-18 | 2020-11-02 | 2020-06-18 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.20609
1139 | 116968 | #SGR21LP EAST MAIN STREET PRIMARY EXTENSION PAVING |  | Primary | Resurfacing | VDOT | Luray | HARRISONBURG | Staunton | NonMPO:NonMPO | Infrastructure Investment Division | Joel D Denunzio | Joel.DeNunzio@VDOT.virginia.gov | (540) 332-9093 | Mark W Hisey | Mark.Hisey@VDOT.Virginia.gov | (540) 280-4820 |  |  |  | 0 |  | 1 | FY2021 | 35752 | 35752 | ACTIVITY DATES SET | Y | Solicit Bids milestone is 51 days ahead of the expected completion date and there is a risk of missing this milestone date | G | Project is on budget | [5 empty] | 2021-01-11 | 2020-11-03 | 2021-02-02 | 2020-11-24 | G | 2021-02-03 | 2020-11-25 | 2021-12-03 | 2021-01-11 | G | [5 empty] | 2021-01-12 | 2021-01-12 | 2021-01-12 | 2021-01-12 | G | [5 empty] | 2020-12-28 | 2021-01-14 | 2021-04-12 | 2021-01-19 | G | [15 empty] | 2021-04-13 |  | 2021-04-13 |  | Y | 2021-06-30 |  | 2021-06-30 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.060449
1140 | 117048 | Lakeside Avenue Bike & Pedestrian Improvements | 9999 | Secondary | Facilities for Pedestrians and Bicycles | Locally | Henrico County | ASHLAND | Richmond | Richmond:Henrico County | Local Assistance Division | Douglas L Orcutt | Doug.Orcutt@vdot.virginia.gov | (804) 609-5428 | Douglas L Orcutt | Doug.Orcutt@vdot.virginia.gov | (804) 609-5428 | TBD |  | TBD | 0 |  | 0 | FY2029 | 3000000 | 3000000 | NO DATES SET YET | G | Agreement with Locality milestone is 1543 days ahead of the expected completion date | G | Project is on budget | 2025-01-06 |  | 2025-05-14 |  | G | 2025-05-15 |  | 2025-06-05 |  | G | 2025-12-15 |  | 2026-04-10 |  | G | [10 empty] | 2027-07-30 |  | 2027-09-02 |  | G | [5 empty] | 2027-09-03 |  | 2028-02-09 |  | G | 2028-01-05 |  | 2028-06-05 |  | G | [5 empty] | 2028-05-12 |  | 2028-06-09 |  | G | 2028-08-29 |  | 2028-08-29 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.36078
1141 | 117196 | #SGR21LP 114-City of Hampton 360 Armistead Ave N | 0134 | Urban | Resurfacing | Locally | Hampton | WILLIAMSBURG | Hampton Roads | Hampton Roads:Hampton | Infrastructure Investment/Asset Management Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Derrick Williams | Derrick.Williams@vdot.virginia.gov | (757) 956-3097 | Sandon S. Rogers, P.E., LS | Sandon.rogers@hampton.gov | (757) 727-6786 | 0 |  | 1 | FY2022 | 287000 | 287000 | NO DATES SET YET | G | Agreement with Locality milestone is 80 days ahead of the expected completion date | G | Project is on budget | 2021-01-04 |  | 2021-05-12 |  | G | 2021-05-13 |  | 2021-06-03 |  | G | 2021-07-02 |  | 2021-07-30 |  | G | [25 empty] | 2021-07-02 |  | 2021-07-30 |  | G | [5 empty] | 2021-09-28 |  | 2021-10-26 |  | G | 2022-01-21 |  | 2022-01-21 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.096514
1142 | 118165 | Hollins - Liberty Road Drainage Improvements | 0000 | Urban | Mitigation of Water Pollution Due to Highway Runof | Locally | Roanoke | SALEM | Salem | Roanoke:Roanoke City | Local Assistance Division | Cheryl B Becker | Cheryl.Becker@vdot.virginia.gov | (540) 492-2531 | Cheryl B Becker | Cheryl.Becker@vdot.virginia.gov | (540) 492-2531 | Joseph Arthur | Joseph.Arthur@roanokeva.gov | (540) 853-5901 | 0 |  | 0 | FY2028 | 550000 | 550000 | NO DATES SET YET | G | Agreement with Locality milestone is 1422 days ahead of the expected completion date | G | Project is on budget | 2024-08-30 |  | 2025-01-13 |  | G | 2025-01-14 |  | 2025-02-05 |  | G | 2025-08-12 |  | 2025-12-08 |  | G | [25 empty] | 2026-12-03 |  | 2027-05-05 |  | G | [5 empty] | 2027-07-02 |  | 2027-07-30 |  | G | 2027-10-20 |  | 2027-10-20 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.20432
1143 | 1850 | RTE 602 - RECONSTRUCTION | 0602 | Secondary | Reconstruction w/o Added Capacity | VDOT | Northampton County | ACCOMAC | Hampton Roads | NonMPO:NonMPO | Infrastructure Investment Division | Christopher E Eggleston | Christopher.Eggleston@vdot.virginia.gov | (757) 857-8955 | Kenneth D Mckinna | Kenneth.McKinna@VDOT.Virginia.gov | (757) 956-3271 |  |  |  | 0 |  | 0 | FY2023 | 924016 | 922489 | ACTIVITY DATES SET | G | Obtained Permits milestone finished 126 days early | G | Project is on budget | [5 empty] | 1990-02-16 | 1990-02-16 | 1990-02-26 | 1990-02-26 | G | 2018-03-14 | 2018-03-14 | 2018-05-11 | 2018-05-11 | G | [5 empty] | 2018-09-20 | 2018-09-11 | 2018-10-03 | 2018-09-11 | G | [15 empty] | 2019-10-01 | 2020-07-20 | 2020-11-23 | 2020-07-20 | G | [5 empty] | 2022-12-14 |  | 2022-12-14 |  | G | 2023-02-01 |  | 2023-03-27 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.15282
1144 | 87071 | Add curb, sidewalk, and bike lanes | 0000 | Urban | Safety | Locally | Bridgewater | HARRISONBURG | Staunton | Harrisonburg:Bridgewater | Local Assistance Division | John-Allen L Ennis | JohnAllen.Ennis@VDOT.Virginia.gov | (540) 332-9118 | Michael S Fulcher | Michael.Fulcher@VDOT.Virginia.gov | (540) 332-2243 | Alex Wilmer | reuben.rhodes@vdot.virginia.gov | (540) 908-4212 | 0 |  | 0 | FY2021 | 1773372 | 2540135 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 82 days early | R | Project estimate is less than $5M and is 20% or more over budget | 2012-09-04 | 2012-09-03 | 2012-09-28 | 2012-09-28 | G | 2012-10-23 | 2012-10-23 | 2012-10-23 | 2012-10-23 | G | 2015-11-23 | 2015-11-23 | 2016-11-30 | 2016-11-30 | G | [10 empty] | 2019-04-30 | 2018-11-01 | 2019-05-31 | 2018-11-15 | G | [20 empty] | 2020-02-28 | 2020-04-01 | 2020-04-30 | 2020-05-11 | R | 2020-05-29 | 2020-06-09 | 2020-09-30 | 2020-07-10 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.10522
1145 | 97817 | 1831 Southampton Insurrection Tour |  | Enhancement | Scenic or Historic Highway Programs | Locally | Southampton County | FRANKLIN | Hampton Roads | NonMPO:NonMPO | Local Assistance Division | Charles T Catlett | Tommy.Catlett@vdot.virginia.gov | (757) 346-3078 | Keisha Wilkins | Keisha.Wilkins@vdot.virginia.gov | (757) 956-3110 | Southampton County |  |  | 0 |  | 0 | FY2023 | 442551 | 260000 | ADVERTISED | R | Solicit Bids milestone finished 2 days late | G | Project is on budget | [5 empty] | 2011-01-18 | 2011-01-17 | 2011-01-18 | 2011-01-18 | G | 2012-05-07 | 2012-05-05 | 2018-06-30 | 2018-06-29 | G | [10 empty] | 2018-02-06 | 2018-02-06 | 2018-02-06 | 2018-02-06 | G | [20 empty] | 2019-01-09 | 2020-02-28 | 2020-06-19 | 2020-06-21 | R | 2022-06-23 |  | 2022-08-03 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.31836
1146 | 104333 | Pruden Blvd Drainage Improvements | 0460 | Urban | Other | Locally | Suffolk | NORFOLK | Hampton Roads | Hampton Roads:Suffolk | Local Assistance Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Johndel A Alcaide | John.Alcaide@vdot.virginia.gov | (757) 956-3098 | Allan Mushett | gmushett@suffolkva.us | (757) 514-7681 | 0 |  | 0 | FY2019 | 850000 | 1373800 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 219 days early | R | Project estimate is less than $5M and is 20% or more over budget | [5 empty] | 2013-08-01 | 2014-01-23 | 2013-08-01 | 2014-01-27 | R | 2014-01-02 | 2014-02-01 | 2014-05-01 | 2014-12-03 | R | [10 empty] | 2015-06-01 | 2015-06-01 | 2015-09-11 | 2015-09-11 | G | [20 empty] | 2016-05-31 | 2016-05-31 | 2016-05-31 | 2016-05-31 | G | 2018-10-30 | 2018-06-25 | 2019-01-30 | 2018-06-25 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.11798
1147 | 105222 | Bridge Repl-Rte 134 over Brick Kiln Ck (Fed ID 19855) | 0134 | Primary | Bridge Replacement w/o Added Capacity | VDOT | York County | WILLIAMSBURG | Hampton Roads | Hampton Roads:York County | Infrastructure Investment Division | Kenneth D Mckinna | Kenneth.McKinna@VDOT.Virginia.gov | (757) 956-3271 | Prakriti K Das | Prakriti.Das@VDOT.Virginia.gov | (757) 897-8952 |  |  |  | 0 |  | 0 | FY2020 | 7380274 | 6976543 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 33 days early | G | Project is on budget | [5 empty] | 2013-10-01 | 2014-05-27 | 2013-10-01 | 2014-05-29 | R | 2014-10-27 | 2014-10-27 | 2015-11-17 | 2015-07-17 | G | [5 empty] | 2016-02-09 | 2016-02-09 | 2016-06-30 | 2016-06-30 | G | 2017-06-13 | 2017-06-13 | 2017-06-14 | 2017-06-14 | G | 2018-08-08 | 2018-08-08 | 2019-04-30 | 2019-04-30 | G | 2017-11-28 | 2017-11-28 | 2018-11-29 | 2018-07-26 | G | 2018-10-11 | 2018-10-11 | 2019-04-11 | 2019-04-01 | G | [5 empty] | 2019-06-11 | 2019-06-11 | 2019-06-11 | 2019-06-11 | G | 2019-07-25 | 2019-08-23 | 2019-09-25 | 2019-08-23 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.089215
1148 | 107140 | #HB2.FY17 #SGR21VB RT 17 I95 BRIDGE TO HOSPITAL BLVD | 0017 | Primary | Reconstruction w/ Added Capacity | VDOT | Spotsylvania County | FREDERICKSBURG | Fredericksburg | Fredericksburg:Spotsylvania County | Infrastructure Investment Division | Benjamin Ernst | Benjamin.Ernst@vdot.virginia.gov | (571) 585-0902 | Benjamin Ernst | Benjamin.Ernst@vdot.virginia.gov | (571) 585-0902 |  |  |  | 1 | 2017 | 0 | FY2021 | 20000000 | 23534380 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 42 days early | R | Project estimate is greater than $10M and is over budget by (a) 10% or more or (b) $5M or more | [5 empty] | 2016-04-01 | 2016-04-01 | 2016-05-10 | 2016-05-10 | G | 2016-05-11 | 2016-05-11 | 2017-05-24 | 2017-05-22 | G | [5 empty] | 2017-10-13 | 2017-10-23 | 2017-10-27 | 2017-10-27 | G | 2019-01-02 | 2018-12-26 | 2019-01-15 | 2019-01-07 | G | 2019-11-05 | 2019-07-19 | 2020-08-06 | 2020-03-27 | G | 2019-02-04 | 2019-03-19 | 2019-11-04 | 2019-10-22 | G | 2018-02-08 | 2018-02-08 | 2019-02-08 | 2019-01-31 | G | [5 empty] | 2020-08-11 | 2020-07-07 | 2020-08-11 | 2020-07-07 | G | 2020-09-24 | 2020-10-20 | 2020-12-01 | 2020-10-20 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.097693
1149 | 107947 | #SMART18 - NEABSCO MILLS ROAD - WIDEN TO 4 LANES | 0638 | Secondary | New Construction Roadway | Locally | Prince William County | MANASSAS | Northern Virginia | Northern Virginia:Prince William County | Infrastructure Investment Division | Amir Salahshoor | A.Salahshoor@VDOT.Virginia.gov | (703) 259-1957 | Saif-Ur Qargha | Saif.Qargha@vdot.virginia.gov | (703) 259-3223 | Gladis Arboleda | Garboleda@pwcgov.org | (703) 792-5276 | 1 | 2018 | 0 | FY2023 | 28255000 | 31174020 | ACTIVITY DATES SET | G | Start Purchasing Right-of-Way milestone finished 518 days early | Y | Project estimate is greater than $10M and is over budget by (a) up to 10% or (b) up to $5M | 2015-12-15 | 2016-11-14 | 2016-03-14 | 2016-11-14 | R | 2017-07-05 | 2016-11-28 | 2017-07-18 | 2016-11-28 | G | 2017-07-19 | 2017-11-09 | 2018-03-19 | 2018-03-15 | G | [10 empty] | 2021-01-08 | 2019-08-07 | 2021-01-25 | 2019-08-26 | G | [5 empty] | 2021-01-27 | 2021-01-03 | 2022-04-08 |  | G | [10 empty] | 2022-08-05 |  | 2022-12-30 |  | G | 2023-01-03 |  | 2023-01-03 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.39595
1150 | 117141 | Shore Drive Corridor Improvements-Phase IV | 0060 | Urban | Reconstruction w/o Added Capacity | Locally | Virginia Beach | NORFOLK | Hampton Roads | Hampton Roads:Virginia Beach | Local Assistance Division | Susan Wilson | Susan.Wilson@vdot.virginia.gov | (757) 956-3099 | Marci Thompson | Marci.Thompson@vdot.virginia.gov | (757) 956-3093 | Katie Shannon | kshannon@vbgov.com | (757) 385-1514 | 0 |  | 0 | FY2026 | 14543895 | 14543895 | NO DATES SET YET | R | Agreement with Locality milestone is 6 days past the expected completion date | G | Project is on budget | 2020-10-01 |  | 2021-02-15 |  | R | 2021-02-16 |  | 2021-03-09 |  | Y | 2021-09-13 |  | 2022-05-19 |  | G | [10 empty] | 2024-08-19 |  | 2024-09-23 |  | G | [5 empty] | 2024-09-24 |  | 2025-04-18 |  | G | 2024-06-21 |  | 2025-02-28 |  | G | [5 empty] | 2025-07-23 |  | 2025-08-19 |  | G | 2025-11-07 |  | 2025-11-07 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.13265
1151 | 117453 | STAUNTON DISTRICT FYA'S TASK 31 | 9999 | Miscellaneous | Traffic Management/Engineering | VDOT | Staunton District-wide |  | Staunton | NonMPO:NonMPO | Infrastructure Investment Division | Matthew Bond | Matthew.Bond@vdot.virginia.gov | (540) 332-9275 | Michael L Surratt | Michael.Surratt@VDOT.Virginia.gov | (540) 332-9325 |  |  |  | 0 |  | 0 | FY2021 | 230000 | 230000 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished on-time | G | Project is on budget | [10 empty] | 2020-06-01 | 2020-06-01 | 2020-10-06 | 2020-10-06 | G | [35 empty] | 2020-10-08 | 2020-10-08 | 2020-10-14 | 2020-10-14 | G | 2020-10-15 | 2020-10-15 | 2020-10-22 | 2020-10-22 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | WORK/TASK ORDER | 1 | 0 | 0.097743
1152 | 118410 | #SGR21LP - City of Richmond 1233 Bells Rd W |  | Urban | Resurfacing | Locally | Richmond | ASHLAND | Richmond | Richmond:Richmond | Infrastructure Investment/Asset Management Division | Olena Fecek | Olena.Fecek@vdot.virginia.gov | (804) 524-6368 | Olena Fecek | Olena.Fecek@vdot.virginia.gov | (804) 524-6368 | Kenny Horak | Kenneth.horak@richmondgov.com | (804) 646-4781 | 0 |  | 1 | FY2024 | 207471 | 207471 | NO DATES SET YET | G | Agreement with Locality milestone is 292 days ahead of the expected completion date | G | Project is on budget | 2021-08-02 |  | 2021-12-10 |  | G | 2021-12-13 |  | 2022-01-04 |  | G | 2022-02-04 |  | 2022-05-27 |  | G | [25 empty] | 2023-05-24 |  | 2023-10-23 |  | G | [5 empty] | 2023-12-22 |  | 2024-01-24 |  | G | 2024-04-12 |  | 2024-04-12 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.062618
1153 | 82513 | RTE.622 - BRIDGE REPL & APPR OVER NS RR FED. STR.NO. (13936) | 0622 | Secondary | Bridge Replacement w/o Added Capacity | VDOT | Prince Edward County | DILLWYN | Lynchburg | NonMPO:NonMPO | Infrastructure Investment Division | brian zobell |  |  | Gregory K Parsons | Gregory.Parsons@vdot.virginia.gov | (434) 856-8297 |  |  |  | 0 |  | 0 | FY2020 | 2153044 | 3155575 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 53 days early | R | Project estimate is less than $5M and is 20% or more over budget | [5 empty] | 2011-09-01 | 2011-09-29 | 2011-09-16 | 2011-09-29 | R | 2011-11-01 | 2011-09-29 | 2013-04-30 | 2013-04-30 | G | [5 empty] | 2013-11-26 | 2013-11-26 | 2013-12-03 | 2014-02-18 | R | 2014-12-05 | 2014-12-05 | 2014-12-10 | 2014-12-10 | G | 2016-03-28 | 2016-03-28 | 2016-11-15 | 2016-11-15 | G | 2015-01-29 | 2015-01-29 | 2016-02-23 | 2016-02-23 | G | [10 empty] | 2019-04-19 | 2019-04-09 | 2019-05-14 | 2019-04-09 | G | 2019-06-18 | 2019-06-26 | 2019-08-18 | 2019-06-26 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.068771
1154 | 95112 | Bridge Rehabilitation Rte 15 over Rappahannock River | 0015 | Primary | Bridge Rehab w/o Added Capacity | VDOT | Culpeper County | WARRENTON | Culpeper | NonMPO:NonMPO | Infrastructure Investment Division | William Gm Mcaninch | Glen.McAninch@VDOT.Virginia.gov | (540) 829-7638 | Howard M Tomlinson | Howard.Tomlinson@VDOT.virginia.gov | (540) 829-7436 |  |  |  | 0 |  | 0 | FY2020 | 4801429 | 2650000 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 69 days early | G | Project is on budget | [5 empty] | 2010-11-15 | 2010-09-13 | 2010-11-15 | 2010-09-23 | G | 2012-08-02 | 2010-11-15 | 2018-06-30 | 2018-07-23 | R | [5 empty] | 2018-10-25 | 2018-10-17 | 2018-11-30 | 2018-11-19 | G | [25 empty] | 2019-07-09 | 2019-07-09 | 2019-07-09 | 2019-07-09 | G | 2019-11-22 | 2019-09-25 | 2019-12-03 | 2019-09-25 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.14257
1155 | 101595 | #HB2.FY17 I-95 RAPPAHANNOCK RIVER CROSSING (SOUTHBOUND) | 0095 | Interstate | Reconstruction w/ Added Capacity | VDOT | Fredericksburg | FREDERICKSBURG | Fredericksburg | Fredericksburg:Fredericksburg | Infrastructure Investment Division | William Arel |  |  | Robert Galen Ridgell | Robert.Ridgell@vdot.virginia.gov | (540) 372-3549 |  |  |  | 1 | 2017 | 0 | FY2018 | 125000000 | 125000000 | CONSTRUCTION STARTED | G | Start Delivery milestone finished on-time | G | Project is on budget | [5 empty] | 2011-07-01 | 2011-08-19 | 2011-07-01 | 2011-08-19 | R | 2011-07-31 | 2013-11-01 | 2017-02-27 | 2016-11-08 | G | [5 empty] | 2017-02-01 | 2017-02-01 | 2017-03-09 | 2017-03-09 | G | 2017-03-30 | 2017-03-30 | 2017-03-30 | 2017-03-30 | G | [20 empty] | 2017-12-19 | 2017-12-19 | 2017-12-19 | 2017-12-19 | G | 2018-01-09 | 2018-01-09 | 2018-01-09 | 2018-01-09 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | DESIGN BUILD/PPTA | 1 | 0 | 0.081254
1156 | 104372 | Freeman Dr. Reconstruction | 0000 | Urban | Reconstruction w/o Added Capacity | Locally | Hampton | WILLIAMSBURG | Hampton Roads | Hampton Roads:Hampton | Local Assistance Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Derrick Williams | Derrick.Williams@vdot.virginia.gov | (757) 956-3097 | Philippe Fenouil P.E. | philippe.fenouil@hampton.gov | (757) 727-6197 | 0 |  | 0 | FY2019 | 1175000 | 2913000 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 42 days early | R | Project estimate is less than $5M and is 20% or more over budget | [5 empty] | 2013-10-01 | 2013-08-13 | 2013-10-01 | 2013-08-13 | G | 2015-05-29 | 2015-04-16 | 2016-01-20 | 2016-01-20 | G | [35 empty] | 2018-06-30 | 2018-06-26 | 2018-06-30 | 2018-06-26 | G | 2018-07-31 | 2018-07-31 | 2019-01-25 | 2018-12-14 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.15883
1157 | 107086 | RTE 647 (Hicks Rd, Mt. Gilead-Cardiff Ln) - RECONSTRUCTION | 0647 | Secondary | Reconstruction w/o Added Capacity | Locally | Chesterfield County | CHESTERFIELD | Richmond | Richmond:Chesterfield County | Local Assistance Division | Brian J Lokker | Brian.Lokker@VDOT.Virginia.gov | (804) 524-6010 | Brian J Lokker | Brian.Lokker@VDOT.Virginia.gov | (804) 524-6010 | Nate Mathis | mathisn@chesterfield.gov | (804) 748-1037 | 0 |  | 0 | FY2019 | 3100000 | 3100000 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 89 days early | G | Project is on budget | 2015-07-01 | 2015-09-29 | 2015-09-24 | 2015-09-29 | R | 2015-09-25 | 2015-11-03 | 2015-10-08 | 2015-11-03 | R | 2015-10-09 | 2017-04-18 | 2016-06-08 | 2017-04-18 | R | [10 empty] | 2017-05-16 | 2017-04-20 | 2017-05-30 | 2017-04-20 | G | [5 empty] | 2017-04-28 | 2017-04-28 | 2018-02-27 | 2018-02-27 | G | [10 empty] | 2018-04-30 | 2018-03-09 | 2018-04-30 | 2018-03-09 | G | 2018-05-01 | 2018-04-27 | 2018-07-25 | 2018-04-27 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.31821
1158 | 107158 | SIGNAL MUTCD COMPLIANCE UPGRADES - DISTRICTWIDE | 9999 | Miscellaneous | Safety | VDOT | Richmond District-wide |  | Richmond | Richmond:Richmond District-wide | Infrastructure Investment Division | Adam S Brooks | Adam.Brooks@VDOT.Virginia.gov | (804) 609-5274 | Adam S Brooks | Adam.Brooks@VDOT.Virginia.gov | (804) 609-5274 |  |  |  | 0 |  | 0 | FY2021 | 2250000 | 961235 | AWARDED | G | Start Delivery milestone finished 161 days early | G | Project is on budget | [5 empty] | 2018-10-19 | 2018-10-19 | 2018-11-01 | 2018-10-23 | G | 2018-11-02 | 2018-10-24 | 2018-12-04 | 2019-08-21 | R | [35 empty] | 2020-06-09 | 2020-06-09 | 2020-06-09 | 2020-06-09 | G | 2020-07-24 | 2020-06-09 | 2020-11-17 | 2020-06-09 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | WORK/TASK ORDER | 1 | 0 | 0.068258
1159 | 108757 | CHARLOTTESVILLE / CONST. NEW SIDEWALKS IN VARIOUS LOCATIONS | 0000 | Urban | Safety | Locally | Charlottesville | CHARLOTTESVILLE | Culpeper | Charlottesville:Charlottesville | Local Assistance Division | Ken Connors |  |  | Michael D Barnes | MichaelD.Barnes@vdot.virginia.gov | (434) 422-9861 | Jeanette Janiczek | janiczek@charlottesville.org | (434) 970-3309 | 0 |  | 0 | FY2019 | 200000 | 200000 | ACTIVITY DATES SET | R | Solicit Bids milestone is 691 days past the expected completion date | G | Project is on budget | 2017-02-15 | 2017-02-15 | 2017-05-10 | 2017-05-10 | G | 2017-05-11 | 2017-08-01 | 2017-05-15 | 2017-08-03 | R | 2017-05-16 | 2017-08-04 | 2017-11-20 | 2018-02-14 | R | [35 empty] | 2019-03-06 |  | 2019-04-02 |  | R | 2019-04-03 |  | 2019-05-13 |  | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.14391
1160 | 109286 | #HB2.FY17 Rte 52 North Spot Improvements | 0052 | Primary | Reconstruction w/o Added Capacity | VDOT | Carroll County | MARTINSVILLE | Salem | NonMPO:NonMPO | Infrastructure Investment Division | Alex H Price | Alex.Price@VDOT.Virginia.gov | (540) 378-5053 | Leslie T Repass | Todd.Repass@VDOT.Virginia.gov | (540) 381-7195 | Nikki Cannon | ncannon@carrollcountyva.org | (276) 730-3001 | 1 | 2017 | 0 | FY2020 | 3731701 | 3585511 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 71 days early | G | Project is on budget | [5 empty] | 2016-06-29 | 2016-06-29 | 2016-06-29 | 2016-07-11 | R | 2016-07-01 | 2016-07-01 | 2017-03-02 | 2017-03-02 | G | [5 empty] | 2017-12-04 | 2017-06-19 | 2017-12-15 | 2017-06-19 | G | 2018-09-24 | 2018-08-24 | 2018-10-05 | 2018-09-13 | G | 2019-02-11 | 2018-01-23 | 2019-06-07 | 2019-03-19 | G | 2018-10-23 | 2018-10-02 | 2019-05-20 | 2019-03-06 | G | 2018-04-18 | 2018-06-29 | 2018-09-04 | 2018-10-26 | R | [5 empty] | 2019-08-13 | 2019-10-08 | 2019-12-10 | 2019-10-08 | G | 2020-01-29 | 2020-01-20 | 2020-03-31 | 2020-01-20 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.092638
1161 | 110203 | RTE 626 - SAFETY AND DRAINAGE IMPROVEMENTS | 0626 | Secondary | Reconstruction w/o Added Capacity | VDOT | Halifax County | HALIFAX | Lynchburg | NonMPO:NonMPO | Infrastructure Investment Division | Raina A Rosado | Raina.Rosado@VDOT.Virginia.gov | (434) 856-8318 | Raina A Rosado | Raina.Rosado@VDOT.Virginia.gov | (434) 856-8318 |  |  |  | 0 |  | 0 | FY2021 | 2158438 | 1730948 | ADVERTISED | G | Solicit Bids milestone finished on-time | G | Project is on budget | [5 empty] | 2016-12-01 | 2016-12-20 | 2016-12-14 | 2016-12-22 | R | 2016-12-15 | 2016-12-23 | 2017-11-09 | 2017-12-04 | R | [5 empty] | 2018-08-30 | 2018-08-30 | 2018-09-13 | 2018-09-13 | G | 2019-08-26 | 2019-08-26 | 2019-09-09 | 2019-09-03 | G | 2020-06-17 | 2020-06-17 | 2020-12-23 | 2020-11-12 | G | 2019-09-25 | 2019-09-17 | 2020-06-16 | 2020-06-16 | G | 2019-02-14 | 2019-02-14 | 2019-10-15 | 2019-10-03 | G | [5 empty] | 2021-01-12 | 2021-01-12 | 2021-01-12 | 2021-01-12 | G | 2021-03-08 |  | 2021-03-26 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.098669
1162 | 111023 | Install and upgrade Countdown Pedestrian Signals | 0000 | Urban | Facilities for Pedestrians and Bicycles | Locally | Norfolk | NORFOLK | Hampton Roads | Hampton Roads:Norfolk | Infrastructure Investment Division | Todd M Halacy | Todd.Halacy@VDOT.Virginia.gov | (757) 956-3010 | Derrick Williams | Derrick.Williams@vdot.virginia.gov | (757) 956-3097 | Deborah Managiarcina, P.E. | deborah.managiaracina@norfolk.gov | (757) 664-7459 | 0 |  | 0 | FY2024 | 1906000 | 1906000 | NO DATES SET YET-PE OPEN | G | Start Development milestone finished 134 days early | G | Project is on budget | 2020-10-15 | 2020-10-15 | 2021-03-02 | 2020-10-20 | G | 2021-03-03 | 2020-10-21 | 2021-03-23 | 2020-11-09 | G | 2021-09-27 |  | 2022-01-26 |  | G | [25 empty] | 2023-01-23 | 2020-06-08 | 2023-06-20 | 2020-06-08 | G | [5 empty] | 2023-08-17 |  | 2023-09-14 |  | G | 2023-12-07 |  | 2023-12-07 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.2385
1163 | 111685 | #SGR18VB - CHAIN BRIDGE RD OVER LEESBURG PIKE (Fed 6463) | 0123 | Primary | Bridge Rehab w/o Added Capacity | VDOT | Fairfax County | FAIRFAX | Northern Virginia | Northern Virginia:Fairfax County | Infrastructure Investment/Asset Management Division | Gary Runco | Gary.Runco@vdot.virginia.gov | (703) 259-3341 | Yusaf M Masud | Yusaf.Masud@vdot.virginia.gov | (703) 259-2973 |  |  |  | 0 |  | 1 | FY2020 | 1250000 | 1250000 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 23 days early | G | Project is on budget | [5 empty] | 2018-03-07 | 2018-03-17 | 2018-03-20 | 2018-03-17 | G | 2018-03-21 | 2018-03-01 | 2018-04-17 | 2018-03-30 | G | [35 empty] | 2019-08-22 | 2019-08-13 | 2019-08-22 | 2019-08-13 | G | 2019-10-08 | 2019-11-13 | 2019-12-06 | 2019-11-13 | G | Final design is still underway | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.079396
1164 | 112310 | DUKE STREET AT WEST TAYLOR INTERSECTION IMPROVEMENTS - BRAC | 0236 | Urban | Safety | Locally | Alexandria | FAIRFAX | Northern Virginia | Northern Virginia:Alexandria | Infrastructure Investment Division | Amir Salahshoor | A.Salahshoor@VDOT.Virginia.gov | (703) 259-1957 | Robert J Strevell | Robert.Strevell@vdot.virginia.gov | (703) 259-1988 | Cuong Nguyen | cuong.nguyen@alexandriava.gov | (703) 746-4142 | 0 |  | 0 | FY2026 | 800000 | 800000 | NO DATES SET YET-PE OPEN | G | Start Development milestone finished on-time | G | Project is on budget | 2018-07-02 | 2018-07-02 | 2019-04-16 | 2019-04-16 | G | 2019-04-17 | 2019-04-17 | 2019-05-14 | 2019-05-14 | G | 2022-08-01 |  | 2022-11-23 |  | G | [35 empty] | 2024-07-17 |  | 2025-01-31 |  | G | 2025-04-22 |  | 2025-08-29 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.26115
1165 | 112855 | #SGR19VP - F19/C19 PM1J Bland Interstate | 9999 | Interstate | Resurfacing | VDOT | Bristol District-wide |  | Bristol | NonMPO:NonMPO | Infrastructure Investment/Asset Management Division | Leslie T Repass | Todd.Repass@VDOT.Virginia.gov | (540) 381-7195 | Kenneth E Turner | Kenneth.Turner@VDOT.Virginia.gov | (804) 225-3940 |  |  |  | 0 |  | 1 | FY2019 | 1930538 | 1930538 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished on-time | G | Project is on budget | [10 empty] | 2019-02-12 | 2019-02-12 | 2019-02-19 | 2019-02-19 | G | [35 empty] | 2019-03-12 | 2019-03-12 | 2019-03-12 | 2019-03-12 | G | 2018-09-28 | 2018-09-28 | 2019-03-13 | 2019-03-13 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.073859
1166 | 113075 | #SGR19VP - RT 179 2019 ACCOMAC RESIDENCY | 0179 | Primary | Resurfacing | VDOT | Accomack County | ACCOMAC | Hampton Roads | NonMPO:NonMPO | Infrastructure Investment/Asset Management Division | Jennifer L Ahlin | Jennifer.Ahlin@vdot.virginia.gov | (804) 786-6581 | John K Arms | John.Arms@vdot.virginia.gov | (757) 995-5156 |  |  |  | 0 |  | 1 | FY2019 | 119553 | 119553 | WAITING FINANCIAL CLOSURE | R | Start Delivery milestone finished 85 days late | G | Project is on budget | [10 empty] | 2019-01-08 | 2018-07-16 | 2019-01-14 | 2019-03-15 | R | [35 empty] | 2018-10-09 | 2019-04-09 | 2019-01-08 | 2019-04-09 | R | 2019-04-02 | 2019-06-26 | 2019-04-02 | 2019-06-26 | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.15152
1167 | 113177 | #SMART20 - WEST MAIN ST. PHASE II - 6TH ST NW TO 8TH ST. NW | 0250 | Urban | Facilities for Pedestrians and Bicycles | Locally | Charlottesville | CHARLOTTESVILLE | Culpeper | Charlottesville:Charlottesville | Local Assistance Division | Ken Connors |  |  | Michael D Barnes | MichaelD.Barnes@vdot.virginia.gov | (434) 422-9861 | Jeanette Janiczek | janiczekj@charlottesville.gov | (434) 970-3182 | 1 | 2020 | 0 | FY2025 | 12689020 | 12689020 | ACTIVITY DATES SET | G | Determine Requirements milestone finished on-time | G | Project is on budget | 2020-03-02 | 2019-08-29 | 2020-05-22 | 2019-10-16 | G | 2020-05-26 | 2019-10-17 | 2020-05-28 | 2020-01-16 | G | 2020-05-29 | 2020-01-21 | 2020-12-04 | 2020-12-04 | G | [10 empty] | 2021-12-08 |  | 2021-12-29 |  | G | [5 empty] | 2022-01-03 |  | 2023-03-06 |  | G | 2020-08-28 |  | 2021-05-06 |  | G | [5 empty] | 2024-07-15 |  | 2024-09-09 |  | G | 2024-12-02 |  | 2025-01-13 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.18065
1168 | 113444 | #SGR19LP - RT 36 Resurfacing, City of Petersburg | 0036 | Urban | Resurfacing | VDOT | Petersburg | PETERSBURG | Richmond | Tri-Cities:Petersburg | Local Assistance Division | James Shepherd | James.Shepherd@vdot.virginia.gov | (804) 609-5305 | James Shepherd | James.Shepherd@vdot.virginia.gov | (804) 609-5305 | Bill Riggleman | bill@petersburg-va.org | (804) 993-1972 | 0 |  | 1 | FY2019 | 117932 | 117932 | AWARDED | G | Start Delivery milestone finished 23 days early | G | Project is on budget | [10 empty] | 2019-01-02 | 2018-12-10 | 2019-01-08 | 2018-12-31 | G | [35 empty] | 2019-05-07 | 2019-03-12 | 2019-05-07 | 2019-03-12 | G | 2019-05-08 | 2019-03-13 | 2019-05-17 | 2019-04-24 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.067135
1169 | 113819 | Warwick Boulevard and Oriana Road | 0060 | Primary | Safety | Locally | Newport News | WILLIAMSBURG | Hampton Roads | Hampton Roads:Newport News | Infrastructure Investment Division | Susan Wilson | Susan.Wilson@vdot.virginia.gov | (757) 956-3099 | Chessica Villaflores | Chessica.Villaflores@vdot.virginia.gov | (757) 956-3094 | Bryan Stilley, P.E. | bstilley@nnva.gov | (757) 926-8699 | 0 |  | 0 | FY2025 | 824900 | 824900 | NO DATES SET YET | G | Agreement with Locality milestone is 222 days ahead of the expected completion date | G | Project is on budget | 2021-07-01 |  | 2021-10-01 |  | G | 2021-10-04 |  | 2021-10-15 |  | G | 2021-10-19 |  | 2022-04-28 |  | G | [10 empty] | 2023-05-02 |  | 2023-05-22 |  | G | [5 empty] | 2023-05-24 |  | 2024-03-07 |  | G | 2022-06-06 |  | 2023-02-10 |  | G | [5 empty] | 2024-03-25 |  | 2024-04-19 |  | G | 2024-07-10 |  | 2024-07-10 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.21414
1170 | 109611 | GLADE CREEK GREENWAY, PHASE 2 |  | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Vinton | SALEM | Salem | Roanoke:Vinton | Local Assistance Division | James M Guy | james.guy@vdot.virginia.gov | (540) 387-5247 | Jessie Nester | Jessie.Nester@vdot.virginia.gov | (540) 613-4115 | Anita McMillan | amcmillan@vintonva.gov | (540) 983-0605 | 0 |  | 0 | FY2020 | 531210 | 682720 | CONSTRUCTION STARTED | R | Start Delivery milestone finished 119 days late | R | Project estimate is less than $5M and is 20% or more over budget | 2016-08-01 | 2016-08-01 | 2016-09-26 | 2016-09-26 | G | 2016-09-22 | 2016-09-22 | 2016-09-23 | 2016-09-23 | G | 2017-11-13 | 2017-11-13 | 2018-08-01 | 2018-07-23 | G | [10 empty] | 2018-12-28 | 2018-12-28 | 2019-01-22 | 2019-01-22 | G | [5 empty] | 2019-01-24 | 2019-01-24 | 2019-06-14 | 2019-09-12 | R | [10 empty] | 2019-07-02 | 2019-10-22 | 2019-07-30 | 2019-11-07 | R | 2019-07-31 | 2020-03-12 | 2019-12-16 | 2020-04-13 | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.39875
1171 | 110910 | #SMART18 - Parham Rd Pedestrian & Transit Stop Improvements | 9999 | Secondary | Safety | Locally | Henrico County | ASHLAND | Richmond | Richmond:Henrico County | Infrastructure Investment Division | Douglas L Orcutt | Doug.Orcutt@vdot.virginia.gov | (804) 609-5428 | Douglas L Orcutt | Doug.Orcutt@vdot.virginia.gov | (804) 609-5428 | Conner Barnes | BAR136@henrico.us | (804) 501-4617 | 1 | 2018 | 0 | FY2024 | 500000 | 726200 | ACTIVITY DATES SET | G | Determine Requirements milestone finished 495 days early | R | Project estimate is less than $5M and is 20% or more over budget | 2021-07-02 | 2017-07-10 | 2021-09-27 | 2017-11-21 | G | 2021-09-28 | 2018-09-11 | 2021-09-30 | 2018-09-16 | G | 2021-10-01 | 2020-03-09 | 2022-04-13 | 2020-12-04 | G | 2021-04-02 |  | 2021-07-15 |  | G | [5 empty] | 2021-09-13 |  | 2021-10-01 |  | G | 2023-03-22 |  | 2023-09-29 |  | G | 2021-10-05 |  | 2023-03-21 |  | G | 2022-10-14 |  | 2023-06-22 |  | G | [5 empty] | 2023-11-16 |  | 2023-11-16 |  | G | 2024-01-18 |  | 2024-04-17 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.20553
1172 | 111137 | Rectangular Rapid Flashing Beacons - Roanoke City | 9999 | Urban | Safety | Locally | Roanoke | SALEM | Salem | Roanoke:Roanoke City | Infrastructure Investment Division | Cheryl B Becker | Cheryl.Becker@vdot.virginia.gov | (540) 492-2531 | Cheryl B Becker | Cheryl.Becker@vdot.virginia.gov | (540) 492-2531 | Hong Liu | hong.liu@roanokeva.gov | (540) 853-2686 | 0 |  | 0 | FY2022 | 108000 | 32551 | AWARDED | G | Start Delivery milestone finished 232 days early | G | Project is on budget | 2019-07-01 | 2019-07-03 | 2019-10-15 | 2019-11-06 | R | 2019-10-16 | 2019-11-07 | 2019-10-18 | 2019-11-21 | R | 2019-10-22 | 2019-11-22 | 2020-04-30 | 2020-01-27 | G | [35 empty] | 2021-03-15 | 2020-10-06 | 2021-04-09 | 2020-12-02 | G | 2021-04-12 | 2020-12-02 | 2021-08-03 | 2020-12-14 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.28877
1173 | 111727 | I-64 / ROUTE 29 INTERCHANGE IMPROVEMENTS | 0029 | Primary | Safety | VDOT | Albemarle County | CHARLOTTESVILLE | Culpeper | Charlottesville:Albemarle County | Infrastructure Investment Division | Ken Connors |  |  | William E Stowe | William.Stowe@vdot.virginia.gov | (540) 827-7287 |  |  |  | 0 |  | 0 | FY2019 | 1404222 | 2080207 | CONSTRUCTION STARTED | R | Start Delivery milestone finished 34 days late | R | Project estimate is less than $5M and is 20% or more over budget | [5 empty] | 2017-10-12 | 2017-10-12 | 2017-10-26 | 2017-10-26 | G | 2017-10-27 | 2017-10-27 | 2018-10-29 | 2017-10-27 | G | [10 empty] | 2018-11-01 | 2018-11-01 | 2018-11-14 | 2018-11-14 | G | [20 empty] | 2018-10-30 | 2018-10-30 | 2018-11-27 | 2018-11-27 | G | 2019-05-28 | 2019-06-26 | 2019-06-19 | 2019-07-23 | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | DESIGN BUILD/PPTA | 1 | 1 | 0.35752
1174 | 112462 | HOADLY ROAD SIDEWALK | 0642 | Primary | Facilities for Pedestrians and Bicycles | Locally | Prince William County | MANASSAS | Northern Virginia | Northern Virginia:Prince William County | Infrastructure Investment Division | Amir Salahshoor | A.Salahshoor@VDOT.Virginia.gov | (703) 259-1957 | Robert J Strevell | Robert.Strevell@vdot.virginia.gov | (703) 259-1988 | TBD |  |  | 0 |  | 0 | FY2027 | 1800000 | 1800000 | NO DATES SET YET | G | Agreement with Locality milestone is 796 days ahead of the expected completion date | G | Project is on budget | 2022-10-03 |  | 2023-04-28 |  | G | 2023-05-01 |  | 2023-05-31 |  | G | 2023-06-01 |  | 2023-12-29 |  | G | [10 empty] | 2025-01-02 |  | 2025-01-24 |  | G | [5 empty] | 2025-01-28 |  | 2025-11-26 |  | G | [10 empty] | 2025-12-15 |  | 2026-06-30 |  | G | 2026-07-01 |  | 2026-12-31 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.24811
1175 | 113031 | #SGR19VB - RT 743 over Tarrara Creek (Fed 17901) REPLACE | 0743 | Secondary | Bridge Replacement w/o Added Capacity | VDOT | Southampton County | FRANKLIN | Hampton Roads | NonMPO:NonMPO | Infrastructure Investment/Asset Management Division | Mark Wagner |  |  | Jayeshkumar J Patel | Jay.Patel@VDOT.Virginia.gov | (757) 956-3212 |  |  |  | 0 |  | 1 | FY2023 | 3250003 | 3250000 | ACTIVITY DATES SET | G | Engage Public milestone finished 122 days early | G | Project is on budget | [5 empty] | 2018-09-17 | 2018-09-17 | 2018-09-28 | 2018-09-28 | G | 2018-10-01 | 2018-10-16 | 2019-08-28 | 2019-08-26 | G | [5 empty] | 2020-07-17 | 2020-03-19 | 2020-07-30 | 2020-03-30 | G | 2021-09-30 |  | 2021-10-13 |  | G | 2022-03-16 |  | 2022-09-16 |  | G | 2021-10-29 |  | 2022-05-10 |  | G | 2018-11-28 | 2018-11-28 | 2022-06-16 |  | G | [5 empty] | 2022-10-11 |  | 2022-10-11 |  | G | 2023-01-06 |  | 2023-01-06 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.13712
1176 | 113138 | Roanoke River Greenway Bridge the Gap Phase II Segment 2 | 0000 | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Roanoke | SALEM | Salem | Roanoke:Roanoke City | Local Assistance Division | Cheryl B Becker | Cheryl.Becker@vdot.virginia.gov | (540) 492-2531 | Cheryl B Becker | Cheryl.Becker@vdot.virginia.gov | (540) 492-2531 | Luke Pugh | Luke.Pugh@RoanokeVa.gov | (540) 853-5208 | 0 |  | 0 | FY2022 | 7985173 | 7985173 | NO DATES SET YET-PE OPEN | R | Determine Requirements milestone is 570 days past the expected completion date | G | Project is on budget | 2018-08-01 | 2018-08-01 | 2018-10-25 | 2018-11-27 | R | 2018-10-26 | 2018-11-28 | 2018-10-30 | 2018-11-28 | R | 2018-10-31 | 2018-11-29 | 2019-08-01 |  | R | [10 empty] | 2020-08-04 |  | 2020-08-24 |  | R | [5 empty] | 2020-08-26 |  | 2021-06-09 |  | G | [10 empty] | 2021-06-10 |  | 2021-07-08 |  | G | 2021-12-03 |  | 2021-12-03 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.47462
1177 | 113326 | PHASE IV - RTE 163 (FIFTH STREET) - RECONSTRUCTION | 0163 | Urban | Reconstruction w/o Added Capacity | Locally | Lynchburg | APPOMATTOX | Lynchburg | Lynchburg:Lynchburg | Local Assistance Division | Gregg Allen | Gregg.Allen@vdot.virginia.gov | (434) 426-5575 | Gregg Allen | Gregg.Allen@vdot.virginia.gov | (434) 426-5575 | Lee Newland | lee.newland@lynchburgva.gov | (434) 455-3947 | 0 |  | 0 | FY2023 | 7100000 | 7100000 | NO DATES SET YET-PE OPEN | R | Determine Requirements milestone is 110 days past the expected completion date | G | Project is on budget | 2020-01-31 | 2019-07-01 | 2020-04-24 | 2019-08-09 | G | 2020-04-27 | 2020-04-27 | 2020-04-29 | 2020-04-29 | G | 2020-04-30 | 2020-04-30 | 2020-11-03 |  | R | [10 empty] | 2021-11-05 |  | 2021-11-30 |  | G | [5 empty] | 2021-12-02 |  | 2022-09-12 |  | G | 2020-12-14 | 2020-01-31 | 2021-08-17 | 2020-01-31 | G | [5 empty] | 2022-09-28 |  | 2022-10-26 |  | G | 2023-01-23 |  | 2023-01-23 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.12338
1178 | 113447 | CANAL WALK (CAP TRAIL CONN) PH I |  | Primary | Facilities for Pedestrians and Bicycles | Locally | Richmond | ASHLAND | Richmond | Richmond:Richmond | Local Assistance Division | Jorg Huckabee-Mayfield | Jorg.Huckabee-Mayfield@VDOT.Virginia.gov | (804) 609-5292 | Jorg Huckabee-Mayfield | Jorg.Huckabee-Mayfield@VDOT.Virginia.gov | (804) 609-5292 | Yongping Wang | Yongping.Wang@Richmondgov.com | (804) 646-2467 | 0 |  | 0 | FY2024 | 487000 | 487000 | NO DATES SET YET-PE OPEN | Y | Determine Requirements milestone is 18 days ahead of the expected completion date and there is a risk of missing this milestone date | G | Project is on budget | 2019-10-02 | 2019-10-02 | 2020-02-14 | 2019-10-25 | G | 2020-02-25 | 2019-09-11 | 2020-03-09 | 2019-09-11 | G | 2020-08-28 |  | 2021-03-11 |  | Y | [10 empty] | 2022-03-15 |  | 2022-04-04 |  | G | [5 empty] | 2022-04-06 |  | 2023-01-18 |  | G | 2020-11-09 |  | 2021-07-16 |  | G | [5 empty] | 2023-02-03 |  | 2023-03-03 |  | G | 2023-08-16 |  | 2023-08-16 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.21491
1179 | 113946 | Project to install Pedestrian crossing at Daniels Creek Rd. | 0220 | Primary | Safety | VDOT | Henry County | MARTINSVILLE | Salem | NonMPO:NonMPO | Infrastructure Investment Division | Craig S Moore | Craig.Moore@vdot.virginia.gov | (540) 375-3556 | Mark C Mckissick | Mark.McKissick@VDOT.Virginia.gov | (540) 375-9416 |  |  |  | 0 |  | 0 | FY2025 | 130000 | 130000 | NO DATES SET YET | G | Start Development milestone is 509 days ahead of the expected completion date | G | Project is on budget | [5 empty] | 2022-07-01 |  | 2022-07-15 |  | G | 2022-07-18 |  | 2023-03-14 |  | G | [5 empty] | 2023-11-15 |  | 2023-12-29 |  | G | [5 empty] | 2024-04-17 |  | 2024-08-08 |  | G | [5 empty] | 2024-04-02 |  | 2024-07-02 |  | G | [5 empty] | 2024-08-13 |  | 2024-08-13 |  | G | 2024-11-04 |  | 2024-11-04 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.066321
1180 | 114241 | HISTORIC GORDONSVILLE DEPOT - C503 EXTERIOR RESTORATION | 9999 | Enhancement | Rehabilitation of Historic Bldgs/Facilities | Locally | Gordonsville | LOUISA | Culpeper | NonMPO:NonMPO | Local Assistance Division | Ken Connors |  |  | John P Price | John.Price@VDOT.Virginia.gov | (540) 347-6371 | Debbie Kendall | dkendall@gordonsville.org | (540) 832-2233 | 0 |  | 0 | FY2021 | 312360 | 407952 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 64 days early | R | Project estimate is less than $5M and is 20% or more over budget | 2018-09-04 | 2000-01-03 | 2018-11-30 | 2000-02-25 | G | 2018-12-03 | 2000-02-25 | 2018-12-05 | 2000-02-25 | G | 2018-12-06 | 2000-02-01 | 2019-06-13 | 2019-06-12 | G | [25 empty] | 2019-07-05 | 2019-07-05 | 2020-03-12 | 2019-07-05 | G | [5 empty] | 2020-04-24 | 2019-08-01 | 2020-05-21 | 2019-09-24 | G | 2020-08-11 | 2020-06-18 | 2020-09-22 | 2020-07-20 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.19855
1181 | 114828 | ROUTE 50 CORRIDOR IMPROVEMENTS - LOUDOUN & FAIRFAX | 0050 | Primary | Traffic Management/Engineering | VDOT | Multi-jurisdictional: Northern Virginia MPO |  | Northern Virginia | Northern Virginia:Multi-jurisdictional: Northern Virginia MPO | Infrastructure Investment Division | Kimberly Mccool | Kimberly.McCool@vdot.virginia.gov | (703) 259-3220 | William C Britt | Calvin.Britt@VDOT.Virginia.gov | (703) 259-2961 |  |  |  | 0 |  | 0 | FY2024 | 5730992 | 5730992 | NO DATES SET YET-PE OPEN | R | Determine Requirements milestone is 346 days past the expected completion date | Y | Estimate not current | 2019-07-01 | 2019-07-01 | 2020-01-08 | 2020-07-29 | R | 2019-04-01 | 2019-04-01 | 2019-04-12 | 2019-04-03 | G | 2019-04-15 | 2020-02-12 | 2020-03-12 |  | R | [5 empty] | 2021-01-14 |  | 2021-01-29 |  | R | 2022-05-05 |  | 2022-05-18 |  | G | 2022-10-11 |  | 2023-04-21 |  | G | 2022-06-06 |  | 2022-12-12 |  | G | 2021-10-19 |  | 2022-04-28 |  | G | [5 empty] | 2023-05-09 |  | 2023-05-09 |  | G | 2023-07-31 |  | 2023-07-31 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.14544
1182 | 115783 | Rivermont Road Sidewalk | 0726 | Secondary | Facilities for Pedestrians and Bicycles | Locally | Chesterfield County | CHESTERFIELD | Richmond | Tri-Cities:Chesterfield County | Infrastructure Investment Division | Michael S Gray | Mike.Gray@vdot.virginia.gov | (804) 609-5347 | Michael S Gray | Mike.Gray@vdot.virginia.gov | (804) 609-5347 | Barb Smith |  |  | 0 |  | 0 | FY2026 | 1152000 | 1152000 | NO DATES SET YET | G | Agreement with Locality milestone is 582 days ahead of the expected completion date | G | Project is on budget | 2022-07-01 |  | 2022-09-26 |  | G | 2022-09-27 |  | 2022-10-18 |  | G | 2022-10-19 |  | 2023-08-31 |  | G | [10 empty] | 2024-08-02 |  | 2024-08-22 |  | G | 2025-07-01 |  | 2026-01-15 |  | G | 2024-09-10 |  | 2025-06-30 |  | G | 2023-06-06 |  | 2024-02-12 |  | G | [5 empty] | 2026-02-11 |  | 2026-03-18 |  | G | 2026-06-05 |  | 2026-06-05 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 |  | 0 | 1 | 0.28825
1183 | 116484 | DISTRICT-WIDE HIGH VISIBILITY BACKPLATES | 9999 | Primary | Safety | VDOT | Fredericksburg District-wide |  | Fredericksburg | Fredericksburg:Fredericksburg District-wide | Infrastructure Investment/Asset Management Division | Peter A Hedrich | Peter.Hedrich@vdot.virginia.gov | (540) 899-4540 | Benjamin Ernst | Benjamin.Ernst@vdot.virginia.gov | (571) 585-0902 |  |  |  | 0 |  | 0 | FY2020 | 1503417 | 1503417 | CONSTRUCTION STARTED | G | Start Delivery milestone finished on-time | G | Project is on budget | [10 empty] | 2019-12-02 | 2019-12-02 | 2020-04-10 | 2020-01-24 | G | [35 empty] | 2020-02-27 | 2020-02-27 | 2020-02-27 | 2020-02-27 | G | 2020-02-27 | 2020-02-27 | 2020-02-27 | 2020-02-27 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | WORK/TASK ORDER | 1 | 0 | 0.07053
1184 | 117117 | Independence Blvd/Columbus St Pedestrian Improvements |  | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Virginia Beach | NORFOLK | Hampton Roads | Hampton Roads:Virginia Beach | Local Assistance Division | Susan Wilson | Susan.Wilson@vdot.virginia.gov | (757) 956-3099 | Marci Thompson | Marci.Thompson@vdot.virginia.gov | (757) 956-3093 | Katie Shannon | kshannon@vbgov.com | (757) 385-1514 | 0 |  | 0 | FY2023 | 511385 | 511385 | NO DATES SET YET | G | Agreement with Locality milestone is 80 days ahead of the expected completion date | G | Project is on budget | 2021-01-04 |  | 2021-05-12 |  | G | 2021-05-13 |  | 2021-06-03 |  | G | 2021-12-13 |  | 2022-04-08 |  | G | [25 empty] | 2021-12-28 |  | 2022-03-25 |  | G | [5 empty] | 2022-05-23 |  | 2022-06-20 |  | G | 2022-09-08 |  | 2022-09-08 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.27468
1185 | 117622 | LEASE COMMUTER PARKING SPACES AT LOWES ISLAND FY'21 - FY'23 | 9999 | Secondary | Other | Locally | Loudoun County | LEESBURG | Northern Virginia | Northern Virginia:Loudoun County | Infrastructure Investment Division | Kimberly Mccool | Kimberly.McCool@vdot.virginia.gov | (703) 259-3220 | Rahul A Trivedi | Rahul.Trivedi@VDOT.Virginia.gov | (703) 259-2308 | Nancy Gourley |  | (703) 737-8384 | 0 |  | 0 | FY2022 | 115000 | 115000 | NO DATES SET YET | G | Agreement with Locality milestone is 402 days ahead of the expected completion date | G | Project is on budget | 2022-01-03 |  | 2022-03-30 |  | G | [5 empty] | 2022-03-31 |  | 2022-03-31 |  | G | [35 empty] | 2022-04-15 |  | 2022-05-12 |  | G | 2022-05-13 |  | 2022-06-23 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.3024
1186 | 118314 | EAST ST NE AND CHURCH STREET NE MINI ROUNDABOUT | 9999 | Urban | Traffic Management/Engineering | Locally | Vienna | FAIRFAX | Northern Virginia | Northern Virginia:Vienna | Local Assistance Division | Andrew G Beacher | Andrew.Beacher@vdot.virginia.gov | (703) 259-2239 | Amir Salahshoor | A.Salahshoor@VDOT.Virginia.gov | (703) 259-1957 | Michael Gallagher | mgallagher@viennava.gov | (703) 255-6389 | 0 |  | 0 | FY2029 | 550000 | 550000 | NO DATES SET YET | G | Agreement with Locality milestone is 1354 days ahead of the expected completion date | G | Project is on budget | 2024-07-01 |  | 2024-11-06 |  | G | 2024-11-07 |  | 2024-12-02 |  | G | 2025-06-11 |  | 2025-10-02 |  | G | [10 empty] | 2027-01-29 |  | 2027-03-05 |  | G | [5 empty] | 2027-03-08 |  | 2027-08-31 |  | G | 2028-05-08 |  | 2028-10-04 |  | G | [5 empty] | 2027-12-08 |  | 2028-05-03 |  | G | 2028-07-24 |  | 2029-01-04 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.22672
1187 | 104947 | #HB2.FY17 RTE 501- SHOULDER WIDENING - RTE 607 TO RTE 655 | 0501 | Primary | Safety | VDOT | Campbell County | APPOMATTOX | Lynchburg | NonMPO:NonMPO | Infrastructure Investment Division | Renard Yeatts |  |  | Lindsey S Hodges | Lindsey.Hodges@vdot.virginia.gov | (434) 856-8143 |  |  |  | 1 | 2017 | 0 | FY2020 | 2271487 | 2271487 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 56 days early | G | Project is on budget | [5 empty] | 2013-07-01 | 2013-07-03 | 2013-07-01 | 2013-07-03 | R | 2014-05-21 | 2014-05-21 | 2017-09-25 | 2017-05-26 | G | 2018-02-08 | 2018-02-08 | 2018-04-23 | 2018-04-20 | G | [5 empty] | 2018-09-26 | 2018-08-14 | 2018-10-25 | 2018-08-20 | G | 2019-06-06 | 2019-05-15 | 2019-12-05 | 2019-12-03 | G | 2018-11-27 | 2018-09-05 | 2019-06-05 | 2019-05-14 | G | [10 empty] | 2019-12-18 | 2019-12-10 | 2020-01-14 | 2019-12-10 | G | 2020-03-26 | 2020-02-27 | 2020-04-23 | 2020-02-27 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.099647
1188 | 107081 | RTE 250 - CONSTRUCT ROUNDABOUT | 0250 | Primary | Safety | VDOT | Goochland County | ASHLAND | Richmond | NonMPO:NonMPO | Infrastructure Investment Division | Roy Soto | Roy.Soto@vdot.virginia.gov | (804) 609-5239 | Roy Soto | Roy.Soto@vdot.virginia.gov | (804) 609-5239 |  |  |  | 0 |  | 0 | FY2022 | 2624801 | 3133270 | ACTIVITY DATES SET | R | Complete Purchasing Right-of-Way milestone finished 152 days late | Y | Project estimate is less than $5M and is up to 20% over budget | [5 empty] | 2016-09-23 | 2016-09-23 | 2016-10-03 | 2016-10-03 | G | 2016-10-04 | 2016-10-04 | 2018-06-13 | 2018-06-11 | G | [5 empty] | 2018-10-11 | 2018-10-11 | 2018-11-01 | 2018-11-01 | G | 2019-11-25 | 2019-12-19 | 2020-01-16 | 2020-01-10 | G | 2020-09-08 | 2020-08-18 | 2021-03-19 | 2020-12-17 | G | 2020-02-05 | 2020-02-06 | 2020-08-07 | 2021-01-06 | R | 2019-03-15 | 2019-03-14 | 2019-09-17 | 2019-03-14 | G | [5 empty] | 2021-06-08 |  | 2021-06-08 |  | G | 2021-07-23 |  | 2021-10-25 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.060993
1189 | 108722 | Hogan Drive Ph 2 |  | Urban | New Construction Roadway | Locally | Newport News | WILLIAMSBURG | Hampton Roads | Hampton Roads:Newport News | Local Assistance Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Chessica Villaflores | Chessica.Villaflores@vdot.virginia.gov | (757) 956-3094 | Everett Skipper, Director of Engineering |  |  | 0 |  | 0 | FY2022 | 16744551 | 11732456 | AWARDED | G | Solicit Bids milestone finished 153 days early | G | Project is on budget | 2018-11-01 | 2017-11-15 | 2019-02-01 | 2017-11-15 | G | 2019-02-04 | 2017-11-15 | 2019-02-15 | 2017-11-15 | G | 2019-02-19 | 2017-11-16 | 2020-02-19 | 2020-02-07 | G | [10 empty] | 2020-04-30 | 2020-04-30 | 2020-05-20 | 2020-05-19 | G | [5 empty] | 2020-06-12 | 2020-06-11 | 2021-01-21 | 2020-06-11 | G | [10 empty] | 2021-02-08 | 2020-09-18 | 2021-04-05 | 2020-11-03 | G | 2021-04-06 |  | 2021-09-23 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.32792
1190 | 114719 | COURTHOUSE ROAD PEDESTRIAN CROSSING IMPROVEMENTS | 0208 | Primary | Safety | VDOT | Spotsylvania County | FREDERICKSBURG | Fredericksburg | Fredericksburg:Spotsylvania County | Infrastructure Investment Division | Ronnie Hobson | Ron.Hobson@vdot.virginia.gov | (804) 840-5501 | Ronnie Hobson | Ron.Hobson@vdot.virginia.gov | (804) 840-5501 |  |  |  | 0 |  | 0 | FY2020 | 450000 | 450000 | CONSTRUCTION COMPLETED | R | Start Delivery milestone finished 44 days late | G | Project is on budget | [5 empty] | 2019-01-02 | 2019-02-19 | 2019-01-02 | 2019-02-19 | R | 2019-01-03 | 2019-02-19 | 2019-04-15 | 2019-03-04 | G | [5 empty] | 2019-06-11 | 2019-03-18 | 2019-06-24 | 2019-03-18 | G | [25 empty] | 2019-07-11 | 2019-07-19 | 2019-07-17 | 2019-07-19 | R | 2019-07-18 | 2019-07-21 | 2019-07-24 | 2019-09-06 | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | WORK/TASK ORDER | 1 | 0 | 0.062976
1191 | 115488 | #SMART20 RTE 29 - INTERSECTION IMPROVEMENTS AT RTE 699 | 0029 | Primary | Safety | VDOT | Campbell County | APPOMATTOX | Lynchburg | NonMPO:NonMPO | Infrastructure Investment Division | Robert F Guercia | Robert.Guercia@VDOT.Virginia.gov | (434) 841-6864 | Brian J Casto | Brian.Casto@VDOT.Virginia.gov | (434) 856-8276 |  |  |  | 1 | 2020 | 0 | FY2025 | 3086810 | 3086810 | NO DATES SET YET | G | Start Development milestone is 66 days ahead of the expected completion date | G | Project is on budget | [5 empty] | 2021-04-15 |  | 2021-04-28 |  | G | 2021-04-29 |  | 2021-12-17 |  | G | [5 empty] | 2022-09-15 |  | 2022-09-28 |  | G | 2024-01-05 |  | 2024-01-22 |  | G | 2024-08-09 |  | 2025-02-20 |  | G | 2024-02-07 |  | 2024-08-09 |  | G | [10 empty] | 2025-03-11 |  | 2025-03-11 |  | G | 2025-05-30 |  | 2025-05-30 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.10036
1192 | 116004 | District-wide High Visibility Backplates Installations | 9999 | Miscellaneous | Safety | VDOT | Culpeper District-wide |  | Culpeper | NonMPO:NonMPO | Infrastructure Investment/Asset Management Division | Gregory J Cooley | Gregory.Cooley@vdot.virginia.gov | (434) 906-7979 | Caroline Awua-Mensah | Caroline.Awua-Mensah@vdot.virginia.gov | (540) 829-7618 |  |  |  | 0 |  | 0 | FY2021 | 660592 | 660592 | CONSTRUCTION STARTED | G | Start Delivery milestone finished on-time | G | Project is on budget | [5 empty] | 2020-06-04 | 2019-11-15 | 2020-06-23 | 2019-11-18 | G | 2020-06-24 | 2019-11-19 | 2021-03-17 | 2020-03-23 | G | [5 empty] | 2020-04-08 | 2020-04-08 | 2020-04-08 | 2020-04-08 | G | [25 empty] | 2020-07-02 | 2020-07-02 | 2020-07-02 | 2020-07-02 | G | 2020-07-12 | 2020-07-12 | 2020-07-12 | 2020-07-12 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | WORK/TASK ORDER | 1 | 0 | 0.10428
1193 | 116885 | EAST WASHINGTON STREET - MILLING, PAVEMENT & RECONSTRUCTION | 9999 | Urban | Resurfacing | Locally | Orange | LOUISA | Culpeper | NonMPO:NonMPO | Local Assistance Division | Gregory J Cooley | Gregory.Cooley@vdot.virginia.gov | (434) 906-7979 | John P Price | John.Price@VDOT.Virginia.gov | (540) 347-6371 | John Cooley | townplanner@townoforangeva.org | (540) 672-6917 | 0 |  | 0 | FY2023 | 27308 | 27308 | NO DATES SET YET | G | Agreement with Locality milestone is 326 days ahead of the expected completion date | G | Project is on budget | 2021-09-01 |  | 2022-01-13 |  | G | [5 empty] | 2022-01-18 |  | 2022-01-31 |  | G | [25 empty] | 2021-09-30 |  | 2022-03-08 |  | G | [5 empty] | 2022-05-04 |  | 2022-06-01 |  | G | 2022-08-19 |  | 2022-08-19 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.047856
1194 | 117131 | Tidewater Drive Sidewalk at I-64 | 0168 | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Norfolk | NORFOLK | Hampton Roads | Hampton Roads:Norfolk | Local Assistance Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Derrick Williams | Derrick.Williams@vdot.virginia.gov | (757) 956-3097 | Deborah Mangiaracina | Deborah.Mangiaracina@norfolk.gov | (757) 664-7305 | 0 |  | 0 | FY2024 | 2142700 | 2142700 | NO DATES SET YET | G | Agreement with Locality milestone is 80 days ahead of the expected completion date | G | Project is on budget | 2021-01-04 |  | 2021-05-12 |  | G | 2021-05-13 |  | 2021-06-07 |  | G | 2021-12-02 |  | 2022-03-30 |  | G | [10 empty] | 2023-05-04 |  | 2023-06-12 |  | G | [5 empty] | 2023-06-13 |  | 2023-11-09 |  | G | 2023-08-31 |  | 2024-02-06 |  | G | [5 empty] | 2024-01-16 |  | 2024-02-12 |  | G | 2024-05-01 |  | 2024-05-01 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.40738
1195 | 117623 | PURCHASE AND IMPLEMENT DASH SCHEDULING SOFTWARE UPGRADES | 9999 | Public Transportation | Transit | Locally | Alexandria | FAIRFAX | Northern Virginia | Northern Virginia:Alexandria | Infrastructure Investment Division | Terry Yates | Terry.Yates@vdot.virginia.gov | (703) 259-2118 | Susie X Lue | Susie.Lue@vdot.virginia.gov | (703) 259-2918 | Evan Davis | Evan.Davis@alexandriava.gov | (703) 746-5643 | 0 |  | 0 | FY2024 | 477568 | 477568 | NO DATES SET YET-PE OPEN | G | Start Development milestone finished 39 days early | G | Project is on budget | 2020-08-03 | 2020-06-26 | 2021-02-19 | 2020-12-23 | G | 2021-02-23 | 2021-01-15 | 2021-03-15 | 2021-02-04 | G | 2021-09-17 |  | 2022-01-18 |  | G | [25 empty] | 2023-04-10 |  | 2023-09-06 |  | G | [5 empty] | 2023-08-09 |  | 2023-12-05 |  | G | 2024-02-28 |  | 2024-06-19 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.17769
1196 | 96739 | Bridge Rehabilitation Rt. 17 over S Railway and Rt. 805 | 0017 | Primary | Bridge Rehab w/o Added Capacity | VDOT | Fauquier County | WARRENTON | Culpeper | NonMPO:NonMPO | Infrastructure Investment Division | Ken Connors |  |  | Howard M Tomlinson | Howard.Tomlinson@VDOT.virginia.gov | (540) 829-7436 |  |  |  | 0 |  | 0 | FY2022 | 3848386 | 7170922 | ADVERTISED | G | Solicit Bids milestone finished 104 days early | R | Project estimate is less than $5M and is 20% or more over budget | [5 empty] | 2011-04-30 | 2011-06-21 | 2011-04-30 | 2011-06-22 | R | 2013-03-07 | 2011-06-23 | 2025-01-01 | 2018-01-03 | G | [5 empty] | 2016-01-15 | 2016-01-15 | 2026-12-07 | 2019-10-28 | G | 2019-11-01 | 2019-11-01 | 2019-11-15 | 2019-11-15 | G | 2019-11-20 | 2019-11-20 | 2021-01-19 | 2019-11-20 | G | 2019-11-20 | 2019-11-20 | 2020-04-29 | 2019-11-20 | G | [10 empty] | 2021-04-26 | 2021-01-12 | 2021-04-26 | 2021-01-12 | G | 2021-05-06 |  | 2021-07-09 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.14687
1197 | 106928 | GALLOWS ROAD WALKWAY | 0650 | Primary | Facilities for Pedestrians and Bicycles | Locally | Fairfax County | FAIRFAX | Northern Virginia | Northern Virginia:Fairfax County | Infrastructure Investment Division | Amir Salahshoor | A.Salahshoor@VDOT.Virginia.gov | (703) 259-1957 | Rita Hockman | Rita.Hockman@vdot.virginia.gov | (804) 824-7421 | Brook Khorashadi | Fereshteh.khorashadi@fairfaxco | (703) 877-5737 | 0 |  | 0 | FY2019 | 525000 | 545000 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 388 days early | Y | Project estimate is less than $5M and is up to 20% over budget | [10 empty] | 2015-03-03 | 2015-03-03 | 2015-03-04 | 2015-03-04 | G | [10 empty] | 2015-08-24 | 2015-08-24 | 2015-08-24 | 2015-08-24 | G | [5 empty] | 2016-04-27 | 2016-04-27 | 2016-10-31 | 2016-10-31 | G | [10 empty] | 2018-10-01 | 2017-09-15 | 2018-10-01 | 2017-09-15 | G | 2018-11-15 | 2017-11-14 | 2018-12-07 | 2017-11-14 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.078271
1198 | 108640 | Richmond Henrico Tpke. construct sidewalk | 9999 | Secondary | Facilities for Pedestrians and Bicycles | Locally | Henrico County | ASHLAND | Richmond | Richmond:Henrico County | Local Assistance Division | Brian J Lokker | Brian.Lokker@VDOT.Virginia.gov | (804) 524-6010 | Brian J Lokker | Brian.Lokker@VDOT.Virginia.gov | (804) 524-6010 | Paul Smith | smi91@henrico.us | (804) 501-5092 | 0 |  | 0 | FY2020 | 400000 | 400000 | AWARDED | R | Start Delivery milestone finished 6 days late | G | Project is on budget | 2017-05-30 | 2016-07-25 | 2017-08-22 | 2016-10-18 | G | 2017-08-23 | 2016-10-21 | 2017-08-25 | 2016-10-27 | G | 2017-08-28 | 2017-09-01 | 2018-03-09 | 2018-02-09 | G | [10 empty] | 2019-03-11 | 2018-02-16 | 2019-03-29 | 2018-02-20 | G | [5 empty] | 2019-04-02 | 2018-02-21 | 2020-01-10 | 2019-06-26 | G | [10 empty] | 2020-01-30 | 2020-02-07 | 2020-02-27 | 2020-02-07 | G | 2020-02-28 | 2020-02-10 | 2020-04-08 | 2020-04-14 | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.34698
1199 | 110766 | #SMART18 - RTE 45 - CONSTRUCT ROUNDABOUT AT RTE 690 | 0045 | Primary | Reconstruction w/ Added Capacity | VDOT | Cumberland County | DILLWYN | Lynchburg | NonMPO:NonMPO | Infrastructure Investment Division | Brian J Casto | Brian.Casto@VDOT.Virginia.gov | (434) 856-8276 | Daniel J Brown | Daniel.Brown@VDOT.Virginia.gov | (434) 856-8265 |  |  |  | 1 | 2018 | 0 | FY2024 | 3526388 | 3526388 | ACTIVITY DATES SET | R | Determine Requirements milestone finished 130 days late | G | Project is on budget | [5 empty] | 2019-07-15 | 2019-06-25 | 2019-07-26 | 2019-07-03 | G | 2019-07-29 | 2019-07-05 | 2020-04-17 | 2020-08-25 | R | [5 empty] | 2021-07-19 |  | 2021-07-30 |  | G | 2022-06-24 |  | 2022-07-08 |  | G | 2023-07-13 |  | 2024-02-06 |  | G | 2022-07-26 |  | 2023-07-12 |  | G | [10 empty] | 2023-10-10 |  | 2023-10-10 |  | G | 2023-11-29 |  | 2024-04-09 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.1098
1200 | 110836 | SYSTEMIC IMPROVEMENTS TO COUNTER ROADWAY DEPARTURE CRASHES | 9999 | Miscellaneous | Safety | VDOT | Richmond District-wide |  | Richmond | Richmond:Richmond District-wide | Infrastructure Investment Division | Adam S Brooks | Adam.Brooks@VDOT.Virginia.gov | (804) 609-5274 | Adam S Brooks | Adam.Brooks@VDOT.Virginia.gov | (804) 609-5274 |  |  |  | 0 |  | 0 | FY2027 | 3570000 | 3570000 | NO DATES SET YET | G | Start Development milestone is 661 days ahead of the expected completion date | G | Project is on budget | [5 empty] | 2022-12-01 |  | 2022-12-14 |  | G | 2022-12-15 |  | 2023-11-09 |  | G | [5 empty] | 2024-09-16 |  | 2024-09-27 |  | G | 2026-01-08 |  | 2026-01-23 |  | G | 2026-06-17 |  | 2026-12-23 |  | G | 2026-02-10 |  | 2026-08-13 |  | G | 2025-06-24 |  | 2025-12-31 |  | G | [5 empty] | 2027-01-12 |  | 2027-01-12 |  | G | 2027-03-08 |  | 2027-03-26 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.069703
1201 | 111460 | RTE 2 - RECONSTRUCTION - DIXON STREET / SR 2/17 | 0002 | Urban | Reconstruction w/o Added Capacity | Locally | Fredericksburg | FREDERICKSBURG | Fredericksburg | NonMPO:NonMPO | Infrastructure Investment Division | Richard A Spurlock | Richard.Spurlock@VDOT.Virginia.gov | (540) 899-4302 | Richard A Spurlock | Richard.Spurlock@VDOT.Virginia.gov | (540) 899-4302 | Erik Nelson | enelson@fredericksburgva.gov | (540) 372-1080 | 0 |  | 0 | FY2019 | 190808 | 190808 | PROJECT CLOSEOUT COMPLETE | G | Start Delivery milestone finished 214 days early | G | Project is on budget | 2017-08-04 | 2017-06-02 | 2017-10-30 | 2017-07-21 | G | [5 empty] | 2017-08-04 | 2017-06-02 | 2017-08-17 | 2017-09-18 | R | [35 empty] | 2018-04-03 | 2018-03-30 | 2018-06-26 | 2018-03-30 | G | 2018-08-09 | 2018-04-02 | 2018-11-02 | 2018-04-02 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.07914
1202 | 111710 | #SMART18 - Route 13 Industrial Park Traffic Light | 0013 | Primary | Safety | VDOT | Accomack County | ACCOMAC | Hampton Roads | NonMPO:NonMPO | Infrastructure Investment Division | Peter G Reilly | Peter.Reilly@vdot.virginia.gov | (757) 858-6748 | John K Arms | John.Arms@vdot.virginia.gov | (757) 995-5156 | Rich Morrison | rmorrison@co.accomack.va.us | (757) 787-5726 | 1 | 2018 | 0 | FY2021 | 846676 | 1003676 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 84 days early | Y | Project estimate is less than $5M and is up to 20% over budget | [5 empty] | 2017-09-01 | 2017-08-25 | 2017-09-15 | 2017-08-25 | G | 2017-09-18 | 2017-09-18 | 2018-01-17 | 2018-01-17 | G | [5 empty] | 2018-08-08 | 2018-06-14 | 2018-08-21 | 2018-07-17 | G | 2019-05-13 | 2018-10-25 | 2019-06-13 | 2019-05-31 | G | 2020-01-10 | 2019-09-13 | 2020-05-11 | 2020-01-16 | G | 2019-07-30 | 2019-07-23 | 2020-02-07 | 2019-09-12 | G | 2018-10-25 | 2018-10-25 | 2019-05-06 | 2018-10-25 | G | [5 empty] | 2020-05-12 | 2020-02-11 | 2020-05-12 | 2020-02-11 | G | 2020-06-26 | 2020-05-29 | 2020-08-21 | 2020-05-29 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.093355
1203 | 111913 | GEORGETOWN PIKE TRAIL - PHASE III C502 FALLS BRIDGE LANE |  | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Fairfax County | FAIRFAX | Northern Virginia | Northern Virginia:Fairfax County | Local Assistance Division | Amir Salahshoor | A.Salahshoor@VDOT.Virginia.gov | (703) 259-1957 | Rita Hockman | Rita.Hockman@vdot.virginia.gov | (804) 824-7421 | John Dresser, PE | john.dresser@fairfaxcounty.gov | (703) 877-5812 | 0 |  | 0 | FY2020 | 300000 | 199048 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 197 days early | G | Project is on budget | 2018-02-01 | 2017-07-14 | 2018-04-26 | 2017-07-17 | G | 2018-04-27 | 2017-07-18 | 2018-05-01 | 2017-07-20 | G | 2018-05-02 | 2017-07-21 | 2018-11-05 | 2018-01-31 | G | [10 empty] | 2018-02-13 | 2018-02-13 | 2018-03-06 | 2018-03-14 | R | [5 empty] | 2018-03-08 | 2018-05-07 | 2019-03-22 | 2018-06-14 | G | [10 empty] | 2019-06-19 | 2018-09-24 | 2019-11-06 | 2018-11-13 | G | 2019-11-07 | 2019-06-03 | 2019-12-20 | 2019-06-06 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.25295
1204 | 113136 | Hickok Street Improvements | 0000 | Urban | Mitigation of Water Pollution Due to Highway Runof | Locally | Christiansburg | CHRISTIANSBURG | Salem | New River Valley:Christiansburg | Local Assistance Division | Adam J Czesnowski | Adam.Czesnowski@vdot.virginia.gov | (540) 541-1216 | Adam J Czesnowski | Adam.Czesnowski@vdot.virginia.gov | (540) 541-1216 | Wayne Nelson | wnelson@christiansburg.org | (540) 382-6120 | 0 |  | 0 | FY2022 | 2987445 | 2987445 | ACTIVITY DATES SET | G | Start Purchasing Right-of-Way milestone finished 4 days early | G | Project is on budget | 2018-08-01 | 2018-08-01 | 2018-10-25 | 2019-01-07 | R | 2018-10-26 | 2019-01-07 | 2018-10-30 | 2019-01-07 | R | 2018-10-31 | 2019-01-29 | 2019-08-01 | 2019-08-01 | G | [10 empty] | 2020-08-04 | 2020-08-20 | 2020-08-24 | 2020-08-20 | G | [5 empty] | 2020-08-26 | 2020-08-21 | 2021-07-20 |  | G | [10 empty] | 2021-07-21 |  | 2021-08-17 |  | G | 2022-01-18 |  | 2022-01-18 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.097313
1205 | 113290 | #SGRLB RTE 360(HULL ST)-REPLACE BRIDGE OVER MANCHESTER CANAL |  | Primary | Bridge Replacement w/o Added Capacity | Locally | Richmond | ASHLAND | Richmond | Richmond:Richmond | Local Assistance Division | James Shepherd | James.Shepherd@vdot.virginia.gov | (804) 609-5305 | James Shepherd | James.Shepherd@vdot.virginia.gov | (804) 609-5305 | Thomas Westbrook | Thomas.Westbrook@richmondgov.com | (804) 646-3421 | 0 |  | 0 | FY2022 | 5004000 | 5004000 | NO DATES SET YET-PE OPEN | R | Determine Requirements milestone is 237 days past the expected completion date | G | Project is on budget | 2019-07-02 | 2019-07-02 | 2019-12-02 | 2019-11-19 | G | 2019-12-03 | 2019-11-20 | 2019-12-20 | 2019-12-18 | G | 2019-12-26 |  | 2020-06-29 |  | R | [25 empty] | 2020-05-18 |  | 2021-01-25 |  | R | [5 empty] | 2021-11-01 |  | 2021-11-30 |  | G | 2022-01-03 |  | 2022-01-31 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.15063
1206 | 113390 | #SGR19VB - REPLACE SUPERSTRUCTURE FORT LEE ROAD OVER I-85 | 0000 | Urban | Bridge Rehab w/o Added Capacity | VDOT | Petersburg | PETERSBURG | Richmond | Tri-Cities:Petersburg | Infrastructure Investment/Asset Management Division | Thomas Kendrick | Thomas.Kendrick@vdot.virginia.gov | (804) 609-5281 | Thomas Kendrick | Thomas.Kendrick@vdot.virginia.gov | (804) 609-5281 |  |  |  | 0 |  | 0 | FY2026 | 4000000 | 4000000 | NO DATES SET YET-PE OPEN | G | Obtained Permits milestone finished 2367 days early | G | Project is on budget | [5 empty] | 2021-09-01 | 2018-10-18 | 2021-09-15 | 2018-10-23 | G | 2021-09-16 | 2018-11-15 | 2022-08-15 |  | G | [5 empty] | 2023-07-20 |  | 2023-08-02 |  | G | 2024-10-02 |  | 2024-10-15 |  | G | 2025-03-18 |  | 2025-09-18 |  | G | 2024-10-31 |  | 2025-05-12 |  | G | 2024-09-25 | 2018-12-10 | 2025-06-03 | 2018-12-10 | G | [5 empty] | 2025-10-14 |  | 2025-10-14 |  | G | 2026-01-09 |  | 2026-01-09 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.11754
1207 | 113439 | Bon Air Pedestrian Improvements |  | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Chesterfield County | CHESTERFIELD | Richmond | Richmond:Chesterfield County | Local Assistance Division | Jorg Huckabee-Mayfield | Jorg.Huckabee-Mayfield@VDOT.Virginia.gov | (804) 609-5292 | Jorg Huckabee-Mayfield | Jorg.Huckabee-Mayfield@VDOT.Virginia.gov | (804) 609-5292 | Brent Epps | eppsb@chesterfield.gov | (804) 748-1037 | 0 |  | 0 | FY2023 | 2012871 | 2012871 | NO DATES SET YET-PE OPEN | R | Determine Requirements milestone is 268 days past the expected completion date | G | Project is on budget | 2018-11-30 | 2018-11-30 | 2019-02-28 | 2019-04-02 | R | 2019-03-01 | 2019-04-03 | 2019-03-05 | 2019-05-06 | R | 2019-03-06 |  | 2020-05-29 |  | R | [10 empty] | 2021-03-26 |  | 2021-04-01 |  | G | [5 empty] | 2021-04-05 |  | 2022-01-13 |  | G | 2019-10-14 |  | 2020-06-19 |  | R | [5 empty] | 2022-02-02 |  | 2022-05-31 |  | G | 2022-08-18 |  | 2022-09-15 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.35917
1208 | 113764 | NEW SIDEWALK SW VA MUSEUM/SLEMP LIBRARY; TO BULLITT PARK | 0000 | Urban | Facilities for Pedestrians and Bicycles | Locally | Big Stone Gap | WISE | Bristol | NonMPO:NonMPO | Infrastructure Investment Division | Allan D Sumpter | Allan.Sumpter@VDOT.virginia.gov | (276) 525-6461 | Kenneth R Plummer | KR.Plummer@VDOT.Virginia.gov | (276) 696-3261 | S. Lawson |  |  | 0 |  | 0 | FY2026 | 253767 | 253767 | NO DATES SET YET | G | Agreement with Locality milestone is 1250 days ahead of the expected completion date | G | Project is on budget | 2024-05-01 |  | 2024-07-25 |  | G | 2024-07-26 |  | 2024-07-30 |  | G | 2024-07-31 |  | 2025-02-10 |  | G | [25 empty] | 2025-03-19 |  | 2025-11-18 |  | G | [5 empty] | 2026-03-02 |  | 2026-03-27 |  | G | 2026-06-16 |  | 2026-06-16 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.10406
1209 | 113862 | Resurface Middlebrook Ave (Rte. 252) - Primary Extension | 0252 | Urban | Resurfacing | Locally | Staunton | HARRISONBURG | Staunton | SAW:Staunton | Local Assistance Division | Donald F Komara | Donald.Komara@VDOT.Virginia.gov | (540) 434-2587 | Michael S Fulcher | Michael.Fulcher@VDOT.Virginia.gov | (540) 332-2243 | Steve Yancey | yanceysc@ci.staunton.va.us | (540) 332-3892 | 0 |  | 1 | FY2020 | 193000 | 193000 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 412 days early | G | Project is on budget | 2018-12-31 | 2018-10-05 | 2019-03-28 | 2018-11-05 | G | 2019-03-29 | 2018-11-06 | 2019-04-02 | 2019-03-01 | G | 2019-04-03 | 2019-03-04 | 2019-10-04 | 2019-03-11 | G | [25 empty] | 2019-03-12 | 2019-03-10 | 2019-11-08 | 2019-03-12 | G | [5 empty] | 2020-01-21 | 2019-03-07 | 2020-02-18 | 2019-03-20 | G | 2020-05-06 | 2019-03-20 | 2020-05-06 | 2019-03-21 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.063215
1210 | 111395 | Sunset Lane to Madison Road Sidewalk Connection |  | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Culpeper | WARRENTON | Culpeper | NonMPO:NonMPO | Local Assistance Division | John P Price | John.Price@VDOT.Virginia.gov | (540) 347-6371 | John P Price | John.Price@VDOT.Virginia.gov | (540) 347-6371 | Salem Bush | SBush@culpeperva.gov | (540) 829-8260 | 0 |  | 0 | FY2021 | 121866 | 353090 | ADVERTISED | G | Solicit Bids milestone finished 222 days early | R | Project estimate is less than $5M and is 20% or more over budget | 2017-10-24 | 2017-10-24 | 2017-10-24 | 2017-10-24 | G | 2017-11-14 | 2017-11-14 | 2017-11-14 | 2017-11-14 | G | 2017-11-14 | 2018-10-01 | 2019-01-31 | 2019-05-02 | R | [10 empty] | 2020-02-28 | 2019-11-08 | 2020-03-19 | 2019-11-22 | G | [5 empty] | 2020-03-23 | 2019-11-25 | 2020-12-30 | 2020-06-04 | G | [10 empty] | 2021-01-20 | 2020-06-05 | 2021-02-16 | 2020-07-09 | G | 2021-02-17 |  | 2021-03-30 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.35758
1211 | 111691 | #SGR18VB - NORTH GLEBE ROAD OVER PIMMIT RUN - Fed 217 | 0120 | Primary | Bridge Rehab w/o Added Capacity | VDOT | Arlington County | FAIRFAX | Northern Virginia | Northern Virginia:Arlington County | Infrastructure Investment/Asset Management Division | Gary Runco | Gary.Runco@vdot.virginia.gov | (703) 259-3341 | Shahrad Behboodi | Shahrad.Behboodi@VDOT.Virginia.gov | (703) 259-2304 |  |  |  | 0 |  | 1 | FY2021 | 5000000 | 8500000 | ADVERTISED | R | Start Delivery milestone is 89 days past the expected completion date | R | Project estimate is between $5M and $10M and is a $1M or more over budget | [10 empty] | 2019-09-03 | 2019-09-03 | 2019-09-09 | 2019-09-09 | G | [25 empty] | 2019-09-03 | 2020-01-21 | 2020-03-13 | 2020-01-21 | G | [5 empty] | 2020-04-14 | 2020-12-08 | 2020-04-14 | 2020-12-08 | R | 2020-07-17 |  | 2020-11-24 |  | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.14062
1212 | 111809 | Benn's Church Boulevard at South Church St Int. Imprv | 0000 | Urban | New Construction Roadway | Locally | Smithfield | FRANKLIN | Hampton Roads | Hampton Roads:Smithfield | Local Assistance Division | Dawn Odom | Dawn.Odom@vdot.virginia.gov | (000) 000-0000 | Derrick Williams | Derrick.Williams@vdot.virginia.gov | (757) 956-3097 | Wayne Griffin P.E. | wgriffin@smithfield.gov | (757) 367-9933 | 0 |  | 0 | FY2023 | 895000 | 895000 | NO DATES SET YET-PE OPEN | R | Determine Requirements milestone is 163 days past the expected completion date | G | Project is on budget | 2019-06-04 | 2019-06-04 | 2019-08-27 | 2020-03-23 | R | 2019-08-28 | 2020-03-24 | 2019-09-11 | 2020-04-10 | R | 2019-09-12 | 2020-04-13 | 2020-09-11 |  | R | [10 empty] | 2021-07-09 |  | 2021-07-29 |  | G | [5 empty] | 2021-08-02 |  | 2022-05-13 |  | G | [10 empty] | 2022-06-01 |  | 2022-07-13 |  | G | 2022-07-14 |  | 2023-01-06 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.16398
1213 | 113114 | Resurface Millwood Ave (US Rt 50,17, & 522) - Primary Ext. | 0050 | Urban | Resurfacing | Locally | Winchester | EDINBURG | Staunton | Winchester:Winchester | Local Assistance Division | Clifton Balderson | clifton.balderson@dbiservices.com | (540) 460-1313 | Kimberly Cameron | Kim.Cameron@vdot.virginia.gov | (540) 332-7886 | Perry Eisenach -City of Winchester | perry.eisenach@winchesterva.gov | (540) 667-2085 | 0 |  | 1 | FY2020 | 275000 | 275000 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 200 days early | G | Project is on budget | 2019-04-02 | 2019-04-02 | 2019-06-25 | 2019-07-25 | R | 2019-06-26 | 2019-07-26 | 2019-06-28 | 2019-07-31 | R | 2019-07-01 | 2019-08-01 | 2020-01-08 | 2019-08-05 | G | [25 empty] | 2019-08-06 | 2019-08-01 | 2019-08-12 | 2019-08-05 | G | [5 empty] | 2019-11-05 | 2019-07-26 | 2019-11-26 | 2019-08-02 | G | 2020-02-21 | 2019-08-05 | 2020-02-21 | 2019-08-05 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.094696
1214 | 113281 | Hungary Road - Sidewalk | 9999 | Secondary | Facilities for Pedestrians and Bicycles | Locally | Henrico County | ASHLAND | Richmond | Richmond:Henrico County | Local Assistance Division | Douglas L Orcutt | Doug.Orcutt@vdot.virginia.gov | (804) 609-5428 | Douglas L Orcutt | Doug.Orcutt@vdot.virginia.gov | (804) 609-5428 | Steve Bandura | ban03@co.henrico.us | (804) 501-5985 | 0 |  | 0 | FY2024 | 1854000 | 1854000 | ACTIVITY DATES SET | G | Start Purchasing Right-of-Way milestone finished 24 days early | G | Project is on budget | 2019-08-09 | 2018-07-06 | 2019-11-04 | 2018-09-27 | G | 2019-11-05 | 2019-10-18 | 2019-11-07 | 2019-10-21 | G | 2019-11-08 | 2020-03-16 | 2020-05-19 | 2020-05-12 | G | 2020-12-15 | 2020-12-15 | 2020-12-15 | 2020-12-15 | G | [5 empty] | 2021-01-14 | 2020-12-18 | 2021-01-14 | 2020-12-21 | G | 2022-08-10 |  | 2022-12-09 |  | G | 2021-01-20 |  | 2022-08-09 |  | G | 2019-07-18 |  | 2022-09-28 |  | G | [5 empty] | 2023-03-07 |  | 2023-04-03 |  | G | 2023-06-21 |  | 2023-09-05 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.35478
1215 | 113294 | #SGR21LB - East Richmond Rd over Gillies Creek - BR Replace | 7573 | Primary | Bridge Replacement w/o Added Capacity | Locally | Richmond | ASHLAND | Richmond | Richmond:Richmond | Local Assistance Division | Douglas L Orcutt | Doug.Orcutt@vdot.virginia.gov | (804) 609-5428 | Douglas L Orcutt | Doug.Orcutt@vdot.virginia.gov | (804) 609-5428 | Tom Westbrook |  |  | 0 |  | 0 | FY2025 | 2252094 | 3050000 | ACTIVITY DATES SET | R | Determine Requirements milestone finished 73 days late | R | Project estimate is less than $5M and is 20% or more over budget | 2018-07-02 | 2018-07-10 | 2018-11-07 | 2018-07-10 | G | 2018-11-08 | 2018-12-14 | 2018-12-03 | 2018-12-17 | R | 2019-01-03 | 2018-12-20 | 2019-04-29 | 2019-07-11 | R | 2019-09-16 |  | 2022-02-17 |  | G | [5 empty] | 2020-06-12 |  | 2022-08-05 |  | G | 2023-04-24 |  | 2023-09-18 |  | G | 2022-08-08 |  | 2023-04-21 |  | G | 2023-05-23 |  | 2023-10-20 |  | G | [5 empty] | 2023-12-18 |  | 2023-12-18 |  | G | 2024-05-23 |  | 2024-07-05 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.14379
1216 | 113427 | Greenbelt Trail and Walking Tour |  | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Big Stone Gap | WISE | Bristol | NonMPO:NonMPO | Local Assistance Division | Tabitha H Crowder | Tabitha.Crowder@vdot.virginia.gov | (276) 696-3482 | Roger L Musser | Roger.Musser@VDOT.Virginia.gov | (276) 696-3260 | Stephen Lawson | slawson@bigstonegap.org | (276) 523-0115 | 0 |  | 0 | FY2024 | 674853 | 674853 | NO DATES SET YET-PE OPEN | G | Start Development milestone finished 688 days early | G | Project is on budget | 2020-09-01 | 2018-10-01 | 2020-11-30 | 2018-12-26 | G | 2020-12-01 | 2019-01-08 | 2020-12-03 | 2019-01-15 | G | 2020-12-04 | 2019-01-16 | 2021-06-11 |  | G | [10 empty] | 2022-06-15 |  | 2022-07-06 |  | G | [5 empty] | 2022-07-08 |  | 2023-04-20 |  | G | 2021-07-20 |  | 2022-03-28 |  | G | [5 empty] | 2023-05-08 |  | 2023-06-05 |  | G | 2023-08-23 |  | 2023-08-23 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.34816
1217 | 113637 | FAIRFAX COUNTY - SRTS - WOLF TRAP ES - CROSSING IMP | 0675 | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Fairfax County | FAIRFAX | Northern Virginia | Northern Virginia:Fairfax County | Local Assistance Division | Amir Salahshoor | A.Salahshoor@VDOT.Virginia.gov | (703) 259-1957 | Rhoderick M Undan | Rhoderick.Undan@vdot.virginia.gov | (703) 259-3347 | Francesco Lauretti | Francesco.Lauretti@fairfaxcounty.gov | (703) 877-5600 | 0 |  | 0 | FY2024 | 370000 | 370000 | NO DATES SET YET-PE OPEN | Y | Determine Requirements milestone is 5 days ahead of the expected completion date and there is a risk of missing this milestone date | G | Project is on budget | 2019-09-03 | 2018-08-17 | 2020-03-31 | 2019-03-18 | G | 2020-04-01 | 2019-03-19 | 2020-04-30 | 2019-04-03 | G | 2020-05-01 | 2019-04-04 | 2021-02-26 |  | Y | [10 empty] | 2022-03-01 |  | 2022-03-31 |  | G | [5 empty] | 2022-04-01 |  | 2022-12-30 |  | G | 2021-01-04 |  | 2021-05-28 |  | G | [5 empty] | 2023-02-01 |  | 2023-06-30 |  | G | 2023-07-03 |  | 2023-12-29 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.2535
1218 | 113852 | #SGR19VB - BRIDGE REPLACE RT 638 SOUTH RIVER ID 04471 | 0638 | Secondary | Bridge Replacement w/o Added Capacity | VDOT | Caroline County | FREDERICKSBURG | Fredericksburg | NonMPO:NonMPO | Infrastructure Investment/Asset Management Division | Annette F Adams | Annette.Adams@VDOT.Virginia.gov | (540) 372-3583 | Jessica Graves | Jessica.Graves@vdot.virginia.gov | (540) 899-4267 |  |  |  | 0 |  | 1 | FY2026 | 4100000 | 4100000 | NO DATES SET YET-PE OPEN | G | Start Development milestone finished 558 days early | G | Project is on budget | [5 empty] | 2021-08-02 | 2020-01-13 | 2021-08-13 | 2020-02-02 | G | 2021-08-16 | 2020-11-18 | 2022-07-14 |  | G | [5 empty] | 2023-06-19 |  | 2023-06-30 |  | G | 2024-08-30 |  | 2024-09-13 |  | G | 2025-02-13 |  | 2025-08-18 |  | G | 2024-09-30 |  | 2025-04-10 |  | G | 2024-08-23 |  | 2025-05-01 |  | G | [5 empty] | 2025-09-09 |  | 2025-09-09 |  | G | 2025-12-03 |  | 2025-12-03 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.060004
1220 | 115252 | Westover Hill Blvd (S) - Resurfacing | 0161 | Urban | Resurfacing | Locally | Richmond | ASHLAND | Richmond | Richmond:Richmond | Local Assistance Division | Brian J Lokker | Brian.Lokker@VDOT.Virginia.gov | (804) 524-6010 | Brian J Lokker | Brian.Lokker@VDOT.Virginia.gov | (804) 524-6010 | Kenny Horak | Kenneth.horak@richmondgov.com | (804) 646-4781 | 0 |  | 0 | FY2020 | 258864 | 258864 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 5 days early | G | Project is on budget | 2019-07-01 | 2019-04-16 | 2019-09-24 | 2020-01-30 | R | [5 empty] | 2019-09-25 | 2020-01-30 | 2019-11-27 | 2020-02-13 | R | [25 empty] | 2020-02-10 | 2020-03-04 | 2020-04-29 | 2020-03-04 | G | [5 empty] | 2020-05-01 | 2020-03-19 | 2020-05-01 | 2020-03-19 | G | 2020-06-30 | 2020-06-25 | 2020-06-30 | 2020-06-25 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 |  | 1 | 0 | 0.081981
1221 | 115411 | #SMART20 - N Laburnum Ave Ped and Transit Improvements | 9999 | Secondary | Facilities for Pedestrians and Bicycles | Locally | Henrico County | ASHLAND | Richmond | Richmond:Henrico County | Infrastructure Investment Division | Douglas L Orcutt | Doug.Orcutt@vdot.virginia.gov | (804) 609-5428 | Douglas L Orcutt | Doug.Orcutt@vdot.virginia.gov | (804) 609-5428 | Todd Eure |  |  | 1 | 2020 | 0 | FY2026 | 3054000 | 3054000 | NO DATES SET YET | G | Agreement with Locality milestone is 709 days ahead of the expected completion date | G | Project is on budget | 2022-10-31 |  | 2023-01-31 |  | G | 2023-02-01 |  | 2023-02-03 |  | G | 2023-02-06 |  | 2023-08-09 |  | G | [10 empty] | 2024-06-05 |  | 2024-06-25 |  | G | 2026-11-09 |  | 2027-05-07 |  | G | 2024-06-27 |  | 2025-04-10 |  | G | 2023-09-15 |  | 2024-05-22 |  | G | [5 empty] | 2025-04-28 |  | 2025-05-23 |  | G | 2025-08-13 |  | 2025-08-13 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.26861
1222 | 116423 | I-395 NORTHERN EXTENSION PROJECT OWNER COST (2A) LANDSCAPING | 0395 | Interstate | Landscaping/Beautification | VDOT | Northern Virginia District-wide |  | Northern Virginia | Northern Virginia:Northern Virginia District-wide | Infrastructure Investment Division | Michael D Gleasman | Michael.Gleasman@VDOT.Virginia.gov | (703) 259-1944 | Rimpal Shah | Rimpal.Shah@vdot.virginia.gov | (703) 259-2362 |  |  |  | 0 |  | 0 | FY2022 | 631250 | 831250 | ACTIVITY DATES SET | G | Obtained Permits milestone finished 540 days early | R | Project estimate is less than $5M and is 20% or more over budget | [5 empty] | 2019-11-01 | 2019-11-01 | 2019-11-15 | 2019-12-03 | R | 2019-11-18 | 2019-12-04 | 2020-07-13 | 2020-01-20 | G | [5 empty] | 2021-04-06 |  | 2021-05-03 |  | G | [5 empty] | 2021-08-17 |  | 2021-12-13 |  | G | [5 empty] | 2021-08-02 | 2020-05-11 | 2021-11-02 | 2020-05-11 | G | [5 empty] | 2021-12-14 |  | 2021-12-14 |  | G | 2022-03-10 |  | 2022-03-10 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | WORK/TASK ORDER | 0 | 0 | 0.13894
1223 | 116975 | #SGR21VP Edinburg Res. Plant Mix Schedule (PM-8M-21) | 9999 | Interstate | Resurfacing | VDOT | Shenandoah County | EDINBURG | Staunton | NonMPO:NonMPO | Infrastructure Investment/Asset Management Division | Joel D Denunzio | Joel.DeNunzio@VDOT.virginia.gov | (540) 332-9093 | Mark W Hisey | Mark.Hisey@VDOT.Virginia.gov | (540) 280-4820 |  |  |  | 0 |  | 1 | FY2021 | 2914782 | 2914336 | ADVERTISED | G | Solicit Bids milestone finished 91 days early | G | Project is on budget | [10 empty] | 2020-06-01 | 2020-09-29 | 2020-06-05 | 2020-09-30 | R | 2020-10-15 | 2020-10-15 | 2020-11-13 | 2020-10-19 | G | [30 empty] | 2020-12-08 | 2020-12-08 | 2021-03-09 | 2020-12-08 | G | 2021-05-27 |  | 2021-05-27 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.070082
1224 | 117163 | #SGR21LP 131-City of Chesapeake 1622 Kempsville Rd | 0190 | Urban | Resurfacing | Locally | Chesapeake | NORFOLK | Hampton Roads | Hampton Roads:Chesapeake | Infrastructure Investment/Asset Management Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Johndel A Alcaide | John.Alcaide@vdot.virginia.gov | (757) 956-3098 | Sam Sawan | ssawan@cityofchesapeake.net | (757) 382-8263 | 0 |  | 1 | FY2022 | 92640 | 92640 | NO DATES SET YET | G | Agreement with Locality milestone is 80 days ahead of the expected completion date | G | Project is on budget | 2021-01-04 |  | 2021-05-12 |  | G | 2021-05-13 |  | 2021-06-03 |  | G | 2021-07-02 |  | 2021-08-04 |  | G | [25 empty] | 2021-07-08 |  | 2021-08-04 |  | G | [5 empty] | 2021-10-01 |  | 2021-10-29 |  | G | 2022-01-26 |  | 2022-01-26 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.080611
1225 | 118492 | #SGR21LP DUKE STREET WB PRIMARY EXTENSION PAVING | 0236 | Primary | Resurfacing | VDOT | Alexandria | FAIRFAX | Northern Virginia | Northern Virginia:Alexandria | Infrastructure Investment/Asset Management Division | Edmund A Okerchiri | Edmund.Okerchiri@VDOT.Virginia.gov | (703) 259-1726 | Sharif Ramsis | Sharif.Ramsis@vdot.virginia.gov | (703) 259-2607 | Mary Alice Winston | maryalice.winston@alexandriava.gov | (703) 746-4067 | 0 |  | 1 | FY2021 | 750000 | 748385 | ACTIVITY DATES SET | Y | Solicit Bids milestone is 2 days ahead of the expected completion date and there is a risk of missing this milestone date | G | Project is on budget | [5 empty] | 2020-12-28 | 2020-12-21 | 2021-01-11 | 2020-12-21 | G | 2021-01-12 | 2020-12-23 | 2021-03-25 | 2020-12-23 | G | [35 empty] | 2021-02-23 |  | 2021-02-23 |  | Y | 2021-06-30 |  | 2021-06-30 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.1027
1226 | 101009 | #SGR17VB - RT 813 OVER ROANOKE RIVER(STR 12363) - BR REPAIR | 0813 | Secondary | Bridge Rehab w/o Added Capacity | VDOT | Montgomery County | CHRISTIANSBURG | Salem | NonMPO:NonMPO | Infrastructure Investment/Asset Management Division | Anthony T Marshall | Todd.Marshall@VDOT.Virginia.gov | (540) 387-5460 | Leslie T Repass | Todd.Repass@VDOT.Virginia.gov | (540) 381-7195 |  |  |  | 0 |  | 1 | FY2020 | 4952596 | 1537738 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 170 days early | G | Project is on budget | [5 empty] | 2016-07-01 | 2013-07-05 | 2016-07-01 | 2013-07-05 | G | 2016-08-22 | 2016-08-22 | 2018-06-29 | 2018-06-29 | G | 2018-06-29 | 2018-06-29 | 2018-08-14 | 2018-08-14 | G | [5 empty] | 2018-02-07 | 2018-02-07 | 2018-02-07 | 2018-02-07 | G | [20 empty] | 2019-06-12 | 2019-04-23 | 2019-07-09 | 2019-04-23 | G | 2019-08-01 | 2019-06-26 | 2019-12-13 | 2019-06-26 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.14245
1227 | 107061 | #HB2.FY17 Rte 419 Safety Improvements at Tanglewood | 0419 | Primary | Safety | VDOT | Roanoke County | SALEM | Salem | Roanoke:Roanoke County | Infrastructure Investment Division | Bernard S Grinnell | Sean.Grinnell@VDOT.Virginia.gov | (540) 375-0148 | Jeffrey A Echols | Jeff.Echols@VDOT.Virginia.gov | (540) 375-3595 |  |  |  | 1 | 2017 | 0 | FY2020 | 5853432 | 6568683 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 28 days early | Y | Project estimate is between $5M and $10M and is up to $1M over budget | [5 empty] | 2016-06-29 | 2016-06-29 | 2016-08-12 | 2016-08-12 | G | 2016-07-20 | 2016-07-20 | 2017-07-18 | 2017-06-06 | G | [5 empty] | 2018-02-06 | 2018-02-06 | 2018-02-20 | 2018-02-06 | G | 2019-03-01 | 2019-02-07 | 2019-03-14 | 2019-02-11 | G | 2019-08-06 | 2019-08-29 | 2020-02-14 | 2020-02-14 | G | 2019-04-01 | 2019-03-06 | 2019-10-02 | 2019-09-30 | G | 2018-08-13 | 2018-08-13 | 2019-08-13 | 2018-08-13 | G | [5 empty] | 2020-03-10 | 2020-02-11 | 2020-03-10 | 2020-02-11 | G | 2020-04-29 | 2020-05-29 | 2020-06-26 | 2020-05-29 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.1336
1228 | 107352 | Princess Anne VII |  | Urban | Reconstruction w/ Added Capacity | Locally | Virginia Beach | NORFOLK | Hampton Roads | Hampton Roads:Virginia Beach | Local Assistance Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Marci Thompson | Marci.Thompson@vdot.virginia.gov | (757) 956-3093 | Katie Shannon | kshannon@vbgov.com | (757) 385-1514 | 0 |  | 0 | FY2021 | 38609843 | 38609843 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 559 days early | G | Project is on budget | 2016-01-14 | 2016-01-14 | 2016-02-09 | 2016-02-09 | G | 2016-02-09 | 2016-02-09 | 2016-02-09 | 2016-02-09 | G | 2016-02-10 | 2016-02-10 | 2018-10-01 | 2018-08-14 | G | [10 empty] | 2016-02-09 | 2016-02-09 | 2016-02-11 | 2016-02-11 | G | [20 empty] | 2020-03-06 | 2018-09-21 | 2020-03-19 | 2018-09-23 | G | 2020-03-20 | 2018-10-24 | 2020-07-27 | 2019-01-15 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.22555
1229 | 109397 | #SMART18 - CONN. ROAD BETWEEN RIO MILLS AND BERKMAR DR. EXT. | 0643 | Secondary | New Construction Roadway | VDOT | Albemarle County | CHARLOTTESVILLE | Culpeper | Charlottesville:Albemarle County | Infrastructure Investment Division | Gregory J Cooley | Gregory.Cooley@vdot.virginia.gov | (434) 906-7979 | William E Stowe | William.Stowe@vdot.virginia.gov | (540) 827-7287 |  |  |  | 1 | 2018 | 0 | FY2019 | 3800000 | 3799233 | CONSTRUCTION STARTED | R | Start Delivery milestone finished 34 days late | G | Project is on budget | [5 empty] | 2020-07-15 | 2017-10-12 | 2020-07-28 | 2017-10-26 | G | 2020-07-29 | 2017-10-27 | 2021-06-25 | 2018-10-29 | G | [10 empty] | 2018-11-01 | 2018-11-01 | 2018-11-14 | 2018-11-14 | G | [20 empty] | 2018-10-30 | 2018-10-30 | 2018-11-27 | 2018-11-27 | G | 2019-05-28 | 2019-06-26 | 2019-06-19 | 2019-07-23 | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | DESIGN BUILD/PPTA | 1 | 1 | 0.3695
1230 | 115408 | #SMART20 - Blvd Shared Use Path to Science Mus BRT Station | 9999 | Urban | Facilities for Pedestrians and Bicycles | Locally | Richmond | ASHLAND | Richmond | Richmond:Richmond | Infrastructure Investment Division | Melinda G Baicy | Melinda.Baicy@vdot.virginia.gov | (804) 609-5390 | Melinda G Baicy | Melinda.Baicy@vdot.virginia.gov | (804) 609-5390 | Lamont Benjamin |  |  | 1 | 2020 | 0 | FY2027 | 2992481 | 2992481 | NO DATES SET YET | G | Agreement with Locality milestone is 1073 days ahead of the expected completion date | G | Project is on budget | 2023-10-30 |  | 2024-01-30 |  | G | 2024-01-31 |  | 2024-02-02 |  | G | 2024-02-05 |  | 2024-08-07 |  | G | [10 empty] | 2025-06-04 |  | 2025-06-24 |  | G | [5 empty] | 2025-06-26 |  | 2026-04-09 |  | G | 2024-09-13 |  | 2025-05-21 |  | G | [5 empty] | 2026-04-27 |  | 2026-05-22 |  | G | 2026-08-12 |  | 2026-08-12 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.13572
1231 | 116161 | #I81CIP NB MM 48.1 EXTEND ACCEL LANE (ID #7) | 0081 | Interstate | Reconstruction w/o Added Capacity | VDOT | Smyth County | ABINGDON | Bristol | NonMPO:NonMPO | Infrastructure Investment Division | Marty R Halloway | Marty.Halloway@VDOT.Virginia.gov | (276) 696-3367 | Robert C Leonard | Robert.Leonard@VDOT.Virginia.gov | (276) 696-3258 |  |  |  | 0 |  | 0 | FY2022 | 18203220 | 17200000 | ACTIVITY DATES SET | G | Determine Requirements milestone finished on-time | G | Project is on budget | [5 empty] | 2020-01-03 | 2020-01-03 | 2020-01-03 | 2020-01-03 | G | 2020-01-06 | 2020-01-06 | 2020-08-24 | 2020-08-24 | G | [10 empty] | 2021-06-28 |  | 2021-07-07 |  | G | [20 empty] | 2021-07-08 |  | 2021-07-16 |  | G | 2022-02-18 |  | 2022-03-18 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | DESIGN BUILD/PPTA | 0 | 0 | 0.096287
1232 | 116945 | HERITAGE WALK MUSEUM CONNECTOR |  | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Wytheville | WYTHEVILLE | Bristol | NonMPO:NonMPO | Local Assistance Division | John W Bechtold | John.Bechtold@vdot.virginia.gov | (276) 696-3365 | Kenneth R Plummer | KR.Plummer@VDOT.Virginia.gov | (276) 696-3261 | Brian Freeman | bfreeman@wytheville.org | (276) 223-3450 | 0 |  | 0 | FY2025 | 650040 | 650040 | NO DATES SET YET | G | Agreement with Locality milestone is 359 days ahead of the expected completion date | G | Project is on budget | 2021-10-01 |  | 2022-02-15 |  | G | 2022-02-16 |  | 2022-03-09 |  | G | 2022-09-13 |  | 2023-01-10 |  | G | [10 empty] | 2024-05-01 |  | 2024-06-05 |  | G | [5 empty] | 2024-06-06 |  | 2024-11-04 |  | G | 2024-10-01 |  | 2025-03-07 |  | G | [5 empty] | 2025-02-13 |  | 2025-03-13 |  | G | 2025-06-02 |  | 2025-06-02 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.29287
1233 | 117033 | ERC I-264 Noise Barriers | 0264 | Interstate | Other | VDOT | Portsmouth | NORFOLK | Hampton Roads | Hampton Roads:Portsmouth | Infrastructure Investment Division | Frank F Fabian | Frank.Fabian@VDOT.Virginia.gov | (757) 272-9203 | Frank F Fabian | Frank.Fabian@VDOT.Virginia.gov | (757) 272-9203 |  |  |  | 0 |  | 0 | FY2026 | 23398069 | 23398069 | NO DATES SET YET-PE OPEN | G | Start Development milestone finished 40 days early | G | Project is on budget | [5 empty] | 2020-09-30 | 2020-09-11 | 2020-10-21 | 2020-09-11 | G | 2020-10-22 | 2020-09-11 | 2022-01-07 |  | G | [5 empty] | 2023-02-07 |  | 2023-03-21 |  | G | 2024-04-10 |  | 2024-05-14 |  | G | 2024-12-05 |  | 2025-04-09 |  | G | 2024-06-06 |  | 2024-12-27 |  | G | 2024-06-11 |  | 2025-02-18 |  | G | [5 empty] | 2025-05-13 |  | 2025-05-13 |  | G | 2025-08-01 |  | 2025-08-01 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.18457
1234 | 118182 | #SGR21VP - Roanoke FKEY 1364 Hollins Rd NE | 0000 | Urban | Resurfacing | VDOT | Roanoke | SALEM | Salem | Roanoke:Roanoke City | Infrastructure Investment/Asset Management Division | Ibrahim M Abuawad | Ibrahim.Abuawad@vdot.virginia.gov | (217) 418-8827 | Ibrahim M Abuawad | Ibrahim.Abuawad@vdot.virginia.gov | (217) 418-8827 | Mark Jamison | mark.jamison@roanokeva.gov | (540) 853-5471 | 0 |  | 1 | FY2021 | 75000 | 75000 | NO DATES SET YET | R | Determine Requirements milestone is 9 days past the expected completion date | G | Project is on budget | [10 empty] | 2021-02-01 |  | 2021-02-12 |  | R | [35 empty] | 2021-03-09 |  | 2021-03-09 |  | Y | 2021-05-27 |  | 2021-05-27 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.14871
1235 | 88300 | #SMART18 - (St) Luray Intersection Improvements | 0000 | Urban | Reconstruction w/o Added Capacity | VDOT | Luray | HARRISONBURG | Staunton | NonMPO:NonMPO | Infrastructure Investment Division | Michael S Fulcher | Michael.Fulcher@VDOT.Virginia.gov | (540) 332-2243 | Timothy Gregory | Tim.Gregory@vdot.virginia.gov | (540) 332-7891 |  |  |  | 1 | 2018 | 0 | FY2020 | 2871596 | 2871596 | ACTIVITY DATES SET | R | Solicit Bids milestone is 502 days past the expected completion date | G | Project is on budget | [5 empty] | 2009-07-01 | 2009-07-01 | 2009-07-17 | 2009-07-17 | G | 2013-12-02 | 2013-12-02 | 2017-07-21 | 2017-07-20 | G | [5 empty] | 2017-09-22 | 2017-09-22 | 2017-10-10 | 2017-10-10 | G | 2017-07-17 | 2019-06-04 | 2018-09-07 | 2019-06-04 | R | [5 empty] | 2018-09-20 | 2019-06-24 | 2019-05-29 | 2019-10-15 | R | [10 empty] | 2019-10-01 |  | 2019-10-08 |  | R | 2019-12-02 |  | 2020-01-28 |  | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.067263
1236 | 104189 | Safety Improvements-Rte. 224 (Phase II-remove curve) | 0224 | Primary | Safety | VDOT | Scott County | WISE | Bristol | Kingsport:Scott County | Infrastructure Investment Division | James R Jones | jamesr.jones@vdot.virginia.gov | (276) 696-3257 | James R Jones | jamesr.jones@vdot.virginia.gov | (276) 696-3257 |  |  |  | 0 |  | 0 | FY2019 | 6650000 | 4640518 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 43 days early | G | Project is on budget | [5 empty] | 2013-09-03 | 2013-08-29 | 2013-09-11 | 2013-09-11 | G | 2012-09-19 | 2012-09-19 | 2013-10-18 | 2013-10-10 | G | [5 empty] | 2015-02-23 | 2015-02-23 | 2015-02-23 | 2015-02-23 | G | 2015-08-13 | 2015-08-13 | 2015-08-27 | 2015-08-27 | G | 2017-07-25 | 2017-07-25 | 2018-01-25 | 2018-01-25 | G | 2015-09-02 | 2015-09-02 | 2017-07-07 | 2017-07-07 | G | 2013-10-23 | 2013-10-23 | 2013-10-25 | 2013-10-25 | G | [5 empty] | 2018-06-12 | 2018-06-12 | 2018-06-12 | 2018-06-12 | G | 2018-08-13 | 2018-08-13 | 2018-09-25 | 2018-08-13 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.072673
1237 | 107310 | Kenwick Trail Drainage Improvements | 1530 | Secondary | Facilities for Pedestrians and Bicycles | Locally | Roanoke County | SALEM | Salem | Roanoke:Roanoke County | Local Assistance Division | Adam J Czesnowski | Adam.Czesnowski@vdot.virginia.gov | (540) 541-1216 | Adam J Czesnowski | Adam.Czesnowski@vdot.virginia.gov | (540) 541-1216 | David Henderson | DHENDERSON@roanokecountyva.gov | (540) 772-2083 | 0 |  | 0 | FY2019 | 50000 | 50000 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 71 days early | G | Project is on budget | 2015-11-02 | 2015-09-05 | 2016-02-02 | 2015-09-14 | G | 2016-02-03 | 2016-02-08 | 2016-02-17 | 2016-03-09 | R | 2016-02-18 | 2016-03-17 | 2016-10-07 | 2017-05-10 | R | [10 empty] | 2017-08-29 | 2017-09-11 | 2017-09-12 | 2017-09-11 | G | [20 empty] | 2017-09-18 | 2018-06-26 | 2018-02-14 | 2018-06-26 | R | 2018-07-03 | 2018-06-27 | 2019-01-04 | 2018-10-25 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.18933
1238 | 107661 | LOUISE ARCHER ELEMENTARY SRTS IMPROVEMENTS |  | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Vienna | FAIRFAX | Northern Virginia | Northern Virginia:Vienna | Local Assistance Division | Amir Salahshoor | A.Salahshoor@VDOT.Virginia.gov | (703) 259-1957 | Rita Hockman | Rita.Hockman@vdot.virginia.gov | (804) 824-7421 | Michael Gallagher, Director PW | mgallagher@viennava.gov | (703) 255-6389 | 0 |  | 0 | FY2019 | 354727 | 349831 | CONSTRUCTION COMPLETED | R | Start Delivery milestone finished 528 days late | G | Project is on budget | 2015-10-01 | 2015-08-17 | 2015-12-30 | 2015-08-17 | G | 2015-12-31 | 2015-09-08 | 2016-01-14 | 2015-09-08 | G | 2016-01-19 | 2016-01-18 | 2016-09-08 | 2016-09-08 | G | [10 empty] | 2017-07-31 | 2018-10-26 | 2018-05-18 | 2019-08-16 | R | [20 empty] | 2017-09-15 | 2019-07-08 | 2018-07-26 | 2019-08-16 | R | 2018-07-27 | 2019-11-06 | 2018-07-27 | 2020-01-06 | R | Delay due to unforeseen issues with utilities, railroad coordination, or right-of-way acquisition | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.31902
1239 | 109473 | BELMONT RIDGE ROAD INTERIM WIDENING AT DULLES GREENWAY | 0659 | Secondary | Reconstruction w/ Added Capacity | VDOT | Loudoun County | LEESBURG | Northern Virginia | Northern Virginia:Loudoun County | Infrastructure Investment Division | Kimberly Mccool | Kimberly.McCool@vdot.virginia.gov | (703) 259-3220 | Yusaf M Masud | Yusaf.Masud@vdot.virginia.gov | (703) 259-2973 | Joe Krioboth, Director, Dept. of Transportation & Capital Infrastructure | joe.kroboth@loudoun.gov | (703) 771-5107 | 0 |  | 0 | FY2020 | 7500000 | 7500000 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 291 days early | G | Project is on budget | [5 empty] | 2016-04-18 | 2016-04-18 | 2016-04-29 | 2016-09-21 | R | 2016-05-02 | 2016-10-13 | 2017-03-30 | 2017-10-13 | R | 2018-01-18 | 2018-02-05 | 2018-03-01 | 2018-02-05 | G | [5 empty] | 2018-06-01 | 2018-06-01 | 2018-06-01 | 2018-06-01 | G | 2018-08-10 | 2016-04-18 | 2019-03-21 | 2018-08-10 | G | [15 empty] | 2019-12-04 | 2019-05-07 | 2019-12-04 | 2019-05-07 | G | 2020-04-27 | 2019-07-29 | 2020-05-15 | 2019-07-29 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 1 | 0.21922
1240 | 109514 | Old Airport Road Sidewalk | 3318 | Urban | Safety | Locally | Bristol | ABINGDON | Bristol | Bristol:Bristol | Infrastructure Investment Division | Tabitha H Crowder | Tabitha.Crowder@vdot.virginia.gov | (276) 696-3482 | Kenneth R Plummer | KR.Plummer@VDOT.Virginia.gov | (276) 696-3261 | Wallace McCulloch |  |  | 0 |  | 0 | FY2023 | 49720 | 49720 | ACTIVITY DATES SET | G | Determine Requirements milestone finished 701 days early | G | Project is on budget | 2016-10-03 | 2016-10-03 | 2018-05-14 | 2018-05-14 | G | 2015-06-17 | 2015-06-17 | 2017-10-03 | 2017-10-03 | G | 2017-10-04 | 2017-10-04 | 2021-06-15 | 2019-07-15 | G | [35 empty] | 2022-10-12 |  | 2022-11-09 |  | G | 2022-11-10 |  | 2022-12-23 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.098292
1244 | 113313 | Primary Extension - Rte 457 (E Commonwealth Boulevard) | 0000 | Urban | Resurfacing | Locally | Martinsville | MARTINSVILLE | Salem | NonMPO:NonMPO | Local Assistance Division | Jessie Nester | Jessie.Nester@vdot.virginia.gov | (540) 613-4115 | Jessie Nester | Jessie.Nester@vdot.virginia.gov | (540) 613-4115 | Chris Morris | cmorris@ci.martinsville.va.us | (276) 403-5159 | 0 |  | 0 | FY2019 | 160000 | 160000 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 137 days early | G | Project is on budget | 2018-10-01 | 2018-08-01 | 2018-12-28 | 2018-08-16 | G | 2018-12-31 | 2018-08-30 | 2019-01-03 | 2018-09-04 | G | 2019-01-04 | 2018-09-05 | 2019-03-22 | 2018-10-16 | G | [35 empty] | 2018-12-03 | 2018-10-16 | 2018-12-31 | 2018-12-21 | G | 2019-05-28 | 2018-12-05 | 2019-06-28 | 2019-02-11 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.059662
1245 | 113412 | INTERSECTION IMPROVEMENTS - ROUTE 17/17B | 0017 | Primary | Reconstruction w/o Added Capacity | VDOT | Gloucester County | SALUDA | Fredericksburg | Hampton Roads:Gloucester County | Infrastructure Investment Division | Curtis B Holloway | Curtis.Holloway@vdot.virginia.gov | (540) 374-3367 | Curtis B Holloway | Curtis.Holloway@vdot.virginia.gov | (540) 374-3367 |  |  |  | 0 |  | 0 | FY2024 | 1180000 | 1180000 | NO DATES SET YET-PE OPEN | G | Start Development milestone finished 24 days early | G | Project is on budget | [5 empty] | 2020-08-10 | 2020-07-27 | 2020-08-28 | 2020-08-04 | G | 2020-08-31 |  | 2021-07-06 |  | G | [5 empty] | 2022-02-08 |  | 2022-03-08 |  | G | 2022-10-25 |  | 2022-12-01 |  | G | 2023-05-04 |  | 2023-09-01 |  | G | 2022-12-16 |  | 2023-05-18 |  | G | 2023-01-19 |  | 2023-06-16 |  | G | [5 empty] | 2023-09-12 |  | 2023-09-12 |  | G | 2023-12-05 |  | 2023-12-05 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.080821
1246 | 113472 | Suffolk Seaboard Coastline Trail Phase II | 0000 | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Suffolk | NORFOLK | Hampton Roads | Hampton Roads:Suffolk | Local Assistance Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Joshua D Negovan | Joshua.Negovan@vdot.virginia.gov | (757) 956-3347 | Darryll D Lewis, P.E., PMP | dlewis@suffolkva.us | (757) 514-7683 | 0 |  | 0 | FY2021 | 1806335 | 1645331 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 220 days early | G | Project is on budget | 2018-09-04 | 2018-09-04 | 2018-11-30 | 2018-12-27 | R | 2018-12-03 | 2018-12-28 | 2018-12-05 | 2019-01-31 | R | 2018-12-06 | 2019-02-01 | 2019-06-13 | 2019-06-03 | G | [25 empty] | 2019-06-04 | 2019-06-04 | 2020-02-10 | 2020-02-20 | R | [5 empty] | 2020-04-24 | 2020-04-27 | 2020-05-21 | 2020-05-19 | G | 2020-08-11 | 2020-06-30 | 2021-02-05 | 2020-06-30 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.29774
1247 | 113710 | #TAP19 RIVERWALK TRAIL SOUTH BANK EXTENSION | 9999 | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Danville | HALIFAX | Lynchburg | Danville:Danville | Local Assistance Division | Gregg Allen | Gregg.Allen@vdot.virginia.gov | (434) 426-5575 | Gregg Allen | Gregg.Allen@vdot.virginia.gov | (434) 426-5575 | CHRIS FRANKS | frankcp@danvilleva.gov | (434) 799-5019 | 0 |  | 0 | FY2022 | 561375 | 561375 | NO DATES SET YET-PE OPEN | R | Determine Requirements milestone is 475 days past the expected completion date | G | Project is on budget | 2019-01-31 | 2019-01-31 | 2019-04-25 | 2019-01-31 | G | 2019-04-26 | 2019-02-01 | 2019-04-30 | 2019-02-08 | G | 2019-05-01 | 2019-05-01 | 2019-11-04 |  | R | [10 empty] | 2020-11-03 |  | 2020-11-24 |  | R | [5 empty] | 2020-11-30 |  | 2021-09-08 |  | G | 2019-12-13 |  | 2020-08-17 |  | R | [5 empty] | 2021-09-24 |  | 2021-10-22 |  | G | 2022-01-19 |  | 2022-01-19 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.18952
1248 | 115553 | #SMART20 - INTERSECTION IMPROV AT OLD BRIDGE AND OCCOQUAN RD | 0641 | Secondary | Reconstruction w/o Added Capacity | Locally | Prince William County | MANASSAS | Northern Virginia | Northern Virginia:Prince William County | Infrastructure Investment Division | Claudia H Llana | Claudia.Llana@VDOT.Virginia.gov | (703) 259-1768 | Marlene Pinedo Fortich | Sofia.Pinedo@vdot.virginia.gov | (703) 259-1724 | Hoainam Nguyen | hnguyen@pwcgov.org | (703) 792-6273 | 1 | 2020 | 0 | FY2029 | 11850000 | 11850000 | NO DATES SET YET-PE OPEN | G | Start Development milestone finished 1491 days early | G | Project is on budget | 2023-08-01 | 2019-10-01 | 2024-02-29 | 2020-01-28 | G | 2024-03-01 | 2020-02-12 | 2024-03-29 | 2020-02-28 | G | 2024-04-01 |  | 2024-11-27 |  | G | [10 empty] | 2025-12-03 |  | 2025-12-31 |  | G | [5 empty] | 2026-01-05 |  | 2026-10-30 |  | G | 2026-11-02 |  | 2027-06-30 |  | G | [5 empty] | 2027-07-30 |  | 2027-12-30 |  | G | 2028-03-23 |  | 2028-07-31 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.38278
1249 | 115885 | SYSTEMIC HIGH-VISIBILITY BACKPLATES - DISTRICTWIDE (CN ONLY) | 9999 | Primary | Safety | VDOT | Richmond District-wide |  | Richmond | Richmond:Richmond District-wide | Infrastructure Investment/Asset Management Division | Ronnie Hobson | Ron.Hobson@vdot.virginia.gov | (804) 840-5501 | Ronnie Hobson | Ron.Hobson@vdot.virginia.gov | (804) 840-5501 | N\A |  |  | 0 |  | 0 | FY2020 | 2558230 | 2558230 | AWARDED | G | Start Delivery milestone finished 67 days early | G | Project is on budget | [10 empty] | 2019-10-08 | 2019-10-08 | 2020-02-21 | 2019-11-15 | G | [35 empty] | 2019-11-19 | 2020-01-02 | 2020-03-02 | 2020-01-02 | G | 2020-03-03 | 2020-01-02 | 2020-03-09 | 2020-01-02 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | WORK/TASK ORDER | 1 | 0 | 0.066482
1250 | 110887 | Rte 220 Access Management Improvements Project | 0220 | Primary | Safety | VDOT | Salem District-wide |  | Salem | Roanoke:Salem District-wide | Infrastructure Investment Division | Alex H Price | Alex.Price@VDOT.Virginia.gov | (540) 378-5053 | Brett A Elledge | Brett.Elledge@vdot.virginia.gov | (540) 375-3580 |  |  |  | 0 |  | 0 | FY2025 | 10196083 | 10196083 | ACTIVITY DATES SET | G | Determine Requirements milestone finished on-time | G | Project is on budget | [5 empty] | 2017-08-02 | 2017-08-02 | 2017-08-02 | 2017-08-02 | G | 2017-08-03 | 2017-08-03 | 2021-01-29 | 2021-01-29 | G | [5 empty] | 2021-03-26 |  | 2022-05-10 |  | G | 2022-12-09 |  | 2022-12-29 |  | G | 2023-10-26 |  | 2024-04-15 |  | G | 2023-01-30 |  | 2023-10-25 |  | G | [10 empty] | 2024-05-14 |  | 2024-05-14 |  | G | 2024-05-15 |  | 2024-10-14 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.15322
1251 | 111799 | Pedestrian Improvements in Downtown Floyd | 0221 | Miscellaneous | Facilities for Pedestrians and Bicycles | VDOT | Floyd County | CHRISTIANSBURG | Salem | NonMPO:NonMPO | Infrastructure Investment Division | Christopher L Price | Christopher.Price@VDOT.Virginia.gov | (540) 381-7182 | Leslie T Repass | Todd.Repass@VDOT.Virginia.gov | (540) 381-7195 |  |  |  | 0 |  | 0 | FY2020 | 1068590 | 1068590 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 44 days early | G | Project is on budget | [5 empty] | 2017-06-28 | 2017-06-28 | 2017-07-12 | 2017-08-14 | R | 2017-07-13 | 2017-10-12 | 2018-06-11 | 2018-05-15 | G | [5 empty] | 2018-07-13 | 2018-04-23 | 2018-07-26 | 2018-06-13 | G | 2019-01-17 | 2019-01-24 | 2019-02-01 | 2019-01-25 | G | 2019-01-03 | 2018-11-05 | 2019-02-15 | 2019-02-05 | G | 2019-02-20 | 2019-01-29 | 2019-04-02 | 2019-04-23 | R | 2018-09-12 | 2018-05-02 | 2018-10-24 | 2018-05-02 | G | [5 empty] | 2019-06-11 | 2019-07-23 | 2019-06-11 | 2019-07-23 | R | 2019-09-13 | 2019-09-25 | 2019-11-08 | 2019-09-25 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | SAAP CONTRACT | 1 | 0 | 0.10091
1253 | 113186 | BERKMAR DRIVE BICYCLE AND PEDESTRIAN IMPROVEMENTS | 1403 | Secondary | Facilities for Pedestrians and Bicycles | Locally | Albemarle County | CHARLOTTESVILLE | Culpeper | NonMPO:NonMPO | Local Assistance Division | Ken Connors |  |  | Thomas Fitzpatrick | Thomas.Fitzpatrick@vdot.virginia.gov |  | JACK KELSEY | jkelsey2@albemarle.org | (434) 296-5816 | 0 |  | 0 | FY2023 | 2647281 | 2647281 | NO DATES SET YET-PE OPEN | R | Determine Requirements milestone is 61 days past the expected completion date | G | Project is on budget | 2020-03-18 | 2019-10-16 | 2020-06-10 | 2019-10-18 | G | 2020-06-11 | 2019-11-19 | 2020-06-15 | 2019-11-22 | G | 2020-06-16 |  | 2020-12-22 |  | R | [10 empty] | 2021-12-27 |  | 2022-01-19 |  | G | [5 empty] | 2022-01-21 |  | 2022-10-27 |  | G | 2021-02-02 | 2020-08-25 | 2021-10-01 | 2021-01-22 | G | [5 empty] | 2022-11-15 |  | 2022-12-14 |  | G | 2023-03-09 |  | 2023-03-09 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.21016
1254 | 113388 | #SGR19VB - BR REPLACE SUPERSTRUCTURE 4TH STREET OVER I-95 | 0004 | Urban | Bridge Replacement w/o Added Capacity | VDOT | Richmond | ASHLAND | Richmond | Richmond:Richmond | Infrastructure Investment/Asset Management Division | Anthony S Haverly | Anthony.Haverly@vdot.virginia.gov | (804) 609-5225 | Anthony S Haverly | Anthony.Haverly@vdot.virginia.gov | (804) 609-5225 |  |  |  | 0 |  | 0 | FY2022 | 9311141 | 9311141 | NO DATES SET YET-PE OPEN | G | Start Development milestone finished on-time | G | Project is on budget | [5 empty] | 2018-08-16 | 2018-08-16 | 2018-08-23 | 2018-08-23 | G | 2018-08-24 | 2019-12-23 | 2021-06-30 |  | G | [10 empty] | 2021-06-25 |  | 2021-07-16 |  | G | [20 empty] | 2021-07-19 |  | 2021-08-16 |  | G | 2022-02-16 |  | 2022-03-16 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | DESIGN BUILD/PPTA | 0 | 0 | 0.066912
1255 | 113429 | GILLIES CREEK GREENWAY - PHASE III |  | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Richmond | ASHLAND | Richmond | Richmond:Richmond | Local Assistance Division | Jorg Huckabee-Mayfield | Jorg.Huckabee-Mayfield@VDOT.Virginia.gov | (804) 609-5292 | Jorg Huckabee-Mayfield | Jorg.Huckabee-Mayfield@VDOT.Virginia.gov | (804) 609-5292 | Adel Edward | Adel.Edward@Richmondgov.com | 804646658 | 0 |  | 0 | FY2023 | 525000 | 525000 | NO DATES SET YET-PE OPEN | Y | Determine Requirements milestone is 19 days ahead of the expected completion date and there is a risk of missing this milestone date | G | Project is on budget | 2019-10-02 | 2019-10-02 | 2020-02-14 | 2019-10-25 | G | 2020-02-25 | 2019-09-15 | 2020-03-09 | 2019-09-15 | G | 2020-08-31 |  | 2021-03-12 |  | Y | [25 empty] | 2020-11-09 |  | 2021-07-16 |  | G | [5 empty] | 2022-03-31 |  | 2022-04-27 |  | G | 2022-10-11 |  | 2022-10-11 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.35286
1256 | 113704 | #SGR19LP - Primary Extension RT 58 Westbound, Segment 3 | 0058 | Urban | Resurfacing | Locally | Suffolk | NORFOLK | Hampton Roads | Hampton Roads:Suffolk | Infrastructure Investment/Asset Management Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Johndel A Alcaide | John.Alcaide@vdot.virginia.gov | (757) 956-3098 | Ed Heide | eheide@suffolkva.us | (757) 514-7615 | 0 |  | 1 | FY2019 | 344000 | 344000 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished on-time | G | Project is on budget | 2018-09-04 | 2018-09-24 | 2018-11-30 | 2018-10-12 | G | 2018-12-03 | 2018-10-25 | 2018-12-05 | 2018-11-19 | G | 2018-12-06 | 2018-11-20 | 2019-06-13 | 2019-05-15 | G | [35 empty] | 2019-06-07 | 2019-06-07 | 2019-06-07 | 2019-06-07 | G | 2019-06-28 | 2019-06-27 | 2019-06-28 | 2019-06-28 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.068048
1257 | 115125 | #SMART20 Hot Springs - US 220 & VA 615 Int. Imp. | 0220 | Primary | Safety | VDOT | Bath County | LEXINGTON | Staunton | NonMPO:NonMPO | Infrastructure Investment Division | Randolph S Kiser | Randy.Kiser@VDOT.Virginia.gov | (540) 332-9092 | Timothy Gregory | Tim.Gregory@vdot.virginia.gov | (540) 332-7891 |  |  |  | 1 | 2020 | 0 | FY2028 | 560769 | 560769 | NO DATES SET YET | G | Start Development milestone is 904 days ahead of the expected completion date | G | Project is on budget | [5 empty] | 2023-08-01 |  | 2023-08-14 |  | G | 2023-08-15 |  | 2024-07-12 |  | G | [5 empty] | 2025-05-19 |  | 2025-06-02 |  | G | 2026-09-04 |  | 2026-09-18 |  | G | 2027-02-19 |  | 2027-08-23 |  | G | 2026-10-06 |  | 2027-04-16 |  | G | 2026-02-26 |  | 2026-08-28 |  | G | [5 empty] | 2027-09-14 |  | 2027-09-14 |  | G | 2027-12-08 |  | 2027-12-08 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.067082
1258 | 115733 | #SGR20LP - RT 165(Cedar Rd) Repaving | 0165 | Urban | Restoration and Rehabilitation | Locally | Chesapeake | NORFOLK | Hampton Roads | Hampton Roads:Chesapeake | Infrastructure Investment/Asset Management Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Johndel A Alcaide | John.Alcaide@vdot.virginia.gov | (757) 956-3098 | Sam Sawan | ssawan@cityofchesapeake.net | (757) 382-8263 | 0 |  | 1 | FY2020 | 365000 | 365000 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 33 days early | G | Project is on budget | 2019-10-01 | 2019-07-01 | 2019-12-30 | 2019-09-24 | G | [5 empty] | 2019-10-01 | 2019-10-01 | 2019-10-14 | 2019-10-14 | G | [35 empty] | 2020-05-18 | 2020-04-21 | 2020-06-15 | 2020-05-15 | G | 2020-06-30 | 2020-05-28 | 2020-06-30 | 2020-05-28 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.094688
1259 | 116626 | NOVA SYSTEMIC FLASHING YELLOW ARROWS PH2 | 9999 | Miscellaneous | Safety | VDOT | Northern Virginia District-wide |  | Northern Virginia | Northern Virginia:Northern Virginia District-wide | Infrastructure Investment/Asset Management Division | Waqar A Siddiqui | Sid.Siddiqui@VDOT.Virginia.gov | (703) 259-3225 | Tienjung Ho | Tien-Jung.Ho@VDOT.Virginia.gov | (703) 259-2752 |  |  |  | 0 |  | 0 | FY2021 | 4084997 | 4084997 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 29 days early | G | Project is on budget | [5 empty] | 2020-10-30 | 2020-02-26 | 2020-11-05 | 2020-03-03 | G | 2020-11-06 | 2020-03-04 | 2020-12-22 | 2020-07-29 | G | [5 empty] | 2020-07-29 | 2020-07-29 | 2020-07-29 | 2020-07-29 | G | [25 empty] | 2020-09-25 | 2020-09-01 | 2020-09-29 | 2020-09-02 | G | 2020-09-30 | 2020-09-02 | 2020-10-01 | 2020-09-02 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | WORK/TASK ORDER | 1 | 0 | 0.067796
1260 | 116719 | ITTF HIGH SPEED COMMUNICATIONS ARTERIALS - EASTERN | 9999 | Miscellaneous | Traffic Management/Engineering | VDOT | Statewide |  | Statewide | NonMPO:NonMPO | Infrastructure Investment Division | Catherine C Mcghee | Cathy.McGhee@VDOT.Virginia.gov | (434) 293-1973 | Jennifer Posey | Jennifer.Posey@vdot.virginia.gov | (757) 925-1691 |  |  |  | 0 |  | 0 | FY2020 | 258000 | 258000 | CONSTRUCTION STARTED | R | Start Delivery milestone finished 8 days late | G | Project is on budget | [10 empty] | 2020-03-02 | 2020-03-02 | 2020-07-07 | 2020-05-11 | G | [35 empty] | 2020-06-16 | 2020-06-18 | 2020-06-22 | 2020-06-24 | R | 2020-06-23 | 2020-06-25 | 2020-06-29 | 2020-07-07 | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | WORK/TASK ORDER | 1 | 1 | 0.25807
1261 | 116947 | PARK BOULEVARD SIDEWALK |  | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Marion | ABINGDON | Bristol | NonMPO:NonMPO | Local Assistance Division | John W Bechtold | John.Bechtold@vdot.virginia.gov | (276) 696-3365 | Roger L Musser | Roger.Musser@VDOT.Virginia.gov | (276) 696-3260 | Jeff Spickard | jspickard@marionva.org | (276) 706-2729 | 0 |  | 0 | FY2025 | 668000 | 668000 | NO DATES SET YET | G | Agreement with Locality milestone is 359 days ahead of the expected completion date | G | Project is on budget | 2021-10-01 |  | 2022-02-15 |  | G | 2022-02-16 |  | 2022-03-09 |  | G | 2022-04-07 |  | 2022-07-29 |  | G | [10 empty] | 2023-11-20 |  | 2023-12-27 |  | G | [5 empty] | 2023-12-28 |  | 2024-05-29 |  | G | 2024-04-25 |  | 2024-09-23 |  | G | [5 empty] | 2024-08-30 |  | 2024-09-27 |  | G | 2024-12-20 |  | 2024-12-20 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.24858
1262 | 117845 | LANDSCAPING - SYCOLIN ROAD | 0625 | Urban | Landscaping/Beautification | Locally | Leesburg | LEESBURG | Northern Virginia | Northern Virginia:Leesburg | Local Assistance Division | Kimberly Mccool | Kimberly.McCool@vdot.virginia.gov | (703) 259-3220 | Susie X Lue | Susie.Lue@vdot.virginia.gov | (703) 259-2918 | Anne Geiger, PE | AGeiger@leesburgva.gov | (703) 771-2742 | 0 |  | 0 | FY2022 | 95000 | 95000 | ACTIVITY DATES SET | G | Determine Requirements milestone finished 28 days early | G | Project is on budget | 2020-08-31 | 2020-08-31 | 2021-01-12 | 2021-01-04 | G | [5 empty] | 2021-01-13 | 2021-01-05 | 2021-02-26 | 2021-01-29 | G | [35 empty] | 2021-03-30 |  | 2021-06-29 |  | G | 2021-09-17 |  | 2021-11-15 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.42199
1263 | 105625 | Campbell Road Reconstruction | 0000 | Urban | Reconstruction w/o Added Capacity | Locally | Newport News | WILLIAMSBURG | Hampton Roads | Hampton Roads:Newport News | Local Assistance Division | Stephen Rowan | Steve.Rowan@vdot.virginia.gov | (757) 790-9925 | Chessica Villaflores | Chessica.Villaflores@vdot.virginia.gov | (757) 956-3094 | Thomas Cheney | cheneytc@nnva.gov | (757) 926-8715 | 0 |  | 0 | FY2019 | 8795092 | 8992606 | CONSTRUCTION STARTED | R | Start Delivery milestone finished 395 days late | Y | Project estimate is between $5M and $10M and is up to $1M over budget | [5 empty] | 2015-01-26 | 2015-01-26 | 2015-01-30 | 2015-01-30 | G | 2017-05-01 | 2017-05-01 | 2017-05-23 | 2017-05-23 | G | [10 empty] | 2017-04-03 | 2017-04-03 | 2018-11-30 | 2018-06-28 | G | [20 empty] | 2018-11-30 | 2019-11-25 | 2018-12-31 | 2019-12-27 | R | 2019-02-01 | 2020-02-07 | 2019-03-04 | 2020-04-02 | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.3
1264 | 106290 | Pedestrian Improvement on Fort Norfolk Site |  | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Norfolk | NORFOLK | Hampton Roads | Hampton Roads:Norfolk | Local Assistance Division | Bryant H Porter | Bryant.Porter@VDOT.Virginia.gov | (757) 956-3092 | Derrick Williams | Derrick.Williams@vdot.virginia.gov | (757) 956-3097 | Keith Darrow, P. E. | Keith.darrow@norfolk.gov | (757) 664-7305 | 0 |  | 0 | FY2021 | 550000 | 531427 | CONSTRUCTION STARTED | R | Start Delivery milestone finished 11 days late | G | Project is on budget | [5 empty] | 2018-03-22 | 2018-03-22 | 2018-03-27 | 2018-03-27 | G | 2018-03-28 | 2018-03-28 | 2019-03-28 | 2018-04-27 | G | [35 empty] | 2020-03-24 | 2020-03-24 | 2020-06-16 | 2020-06-14 | G | 2020-06-17 | 2020-06-15 | 2020-09-10 | 2020-09-21 | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.39672
1265 | 107300 | Riverlawn Court Trail | 0724 | Secondary | Facilities for Pedestrians and Bicycles | Locally | Pulaski County | CHRISTIANSBURG | Salem | NonMPO:NonMPO | Local Assistance Division | Adam J Czesnowski | Adam.Czesnowski@vdot.virginia.gov | (540) 541-1216 | Adam J Czesnowski | Adam.Czesnowski@vdot.virginia.gov | (540) 541-1216 | Jared Linkous | jlinkous@pulaskicounty.org | (540) 980-7710 | 0 |  | 0 | FY2021 | 558600 | 664580 | AWARDED | G | Start Delivery milestone finished 2 days early | Y | Project estimate is less than $5M and is up to 20% over budget | 2016-06-24 | 2016-06-24 | 2016-08-10 | 2016-08-10 | G | 2017-07-05 | 2017-07-05 | 2017-07-18 | 2017-07-18 | G | 2018-04-04 | 2019-02-01 | 2019-04-04 | 2019-10-01 | R | [10 empty] | 2019-12-31 | 2019-12-31 | 2019-12-31 | 2019-12-31 | G | [20 empty] | 2020-03-24 | 2020-03-24 | 2020-04-20 | 2020-04-19 | G | 2020-05-12 | 2020-09-01 | 2020-10-01 | 2020-09-29 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.1737
1266 | 109437 | #HB2.FY17 - Route 21 and 58 Intersection Radius Improvement | 0058 | Primary | Reconstruction w/o Added Capacity | VDOT | Grayson County | WYTHEVILLE | Bristol | NonMPO:NonMPO | Infrastructure Investment Division | Jeffrey R R Russell | J.Russell@VDOT.Virginia.gov | (276) 696-3286 | Jeremy J Mullins | Jeremy.Mullins@vdot.virginia.gov | (276) 696-3259 |  |  |  | 1 | 2017 | 0 | FY2019 | 250245 | 250245 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 90 days early | G | Project is on budget | [5 empty] | 2016-08-01 | 2016-08-01 | 2016-08-25 | 2016-08-25 | G | 2016-08-15 | 2016-08-15 | 2017-03-24 | 2017-03-24 | G | [5 empty] | 2017-07-12 | 2017-07-12 | 2017-07-25 | 2017-07-25 | G | 2018-04-03 | 2018-01-26 | 2018-04-16 | 2018-01-26 | G | 2018-05-30 | 2017-11-27 | 2018-10-19 | 2017-11-27 | G | 2018-05-02 | 2018-01-26 | 2018-10-22 | 2018-01-26 | G | 2017-12-08 | 2017-12-12 | 2018-12-10 | 2017-12-29 | G | [5 empty] | 2019-02-12 | 2018-11-06 | 2019-02-12 | 2018-11-06 | G | 2019-03-29 | 2019-02-22 | 2019-05-23 | 2019-02-22 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.086577
1267 | 109546 | #HB2.FY17 RTE 460 - LEFT & RIGHT TURN LANES AT RTE 609 | 0460 | Primary | Safety | VDOT | Appomattox County | APPOMATTOX | Lynchburg | NonMPO:NonMPO | Infrastructure Investment Division | Laura J Walton | Laura.Walton@VDOT.Virginia.gov | (434) 856-8286 | Gregory K Parsons | Gregory.Parsons@vdot.virginia.gov | (434) 856-8297 |  |  |  | 1 | 2017 | 0 | FY2019 | 1182981 | 1182981 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 23 days early | G | Project is on budget | [5 empty] | 2016-08-05 | 2016-08-05 | 2016-08-17 | 2016-08-17 | G | 2016-08-17 | 2016-08-17 | 2017-03-02 | 2017-03-01 | G | [5 empty] | 2017-07-10 | 2017-07-10 | 2017-07-21 | 2017-07-21 | G | 2017-12-01 | 2017-12-01 | 2017-12-14 | 2017-12-14 | G | 2018-07-31 | 2017-06-28 | 2019-02-20 | 2018-12-11 | G | 2018-01-25 | 2018-01-25 | 2018-07-30 | 2018-05-30 | G | 2018-01-25 | 2018-01-25 | 2018-09-25 | 2018-01-25 | G | [5 empty] | 2019-03-12 | 2019-03-12 | 2019-03-12 | 2019-03-12 | G | 2019-04-25 | 2019-05-28 | 2019-06-20 | 2019-05-28 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.098719
1268 | 110890 | #SGR18LB - BR MAINTENANCE - MELBOURNE RD OVER NS RAILROAD | 9999 | Urban | Bridge Rehab w/o Added Capacity | Locally | Charlottesville | CHARLOTTESVILLE | Culpeper | Charlottesville:Charlottesville | Infrastructure Investment Division | Ken Connors |  |  | Michael D Barnes | MichaelD.Barnes@vdot.virginia.gov | (434) 422-9861 | Kyle Kling | klingk@charlottesville.gov | (434) 970-3182 | 0 |  | 1 | FY2022 | 2440626 | 2721779 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 423 days early | Y | Project estimate is less than $5M and is up to 20% over budget | 2019-01-02 | 2019-01-02 | 2019-03-29 | 2019-01-10 | G | 2019-04-01 | 2019-01-10 | 2019-04-03 | 2019-01-24 | G | 2019-04-04 | 2019-01-25 | 2019-10-07 | 2019-06-11 | G | [10 empty] | 2020-10-08 | 2020-07-06 | 2020-10-29 | 2020-07-24 | G | [5 empty] | 2020-11-02 | 2020-07-28 | 2021-08-13 | 2020-08-10 | G | [10 empty] | 2021-08-31 | 2020-08-24 | 2021-09-28 | 2020-11-06 | G | 2021-09-29 | 2020-11-09 | 2022-01-06 | 2020-11-09 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.21109
1269 | 111314 | Depot Park Trail Extension |  | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Christiansburg | CHRISTIANSBURG | Salem | New River Valley:Christiansburg | Local Assistance Division | Adam J Czesnowski | Adam.Czesnowski@vdot.virginia.gov | (540) 541-1216 | Adam J Czesnowski | Adam.Czesnowski@vdot.virginia.gov | (540) 541-1216 | Justin St. Clair | jstclair@christiansburg.org | (540) 382-6120 | 0 |  | 0 | FY2021 | 440600 | 499045 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 190 days early | Y | Project estimate is less than $5M and is up to 20% over budget | 2017-10-02 | 2017-10-02 | 2017-11-06 | 2017-11-06 | G | 2017-12-06 | 2017-12-06 | 2017-12-07 | 2017-12-07 | G | 2017-12-08 | 2018-02-20 | 2018-12-06 | 2018-08-01 | G | [10 empty] | 2019-07-12 | 2019-05-23 | 2019-08-01 | 2019-05-23 | G | [5 empty] | 2019-08-05 | 2019-05-24 | 2020-01-27 | 2019-08-07 | G | [10 empty] | 2020-02-12 | 2019-08-15 | 2020-02-26 | 2019-09-15 | G | 2020-02-27 | 2019-11-05 | 2020-07-17 | 2020-01-09 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.24608
1270 | 116914 | TABOR/HILLTOP PEDESTRIAN IMPROVEMENTS |  | Secondary | Facilities for Pedestrians and Bicycles | Locally | Albemarle County | CHARLOTTESVILLE | Culpeper | Charlottesville:Albemarle County | Local Assistance Division | Gregory J Cooley | Gregory.Cooley@vdot.virginia.gov | (434) 906-7979 | Michael D Barnes | MichaelD.Barnes@vdot.virginia.gov | (434) 422-9861 | JACK KELSEY | jkelsey2@albemarle.org | (434) 760-1272 | 0 |  | 0 | FY2024 | 1205000 | 1205000 | NO DATES SET YET | R | Agreement with Locality milestone is 6 days past the expected completion date | G | Project is on budget | 2020-10-01 |  | 2021-02-15 |  | R | 2021-02-16 |  | 2021-03-09 |  | Y | 2021-09-13 |  | 2022-01-10 |  | G | [10 empty] | 2023-05-02 |  | 2023-06-06 |  | G | [5 empty] | 2023-06-07 |  | 2023-11-03 |  | G | 2023-10-02 |  | 2024-03-07 |  | G | [5 empty] | 2024-02-14 |  | 2024-03-13 |  | G | 2024-05-31 |  | 2024-05-31 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.31161
1271 | 117013 | #SGR21VB - RTE 757 OVER GREASY CR (STR. 4759)-SUPER REPLACE | 0757 | Secondary | Bridge Rehab w/o Added Capacity | VDOT | Carroll County | MARTINSVILLE | Salem | NonMPO:NonMPO | Infrastructure Investment Division | Anthony T Marshall | Todd.Marshall@VDOT.Virginia.gov | (540) 387-5460 | Leonard W Gisiner | Len.Gisiner@VDOT.Virginia.gov | (540) 387-5457 |  |  |  | 0 |  | 1 | FY2025 | 1269275 | 1269275 | NO DATES SET YET | G | Start Development milestone is 516 days ahead of the expected completion date | G | Project is on budget | [5 empty] | 2022-07-01 |  | 2022-07-22 |  | G | 2022-07-25 |  | 2023-05-26 |  | G | [5 empty] | 2023-10-20 |  | 2023-11-17 |  | G | [15 empty] | 2024-06-17 |  | 2024-11-14 |  | G | [5 empty] | 2025-02-11 |  | 2025-02-14 |  | G | 2025-05-06 |  | 2025-05-06 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.16545
1272 | 101042 | #SGR17VB - RT 778 - BRIDGE & APPROACHES OVER BUFFALO RIVER | 0778 | Secondary | Bridge Replacement w/o Added Capacity | VDOT | Amherst County | APPOMATTOX | Lynchburg | NonMPO:NonMPO | Infrastructure Investment/Asset Management Division | Renard Yeatts |  |  | Bryan S Witt | Bryan.Witt@VDOT.Virginia.gov | (434) 856-8319 |  |  |  | 0 |  | 1 | FY2019 | 2623363 | 2567099 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 21 days early | G | Project is on budget | [5 empty] | 2012-08-01 | 2012-08-10 | 2012-08-01 | 2012-08-10 | R | 2012-10-22 | 2012-10-21 | 2015-03-11 | 2015-03-03 | G | [5 empty] | 2015-01-06 | 2015-01-06 | 2015-03-03 | 2015-03-03 | G | 2015-07-13 | 2015-07-13 | 2015-07-24 | 2015-07-24 | G | 2016-05-31 | 2016-05-31 | 2017-05-12 | 2017-05-12 | G | 2015-09-09 | 2015-09-08 | 2016-05-11 | 2016-05-10 | G | 2016-10-17 | 2016-10-17 | 2017-06-29 | 2017-06-29 | G | [5 empty] | 2018-09-13 | 2018-10-09 | 2018-10-09 | 2018-10-09 | G | 2018-11-20 | 2018-12-27 | 2019-01-17 | 2018-12-27 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.057407
1273 | 105782 | Waterloo (Rte. 613) Bridge Restoration over Rappahannock R | 0613 | Secondary | Special Bridge | VDOT | Fauquier County | WARRENTON | Culpeper | NonMPO:NonMPO | Asset Management Division | Howard M Tomlinson | Howard.Tomlinson@VDOT.virginia.gov | (540) 829-7436 | Howard M Tomlinson | Howard.Tomlinson@VDOT.virginia.gov | (540) 829-7436 | Erin Kozanecki | erin.kozanecki@fauquiercounty.gov |  | 0 |  | 0 | FY2020 | 5100000 | 802911 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 74 days early | Y | Estimate not current | [5 empty] | 2018-07-02 | 2017-04-13 | 2018-07-02 | 2017-04-13 | G | 2017-05-17 | 2017-05-05 | 2020-12-01 | 2017-05-05 | G | [10 empty] | 2018-10-16 | 2018-10-16 | 2018-10-16 | 2018-10-16 | G | [20 empty] | 2019-10-08 | 2019-10-08 | 2019-10-08 | 2019-10-08 | G | 2020-02-03 | 2019-12-16 | 2020-02-28 | 2019-12-16 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.074632
1274 | 107176 | GLENSIDE DR - ADD SIDEWALK | 9999 | Secondary | Facilities for Pedestrians and Bicycles | Locally | Henrico County | ASHLAND | Richmond | Richmond:Henrico County | Local Assistance Division | Brian J Lokker | Brian.Lokker@VDOT.Virginia.gov | (804) 524-6010 | Brian J Lokker | Brian.Lokker@VDOT.Virginia.gov | (804) 524-6010 | Paul Smith | smi91@henrico.us | (804) 501-4617 | 0 |  | 0 | FY2019 | 267000 | 267000 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 8 days early | G | Project is on budget | 2015-07-01 | 2015-07-10 | 2015-09-24 | 2016-02-02 | R | 2015-09-25 | 2016-02-11 | 2015-10-08 | 2016-02-11 | R | 2015-10-09 | 2017-04-01 | 2016-06-08 | 2017-05-11 | R | [10 empty] | 2017-01-10 | 2017-01-10 | 2017-01-19 | 2017-01-19 | G | [20 empty] | 2017-06-15 | 2018-07-17 | 2017-10-06 | 2018-07-17 | R | 2018-07-10 | 2018-07-17 | 2018-07-25 | 2018-07-17 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.34626
1275 | 108980 | Briarfield Sidewalk | 0000 | Urban | Facilities for Pedestrians and Bicycles | Locally | Newport News | WILLIAMSBURG | Hampton Roads | Hampton Roads:Newport News | Infrastructure Investment Division | Stephen Rowan | Steve.Rowan@vdot.virginia.gov | (757) 790-9925 | Chessica Villaflores | Chessica.Villaflores@vdot.virginia.gov | (757) 956-3094 | Bryan Stilley | bstilley@nnva.gov | (757) 926-8699 | 0 |  | 0 | FY2023 | 814907 | 814907 | NO DATES SET YET-PE OPEN | G | Start Development milestone finished 22 days early | G | Project is on budget | 2020-01-15 | 2019-12-09 | 2020-04-10 | 2020-01-22 | G | 2020-04-13 | 2020-01-27 | 2020-04-24 | 2020-04-02 | G | 2020-04-27 |  | 2021-04-13 |  | G | [10 empty] | 2022-02-08 |  | 2022-03-01 |  | G | [5 empty] | 2022-03-03 |  | 2022-12-09 |  | G | 2020-12-09 |  | 2021-08-12 |  | G | [5 empty] | 2022-12-28 |  | 2023-01-27 |  | G | 2023-04-18 |  | 2023-04-18 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.25333
1276 | 109537 | #HB2.FY17 RTE 15 - CONSTRUCT ROUNDABOUT AT RTE 692 | 0015 | Primary | Safety | VDOT | Prince Edward County | DILLWYN | Lynchburg | NonMPO:NonMPO | Infrastructure Investment Division | Raina A Rosado | Raina.Rosado@VDOT.Virginia.gov | (434) 856-8318 | Gregory K Parsons | Gregory.Parsons@vdot.virginia.gov | (434) 856-8297 |  |  |  | 1 | 2017 | 0 | FY2021 | 2808037 | 2808037 | AWARDED | G | Start Delivery milestone finished 42 days early | G | Project is on budget | [5 empty] | 2016-08-17 | 2016-08-17 | 2016-08-17 | 2016-08-17 | G | 2016-08-19 | 2016-08-19 | 2017-07-19 | 2017-06-30 | G | [5 empty] | 2018-05-15 | 2018-05-15 | 2018-05-29 | 2018-05-29 | G | 2019-08-08 | 2019-04-16 | 2019-08-21 | 2019-04-19 | G | 2020-03-20 | 2019-06-03 | 2020-09-22 | 2020-05-14 | G | 2019-09-09 | 2019-05-13 | 2020-03-19 | 2020-03-18 | G | 2019-01-02 | 2019-01-02 | 2020-01-02 | 2019-01-02 | G | [5 empty] | 2020-10-13 | 2020-09-08 | 2020-10-13 | 2020-09-08 | G | 2020-12-08 | 2020-11-17 | 2020-12-29 | 2020-11-17 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.095798
1277 | 110827 | RTE 7 SHOULDER WIDENING & RUMBLE STRIPS | 0007 | Primary | Safety | VDOT | Clarke County | EDINBURG | Staunton | NonMPO:NonMPO | Infrastructure Investment/Asset Management Division | Keith M Rider | Keith.Rider@VDOT.Virginia.gov | (434) 856-8145 | Kunal Kothawade | Kunal.Kothawade@vdot.virginia.gov | (540) 332-9259 |  |  |  | 0 |  | 0 | FY2023 | 2240000 | 2240000 | NO DATES SET YET | G | Start Development milestone is 382 days ahead of the expected completion date | G | Project is on budget | [5 empty] | 2022-02-25 |  | 2022-03-10 |  | G | 2022-03-11 |  | 2022-04-07 |  | G | [35 empty] | 2023-03-14 |  | 2023-03-14 |  | G | 2023-04-26 |  | 2023-05-16 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.1003
1278 | 110968 | FOUR MILE CREEK VCT IMPROVEMENTS |  | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Henrico County | ASHLAND | Richmond | Richmond:Henrico County | Local Assistance Division | Jorg Huckabee-Mayfield | Jorg.Huckabee-Mayfield@VDOT.Virginia.gov | (804) 609-5292 | Jorg Huckabee-Mayfield | Jorg.Huckabee-Mayfield@VDOT.Virginia.gov | (804) 609-5292 | Steve Bandura | ban03@henrico.us | (804) 501-5985 | 0 |  | 0 | FY2021 | 847733 | 948579 | ACTIVITY DATES SET | R | Solicit Bids milestone is 319 days past the expected completion date | Y | Project estimate is less than $5M and is up to 20% over budget | 2018-05-01 | 2018-03-01 | 2018-07-25 | 2018-03-27 | G | 2018-07-26 | 2018-04-03 | 2018-07-30 | 2018-04-09 | G | 2018-07-31 | 2018-04-10 | 2019-02-08 | 2019-02-07 | G | [35 empty] | 2020-04-08 |  | 2020-04-08 |  | R | 2020-06-12 |  | 2021-03-23 |  | Y |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.4332
1279 | 111320 | #SGR18VB - WILSON BLVD OVER ARLINGTON BLVD - Fed 6685 | 0613 | Secondary | Bridge Rehab w/ Added Capacity | VDOT | Fairfax County | FAIRFAX | Northern Virginia | Northern Virginia:Fairfax County | Infrastructure Investment/Asset Management Division | Gary Runco | Gary.Runco@vdot.virginia.gov | (703) 259-3341 | Chandraratne B Basnayake | Chan.Basnayake@vdot.virginia.gov | (703) 259-2947 |  |  |  | 0 |  | 1 | FY2019 | 2500000 | 2500000 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 7 days early | G | Project is on budget | [5 empty] | 2017-08-01 | 2017-08-09 | 2017-08-14 | 2017-08-09 | G | 2017-08-15 | 2017-08-15 | 2017-09-12 | 2017-10-31 | R | [35 empty] | 2018-11-13 | 2018-11-20 | 2018-11-13 | 2018-11-20 | R | 2019-01-02 | 2019-02-22 | 2019-03-01 | 2019-02-22 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.076409
1280 | 111434 | #SGR18LB - REPLACE SUPERSTRUCT. & REPAIR SUBSTUCT(29759 Fed) | 0000 | Miscellaneous | Bridge Rehab w/o Added Capacity | Locally | Buchanan County | LEBANON | Bristol | NonMPO:NonMPO | Infrastructure Investment Division | John W Bechtold | John.Bechtold@vdot.virginia.gov | (276) 696-3365 | John W Bechtold | John.Bechtold@vdot.virginia.gov | (276) 696-3365 | Marcus Stiltner | marcus.stiltner@buchanancounty-va.gov | (276) 935-4013 | 0 |  | 1 | FY2021 | 92500 | 92500 | CONSTRUCTION STARTED | G | Start Delivery milestone finished on-time | G | Project is on budget | 2018-05-10 | 2018-02-01 | 2018-08-03 | 2018-04-02 | G | 2018-08-06 | 2018-04-03 | 2018-08-08 | 2018-04-05 | G | 2018-08-09 | 2018-04-06 | 2019-02-20 | 2019-02-19 | G | [35 empty] | 2020-01-14 | 2020-01-14 | 2020-04-09 | 2020-04-07 | G | 2020-04-10 | 2020-04-10 | 2020-07-06 | 2020-07-06 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.1003
1281 | 113134 | Roanoke St./Tower Rd./Hampton Blvd Intersection | 0000 | Urban | Reconstruction w/o Added Capacity | Locally | Christiansburg | CHRISTIANSBURG | Salem | New River Valley:Christiansburg | Local Assistance Division | Adam J Czesnowski | Adam.Czesnowski@vdot.virginia.gov | (540) 541-1216 | Adam J Czesnowski | Adam.Czesnowski@vdot.virginia.gov | (540) 541-1216 | Wayne Nelson | wnelson@christiansburg.org | (540) 382-6120 | 0 |  | 0 | FY2022 | 1942461 | 1942461 | ACTIVITY DATES SET | Y | Complete Purchasing Right-of-Way milestone is 59 days ahead of the expected completion date and there is a risk of missing this milestone date | G | Project is on budget | 2018-08-01 | 2018-08-01 | 2018-10-25 | 2019-01-07 | R | 2018-10-26 | 2019-01-07 | 2018-10-30 | 2019-01-07 | R | 2018-10-31 | 2019-01-29 | 2019-08-01 | 2020-04-15 | R | [10 empty] | 2020-06-30 | 2020-07-20 | 2020-07-21 | 2020-07-20 | G | [5 empty] | 2020-07-23 | 2020-07-21 | 2021-04-21 |  | Y | [10 empty] | 2021-04-22 |  | 2021-05-19 |  | G | 2021-10-12 |  | 2021-10-19 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.091801
1282 | 113413 | INTERSECTION IMPROVEMENTS AT RT 17/216 | 0017 | Primary | Reconstruction w/o Added Capacity | VDOT | Gloucester County | SALUDA | Fredericksburg | Hampton Roads:Gloucester County | Infrastructure Investment Division | Curtis B Holloway | Curtis.Holloway@vdot.virginia.gov | (540) 374-3367 | Curtis B Holloway | Curtis.Holloway@vdot.virginia.gov | (540) 374-3367 |  |  |  | 0 |  | 0 | FY2023 | 977900 | 977900 | ACTIVITY DATES SET | G | Engage Public milestone finished on-time | G | Project is on budget | [5 empty] | 2018-07-19 | 2018-06-08 | 2018-08-01 | 2018-06-21 | G | 2018-08-02 | 2018-06-22 | 2019-07-01 | 2019-10-02 | R | [5 empty] | 2021-01-01 | 2021-01-01 | 2021-01-15 | 2021-01-15 | G | 2021-12-23 |  | 2022-01-25 |  | G | 2022-08-29 |  | 2023-02-24 |  | G | 2022-02-25 |  | 2022-08-29 |  | G | [10 empty] | 2023-03-14 |  | 2023-03-14 |  | G | 2023-05-03 |  | 2023-06-28 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.08062
1283 | 113815 | #SGR19LP - Oyster Point Road Mill and Overlay | 0171 | Urban | Resurfacing | Locally | Newport News | WILLIAMSBURG | Hampton Roads | Hampton Roads:Newport News | Infrastructure Investment Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Chessica Villaflores | Chessica.Villaflores@vdot.virginia.gov | (757) 956-3094 | Bryan Stilley, P.E. | bstilley@nnva.gov | (757) 926-8699 | 0 |  | 1 | FY2019 | 653867 | 653867 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 14 days early | G | Project is on budget | 2018-09-04 | 2018-09-04 | 2018-11-30 | 2018-12-06 | R | 2018-12-03 | 2018-12-06 | 2018-12-05 | 2018-12-06 | R | 2018-12-06 | 2018-12-07 | 2019-06-13 | 2019-04-08 | G | [25 empty] | 2019-03-27 | 2019-03-26 | 2019-05-21 | 2019-03-26 | G | [5 empty] | 2019-06-07 | 2019-06-03 | 2019-06-07 | 2019-06-04 | G | 2019-06-28 | 2019-06-14 | 2019-06-28 | 2019-06-14 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.16318
1284 | 115244 | #SMART20 Virginia Beach Blvd Widening ??? George St to Newto | 0058 | Urban | Reconstruction w/ Added Capacity | Locally | Norfolk | NORFOLK | Hampton Roads | Hampton Roads:Norfolk | Infrastructure Investment Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Derrick Williams | Derrick.Williams@vdot.virginia.gov | (757) 956-3097 | Christine Fuller | christine.armstrong@norfolk.gov | (757) 664-7459 | 1 | 2020 | 0 | FY2029 | 15701021 | 15701021 | NO DATES SET YET | G | Agreement with Locality milestone is 976 days ahead of the expected completion date | Y | Estimate not current | 2023-08-01 |  | 2023-10-25 |  | G | 2023-10-26 |  | 2023-11-08 |  | G | 2023-11-09 |  | 2024-10-25 |  | G | [10 empty] | 2026-10-29 |  | 2026-11-19 |  | G | [5 empty] | 2026-11-23 |  | 2028-03-16 |  | G | 2024-06-26 |  | 2025-03-05 |  | G | [5 empty] | 2028-04-03 |  | 2028-04-28 |  | G | 2028-07-19 |  | 2028-07-19 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.39467
1285 | 115791 | Primary Extension - Galax - S Main St | 0089 | Urban | Reconstruction w/o Added Capacity | Locally | Galax | MARTINSVILLE | Salem | NonMPO:NonMPO | Local Assistance Division | Jessie Nester | Jessie.Nester@vdot.virginia.gov | (540) 613-4115 | Jessie Nester | Jessie.Nester@vdot.virginia.gov | (540) 613-4115 | Keith Barker | kbarker@galaxva.com | (276) 236-5773 | 0 |  | 0 | FY2020 | 190634 | 190634 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 202 days early | G | Project is on budget | 2020-01-02 | 2019-07-02 | 2020-03-30 | 2019-08-07 | G | 2020-03-31 | 2019-08-07 | 2020-04-02 | 2019-08-07 | G | 2020-04-03 | 2019-08-13 | 2020-10-06 | 2019-09-17 | G | [25 empty] | 2019-08-22 | 2019-08-21 | 2019-11-22 | 2019-08-21 | G | [5 empty] | 2019-12-11 | 2019-10-31 | 2019-12-31 | 2019-11-15 | G | 2020-03-24 | 2019-12-06 | 2020-06-30 | 2019-12-11 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.084463
1286 | 116320 | FAIRFAX COUNTY CIVIL WAR BICYCLE TOUR - HISTORICAL MARKERS |  | Enhancement | Historic Preservation | Locally | Fairfax County | FAIRFAX | Northern Virginia | Northern Virginia:Fairfax County | Local Assistance Division | Amir Salahshoor | A.Salahshoor@VDOT.Virginia.gov | (703) 259-1957 | Jeffrey S Daily | Jeff.Daily@VDOT.Virginia.gov | (703) 259-2993 | Negin Askarzadeh | Negin.Askarzadeh@fairfaxcounty.gov | (703) 877-5773 | 0 |  | 0 | FY2021 | 30000 | 24840 | ADVERTISED | R | Start Delivery milestone is 115 days past the expected completion date | G | Project is on budget | 2019-10-01 | 2019-09-30 | 2019-10-31 | 2019-10-30 | G | [5 empty] | 2019-11-01 | 2019-10-31 | 2019-11-15 | 2019-11-14 | G | [25 empty] | 2019-10-31 | 2019-10-31 | 2020-02-27 | 2019-10-31 | G | [5 empty] | 2020-02-05 | 2020-02-05 | 2020-03-30 | 2021-01-04 | R | 2020-06-17 |  | 2020-10-29 |  | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.28431
1287 | 117145 | #SGR21LP City of Hampton 447 Mercury Blvd W | 0258 | Urban | Resurfacing | Locally | Hampton | WILLIAMSBURG | Hampton Roads | Hampton Roads:Hampton | Infrastructure Investment/Asset Management Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Derrick Williams | Derrick.Williams@vdot.virginia.gov | (757) 956-3097 | Sandon Rogers | Sandon.rogers@hampton.gov | (757) 727-6786 | 0 |  | 1 | FY2022 | 565000 | 565000 | NO DATES SET YET | G | Agreement with Locality milestone is 80 days ahead of the expected completion date | G | Project is on budget | 2021-01-04 |  | 2021-05-12 |  | G | 2021-05-13 |  | 2021-06-03 |  | G | 2021-07-02 |  | 2021-07-30 |  | G | [25 empty] | 2021-07-02 |  | 2021-07-30 |  | G | [5 empty] | 2021-09-28 |  | 2021-10-26 |  | G | 2022-01-21 |  | 2022-01-21 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.097283
1288 | 118166 | Kirk Avenue Drainage Improvements | 0000 | Urban | Mitigation of Water Pollution Due to Highway Runof | Locally | Roanoke | SALEM | Salem | Roanoke:Roanoke City | Local Assistance Division | Cheryl B Becker | Cheryl.Becker@vdot.virginia.gov | (540) 492-2531 | Cheryl B Becker | Cheryl.Becker@vdot.virginia.gov | (540) 492-2531 | Joseph Arthur | Joseph.Arthur@roanokeva.gov | (540) 853-5901 | 0 |  | 0 | FY2028 | 252000 | 252000 | NO DATES SET YET | G | Agreement with Locality milestone is 1422 days ahead of the expected completion date | G | Project is on budget | 2024-08-30 |  | 2025-01-13 |  | G | 2025-01-14 |  | 2025-02-05 |  | G | 2025-08-12 |  | 2025-12-08 |  | G | [10 empty] | 2027-04-01 |  | 2027-05-05 |  | G | [5 empty] | 2027-05-06 |  | 2027-10-04 |  | G | 2027-08-31 |  | 2028-02-04 |  | G | [5 empty] | 2028-01-12 |  | 2028-02-10 |  | G | 2028-05-01 |  | 2028-05-01 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.2029
1289 | 75878 | #SGR19LB??- RT 20 - BRIDGE REPLACEMENT | 0020 | Urban | Bridge Replacement w/o Added Capacity | Locally | Charlottesville | CHARLOTTESVILLE | Culpeper | Charlottesville:Charlottesville | Infrastructure Investment Division | William E Stowe | William.Stowe@vdot.virginia.gov | (540) 827-7287 | Michael D Barnes | MichaelD.Barnes@vdot.virginia.gov | (434) 422-9861 | Jeanette Janiczek | JANICZEK@charlottesville.org | (434) 970-3182 | 0 |  | 0 | FY2020 | 25187399 | 31100043 | ADVERTISED | R | Start Delivery milestone is 264 days past the expected completion date | R | Project estimate is greater than $10M and is over budget by (a) 10% or more or (b) $5M or more | [5 empty] | 2005-06-20 | 2005-06-19 | 2005-12-01 | 2005-12-01 | G | 2009-02-02 | 2017-01-01 | 2018-06-01 | 2018-05-29 | G | [10 empty] | 2018-06-01 | 2018-05-30 | 2019-07-30 | 2019-07-15 | G | [20 empty] | 2020-01-31 | 2020-11-14 | 2020-04-06 | 2021-01-15 | R | 2020-06-02 |  | 2020-06-02 |  | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.17609
1290 | 112353 | #SGR18LB - REPLACE SUPERSTRUCT & REPAIR SUBSTRUCT(29808 Fed) | 0000 | Miscellaneous | Bridge Replacement w/o Added Capacity | Locally | Buchanan County | LEBANON | Bristol | NonMPO:NonMPO | Infrastructure Investment/Asset Management Division | John W Bechtold | John.Bechtold@vdot.virginia.gov | (276) 696-3365 | Roger L Musser | Roger.Musser@VDOT.Virginia.gov | (276) 696-3260 | Marcus Stiltner | marcus.stiltner@buchanancounty-va.gov | (276) 935-4013 | 0 |  | 1 | FY2023 | 265000 | 265000 | ACTIVITY DATES SET | G | Determine Requirements milestone finished on-time | G | Project is on budget | 2019-01-15 | 2018-02-01 | 2019-04-11 | 2018-04-02 | G | 2019-04-12 | 2018-04-03 | 2019-04-16 | 2018-04-05 | G | 2019-04-17 | 2018-04-06 | 2019-10-18 | 2019-10-18 | G | [35 empty] | 2023-02-15 |  | 2023-04-14 |  | G | 2023-04-17 |  | 2023-06-09 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.043087
1291 | 113331 | PHASE II - BUS 58 - RECONSTRUCTION (ARNETT TO LOCUST) | 0058 | Urban | Reconstruction w/o Added Capacity | Locally | Danville | HALIFAX | Lynchburg | Danville:Danville | Local Assistance Division | Sharon S White | Sharon.White@VDOT.Virginia.gov | (434) 856-8220 | Sharon S White | Sharon.White@VDOT.Virginia.gov | (434) 856-8220 | Brian Dunevant, P.E. | dunevbl@danville.va.gov | (434) 799-5019 | 0 |  | 0 | FY2021 | 1082374 | 1082374 | AWARDED | G | Start Delivery milestone finished on-time | G | Project is on budget | 2020-01-28 | 2019-08-01 | 2020-04-21 | 2019-08-23 | G | 2020-04-22 | 2019-08-26 | 2020-04-24 | 2019-08-28 | G | 2020-04-27 | 2019-08-29 | 2020-10-29 | 2020-06-17 | G | [10 empty] | 2020-06-19 | 2020-06-19 | 2020-06-19 | 2020-06-19 | G | [5 empty] | 2020-06-23 | 2020-06-23 | 2020-06-23 | 2020-06-23 | G | [10 empty] | 2020-08-04 | 2020-08-04 | 2020-08-31 | 2020-08-31 | G | 2020-12-30 | 2020-12-29 | 2020-12-30 | 2020-12-30 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.070835
1292 | 113428 | Appalachia - Big Stone Gap Trail and Trailhead Project |  | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Appalachia | WISE | Bristol | NonMPO:NonMPO | Local Assistance Division | John W Bechtold | John.Bechtold@vdot.virginia.gov | (276) 696-3365 | Kenneth R Plummer | KR.Plummer@VDOT.Virginia.gov | (276) 696-3261 | Fred Luntsford | fluntsford@townofappalachiava.us | (276) 565-3910 | 0 |  | 0 | FY2021 | 207986 | 207986 | ADVERTISED | G | Solicit Bids milestone finished 85 days early | G | Project is on budget | 2020-09-01 | 2018-08-01 | 2020-11-30 | 2018-11-30 | G | 2020-12-01 | 2019-01-08 | 2020-12-03 | 2019-01-10 | G | 2020-12-04 | 2019-01-11 | 2021-06-11 | 2021-01-06 | G | [10 empty] | 2021-02-01 | 2020-12-01 | 2021-02-12 | 2020-12-01 | G | [5 empty] | 2021-02-16 | 2020-12-03 | 2021-02-16 | 2020-12-03 | G | [10 empty] | 2021-03-05 | 2020-12-08 | 2021-04-02 | 2021-01-07 | G | 2021-06-22 |  | 2021-06-22 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.34579
1293 | 114721 | Little Creek Corridor (PSAP) | 0165 | Urban | Facilities for Pedestrians and Bicycles | Locally | Norfolk | NORFOLK | Hampton Roads | Hampton Roads:Norfolk | Infrastructure Investment Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Derrick Williams | Derrick.Williams@vdot.virginia.gov | (757) 956-3097 | Keith Darrow, P. E. | keith.darrow@norfolk.gov | (757) 664-7857 | 0 |  | 0 | FY2020 | 285000 | 285000 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished on-time | G | Project is on budget | 2019-03-18 | 2019-03-18 | 2019-06-10 | 2019-08-28 | R | 2019-06-11 | 2019-08-28 | 2019-06-24 | 2019-08-28 | R | 2019-06-25 | 2019-08-29 | 2020-06-08 | 2019-12-11 | G | [35 empty] | 2019-12-10 | 2019-12-10 | 2020-01-16 | 2020-01-16 | G | 2020-03-13 | 2020-03-13 | 2020-04-20 | 2020-04-20 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.22998
1294 | 115787 | Primary Extension - Martinsville - S Memorial Blvd | 0220 | Urban | Reconstruction w/o Added Capacity | Locally | Martinsville | MARTINSVILLE | Salem | NonMPO:NonMPO | Local Assistance Division | Jessie Nester | Jessie.Nester@vdot.virginia.gov | (540) 613-4115 | Jessie Nester | Jessie.Nester@vdot.virginia.gov | (540) 613-4115 | Leon Towarnicki | ltowarnicki@ci.martinsville.va.us | (276) 403-5185 | 0 |  | 0 | FY2020 | 175000 | 175000 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 155 days early | G | Project is on budget | 2020-01-02 | 2019-07-02 | 2020-03-30 | 2019-09-19 | G | 2020-03-31 | 2019-09-19 | 2020-04-02 | 2019-09-19 | G | 2020-04-03 | 2019-09-26 | 2020-10-06 | 2019-10-02 | G | [35 empty] | 2019-12-31 | 2019-12-17 | 2019-12-31 | 2019-12-31 | G | 2020-01-27 | 2020-01-24 | 2020-06-30 | 2020-01-27 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.084428
1295 | 116279 | #I81CIP SB MM 221 TO 220, AUXILIARY LANE (ID #58) | 0081 | Interstate | Reconstruction w/ Added Capacity | VDOT | Augusta County | HARRISONBURG | Staunton | SAW:Augusta County | Infrastructure Investment Division | John-Allen L Ennis | JohnAllen.Ennis@VDOT.Virginia.gov | (540) 332-9118 | Jennifer Hoover | Jennifer.Hoover@vdot.virginia.gov | (540) 332-2264 |  |  |  | 0 |  | 0 | FY2025 | 14326755 | 14326755 | NO DATES SET YET-PE OPEN | G | Start Development milestone finished 159 days early | G | Project is on budget | [5 empty] | 2020-07-01 | 2020-01-27 | 2020-07-15 | 2020-02-07 | G | 2020-07-16 |  | 2021-08-24 |  | G | [5 empty] | 2022-08-23 |  | 2022-09-06 |  | G | 2023-12-05 |  | 2023-12-18 |  | G | 2024-05-15 |  | 2024-11-19 |  | G | 2024-01-05 |  | 2024-07-11 |  | G | 2023-05-22 |  | 2024-01-29 |  | G | [5 empty] | 2024-12-10 |  | 2024-12-10 |  | G | 2025-04-03 |  | 2025-04-03 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.090652
1296 | 116385 | #I81CIP SWRO SSP | 0081 | Interstate | Safety | VDOT | Roanoke County | SALEM | Salem | NonMPO:NonMPO | Infrastructure Investment Division | Ricky A Via | Ricky.Via@vdot.virginia.gov | (804) 371-2396 | Timothy L Martin | TimL.Martin@VDOT.Virginia.gov | (540) 375-0113 |  |  |  | 0 |  | 0 | FY2021 | 7432790 | 7432790 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 6 days early | G | Project is on budget | [10 empty] | 2020-05-01 | 2020-05-01 | 2020-09-08 | 2020-08-26 | G | [35 empty] | 2020-08-26 | 2020-08-26 | 2020-08-26 | 2020-08-26 | G | 2020-08-27 | 2020-08-27 | 2020-09-02 | 2020-08-27 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | WORK/TASK ORDER | 1 | 0 | 0.13722
1297 | 117991 | DELTAVILLE MULTI-MODAL PROJECT | 0033 | Miscellaneous | Facilities for Pedestrians and Bicycles | VDOT | Middlesex County | SALUDA | Fredericksburg | NonMPO:NonMPO | Local Assistance Division | Catherine C Coffey | Catherine.Coffey@vdot.virginia.gov | (540) 899-4280 | Anastasia Kapitan | Anastasia.Kapitan@vdot.virginia.gov | (540) 899-4292 | Marc Longest | m.longest@co.middlesex.va.us | (804) 758-3382 | 0 |  | 0 | FY2024 | 1001175 | 1001175 | NO DATES SET YET | Y | Start Development milestone is 26 days ahead of the expected completion date and there is a risk of missing this milestone date | G | Project is on budget | [5 empty] | 2021-03-01 |  | 2021-03-19 |  | Y | 2021-03-22 |  | 2022-01-24 |  | G | [5 empty] | 2022-08-19 |  | 2022-09-16 |  | G | 2023-05-12 |  | 2023-06-16 |  | G | 2023-11-16 |  | 2024-03-22 |  | G | 2023-07-03 |  | 2023-12-04 |  | G | 2023-08-09 |  | 2024-01-11 |  | G | [5 empty] | 2024-04-09 |  | 2024-04-09 |  | G | 2024-06-27 |  | 2024-06-27 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.11584
1298 | 16314 | Penniman Rd/Government Rd/ROADWAY IMPROVEMENTS | 0641 | Secondary | Reconstruction w/o Added Capacity | VDOT | York County | WILLIAMSBURG | Hampton Roads | Hampton Roads:York County | Infrastructure Investment Division | Kenneth D Mckinna | Kenneth.McKinna@VDOT.Virginia.gov | (757) 956-3271 | Kenneth D Mckinna | Kenneth.McKinna@VDOT.Virginia.gov | (757) 956-3271 |  |  |  | 0 |  | 0 | FY2023 | 5744330 | 5553961 | ACTIVITY DATES SET | R | Start Purchasing Right-of-Way milestone finished 9 days late | G | Project is on budget | [5 empty] | 2000-07-17 | 2000-08-23 | 2000-09-29 | 2000-08-24 | G | 2018-03-14 | 2018-03-14 | 2018-04-27 | 2019-08-23 | R | 2018-11-06 | 2019-09-12 | 2019-09-12 | 2019-09-12 | G | [5 empty] | 2020-03-11 | 2020-03-18 | 2020-03-24 | 2020-04-02 | R | 2021-04-21 |  | 2022-02-16 |  | G | 2020-03-30 | 2020-07-08 | 2021-04-06 |  | Y | [10 empty] | 2022-05-10 |  | 2022-05-10 |  | G | 2022-07-22 |  | 2022-07-22 |  | G | Delay due to scope of work change/Project Management change/plan or design change | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.18899
1299 | 100708 | Corridor Q - 460 Connector Phase II Finish Grade | 0460 | Primary | New Construction Roadway | VDOT | Buchanan County | LEBANON | Bristol | NonMPO:NonMPO | Infrastructure Investment Division | Marty R Halloway | Marty.Halloway@VDOT.Virginia.gov | (276) 696-3367 | Stephen Warner Gray | Stephen.Gray@vdot.virginia.gov | (276) 619-1389 |  |  |  | 0 |  | 0 | FY2025 | 38890794 | 38890794 | NO DATES SET YET | R | Start Development milestone is 186 days past the expected completion date | G | Project is on budget | [5 empty] | 2020-07-30 | 2020-04-03 | 2020-08-19 |  | R | 2020-08-20 |  | 2021-11-02 |  | G | [5 empty] | 2022-12-02 |  | 2023-01-18 |  | G | [15 empty] | 2023-10-09 |  | 2024-06-14 |  | G | [5 empty] | 2024-09-10 |  | 2024-09-10 |  | G | 2024-12-03 |  | 2024-12-03 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.13587
1300 | 100822 | #HB2.FY17 PHASE I - MOUNT CROSS ROAD WIDENING | 0000 | Urban | Reconstruction w/ Added Capacity | Locally | Danville | HALIFAX | Lynchburg | Danville:Danville | Infrastructure Investment Division | Sharon S White | Sharon.White@VDOT.Virginia.gov | (434) 856-8220 | Sharon S White | Sharon.White@VDOT.Virginia.gov | (434) 856-8220 | Brian Dunevant | bdunevant@ci.danville.va.us | (434) 799-5019 | 1 | 2017 | 0 | FY2019 | 5730000 | 6275383 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 157 days early | Y | Project estimate is between $5M and $10M and is up to $1M over budget | [5 empty] | 2012-03-08 | 2012-03-08 | 2012-03-08 | 2012-03-08 | G | 2013-09-01 | 2013-08-20 | 2014-03-15 | 2013-12-03 | G | [10 empty] | 2016-08-23 | 2016-08-23 | 2016-08-23 | 2016-08-23 | G | 2017-09-15 | 2017-09-15 | 2018-09-18 | 2018-03-22 | G | 2016-09-20 | 2016-09-20 | 2020-08-21 | 2016-09-20 | G | [10 empty] | 2018-09-17 | 2018-05-30 | 2019-01-31 | 2018-07-19 | G | 2019-02-28 | 2018-08-15 | 2019-03-22 | 2018-10-16 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.11046
1301 | 106055 | Green Circle Trail - Jubal Early Segment |  | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Winchester | EDINBURG | Staunton | Winchester:Winchester | Local Assistance Division | Kimberly Cameron | Kim.Cameron@vdot.virginia.gov | (540) 332-7886 | Kimberly Cameron | Kim.Cameron@vdot.virginia.gov | (540) 332-7886 | Perry Eisenach | Perry.Eisenach@winchester.va.gov | (540) 535-3660 | 0 |  | 0 | FY2020 | 350000 | 941132 | CONSTRUCTION STARTED | R | Start Delivery milestone finished 213 days late | R | Project estimate is less than $5M and is 20% or more over budget | [5 empty] | 2016-10-03 | 2016-09-21 | 2016-10-03 | 2016-10-03 | G | 2016-11-01 | 2016-10-26 | 2017-11-30 | 2017-11-30 | G | [10 empty] | 2019-04-02 | 2019-04-02 | 2019-04-02 | 2019-04-02 | G | [20 empty] | 2019-10-01 | 2019-09-19 | 2019-10-01 | 2019-09-19 | G | 2019-10-18 | 2019-10-08 | 2019-11-15 | 2020-06-15 | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.37168
1302 | 107726 | CITY OF DANVILLE - MULTI USE TRAIL PHASE VII |  | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Danville | HALIFAX | Lynchburg | Danville:Danville | Local Assistance Division | Sharon S White | Sharon.White@VDOT.Virginia.gov | (434) 856-8220 | Sharon S White | Sharon.White@VDOT.Virginia.gov | (434) 856-8220 | Brian Dunevant | dunevbl@ci.danville.va.us | (434) 799-5019 | 0 |  | 0 | FY2020 | 406927 | 406927 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 7 days early | G | Project is on budget | 2015-10-01 | 2015-10-01 | 2015-12-30 | 2016-03-18 | R | 2015-12-31 | 2015-12-31 | 2016-01-14 | 2016-03-18 | R | 2016-01-19 | 2016-06-01 | 2016-09-08 | 2016-11-10 | R | [10 empty] | 2019-03-11 | 2018-12-12 | 2019-03-11 | 2018-12-12 | G | [20 empty] | 2017-01-04 | 2019-02-11 | 2017-04-28 | 2019-03-08 | R | 2019-03-22 | 2019-03-11 | 2019-07-29 | 2019-07-22 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.18903
1303 | 108649 | RTE 5 (MAIN STREET) - NEW ROAD | 0005 | Primary | Relocation | Locally | Richmond | ASHLAND | Richmond | Richmond:Richmond | Local Assistance Division | Evan Austin | Evan.Austin@vdot.virginia.gov | (804) 609-5384 | Evan Austin | Evan.Austin@vdot.virginia.gov | (804) 609-5384 | Lamont Banjamin | lamont.benjamin@richmondgov.co | (804) 646-6339 | 0 |  | 0 | FY2020 | 2300000 | 2800000 | ACTIVITY DATES SET | R | Complete Purchasing Right-of-Way milestone is 1482 days past the expected completion date | Y | Project estimate is less than $5M and is up to 20% over budget | 2017-01-31 | 2016-07-01 | 2017-04-25 | 2016-09-26 | G | 2017-04-26 | 2017-01-29 | 2017-04-28 | 2017-01-29 | G | 2017-05-01 | 2016-08-09 | 2017-11-02 | 2018-01-30 | R | [10 empty] | 2017-01-31 | 2020-08-05 | 2017-01-31 | 2020-08-20 | R | [5 empty] | 2017-01-31 |  | 2017-01-31 |  | R | [10 empty] | 2019-09-27 |  | 2019-10-25 |  | R | 2019-10-28 |  | 2020-01-21 |  | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.20189
1304 | 109272 | EVERGREEN MILLS RD INT. IMPROVEMENTS AT RELOCATED RTE 771 | 0621 | Secondary | Reconstruction w/o Added Capacity | VDOT | Loudoun County | LEESBURG | Northern Virginia | Northern Virginia:Loudoun County | Infrastructure Investment Division | Kimberly Mccool | Kimberly.McCool@vdot.virginia.gov | (703) 259-3220 | Mehrdad Naderi | Mehrdad.Naderi@vdot.virginia.gov | (703) 259-2217 | Susan Glass, Loudoun County Dept. of Transportation & Capital Infrastructure | susan.glass@loudoun.gov | (703) 777-0251 | 0 |  | 0 | FY2019 | 2350000 | 2465000 | CONSTRUCTION COMPLETED | R | Start Delivery milestone finished 281 days late | Y | Project estimate is less than $5M and is up to 20% over budget | [10 empty] | 2017-06-06 | 2017-06-06 | 2017-06-16 | 2017-06-16 | G | [10 empty] | 2017-07-11 | 2017-06-23 | 2017-07-24 | 2017-07-19 | G | 2017-12-20 | 2019-09-26 | 2018-05-30 | 2019-10-16 | R | 2017-08-09 | 2017-07-19 | 2018-02-20 | 2018-08-13 | R | 2017-03-17 | 2017-03-17 | 2017-03-20 | 2017-03-20 | G | [5 empty] | 2018-06-12 | 2019-03-12 | 2018-06-12 | 2019-03-12 | R | 2018-08-02 | 2019-05-28 | 2018-08-22 | 2019-05-30 | R | Project is late due to a decision / action on the part of the locality (Board of Supervisors, Council, officials) | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 1 | 0.21886
1305 | 109538 | #HB2.FY17 BUS 29 - RIGHT TURN LANE @ RTE 1466 (LYNCHMILL RD) | 0029 | Primary | Safety | VDOT | Altavista | APPOMATTOX | Lynchburg | NonMPO:NonMPO | Infrastructure Investment Division | Daniel J Brown | Daniel.Brown@VDOT.Virginia.gov | (434) 856-8265 | Lindsey S Hodges | Lindsey.Hodges@vdot.virginia.gov | (434) 856-8143 |  |  |  | 1 | 2017 | 0 | FY2020 | 2370161 | 2195907 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 12 days early | G | Project is on budget | [5 empty] | 2016-08-16 | 2016-08-16 | 2016-08-17 | 2016-08-17 | G | 2016-08-18 | 2016-08-18 | 2017-04-12 | 2017-04-21 | R | [5 empty] | 2017-08-23 | 2017-08-23 | 2017-09-06 | 2017-09-06 | G | 2018-07-18 | 2018-07-23 | 2018-07-31 | 2018-08-01 | R | 2019-02-13 | 2019-01-25 | 2019-08-02 | 2019-10-17 | R | 2018-08-16 | 2018-08-13 | 2019-02-12 | 2018-12-14 | G | 2018-02-23 | 2018-02-23 | 2018-08-27 | 2018-08-02 | G | [5 empty] | 2019-08-13 | 2019-08-13 | 2019-08-13 | 2019-08-13 | G | 2019-09-27 | 2019-11-13 | 2019-11-25 | 2019-11-13 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.099638
1306 | 109923 | Alternate Route 58 Shoulder Initiative -Lee Co. | 0058 | Primary | Safety | VDOT | Bristol District-wide |  | Bristol | NonMPO:NonMPO | Infrastructure Investment Division | Chase R Buchanan | Chase.Buchanan@VDOT.Virginia.gov | (276) 696-3251 | Jonathan A Henegar | Jonathan.Henegar@vdot.virginia.gov | (276) 206-0360 |  |  |  | 0 |  | 0 | FY2022 | 1686467 | 1686467 | ACTIVITY DATES SET | R | Relocate Utilities milestone is 74 days past the expected completion date | G | Project is on budget | [5 empty] | 2019-10-01 | 2019-10-01 | 2019-10-14 | 2019-10-11 | G | 2019-10-15 | 2019-10-15 | 2020-06-10 | 2020-05-06 | G | [5 empty] | 2020-07-31 | 2020-07-08 | 2020-07-31 | 2020-07-08 | G | [5 empty] | 2020-09-25 |  | 2020-12-09 |  | R | [15 empty] | 2021-03-09 |  | 2021-03-09 |  | Y | 2021-04-28 |  | 2021-10-15 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.069065
1307 | 111005 | Western Branch Blvd Flashing Yellow Arrows (FYA) |  | Urban | Safety | Locally | Chesapeake | NORFOLK | Hampton Roads | Hampton Roads:Chesapeake | Infrastructure Investment Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Johndel A Alcaide | John.Alcaide@vdot.virginia.gov | (757) 956-3098 | Sam Sawan, PE | sawan@cityofchesapeake.net | (757) 682-8263 | 0 |  | 0 | FY2023 | 159000 | 159000 | NO DATES SET YET-PE OPEN | G | Obtained Permits milestone finished 785 days early | G | Project is on budget | 2020-09-30 | 2020-07-15 | 2021-02-12 | 2020-08-26 | G | 2021-02-15 | 2020-08-28 | 2021-03-08 | 2020-09-14 | G | 2021-04-06 |  | 2021-07-28 |  | G | [25 empty] | 2022-07-25 | 2020-10-29 | 2022-12-23 | 2020-10-29 | G | [5 empty] | 2023-02-27 |  | 2023-03-24 |  | G | 2023-06-13 |  | 2023-06-13 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.20395
1308 | 111319 | Town of Blacksburg - Bike Parking |  | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Blacksburg | CHRISTIANSBURG | Salem | New River Valley:Blacksburg | Local Assistance Division | Adam J Czesnowski | Adam.Czesnowski@vdot.virginia.gov | (540) 541-1216 | Adam J Czesnowski | Adam.Czesnowski@vdot.virginia.gov | (540) 541-1216 | Joshua Middleton | JMiddleton@blacksburg.gov | (540) 443-1353 | 0 |  | 0 | FY2020 | 160885 | 160885 | AWARDED | G | Start Delivery milestone finished 15 days early | G | Project is on budget | 2017-10-02 | 2017-10-02 | 2018-03-30 | 2018-01-26 | G | 2018-04-02 | 2018-03-01 | 2018-04-04 | 2018-03-12 | G | 2018-04-05 | 2018-04-03 | 2019-04-08 | 2018-08-03 | G | [35 empty] | 2019-10-28 | 2020-04-08 | 2019-11-25 | 2020-05-05 | R | 2019-11-26 | 2020-05-05 | 2020-05-22 | 2020-05-07 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.35636
1309 | 111451 | #SGR18LB - REPLACE SUPERSTRUCT & REPAIR SUBSTRUCT(29793 Fed) | 0000 | Miscellaneous | Bridge Rehab w/o Added Capacity | Locally | Buchanan County | LEBANON | Bristol | NonMPO:NonMPO | Infrastructure Investment Division | Tabitha H Crowder | Tabitha.Crowder@vdot.virginia.gov | (276) 696-3482 | Tabitha H Crowder | Tabitha.Crowder@vdot.virginia.gov | (276) 696-3482 | Marcus Stiltner | marcus.stiltner@buchanancounty-va.gov | (276) 935-4013 | 0 |  | 1 | FY2021 | 85000 | 85000 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 308 days early | G | Project is on budget | 2020-07-01 | 2017-10-01 | 2020-09-24 | 2018-03-30 | G | 2020-09-25 | 2018-04-02 | 2020-09-29 | 2018-05-11 | G | 2020-09-30 | 2018-05-14 | 2021-04-12 | 2019-06-03 | G | [35 empty] | 2020-06-05 | 2020-01-09 | 2020-10-12 | 2020-03-09 | G | 2020-10-13 | 2020-03-10 | 2021-01-12 | 2020-03-10 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.10028
1310 | 104245 | RTE. 639 - Spot Widening & Hardsurface Roadway | 0639 | Secondary | Other | VDOT | Montgomery County | CHRISTIANSBURG | Salem | NonMPO:NonMPO | Local Assistance Division | Anthony W Ford | Anthony.Ford@VDOT.Virginia.gov | (540) 378-5040 | Leslie T Repass | Todd.Repass@VDOT.Virginia.gov | (540) 381-7195 | Craig Meadows |  |  | 0 |  | 0 | FY2024 | 1000000 | 855975 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 1345 days early | G | Project is on budget | [5 empty] | 2014-08-01 | 2014-08-01 | 2014-08-01 | 2014-08-01 | G | 2014-09-04 | 2014-09-04 | 2018-12-30 | 2018-12-27 | G | [10 empty] | 2022-10-14 | 2019-03-25 | 2023-02-14 | 2019-03-25 | G | [20 empty] | 2023-02-14 | 2019-10-22 | 2023-02-23 | 2019-10-22 | G | 2023-04-25 | 2019-12-16 | 2023-08-22 | 2019-12-16 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | SAAP CONTRACT | 1 | 0 | 0.1278
1311 | 107087 | RTE 652 (Otterdale Rd./Old Hundred Rd.) - ROUNDABOUT | 0652 | Secondary | Safety | Locally | Chesterfield County | CHESTERFIELD | Richmond | Richmond:Chesterfield County | Local Assistance Division | Brian J Lokker | Brian.Lokker@VDOT.Virginia.gov | (804) 524-6010 | Brian J Lokker | Brian.Lokker@VDOT.Virginia.gov | (804) 524-6010 | Chessa Faulkner | faulknerc@chesterfield.gov | (804) 748-1037 | 0 |  | 0 | FY2020 | 3800000 | 5000000 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 37 days early | R | Project estimate is less than $5M and is 20% or more over budget | 2015-07-01 | 2015-09-29 | 2015-09-24 | 2015-09-29 | R | 2015-09-25 | 2015-11-02 | 2015-10-08 | 2015-11-02 | R | 2015-10-09 | 2017-11-27 | 2016-06-08 | 2017-12-22 | R | [5 empty] | 2018-06-11 | 2018-06-11 | 2018-08-14 | 2018-06-11 | G | 2018-08-24 | 2018-07-25 | 2018-09-07 | 2018-07-27 | G | 2019-08-09 | 2019-07-08 | 2019-10-01 | 2020-02-21 | R | 2018-09-12 | 2018-07-27 | 2019-08-08 | 2019-06-24 | G | [10 empty] | 2019-10-17 | 2019-10-17 | 2019-10-30 | 2019-10-17 | G | 2019-10-31 | 2019-10-18 | 2020-02-28 | 2020-01-22 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.24536
1312 | 108499 | ROUTE 50 SIDEWALK FROM CEDAR HILL ROAD TO ALLEN STREET | 0050 | Primary | Safety | Locally | Fairfax County | FAIRFAX | Northern Virginia | Northern Virginia:Fairfax County | Infrastructure Investment Division | Amir Salahshoor | A.Salahshoor@VDOT.Virginia.gov | (703) 259-1957 | Rita Hockman | Rita.Hockman@vdot.virginia.gov | (804) 824-7421 | Thomas Cutler | Thomas.Cutler@fairfaxcounty.gov | (703) 324-5139 | 0 |  | 0 | FY2020 | 800000 | 777946 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 376 days early | G | Project is on budget | 2015-03-06 | 2014-12-30 | 2015-05-29 | 2015-03-27 | G | 2015-06-01 | 2015-06-01 | 2015-06-03 | 2015-06-03 | G | 2015-06-04 | 2015-06-04 | 2015-12-10 | 2016-12-15 | R | [10 empty] | 2017-10-09 | 2017-10-06 | 2017-10-30 | 2017-10-06 | G | [5 empty] | 2017-11-01 | 2017-10-06 | 2018-08-14 | 2017-10-06 | G | [10 empty] | 2018-08-30 | 2018-09-14 | 2020-01-27 | 2018-10-16 | G | 2020-01-28 | 2018-08-08 | 2020-03-09 | 2019-02-27 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.076355
1313 | 109054 | Providence Road Sidewalk |  | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Virginia Beach | NORFOLK | Hampton Roads | Hampton Roads:Virginia Beach | Local Assistance Division | Susan Wilson | Susan.Wilson@vdot.virginia.gov | (757) 956-3099 | Marci Thompson | Marci.Thompson@vdot.virginia.gov | (757) 956-3093 | Katie Shannon | kshannon@vbgov.com | (757) 385-1514 | 0 |  | 0 | FY2021 | 955450 | 1308298 | ACTIVITY DATES SET | R | Solicit Bids milestone is 262 days past the expected completion date | R | Project estimate is less than $5M and is 20% or more over budget | 2016-10-03 | 2016-10-03 | 2017-04-17 | 2017-04-17 | G | 2017-01-03 | 2017-01-03 | 2017-04-26 | 2017-04-26 | G | 2017-04-27 | 2017-04-27 | 2018-07-31 | 2018-10-22 | R | [10 empty] | 2019-09-10 | 2019-09-09 | 2019-09-30 | 2019-09-09 | G | [5 empty] | 2019-10-02 | 2019-09-09 | 2020-04-07 | 2019-09-09 | G | [10 empty] | 2020-04-23 |  | 2020-06-04 |  | R | 2020-06-05 |  | 2020-10-12 |  | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.27806
1314 | 109315 | #HB2.FY17 RTE 288 - IMPROVE INTERCHANGE AT RTE 250 | 0288 | Primary | Safety | VDOT | Goochland County | ASHLAND | Richmond | Richmond:Goochland County | Infrastructure Investment Division | Lawrence Ramsey | Brian.Ramsey@VDOT.Virginia.gov | (804) 585-3579 | Lawrence Ramsey | Brian.Ramsey@VDOT.Virginia.gov | (804) 585-3579 |  |  |  | 1 | 2017 | 0 | FY2021 | 4270000 | 3765475 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 304 days early | G | Project is on budget | [5 empty] | 2016-10-14 | 2016-10-14 | 2016-10-17 | 2016-10-17 | G | 2016-10-18 | 2016-10-18 | 2017-09-14 | 2017-09-11 | G | [5 empty] | 2018-06-12 | 2018-06-12 | 2018-06-25 | 2018-06-25 | G | 2019-07-10 | 2019-07-10 | 2019-07-23 | 2019-07-23 | G | 2020-02-04 | 2019-06-27 | 2020-08-20 | 2019-06-27 | G | 2019-08-08 | 2019-05-21 | 2020-02-19 | 2019-05-30 | G | 2018-12-20 | 2018-12-20 | 2019-12-10 | 2018-12-20 | G | [5 empty] | 2020-09-08 | 2019-10-08 | 2020-09-08 | 2019-10-08 | G | 2020-10-29 | 2020-01-20 | 2020-11-19 | 2020-01-20 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.067053
1315 | 109584 | Route 8 Safety Improvements | 0008 | Primary | Safety | VDOT | Patrick County | MARTINSVILLE | Salem | NonMPO:NonMPO | Infrastructure Investment Division | Alex H Price | Alex.Price@VDOT.Virginia.gov | (540) 378-5053 | Anthony L Handy | Tony.Handy@VDOT.Virginia.gov | (540) 352-9050 |  |  |  | 0 |  | 0 | FY2019 | 1600000 | 1544624 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 106 days early | G | Project is on budget | [5 empty] | 2017-07-10 | 2017-07-10 | 2017-08-02 | 2017-08-02 | G | 2017-08-03 | 2017-08-03 | 2018-04-20 | 2018-04-17 | G | [5 empty] | 2018-07-03 | 2018-06-26 | 2018-08-07 | 2018-06-26 | G | [5 empty] | 2018-06-18 | 2018-06-18 | 2018-06-18 | 2018-06-18 | G | [5 empty] | 2018-08-13 | 2018-07-24 | 2018-10-01 | 2018-07-24 | G | [5 empty] | 2019-01-08 | 2018-10-09 | 2019-01-08 | 2018-10-09 | G | 2019-03-04 | 2018-12-27 | 2019-04-12 | 2018-12-27 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.067514
1316 | 110998 | Portsmouth Boulevard Sidewalk Segment I | 0000 | Urban | Facilities for Pedestrians and Bicycles | Locally | Suffolk | NORFOLK | Hampton Roads | Hampton Roads:Suffolk | Infrastructure Investment Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Johndel A Alcaide | John.Alcaide@vdot.virginia.gov | (757) 956-3098 | LJ Hansen | lhansen@suffolkva.us | (757) 514-7687 | 0 |  | 0 | FY2022 | 238000 | 238841 | ACTIVITY DATES SET | G | Start Purchasing Right-of-Way milestone finished 149 days early | Y | Project estimate is less than $5M and is up to 20% over budget | 2017-10-02 | 2017-10-02 | 2017-11-15 | 2017-11-15 | G | 2017-11-09 | 2017-11-09 | 2017-11-14 | 2017-11-14 | G | 2017-11-15 | 2017-11-15 | 2019-02-01 | 2019-04-05 | R | [10 empty] | 2020-04-09 | 2019-11-06 | 2020-04-29 | 2019-12-02 | G | [5 empty] | 2020-05-01 |  | 2021-05-17 |  | G | [10 empty] | 2021-06-03 |  | 2021-06-30 |  | G | 2021-07-01 |  | 2021-11-08 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.15331
1317 | 111047 | RICHMOND AVE - STATLER BLVD INTERSECTION | 0250 | Urban | Reconstruction w/ Added Capacity | VDOT | Staunton | HARRISONBURG | Staunton | SAW:Staunton | Infrastructure Investment Division | Matthew P Dana | Matt.Dana@VDOT.Virginia.gov | (540) 332-7786 | Alexander Alvarado | Alexander.Alvarado@vdot.virginia.gov | (540) 332-7372 |  |  |  | 0 |  | 0 | FY2022 | 876056 | 876056 | ACTIVITY DATES SET | G | Engage Public milestone finished 132 days early | G | Project is on budget | [5 empty] | 2019-08-01 | 2019-07-12 | 2019-08-14 | 2019-07-12 | G | 2019-08-15 | 2019-07-15 | 2020-04-10 | 2020-08-28 | R | [5 empty] | 2020-12-21 | 2020-09-22 | 2021-02-01 | 2020-09-22 | G | [5 empty] | 2021-05-14 |  | 2021-09-07 |  | G | [5 empty] | 2021-04-30 |  | 2021-07-30 |  | G | [5 empty] | 2021-10-12 |  | 2021-10-12 |  | G | 2021-12-01 |  | 2022-04-26 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.093058
1318 | 111443 | #SGR18LB - BRIDGE REPLACEMENT DAN BRANCH (29739 Fed.) | 0000 | Miscellaneous | Bridge Replacement w/o Added Capacity | Locally | Buchanan County | LEBANON | Bristol | NonMPO:NonMPO | Infrastructure Investment Division | Tabitha H Crowder | Tabitha.Crowder@vdot.virginia.gov | (276) 696-3482 | Tabitha H Crowder | Tabitha.Crowder@vdot.virginia.gov | (276) 696-3482 | Marcus Stiltner | marcus.stiltner@buchanancounty-va.gov | (276) 935-4013 | 0 |  | 1 | FY2021 | 180000 | 180000 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 363 days early | G | Project is on budget | 2018-05-10 | 2018-02-01 | 2018-08-03 | 2018-04-02 | G | 2018-08-06 | 2018-04-03 | 2018-08-08 | 2018-04-05 | G | 2018-08-09 | 2018-04-06 | 2019-02-20 | 2019-02-20 | G | [35 empty] | 2020-01-15 | 2019-04-08 | 2020-04-10 | 2019-06-08 | G | 2020-04-13 | 2019-06-10 | 2020-07-07 | 2019-07-10 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.043537
1319 | 112566 | State Route 156 Winston Churchill Dr. Surface Treatment | 0156 | Urban | Reconstruction w/o Added Capacity | Locally | Hopewell | PETERSBURG | Richmond | Tri-Cities:Hopewell | Local Assistance Division | Brian J Lokker | Brian.Lokker@VDOT.Virginia.gov | (804) 524-6010 | Brian J Lokker | Brian.Lokker@VDOT.Virginia.gov | (804) 524-6010 | Austin Anderson | aanderson@hopewellVA.gov | (804) 541-2379 | 0 |  | 1 | FY2019 | 340000 | 340000 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 113 days early | G | Project is on budget | 2018-04-02 | 2018-01-29 | 2018-04-13 | 2018-05-07 | R | 2018-04-16 | 2018-05-07 | 2018-04-18 | 2018-05-18 | R | 2018-04-19 | 2018-05-11 | 2018-05-02 | 2018-05-11 | R | [35 empty] | 2018-06-04 | 2018-05-28 | 2018-06-22 | 2018-06-01 | G | 2018-09-26 | 2018-06-05 | 2018-09-26 | 2018-06-05 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.071232
1320 | 112660 | RTE 746 (N. Enon Ch Rd, Rt 10-Meadowville Tech Pk) WIDENING | 0746 | Secondary | Reconstruction w/ Added Capacity | Locally | Chesterfield County | CHESTERFIELD | Richmond | Tri-Cities:Chesterfield County | Infrastructure Investment Division | Michael S Gray | Mike.Gray@vdot.virginia.gov | (804) 609-5347 | Michael S Gray | Mike.Gray@vdot.virginia.gov | (804) 609-5347 | Barb Smith | smithbk@chesterfield.gov | (804) 748-1037 | 0 |  | 0 | FY2024 | 4214960 | 4214960 | NO DATES SET YET | G | Agreement with Locality milestone is 215 days ahead of the expected completion date | G | Project is on budget | 2021-07-01 |  | 2021-09-24 |  | G | 2021-09-27 |  | 2021-09-29 |  | G | 2021-09-30 |  | 2022-12-22 |  | G | [10 empty] | 2023-04-12 |  | 2023-05-02 |  | G | [5 empty] | 2023-05-04 |  | 2024-02-15 |  | G | [10 empty] | 2024-03-05 |  | 2024-04-01 |  | G | 2024-04-02 |  | 2024-06-18 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.32746
1321 | 112935 | JACKSON RIVER TRAIL PHASE 5 |  | Miscellaneous | Facilities for Pedestrians and Bicycles | Locally | Alleghany County | LEXINGTON | Staunton | NonMPO:NonMPO | Local Assistance Division | Susan E Hammond | Susan.Hammond@VDOT.Virginia.gov | (540) 462-6990 | Jamison Brown | Jamison.Brown@vdot.virginia.gov | (540) 332-7389 | Chad Williams | cwilliams@co.alleghany.va.us | (540) 863-6622 | 0 |  | 0 | FY2021 | 1908000 | 1908000 | NO DATES SET YET-PE OPEN | R | Determine Requirements milestone is 592 days past the expected completion date | G | Project is on budget | 2018-09-28 | 2018-09-28 | 2018-12-27 | 2018-10-22 | G | 2018-12-28 | 2018-10-23 | 2019-01-02 | 2018-10-25 | G | 2019-01-03 | 2018-10-26 | 2019-07-10 |  | R | [25 empty] | 2019-08-15 |  | 2020-04-22 |  | R | [5 empty] | 2020-07-24 |  | 2020-08-20 |  | R | 2020-11-10 |  | 2020-11-10 |  | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.15283
1322 | 113132 | Harding Ave Stormwater Drainage Improvements | 0000 | Urban | Mitigation of Water Pollution Due to Highway Runof | Locally | Blacksburg | CHRISTIANSBURG | Salem | New River Valley:Blacksburg | Local Assistance Division | Adam J Czesnowski | Adam.Czesnowski@vdot.virginia.gov | (540) 541-1216 | Adam J Czesnowski | Adam.Czesnowski@vdot.virginia.gov | (540) 541-1216 | Randy Formica | rformica@blacksburg.gov | (540) 961-1121 | 0 |  | 0 | FY2022 | 2862836 | 2862836 | ACTIVITY DATES SET | G | Engage Public milestone finished 1 days early | G | Project is on budget | 2019-08-01 | 2019-07-01 | 2019-10-25 | 2019-09-16 | G | 2019-10-28 | 2019-09-16 | 2019-10-30 | 2019-09-16 | G | 2019-10-31 | 2019-09-17 | 2020-08-03 | 2020-09-09 | R | [5 empty] | 2020-09-10 | 2020-09-10 | 2020-12-30 | 2020-12-29 | G | [25 empty] | 2021-11-16 |  | 2021-12-15 |  | G | 2022-01-10 |  | 2022-06-02 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.17427
1323 | 113312 | Primary Extension - Rte 122 (Booker T. Washington Hwy) | 0000 | Urban | Resurfacing | Locally | Rocky Mount | BEDFORD | Salem | NonMPO:NonMPO | Local Assistance Division | Jessie Nester | Jessie.Nester@vdot.virginia.gov | (540) 613-4115 | Jessie Nester | Jessie.Nester@vdot.virginia.gov | (540) 613-4115 | Jessica Heckman | jheckman@rockymountva.org | (540) 483-0907 | 0 |  | 0 | FY2019 | 108416 | 108416 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 107 days early | G | Project is on budget | 2018-10-01 | 2018-07-05 | 2018-12-28 | 2018-09-10 | G | 2018-12-31 | 2018-09-18 | 2019-01-03 | 2018-09-18 | G | 2019-01-04 | 2018-09-19 | 2019-03-22 | 2018-10-23 | G | [35 empty] | 2018-12-03 | 2018-10-23 | 2018-12-31 | 2018-12-14 | G | 2019-05-28 | 2019-01-14 | 2019-06-28 | 2019-03-13 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.10268
1324 | 113592 | MEADOW CREEK VALLEY TRAIL | 9999 | Urban | Facilities for Pedestrians and Bicycles | Locally | Charlottesville | CHARLOTTESVILLE | Culpeper | NonMPO:NonMPO | Local Assistance Division | Ken Connors |  |  | Michael D Barnes | MichaelD.Barnes@vdot.virginia.gov | (434) 422-9861 | CHRIS GENSIC | gensic@charlottesville.gov | (434) 989-0061 | 0 |  | 0 | FY2021 | 375000 | 375000 | NO DATES SET YET-PE OPEN | R | Determine Requirements milestone is 559 days past the expected completion date | G | Project is on budget | 2018-11-01 | 2018-11-01 | 2019-02-01 | 2018-11-05 | G | 2019-02-04 | 2018-11-06 | 2019-02-06 | 2018-11-26 | G | 2019-02-07 |  | 2019-08-12 |  | R | [25 empty] | 2019-09-18 |  | 2020-05-26 |  | R | [5 empty] | 2020-08-28 |  | 2020-09-25 |  | R | 2020-12-18 |  | 2020-12-18 |  | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.13252
1325 | 113835 | Transit Stop Access and Sidewalk Improvement Program |  | Primary | Facilities for Pedestrians and Bicycles | Locally | Richmond | ASHLAND | Richmond | Richmond:Richmond | Infrastructure Investment Division | Olena Fecek | Olena.Fecek@vdot.virginia.gov | (804) 524-6368 | Olena Fecek | Olena.Fecek@vdot.virginia.gov | (804) 524-6368 | Ishoc Salaam | ishoc.salaam@richmondgov.com | (804) 646-6319 | 0 |  | 0 | FY2022 | 959800 | 958045 | ACTIVITY DATES SET | G | Obtained Permits milestone finished 223 days early | G | Project is on budget | 2018-07-02 | 2018-07-30 | 2018-09-25 | 2019-08-07 | R | 2018-09-26 | 2019-08-08 | 2018-09-28 | 2019-08-14 | R | 2018-10-01 | 2019-08-15 | 2019-04-11 | 2020-06-29 | R | [25 empty] | 2020-06-30 | 2020-06-30 | 2021-02-08 | 2020-06-30 | G | [5 empty] | 2021-02-24 |  | 2021-06-15 |  | G | 2021-09-02 |  | 2021-11-15 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.11949
1326 | 115241 | #SMART20 Jefferson Ave & Oyster Point Rd Intersection Imprv. | 0143 | Primary | Safety | Locally | Newport News | WILLIAMSBURG | Hampton Roads | Hampton Roads:Newport News | Infrastructure Investment Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Chessica Villaflores | Chessica.Villaflores@vdot.virginia.gov | (757) 956-3094 | Bryan Stilley | bstilley@nnva.gov | (757) 926-8699 | 1 | 2020 | 0 | FY2027 | 10856521 | 10856521 | NO DATES SET YET | G | Agreement with Locality milestone is 977 days ahead of the expected completion date | Y | Estimate not current | 2023-08-02 |  | 2023-10-26 |  | G | 2023-10-27 |  | 2023-10-31 |  | G | 2023-11-01 |  | 2024-05-10 |  | G | [10 empty] | 2025-05-14 |  | 2025-06-04 |  | G | [5 empty] | 2025-06-06 |  | 2026-03-20 |  | G | 2024-06-18 |  | 2025-02-25 |  | G | [5 empty] | 2026-04-07 |  | 2026-05-04 |  | G | 2026-07-23 |  | 2026-07-23 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.26687
1328 | 116158 | #I81CIP SB MM 47.4 EXTEND ACCEL LANE (ID #16) | 0081 | Interstate | Reconstruction w/o Added Capacity | VDOT | Smyth County | ABINGDON | Bristol | NonMPO:NonMPO | Infrastructure Investment Division | Donald A Necessary | Donald.Necessary@VDOT.Virginia.gov | (276) 696-3285 | Marvin E Holley | Gene.Holley@VDOT.Virginia.gov | (276) 696-3255 |  |  |  | 0 |  | 0 | FY2022 | 2365000 | 2365000 | ACTIVITY DATES SET | G | Engage Public milestone finished 90 days early | G | Project is on budget | [5 empty] | 2020-07-01 | 2020-01-03 | 2020-07-15 | 2020-01-03 | G | 2020-07-16 | 2020-01-15 | 2021-03-12 | 2020-09-14 | G | [5 empty] | 2021-04-05 | 2021-01-05 | 2021-04-05 | 2021-01-05 | G | [5 empty] | 2021-04-09 |  | 2021-04-09 |  | G | [5 empty] | 2021-06-04 |  | 2021-08-20 |  | G | [5 empty] | 2021-09-14 |  | 2021-09-14 |  | G | 2021-12-08 |  | 2021-12-08 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.080955
1329 | 116732 | #I81CIP SHOULDER STABILIZATION FOR VARIOUS I-81 CIP PROJECTS | 0081 | Interstate | Reconstruction w/o Added Capacity | VDOT | Bristol District-wide |  | Bristol | NonMPO:NonMPO | Infrastructure Investment Division | Dennis R Harris | Dennis.Harris@VDOT.Virginia.gov | (276) 696-3289 | Marvin E Holley | Gene.Holley@VDOT.Virginia.gov | (276) 696-3255 |  |  |  | 0 |  | 0 | FY2021 | 4500000 | 4500000 | AWARDED | G | Start Delivery milestone finished on-time | G | Project is on budget | [5 empty] | 2020-03-06 | 2020-03-06 | 2020-03-12 | 2020-03-12 | G | 2020-03-13 | 2020-03-13 | 2020-03-26 | 2020-04-28 | R | [5 empty] | 2020-04-20 | 2020-04-20 | 2020-04-20 | 2020-04-20 | G | [5 empty] | 2020-03-17 | 2020-03-17 | 2020-05-26 | 2020-08-13 | R | [15 empty] | 2020-06-09 | 2020-06-09 | 2020-06-09 | 2020-06-09 | G | 2020-08-28 | 2020-08-28 | 2020-08-28 | 2020-08-28 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.088921
1330 | 112712 | AIRPORT DRIVE - CONSTRUCT NEW CURVE | 9999 | Urban | Reconstruction w/o Added Capacity | Locally | Danville | HALIFAX | Lynchburg | Danville:Danville | Infrastructure Investment Division | Gregg Allen | Gregg.Allen@vdot.virginia.gov | (434) 426-5575 | Jay S Brown | Jay.Brown@VDOT.Virginia.gov | (434) 856-8246 | BRIAN DUNEVANT | dunebl@ci.danville.va.us | (434) 799-5019 | 0 |  | 0 | FY2023 | 398500 | 398500 | ACTIVITY DATES SET | G | Start Purchasing Right-of-Way milestone finished 20 days early | G | Project is on budget | 2018-10-01 | 2018-10-01 | 2018-12-28 | 2018-10-01 | G | 2018-12-31 | 2018-10-02 | 2019-01-03 | 2018-10-04 | G | 2019-01-04 | 2018-10-05 | 2019-07-15 | 2020-10-28 | R | [10 empty] | 2020-11-09 | 2020-11-09 | 2020-12-02 | 2020-11-12 | G | [5 empty] | 2020-12-04 |  | 2021-12-07 |  | G | [10 empty] | 2021-12-23 |  | 2022-01-25 |  | G | 2022-01-26 |  | 2022-07-22 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.079127
1331 | 113027 | #SGR19VB - RT690 over Ennis Pond (Fed 10442) Replacement | 0690 | Secondary | Bridge Replacement w/o Added Capacity | VDOT | Isle of Wight County | FRANKLIN | Hampton Roads | Hampton Roads:Isle of Wight County | Infrastructure Investment/Asset Management Division | Mark Wagner |  |  | Andrew B Scott | Andrew.Scott@VDOT.Virginia.gov | (757) 956-3273 |  |  |  | 0 |  | 1 | FY2022 | 2700000 | 2027864 | ACTIVITY DATES SET | R | Complete Purchasing Right-of-Way milestone finished 45 days late | G | Project is on budget | [10 empty] | 2020-03-30 | 2019-12-04 | 2020-04-03 | 2019-12-10 | G | [10 empty] | 2020-04-15 | 2020-01-30 | 2020-05-12 | 2020-02-13 | G | 2020-04-02 | 2020-03-05 | 2020-04-02 | 2020-03-05 | G | 2020-05-29 | 2020-03-06 | 2020-12-11 | 2021-01-25 | R | 2020-05-28 | 2020-03-09 | 2021-02-17 | 2020-11-13 | G | [5 empty] | 2021-08-10 |  | 2021-08-10 |  | G | 2021-11-01 |  | 2021-11-01 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.1457
1332 | 113172 | RTE 3 OPERATIONAL IMPROVEMENTS | 0003 | Primary | Traffic Management/Engineering | VDOT | Spotsylvania County | FREDERICKSBURG | Fredericksburg | Fredericksburg:Spotsylvania County | Local Assistance Division | Catherine C Coffey | Catherine.Coffey@vdot.virginia.gov | (540) 899-4280 | Curtis B Holloway | Curtis.Holloway@vdot.virginia.gov | (540) 374-3367 |  |  |  | 0 |  | 0 | FY2024 | 5000000 | 5000000 | ACTIVITY DATES SET | R | Determine Requirements milestone finished 435 days late | G | Project is on budget | [5 empty] | 2018-07-16 | 2018-08-15 | 2018-07-27 | 2019-01-07 | R | 2018-07-30 | 2019-01-08 | 2019-06-26 | 2020-09-03 | R | [5 empty] | 2021-07-07 |  | 2021-07-20 |  | G | 2022-10-24 |  | 2022-11-21 |  | G | 2023-06-16 |  | 2023-12-22 |  | G | 2022-12-09 |  | 2023-06-16 |  | G | 2022-04-15 |  | 2022-10-19 |  | G | [5 empty] | 2024-01-09 |  | 2024-01-09 |  | G | 2024-04-02 |  | 2024-04-02 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.14541
1333 | 113466 | Mellen St Bike & Pedestrian - Segment I | 0000 | Urban | Facilities for Pedestrians and Bicycles | Locally | Hampton | WILLIAMSBURG | Hampton Roads | Hampton Roads:Hampton | Local Assistance Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Derrick Williams | Derrick.Williams@vdot.virginia.gov | (757) 956-3097 | Sandon S. Rogers, P.E., LS | Sandon.rogers@hampton.gov | (757) 727-6786 | 0 |  | 0 | FY2022 | 468686 | 468686 | ACTIVITY DATES SET | G | Obtained Permits milestone finished 178 days early | G | Project is on budget | 2018-10-09 | 2018-10-09 | 2019-01-08 | 2018-11-21 | G | 2019-01-09 | 2018-11-26 | 2019-01-11 | 2018-12-18 | G | 2019-01-14 | 2018-12-19 | 2019-07-19 | 2020-05-28 | R | 2020-07-20 | 2020-07-17 | 2020-08-28 | 2020-07-17 | G | [20 empty] | 2020-10-21 | 2020-05-06 | 2021-03-26 | 2020-09-29 | G | [5 empty] | 2021-03-29 |  | 2021-06-21 |  | G | 2021-09-09 |  | 2022-03-08 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.14856
1334 | 113712 | RTE 626 - RURAL RUSTIC - SURFACE TREAT NON-HARDSURFACE ROAD | 0626 | Secondary | Reconstruction w/o Added Capacity | VDOT | Culpeper County | WARRENTON | Culpeper | NonMPO:NonMPO | Infrastructure Investment Division | Ken Connors |  |  | Benjamin Davison | Ben.Davison@vdot.virginia.gov | (540) 347-6446 |  |  |  | 0 |  | 0 | FY2024 | 440000 | 440000 | NO DATES SET YET | G | Start Development milestone is 235 days ahead of the expected completion date | Y | Estimate not current | [5 empty] | 2021-10-01 |  | 2021-10-14 |  | G | 2021-10-15 |  | 2022-06-13 |  | G | [5 empty] | 2023-02-22 |  | 2023-04-04 |  | G | [5 empty] | 2023-07-19 |  | 2023-11-09 |  | G | [5 empty] | 2023-07-03 |  | 2023-10-03 |  | G | [5 empty] | 2023-11-14 |  | 2023-11-14 |  | G | 2024-02-09 |  | 2024-02-09 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | SAAP CONTRACT | 0 | 0 | 0.10376
1335 | 113847 | I-81 Exit 32 - Improve Superelevation NB & SB | 0081 | Interstate | Safety | VDOT | Washington County | ABINGDON | Bristol | NonMPO:NonMPO | Infrastructure Investment Division | Chase R Buchanan | Chase.Buchanan@VDOT.Virginia.gov | (276) 696-3251 | Chase R Buchanan | Chase.Buchanan@VDOT.Virginia.gov | (276) 696-3251 |  |  |  | 0 |  | 0 | FY2021 | 1179970 | 1179970 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 510 days early | G | Project is on budget | [5 empty] | 2018-11-01 | 2018-10-01 | 2018-11-15 | 2018-10-22 | G | 2018-11-16 | 2018-11-16 | 2019-07-12 | 2019-07-12 | G | [5 empty] | 2020-03-23 | 2019-09-11 | 2020-05-01 | 2019-09-11 | G | [5 empty] | 2020-08-17 | 2019-07-24 | 2020-12-11 | 2019-07-24 | G | [5 empty] | 2020-07-31 | 2019-07-11 | 2020-11-02 | 2019-07-11 | G | [5 empty] | 2021-01-12 | 2019-08-13 | 2021-01-12 | 2019-08-13 | G | 2021-04-06 | 2019-11-13 | 2021-04-06 | 2019-11-13 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.078746
1337 | 115713 | Townwide Street Paving, Milling, Overlay and Remarking | 0000 | Urban | Resurfacing | Locally | Blacksburg | CHRISTIANSBURG | Salem | New River Valley:Blacksburg | Local Assistance Division | Adam J Czesnowski | Adam.Czesnowski@vdot.virginia.gov | (540) 541-1216 | Adam J Czesnowski | Adam.Czesnowski@vdot.virginia.gov | (540) 541-1216 | Randy Formica | rformica@blacksburg.gov | (540) 443-1300 | 0 |  | 0 | FY2020 | 650000 | 650000 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 231 days early | G | Project is on budget | 2019-10-01 | 2019-07-01 | 2019-12-30 | 2019-09-16 | G | [5 empty] | 2019-10-01 | 2019-09-17 | 2019-10-14 | 2019-09-19 | G | [35 empty] | 2019-09-20 | 2019-09-20 | 2019-12-18 | 2019-09-20 | G | 2020-01-13 | 2019-09-25 | 2020-05-13 | 2019-09-25 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.10007
1338 | 116201 | #I81CIP MM 144 TO EXIT 150 ADDING NB AND SB LANES (ID #40) | 0081 | Interstate | Reconstruction w/ Added Capacity | VDOT | Roanoke County | SALEM | Salem | Roanoke:Roanoke County | Infrastructure Investment Division | Thomas W Digiulian | Thomas.DiGiulian@VDOT.Virginia.gov | (540) 387-5356 | Craig S Moore | Craig.Moore@vdot.virginia.gov | (540) 375-3556 |  |  |  | 0 |  | 0 | FY2025 | 322157080 | 322157080 | NO DATES SET YET-PE OPEN | G | Start Development milestone finished 195 days early | G | Project is on budget | [5 empty] | 2020-07-01 | 2020-01-02 | 2020-07-15 | 2020-01-02 | G | 2020-07-16 | 2020-01-06 | 2021-08-24 |  | G | [5 empty] | 2022-08-23 |  | 2022-09-06 |  | G | 2023-12-05 |  | 2023-12-18 |  | G | 2024-05-15 |  | 2024-11-19 |  | G | 2024-01-05 |  | 2024-07-11 |  | G | 2023-05-22 |  | 2024-01-29 |  | G | [5 empty] | 2024-12-10 |  | 2024-12-10 |  | G | 2025-04-03 |  | 2025-04-03 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.13512
1339 | 116805 | DISTRICT-WIDE HIGH VISIBILITY BACKPLATES | 9999 | Primary | Safety | VDOT | Stafford County | FREDERICKSBURG | Fredericksburg | Fredericksburg:Stafford County | Infrastructure Investment/Asset Management Division | Peter A Hedrich | Peter.Hedrich@vdot.virginia.gov | (540) 899-4540 | Benjamin Ernst | Benjamin.Ernst@vdot.virginia.gov | (571) 585-0902 |  |  |  | 0 |  | 0 | FY2021 |  |  | AWARDED | G | Start Delivery milestone finished 29 days early | R | Critical information missing | [10 empty] | 2020-03-16 | 2019-12-02 | 2020-07-21 | 2019-12-02 | G | [35 empty] | 2020-11-17 | 2020-11-17 | 2020-11-17 | 2020-11-17 | G | 2020-11-18 | 2020-11-20 | 2021-01-04 | 2020-12-06 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | WORK/TASK ORDER | 1 | 0 | 0.070288
1340 | 117055 | Ridgefield Parkway Sidewalk | 7516 | Secondary | Facilities for Pedestrians and Bicycles | Locally | Henrico County | ASHLAND | Richmond | Richmond:Henrico County | Local Assistance Division | Cynthia Crouch | Cynthia.Crouch@vdot.virginia.gov | (804) 609-5313 | Cynthia Crouch | Cynthia.Crouch@vdot.virginia.gov | (804) 609-5313 | TBD |  | TBD | 0 |  | 0 | FY2029 | 1329800 | 1329800 | NO DATES SET YET | G | Agreement with Locality milestone is 1543 days ahead of the expected completion date | G | Project is on budget | 2025-01-06 |  | 2025-05-14 |  | G | 2025-05-15 |  | 2025-06-05 |  | G | 2025-12-15 |  | 2026-04-10 |  | G | [10 empty] | 2027-07-30 |  | 2027-09-02 |  | G | [5 empty] | 2027-09-03 |  | 2028-02-09 |  | G | 2028-01-05 |  | 2028-06-05 |  | G | [5 empty] | 2028-05-12 |  | 2028-06-09 |  | G | 2028-08-29 |  | 2028-08-29 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.35199
1341 | 117158 | #SGR21LP 133-City of Suffolk 1814 Carolina Rd | 0032 | Urban | Resurfacing | Locally | Suffolk | NORFOLK | Hampton Roads | Hampton Roads:Suffolk | Infrastructure Investment/Asset Management Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Johndel A Alcaide | John.Alcaide@vdot.virginia.gov | (757) 956-3098 | Edward Heide | eheide@suffolkva.us | 75751476 | 0 |  | 1 | FY2022 | 242572 | 242572 | NO DATES SET YET | G | Agreement with Locality milestone is 80 days ahead of the expected completion date | G | Project is on budget | 2021-01-04 |  | 2021-05-12 |  | G | 2021-05-13 |  | 2021-06-03 |  | G | 2021-07-02 |  | 2021-10-26 |  | G | [25 empty] | 2021-03-09 |  | 2021-08-04 |  | G | [5 empty] | 2021-10-29 |  | 2021-10-29 |  | G | 2022-01-26 |  | 2022-01-26 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.067885
1342 | 117388 | HSIP HR Flashing Yellow Arrows #2 | 9999 | Miscellaneous | Safety | VDOT | Hampton Roads District-wide |  | Hampton Roads | Hampton Roads:Hampton Roads District-wide | Infrastructure Investment/Asset Management Division | Mark S Winslow | Mark.Winslow@VDOT.Virginia.gov | (757) 925-1528 | Mark S Winslow | Mark.Winslow@VDOT.Virginia.gov | (757) 925-1528 |  |  |  | 0 |  | 0 | FY2021 | 16000 | 16000 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 35 days early | G | Project is on budget | [10 empty] | 2021-07-13 | 2020-08-14 | 2021-11-18 | 2020-09-04 | G | [35 empty] | 2020-10-21 | 2020-09-23 | 2020-10-27 | 2020-09-28 | G | 2020-10-28 | 2020-09-29 | 2020-11-03 | 2020-09-29 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | WORK/TASK ORDER | 1 | 0 | 0.076045
1343 | 118071 | Colonial Heights High School Sidewalks |  | Urban | Safety | Locally | Colonial Heights | CHESTERFIELD | Richmond | Tri-Cities:Colonial Heights | Local Assistance Division | Evan Austin | Evan.Austin@vdot.virginia.gov | (804) 609-5384 | Evan Austin | Evan.Austin@vdot.virginia.gov | (804) 609-5384 | Keith A Chisolm | chisolmk@colonialheightsva.gov | (804) 520-9215 | 0 |  | 0 | FY2025 | 710844 | 710844 | NO DATES SET YET | G | Agreement with Locality milestone is 199 days ahead of the expected completion date | G | Project is on budget | 2021-05-03 |  | 2021-09-08 |  | G | 2021-09-09 |  | 2021-09-29 |  | G | 2022-04-13 |  | 2022-08-04 |  | G | [10 empty] | 2023-11-28 |  | 2024-01-03 |  | G | [5 empty] | 2024-01-04 |  | 2024-06-04 |  | G | 2024-05-01 |  | 2024-09-27 |  | G | [5 empty] | 2024-09-06 |  | 2024-10-03 |  | G | 2024-12-27 |  | 2024-12-27 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.14515
1344 | 118163 | Florida Avenue Drainage Improvements | 0000 | Urban | Mitigation of Water Pollution Due to Highway Runof | Locally | Roanoke | SALEM | Salem | Roanoke:Roanoke City | Local Assistance Division | Cheryl B Becker | Cheryl.Becker@vdot.virginia.gov | (540) 492-2531 | Cheryl B Becker | Cheryl.Becker@vdot.virginia.gov | (540) 492-2531 | Joseph Arthur | Joseph.Arthur@roanokeva.gov | (540) 853-5901 | 0 |  | 0 | FY2028 | 300000 | 300000 | NO DATES SET YET | G | Agreement with Locality milestone is 1422 days ahead of the expected completion date | G | Project is on budget | 2024-08-30 |  | 2025-01-13 |  | G | 2025-01-14 |  | 2025-02-05 |  | G | 2025-08-12 |  | 2025-12-08 |  | G | [10 empty] | 2027-04-01 |  | 2027-05-05 |  | G | [5 empty] | 2027-05-06 |  | 2027-10-04 |  | G | 2027-08-31 |  | 2028-02-04 |  | G | [5 empty] | 2028-01-12 |  | 2028-02-10 |  | G | 2028-05-01 |  | 2028-05-01 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.20313
1345 | 118341 | #SGR21VB (VARIOUS) CULV REPL - SALEM DIST | 0000 | Secondary | Bridge Replacement w/o Added Capacity | VDOT | Salem District-wide |  | Salem | NonMPO:NonMPO | Infrastructure Investment Division | Anthony T Marshall | Todd.Marshall@VDOT.Virginia.gov | (540) 387-5460 | Jack D Bayne | Jack.Bayne@VDOT.Virginia.gov | (540) 387-5451 |  |  |  | 0 |  | 1 | FY2023 | 4067257 | 4067257 | NO DATES SET YET | G | Determine Requirements milestone is 509 days ahead of the expected completion date | G | Project is on budget | [10 empty] | 2022-07-01 |  | 2022-07-15 |  | G | [25 empty] | 2022-07-01 |  | 2022-12-02 |  | G | [5 empty] | 2022-10-11 |  | 2022-10-11 |  | G | 2023-01-05 |  | 2023-01-05 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.087291
1346 | 87868 | RTE. 639 OVER ELLIOT CREEK (STR. 12258) - BRG. REPL. | 0639 | Secondary | Bridge Replacement w/o Added Capacity | VDOT | Montgomery County | CHRISTIANSBURG | Salem | NonMPO:NonMPO | Infrastructure Investment Division | Anthony T Marshall | Todd.Marshall@VDOT.Virginia.gov | (540) 387-5460 | Marvin D Mann | M.Mann@VDOT.Virginia.gov | (540) 378-5055 |  |  |  | 0 |  | 0 | FY2019 | 2913137 | 3040913 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 79 days early | Y | Project estimate is less than $5M and is up to 20% over budget | [5 empty] | 2010-06-30 | 2009-02-06 | 2010-07-30 | 2009-02-06 | G | 2013-08-02 | 2013-09-28 | 2015-03-27 | 2015-05-22 | R | [5 empty] | 2016-02-17 | 2016-02-17 | 2016-03-17 | 2016-03-17 | G | 2016-09-06 | 2016-09-06 | 2016-10-24 | 2016-10-24 | G | [5 empty] | 2016-10-26 | 2016-10-26 | 2017-07-24 | 2017-07-24 | G | 2016-06-29 | 2016-06-29 | 2017-07-11 | 2017-07-11 | G | [5 empty] | 2018-09-13 | 2018-08-14 | 2018-10-09 | 2018-08-14 | G | 2018-11-29 | 2018-10-22 | 2019-01-09 | 2018-10-22 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.061907
1347 | 97565 | RTE 64 - REPLACE BRIDGES OVER RTE 156 (FED ID 9760 & 9762) | 0064 | Interstate | Bridge Replacement w/o Added Capacity | VDOT | Henrico County | ASHLAND | Richmond | Richmond:Henrico County | Infrastructure Investment Division | Robert F Poutier | Robert.Poutier@vdot.virginia.gov | (804) 609-5368 | Lawrence Ramsey | Brian.Ramsey@VDOT.Virginia.gov | (804) 585-3579 |  |  |  | 0 |  | 0 | FY2019 | 30156098 | 30156098 | CONSTRUCTION STARTED | R | Start Delivery milestone finished 20 days late | G | Project is on budget | [5 empty] | 2013-07-26 | 2013-09-06 | 2013-07-26 | 2013-09-06 | R | 2016-01-04 | 2015-07-13 | 2017-04-20 | 2017-04-20 | G | [5 empty] | 2017-07-05 | 2017-07-05 | 2018-02-20 | 2018-05-03 | R | [15 empty] | 2017-10-09 | 2017-10-09 | 2018-05-24 | 2018-05-24 | G | [5 empty] | 2018-07-10 | 2018-08-14 | 2018-08-14 | 2018-08-14 | G | 2018-10-19 | 2018-12-05 | 2018-11-15 | 2018-12-05 | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.086018
1348 | 102928 | MAPLE ST - IMPROVE DRAINAGE |  | Urban | Facilities for Pedestrians and Bicycles | Locally | Hopewell | PETERSBURG | Richmond | Tri-Cities:Hopewell | Local Assistance Division | Brian J Lokker | Brian.Lokker@VDOT.Virginia.gov | (804) 524-6010 | Brian J Lokker | Brian.Lokker@VDOT.Virginia.gov | (804) 524-6010 | Austin Anderson | aanderson@hopewellva.gov | (804) 541-2379 | 0 |  | 0 | FY2019 | 160000 | 273304 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 24 days early | R | Project estimate is less than $5M and is 20% or more over budget | [5 empty] | 2012-10-01 | 2012-10-01 | 2012-10-01 | 2012-10-01 | G | 2013-07-01 | 2013-07-13 | 2014-02-28 | 2013-10-01 | G | [35 empty] | 2017-11-16 | 2018-06-05 | 2018-02-27 | 2018-06-29 | R | 2018-06-01 | 2018-06-29 | 2018-09-13 | 2018-08-20 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.082388
1349 | 102982 | South Lawson Park Multi-Use Path | 0000 | Urban | Facilities for Pedestrians and Bicycles | Locally | Poquoson | WILLIAMSBURG | Hampton Roads | Hampton Roads:Poquoson | Infrastructure Investment Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Chessica Villaflores | Chessica.Villaflores@vdot.virginia.gov | (757) 956-3094 | Ellen Roberts | Ellen.Roberts@poquoson-va.gov | (757) 868-3025 | 0 |  | 0 | FY2022 | 195000 | 195000 | NO DATES SET YET-PE OPEN | R | Determine Requirements milestone is 4 days past the expected completion date | Y | Estimate not current | 2019-09-03 | 2019-09-03 | 2020-01-06 | 2019-12-31 | G | 2020-01-21 | 2019-12-31 | 2020-02-03 | 2019-12-31 | G | 2020-02-19 |  | 2021-02-17 |  | R | [35 empty] | 2021-04-02 |  | 2021-05-27 |  | G | 2021-06-28 |  | 2021-12-20 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.19973
1350 | 117116 | Westminster Avenue Reconstruction | 0000 | Urban | Reconstruction w/o Added Capacity | Locally | Norfolk | NORFOLK | Hampton Roads | Hampton Roads:Norfolk | Local Assistance Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Derrick Williams | Derrick.Williams@vdot.virginia.gov | (757) 956-3097 | Robert Brown, P.E. | robert.brown@norfolk.gov | (757) 664-7305 | 0 |  | 0 | FY2024 | 1945000 | 1945000 | NO DATES SET YET | R | Agreement with Locality milestone is 72 days past the expected completion date | G | Project is on budget | 2020-08-03 |  | 2020-12-11 |  | R | 2020-12-14 |  | 2021-01-05 |  | R | 2021-07-14 |  | 2021-11-04 |  | G | [25 empty] | 2022-11-01 |  | 2023-04-06 |  | G | [5 empty] | 2023-06-05 |  | 2023-06-30 |  | G | 2023-09-20 |  | 2023-09-20 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.13333
1351 | 117160 | #SGR21LP 131-City of Chesapeake 1626 Kempsville Rd WB | 0190 | Urban | Resurfacing | Locally | Chesapeake | NORFOLK | Hampton Roads | Hampton Roads:Chesapeake | Infrastructure Investment/Asset Management Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Johndel A Alcaide | John.Alcaide@vdot.virginia.gov | (757) 956-3098 | Sam Sawan | ssawan@cityofchesapeake.net | (757) 382-8263 | 0 |  | 1 | FY2022 | 403220 | 403220 | NO DATES SET YET | G | Agreement with Locality milestone is 80 days ahead of the expected completion date | G | Project is on budget | 2021-01-04 |  | 2021-05-12 |  | G | 2021-05-13 |  | 2021-06-03 |  | G | 2021-07-02 |  | 2021-08-04 |  | G | [25 empty] | 2021-07-08 |  | 2021-08-04 |  | G | [5 empty] | 2021-10-01 |  | 2021-10-29 |  | G | 2022-01-26 |  | 2022-01-26 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.081188
1352 | 117946 | MARY WASHINGTON HOSPITAL CONNECTOR | 3965 | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Fredericksburg | FREDERICKSBURG | Fredericksburg | Fredericksburg:Fredericksburg | Local Assistance Division | Catherine C Coffey | Catherine.Coffey@vdot.virginia.gov | (540) 899-4280 | Anastasia Kapitan | Anastasia.Kapitan@vdot.virginia.gov | (540) 899-4292 | Erik Nelson | enelson@fredericksburgva.gov | (540) 937-0572 | 0 |  | 0 | FY2025 | 266000 | 266000 | NO DATES SET YET | G | Agreement with Locality milestone is 80 days ahead of the expected completion date | G | Project is on budget | 2021-01-04 |  | 2021-05-12 |  | G | 2021-05-13 |  | 2021-06-03 |  | G | 2021-12-13 |  | 2022-04-08 |  | G | [10 empty] | 2023-07-28 |  | 2023-08-31 |  | G | [5 empty] | 2023-09-01 |  | 2024-02-07 |  | G | 2024-01-03 |  | 2024-06-03 |  | G | [5 empty] | 2024-05-10 |  | 2024-06-07 |  | G | 2024-08-27 |  | 2024-08-27 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.36724
1353 | 118113 | #SGR21LP RTE 58 WBL - (ID6591) RESURFACING (SOUTH BOSTON RD) | 6058 | Urban | Resurfacing | Locally | Danville | HALIFAX | Lynchburg | Danville:Danville | Local Assistance Division | Gregg Allen | Gregg.Allen@vdot.virginia.gov | (434) 426-5575 | Gregg Allen | Gregg.Allen@vdot.virginia.gov | (434) 426-5575 | BRAN DUNEVANT | dunevbl@danvilleva.gov | (434) 799-5019 | 0 |  | 1 | FY2024 | 970316 | 970316 | NO DATES SET YET | G | Agreement with Locality milestone is 106 days ahead of the expected completion date | G | Project is on budget | 2021-01-29 |  | 2021-06-07 |  | G | 2021-06-08 |  | 2021-06-28 |  | G | 2022-01-07 |  | 2022-05-03 |  | G | [25 empty] | 2023-04-28 |  | 2023-09-26 |  | G | [5 empty] | 2023-11-28 |  | 2023-12-26 |  | G | 2024-03-19 |  | 2024-03-19 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.05105
1354 | 118174 | #SGR21LP - Pulaski FKEY 1145 E Main St | 0000 | Urban | Resurfacing | Locally | Pulaski | CHRISTIANSBURG | Salem | NonMPO:NonMPO | Infrastructure Investment/Asset Management Division | Adam J Czesnowski | Adam.Czesnowski@vdot.virginia.gov | (540) 541-1216 | Adam J Czesnowski | Adam.Czesnowski@vdot.virginia.gov | (540) 541-1216 | Rick Tawney | rtawney@pulaskitown.org | (540) 994-8618 | 0 |  | 1 | FY2024 | 172445 | 172445 | NO DATES SET YET | G | Agreement with Locality milestone is 50 days ahead of the expected completion date | G | Project is on budget | 2020-12-01 |  | 2021-04-12 |  | G | 2021-04-13 |  | 2021-05-03 |  | G | 2021-11-08 |  | 2022-03-09 |  | G | [25 empty] | 2023-03-06 |  | 2023-08-01 |  | G | [5 empty] | 2023-09-28 |  | 2023-10-26 |  | G | 2024-01-23 |  | 2024-01-23 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.06641
1355 | 118478 | #SGR21LP - City of Petersburg 1029 East Washington Street | 0036 | Urban | Resurfacing | VDOT | Petersburg | PETERSBURG | Richmond | Tri-Cities:Petersburg | Infrastructure Investment/Asset Management Division | Raymond Chapman | Scott.Chapman@vdot.virginia.gov | (804) 609-5277 | Raymond Chapman | Scott.Chapman@vdot.virginia.gov | (804) 609-5277 |  |  |  | 0 |  | 1 | FY2023 | 465825 | 465825 | NO DATES SET YET | G | Start Development milestone is 190 days ahead of the expected completion date | G | Project is on budget | [5 empty] | 2021-08-17 |  | 2021-08-30 |  | G | 2021-08-31 |  | 2021-11-10 |  | G | [35 empty] | 2022-06-14 |  | 2022-06-14 |  | G | 2022-09-02 |  | 2022-09-02 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.060646
1356 | 97112 | #SGR17VB - Br Replacemnt (Fed 20408 Smithland Rd / I-81) | 0720 | Secondary | Bridge Replacement w/o Added Capacity | VDOT | Rockingham County | HARRISONBURG | Staunton | Harrisonburg:Rockingham County | Infrastructure Investment/Asset Management Division | Rex L Pearce | Rex.Pearce@vdot.virginia.gov | (540) 332-9104 | Ronald L Tabor | Ronald.Tabor@vdot.virginia.gov | (540) 332-7887 |  |  |  | 0 |  | 1 | FY2021 | 7500942 | 10220470 | ACTIVITY DATES SET | R | Complete Purchasing Right-of-Way milestone is 703 days past the expected completion date | R | Project estimate is between $5M and $10M and is a $1M or more over budget | [5 empty] | 2010-09-01 | 2010-08-27 | 2010-09-01 | 2010-08-27 | G | 2010-10-01 | 2010-12-15 | 2011-09-30 | 2012-12-12 | R | [10 empty] | 2015-08-25 | 2015-08-25 | 2015-09-28 | 2015-09-28 | G | 2019-03-22 |  | 2019-11-20 |  | R | 2018-08-24 |  | 2019-03-21 |  | R | [10 empty] | 2020-11-10 |  | 2020-11-10 |  | R | 2021-02-10 |  | 2021-05-06 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.070852
1357 | 100423 | ROBERTS ROAD SIDEWALK IMPROVEMENTS | 0000 | Urban | Facilities for Pedestrians and Bicycles | Locally | Fairfax | FAIRFAX | Northern Virginia | Northern Virginia:Fairfax | Infrastructure Investment Division | Terry Yates | Terry.Yates@vdot.virginia.gov | (703) 259-2118 | Rita Hockman | Rita.Hockman@vdot.virginia.gov | (804) 824-7421 | Wendy Block-Sanford | Wendy.Sanford@fairfaxva.gov | (703) 385-7889 | 0 |  | 0 | FY2019 | 877444 | 1567300 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 154 days early | R | Project estimate is less than $5M and is 20% or more over budget | 2012-07-02 | 2012-07-02 | 2012-12-10 | 2012-12-10 | G | 2012-10-01 | 2012-11-14 | 2012-10-01 | 2012-11-14 | R | 2014-07-01 | 2014-03-31 | 2014-08-01 | 2014-04-04 | G | [10 empty] | 2015-09-01 | 2015-09-01 | 2015-09-24 | 2015-09-24 | G | [20 empty] | 2018-02-23 | 2018-02-23 | 2018-02-28 | 2018-02-28 | G | 2018-09-17 | 2018-05-04 | 2018-10-12 | 2018-05-11 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.19148
1358 | 102980 | Pocahontas Trail Reconstruction | 0060 | Primary | Facilities for Pedestrians and Bicycles | VDOT | James City County | WILLIAMSBURG | Hampton Roads | Hampton Roads:James City County | Infrastructure Investment Division | Emmanuel Eod Ofori-Darko | Emmanuel.Darko@VDOT.Virginia.gov | (757) 956-3261 | Kenneth D Mckinna | Kenneth.McKinna@VDOT.Virginia.gov | (757) 956-3271 |  |  |  | 0 |  | 0 | FY2026 | 30680519 | 30680519 | NO DATES SET YET-PE OPEN | R | Determine Requirements milestone is 144 days past the expected completion date | G | Project is on budget | [5 empty] | 2014-06-02 | 2014-06-02 | 2014-07-01 | 2014-06-20 | G | 2020-02-28 |  | 2020-09-30 |  | R | [10 empty] | 2023-10-27 |  | 2023-11-24 |  | G | [20 empty] | 2025-11-12 |  | 2025-12-09 |  | G | 2026-01-29 |  | 2026-03-17 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 1 | 0.25555
1359 | 103284 | SUNRISE VALLEY DRIVE SOUTH - SOAPSTONE- SOUTH LAKES - CMAQ | 9999 | Primary | Reconstruction w/o Added Capacity | Locally | Fairfax County | FAIRFAX | Northern Virginia | Northern Virginia:Fairfax County | Infrastructure Investment Division | Amir Salahshoor | A.Salahshoor@VDOT.Virginia.gov | (703) 259-1957 | Rita Hockman | Rita.Hockman@vdot.virginia.gov | (804) 824-7421 | Todd Minnix | Wesley.minnix@fairfaxcounty.gov | (703) 877-5749 | 0 |  | 0 | FY2020 | 1282541 | 1156770 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 17 days early | G | Project is on budget | [5 empty] | 2014-06-18 | 2014-06-20 | 2014-06-18 | 2014-06-20 | R | 2013-07-31 | 2014-06-20 | 2013-11-30 | 2014-09-19 | R | [10 empty] | 2016-05-24 | 2016-05-24 | 2016-06-09 | 2016-06-09 | G | [5 empty] | 2016-06-11 | 2016-05-24 | 2019-02-28 | 2019-02-28 | G | [10 empty] | 2019-03-01 | 2019-05-01 | 2019-05-01 | 2019-05-01 | G | 2019-05-02 | 2019-08-13 | 2019-08-30 | 2019-08-13 | G | Delay due to unforeseen issues with utilities, railroad coordination, or right-of-way acquisition | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.090244
1360 | 104005 | HOT Lanes Bicycle/Pedestrian Facilities - Phase II | 0495 | Interstate | Facilities for Pedestrians and Bicycles | VDOT | Fairfax County | FAIRFAX | Northern Virginia | Northern Virginia:Fairfax County | Infrastructure Investment Division | Abraham Lerner | Abraham.Lerner@vdot.virginia.gov | (703) 259-3345 | Abraham Lerner | Abraham.Lerner@vdot.virginia.gov | (703) 259-3345 | na |  |  | 0 |  | 0 | FY2020 | 6163820 | 13405718 | ACTIVITY DATES SET | R | Solicit Bids milestone is 382 days past the expected completion date | R | Project estimate is between $5M and $10M and is a $1M or more over budget | [5 empty] | 2012-12-31 | 2013-06-13 | 2013-01-01 | 2013-06-13 | R | 2013-06-13 | 2013-06-13 | 2013-07-15 | 2013-07-15 | G | [5 empty] | 2014-05-14 | 2014-05-14 | 2018-11-19 | 2018-11-19 | G | 2019-01-03 | 2019-09-30 | 2019-02-22 | 2019-10-30 | R | 2020-07-28 | 2019-08-15 | 2021-04-20 | 2020-09-30 | G | 2019-11-04 | 2019-11-04 | 2020-08-05 | 2020-10-09 | R | [10 empty] | 2020-02-04 |  | 2020-02-05 |  | R | 2020-05-28 |  | 2020-05-28 |  | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.072191
1361 | 105675 | PARK/TANNER ST.- PEDESTRIAN, ROAD, STORM DRAIN. IMPROVEMENTS | 0000 | Urban | Other | Locally | Abingdon | ABINGDON | Bristol | Bristol:Abingdon | Infrastructure Investment Division | Tabitha H Crowder | Tabitha.Crowder@vdot.virginia.gov | (276) 696-3482 | Roger L Musser | Roger.Musser@VDOT.Virginia.gov | (276) 696-3260 | Matt Bolick | mbolick@abingdon-va.gov | (276) 492-2128 | 0 |  | 0 | FY2022 | 1707285 | 1707285 | ACTIVITY DATES SET | R | Start Purchasing Right-of-Way milestone is 132 days past the expected completion date | G | Project is on budget | [5 empty] | 2017-11-01 | 2017-11-01 | 2017-11-17 | 2017-11-17 | G | 2017-11-30 | 2017-11-30 | 2019-01-15 | 2019-01-14 | G | [10 empty] | 2020-08-11 |  | 2020-10-12 |  | R | [20 empty] | 2021-12-29 |  | 2022-01-31 |  | G | 2022-02-02 |  | 2022-03-29 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.10831
1362 | 107046 | Curve Advisory Speed Review | 9999 | Primary | Safety | VDOT | Hampton Roads District-wide |  | Hampton Roads | Hampton Roads:Hampton Roads District-wide | Infrastructure Investment Division | Cheryl L Tate | Cheryl.Tate@vdot.virginia.gov | (757) 956-3146 | Jesse Alan Williams | Alan.Williams@vdot.virginia.gov | (757) 925-1574 |  |  |  | 0 |  | 0 | FY2019 | 2552430 | 2552430 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 62 days early | G | Project is on budget | [5 empty] | 2017-10-02 | 2017-10-02 | 2017-10-13 | 2017-10-13 | G | 2017-10-17 | 2017-10-16 | 2018-05-24 | 2018-05-24 | G | [35 empty] | 2018-09-11 | 2018-08-14 | 2018-09-11 | 2018-08-14 | G | 2018-10-25 | 2018-09-14 | 2018-11-15 | 2018-09-14 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | WORK/TASK ORDER | 1 | 0 | 0.09554
1363 | 107518 | Harrisonburg Streetscape Phase 3 |  | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Harrisonburg | HARRISONBURG | Staunton | Harrisonburg:Harrisonburg | Local Assistance Division | Michael S Fulcher | Michael.Fulcher@VDOT.Virginia.gov | (540) 332-2243 | Michael S Fulcher | Michael.Fulcher@VDOT.Virginia.gov | (540) 332-2243 | Aaron Rhoney | Aaron.Rhoney@harrisonburgva.gov | (540) 434-5928 | 0 |  | 0 | FY2020 | 624276 | 884753 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 443 days early | R | Project estimate is less than $5M and is 20% or more over budget | 2015-10-01 | 2015-10-01 | 2015-12-30 | 2015-12-30 | G | 2015-08-31 | 2015-08-31 | 2015-08-31 | 2015-08-31 | G | 2015-09-01 | 2015-09-01 | 2018-07-31 | 2018-07-31 | G | [10 empty] | 2019-12-16 | 2018-04-15 | 2019-12-30 | 2018-05-15 | G | [20 empty] | 2020-02-05 | 2018-11-10 | 2020-05-28 | 2018-12-10 | G | 2020-05-29 | 2019-01-15 | 2020-05-29 | 2019-03-13 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.21372
1364 | 109293 | #HB2.FY17 SUDLEY ROAD NB WIDENING | 0234 | Urban | Reconstruction w/ Added Capacity | Locally | Manassas | MANASSAS | Northern Virginia | Northern Virginia:Manassas | Infrastructure Investment Division | Amir Salahshoor | A.Salahshoor@VDOT.Virginia.gov | (703) 259-1957 | Rhoderick M Undan | Rhoderick.Undan@vdot.virginia.gov | (703) 259-3347 | Michelle Brickner | mbrickner@ci.manassas.va.us | (703) 257-8251 | 1 | 2017 | 0 | FY2023 | 7400000 | 7300000 | ACTIVITY DATES SET | R | Determine Requirements milestone finished 827 days late | Y | Estimate not current | 2016-12-30 | 2016-12-30 | 2017-03-29 | 2017-02-27 | G | 2017-03-30 | 2017-02-28 | 2017-04-03 | 2017-03-22 | G | 2017-04-04 | 2017-03-23 | 2017-10-05 | 2020-01-10 | R | [10 empty] | 2021-06-08 |  | 2021-08-31 |  | G | [5 empty] | 2021-09-02 |  | 2022-06-30 |  | G | [10 empty] | 2022-08-02 |  | 2022-12-29 |  | G | 2022-12-30 |  | 2023-06-30 |  | G | Delay due to changes in scope of work, project management, plan designs, or resolution of public comments | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.22606
1365 | 110000 | #SGR18VB - RT 641 FRAYS MILL RD STR 709 OVER MARSH RUN | 0641 | Secondary | Bridge Rehab w/o Added Capacity | VDOT | Albemarle County | CHARLOTTESVILLE | Culpeper | Charlottesville:Albemarle County | Infrastructure Investment/Asset Management Division | Jennifer L Ahlin | Jennifer.Ahlin@vdot.virginia.gov | (804) 786-6581 | Brian A Arnold | Brian.Arnold@VDOT.Virginia.gov | (540) 829-7557 |  |  |  | 0 |  | 1 | FY2027 | 1600000 | 1600000 | NO DATES SET YET-PE OPEN | G | Start Development milestone finished 1481 days early | G | Project is on budget | [5 empty] | 2022-07-01 | 2018-06-25 | 2022-07-15 | 2018-06-25 | G | 2022-07-18 | 2018-09-26 | 2023-06-14 |  | G | [5 empty] | 2024-05-17 |  | 2024-05-31 |  | G | 2025-08-01 |  | 2025-08-14 |  | G | 2026-01-13 |  | 2026-07-20 |  | G | 2025-08-29 |  | 2026-03-12 |  | G | 2025-07-25 |  | 2026-04-02 |  | G | [5 empty] | 2026-08-11 |  | 2026-08-11 |  | G | 2026-11-02 |  | 2026-11-02 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 1 | 0.27693
1366 | 111298 | #SGR18VB - BR REHAB RT 460 BUS OVER RT 460 (Fed 12826) | 0460 | Primary | Bridge Rehab w/o Added Capacity | VDOT | Nottoway County | PETERSBURG | Richmond | NonMPO:NonMPO | Infrastructure Investment/Asset Management Division | Warren T Hall | Warren.Hall@vdot.virginia.gov | (804) 337-1446 | Susan Warr | Susan.Warr@VDOT.Virginia.gov | (804) 720-5478 |  |  |  | 0 |  | 1 | FY2021 | 4347140 | 4347140 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 230 days early | G | Project is on budget | [5 empty] | 2018-09-04 | 2018-06-13 | 2018-09-17 | 2018-06-22 | G | 2018-09-18 | 2018-06-25 | 2019-08-15 | 2019-08-15 | G | [5 empty] | 2019-09-09 | 2019-09-09 | 2019-09-20 | 2019-09-20 | G | 2019-10-14 | 2019-10-14 | 2019-10-14 | 2019-10-14 | G | 2019-08-19 | 2019-08-19 | 2019-08-19 | 2019-08-19 | G | 2019-10-14 | 2019-10-14 | 2019-10-14 | 2019-10-14 | G | [10 empty] | 2020-07-14 | 2020-02-11 | 2020-07-14 | 2020-02-11 | G | 2020-09-02 | 2020-05-29 | 2021-01-14 | 2020-05-29 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.12208
1367 | 113307 | #SGR19LP - Pri Ext-Roanoke St-Dunlap Dr to Mt Pleasant Rd | 0000 | Urban | Resurfacing | Locally | Christiansburg | CHRISTIANSBURG | Salem | New River Valley:Christiansburg | Local Assistance Division | Adam J Czesnowski | Adam.Czesnowski@vdot.virginia.gov | (540) 541-1216 | Adam J Czesnowski | Adam.Czesnowski@vdot.virginia.gov | (540) 541-1216 | Wayne Nelson | wnelson@christiansburg.org | (540) 382-6120 | 0 |  | 0 | FY2019 | 396747 | 396747 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 163 days early | G | Project is on budget | 2018-08-01 | 2018-08-01 | 2018-10-25 | 2018-08-16 | G | 2018-10-26 | 2018-09-26 | 2018-10-30 | 2018-10-02 | G | 2018-10-31 | 2018-10-01 | 2019-02-22 | 2018-10-02 | G | [35 empty] | 2018-12-03 | 2018-12-03 | 2018-12-31 | 2018-12-12 | G | 2019-05-28 | 2019-01-02 | 2019-06-28 | 2019-01-16 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.060261
1368 | 113433 | 19 JEFF DAVIS HWY (S) - RESURFACING | 0001 | Primary | Resurfacing | Locally | Richmond | ASHLAND | Richmond | Richmond:Richmond | Local Assistance Division | Michael G Campbell | disabled-Michael.Campbell@vdot.virginia.gov | (804) 998-3960 | Brian J Lokker | Brian.Lokker@VDOT.Virginia.gov | (804) 524-6010 | Kenny Horak | Kenny.Horak@Richmondgov.com | (804) 646-4781 | 0 |  | 1 | FY2020 | 408000 | 407983 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 111 days early | G | Project is on budget | 2019-02-01 | 2018-12-19 | 2019-04-26 | 2019-01-29 | G | [5 empty] | 2019-02-01 | 2019-01-30 | 2019-02-14 | 2019-02-12 | G | [25 empty] | 2019-02-13 | 2019-02-14 | 2019-05-10 | 2019-02-14 | G | [5 empty] | 2019-05-14 | 2019-04-17 | 2019-06-11 | 2019-04-17 | G | 2019-08-29 | 2019-05-10 | 2019-08-29 | 2019-05-10 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.10436
1369 | 113878 | #SGR19LB??- Allegheny St / Big Ck Richland VA 8003 Fed 22461 | 0000 | Urban | Bridge Rehab w/o Added Capacity | VDOT | Richlands | LEBANON | Bristol | NonMPO:NonMPO | Infrastructure Investment/Asset Management Division | Gary Lester |  |  | David L Lively | David.Lively@VDOT.Virginia.gov | (276) 696-3388 |  |  |  | 0 |  | 1 | FY2021 | 853590 | 727402 | AWARDED | G | Start Delivery milestone finished 13 days early | G | Project is on budget | [5 empty] | 2019-12-16 | 2018-10-01 | 2019-12-30 | 2018-10-12 | G | 2019-12-31 | 2018-10-16 | 2020-03-27 | 2019-07-08 | G | [35 empty] | 2020-11-10 | 2020-11-04 | 2020-11-10 | 2020-11-04 | G | 2021-02-08 | 2021-01-26 | 2021-02-08 | 2021-01-26 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.14289
1370 | 104187 | #SGR19VB - RT 622 OVER NSRR (STR 02708) - BRIDGE REPLACE | 0622 | Secondary | Bridge Replacement w/o Added Capacity | VDOT | Bedford County | BEDFORD | Salem | NonMPO:NonMPO | Infrastructure Investment/Asset Management Division | Anthony T Marshall | Todd.Marshall@VDOT.Virginia.gov | (540) 387-5460 | Anthony L Handy | Tony.Handy@VDOT.Virginia.gov | (540) 352-9050 |  |  |  | 0 |  | 0 | FY2022 | 4564000 | 4564000 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 414 days early | G | Project is on budget | [5 empty] | 2017-07-12 | 2013-06-21 | 2017-07-12 | 2013-06-21 | G | 2015-07-31 | 2015-07-14 | 2016-09-27 | 2017-08-15 | R | [5 empty] | 2017-07-12 | 2017-07-12 | 2017-08-15 | 2017-08-15 | G | 2018-10-22 | 2018-10-22 | 2019-11-04 | 2018-11-02 | G | 2019-11-19 | 2020-01-09 | 2021-06-07 | 2020-04-29 | G | 2019-01-30 | 2019-01-09 | 2021-06-07 | 2019-09-04 | G | 2018-07-05 | 2019-02-27 | 2021-06-07 | 2019-02-27 | G | [5 empty] | 2021-05-14 | 2020-07-07 | 2021-06-08 | 2020-07-07 | G | 2021-07-08 | 2020-09-28 | 2021-11-16 | 2020-09-28 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.089429
1371 | 106971 | PERSHING DRIVE SIDEWALK & INTERSECTION IMPROVEMENTS | 9999 | Secondary | Facilities for Pedestrians and Bicycles | Locally | Arlington County | FAIRFAX | Northern Virginia | Northern Virginia:Arlington County | Local Assistance Division | Amir Salahshoor | A.Salahshoor@VDOT.Virginia.gov | (703) 259-1957 | Rita Hockman | Rita.Hockman@vdot.virginia.gov | (804) 824-7421 | Valerie Mosley | mvmosley@arlingtonva.us | (703) 228-4938 | 0 |  | 0 | FY2021 | 3100000 | 2293000 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 304 days early | G | Project is on budget | 2015-09-01 | 2015-09-01 | 2015-11-30 | 2015-11-30 | G | 2015-12-01 | 2016-03-07 | 2015-12-14 | 2016-03-07 | R | 2015-12-15 | 2016-03-08 | 2016-08-09 | 2016-10-27 | R | [10 empty] | 2020-02-04 | 2019-07-02 | 2020-02-04 | 2019-08-01 | G | [20 empty] | 2020-03-06 | 2019-09-13 | 2020-06-26 | 2019-10-15 | G | 2020-06-29 | 2019-12-18 | 2020-12-21 | 2020-02-21 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.24581
1372 | 107439 | WIEHLE AVENUE & W&OD TRAIL GRADE SEPARATED CROSSING | 0828 | Secondary | Facilities for Pedestrians and Bicycles | Locally | Fairfax County | FAIRFAX | Northern Virginia | Northern Virginia:Fairfax County | Infrastructure Investment Division | Amir Salahshoor | A.Salahshoor@VDOT.Virginia.gov | (703) 259-1957 | Jeffrey S Daily | Jeff.Daily@VDOT.Virginia.gov | (703) 259-2993 | Todd Minnix | wesley.minnix@fairfaxcounty.gov | (703) 877-5749 | 0 |  | 0 | FY2023 | 12250000 | 11390265 | ACTIVITY DATES SET | R | Relocate Utilities milestone is 1208 days past the expected completion date | G | Project is on budget | [10 empty] | 2015-07-01 | 2015-07-01 | 2019-12-31 | 2020-01-29 | R | [10 empty] | 2020-03-02 | 2020-05-18 | 2020-03-31 | 2020-06-09 | R | 2017-11-01 | 2020-06-10 | 2017-11-01 |  | R | 2020-04-01 | 2020-06-30 | 2021-11-30 |  | G | [10 empty] | 2021-12-14 |  | 2022-10-11 |  | G | 2022-10-27 |  | 2023-04-24 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.15349
1373 | 109026 | BLUE RIDGE ROAD SHARED-USE PATH |  | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Glasgow | LEXINGTON | Staunton | NonMPO:NonMPO | Local Assistance Division | Amanda Hughes |  |  | Michael S Fulcher | Michael.Fulcher@VDOT.Virginia.gov | (540) 332-2243 | Heather Ryan | hryan@glasgowvirginia.org | (540) 258-2246 | 0 |  | 0 | FY2020 | 294400 | 324175 | CONSTRUCTION STARTED | R | Start Delivery milestone finished 103 days late | Y | Project estimate is less than $5M and is up to 20% over budget | 2016-10-04 | 2016-10-04 | 2016-11-16 | 2016-11-16 | G | 2016-11-10 | 2016-11-10 | 2017-02-23 | 2017-02-23 | G | 2017-01-06 | 2017-01-06 | 2019-04-12 | 2019-03-26 | G | [35 empty] | 2019-10-01 | 2019-08-19 | 2020-01-14 | 2019-10-30 | G | 2020-01-15 | 2020-07-31 | 2020-05-22 | 2020-09-02 | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.38834
1374 | 109319 | #HB2.FY17 RTE 95 - ITS LOW BRIDGE WARNING SYSTEM | 0095 | Interstate | Safety | VDOT | Richmond | ASHLAND | Richmond | Richmond:Richmond | Infrastructure Investment Division | Ronnie Hobson | Ron.Hobson@vdot.virginia.gov | (804) 840-5501 | Ronnie Hobson | Ron.Hobson@vdot.virginia.gov | (804) 840-5501 |  |  |  | 1 | 2017 | 0 | FY2019 | 822140 | 822140 | AWARDED | G | Start Delivery milestone finished on-time | G | Project is on budget | [5 empty] | 2017-06-20 | 2017-06-26 | 2017-07-03 | 2017-07-07 | R | 2017-07-05 | 2017-07-10 | 2018-06-01 | 2017-11-22 | G | [5 empty] | 2018-03-21 | 2018-03-09 | 2018-04-03 | 2018-03-12 | G | 2018-04-25 | 2018-04-25 | 2018-04-25 | 2018-04-25 | G | 2018-03-01 | 2018-02-05 | 2018-03-01 | 2018-02-05 | G | 2018-04-25 | 2018-04-25 | 2018-04-25 | 2018-04-25 | G | [10 empty] | 2019-03-12 | 2019-01-08 | 2019-03-12 | 2019-01-10 | G | 2019-04-25 | 2019-03-13 | 2019-06-20 | 2019-06-20 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | WORK/TASK ORDER | 1 | 0 | 0.071223
1375 | 111060 | #SMART18 - (St) RTE 655 - INTERSECTION RECONSTRUCTION | 0655 | Secondary | Reconstruction w/o Added Capacity | VDOT | Frederick County | EDINBURG | Staunton | Winchester:Frederick County | Infrastructure Investment Division | Clifton Balderson | clifton.balderson@dbiservices.com | (540) 460-1313 | Scott A Alexander | Scott.Alexander@VDOT.Virginia.gov | (540) 332-9030 |  |  |  | 1 | 2018 | 0 | FY2019 | 2812610 | 2524690 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 44 days early | G | Project is on budget | [10 empty] | 2017-08-01 | 2017-08-01 | 2017-09-26 | 2017-09-26 | G | [25 empty] | 2017-08-01 | 2017-08-01 | 2018-05-08 | 2018-07-23 | R | [5 empty] | 2018-11-13 | 2018-10-09 | 2018-11-13 | 2018-11-06 | G | 2019-01-02 | 2019-01-16 | 2019-03-01 | 2019-01-16 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.088309
1376 | 111724 | TOWNWIDE - STREETSCAPE EXTENSION |  | Enhancement | Facilities for Pedestrians and Bicycles | VDOT | Halifax | HALIFAX | Lynchburg | NonMPO:NonMPO | Local Assistance Division | Sharon S White | Sharon.White@VDOT.Virginia.gov | (434) 856-8220 | Sharon S White | Sharon.White@VDOT.Virginia.gov | (434) 856-8220 | S White |  |  | 0 |  | 0 | FY2019 | 495361 | 495360 | CONSTRUCTION COMPLETED | R | Start Delivery milestone finished 344 days late | G | Project is on budget | 2017-10-02 | 2017-10-02 | 2017-10-10 | 2017-10-10 | G | 2017-11-14 | 2017-11-14 | 2017-11-16 | 2017-11-16 | G | 2018-02-05 | 2018-02-05 | 2018-09-21 | 2018-09-20 | G | [10 empty] | 2019-03-06 | 2019-03-06 | 2019-03-26 | 2019-03-06 | G | [5 empty] | 2019-03-27 | 2019-03-07 | 2019-03-27 | 2019-03-07 | G | [10 empty] | 2019-04-12 | 2020-03-10 | 2019-05-09 | 2020-03-10 | R | 2019-05-10 | 2020-05-29 | 2019-06-20 | 2020-05-29 | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 1 | 0.21124
1377 | 113319 | Downtown Main Street Pedestrian Improvements - City of Galax | 0000 | Urban | Facilities for Pedestrians and Bicycles | Locally | Galax | MARTINSVILLE | Salem | NonMPO:NonMPO | Local Assistance Division | Jessie Nester | Jessie.Nester@vdot.virginia.gov | (540) 613-4115 | Jessie Nester | Jessie.Nester@vdot.virginia.gov | (540) 613-4115 | Keith Barker | kbarker@GalaxVa.com | (276) 236-5773 | 0 |  | 0 | FY2023 | 878910 | 459174 | ACTIVITY DATES SET | G | Determine Requirements milestone finished on-time | G | Project is on budget | 2019-10-01 | 2019-07-31 | 2019-12-30 | 2019-08-23 | G | 2019-12-31 | 2019-09-23 | 2020-01-03 | 2019-09-23 | G | 2020-01-06 | 2020-07-09 | 2020-08-03 | 2020-08-03 | G | [10 empty] | 2021-08-12 |  | 2021-11-18 |  | G | [5 empty] | 2021-11-22 |  | 2022-04-19 |  | G | 2021-08-11 |  | 2022-04-19 |  | G | [5 empty] | 2022-09-08 |  | 2022-10-05 |  | G | 2022-10-28 |  | 2023-03-28 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.10846
1378 | 113816 | Yorktown Road 728 Mill and Overlay | 0238 | Urban | Resurfacing | Locally | Newport News | WILLIAMSBURG | Hampton Roads | Hampton Roads:Newport News | Infrastructure Investment Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Chessica Villaflores | Chessica.Villaflores@vdot.virginia.gov | (757) 956-3094 | Bryan Stilley, P.E. | bstilley@nnva.gov | (757) 926-8699 | 0 |  | 1 | FY2019 | 97485 | 97485 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 14 days early | G | Project is on budget | 2018-09-04 | 2018-09-04 | 2018-11-30 | 2018-12-06 | R | 2018-12-03 | 2018-12-06 | 2018-12-05 | 2018-12-06 | R | 2018-12-06 | 2018-12-07 | 2019-06-13 | 2019-04-08 | G | [25 empty] | 2019-03-27 | 2019-03-26 | 2019-05-21 | 2019-03-26 | G | [5 empty] | 2019-06-07 | 2019-06-03 | 2019-06-07 | 2019-06-04 | G | 2019-06-28 | 2019-06-14 | 2019-06-28 | 2019-06-14 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.16041
1379 | 113933 | DISTRICTWIDE ON-CALL RUMBLE STRIP INSTALLATION | 9999 | Primary | Safety | VDOT | Lynchburg District-wide |  | Lynchburg | NonMPO:NonMPO | Infrastructure Investment Division | Lindsey S Hodges | Lindsey.Hodges@vdot.virginia.gov | (434) 856-8143 | Gregory K Parsons | Gregory.Parsons@vdot.virginia.gov | (434) 856-8297 |  |  |  | 0 |  | 0 | FY2019 | 1000000 | 999945 | CONSTRUCTION STARTED | R | Start Delivery milestone finished 17 days late | G | Project is on budget | [10 empty] | 2019-01-31 | 2018-08-27 | 2019-02-06 | 2018-09-21 | G | [35 empty] | 2019-01-08 | 2019-01-08 | 2019-01-08 | 2019-01-08 | G | 2019-04-02 | 2019-04-19 | 2019-04-02 | 2019-04-19 | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | REGIONAL ON-CALL CONTRACT | 1 | 0 | 0.11786
1380 | 115236 | #SMART20 Terminal Blvd/Diven St Intersection Improvements | 0000 | Primary | Traffic Management/Engineering | Locally | Norfolk | NORFOLK | Hampton Roads | Hampton Roads:Norfolk | Infrastructure Investment Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Derrick Williams | Derrick.Williams@vdot.virginia.gov | (757) 956-3097 | Christine Fuller | christine.armstrong@norfolk.gov | (757) 664-7459 | 1 | 2020 | 0 | FY2027 | 1732600 | 1732600 | NO DATES SET YET | G | Agreement with Locality milestone is 976 days ahead of the expected completion date | Y | Estimate not current | 2023-08-01 |  | 2023-10-25 |  | G | 2023-10-26 |  | 2023-11-08 |  | G | 2023-11-09 |  | 2024-10-25 |  | G | [10 empty] | 2025-10-29 |  | 2025-11-19 |  | G | [5 empty] | 2025-11-21 |  | 2026-10-06 |  | G | 2024-06-26 |  | 2025-03-05 |  | G | [5 empty] | 2026-10-23 |  | 2026-11-20 |  | G | 2027-02-17 |  | 2027-02-17 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.35329
1381 | 115270 | MONTICELLO AVE. - PRIMARY EXTENSION PAVING | 0020 | Urban | Resurfacing | Locally | Charlottesville | CHARLOTTESVILLE | Culpeper | Charlottesville:Charlottesville | Local Assistance Division | Gregory J Cooley | Gregory.Cooley@vdot.virginia.gov | (434) 906-7979 | Michael D Barnes | MichaelD.Barnes@vdot.virginia.gov | (434) 422-9861 | MARTY SILMAN | SILMANM@CHARLOTTESVILLE.ORG | (434) 970-3071 | 0 |  | 1 | FY2020 | 342447 | 342447 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 3 days early | G | Project is on budget | 2019-10-02 | 2019-09-20 | 2019-12-31 | 2019-10-10 | G | [5 empty] | 2019-10-02 | 2019-09-22 | 2019-10-15 | 2019-09-25 | G | [25 empty] | 2019-09-26 | 2019-12-06 | 2019-12-24 | 2019-12-09 | G | [5 empty] | 2020-01-13 | 2020-01-13 | 2020-03-11 | 2020-03-11 | G | 2020-05-29 | 2020-05-29 | 2020-06-11 | 2020-06-08 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.081034
1382 | 116480 | RTE 705 LIGHTRIDGE FARM ROAD - RURAL RUSTIC ROAD | 0705 | Secondary | Reconstruction w/o Added Capacity | VDOT | Loudoun County | LEESBURG | Northern Virginia | Northern Virginia:Loudoun County | Infrastructure Investment Division | Kimberly Mccool | Kimberly.McCool@vdot.virginia.gov | (703) 259-3220 | Mehrdad Naderi | Mehrdad.Naderi@vdot.virginia.gov | (703) 259-2217 | James Zeller, P.E. | james.zeller@loudoun.gov | (571) 258-3548 | 0 |  | 0 | FY2024 | 1000000 | 1000000 | ACTIVITY DATES SET | G | Determine Requirements milestone finished on-time | G | Project is on budget | [5 empty] | 2020-03-02 | 2020-03-02 | 2020-04-01 | 2020-04-01 | G | 2020-04-02 | 2020-04-02 | 2020-06-01 | 2020-06-01 | G | [35 empty] | 2023-06-26 |  | 2023-09-19 |  | G | 2023-09-20 |  | 2024-02-02 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | WORK/TASK ORDER | 0 | 1 | 0.21488
1383 | 117022 | #SGR21VB ROUTE 220 BRIDGE AND APPROACHES | 0220 | Primary | Bridge Replacement w/o Added Capacity | VDOT | Highland County | LEXINGTON | Staunton | NonMPO:NonMPO | Infrastructure Investment Division | Eulogio A Javier | Eulogio.Javier@VDOT.Virginia.gov | (540) 332-9105 | Jean Uhl | Jean.Uhl@vdot.virginia.gov | (540) 332-9267 |  |  |  | 0 |  | 1 | FY2024 | 6706427 | 6706427 | NO DATES SET YET-PE OPEN | G | Start Development milestone finished on-time | G | Project is on budget | [5 empty] | 2020-08-17 | 2020-08-17 | 2020-09-04 | 2020-09-04 | G | 2020-09-08 |  | 2021-07-13 |  | G | [5 empty] | 2022-02-15 |  | 2022-03-15 |  | G | 2022-11-01 |  | 2022-12-08 |  | G | 2023-05-11 |  | 2023-09-11 |  | G | 2022-12-23 |  | 2023-05-25 |  | G | 2023-01-19 |  | 2023-06-16 |  | G | [5 empty] | 2023-09-12 |  | 2023-09-12 |  | G | 2023-12-05 |  | 2023-12-05 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.057724
1384 | 117174 | Patterson Avenue Pedestrian Improvements | 0000 | Urban | Facilities for Pedestrians and Bicycles | Locally | Roanoke | SALEM | Salem | Roanoke:Roanoke City | Local Assistance Division | Cheryl B Becker | Cheryl.Becker@vdot.virginia.gov | (540) 492-2531 | Cheryl B Becker | Cheryl.Becker@vdot.virginia.gov | (540) 492-2531 | Luke Pugh | luke.pugh@roanokeva.gov | (540) 853-5208 | 0 |  | 0 | FY2028 | 1800000 | 1800000 | NO DATES SET YET | G | Agreement with Locality milestone is 1422 days ahead of the expected completion date | G | Project is on budget | 2024-08-30 |  | 2025-01-13 |  | G | 2025-01-14 |  | 2025-02-05 |  | G | 2025-08-12 |  | 2025-12-08 |  | G | [10 empty] | 2027-04-01 |  | 2027-05-05 |  | G | [5 empty] | 2027-05-06 |  | 2027-10-04 |  | G | 2027-08-31 |  | 2028-02-04 |  | G | [5 empty] | 2028-01-12 |  | 2028-02-10 |  | G | 2028-05-01 |  | 2028-05-01 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.22902
1385 | 118307 | LINCOLN STREET (NEW CONNECTION) | 9999 | Urban | New Construction Roadway | Locally | Fairfax County | FAIRFAX | Northern Virginia | Northern Virginia:Fairfax County | Local Assistance Division | Andrew G Beacher | Andrew.Beacher@vdot.virginia.gov | (703) 259-2239 | Christer P Carshult | Christer.Carshult@vdot.virginia.gov | (703) 259-1765 | Ray Johnson |  |  | 0 |  | 0 | FY2030 | 33464000 | 33464000 | NO DATES SET YET | G | Agreement with Locality milestone is 1433 days ahead of the expected completion date | G | Project is on budget | 2024-07-01 |  | 2025-01-24 |  | G | 2025-01-27 |  | 2025-02-14 |  | G | 2025-08-21 |  | 2026-04-29 |  | G | [10 empty] | 2028-07-28 |  | 2028-08-31 |  | G | [5 empty] | 2028-09-01 |  | 2029-07-23 |  | G | 2028-10-24 |  | 2029-06-29 |  | G | [5 empty] | 2029-10-25 |  | 2029-12-24 |  | G | 2030-03-19 |  | 2030-05-13 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.30053
1386 | 118555 | BIKESHARE STATIONS | 9999 | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Vienna | FAIRFAX | Northern Virginia | Northern Virginia:Vienna | Local Assistance Division | Andrew G Beacher | Andrew.Beacher@vdot.virginia.gov | (703) 259-2239 | Rhoderick M Undan | Rhoderick.Undan@vdot.virginia.gov | (703) 259-3347 | Michael Gallagher | andrew.jinks@viennava.gov | (703) 255-6380 | 0 |  | 0 | FY2025 | 272400 | 272400 | NO DATES SET YET | G | Agreement with Locality milestone is 107 days ahead of the expected completion date | G | Project is on budget | 2021-02-01 |  | 2021-06-08 |  | G | 2021-06-09 |  | 2021-06-29 |  | G | 2022-01-10 |  | 2022-05-04 |  | G | [25 empty] | 2023-08-30 |  | 2024-02-05 |  | G | [5 empty] | 2023-11-29 |  | 2024-04-30 |  | G | 2024-07-19 |  | 2024-12-31 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.31865
1387 | 12993 | RTE 614 - BRIDGE REPLACEMENT | 0614 | Secondary | Bridge Replacement w/o Added Capacity | Locally | Greensville County | FRANKLIN | Hampton Roads | NonMPO:NonMPO | Infrastructure Investment Division | Bryant H Porter | Bryant.Porter@VDOT.Virginia.gov | (757) 956-3092 | Keisha Wilkins | Keisha.Wilkins@vdot.virginia.gov | (757) 956-3110 | Lin Pope | lpope@greensvillecountyva.gov | (434) 348-4232 | 0 |  | 0 | FY2024 | 1071100 | 2535330 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 1551 days early | R | Project estimate is less than $5M and is 20% or more over budget | [5 empty] | 2000-07-17 | 2000-08-23 | 2000-09-29 | 2000-08-24 | G | 2000-08-01 | 2000-08-01 | 2001-01-31 | 2001-01-31 | G | 2021-12-27 | 2019-01-23 | 2022-03-03 | 2019-01-23 | G | [5 empty] | 2020-04-28 | 2019-04-17 | 2020-05-22 | 2019-04-17 | G | 2023-05-12 | 2019-04-17 | 2023-12-15 | 2019-04-17 | G | 2023-05-12 | 2019-04-17 | 2023-12-15 | 2019-04-17 | G | 2023-12-13 | 2019-04-02 | 2023-12-19 | 2019-04-03 | G | [5 empty] | 2024-01-29 | 2019-08-18 | 2024-03-29 | 2019-09-19 | G | 2024-04-01 | 2020-02-07 | 2024-05-13 | 2020-02-13 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.1618
1388 | 92652 | #SMART18 - RTE 155 - WIDEN SHOULDERs | 0155 | Primary | Safety | VDOT | New Kent County | ASHLAND | Richmond | Richmond:New Kent County | Infrastructure Investment Division | Noyan F Erermis | Noyan.Erermis@vdot.virginia.gov | (804) 819-9653 | Noyan F Erermis | Noyan.Erermis@vdot.virginia.gov | (804) 819-9653 |  |  |  | 1 | 2018 | 0 | FY2022 | 5702200 | 5692755 | ACTIVITY DATES SET | G | Obtained Permits milestone finished 95 days early | G | Project is on budget | [5 empty] | 2010-10-25 | 2011-01-25 | 2010-10-25 | 2011-01-25 | R | 2017-07-05 | 2017-07-05 | 2017-12-05 | 2017-12-04 | G | [5 empty] | 2018-07-13 | 2018-05-24 | 2018-07-30 | 2018-06-11 | G | 2019-06-13 | 2019-05-17 | 2019-06-26 | 2019-06-24 | G | 2020-09-23 |  | 2021-06-23 |  | G | 2019-07-15 | 2019-07-10 | 2020-10-15 | 2020-09-03 | G | 2020-11-16 | 2020-11-16 | 2021-03-16 | 2020-12-11 | G | [5 empty] | 2021-07-13 |  | 2021-07-13 |  | G | 2021-09-01 |  | 2021-11-30 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.10127
1389 | 106969 | S. ARLINGTON RIDGE ROAD INTERSECTION IMPROVEMENTS | 9999 | Secondary | Facilities for Pedestrians and Bicycles | Locally | Arlington County | FAIRFAX | Northern Virginia | Northern Virginia:Arlington County | Local Assistance Division | Amir Salahshoor | A.Salahshoor@VDOT.Virginia.gov | (703) 259-1957 | Rita Hockman | Rita.Hockman@vdot.virginia.gov | (804) 824-7421 | Glenn Page | GPage@ArlingtonVA.us | (703) 228-7525 | 0 |  | 0 | FY2024 | 2672000 | 2582168 | AWARDED | G | Start Delivery milestone finished 1276 days early | G | Project is on budget | 2015-09-01 | 2015-09-01 | 2015-11-30 | 2015-10-06 | G | 2015-12-01 | 2015-10-06 | 2015-12-14 | 2015-10-07 | G | 2015-12-15 | 2015-10-20 | 2016-08-09 | 2016-06-16 | G | [10 empty] | 2001-09-17 | 2001-09-17 | 2018-03-08 | 2016-06-17 | G | [20 empty] | 2023-02-08 | 2020-03-03 | 2023-07-28 | 2020-05-11 | G | 2023-07-31 | 2020-07-17 | 2024-01-25 | 2020-07-28 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.24587
1390 | 115249 | #SGR20LP - Chippenham Parkway N(Gravel Hill Rd) - Resurface | 0150 | Urban | Resurfacing | Locally | Richmond | ASHLAND | Richmond | Richmond:Richmond | Local Assistance Division | Brian J Lokker | Brian.Lokker@VDOT.Virginia.gov | (804) 524-6010 | Brian J Lokker | Brian.Lokker@VDOT.Virginia.gov | (804) 524-6010 | Kenny Horak | Kenneth.horak@richmondgov.com | (804) 646-4781 | 0 |  | 1 | FY2020 | 92386 | 92386 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 5 days early | G | Project is on budget | 2019-07-01 | 2019-04-16 | 2019-09-24 | 2020-01-30 | R | [5 empty] | 2019-09-25 | 2020-01-30 | 2019-11-27 | 2020-02-13 | R | [25 empty] | 2020-02-14 | 2020-03-04 | 2020-04-29 | 2020-03-04 | G | [5 empty] | 2020-05-01 | 2020-03-19 | 2020-05-01 | 2020-03-19 | G | 2020-06-30 | 2020-06-25 | 2020-06-30 | 2020-06-25 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 |  | 1 | 0 | 0.081662
1391 | 115475 | #SMART20 - US 33/RTE. 20 EAST ROUNDABOUT | 0033 | Primary | Reconstruction w/o Added Capacity | VDOT | Orange County | LOUISA | Culpeper | NonMPO:NonMPO | Infrastructure Investment Division | Gregory J Cooley | Gregory.Cooley@vdot.virginia.gov | (434) 906-7979 | Justin Warfield | Justin.Warfield@vdot.virginia.gov | (540) 829-7599 |  |  |  | 1 | 2020 | 0 | FY2024 | 5500000 | 5500000 | NO DATES SET YET-PE OPEN | R | Determine Requirements milestone is 130 days past the expected completion date | G | Project is on budget | [5 empty] | 2019-10-01 | 2019-09-16 | 2019-10-14 | 2019-09-27 | G | 2019-10-15 |  | 2020-10-14 |  | R | [5 empty] | 2021-08-20 |  | 2021-09-02 |  | G | 2022-07-07 |  | 2022-07-20 |  | G | 2023-05-05 |  | 2023-11-08 |  | G | 2022-08-05 |  | 2023-05-04 |  | G | 2022-02-23 |  | 2022-08-25 |  | G | [5 empty] | 2023-11-14 |  | 2023-11-14 |  | G | 2024-03-11 |  | 2024-03-11 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.090737
1392 | 116992 | #SGR21VP PM7D-967-F21,P401 Primary Plant Mix | 9999 | Primary | Resurfacing | VDOT | Culpeper District-wide |  | Culpeper | NonMPO:NonMPO | Infrastructure Investment/Asset Management Division | Donald R Schoch | Donald.Schoch@vdot.virginia.gov | (540) 829-7500 | Donald R Schoch | Donald.Schoch@vdot.virginia.gov | (540) 829-7500 |  |  |  | 0 |  | 1 | FY2021 | 1329565 | 1329565 | ADVERTISED | G | Solicit Bids milestone finished on-time | G | Project is on budget | [10 empty] | 2021-03-01 | 2021-01-22 | 2021-03-05 | 2021-01-22 | G | [35 empty] | 2021-02-09 | 2021-02-09 | 2021-02-09 | 2021-02-09 | G | 2021-04-30 |  | 2021-04-30 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.10623
1393 | 117040 | County-wide Pedestrian Intersection Accommodations | 9999 | Secondary | Facilities for Pedestrians and Bicycles | Locally | Henrico County | ASHLAND | Richmond | Richmond:Henrico County | Local Assistance Division | Douglas L Orcutt | Doug.Orcutt@vdot.virginia.gov | (804) 609-5428 | Douglas L Orcutt | Doug.Orcutt@vdot.virginia.gov | (804) 609-5428 | TBD |  | TBD | 0 |  | 0 | FY2029 | 902570 | 902570 | NO DATES SET YET | G | Agreement with Locality milestone is 1543 days ahead of the expected completion date | G | Project is on budget | 2025-01-06 |  | 2025-05-14 |  | G | 2025-05-15 |  | 2025-06-05 |  | G | 2025-12-15 |  | 2026-04-10 |  | G | [10 empty] | 2027-07-30 |  | 2027-09-02 |  | G | [5 empty] | 2027-09-03 |  | 2028-02-09 |  | G | 2028-01-05 |  | 2028-06-05 |  | G | [5 empty] | 2028-05-12 |  | 2028-06-09 |  | G | 2028-08-29 |  | 2028-08-29 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.3497
1394 | 118134 | STAUNTON DISTRICT - HIGH VISIBILITY BACKPLATE SSI | 9999 | Primary | Safety | VDOT | Staunton District-wide |  | Staunton | NonMPO:NonMPO | Infrastructure Investment Division | Keith M Rider | Keith.Rider@VDOT.Virginia.gov | (434) 856-8145 | Kunal Kothawade | Kunal.Kothawade@vdot.virginia.gov | (540) 332-9259 |  |  |  | 0 |  | 0 | FY2023 | 1520000 | 1520000 | ACTIVITY DATES SET | G | Obtained Permits milestone finished 463 days early | G | Project is on budget | [5 empty] | 2020-11-02 | 2020-10-30 | 2020-11-23 | 2020-10-30 | G | 2020-11-24 | 2020-11-02 | 2021-09-27 | 2020-11-06 | G | [5 empty] | 2021-06-11 |  | 2021-07-09 |  | G | [5 empty] | 2022-03-08 |  | 2022-07-06 |  | G | [5 empty] | 2021-11-10 | 2021-01-07 | 2022-04-15 | 2021-01-07 | G | [5 empty] | 2022-07-12 |  | 2022-07-12 |  | G | 2022-09-29 |  | 2022-09-29 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | WORK/TASK ORDER | 0 | 0 | 0.068716
1395 | 118312 | SYCOLIN ROAD / GATEWAY DRIVE SIGNAL | 9999 | Urban | Traffic Management/Engineering | Locally | Leesburg | LEESBURG | Northern Virginia | Northern Virginia:Leesburg | Local Assistance Division | Kimberly Mccool | Kimberly.McCool@vdot.virginia.gov | (703) 259-3220 | Susie X Lue | Susie.Lue@vdot.virginia.gov | (703) 259-2918 | Terry Yates |  |  | 0 |  | 0 | FY2029 | 800000 | 800000 | NO DATES SET YET | G | Agreement with Locality milestone is 1433 days ahead of the expected completion date | G | Project is on budget | 2024-07-01 |  | 2025-01-24 |  | G | 2025-01-27 |  | 2025-02-14 |  | G | 2025-08-21 |  | 2025-12-17 |  | G | [10 empty] | 2027-04-12 |  | 2027-05-14 |  | G | [5 empty] | 2027-05-17 |  | 2027-10-13 |  | G | 2027-07-21 |  | 2027-12-21 |  | G | [5 empty] | 2028-01-25 |  | 2028-03-21 |  | G | 2028-06-08 |  | 2028-08-03 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.3818
1396 | 1852 | #SMART18 - RTE 602 - RECONSTRUCTION | 0602 | Secondary | Reconstruction w/o Added Capacity | VDOT | Belle Haven | ACCOMAC | Hampton Roads | NonMPO:NonMPO | Infrastructure Investment Division | Kenneth D Mckinna | Kenneth.McKinna@VDOT.Virginia.gov | (757) 956-3271 | Kenneth D Mckinna | Kenneth.McKinna@VDOT.Virginia.gov | (757) 956-3271 |  |  |  | 1 | 2018 | 0 | FY2023 | 3992306 | 3991247 | ACTIVITY DATES SET | G | Obtained Permits milestone finished 24 days early | G | Project is on budget | [5 empty] | 2014-06-30 | 2014-01-08 | 2014-06-30 | 2014-01-09 | G | 2017-07-26 | 2017-06-26 | 2017-11-21 | 2017-11-21 | G | [5 empty] | 2018-09-17 | 2018-10-02 | 2018-09-28 | 2018-10-03 | R | 2019-10-07 | 2019-10-04 | 2019-10-18 | 2019-10-18 | G | 2021-11-08 |  | 2022-11-23 |  | G | 2019-11-05 | 2020-01-22 | 2021-11-05 |  | G | 2019-09-30 | 2020-06-18 | 2020-12-14 | 2020-11-20 | G | [5 empty] | 2022-12-13 |  | 2022-12-13 |  | G | 2023-02-01 |  | 2023-03-29 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.16236
1397 | 75919 | RTE 711 -JUGGINS ROAD RECONSTRUCTION | 0711 | Secondary | Reconstruction w/o Added Capacity | Locally | Stafford County | FREDERICKSBURG | Fredericksburg | Fredericksburg:Stafford County | Infrastructure Investment Division | Lynne Keenan |  |  | Robert Galen Ridgell | Robert.Ridgell@vdot.virginia.gov | (540) 372-3549 | Alexander Owsiak | aowsiak@staffordcountyva.gov | (540) 658-4593 | 0 |  | 0 | FY2020 | 2243558 | 2253905 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 343 days early | Y | Project estimate is less than $5M and is up to 20% over budget | [5 empty] | 2005-07-15 | 2005-08-06 | 2005-09-30 | 2005-08-08 | G | 2017-07-03 | 2017-06-30 | 2017-12-01 | 2017-07-25 | G | [10 empty] | 2017-07-25 | 2017-07-25 | 2017-08-23 | 2017-08-23 | G | [20 empty] | 2018-12-28 | 2018-12-07 | 2019-07-01 | 2018-12-07 | G | 2019-07-01 | 2019-01-22 | 2019-12-31 | 2019-01-22 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.10643
1398 | 98177 | Realign & Signalize Elden Street @ Center Street | 0000 | Urban | Resurfacing | Locally | Herndon | FAIRFAX | Northern Virginia | Northern Virginia:Herndon | Local Assistance Division | Jan S Vaughan | Jan.Vaughan@VDOT.Virginia.gov | (703) 259-2425 | Christer P Carshult | Christer.Carshult@vdot.virginia.gov | (703) 259-1765 | Zoran Dragacevac | zoran.dragacevac@herndonva.gov | (703) 435-6856 | 0 |  | 0 | FY2022 | 1929694 | 1929694 | ACTIVITY DATES SET | R | Solicit Bids milestone is 68 days past the expected completion date | G | Project is on budget | 2010-06-21 | 2010-06-15 | 2010-12-30 | 2010-12-22 | G | 2011-06-01 | 2011-09-13 | 2011-06-01 | 2011-09-13 | R | 2012-12-12 | 2012-05-31 | 2012-12-21 | 2012-05-31 | G | [10 empty] | 2011-09-14 | 2011-09-14 | 2011-09-14 | 2011-09-14 | G | [20 empty] | 2020-08-17 | 2020-08-17 | 2020-12-15 |  | R | 2021-03-15 |  | 2021-07-15 |  | G | Final design is still underway | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.17786
1399 | 107041 | Route 58 SuperElevation Correction | 0058 | Primary | Safety | VDOT | Southampton County | FRANKLIN | Hampton Roads | NonMPO:NonMPO | Infrastructure Investment Division | Emmanuel Eod Ofori-Darko | Emmanuel.Darko@VDOT.Virginia.gov | (757) 956-3261 | Miranda S Kidd | miranda.kidd@vdot.virginia.gov | (757) 956-3342 |  |  |  | 0 |  | 0 | FY2021 | 2361000 | 1750768 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 319 days early | G | Project is on budget | [5 empty] | 2017-08-01 | 2017-07-12 | 2017-08-14 | 2017-08-14 | G | 2017-08-15 | 2017-07-17 | 2018-09-10 | 2018-01-17 | G | [5 empty] | 2018-08-02 | 2018-06-01 | 2018-08-15 | 2018-06-01 | G | 2018-12-07 | 2018-12-13 | 2018-12-17 | 2018-12-16 | G | 2019-06-06 | 2019-10-17 | 2019-11-06 | 2020-03-26 | R | 2018-12-28 | 2019-01-07 | 2019-04-09 | 2019-09-03 | R | [10 empty] | 2020-12-08 | 2020-02-11 | 2020-12-08 | 2020-02-11 | G | 2021-03-03 | 2020-05-07 | 2021-03-22 | 2020-05-07 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.11199
1400 | 107044 | #HB2.FY17 I64/Northampton Boulevard Interchange Modification | 0064 | Interstate | Traffic Management/Engineering | VDOT | Norfolk | NORFOLK | Hampton Roads | Hampton Roads:Norfolk | Infrastructure Investment Division | Peter G Reilly | Peter.Reilly@vdot.virginia.gov | (757) 858-6748 | Lynette Guy | Lynette.Guy@vdot.virginia.gov | (757) 956-3350 |  |  |  | 1 | 2017 | 0 | FY2017 | 9300000 | 9300000 | WAITING FINANCIAL CLOSURE | R | Start Delivery milestone finished 3 days late | G | Project is on budget | [5 empty] | 2016-08-09 | 2016-08-09 | 2016-08-09 | 2016-08-09 | G | 2016-07-20 | 2016-07-20 | 2016-10-28 | 2016-10-28 | G | [5 empty] | 2016-10-13 | 2016-10-13 | 2016-12-16 | 2016-12-16 | G | 2017-03-14 | 2017-03-14 | 2017-03-14 | 2017-03-14 | G | [10 empty] | 2016-09-29 | 2016-09-29 | 2016-10-17 | 2016-10-18 | R | [5 empty] | 2017-03-14 | 2017-03-14 | 2017-03-14 | 2017-03-14 | G | 2017-04-26 | 2017-05-19 | 2017-05-16 | 2017-05-19 | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 1 | 0.36991
1401 | 108158 | PHASE III - BLUE RIDGE RAILROAD TUNNEL (NELSON COUNTY) | 9999 | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Nelson County | DILLWYN | Lynchburg | NonMPO:NonMPO | Local Assistance Division | Sharon S White | Sharon.White@VDOT.Virginia.gov | (434) 856-8220 | Sharon S White | Sharon.White@VDOT.Virginia.gov | (434) 856-8220 | Steven Carter | scarter@nelsoncounty.org | (434) 263-7001 | 0 |  | 0 | FY2020 | 1221974 | 1649250 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 4 days early | R | Project estimate is less than $5M and is 20% or more over budget | 2016-10-03 | 2015-11-04 | 2016-12-30 | 2015-11-17 | G | [5 empty] | 2015-11-18 | 2015-11-18 | 2017-02-13 | 2017-02-13 | G | [35 empty] | 2017-04-28 | 2017-04-23 | 2017-04-28 | 2017-04-24 | G | 2019-07-10 | 2019-07-17 | 2019-08-19 | 2019-08-15 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.34718
1402 | 108731 | #HB2.FY17 Coliseum Drive Extension - Segment A |  | Urban | New Construction Roadway | Locally | Hampton | WILLIAMSBURG | Hampton Roads | Hampton Roads:Hampton | Infrastructure Investment Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Joshua D Negovan | Joshua.Negovan@vdot.virginia.gov | (757) 956-3347 | Sandon Rogers, P.E. | sandon.rogers@hampton.gov | (757) 727-6786 | 1 | 2017 | 0 | FY2020 | 4573000 | 5487227 | CONSTRUCTION STARTED | R | Start Delivery milestone finished 153 days late | Y | Project estimate is less than $5M and is up to 20% over budget | 2016-06-23 | 2016-06-23 | 2016-09-06 | 2016-09-05 | G | 2016-09-06 | 2016-09-06 | 2016-09-19 | 2016-09-19 | G | 2016-09-20 | 2016-09-20 | 2017-04-10 | 2018-04-19 | R | [10 empty] | 2018-05-04 | 2018-05-04 | 2018-09-04 | 2019-01-03 | R | [5 empty] | 2018-09-06 | 2019-01-08 | 2019-06-19 | 2019-07-01 | R | [10 empty] | 2019-07-08 | 2019-11-04 | 2019-09-06 | 2020-01-21 | R | 2019-09-09 | 2020-04-20 | 2019-11-19 | 2020-04-20 | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.30632
1403 | 109555 | #HB2.FY17 BUS 460 - RECONSTRUCT INTERSECTION AT RTE 622 | 0460 | Primary | Safety | VDOT | Lynchburg | APPOMATTOX | Lynchburg | Lynchburg:Lynchburg | Infrastructure Investment Division | Brian J Casto | Brian.Casto@VDOT.Virginia.gov | (434) 856-8276 | Anthony W Revelle | Anthony.Revelle@vdot.virginia.gov | (434) 856-8258 |  |  |  | 1 | 2017 | 0 | FY2021 | 3233297 | 3233297 | ADVERTISED | R | Start Delivery milestone is 54 days past the expected completion date | G | Project is on budget | [5 empty] | 2017-03-01 | 2017-02-27 | 2017-03-14 | 2017-02-28 | G | 2017-03-15 | 2017-03-01 | 2018-02-09 | 2017-11-30 | G | [5 empty] | 2018-09-28 | 2018-06-12 | 2018-10-11 | 2018-07-10 | G | 2019-09-17 | 2019-06-04 | 2019-09-30 | 2019-07-09 | G | 2020-02-24 | 2020-05-08 | 2020-09-23 | 2020-10-08 | R | 2019-10-16 | 2019-12-09 | 2020-04-27 | 2020-04-24 | G | 2019-03-08 | 2018-08-16 | 2020-03-09 | 2018-08-16 | G | [5 empty] | 2020-10-13 | 2020-10-06 | 2020-10-13 | 2020-10-06 | G | 2020-12-08 |  | 2020-12-29 |  | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.15578
1404 | 111019 | #SMART18 - Brambleton Ave/Park Ave Intersection Improvements | 0166 | Urban | Reconstruction w/ Added Capacity | Locally | Norfolk | NORFOLK | Hampton Roads | Hampton Roads:Norfolk | Infrastructure Investment Division | Todd M Halacy | Todd.Halacy@VDOT.Virginia.gov | (757) 956-3010 | Derrick Williams | Derrick.Williams@vdot.virginia.gov | (757) 956-3097 | Deborah A. Mangiaracina, PE | deborah.mangiaracina@norfolk.gov | (757) 664-7459 | 1 | 2018 | 0 | FY2023 | 594000 | 593999 | NO DATES SET YET | R | Agreement with Locality milestone is 194 days past the expected completion date | G | Project is on budget | 2020-05-18 |  | 2020-08-11 |  | R | 2020-08-12 |  | 2020-08-17 |  | R | 2020-08-18 |  | 2021-03-01 |  | Y | [10 empty] | 2021-07-13 |  | 2021-08-02 |  | G | [5 empty] | 2021-08-04 |  | 2022-06-30 |  | G | [10 empty] | 2022-07-19 |  | 2022-08-15 |  | G | 2022-08-16 |  | 2022-09-26 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.32233
1405 | 111090 | Jefferson Avenue Sidewalk | 0000 | Urban | Safety | Locally | Newport News | WILLIAMSBURG | Hampton Roads | Hampton Roads:Newport News | Infrastructure Investment Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Chessica Villaflores | Chessica.Villaflores@vdot.virginia.gov | (757) 956-3094 | Bryan Stilley | bstilley@nnva.gov | (757) 925-2616 | 0 |  | 0 | FY2024 | 781000 | 781000 | NO DATES SET YET-PE OPEN | G | Start Development milestone finished 49 days early | G | Project is on budget | 2020-09-01 | 2020-07-17 | 2020-11-30 | 2020-09-02 | G | 2020-12-01 | 2020-09-03 | 2020-12-14 | 2020-10-26 | G | 2020-12-15 | 2020-10-27 | 2021-12-15 |  | G | [10 empty] | 2022-10-07 |  | 2022-10-28 |  | G | [5 empty] | 2022-11-01 |  | 2023-08-14 |  | G | [10 empty] | 2023-08-30 |  | 2023-10-26 |  | G | 2023-10-27 |  | 2024-04-23 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.30087
1406 | 111431 | #SGR18LB - BRIDGE REPLACEMENT SUGAR BEND RD. (29702 Fed) | 0000 | Miscellaneous | Bridge Replacement w/o Added Capacity | Locally | Buchanan County | LEBANON | Bristol | NonMPO:NonMPO | Infrastructure Investment Division | Tabitha H Crowder | Tabitha.Crowder@vdot.virginia.gov | (276) 696-3482 | Roger L Musser | Roger.Musser@VDOT.Virginia.gov | (276) 696-3260 | Marcus Stiltner | marcus.stiltner@buchanancounty-va.gov | (276) 935-4013 | 0 |  | 1 | FY2021 | 180000 | 180000 | CONSTRUCTION STARTED | G | Start Delivery milestone finished on-time | G | Project is on budget | 2018-05-10 | 2018-02-01 | 2018-08-03 | 2018-04-02 | G | 2018-08-06 | 2018-04-03 | 2018-08-08 | 2018-04-05 | G | 2018-08-09 | 2018-04-06 | 2019-02-20 | 2019-02-19 | G | [35 empty] | 2020-01-14 | 2020-01-14 | 2020-04-09 | 2020-04-07 | G | 2020-04-10 | 2020-04-10 | 2020-07-06 | 2020-07-06 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.043537
1407 | 112022 | #SGR19LP - RT 60 EAST NELSON STREET - FY18 PRIMARY EXT. | 0060 | Urban | Restoration and Rehabilitation | Locally | Lexington | LEXINGTON | Staunton | NonMPO:NonMPO | Local Assistance Division | Michael L Branscome | Michael.Branscome@VDOT.Virginia.gov | (540) 332-2377 | Michael L Branscome | Michael.Branscome@VDOT.Virginia.gov | (540) 332-2377 | City of Lexington | jmartone@lexingtonva.gov | (540) 463-3154 | 0 |  | 1 | FY2019 | 447000 | 447000 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 17 days early | G | Project is on budget | 2017-12-29 | 2017-12-29 | 2018-03-28 | 2018-03-27 | G | [5 empty] | 2017-12-29 | 2017-12-29 | 2018-03-28 | 2018-03-27 | G | [35 empty] | 2018-04-12 | 2018-04-11 | 2018-05-15 | 2018-05-14 | G | 2018-05-16 | 2018-05-15 | 2018-07-12 | 2018-06-25 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.085883
1408 | 112893 | CROSSOVER MUTCD COMPLIANCE SIGNING | 9999 | Miscellaneous | Safety | VDOT | Fredericksburg District-wide |  | Fredericksburg | Fredericksburg:Fredericksburg District-wide | Infrastructure Investment Division | Sylvester C Okpala | Sylvester.Okpala@VDOT.Virginia.gov | (540) 907-8174 | Sylvester C Okpala | Sylvester.Okpala@VDOT.Virginia.gov | (540) 907-8174 |  |  |  | 0 |  | 0 | FY2019 | 500000 | 546690 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 70 days early | Y | Project estimate is less than $5M and is up to 20% over budget | [10 empty] | 2018-05-01 | 2018-05-01 | 2018-05-07 | 2018-05-04 | G | [25 empty] | 2018-05-01 | 2018-07-18 | 2018-11-02 | 2018-07-18 | G | [5 empty] | 2018-12-11 | 2018-08-14 | 2018-12-11 | 2018-10-09 | G | 2019-03-07 | 2018-12-27 | 2019-03-07 | 2018-12-27 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.07026
1409 | 113848 | #SGR19VB - RT 61 over Cove Crk Tazewell VA 1069 Fed 18469 | 0061 | Primary | Bridge Rehab w/o Added Capacity | VDOT | Tazewell County | LEBANON | Bristol | NonMPO:NonMPO | Infrastructure Investment/Asset Management Division | Gary Lester |  |  | Shane C Morrison | Shane.Morrison@vdot.virginia.gov | (276) 696-3380 |  |  |  | 0 |  | 1 | FY2022 | 750000 | 750000 | NO DATES SET YET | G | Determine Requirements milestone is 269 days ahead of the expected completion date | G | Project is on budget | [10 empty] | 2021-11-03 |  | 2021-11-17 |  | G | [35 empty] | 2021-12-14 |  | 2021-12-14 |  | G | 2022-03-10 |  | 2022-03-10 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.14158
1410 | 107228 | Criser Road Bridge Replacement - Front Royal | 0002 | Urban | Bridge Replacement w/o Added Capacity | Locally | Front Royal | EDINBURG | Staunton | NonMPO:NonMPO | Local Assistance Division | Kimberly Cameron | Kim.Cameron@vdot.virginia.gov | (540) 332-7886 | Kimberly Cameron | Kim.Cameron@vdot.virginia.gov | (540) 332-7886 | Robert Brown | rbrown@frontroyalva.com | (540) 631-3595 | 0 |  | 0 | FY2019 | 450000 | 450000 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 212 days early | G | Project is on budget | 2015-09-30 | 2015-09-02 | 2015-12-29 | 2015-09-28 | G | 2015-12-30 | 2015-12-30 | 2016-01-13 | 2016-01-13 | G | 2016-01-14 | 2016-01-14 | 2016-09-07 | 2016-09-07 | G | [10 empty] | 2016-07-28 | 2016-07-28 | 2017-08-10 | 2017-08-10 | G | [20 empty] | 2017-09-15 | 2017-08-14 | 2018-01-16 | 2017-08-14 | G | 2018-06-01 | 2017-09-14 | 2018-11-21 | 2018-04-23 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.086611
1411 | 108631 | RIVERSIDE DR - REPLACE BRIDGE |  | Secondary | Bridge Replacement w/o Added Capacity | Locally | Richmond | ASHLAND | Richmond | Richmond:Richmond | Local Assistance Division | Brian J Lokker | Brian.Lokker@VDOT.Virginia.gov | (804) 524-6010 | Brian J Lokker | Brian.Lokker@VDOT.Virginia.gov | (804) 524-6010 | Tom Westbrook | thomas.westbrook@richmondgov.com | (804) 646-3421 | 0 |  | 0 | FY2020 | 700000 | 603094 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 56 days early | G | Project is on budget | 2017-07-25 | 2016-08-03 | 2017-10-18 | 2016-08-03 | G | 2017-10-19 | 2017-11-20 | 2017-10-23 | 2017-11-28 | R | 2017-10-24 | 2017-11-22 | 2018-05-03 | 2018-06-06 | R | [35 empty] | 2019-05-22 | 2019-05-08 | 2019-06-19 | 2019-06-19 | G | 2019-06-20 | 2019-06-20 | 2019-10-30 | 2019-09-04 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.16844
1412 | 109382 | #HB2.FY17 Deep Creek Bridge Replacement | 0017 | Primary | Bridge Rehab w/ Added Capacity | Locally | Chesapeake | NORFOLK | Hampton Roads | Hampton Roads:Chesapeake | Infrastructure Investment Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Johndel A Alcaide | John.Alcaide@vdot.virginia.gov | (757) 956-3098 | Troy Eisenberger, PE | teisenberger@cityofchesapeake.net | (757) 382-6383 | 1 | 2017 | 0 | FY2020 | 48468000 | 48468000 | ACTIVITY DATES SET | R | Solicit Bids milestone is 1068 days past the expected completion date | Y | Estimate not current | 2016-07-12 | 2016-07-12 | 2017-01-31 | 2018-11-27 | R | 2015-05-26 | 2015-05-26 | 2015-05-28 | 2015-05-28 | G | 2015-05-29 | 2015-05-29 | 2016-03-18 | 2016-03-18 | G | 2016-01-22 | 2016-01-22 | 2016-02-18 | 2016-02-18 | G | [5 empty] | 2017-03-31 | 2017-01-09 | 2017-04-20 | 2017-01-09 | G | [5 empty] | 2017-01-10 | 2017-01-10 | 2019-06-17 |  | R | [10 empty] | 2018-02-22 |  | 2018-03-21 |  | R | 2019-08-30 |  | 2020-02-27 |  | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.25331
1413 | 109954 | BIKESHARE CONNECTIONS-ORANGE & SILVER LINE METRORAIL STATION | 9999 | Urban | Facilities for Pedestrians and Bicycles | Locally | Falls Church | FAIRFAX | Northern Virginia | Northern Virginia:Falls Church | Infrastructure Investment Division | Amir Salahshoor | A.Salahshoor@VDOT.Virginia.gov | (703) 259-1957 | Rita Hockman | Rita.Hockman@vdot.virginia.gov | (804) 824-7421 | Kerri Oddenino | koddenino@fallschurchva.gov | (703) 248-5041 | 0 |  | 0 | FY2020 | 2000000 | 1215902 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 273 days early | G | Project is on budget | 2016-08-31 | 2016-08-31 | 2016-11-29 | 2016-11-18 | G | 2016-11-30 | 2016-11-21 | 2016-12-02 | 2016-12-02 | G | 2016-12-05 | 2016-12-02 | 2017-06-12 | 2017-12-05 | R | [10 empty] | 2018-06-14 | 2018-02-16 | 2018-07-05 | 2018-02-19 | G | [5 empty] | 2018-07-09 | 2018-02-21 | 2019-04-19 | 2018-02-21 | G | [10 empty] | 2019-05-07 | 2018-05-25 | 2019-06-04 | 2018-05-25 | G | 2019-06-05 | 2018-08-13 | 2019-07-16 | 2018-10-16 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.30311
1414 | 111057 | #SMART18 - (St) LEXINGTON N. MAIN ST COMPLETE STREETS ENTRY | 0011 | Primary | Reconstruction w/o Added Capacity | VDOT | Lexington | LEXINGTON | Staunton | NonMPO:NonMPO | Infrastructure Investment Division | Matthew P Dana | Matt.Dana@VDOT.Virginia.gov | (540) 332-7786 | Jethro Dienner | Jet.Dienner@vdot.virginia.gov | (540) 332-9290 |  |  |  | 1 | 2018 | 0 | FY2023 | 2845557 | 2845557 | NO DATES SET YET-PE OPEN | R | Determine Requirements milestone is 590 days past the expected completion date | G | Project is on budget | [5 empty] | 2018-07-31 | 2018-06-18 | 2018-08-13 | 2018-06-22 | G | 2018-08-14 | 2018-06-25 | 2019-07-12 |  | R | [5 empty] | 2020-03-16 |  | 2020-03-27 |  | R | 2021-03-17 |  | 2021-03-30 |  | G | 2021-11-17 |  | 2022-08-22 |  | G | 2021-04-15 |  | 2022-01-20 |  | G | 2020-08-27 |  | 2021-05-19 |  | G | [5 empty] | 2022-09-13 |  | 2022-09-13 |  | G | 2022-10-28 |  | 2022-12-28 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.089529
1415 | 111365 | #SMART18 - Right Turn Lane NB Rte 811 at Rte 622 | 0811 | Secondary | Other | VDOT | Bedford County | BEDFORD | Salem | Lynchburg:Bedford County | Infrastructure Investment Division | Alex H Price | Alex.Price@VDOT.Virginia.gov | (540) 378-5053 | Anthony L Handy | Tony.Handy@VDOT.Virginia.gov | (540) 352-9050 | Gregg Zody | gzody@bedfordcountyva.gov | (540) 586-7616 | 1 | 2018 | 0 | FY2021 | 321404 | 381163 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 451 days early | Y | Project estimate is less than $5M and is up to 20% over budget | [5 empty] | 2017-07-03 | 2017-06-22 | 2017-07-17 | 2017-06-27 | G | 2017-07-18 | 2017-07-24 | 2018-02-09 | 2018-02-08 | G | [5 empty] | 2018-11-20 | 2018-08-09 | 2018-12-05 | 2018-08-14 | G | 2019-06-03 | 2018-11-02 | 2019-06-14 | 2018-11-16 | G | 2019-10-09 | 2018-04-17 | 2020-03-23 | 2019-03-15 | G | 2019-07-02 | 2018-12-05 | 2020-01-09 | 2019-01-30 | G | [10 empty] | 2020-04-14 | 2019-03-26 | 2020-04-14 | 2019-03-26 | G | 2020-05-29 | 2019-05-28 | 2020-08-21 | 2019-05-28 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | SAAP CONTRACT | 1 | 0 | 0.19149
1417 | 112819 | NEW TRAFFIC SIGNALS - MULTIPLE LOCATIONS. | 9999 | Secondary | Safety | VDOT | Northern Virginia District-wide |  | Northern Virginia | Northern Virginia:Northern Virginia District-wide | Infrastructure Investment Division | Waqar A Siddiqui | Sid.Siddiqui@VDOT.Virginia.gov | (703) 259-3225 | Tienjung Ho | Tien-Jung.Ho@VDOT.Virginia.gov | (703) 259-2752 |  |  |  | 0 |  | 0 | FY2019 | 700000 | 700000 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 24 days early | G | Project is on budget | [10 empty] | 2018-12-03 | 2018-04-25 | 2019-04-12 | 2018-05-16 | G | [35 empty] | 2018-06-28 | 2018-06-20 | 2018-07-05 | 2018-06-20 | G | 2018-07-06 | 2018-06-21 | 2018-07-19 | 2018-06-25 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | WORK/TASK ORDER | 1 | 0 | 0.098523
1418 | 113325 | GREENWAY DRIVE - RECONSTRUCTION | 9999 | Urban | Reconstruction w/o Added Capacity | Locally | South Boston | HALIFAX | Lynchburg | NonMPO:NonMPO | Local Assistance Division | Sharon S White | Sharon.White@VDOT.Virginia.gov | (434) 856-8220 | Sharon S White | Sharon.White@VDOT.Virginia.gov | (434) 856-8220 | C. W. Crowder, Jr. | ccrowder@southboston.va.us | (434) 575-4261 | 0 |  | 0 | FY2020 | 246420 | 246420 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 5 days early | G | Project is on budget | 2020-01-31 | 2019-07-01 | 2020-04-24 | 2019-07-23 | G | 2020-04-27 | 2019-10-01 | 2020-04-29 | 2019-10-01 | G | 2020-04-30 | 2019-10-01 | 2020-11-03 | 2019-10-01 | G | [10 empty] | 2020-02-04 | 2020-02-04 | 2020-02-04 | 2020-02-04 | G | [5 empty] | 2020-02-06 | 2020-02-06 | 2020-02-06 | 2020-02-06 | G | [10 empty] | 2020-02-07 | 2020-02-07 | 2020-02-07 | 2020-02-07 | G | 2020-02-08 | 2020-02-08 | 2020-02-13 | 2020-02-08 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.071977
1419 | 113881 | #SGR19LB??- Oak St over NS RWY Bristol VA 8010 Fed 19982 | 0000 | Urban | Bridge Replacement w/o Added Capacity | Locally | Bristol | ABINGDON | Bristol | Bristol:Bristol | Infrastructure Investment/Asset Management Division | John W Bechtold | John.Bechtold@vdot.virginia.gov | (276) 696-3365 | Kenneth R Plummer | KR.Plummer@VDOT.Virginia.gov | (276) 696-3261 | Wallace McCulloch | wallace.mcculloch@bristolva.org | (276) 642-2316 | 0 |  | 1 | FY2023 | 3000000 | 3000000 | NO DATES SET YET-PE OPEN | G | Start Development milestone finished 289 days early | G | Project is on budget | 2020-11-05 | 2019-08-16 | 2021-02-05 | 2020-02-24 | G | 2021-02-08 | 2020-02-25 | 2021-02-10 | 2020-04-27 | G | 2021-02-11 |  | 2021-08-16 |  | G | [25 empty] | 2021-09-22 |  | 2022-05-31 |  | G | [5 empty] | 2022-09-02 |  | 2022-09-30 |  | G | 2022-12-23 |  | 2022-12-23 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.061787
1420 | 114652 | RUSSELL ROAD-INSTALL SIGNALIZED CROSSWALK | 0000 | Urban | Safety | Locally | Abingdon | ABINGDON | Bristol | Bristol:Abingdon | Infrastructure Investment Division | John W Bechtold | John.Bechtold@vdot.virginia.gov | (276) 696-3365 | Roger L Musser | Roger.Musser@VDOT.Virginia.gov | (276) 696-3260 | John Dew | jdew@abingdon-va.gov | (276) 628-3167 | 0 |  | 0 | FY2021 | 113452 | 113452 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 48 days early | G | Project is on budget | 2018-12-13 | 2018-12-13 | 2019-03-13 | 2019-02-06 | G | 2019-03-14 | 2019-02-01 | 2019-03-18 | 2019-02-27 | G | 2019-03-19 | 2019-02-28 | 2019-09-19 | 2019-06-14 | G | [25 empty] | 2019-06-17 | 2019-06-17 | 2019-09-10 | 2019-06-17 | G | [5 empty] | 2020-02-18 | 2020-02-18 | 2020-04-23 | 2020-04-02 | G | 2020-07-14 | 2020-04-14 | 2020-07-14 | 2020-05-27 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.089879
1421 | 115352 | #SGR20LP - RT 17 ( Bridge Rd) | 0017 | Urban | Resurfacing | Locally | Suffolk | NORFOLK | Hampton Roads | Hampton Roads:Suffolk | Infrastructure Investment/Asset Management Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Johndel A Alcaide | John.Alcaide@vdot.virginia.gov | (757) 956-3098 | Edward Heide | eheide@suffolkva.us | (757) 514-7615 | 0 |  | 1 | FY2020 | 248288 | 248288 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 188 days early | G | Project is on budget | 2019-10-01 | 2019-10-01 | 2019-12-30 | 2019-10-25 | G | [5 empty] | 2019-10-01 | 2019-10-01 | 2019-10-14 | 2019-10-14 | G | [35 empty] | 2020-01-16 | 2019-10-25 | 2020-02-14 | 2019-10-30 | G | 2020-03-10 | 2019-10-25 | 2020-05-05 | 2019-10-30 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.067894
1422 | 115764 | #SMART20 - HARRISON RD & SALEM CHURCH | 0620 | Secondary | Safety | VDOT | Spotsylvania County | FREDERICKSBURG | Fredericksburg | Fredericksburg:Spotsylvania County | Infrastructure Investment Division | Catherine C Coffey | Catherine.Coffey@vdot.virginia.gov | (540) 899-4280 | Khalil Minhas | Khalil.Minhas@vdot.virginia.gov | (540) 374-3369 | Paul Agnello | pagnello@spotsylvania.va.us | (540) 507-7398 | 1 | 2020 | 0 | FY2025 | 6100000 | 6100000 | NO DATES SET YET-PE OPEN | G | Start Development milestone finished on-time | G | Project is on budget | [5 empty] | 2019-08-26 | 2019-08-26 | 2019-09-12 | 2019-09-12 | G | 2020-08-05 | 2020-08-05 | 2021-06-21 |  | G | [5 empty] | 2022-01-07 |  | 2022-01-24 |  | G | 2022-10-28 |  | 2022-12-13 |  | G | 2023-10-03 |  | 2024-06-24 |  | G | 2022-12-30 |  | 2023-10-02 |  | G | 2022-05-06 |  | 2022-11-09 |  | G | [5 empty] | 2024-07-09 |  | 2024-07-09 |  | G | 2024-09-27 |  | 2024-09-27 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.072836
1423 | 116171 | #I81CIP SB MM 16.6 EXTEND ACCEL LANE (ID #26) | 0081 | Interstate | Reconstruction w/o Added Capacity | VDOT | Abingdon | ABINGDON | Bristol | Bristol:Abingdon | Infrastructure Investment Division | Donald A Necessary | Donald.Necessary@VDOT.Virginia.gov | (276) 696-3285 | Ronald C Flanary | Ronald.Flanary@VDOT.Virginia.gov | (276) 696-3252 |  |  |  | 0 |  | 0 | FY2021 | 3704108 | 1621184 | CONSTRUCTION STARTED | G | Start Delivery milestone finished on-time | G | Project is on budget | [5 empty] | 2020-07-01 | 2020-01-31 | 2020-07-15 | 2020-02-03 | G | 2020-07-16 | 2020-02-03 | 2021-03-12 | 2020-02-03 | G | [5 empty] | 2020-02-18 | 2020-02-18 | 2020-02-18 | 2020-02-18 | G | [5 empty] | 2019-12-18 | 2019-12-18 | 2019-12-18 | 2019-12-18 | G | [15 empty] | 2020-09-08 | 2020-09-08 | 2020-09-08 | 2020-09-08 | G | 2020-12-02 | 2020-12-02 | 2020-12-02 | 2020-12-02 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.090643
1424 | 116906 | ROUTE 250 BYPASS/HYDRAULIC TURN LANE EXTENSION | 0250 | Primary | Safety | Locally | Charlottesville | CHARLOTTESVILLE | Culpeper | Charlottesville:Charlottesville | Local Assistance Division | Gregory J Cooley | Gregory.Cooley@vdot.virginia.gov | (434) 906-7979 | Michael D Barnes | MichaelD.Barnes@vdot.virginia.gov | (434) 422-9861 | Jeanette Janiczek | janiczek@charlottesville.org | (434) 970-3309 | 0 |  | 0 | FY2024 | 300000 | 300000 | NO DATES SET YET | R | Agreement with Locality milestone is 6 days past the expected completion date | G | Project is on budget | 2020-10-01 |  | 2021-02-15 |  | R | 2021-02-16 |  | 2021-03-09 |  | Y | 2021-09-13 |  | 2022-01-10 |  | G | [25 empty] | 2023-01-05 |  | 2023-06-06 |  | G | [5 empty] | 2023-08-03 |  | 2023-08-30 |  | G | 2023-11-21 |  | 2023-11-21 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.2099
1425 | 117045 | Ridge Road Sidewalk Phase 2 | 7649 | Secondary | Facilities for Pedestrians and Bicycles | Locally | Henrico County | ASHLAND | Richmond | Richmond:Henrico County | Local Assistance Division | Cynthia Crouch | Cynthia.Crouch@vdot.virginia.gov | (804) 609-5313 | Cynthia Crouch | Cynthia.Crouch@vdot.virginia.gov | (804) 609-5313 | TBD |  | TBD | 0 |  | 0 | FY2029 | 3393000 | 3393000 | NO DATES SET YET | G | Agreement with Locality milestone is 1543 days ahead of the expected completion date | G | Project is on budget | 2025-01-06 |  | 2025-05-14 |  | G | 2025-05-15 |  | 2025-06-05 |  | G | 2025-12-15 |  | 2026-04-10 |  | G | [10 empty] | 2027-07-30 |  | 2027-09-02 |  | G | [5 empty] | 2027-09-03 |  | 2028-02-09 |  | G | 2028-01-05 |  | 2028-06-05 |  | G | [5 empty] | 2028-05-12 |  | 2028-06-09 |  | G | 2028-08-29 |  | 2028-08-29 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.36281
1426 | 117424 | ITTF HIGH SPEED COMMUNICATIONS ARTERIALS - NORTHERN | 9999 | Miscellaneous | Traffic Management/Engineering | VDOT | Northern Virginia District-wide |  | Northern Virginia | NonMPO:NonMPO | Infrastructure Investment Division | Catherine C Mcghee | Cathy.McGhee@VDOT.Virginia.gov | (434) 293-1973 | Ebo Y Duker | Ebo.Duker@vdot.virginia.gov | (571) 350-2077 |  |  |  | 0 |  | 0 | FY2021 | 600000 | 600000 | AWARDED | G | Start Delivery milestone finished 14 days early | G | Project is on budget | [10 empty] | 2020-06-01 | 2020-06-01 | 2020-10-06 | 2020-08-06 | G | [35 empty] | 2020-09-16 | 2020-09-25 | 2020-10-14 | 2020-10-07 | G | 2020-10-15 | 2020-10-08 | 2020-10-22 | 2020-10-08 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | WORK/TASK ORDER | 1 | 0 | 0.14125
1427 | 117973 | #81 CIP DETOUR IMPROVEMENTS-CHRISTIANSBURG, RADFORD, PULASKI | 9999 | Miscellaneous | Traffic Management/Engineering | VDOT | Radford | CHRISTIANSBURG | Salem | NonMPO:NonMPO | Infrastructure Investment Division | Bernard S Grinnell | Sean.Grinnell@VDOT.Virginia.gov | (540) 375-0148 | Shanon Spence | Shanon.Spence@vdot.virginia.gov | (540) 375-0115 |  |  |  | 0 |  | 0 | FY2024 | 4700000 | 4700000 | NO DATES SET YET-PE OPEN | G | Start Development milestone finished 1 days early | G | Project is on budget | [5 empty] | 2020-12-28 | 2020-12-28 | 2021-01-20 | 2021-01-19 | G | 2021-01-21 |  | 2021-11-18 |  | G | [5 empty] | 2022-06-22 |  | 2022-07-20 |  | G | [5 empty] | 2023-03-17 |  | 2023-07-17 |  | G | [5 empty] | 2022-12-12 | 2020-12-22 | 2023-05-12 | 2020-12-22 | G | [5 empty] | 2023-08-08 |  | 2023-08-08 |  | G | 2023-10-27 |  | 2023-10-27 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.11644
1428 | 118286 | W&OD TRAIL AT-GRADE IMPROVEMENTS |  | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Loudoun County | LEESBURG | Northern Virginia | Northern Virginia:Loudoun County | Local Assistance Division | Kimberly Mccool | Kimberly.McCool@vdot.virginia.gov | (703) 259-3220 | Susie X Lue | Susie.Lue@vdot.virginia.gov | (703) 259-2918 | Jim Zeller | james.zeller@loudoun.gov | (571) 258-3548 | 0 |  | 0 | FY2025 | 1446452 | 1446452 | NO DATES SET YET | G | Agreement with Locality milestone is 107 days ahead of the expected completion date | G | Project is on budget | 2021-02-01 | 2021-01-13 | 2021-06-08 |  | G | 2021-06-09 |  | 2021-06-29 |  | G | 2022-01-10 |  | 2022-05-04 |  | G | [10 empty] | 2023-08-23 |  | 2023-09-27 |  | G | [5 empty] | 2023-09-28 |  | 2024-03-05 |  | G | 2024-08-29 |  | 2025-02-04 |  | G | [5 empty] | 2024-06-06 |  | 2024-09-30 |  | G | 2024-12-23 |  | 2025-04-30 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.49175
1429 | 60933 | RTE 9999 - DABBS HOUSE RD; RECONSTRUCTION | 9999 | Secondary | Reconstruction w/ Added Capacity | Locally | Henrico County | ASHLAND | Richmond | Richmond:Henrico County | Infrastructure Investment Division | Brian J Lokker | Brian.Lokker@VDOT.Virginia.gov | (804) 524-6010 | Brian J Lokker | Brian.Lokker@VDOT.Virginia.gov | (804) 524-6010 | Paul Smith | smi91@henrico.us | (804) 501-5092 | 0 |  | 0 | FY2019 | 5180575 | 13289743 | CONSTRUCTION STARTED | R | Start Delivery milestone finished 621 days late | R | Project estimate is between $5M and $10M and is a $1M or more over budget | 2002-10-01 | 2002-10-01 | 2002-12-01 | 2004-04-14 | R | 2002-12-03 | 2002-12-03 | 2002-12-20 | 2002-12-20 | G | 2003-11-03 | 2003-11-01 | 2003-12-15 | 2003-12-15 | G | [5 empty] | 2014-05-22 | 2014-05-22 | 2014-05-22 | 2014-05-22 | G | 2014-04-15 | 2014-04-15 | 2014-06-23 | 2014-06-23 | G | 2018-05-07 | 2018-10-22 | 2019-02-28 | 2019-05-14 | R | 2016-08-08 | 2016-08-08 | 2018-01-11 | 2018-01-11 | G | [10 empty] | 2018-05-01 | 2020-06-10 | 2018-06-01 | 2020-06-10 | R | 2018-07-02 | 2020-07-14 | 2018-11-01 | 2020-07-14 | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.32736
1430 | 115274 | #SGR20LP - RT 293 - (ID 5415) RESURFACING (MAIN STREET) | 0293 | Urban | Resurfacing | Locally | Danville | HALIFAX | Lynchburg | Danville:Danville | Local Assistance Division | Sharon S White | Sharon.White@VDOT.Virginia.gov | (434) 856-8220 | Sharon S White | Sharon.White@VDOT.Virginia.gov | (434) 856-8220 | Brian Dunevant | dunevbl@danvilleva.gov | (434) 799-5019 | 0 |  | 0 | FY2020 | 254000 | 254000 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 90 days early | G | Project is on budget | 2020-01-31 | 2019-07-01 | 2020-04-24 | 2019-09-26 | G | [5 empty] | 2020-01-31 | 2019-09-27 | 2020-02-13 | 2020-01-23 | G | [35 empty] | 2020-01-24 | 2020-02-03 | 2020-02-21 | 2020-02-03 | G | 2020-05-11 | 2020-02-11 | 2020-05-11 | 2020-02-11 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.050195
1431 | 115458 | #SMART20 - Int Imprv on Rtes 122 & 636 (Lost Mtn Rd) | 0122 | Primary | Safety | VDOT | Franklin County | BEDFORD | Salem | NonMPO:NonMPO | Infrastructure Investment Division | Alex H Price | Alex.Price@VDOT.Virginia.gov | (540) 378-5053 | Brian H Becker | Brian.Becker@VDOT.Virginia.gov | (540) 204-7959 |  |  |  | 1 | 2020 | 0 | FY2028 | 9759000 | 9759000 | NO DATES SET YET | G | Start Development milestone is 904 days ahead of the expected completion date | G | Project is on budget | [5 empty] | 2023-08-01 |  | 2023-08-14 |  | G | 2023-08-15 |  | 2024-07-12 |  | G | [5 empty] | 2025-05-19 |  | 2025-06-02 |  | G | 2026-09-04 |  | 2026-09-18 |  | G | 2027-02-19 |  | 2027-08-23 |  | G | 2026-10-06 |  | 2027-04-16 |  | G | 2026-02-26 |  | 2026-08-28 |  | G | [5 empty] | 2027-09-14 |  | 2027-09-14 |  | G | 2027-12-08 |  | 2027-12-08 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 1 | 0.20229
1432 | 115789 | Primary Extension - C'burg - Radford Rd | 0011 | Urban | Reconstruction w/o Added Capacity | Locally | Christiansburg | CHRISTIANSBURG | Salem | New River Valley:Christiansburg | Local Assistance Division | Adam J Czesnowski | Adam.Czesnowski@vdot.virginia.gov | (540) 541-1216 | Adam J Czesnowski | Adam.Czesnowski@vdot.virginia.gov | (540) 541-1216 | Justin St. Clair | jstclair@christiansburg.org | (540) 382-6120 | 0 |  | 0 | FY2020 | 439019 | 439019 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 155 days early | G | Project is on budget | 2020-01-02 | 2019-07-01 | 2020-03-30 | 2019-08-07 | G | 2020-03-31 | 2019-09-03 | 2020-04-02 | 2019-09-05 | G | 2020-04-03 | 2019-09-19 | 2020-10-06 | 2019-09-20 | G | [35 empty] | 2019-12-31 | 2019-11-22 | 2019-12-31 | 2019-11-24 | G | 2020-01-27 | 2019-11-25 | 2020-06-30 | 2020-01-27 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.088366
1433 | 116834 | Wayfinding - High Knob Access Enhancements | 0018 | Miscellaneous | Facilities for Pedestrians and Bicycles | Locally | Norton | WISE | Bristol | NonMPO:NonMPO | Local Assistance Division | Kenneth R Plummer | KR.Plummer@VDOT.Virginia.gov | (276) 696-3261 | Kenneth R Plummer | KR.Plummer@VDOT.Virginia.gov | (276) 696-3261 | Fred Ramey | fredr@nortonva.org | (276) 679-1160 | 0 |  | 0 | FY2023 | 148000 | 148000 | NO DATES SET YET-PE OPEN | G | Start Development milestone finished 99 days early | G | Project is on budget | 2020-04-29 | 2020-04-29 | 2020-09-03 | 2020-05-20 | G | 2020-09-04 | 2020-04-29 | 2020-09-25 | 2020-06-18 | G | 2021-04-09 |  | 2021-08-02 |  | G | [25 empty] | 2022-07-28 |  | 2022-12-29 |  | G | [5 empty] | 2023-03-02 |  | 2023-03-29 |  | G | 2023-06-16 |  | 2023-06-16 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.12789
1434 | 117044 | Monument Ave Sidewalk | 9999 | Secondary | Facilities for Pedestrians and Bicycles | Locally | Henrico County | ASHLAND | Richmond | Richmond:Henrico County | Local Assistance Division | Douglas L Orcutt | Doug.Orcutt@vdot.virginia.gov | (804) 609-5428 | Douglas L Orcutt | Doug.Orcutt@vdot.virginia.gov | (804) 609-5428 | TBD |  | TBD | 0 |  | 0 | FY2029 | 3138650 | 3138650 | NO DATES SET YET | G | Agreement with Locality milestone is 1543 days ahead of the expected completion date | G | Project is on budget | 2025-01-06 |  | 2025-05-14 |  | G | 2025-05-15 |  | 2025-06-05 |  | G | 2025-12-15 |  | 2026-04-10 |  | G | [10 empty] | 2027-07-30 |  | 2027-09-02 |  | G | [5 empty] | 2027-09-03 |  | 2028-02-09 |  | G | 2028-01-05 |  | 2028-06-05 |  | G | [5 empty] | 2028-05-12 |  | 2028-06-09 |  | G | 2028-08-29 |  | 2028-08-29 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.3615
1435 | 117081 | #SGR21LB (Fed ID 22444) Br Repl/Rose Ave SE over Clear Crk | 0000 | Urban | Bridge Replacement w/o Added Capacity | VDOT | Norton | WISE | Bristol | NonMPO:NonMPO | Infrastructure Investment/Asset Management Division | Gary Lester |  |  | Emily V Collins | Emily.Collins@vdot.virginia.gov | (276) 696-3394 | Fred L. Ramey | fredr@nortonva.org | (276) 679-1160 | 0 |  | 1 | FY2025 | 1219877 | 1219877 | NO DATES SET YET | G | Start Development milestone is 247 days ahead of the expected completion date | G | Project is on budget | [5 empty] | 2021-10-05 |  | 2021-10-26 |  | G | 2021-10-27 |  | 2022-08-30 |  | G | [5 empty] | 2023-01-31 |  | 2023-02-28 |  | G | [15 empty] | 2023-09-20 |  | 2024-02-26 |  | G | [5 empty] | 2024-05-14 |  | 2024-05-20 |  | G | 2024-08-08 |  | 2024-08-08 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.060244
1436 | 117506 | JTHG Ground Graphic & Visual Identity-Fabrication |  | Enhancement | Scenic or Historic Highway Programs | VDOT | Statewide |  | Statewide | NonMPO:NonMPO | Local Assistance Division | Synthia Waymack | Synthia.Waymack@vdot.virginia.gov | (804) 786-2586 | Synthia Waymack | Synthia.Waymack@vdot.virginia.gov | (804) 786-2586 |  |  |  | 0 |  | 0 | FY2021 | 31204 | 31204 | NO DATES SET YET | R | Solicit Bids milestone is 47 days past the expected completion date | G | Project is on budget | [10 empty] | 2020-10-01 |  | 2021-02-15 |  | R | [35 empty] | 2020-12-29 |  | 2021-01-05 |  | R | 2021-01-06 |  | 2021-01-12 |  | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | WORK/TASK ORDER | 0 | 1 | 0.32142
1437 | 118194 | #I95 CIP NRO SSP FY21-24 | 0095 | Interstate | Safety | VDOT | Statewide |  | Statewide | Multiple MPOs:Statewide | Infrastructure Investment Division | Ricky A Via | Ricky.Via@vdot.virginia.gov | (804) 371-2396 | Teresa H Butler | Teresa.Butler@VDOT.Virginia.gov | (540) 229-3722 |  |  |  | 0 |  | 0 | FY2022 | 1033334 | 1033334 | ACTIVITY DATES SET | R | Determine Requirements milestone is 54 days past the expected completion date | G | Project is on budget | [10 empty] | 2020-12-15 |  | 2020-12-29 |  | R | [25 empty] | 2020-12-15 | 2020-10-22 | 2021-05-17 | 2020-10-22 | G | [5 empty] | 2021-04-13 |  | 2021-04-13 |  | Y | 2021-07-01 |  | 2021-07-01 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | ADMINISTRATIVE SERVICES | 0 | 1 | 0.30669
1438 | 17714 | #HB2.FY17 RTE 624 - RECONSTRUCTION | 0624 | Secondary | Reconstruction w/o Added Capacity | VDOT | Warren County | EDINBURG | Staunton | NonMPO:NonMPO | Infrastructure Investment Division | Charles W Gardner | Charles.Gardner@VDOT.Virginia.gov | (540) 332-7893 | Joseph M Seaman | Joseph.Seaman@VDOT.Virginia.gov | (540) 332-9908 |  |  |  | 1 | 2017 | 0 | FY2022 | 10487052 | 5863957 | ADVERTISED | G | Solicit Bids milestone finished on-time | G | Project is on budget | [5 empty] | 2013-03-01 | 2013-03-01 | 2013-07-31 | 2013-07-31 | G | 2016-09-16 | 2016-09-16 | 2017-10-19 | 2017-10-06 | G | [5 empty] | 2018-08-31 | 2018-08-30 | 2018-11-30 | 2018-11-29 | G | 2019-08-01 | 2019-06-17 | 2019-08-15 | 2019-07-01 | G | 2020-06-09 | 2020-06-16 | 2021-01-08 | 2020-06-24 | G | 2019-08-09 | 2019-07-11 | 2020-06-09 | 2020-05-21 | G | 2019-01-03 | 2019-06-06 | 2020-01-03 | 2019-12-06 | G | [5 empty] | 2020-12-16 | 2021-01-12 | 2021-01-12 | 2021-01-12 | G | 2021-04-23 |  | 2021-07-13 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.093118
1439 | 71962 | RTE 622 - PAVE ROADWAY & UPGRADE RAILROAD CROSSING | 0622 | Secondary | Reconstruction w/o Added Capacity | VDOT | Fauquier County | WARRENTON | Culpeper | NonMPO:NonMPO | Infrastructure Investment Division | Gregory J Cooley | Gregory.Cooley@vdot.virginia.gov | (434) 906-7979 | James D Cubbage | David.Cubbage@VDOT.Virginia.gov | (540) 727-7129 |  |  |  | 0 |  | 0 | FY2022 | 2045000 | 2045000 | NO DATES SET YET-PE OPEN | R | Determine Requirements milestone is 811 days past the expected completion date | G | Project is on budget | [5 empty] | 2012-09-04 | 2012-09-04 | 2016-10-31 | 2016-10-31 | G | 2016-12-01 | 2016-12-01 | 2018-12-03 |  | R | [10 empty] | 2020-04-09 |  | 2020-04-22 |  | R | [20 empty] | 2021-11-23 |  | 2021-11-23 |  | G | 2022-03-11 |  | 2022-04-06 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAILROAD FORCES | 0 | 0 | 0.10641
1440 | 101007 | RTE. F047 OVER PEAK CREEK (STR. 14442) - BRIDGE REPLACEMENT | 0047 | Secondary | Bridge Replacement w/o Added Capacity | VDOT | Pulaski County | CHRISTIANSBURG | Salem | NonMPO:NonMPO | Infrastructure Investment Division | Anthony T Marshall | Todd.Marshall@VDOT.Virginia.gov | (540) 387-5460 | Marvin D Mann | M.Mann@VDOT.Virginia.gov | (540) 378-5055 |  |  |  | 0 |  | 0 | FY2020 | 6661280 | 5786586 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 262 days early | G | Project is on budget | [5 empty] | 2016-08-01 | 2013-07-05 | 2016-08-01 | 2013-07-05 | G | 2016-08-31 | 2014-02-19 | 2016-10-31 | 2016-10-31 | G | [5 empty] | 2016-10-26 | 2016-10-26 | 2016-11-01 | 2016-11-01 | G | 2017-10-04 | 2017-10-04 | 2017-11-13 | 2017-11-13 | G | [5 empty] | 2018-02-20 | 2017-11-22 | 2018-08-22 | 2018-08-13 | G | 2017-12-15 | 2018-07-10 | 2019-01-08 | 2018-11-20 | G | [5 empty] | 2019-07-09 | 2019-02-12 | 2019-07-09 | 2019-02-12 | G | 2019-08-21 | 2019-04-29 | 2020-01-16 | 2019-04-29 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.065253
1441 | 102975 | REEDY CREEK - STORMWATER UTILITY - PHASE 2 |  | Urban | Utilities | Locally | Richmond | ASHLAND | Richmond | Richmond:Richmond | Local Assistance Division | Brian J Lokker | Brian.Lokker@VDOT.Virginia.gov | (804) 524-6010 | Brian J Lokker | Brian.Lokker@VDOT.Virginia.gov | (804) 524-6010 | LAMONT BENJAMIN | lamont.benjamin@richmondgov.co | (804) 646-6339 | 0 |  | 0 | FY2019 | 800000 | 800000 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 73 days early | G | Project is on budget | [5 empty] | 2012-10-01 | 2012-12-20 | 2012-12-31 | 2012-12-20 | G | 2014-02-03 | 2013-12-13 | 2014-06-01 | 2013-12-27 | G | [35 empty] | 2017-10-27 | 2017-10-27 | 2017-10-27 | 2017-10-27 | G | 2017-12-21 | 2018-04-20 | 2018-07-02 | 2018-04-20 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.16104
1442 | 103584 | Highway 301 North Sidewalk |  | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Greensville County | FRANKLIN | Hampton Roads | NonMPO:NonMPO | Local Assistance Division | Bryant H Porter | Bryant.Porter@VDOT.Virginia.gov | (757) 956-3092 | Joshua D Negovan | Joshua.Negovan@vdot.virginia.gov | (757) 956-3347 | Linwood E. Pope, Jr. | Lpope@greensvillecountyva.gov | (434) 348-4232 | 0 |  | 0 | FY2019 | 574100 | 832615 | CONSTRUCTION STARTED | R | Start Delivery milestone finished 370 days late | R | Project estimate is less than $5M and is 20% or more over budget | [5 empty] | 2013-06-24 | 2013-06-23 | 2013-06-24 | 2013-06-24 | G | 2014-07-17 | 2014-07-17 | 2018-05-01 | 2018-05-21 | R | [35 empty] | 2018-07-30 | 2018-07-30 | 2018-08-07 | 2018-08-07 | G | 2018-08-08 | 2019-09-18 | 2018-09-20 | 2019-09-25 | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.40515
1443 | 105958 | ALTAVISTA RTE 43/29 DOWNTOWN GATEWAY |  | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Altavista | APPOMATTOX | Lynchburg | NonMPO:NonMPO | Local Assistance Division | Sharon S White | Sharon.White@VDOT.Virginia.gov | (434) 856-8220 | Sharon S White | Sharon.White@VDOT.Virginia.gov | (434) 856-8220 | Waverly Coggsdale | jwcoggsdale@altavistava.gov | (434) 369-4369 | 0 |  | 0 | FY2019 | 648315 | 648315 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished on-time | G | Project is on budget | [5 empty] | 2014-09-02 | 2014-09-30 | 2014-10-01 | 2014-12-09 | R | 2018-04-02 | 2018-04-02 | 2018-04-30 | 2018-04-30 | G | [35 empty] | 2018-12-03 | 2018-11-30 | 2018-12-31 | 2018-12-27 | G | 2019-02-01 | 2019-01-31 | 2019-03-29 | 2019-03-29 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.28759
1444 | 107658 | VAN BUREN STREET MULTI-MODAL IMPROVEMENTS |  | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Herndon | FAIRFAX | Northern Virginia | Northern Virginia:Herndon | Local Assistance Division | Amir Salahshoor | A.Salahshoor@VDOT.Virginia.gov | (703) 259-1957 | Christer P Carshult | Christer.Carshult@vdot.virginia.gov | (703) 259-1765 | Town of Herndon |  |  | 0 |  | 0 | FY2019 | 1387275 | 1387275 | ACTIVITY DATES SET | R | Solicit Bids milestone is 774 days past the expected completion date | G | Project is on budget | 2015-10-01 | 2016-03-03 | 2015-12-30 | 2016-03-03 | R | 2015-12-31 | 2016-05-06 | 2016-01-05 | 2016-05-06 | R | 2016-01-06 | 2016-05-08 | 2016-07-12 | 2017-06-12 | R | [35 empty] | 2019-01-09 |  | 2019-01-09 |  | R | 2019-01-10 |  | 2019-02-22 |  | R | Delay due to changes in scope of work, project management, plan designs, or resolution of public comments | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.34139
1445 | 108729 | West Oceanview Avenue | 0060 | Urban | Bridge Replacement w/o Added Capacity | Locally | Norfolk | NORFOLK | Hampton Roads | Hampton Roads:Norfolk | Local Assistance Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Joshua D Negovan | Joshua.Negovan@vdot.virginia.gov | (757) 956-3347 | Deborah Mangiaracina, P.E. | deborah.mangiaracina@norfolk.gov | (757) 664-7459 | 0 |  | 0 | FY2019 | 3140000 | 3140000 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 104 days early | G | Project is on budget | 2016-11-10 | 2016-11-10 | 2016-11-17 | 2016-11-17 | G | 2016-12-19 | 2016-12-19 | 2016-12-30 | 2016-12-30 | G | 2017-01-03 | 2017-01-03 | 2018-05-14 | 2018-06-05 | R | [35 empty] | 2018-09-17 | 2018-09-17 | 2018-10-12 | 2018-09-21 | G | 2018-10-16 | 2018-03-09 | 2019-01-14 | 2018-10-02 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.11221
1447 | 109520 | #HB2.FY17 RTE. 22/208 INT. IMPROVEMENT AT REL. SCHOOL BUS RD | 0022 | Primary | Safety | VDOT | Louisa County | LOUISA | Culpeper | NonMPO:NonMPO | Infrastructure Investment Division | Gregory J Cooley | Gregory.Cooley@vdot.virginia.gov | (434) 906-7979 | Mike Brown | Mike.Brown@VDOT.Virginia.gov | (434) 422-9789 |  |  |  | 1 | 2017 | 0 | FY2021 | 7500000 | 7500000 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 21 days early | G | Project is on budget | [5 empty] | 2016-07-19 | 2016-07-19 | 2016-08-01 | 2016-08-01 | G | 2016-08-02 | 2016-08-02 | 2017-06-29 | 2017-06-19 | G | [5 empty] | 2018-03-12 | 2018-03-03 | 2018-03-23 | 2018-03-14 | G | 2019-04-03 | 2019-03-08 | 2019-04-16 | 2019-03-14 | G | 2020-02-06 | 2020-02-05 | 2020-08-10 | 2020-06-29 | G | 2019-05-02 | 2019-03-28 | 2020-02-05 | 2020-02-03 | G | 2018-09-14 | 2018-09-14 | 2019-09-16 | 2019-08-22 | G | [5 empty] | 2020-08-11 | 2020-08-11 | 2020-08-11 | 2020-08-11 | G | 2020-09-25 | 2020-11-02 | 2020-11-23 | 2020-11-02 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.079533
1448 | 111052 | #SMART18 - (St) RTE 682 FRIEDENS CHURCH RD INTERSECTION | 0682 | Secondary | Reconstruction w/o Added Capacity | VDOT | Rockingham County | HARRISONBURG | Staunton | Harrisonburg:Rockingham County | Infrastructure Investment Division | Matthew P Dana | Matt.Dana@VDOT.Virginia.gov | (540) 332-7786 | Joseph M Seaman | Joseph.Seaman@VDOT.Virginia.gov | (540) 332-9908 |  |  |  | 1 | 2018 | 0 | FY2022 | 1616434 | 1616434 | ACTIVITY DATES SET | G | Start Purchasing Right-of-Way milestone finished 5 days early | G | Project is on budget | [5 empty] | 2017-08-03 | 2017-07-17 | 2017-08-16 | 2017-07-26 | G | 2017-08-17 | 2017-08-07 | 2018-07-17 | 2018-07-16 | G | [5 empty] | 2019-05-21 | 2019-05-21 | 2019-06-04 | 2019-06-04 | G | 2020-09-17 | 2020-09-17 | 2020-09-29 | 2020-09-24 | G | 2021-03-02 |  | 2021-09-01 |  | G | 2020-10-15 |  | 2021-04-27 |  | G | 2020-03-10 | 2020-03-10 | 2020-09-09 | 2020-03-10 | G | [5 empty] | 2021-09-14 |  | 2021-09-14 |  | G | 2021-10-29 |  | 2021-12-29 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.09712
1449 | 111661 | #SMART18 - NAVAL BASE DAHLGREN TURN LANE EXT. RT. 301 SOUTH | 0301 | Primary | Safety | VDOT | King George County | FREDERICKSBURG | Fredericksburg | NonMPO:NonMPO | Infrastructure Investment Division | Khalil Minhas | Khalil.Minhas@vdot.virginia.gov | (540) 374-3369 | Sylvester C Okpala | Sylvester.Okpala@VDOT.Virginia.gov | (540) 907-8174 |  |  |  | 1 | 2018 | 0 | FY2021 | 2000000 | 2000000 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 129 days early | G | Project is on budget | [5 empty] | 2017-07-14 | 2017-06-30 | 2017-08-01 | 2017-07-07 | G | 2017-08-02 | 2017-07-10 | 2018-02-27 | 2018-02-20 | G | [5 empty] | 2018-07-30 | 2018-06-29 | 2018-08-24 | 2018-08-02 | G | 2019-01-14 | 2018-12-26 | 2019-01-29 | 2019-01-08 | G | 2019-08-12 | 2019-03-11 | 2020-02-13 | 2019-03-29 | G | 2019-02-14 | 2019-02-06 | 2019-08-12 | 2019-02-06 | G | 2018-09-13 | 2018-07-12 | 2019-03-26 | 2018-07-13 | G | [5 empty] | 2020-03-10 | 2020-01-07 | 2020-03-10 | 2020-01-07 | G | 2020-06-11 | 2020-03-30 | 2020-08-06 | 2020-03-30 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.067554
1450 | 101279 | #HB2.FY17 Replacement of bridge over Lake Maury | 0060 | Urban | Bridge Replacement w/o Added Capacity | Locally | Newport News | WILLIAMSBURG | Hampton Roads | Hampton Roads:Newport News | Infrastructure Investment Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Chessica Villaflores | Chessica.Villaflores@vdot.virginia.gov | (757) 956-3094 | Carolyn Bowman | cbowman@nnva.gov | (757) 926-3667 | 1 | 2017 | 0 | FY2017 | 8200000 | 8200000 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished on-time | G | Project is on budget | [5 empty] | 2012-10-16 | 2012-03-30 | 2012-10-16 | 2012-04-02 | G | 2012-11-15 | 2012-07-10 | 2013-03-15 | 2014-01-07 | R | 2014-01-07 | 2014-01-07 | 2014-01-07 | 2014-01-07 | G | [5 empty] | 2014-08-24 | 2014-08-24 | 2014-08-25 | 2014-08-25 | G | [5 empty] | 2014-08-25 | 2014-08-25 | 2017-01-19 | 2017-01-19 | G | 2016-11-23 | 2016-11-23 | 2016-11-29 | 2016-11-29 | G | [5 empty] | 2017-02-01 | 2017-02-01 | 2017-02-14 | 2017-02-14 | G | 2017-03-29 | 2017-03-29 | 2017-03-29 | 2017-03-29 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.26017
1451 | 103059 | Newport News Pedestrian Improvements | 0000 | Urban | Facilities for Pedestrians and Bicycles | Locally | Newport News | WILLIAMSBURG | Hampton Roads | Hampton Roads:Newport News | Infrastructure Investment Division | Stephen Rowan | Steve.Rowan@vdot.virginia.gov | (757) 790-9925 | Chessica Villaflores | Chessica.Villaflores@vdot.virginia.gov | (757) 956-3094 | David T. Wilkinson | dwilkinson@nngov.com | (757) 926-8611 | 0 |  | 0 | FY2023 | 1282015 | 1266918 | ACTIVITY DATES SET | Y | Start Purchasing Right-of-Way milestone is 8 days ahead of the expected completion date and there is a risk of missing this milestone date | G | Project is on budget | [5 empty] | 2018-12-03 | 2018-10-25 | 2019-03-01 | 2018-11-16 | G | 2019-03-04 | 2018-11-19 | 2020-10-28 | 2020-10-01 | G | [10 empty] | 2020-10-16 |  | 2021-03-01 |  | Y | [5 empty] | 2021-03-02 |  | 2022-11-01 |  | G | 2022-05-05 | 2021-01-22 | 2022-10-03 | 2021-01-22 | G | [5 empty] | 2022-12-05 |  | 2023-01-03 |  | G | 2023-03-27 |  | 2023-05-05 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.25654
1452 | 105233 | CITY OF COLONIAL HEIGHTS - SRTS - NORTH ES - SIDEWALKS | 0004 | Urban | Safety | Locally | Colonial Heights | CHESTERFIELD | Richmond | Tri-Cities:Colonial Heights | Infrastructure Investment Division | Evan Austin | Evan.Austin@vdot.virginia.gov | (804) 609-5384 | Evan Austin | Evan.Austin@vdot.virginia.gov | (804) 609-5384 | Keith Chisolm | chisolmk@colonialheightsva.gov | (804) 520-9215 | 0 |  | 0 | FY2020 | 250092 | 250052 | ADVERTISED | R | Start Delivery milestone is 541 days past the expected completion date | G | Project is on budget | 2013-10-01 | 2014-04-16 | 2013-11-01 | 2014-04-16 | R | 2013-11-01 | 2013-12-10 | 2014-02-01 | 2013-12-10 | G | 2013-10-01 | 2018-05-30 | 2018-07-31 | 2018-07-31 | G | [5 empty] | 2018-07-30 | 2018-07-30 | 2018-08-30 | 2018-07-30 | G | [25 empty] | 2019-05-30 | 2020-12-04 | 2019-06-28 | 2021-02-11 | R | 2019-07-30 |  | 2019-08-30 |  | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.15202
1453 | 106450 | TICONDEROGA ROAD - RECONSTRUCT AND PAVE GRAVEL ROAD | 0613 | Secondary | Reconstruction w/o Added Capacity | VDOT | Loudoun County | LEESBURG | Northern Virginia | Northern Virginia:Loudoun County | Infrastructure Investment Division | Mehrdad Naderi | Mehrdad.Naderi@vdot.virginia.gov | (703) 259-2217 | Kimberly Mccool | Kimberly.McCool@vdot.virginia.gov | (703) 259-3220 | Susan Glass, Loudoun County Dept. of Transportation & Capital Infrastructure | susan.glass@loudoun.gov | (703) 777-0551 | 0 |  | 0 | FY2023 | 2123742 | 2123742 | ACTIVITY DATES SET | Y | Obtained Permits milestone is 23 days ahead of the expected completion date and there is a risk of missing this milestone date | Y | Estimate not current | [5 empty] | 2017-07-05 | 2017-07-05 | 2017-07-05 | 2017-07-05 | G | 2020-11-02 | 2017-07-05 | 2021-02-28 | 2017-10-27 | G | [25 empty] | 2020-11-03 |  | 2021-03-16 |  | Y | [5 empty] | 2022-02-11 |  | 2022-02-11 |  | G | 2022-02-14 |  | 2022-08-30 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 1 | 0.21804
1454 | 108728 | New ADA Ramps throught out City | 0000 | Urban | Facilities for Pedestrians and Bicycles | Locally | Norfolk | NORFOLK | Hampton Roads | Hampton Roads:Norfolk | Local Assistance Division | Stephen Rowan | Steve.Rowan@vdot.virginia.gov | (757) 790-9925 | Derrick Williams | Derrick.Williams@vdot.virginia.gov | (757) 956-3097 | John White, P.E. | john.m.white@norfolk.gov | (757) 823-4108 | 0 |  | 0 | FY2019 | 500000 | 500000 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 177 days early | G | Project is on budget | 2016-10-04 | 2016-11-17 | 2017-01-03 | 2016-11-17 | G | 2017-01-04 | 2016-12-12 | 2017-01-06 | 2016-12-30 | G | 2017-01-09 | 2017-01-09 | 2017-07-14 | 2017-07-14 | G | [35 empty] | 2018-02-05 | 2018-01-11 | 2018-06-22 | 2018-01-11 | G | 2018-06-25 | 2018-02-03 | 2018-08-03 | 2018-02-07 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.13655
1455 | 109265 | ASHLAND ST EXTENSION |  | Urban | New Construction Roadway | VDOT | Hopewell | PETERSBURG | Richmond | Tri-Cities:Hopewell | Infrastructure Investment Division | Noyan F Erermis | Noyan.Erermis@vdot.virginia.gov | (804) 819-9653 | Noyan F Erermis | Noyan.Erermis@vdot.virginia.gov | (804) 819-9653 |  |  |  | 0 |  | 0 | FY2024 | 5314596 | 5314596 | NO DATES SET YET-PE OPEN | R | Determine Requirements milestone is 163 days past the expected completion date | G | Project is on budget | [5 empty] | 2019-10-01 | 2019-09-02 | 2019-10-14 | 2019-09-16 | G | 2019-10-15 |  | 2020-09-11 |  | R | [5 empty] | 2021-07-20 |  | 2021-08-02 |  | G | 2022-11-07 |  | 2022-11-21 |  | G | 2023-04-20 |  | 2023-10-24 |  | G | 2022-12-09 |  | 2023-06-16 |  | G | 2022-04-27 |  | 2022-10-31 |  | G | [5 empty] | 2023-11-14 |  | 2023-11-14 |  | G | 2024-02-09 |  | 2024-02-09 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.086766
1456 | 109370 | #SMART18 - (St) RTE. 606 INTER IMPROVEMENTS AT I-81 EXIT 205 | 0606 | Secondary | Reconstruction w/o Added Capacity | VDOT | Rockbridge County | LEXINGTON | Staunton | NonMPO:NonMPO | Infrastructure Investment Division | Susan E Hammond | Susan.Hammond@VDOT.Virginia.gov | (540) 462-6990 | Timothy Gregory | Tim.Gregory@vdot.virginia.gov | (540) 332-7891 |  |  |  | 1 | 2018 | 0 | FY2022 | 2440103 | 2440100 | ACTIVITY DATES SET | R | Complete Purchasing Right-of-Way milestone is 234 days past the expected completion date | G | Project is on budget | [5 empty] | 2017-08-03 | 2017-07-17 | 2017-08-16 | 2017-07-26 | G | 2017-08-17 | 2017-07-26 | 2018-09-26 | 2018-09-25 | G | [5 empty] | 2019-03-21 | 2019-03-21 | 2019-04-15 | 2019-04-15 | G | 2019-11-14 | 2020-09-01 | 2019-11-27 | 2020-09-24 | R | 2020-07-08 | 2020-11-25 | 2021-04-05 |  | G | 2019-12-17 | 2020-10-26 | 2020-07-02 |  | R | 2019-08-05 | 2019-12-16 | 2020-02-13 | 2020-03-19 | R | [5 empty] | 2021-04-13 |  | 2021-04-13 |  | Y | 2021-05-27 |  | 2021-07-23 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.094263
1458 | 111300 | #SGR18VB - BRIDGE REHAB 1ST STREET OVER I-95 | 9999 | Primary | Bridge Rehab w/o Added Capacity | VDOT | Richmond | ASHLAND | Richmond | Richmond:Richmond | Infrastructure Investment/Asset Management Division | Anthony S Haverly | Anthony.Haverly@vdot.virginia.gov | (804) 609-5225 | Anthony S Haverly | Anthony.Haverly@vdot.virginia.gov | (804) 609-5225 |  |  |  | 0 |  | 1 | FY2022 | 11146431 | 11146431 | NO DATES SET YET-PE OPEN | G | Start Development milestone finished on-time | G | Project is on budget | [5 empty] | 2017-03-17 | 2017-03-17 | 2017-03-17 | 2017-03-17 | G | 2020-08-10 | 2019-12-23 | 2021-06-30 |  | G | [10 empty] | 2021-06-25 |  | 2021-07-16 |  | G | [20 empty] | 2021-07-19 |  | 2021-08-16 |  | G | 2022-02-16 |  | 2022-03-16 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | DESIGN BUILD/PPTA | 0 | 0 | 0.12186
1459 | 111708 | #SMART18 - Route 13 at Stone Road - Northampton County | 0013 | Primary | Safety | VDOT | Northampton County | ACCOMAC | Hampton Roads | NonMPO:NonMPO | Infrastructure Investment Division | Peter G Reilly | Peter.Reilly@vdot.virginia.gov | (757) 858-6748 | John K Arms | John.Arms@vdot.virginia.gov | (757) 995-5156 | John J Andrzejewski | ckowlakowski@co.northampton.va.us | (757) 678-0440 | 1 | 2018 | 0 | FY2021 | 1739812 | 2069812 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 16 days early | Y | Project estimate is less than $5M and is up to 20% over budget | [5 empty] | 2017-09-01 | 2017-08-25 | 2017-09-15 | 2017-08-25 | G | 2017-09-18 | 2017-09-18 | 2018-01-17 | 2018-01-17 | G | [5 empty] | 2018-08-03 | 2018-08-03 | 2018-08-16 | 2019-02-08 | R | 2019-01-17 | 2019-08-08 | 2019-02-01 | 2019-09-10 | R | 2020-01-07 | 2020-03-04 | 2020-05-11 | 2020-07-27 | R | 2019-02-20 | 2019-09-16 | 2019-08-22 | 2020-01-21 | R | 2018-10-22 | 2019-01-03 | 2019-05-01 | 2019-01-03 | G | [5 empty] | 2020-05-12 | 2020-05-05 | 2020-05-12 | 2020-05-05 | G | 2020-06-26 | 2020-07-21 | 2020-08-06 | 2020-07-21 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.094928
1460 | 111919 | #SGR18LB - RT 938 - LINK ROAD BRIDGE REPLACE (Fed 20504) | 0938 | Urban | Bridge Replacement w/o Added Capacity | Locally | Lynchburg | APPOMATTOX | Lynchburg | Lynchburg:Lynchburg | Local Assistance Division | Gregg Allen | Gregg.Allen@vdot.virginia.gov | (434) 426-5575 | Sharon S White | Sharon.White@VDOT.Virginia.gov | (434) 856-8220 | Lee Newland | Lee.newland@lynchburg.gov | (434) 455-3947 | 0 |  | 1 | FY2022 | 4236175 | 4236175 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 268 days early | G | Project is on budget | 2021-07-15 | 2018-12-24 | 2021-10-07 | 2019-03-22 | G | 2021-10-08 | 2019-12-02 | 2021-10-12 | 2019-12-02 | G | 2021-10-13 | 2020-09-01 | 2022-04-25 | 2020-09-01 | G | [10 empty] | 2020-09-10 | 2020-09-10 | 2020-09-11 | 2020-09-11 | G | [5 empty] | 2020-09-15 | 2020-09-15 | 2020-09-16 | 2020-09-16 | G | [10 empty] | 2020-09-21 | 2020-09-21 | 2020-10-20 | 2020-10-20 | G | 2021-07-28 | 2020-10-21 | 2021-07-28 | 2020-11-02 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.0881
1461 | 113780 | RTE. 721 - RURAL RUSTIC RD (SURFACE TREAT NONHARDSURFACE RD) | 0721 | Secondary | Reconstruction w/o Added Capacity | VDOT | Albemarle County | CHARLOTTESVILLE | Culpeper | NonMPO:NonMPO | Infrastructure Investment Division | Ken Connors |  |  | Harold L Jones | Harold.Jones@VDOT.virginia.gov | (434) 422-9378 |  |  |  | 0 |  | 0 | FY2024 | 300000 | 300000 | NO DATES SET YET | G | Start Development milestone is 235 days ahead of the expected completion date | G | Project is on budget | [5 empty] | 2021-10-01 |  | 2021-10-14 |  | G | 2021-10-15 |  | 2022-06-13 |  | G | [5 empty] | 2023-02-22 |  | 2023-04-04 |  | G | [5 empty] | 2023-07-19 |  | 2023-11-09 |  | G | [5 empty] | 2023-07-03 |  | 2023-10-03 |  | G | [5 empty] | 2023-11-14 |  | 2023-11-14 |  | G | 2024-02-09 |  | 2024-02-09 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | SAAP CONTRACT | 0 | 0 | 0.15629
1462 | 114388 | Citywide ITS Upgrades- Multi Locations- CN Phase | 0060 | Urban | Safety | Locally | Newport News | WILLIAMSBURG | Hampton Roads | Hampton Roads:Newport News | Infrastructure Investment Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Chessica Villaflores | Chessica.Villaflores@vdot.virginia.gov | (757) 956-3094 | Randy Cooper | rcooper@nnva.gov | (757) 926-8702 | 0 |  | 0 | FY2020 | 2291162 | 1119497 | CONSTRUCTION STARTED | R | Start Delivery milestone finished 63 days late | G | Project is on budget | 2018-10-01 | 2017-11-06 | 2018-12-28 | 2017-11-07 | G | [5 empty] | 2018-10-01 | 2018-10-01 | 2018-10-12 | 2018-10-12 | G | [35 empty] | 2019-02-25 | 2020-03-10 | 2019-12-31 | 2020-04-21 | R | 2020-03-24 | 2020-05-22 | 2020-05-04 | 2020-07-06 | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.30714
1463 | 115116 | #SMART20 ROUTE 301 UNIVERSITYDR/MARKET CTR DOUBLE R-CUT | 0301 | Primary | Traffic Management/Engineering | VDOT | King George County | FREDERICKSBURG | Fredericksburg | NonMPO:NonMPO | Infrastructure Investment Division | Catherine C Coffey | Catherine.Coffey@vdot.virginia.gov | (540) 899-4280 | Khalil Minhas | Khalil.Minhas@vdot.virginia.gov | (540) 374-3369 |  |  |  | 1 | 2020 | 0 | FY2028 | 3500000 | 3500000 | NO DATES SET YET | G | Start Development milestone is 918 days ahead of the expected completion date | G | Project is on budget | [5 empty] | 2023-08-15 |  | 2023-08-28 |  | G | 2023-08-29 |  | 2024-07-26 |  | G | [5 empty] | 2025-06-03 |  | 2025-06-16 |  | G | 2026-09-21 |  | 2026-10-02 |  | G | 2027-03-05 |  | 2027-09-07 |  | G | 2026-10-21 |  | 2027-04-30 |  | G | 2026-03-12 |  | 2026-09-14 |  | G | [5 empty] | 2027-09-14 |  | 2027-09-14 |  | G | 2027-12-08 |  | 2027-12-08 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.096916
1464 | 115349 | BUS 58 EBL - (ID 5485) RESURFACING (SOUTH BOSTON ROAD) | 0058 | Urban | Resurfacing | Locally | Danville | HALIFAX | Lynchburg | Danville:Danville | Local Assistance Division | Sharon S White | Sharon.White@VDOT.Virginia.gov | (434) 856-8220 | Sharon S White | Sharon.White@VDOT.Virginia.gov | (434) 856-8220 | Brian Dunevant | dunevbl@danvilleva.gov | (434) 799-5019 | 0 |  | 0 | FY2020 | 155000 | 155000 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 93 days early | G | Project is on budget | 2020-01-31 | 2019-07-01 | 2020-04-24 | 2019-09-20 | G | [5 empty] | 2020-01-31 | 2019-09-23 | 2020-02-13 | 2020-01-28 | G | [35 empty] | 2020-01-29 | 2020-02-03 | 2020-02-26 | 2020-02-03 | G | 2020-05-14 | 2020-02-11 | 2020-05-14 | 2020-02-11 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.050079
1465 | 115541 | #SGR21VP - Cold In-Place Recycling, 2021 Accomac Residency | 9999 | Primary | Restoration and Rehabilitation | VDOT | Northampton County | ACCOMAC | Hampton Roads |  | Infrastructure Investment Division | William M Collier | W.Collier@VDOT.Virginia.gov | (757) 956-3006 | Andrew Mcgilvray | Andrew.McGilvray@vdot.virginia.gov | (757) 956-3171 |  |  |  | 0 |  | 1 | FY2022 | 2356817 | 962519 | ACTIVITY DATES SET | R | Determine Requirements milestone finished 322 days late | G | Project is on budget | [10 empty] | 2019-12-03 | 2019-10-28 | 2019-12-16 | 2020-11-02 | R | [35 empty] | 2020-12-08 |  | 2021-04-13 |  | Y | 2021-07-02 |  | 2021-08-12 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.12225
1466 | 116591 | DISTRICT-WIDE SYSTEMIC UNSIGNALIZED INTER (FY20-FY22) | 9999 | Miscellaneous | Safety | VDOT | Fredericksburg District-wide |  | Fredericksburg | Fredericksburg:Fredericksburg District-wide | Infrastructure Investment Division | Peter A Hedrich | Peter.Hedrich@vdot.virginia.gov | (540) 899-4540 | Jessica Graves | Jessica.Graves@vdot.virginia.gov | (540) 899-4267 |  |  |  | 0 |  | 0 | FY2022 | 705556 | 705556 | ACTIVITY DATES SET | G | Engage Public milestone finished 297 days early | G | Project is on budget | [5 empty] | 2020-04-01 | 2020-01-23 | 2020-04-01 | 2020-02-24 | G | 2020-04-02 | 2020-02-25 | 2020-07-10 | 2020-09-04 | R | [5 empty] | 2020-09-08 | 2020-09-04 | 2021-06-28 | 2020-09-04 | G | [25 empty] | 2021-09-15 |  | 2021-09-21 |  | G | 2021-09-22 |  | 2021-09-28 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | WORK/TASK ORDER | 0 | 0 | 0.070377
1467 | 117216 | 1400 -1500 24th Street Drainage Improvements | 0000 | Urban | Mitigation of Water Pollution Due to Highway Runof | Locally | Roanoke | SALEM | Salem | Roanoke:Roanoke City | Local Assistance Division | Cheryl B Becker | Cheryl.Becker@vdot.virginia.gov | (540) 492-2531 | Cheryl B Becker | Cheryl.Becker@vdot.virginia.gov | (540) 492-2531 | Joseph Arthur | Joseph.Arthur@roanokeva.gov | (540) 853-5906 | 0 |  | 0 | FY2024 | 340000 | 340000 | NO DATES SET YET-PE OPEN | G | Start Development milestone finished 131 days early | G | Project is on budget | 2020-06-01 | 2020-06-01 | 2020-10-06 | 2020-06-18 | G | 2020-10-07 | 2020-06-19 | 2020-10-28 | 2020-06-19 | G | 2021-05-11 |  | 2021-09-01 |  | G | [25 empty] | 2022-08-29 |  | 2023-02-02 |  | G | [5 empty] | 2023-04-03 |  | 2023-04-28 |  | G | 2023-07-19 |  | 2023-07-19 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.20332
1468 | 118221 | ACTUATED FLASHER AT RT 3/ RT 610 AND RT. 3 / RT. 613 SPOTSY | 0003 | Primary | Safety | VDOT | Spotsylvania County | FREDERICKSBURG | Fredericksburg | Fredericksburg:Spotsylvania County | Infrastructure Investment Division | Peter A Hedrich | Peter.Hedrich@vdot.virginia.gov | (540) 899-4540 | Benjamin Ernst | Benjamin.Ernst@vdot.virginia.gov | (571) 585-0902 |  |  |  | 0 |  | 0 | FY2021 | 240000 | 240000 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 2 days early | G | Project is on budget | [10 empty] | 2020-11-13 | 2020-10-26 | 2021-03-29 | 2020-10-27 | G | [35 empty] | 2020-12-17 | 2020-12-14 | 2020-12-23 | 2020-12-14 | G | 2020-12-24 | 2020-12-15 | 2020-12-31 | 2020-12-29 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | WORK/TASK ORDER | 1 | 0 | 0.062872
1469 | 16382 | RTE 58 - PARALLEL LN-CORRIDOR DEV (RHEA VALLEY) | 0058 | Primary | Reconstruction w/ Added Capacity | VDOT | Washington County | ABINGDON | Bristol | NonMPO:NonMPO | Infrastructure Investment Division | Dennis R Harris | Dennis.Harris@VDOT.Virginia.gov | (276) 696-3289 | Tamara D Pritchard | Tamara.Pritchard@VDOT.Virginia.gov | (276) 696-3249 |  |  |  | 0 |  | 0 | FY2021 | 7243000 | 54446338 | ACTIVITY DATES SET | R | Relocate Utilities milestone is 171 days past the expected completion date | R | Project estimate is between $5M and $10M and is a $1M or more over budget | [5 empty] | 1997-11-14 | 1997-11-14 | 1997-11-17 | 1997-11-17 | G | 1998-02-02 | 1998-02-02 | 1998-03-31 | 1998-03-31 | G | [5 empty] | 2000-02-18 | 2000-02-18 | 2000-03-16 | 2000-03-16 | G | 2000-10-19 | 2000-10-19 | 2000-10-23 | 2000-10-23 | G | 2001-12-04 | 2020-04-30 | 2020-09-03 |  | R | 2001-01-29 | 2001-01-29 | 2020-03-17 | 2020-11-24 | R | 2019-05-22 | 2019-05-22 | 2020-05-08 | 2020-12-03 | R | [5 empty] | 2020-09-10 |  | 2020-10-13 |  | R | 2020-12-17 |  | 2021-02-17 |  | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.12438
1470 | 113723 | Primary Extension Paving - Hampton Blvd/ Bolling Ave. | 0337 | Urban | Resurfacing | Locally | Norfolk | NORFOLK | Hampton Roads | Hampton Roads:Norfolk | Local Assistance Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Derrick Williams | Derrick.Williams@vdot.virginia.gov | (757) 956-3097 | Deborah Mangiaracina, P.E. | Deborah.Mangiaracina@norfolk.gov | (757) 664-7459 | 0 |  | 1 | FY2019 | 200502 | 200502 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 83 days early | G | Project is on budget | 2018-09-04 | 2018-09-04 | 2018-11-30 | 2019-01-07 | R | 2018-12-03 | 2019-01-08 | 2018-12-05 | 2019-01-16 | R | 2018-12-06 | 2018-07-10 | 2019-06-13 | 2019-01-16 | G | [25 empty] | 2018-05-11 | 2019-01-16 | 2019-01-16 | 2019-01-16 | G | [5 empty] | 2018-12-18 | 2018-12-18 | 2019-01-16 | 2019-01-16 | G | 2019-04-09 | 2019-01-16 | 2019-04-09 | 2019-01-16 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.082741
1471 | 114006 | UPGRADE EXISTING SIGNAL COLUMBIA PK AND LACY BLVD | 0244 | Primary | Safety | VDOT | Fairfax County | FAIRFAX | Northern Virginia | Northern Virginia:Fairfax County | Infrastructure Investment Division | Ivan M Horodyskyj | Ivan.Horodyskyj@VDOT.Virginia.gov | (703) 259-2330 | Anwar A Ansari | Anwar.Ansari@VDOT.Virginia.gov | (703) 334-0204 |  |  |  | 0 |  | 0 | FY2021 | 626226 | 578820 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 2 days early | G | Project is on budget | [5 empty] | 2019-02-01 | 2019-01-01 | 2019-02-14 | 2019-01-24 | G | 2019-02-15 | 2019-02-15 | 2020-01-13 | 2020-01-10 | G | [5 empty] | 2020-02-12 | 2020-02-12 | 2020-02-12 | 2020-02-12 | G | 2020-05-12 | 2020-04-20 | 2020-05-26 | 2020-05-20 | G | 2020-04-14 | 2020-04-14 | 2020-10-15 | 2020-04-14 | G | 2020-06-11 | 2020-06-30 | 2020-07-23 | 2021-01-04 | R | [10 empty] | 2020-11-10 | 2021-01-05 | 2020-11-10 | 2021-01-05 | R | 2021-01-06 | 2021-01-26 | 2021-01-28 | 2021-01-26 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | WORK/TASK ORDER | 1 | 0 | 0.051524
1472 | 114732 | PEDESTRIAN IMPROVEMENTS RRFB AT VARIOUS LOCATIONS - FAIRFAX | 9999 | Miscellaneous | Safety | VDOT | Fairfax County | FAIRFAX | Northern Virginia | Northern Virginia:Fairfax County | Infrastructure Investment Division | Andrew G Beacher | Andrew.Beacher@vdot.virginia.gov | (703) 259-2239 | Tienjung Ho | Tien-Jung.Ho@VDOT.Virginia.gov | (703) 259-2752 |  |  |  | 0 |  | 0 | FY2020 | 1263000 | 1263000 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 20 days early | G | Project is on budget | [5 empty] | 2019-02-01 | 2019-01-30 | 2019-02-19 | 2019-02-07 | G | 2019-02-20 | 2019-02-08 | 2019-08-08 | 2019-08-06 | G | [5 empty] | 2019-08-02 | 2019-08-02 | 2019-08-02 | 2019-08-02 | G | [25 empty] | 2019-09-24 | 2019-09-17 | 2019-09-30 | 2019-09-17 | G | 2019-10-01 | 2019-09-17 | 2019-10-07 | 2019-09-17 | G | Preliminary design and/or investigations are still underway | 2021-02-21 11:00 | 2021-02-21 06:04 | WORK/TASK ORDER | 1 | 0 | 0.062981
1473 | 115243 | #SMART20 N Armistead Ave Recon, Ped, & Drainage Improvemts. |  | Primary | Safety | Locally | Hampton | WILLIAMSBURG | Hampton Roads | Hampton Roads:Hampton | Infrastructure Investment Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Derrick Williams | Derrick.Williams@vdot.virginia.gov | (757) 956-3097 | Philippe Fenouil, P.E. | philippe.fenouil@hampton.gov | (757) 727-6197 | 1 | 2020 | 0 | FY2027 | 5298528 | 5298528 | NO DATES SET YET | G | Agreement with Locality milestone is 976 days ahead of the expected completion date | Y | Estimate not current | 2023-08-01 |  | 2023-10-25 |  | G | 2023-10-26 |  | 2023-11-08 |  | G | 2023-11-09 |  | 2024-10-25 |  | G | [10 empty] | 2025-10-29 |  | 2025-11-19 |  | G | [5 empty] | 2025-11-21 |  | 2026-10-06 |  | G | 2024-06-26 |  | 2025-03-05 |  | G | [5 empty] | 2026-10-23 |  | 2026-11-20 |  | G | 2027-02-17 |  | 2027-02-17 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.2011
1474 | 115410 | #SMART20 - Riverfront/Orleans BRT Station Ped Safety/Streets | 9999 | Urban | Facilities for Pedestrians and Bicycles | Locally | Richmond | ASHLAND | Richmond | Richmond:Richmond | Infrastructure Investment Division | Melinda G Baicy | Melinda.Baicy@vdot.virginia.gov | (804) 609-5390 | Melinda G Baicy | Melinda.Baicy@vdot.virginia.gov | (804) 609-5390 | Lamont Benjamin |  |  | 1 | 2020 | 0 | FY2027 | 2057000 | 2057000 | NO DATES SET YET | G | Agreement with Locality milestone is 1073 days ahead of the expected completion date | G | Project is on budget | 2023-10-30 |  | 2024-01-30 |  | G | 2024-01-31 |  | 2024-02-02 |  | G | 2024-02-05 |  | 2024-08-07 |  | G | [10 empty] | 2025-06-04 |  | 2025-06-24 |  | G | [5 empty] | 2025-06-26 |  | 2026-04-09 |  | G | 2024-09-13 |  | 2025-05-21 |  | G | [5 empty] | 2026-04-27 |  | 2026-05-22 |  | G | 2026-08-12 |  | 2026-08-12 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.13353
1475 | 116590 | DISTRICT-WIDE SYSTEMIC RUMBLE STRIPS (FY23 THRU FY25) | 9999 | Primary | Safety | VDOT | Stafford County | FREDERICKSBURG | Fredericksburg | Fredericksburg:Stafford County | Infrastructure Investment Division | Peter A Hedrich | Peter.Hedrich@vdot.virginia.gov | (540) 899-4540 | Jessica Graves | Jessica.Graves@vdot.virginia.gov | (540) 899-4267 |  |  |  | 0 |  | 0 | FY2023 | 2786702 | 2786702 | NO DATES SET YET | G | Start Development milestone is 604 days ahead of the expected completion date | G | Project is on budget | [5 empty] | 2022-10-18 |  | 2022-10-18 |  | G | 2022-10-19 |  | 2023-02-02 |  | G | [5 empty] | 2023-02-15 |  | 2023-03-01 |  | G | [25 empty] | 2023-03-17 |  | 2023-03-23 |  | G | 2023-03-24 |  | 2023-03-30 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | WORK/TASK ORDER | 0 | 0 | 0.05961
1476 | 116858 | BOSCAWEN STREET PEDESTRIAN MALL |  | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Winchester | EDINBURG | Staunton | Winchester:Winchester | Local Assistance Division | Kimberly Cameron | Kim.Cameron@vdot.virginia.gov | (540) 332-7886 | Kimberly Cameron | Kim.Cameron@vdot.virginia.gov | (540) 332-7886 | Perry Eisenach | perry.eisenach@winchesterva.gov | (540) 667-2085 | 0 |  | 0 | FY2025 | 2504100 | 2504100 | NO DATES SET YET | G | Agreement with Locality milestone is 107 days ahead of the expected completion date | G | Project is on budget | 2021-02-01 |  | 2021-06-08 |  | G | 2021-06-09 |  | 2021-06-29 |  | G | 2021-07-29 |  | 2021-11-22 |  | G | [25 empty] | 2023-12-28 |  | 2024-05-29 |  | G | [5 empty] | 2024-07-26 |  | 2024-08-22 |  | G | 2024-11-13 |  | 2024-11-13 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.38126
1477 | 117993 | W. Main Pedestrian Improvements North - Pulaski |  | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Pulaski | CHRISTIANSBURG | Salem | NonMPO:NonMPO | Local Assistance Division | Adam J Czesnowski | Adam.Czesnowski@vdot.virginia.gov | (540) 541-1216 | Adam J Czesnowski | Adam.Czesnowski@vdot.virginia.gov | (540) 541-1216 | Bill Pedigo | bpedigo@pulaskitown.org | (540) 994-8616 | 0 |  | 0 | FY2024 | 577851 | 577851 | NO DATES SET YET | G | Agreement with Locality milestone is 50 days ahead of the expected completion date | G | Project is on budget | 2020-12-01 |  | 2021-04-12 |  | G | 2021-04-13 |  | 2021-05-03 |  | G | 2021-11-08 |  | 2022-03-09 |  | G | [25 empty] | 2023-03-06 |  | 2023-08-01 |  | G | [5 empty] | 2023-09-28 |  | 2023-10-26 |  | G | 2024-01-23 |  | 2024-01-23 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.36347
1478 | 118260 | #SGR21LP - RTE 250 BYPASS WB SGR PAVING | 0250 | Primary | Resurfacing | VDOT | Charlottesville | CHARLOTTESVILLE | Culpeper | Charlottesville:Charlottesville | Infrastructure Investment Division | David S Pearce | David.Pearce@VDOT.Virginia.gov | (540) 829-7513 | Donald R Schoch | Donald.Schoch@vdot.virginia.gov | (540) 829-7500 |  |  |  | 0 |  | 1 | FY2021 | 242619 | 242619 | ADVERTISED | G | Solicit Bids milestone finished 56 days early | G | Project is on budget | [10 empty] | 2021-03-05 | 2021-01-22 | 2021-03-18 | 2021-01-22 | G | [35 empty] | 2021-03-09 | 2021-02-09 | 2021-04-06 | 2021-02-09 | G | 2021-06-24 |  | 2021-06-24 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.12669
1479 | 105288 | FAIRFAX COUNTY - SRTS - FLINT HILL ES - INTERSECTION IMP | 0000 | Secondary | Safety | Locally | Fairfax County | FAIRFAX | Northern Virginia | Northern Virginia:Fairfax County | Infrastructure Investment Division | Jeffrey S Daily | Jeff.Daily@VDOT.Virginia.gov | (703) 259-2993 | Rita Hockman | Rita.Hockman@vdot.virginia.gov | (804) 824-7421 | Alan Rashid | Alan.Rashid@fairfaxcounty.gov | (703) 324-5379 | 0 |  | 0 | FY2019 | 260000 | 233733 | WAITING FINANCIAL CLOSURE | R | Start Delivery milestone finished 35 days late | G | Project is on budget | [5 empty] | 2013-11-01 | 2013-11-01 | 2014-02-01 | 2013-11-20 | G | 2013-12-02 | 2013-12-01 | 2014-04-01 | 2014-04-01 | G | [35 empty] | 2018-04-02 | 2018-04-02 | 2018-06-01 | 2018-06-20 | R | 2018-06-01 | 2018-07-24 | 2018-10-01 | 2018-11-05 | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.13686
1480 | 105890 | SIGNAL SYSTEM |  | Urban | Safety | Locally | Richmond | ASHLAND | Richmond | Richmond:Richmond | Infrastructure Investment Division | Evan Austin | Evan.Austin@vdot.virginia.gov | (804) 609-5384 | Evan Austin | Evan.Austin@vdot.virginia.gov | (804) 609-5384 | Enrique Burgos | Enrique.Burgos@richmondgov.com | (804) 646-6337 | 0 |  | 0 | FY2021 | 6312350 | 7340000 | ADVERTISED | R | Start Delivery milestone is 205 days past the expected completion date | R | Project estimate is between $5M and $10M and is a $1M or more over budget | 2017-08-01 | 2018-01-04 | 2017-10-01 | 2018-02-12 | R | 2017-10-02 | 2018-02-23 | 2018-04-01 | 2018-03-13 | G | 2017-10-02 | 2017-08-01 | 2018-01-31 | 2018-11-06 | R | [5 empty] | 2018-09-14 | 2018-09-14 | 2019-05-15 | 2019-05-08 | G | [25 empty] | 2019-12-31 | 2020-02-11 | 2019-12-31 | 2020-02-11 | R | 2020-02-18 |  | 2020-07-31 |  | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.1393
1481 | 107141 | ROUTE 620 - RECONSTRUCTION | 0620 | Secondary | Reconstruction w/ Added Capacity | VDOT | Spotsylvania County | FREDERICKSBURG | Fredericksburg | Fredericksburg:Spotsylvania County | Local Assistance Division | Bryan J Bulluck | Bryan.Bulluck@VDOT.Virginia.gov | (540) 899-4277 | Bryan J Bulluck | Bryan.Bulluck@VDOT.Virginia.gov | (540) 899-4277 |  |  |  | 0 |  | 0 | FY2025 | 11200000 | 11200000 | ACTIVITY DATES SET | G | Engage Public milestone finished 5 days early | G | Project is on budget | [5 empty] | 2016-10-14 | 2016-10-14 | 2016-10-19 | 2016-10-19 | G | 2016-06-15 | 2016-06-15 | 2018-11-30 | 2018-11-30 | G | [5 empty] | 2019-12-05 | 2020-01-16 | 2020-01-21 | 2020-01-16 | G | 2021-05-06 |  | 2021-06-03 |  | G | 2022-12-30 |  | 2024-03-01 |  | G | 2021-06-21 |  | 2022-12-29 |  | G | 2020-07-29 | 2019-05-02 | 2022-12-27 | 2019-05-02 | G | [5 empty] | 2024-03-12 |  | 2024-03-12 |  | G | 2024-06-20 |  | 2024-08-22 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.15968
1482 | 107264 | Realignment of Colonial Avenue | 0000 | Urban | Reconstruction w/o Added Capacity | Locally | Suffolk | NORFOLK | Hampton Roads | Hampton Roads:Suffolk | Local Assistance Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Johndel A Alcaide | John.Alcaide@vdot.virginia.gov | (757) 956-3098 | Robert Lewis | relewis@suffolkva.us | (757) 514-7621 | 0 |  | 0 | FY2019 | 650000 | 740780 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 62 days early | Y | Project estimate is less than $5M and is up to 20% over budget | 2015-10-01 | 2015-08-14 | 2015-12-30 | 2015-08-14 | G | 2015-12-31 | 2015-08-17 | 2016-01-14 | 2015-08-20 | G | 2016-01-19 | 2015-08-21 | 2016-09-08 | 2016-08-02 | G | [10 empty] | 2018-01-01 | 2018-01-19 | 2018-02-06 | 2018-01-19 | G | [20 empty] | 2018-06-25 | 2018-06-25 | 2018-09-04 | 2018-09-06 | R | 2018-09-05 | 2018-09-07 | 2019-01-16 | 2018-11-15 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.091364
1483 | 108012 | Rte. 744 Grade Drain and Pave | 0744 | Secondary | New Construction Roadway | VDOT | Buchanan County | LEBANON | Bristol | NonMPO:NonMPO | Infrastructure Investment Division | Conrad Hill | Conrad.Hill@vdot.virginia.gov | (804) 773-0170 | Robert C Leonard | Robert.Leonard@VDOT.Virginia.gov | (276) 696-3258 |  |  |  | 0 |  | 0 | FY2019 | 4064912 | 4064912 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 9 days early | G | Project is on budget | [5 empty] | 2016-07-01 | 2016-09-02 | 2016-07-15 | 2016-09-27 | R | 2016-07-18 | 2016-09-20 | 2017-03-14 | 2017-05-30 | R | [5 empty] | 2017-10-26 | 2017-10-26 | 2018-01-10 | 2018-01-10 | G | [5 empty] | 2018-01-10 | 2018-04-06 | 2018-05-04 | 2018-05-10 | R | [15 empty] | 2018-06-12 | 2018-06-26 | 2018-06-12 | 2018-06-26 | R | 2018-08-02 | 2018-08-13 | 2018-08-22 | 2018-08-13 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.092785
1484 | 108760 | SIDEWALK - NEW CONSTRUCTION | 0000 | Urban | Other | Locally | Bluefield | LEBANON | Bristol | NonMPO:NonMPO | Local Assistance Division | Tabitha H Crowder | Tabitha.Crowder@vdot.virginia.gov | (276) 696-3482 | Tabitha H Crowder | Tabitha.Crowder@vdot.virginia.gov | (276) 696-3482 | Mike Watson |  |  | 0 |  | 0 | FY2019 | 80000 | 80000 | CONSTRUCTION COMPLETED | G | Solicit Bids milestone finished on-time | G | Project is on budget | 2016-06-14 | 2016-06-14 | 2016-08-10 | 2016-08-10 | G | 2018-05-14 | 2018-05-14 | 2018-05-14 | 2018-05-14 | G | 2016-09-13 | 2016-09-13 | 2018-11-19 | 2018-03-28 | G | [35 empty] | 2018-04-06 | 2018-04-06 | 2018-07-15 | 2018-07-15 | G | 2018-05-04 | 2018-05-04 | 2018-07-16 | 2018-05-04 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.085794
1485 | 110898 | Rt. 610/ASHLEIGH CHANNELIZE OFFSET RT TURN LANE - SPOTSY | 0610 | Secondary | Safety | VDOT | Spotsylvania County | FREDERICKSBURG | Fredericksburg | Fredericksburg:Spotsylvania County | Infrastructure Investment Division | Peter A Hedrich | Peter.Hedrich@vdot.virginia.gov | (540) 899-4540 | Ng Neuk Chin Ng-Sui-Hing | Doreen.Ng-Sui-Hing@vdot.virginia.gov | (540) 372-3596 |  |  |  | 0 |  | 0 | FY2022 | 855000 | 905000 | ACTIVITY DATES SET | G | Start Purchasing Right-of-Way milestone finished 132 days early | Y | Project estimate is less than $5M and is up to 20% over budget | [5 empty] | 2018-09-21 | 2018-06-18 | 2018-10-04 | 2018-06-21 | G | 2018-10-05 | 2018-08-24 | 2019-09-04 | 2019-08-28 | G | [5 empty] | 2020-03-12 | 2019-12-16 | 2020-03-25 | 2020-01-10 | G | 2020-12-10 | 2020-09-07 | 2021-01-26 | 2020-09-16 | G | 2021-08-10 |  | 2022-02-11 |  | G | 2021-02-11 | 2020-10-20 | 2021-08-09 |  | G | [10 empty] | 2022-03-08 |  | 2022-03-08 |  | G | 2022-04-27 |  | 2022-05-17 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.068628
1486 | 111003 | High Visibility Backplates on Existing Signal Heads |  | Urban | Safety | Locally | Virginia Beach | NORFOLK | Hampton Roads | Hampton Roads:Virginia Beach | Infrastructure Investment Division | Susan Wilson | Susan.Wilson@vdot.virginia.gov | (757) 956-3099 | Marci Thompson | Marci.Thompson@vdot.virginia.gov | (757) 956-3093 | Katie E Shannon, PE | kshannon@vbgov.com | (757) 385-4131 | 0 |  | 0 | FY2022 | 623703 | 623703 | ACTIVITY DATES SET | G | Determine Requirements milestone finished 7 days early | G | Project is on budget | 2019-07-01 | 2019-09-16 | 2019-09-24 | 2019-10-25 | R | 2019-09-25 | 2019-10-28 | 2019-10-08 | 2019-11-05 | R | 2019-10-09 | 2019-11-06 | 2020-10-08 | 2020-10-01 | G | [35 empty] | 2021-11-04 |  | 2021-12-20 |  | G | 2022-03-15 |  | 2022-06-07 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.1525
1487 | 111299 | #SGR18VB - RT 641 ??? REPLACE SD BRIDGE Fed 5280 | 0641 | Secondary | Facilities for Pedestrians and Bicycles | VDOT | Chesterfield County | CHESTERFIELD | Richmond | Richmond:Chesterfield County | Infrastructure Investment/Asset Management Division | Raymond Chapman | Scott.Chapman@vdot.virginia.gov | (804) 609-5277 | Raymond Chapman | Scott.Chapman@vdot.virginia.gov | (804) 609-5277 |  |  |  | 0 |  | 1 | FY2022 | 3500000 | 6000000 | ACTIVITY DATES SET | G | Determine Requirements milestone finished 1099 days early | R | Project estimate is less than $5M and is 20% or more over budget | [10 empty] | 2021-05-03 | 2018-04-25 | 2021-05-07 | 2018-05-04 | G | [35 empty] | 2021-08-10 |  | 2021-08-10 |  | G | 2021-10-29 |  | 2022-02-07 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.15844
1488 | 112317 | Elbow Road Phase 2C |  | Urban | New Construction Roadway | Locally | Virginia Beach | NORFOLK | Hampton Roads | Hampton Roads:Virginia Beach | Infrastructure Investment Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Marci Thompson | Marci.Thompson@vdot.virginia.gov | (757) 956-3093 | Katie Shannon, PE | kshannon@vbgov.com | (757) 385-1514 | 0 |  | 0 | FY2021 | 24834137 | 24834137 | NO DATES SET YET-PE OPEN | R | Determine Requirements milestone is 500 days past the expected completion date | G | Project is on budget | 2018-07-02 | 2018-05-24 | 2018-09-25 | 2018-09-05 | G | 2018-09-26 | 2018-09-06 | 2018-10-09 | 2019-01-10 | R | 2018-10-10 | 2019-01-11 | 2019-10-10 |  | R | [35 empty] | 2020-11-09 |  | 2020-12-23 |  | R | 2020-12-24 |  | 2021-06-17 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.23723
1489 | 113270 | COMMERCE STREET - STREETSCAPE | 9999 | Urban | Reconstruction w/o Added Capacity | Locally | Lynchburg | APPOMATTOX | Lynchburg | Lynchburg:Lynchburg | Local Assistance Division | Gregg Allen | Gregg.Allen@vdot.virginia.gov | (434) 426-5575 | Gregg Allen | Gregg.Allen@vdot.virginia.gov | (434) 426-5575 | Lee Newland, P.E. | lee.newland@lynchburgva.gov | (434) 455-3947 | 0 |  | 0 | FY2022 | 10459511 | 10459511 | NO DATES SET YET-PE OPEN | R | Determine Requirements milestone is 475 days past the expected completion date | G | Project is on budget | 2019-01-31 | 2019-07-01 | 2019-04-25 | 2019-08-09 | R | 2019-04-26 | 2019-08-12 | 2019-04-30 | 2019-08-21 | R | 2019-05-01 |  | 2019-11-04 |  | R | [10 empty] | 2020-08-28 |  | 2020-09-18 |  | R | [5 empty] | 2020-09-22 |  | 2021-07-06 |  | G | 2019-12-13 | 2020-11-05 | 2020-08-17 | 2020-11-05 | R | [5 empty] | 2021-07-22 |  | 2021-08-18 |  | G | 2021-11-08 |  | 2021-11-08 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.13257
1490 | 106562 | ITS INTEGRATION - PHASE IV | 9999 | Urban | Traffic Management/Engineering | Locally | Alexandria | FAIRFAX | Northern Virginia | Northern Virginia:Alexandria | Infrastructure Investment Division | Terry Yates | Terry.Yates@vdot.virginia.gov | (703) 259-2118 | Robert J Strevell | Robert.Strevell@vdot.virginia.gov | (703) 259-1988 | Daphne Kott | Daphne.kott@alexandriava.gov | (703) 838-4411 | 0 |  | 0 | FY2022 | 2235381 | 2235381 | NO DATES SET YET-PE OPEN | R | Determine Requirements milestone is 478 days past the expected completion date | G | Project is on budget | 2017-04-17 | 2017-04-17 | 2017-04-17 | 2017-04-17 | G | 2018-02-15 | 2018-02-15 | 2018-04-10 | 2018-04-10 | G | 2018-09-04 | 2018-09-04 | 2019-11-01 |  | R | [35 empty] | 2020-12-01 |  | 2021-06-30 |  | G | 2021-07-01 |  | 2021-11-30 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.32116
1491 | 107196 | ROADWAY DEPARTURE - CURVE COUNTERMEASURES - DISTRICTWIDE | 9999 | Miscellaneous | Safety | VDOT | Fredericksburg District-wide |  | Fredericksburg | Fredericksburg:Fredericksburg District-wide | Infrastructure Investment Division | Wesley Foor | Wesley.Foor@vdot.virginia.gov | (540) 604-1370 | Wesley Foor | Wesley.Foor@vdot.virginia.gov | (540) 604-1370 |  |  |  | 0 |  | 0 | FY2020 | 1500000 | 1500000 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 2 days early | G | Project is on budget | [5 empty] | 2018-10-19 | 2018-10-08 | 2018-11-01 | 2018-10-22 | G | 2018-11-02 | 2018-10-23 | 2018-12-04 | 2018-11-30 | G | [35 empty] | 2019-05-29 | 2019-05-07 | 2019-05-29 | 2019-05-07 | G | 2019-07-12 | 2019-07-30 | 2019-08-01 | 2019-07-30 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.07092
1492 | 107867 | RTE 5 (MAIN ST) - REPLACE BRIDGE | 0005 | Urban | Bridge Replacement w/o Added Capacity | VDOT | Richmond | ASHLAND | Richmond | Richmond:Richmond | Infrastructure Investment Division | George Fecek | Joe.Fecek@vdot.virginia.gov | (804) 609-5421 | George Fecek | Joe.Fecek@vdot.virginia.gov | (804) 609-5421 |  |  |  | 0 |  | 0 | FY2024 | 3000000 | 2996344 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 2755 days early | G | Project is on budget | 2015-08-18 | 2015-08-18 | 2015-12-15 | 2015-12-15 | G | 2015-08-03 | 2015-08-18 | 2015-08-14 | 2015-08-18 | R | 2015-08-17 | 2015-08-18 | 2016-07-14 | 2015-08-18 | G | [5 empty] | 2017-12-26 | 2016-08-05 | 2017-12-26 | 2016-08-05 | G | 2038-07-26 | 2016-08-05 | 2038-07-26 | 2016-08-05 | G | 2042-01-24 | 2016-07-05 | 2051-12-25 | 2016-08-05 | G | 2038-07-26 | 2016-08-05 | 2038-07-26 | 2016-08-05 | G | 2015-08-03 | 2015-08-03 | 2015-08-04 | 2015-08-03 | G | [5 empty] | 2016-09-13 | 2016-09-13 | 2016-09-13 | 2016-09-13 | G | 2024-05-15 | 2016-11-18 | 2024-06-04 | 2016-11-18 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.072314
1493 | 108514 | Pave Existing Shoulders and Install Rumble Strips & Signs. | 0460 | Primary | Safety | VDOT | Bedford County | BEDFORD | Salem | Roanoke:Bedford County | Infrastructure Investment Division | Bernard S Grinnell | Sean.Grinnell@VDOT.Virginia.gov | (540) 375-0148 | Anthony L Handy | Tony.Handy@VDOT.Virginia.gov | (540) 352-9050 |  |  |  | 0 |  | 0 | FY2021 | 1852843 | 1852843 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 163 days early | G | Project is on budget | [10 empty] | 2020-11-16 | 2018-03-14 | 2020-11-20 | 2019-03-14 | G | [25 empty] | 2018-08-08 | 2019-08-08 | 2018-08-22 | 2019-08-08 | R | [5 empty] | 2020-01-14 | 2020-01-07 | 2020-01-14 | 2020-01-07 | G | 2020-04-20 | 2020-03-30 | 2020-09-09 | 2020-03-30 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 1 | 0.32898
1494 | 110879 | #SMART18 - Gilley Ave. Shoulder Widening | 0058 | Urban | Reconstruction w/o Added Capacity | VDOT | Big Stone Gap | WISE | Bristol | NonMPO:NonMPO | Infrastructure Investment Division | Tamara D Pritchard | Tamara.Pritchard@VDOT.Virginia.gov | (276) 696-3249 | James M Bullins | James.Bullins@VDOT.Virginia.gov | (276) 696-3349 |  |  |  | 1 | 2018 | 0 | FY2024 | 3330000 | 3330000 | ACTIVITY DATES SET | Y | Engage Public milestone is 8 days ahead of the expected completion date and there is a risk of missing this milestone date | G | Project is on budget | [5 empty] | 2019-07-05 | 2019-07-05 | 2019-07-18 | 2019-07-18 | G | 2019-07-19 | 2019-07-19 | 2020-04-09 | 2020-04-09 | G | [5 empty] | 2021-02-15 |  | 2021-03-01 |  | Y | 2022-04-21 |  | 2022-05-04 |  | G | 2022-09-27 |  | 2023-04-07 |  | G | 2022-05-20 |  | 2023-05-25 |  | G | 2021-10-04 |  | 2022-04-14 |  | G | [5 empty] | 2023-08-08 |  | 2023-08-08 |  | G | 2023-10-30 |  | 2023-10-30 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.087599
1496 | 111020 | #SMART18 - IRONBOUND ROAD IMPROVEMENTS - PHASE 3 | 7081 | Urban | Reconstruction w/ Added Capacity | Locally | Williamsburg | WILLIAMSBURG | Hampton Roads | Hampton Roads:Williamsburg | Infrastructure Investment Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Chessica Villaflores | Chessica.Villaflores@vdot.virginia.gov | (757) 956-3094 | Aaron Small | ASmall@williamsburgva.gov | (757) 220-6140 | 1 | 2018 | 0 | FY2025 | 3312400 | 3312400 | NO DATES SET YET | G | Agreement with Locality milestone is 276 days ahead of the expected completion date | Y | Estimate not current | 2021-10-01 |  | 2021-11-24 |  | G | 2021-11-29 |  | 2021-12-01 |  | G | 2021-12-02 |  | 2022-06-09 |  | G | [10 empty] | 2023-06-13 |  | 2023-06-30 |  | G | [5 empty] | 2023-07-05 |  | 2024-05-16 |  | G | [10 empty] | 2024-06-04 |  | 2024-07-01 |  | G | 2024-07-02 |  | 2024-09-11 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.29992
1497 | 111657 | #SMART18 - TRAFFIC ADAPTIVE SIGNAL CONTROL FIBER OPTIC | 9999 | Urban | Traffic Management/Engineering | Locally | Alexandria | FAIRFAX | Northern Virginia | Northern Virginia:Alexandria | Infrastructure Investment Division | Amir Salahshoor | A.Salahshoor@VDOT.Virginia.gov | (703) 259-1957 | Susie X Lue | Susie.Lue@vdot.virginia.gov | (703) 259-2918 | Bob Garbacz | bob.garbacz@alexandriava.gov | (703) 746-4143 | 1 | 2018 | 0 | FY2027 | 7675900 | 7466591 | NO DATES SET YET | R | Agreement with Locality milestone is 516 days past the expected completion date | G | Project is on budget | 2019-07-01 |  | 2019-09-24 |  | R | 2019-09-25 |  | 2019-09-27 |  | R | 2019-09-30 |  | 2020-04-09 |  | R | 2024-07-12 |  | 2024-11-04 |  | G | [5 empty] | 2024-07-12 |  | 2024-08-01 |  | G | [5 empty] | 2024-08-05 |  | 2025-05-16 |  | G | 2025-03-18 |  | 2025-09-04 |  | G | [5 empty] | 2025-06-04 |  | 2025-11-05 |  | G | 2026-02-02 |  | 2026-07-08 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.3484
1498 | 112963 | North Cameron Street Drainage Improvements - Winchester | 0011 | Urban | Reconstruction w/o Added Capacity | Locally | Winchester | EDINBURG | Staunton | Winchester:Winchester | Local Assistance Division | Kimberly Cameron | Kim.Cameron@vdot.virginia.gov | (540) 332-7886 | Kimberly Cameron | Kim.Cameron@vdot.virginia.gov | (540) 332-7886 | Perry Eisenach | peisenach@ci.winchester.va.us | (540) 667-1815 | 0 |  | 0 | FY2022 | 7300000 | 12500000 | ACTIVITY DATES SET | G | Start Purchasing Right-of-Way milestone finished 208 days early | R | Project estimate is between $5M and $10M and is a $1M or more over budget | 2018-10-31 | 2018-10-31 | 2019-01-31 | 2019-03-14 | R | 2019-02-01 | 2019-06-05 | 2019-02-05 | 2019-06-11 | R | 2019-02-06 | 2019-06-12 | 2019-08-09 | 2019-10-10 | R | [10 empty] | 2020-08-06 | 2019-12-06 | 2020-08-26 | 2020-01-31 | G | [5 empty] | 2020-08-28 |  | 2021-06-11 |  | G | [10 empty] | 2021-06-29 |  | 2021-07-27 |  | G | 2021-10-14 |  | 2021-10-14 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.17635
1499 | 113446 | RTE 60 (SEMMES AVE)- PEDESTRIAN IMPRV. PH I | 0060 | Primary | Facilities for Pedestrians and Bicycles | Locally | Richmond | ASHLAND | Richmond | Richmond:Richmond | Local Assistance Division | Jorg Huckabee-Mayfield | Jorg.Huckabee-Mayfield@VDOT.Virginia.gov | (804) 609-5292 | Jorg Huckabee-Mayfield | Jorg.Huckabee-Mayfield@VDOT.Virginia.gov | (804) 609-5292 | Jian Xu | Jian.Xu@Richmondgov.com | (804) 646-5402 | 0 |  | 0 | FY2023 | 300000 | 300000 | NO DATES SET YET-PE OPEN | Y | Determine Requirements milestone is 18 days ahead of the expected completion date and there is a risk of missing this milestone date | G | Project is on budget | 2019-10-02 | 2019-10-02 | 2020-02-14 | 2019-10-23 | G | 2020-02-25 | 2019-09-11 | 2020-03-09 | 2019-09-11 | G | 2020-08-28 |  | 2021-03-11 |  | Y | [25 empty] | 2020-11-09 |  | 2021-07-16 |  | G | [5 empty] | 2022-03-30 |  | 2022-04-26 |  | G | 2022-10-10 |  | 2022-10-10 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.2142
1500 | 113467 | Mercury Blvd Rd Diet - Segment I | 0258 | Urban | Facilities for Pedestrians and Bicycles | Locally | Hampton | WILLIAMSBURG | Hampton Roads | Hampton Roads:Hampton | Local Assistance Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Derrick Williams | Derrick.Williams@vdot.virginia.gov | (757) 956-3097 | Sandon Rogers, P.E. | sandon.rogers@hampton.gov | (757) 727-6786 | 0 |  | 0 | FY2023 | 358000 | 358000 | ACTIVITY DATES SET | G | Engage Public milestone finished 20 days early | G | Project is on budget | 2018-11-06 | 2018-11-06 | 2019-02-06 | 2019-06-20 | R | 2019-02-07 | 2019-06-21 | 2019-02-11 | 2019-06-25 | R | 2019-02-12 | 2019-06-26 | 2019-08-15 | 2020-06-26 | R | 2020-06-29 | 2020-06-29 | 2020-08-10 | 2020-07-21 | G | [5 empty] | 2021-04-23 |  | 2021-05-13 |  | G | [5 empty] | 2021-05-17 |  | 2022-03-01 |  | G | [10 empty] | 2022-03-17 |  | 2022-04-27 |  | G | 2022-07-18 |  | 2023-01-10 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.14801
1501 | 113534 | Clara Byrd Baker SRTS Infrastructure | 0615 | Enhancement | Facilities for Pedestrians and Bicycles | Locally | James City County | WILLIAMSBURG | Hampton Roads | Hampton Roads:James City County | Local Assistance Division | Dawn Odom | Dawn.Odom@vdot.virginia.gov | (000) 000-0000 | Keisha Wilkins | Keisha.Wilkins@vdot.virginia.gov | (757) 956-3110 | Roberta Sulouff | Roberta.Sulouff@jamescitycountyva.gov | (757) 253-6783 | 0 |  | 0 | FY2023 | 490470 | 480113 | ACTIVITY DATES SET | G | Obtained Permits milestone finished 371 days early | G | Project is on budget | 2019-02-15 | 2019-02-15 | 2019-05-10 | 2019-04-04 | G | 2019-05-13 | 2019-05-13 | 2019-05-15 | 2019-05-24 | R | 2019-05-16 | 2019-05-28 | 2019-11-20 | 2020-05-27 | R | [10 empty] | 2020-11-18 | 2020-08-18 | 2020-12-24 | 2020-09-14 | G | [5 empty] | 2020-12-30 |  | 2021-11-29 |  | G | 2021-06-01 | 2021-02-01 | 2022-02-07 | 2021-02-01 | G | [5 empty] | 2022-03-23 |  | 2022-05-03 |  | G | 2022-07-22 |  | 2022-10-14 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.38457
1502 | 114000 | SYSTEMIC LANE DEPARTURE IMPROVEMENTS - DISTRICTWIDE | 9999 | Miscellaneous | Safety | VDOT | Richmond District-wide |  | Richmond | Richmond:Richmond District-wide | Infrastructure Investment Division | Adam S Brooks | Adam.Brooks@VDOT.Virginia.gov | (804) 609-5274 | Adam S Brooks | Adam.Brooks@VDOT.Virginia.gov | (804) 609-5274 |  |  |  | 0 |  | 0 | FY2025 | 1621853 | 1621853 | NO DATES SET YET | G | Start Development milestone is 661 days ahead of the expected completion date | G | Project is on budget | [5 empty] | 2022-12-01 |  | 2022-12-14 |  | G | 2022-12-15 |  | 2023-08-08 |  | G | [5 empty] | 2024-04-17 |  | 2024-05-29 |  | G | [5 empty] | 2024-09-12 |  | 2025-01-09 |  | G | [5 empty] | 2024-08-27 |  | 2024-12-02 |  | G | [5 empty] | 2025-01-14 |  | 2025-01-14 |  | G | 2025-04-08 |  | 2025-04-08 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.068387
1503 | 115137 | #SMART20 North Augusta Sidewalk |  | Urban | Facilities for Pedestrians and Bicycles | Locally | Staunton | HARRISONBURG | Staunton | SAW:Staunton | Infrastructure Investment Division | Randolph S Kiser | Randy.Kiser@VDOT.Virginia.gov | (540) 332-9092 | Michael S Fulcher | Michael.Fulcher@VDOT.Virginia.gov | (540) 332-2243 | Staunton City | millsnd@ci.staunton.va.us | (540) 332-3858 | 1 | 2020 | 0 | FY2027 | 1477371 | 1477371 | NO DATES SET YET | G | Agreement with Locality milestone is 976 days ahead of the expected completion date | G | Project is on budget | 2023-08-01 |  | 2023-10-25 |  | G | 2023-10-26 |  | 2023-10-30 |  | G | 2023-10-31 |  | 2024-05-09 |  | G | [10 empty] | 2025-05-09 |  | 2025-05-30 |  | G | [5 empty] | 2025-06-03 |  | 2026-03-17 |  | G | 2024-06-17 |  | 2025-02-24 |  | G | [5 empty] | 2026-04-02 |  | 2026-04-29 |  | G | 2026-07-20 |  | 2026-07-20 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.11039
1504 | 115460 | #SMART20 - Rte 419 & Rte 220 Diverging Diamond Interchange | 0419 | Primary | Other | VDOT | Roanoke County | SALEM | Salem | Roanoke:Roanoke County | Infrastructure Investment Division | Alex H Price | Alex.Price@VDOT.Virginia.gov | (540) 378-5053 | Jesse N Weitzenfeld | Jesse.Weitzenfeld@VDOT.Virginia.gov | (540) 378-5050 |  |  |  | 1 | 2020 | 0 | FY2024 | 17505000 | 17505000 | ACTIVITY DATES SET | G | Determine Requirements milestone finished on-time | G | Project is on budget | [5 empty] | 2019-09-17 | 2019-08-26 | 2019-09-30 | 2019-09-05 | G | 2019-10-01 | 2019-09-06 | 2020-10-08 | 2020-10-08 | G | [5 empty] | 2021-10-07 |  | 2021-10-21 |  | G | 2023-01-18 |  | 2023-01-31 |  | G | 2023-06-26 |  | 2024-01-03 |  | G | 2023-02-16 |  | 2023-08-21 |  | G | 2023-04-27 |  | 2024-01-02 |  | G | [5 empty] | 2024-02-13 |  | 2024-02-13 |  | G | 2024-06-03 |  | 2024-06-26 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.15958
1505 | 116726 | #I95 CIP - INSTALL ITS DEVICES, NORTHERN REGION | 0095 | Interstate | Safety | VDOT | Richmond District-wide |  | Richmond | Richmond:Richmond District-wide | Infrastructure Investment/Asset Management Division | Adam S Brooks | Adam.Brooks@VDOT.Virginia.gov | (804) 609-5274 | Adam S Brooks | Adam.Brooks@VDOT.Virginia.gov | (804) 609-5274 | N\A | nogov@virginia.gov |  | 0 |  | 0 | FY2021 | 5778143 | 5778143 | NO DATES SET YET-PE OPEN | G | Start Development milestone finished 126 days early | G | Project is on budget | [5 empty] | 2021-01-04 | 2020-09-01 | 2021-01-26 | 2020-09-22 | G | 2021-01-27 |  | 2021-05-05 |  | G | [5 empty] | 2021-05-18 |  | 2021-06-01 |  | G | [25 empty] | 2021-06-17 |  | 2021-06-23 |  | G | 2021-06-24 |  | 2021-06-30 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | WORK/TASK ORDER | 0 | 0 | 0.067954
1506 | 118133 | STAUNTON DISTRICT - FLASHING YELLOW ARROW SSI | 9999 | Primary | Safety | VDOT | Staunton District-wide |  | Staunton | NonMPO:NonMPO | Infrastructure Investment Division | Keith M Rider | Keith.Rider@VDOT.Virginia.gov | (434) 856-8145 | Kunal Kothawade | Kunal.Kothawade@vdot.virginia.gov | (540) 332-9259 |  |  |  | 0 |  | 0 | FY2021 | 310000 | 310000 | ACTIVITY DATES SET | G | Start Development milestone finished 21 days early | G | Project is on budget | [5 empty] | 2020-11-02 | 2020-11-02 | 2020-11-23 | 2020-11-02 | G | 2020-11-24 | 2020-09-30 | 2021-03-10 | 2020-09-30 | G | [5 empty] | 2021-03-23 |  | 2021-04-05 |  | G | [25 empty] | 2021-04-21 |  | 2021-04-27 |  | G | 2021-04-28 |  | 2021-05-04 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | WORK/TASK ORDER | 0 | 0 | 0.067672
1507 | 91228 | 1/2 mi. paved bicycle/pedestrian trail at Woods of Warrenton | 1283 | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Fauquier County | WARRENTON | Culpeper | Northern Virginia:Fauquier | Local Assistance Division | John P Price | John.Price@VDOT.Virginia.gov | (540) 347-6371 | John P Price | John.Price@VDOT.Virginia.gov | (540) 347-6371 | Gary Rzepecki | Gary.Rzepecki@fauquiercounty.gov | (540) 422-8557 | 0 |  | 0 | FY2019 | 650038 | 1254454 | CONSTRUCTION STARTED | R | Start Delivery milestone finished 372 days late | R | Project estimate is less than $5M and is 20% or more over budget | [5 empty] | 2009-01-01 | 2010-02-18 | 2009-01-01 | 2010-02-18 | R | 2015-04-30 | 2011-01-31 | 2015-08-30 | 2015-08-30 | G | [35 empty] | 2015-09-25 | 2015-09-25 | 2015-09-25 | 2015-09-25 | G | 2015-09-30 | 2019-09-03 | 2018-10-01 | 2019-10-08 | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.36331
1508 | 104078 | Commonwealth Blvd Bridge Repairs | 0457 | Urban | Bridge Rehab w/o Added Capacity | Locally | Martinsville | MARTINSVILLE | Salem | NonMPO:NonMPO | Infrastructure Investment Division | Jessie Nester | Jessie.Nester@vdot.virginia.gov | (540) 613-4115 | Jessie Nester | Jessie.Nester@vdot.virginia.gov | (540) 613-4115 | Leon Towarnicki | ltowarnicki@ci.martinsville.va.us | (276) 403-5185 | 0 |  | 0 | FY2020 | 2389612 | 2575599 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 70 days early | Y | Project estimate is less than $5M and is up to 20% over budget | [5 empty] | 2014-07-01 | 2016-11-04 | 2016-06-30 | 2016-11-08 | R | 2017-10-02 | 2017-11-08 | 2018-06-01 | 2018-05-09 | G | [35 empty] | 2019-02-08 | 2019-04-04 | 2019-03-01 | 2019-05-24 | R | 2019-03-04 | 2019-06-25 | 2019-09-03 | 2019-06-25 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.18884
1509 | 105778 | Wormley Ck Culvert Imp.(along Cannon) | 1227 | Urban | Other | Locally | York County | WILLIAMSBURG | Hampton Roads | Hampton Roads:York County | Local Assistance Division | Christopher R Carroll | C.Carroll@VDOT.Virginia.gov | (757) 253-5140 | Chessica Villaflores | Chessica.Villaflores@vdot.virginia.gov | (757) 956-3094 | Anna Drake | Anna.Drake@yorkcounty.gov | (757) 890-3890 | 0 |  | 0 | FY2019 | 800000 | 800000 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 5 days early | G | Project is on budget | [5 empty] | 2014-08-01 | 2014-07-03 | 2014-08-01 | 2014-08-07 | R | 2014-12-01 | 2014-10-15 | 2019-02-27 | 2018-11-08 | G | [10 empty] | 2015-02-01 | 2015-02-01 | 2015-02-22 | 2015-02-22 | G | [20 empty] | 2018-11-09 | 2018-11-09 | 2019-03-06 | 2018-11-09 | G | 2019-03-06 | 2018-03-06 | 2019-03-11 | 2019-03-06 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.14389
1510 | 113512 | (FKEY 218) BUS 29 - RESURFACING (MEMORIAL DRIVE) | 7029 | Urban | Resurfacing | Locally | Danville | HALIFAX | Lynchburg | Danville:Danville | Local Assistance Division | Sharon S White | Sharon.White@VDOT.Virginia.gov | (434) 856-8220 | Bhavesh Shah | Bhavesh.Shah@vdot.virginia.gov | (804) 524-6149 | Brian Dunevant | dunebl@danville.gov | (434) 799-5019 | 0 |  | 0 | FY2019 | 292000 | 292000 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 17 days early | G | Project is on budget | 2019-01-31 | 2018-09-04 | 2019-04-25 | 2018-09-04 | G | [5 empty] | 2019-01-31 | 2018-09-04 | 2019-02-13 | 2018-09-17 | G | [25 empty] | 2018-10-02 | 2018-09-18 | 2018-12-31 | 2018-12-31 | G | [5 empty] | 2018-10-02 | 2018-10-02 | 2018-10-30 | 2018-10-30 | G | 2019-01-25 | 2019-01-08 | 2019-01-25 | 2019-01-08 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.05024
1511 | 113574 | #SGR19LP - RECONSTRUCTION - 311 LAFAYETTE BLVD | 0001 | Urban | Reconstruction w/o Added Capacity | Locally | Fredericksburg | FREDERICKSBURG | Fredericksburg | NonMPO:NonMPO | Infrastructure Investment Division | Richard A Spurlock | Richard.Spurlock@VDOT.Virginia.gov | (540) 899-4302 | Richard A Spurlock | Richard.Spurlock@VDOT.Virginia.gov | (540) 899-4302 | Erik Nelson | enelson@fredericksburgva.gov | (540) 372-1080 | 0 |  | 1 | FY2019 | 483444 | 483444 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 60 days early | G | Project is on budget | 2019-01-10 | 2018-07-30 | 2019-04-08 | 2018-10-23 | G | [5 empty] | 2019-01-10 | 2019-01-10 | 2019-01-25 | 2019-01-25 | G | [25 empty] | 2019-01-28 | 2019-01-28 | 2019-04-22 | 2019-01-28 | G | [5 empty] | 2019-04-23 | 2019-01-07 | 2019-05-20 | 2019-01-07 | G | 2019-05-21 | 2019-03-12 | 2019-05-21 | 2019-03-22 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.0796
1512 | 115124 | #SMART20 ROUTE 3 STARS STUDY AND I-95 OFF-RAMP IMPROVEMENTS | 0003 | Primary | Reconstruction w/o Added Capacity | VDOT | Fredericksburg | FREDERICKSBURG | Fredericksburg | Fredericksburg:Fredericksburg | Infrastructure Investment Division | Catherine C Coffey | Catherine.Coffey@vdot.virginia.gov | (540) 899-4280 | Curtis B Holloway | Curtis.Holloway@vdot.virginia.gov | (540) 374-3367 |  |  |  | 1 | 2020 | 0 | FY2028 | 11500000 | 11500000 | NO DATES SET YET | G | Start Development milestone is 918 days ahead of the expected completion date | G | Project is on budget | [5 empty] | 2023-08-15 |  | 2023-08-28 |  | G | 2023-08-29 |  | 2024-07-26 |  | G | [5 empty] | 2025-06-03 |  | 2025-06-16 |  | G | 2026-09-21 |  | 2026-10-02 |  | G | 2027-03-05 |  | 2027-09-07 |  | G | 2026-10-21 |  | 2027-04-30 |  | G | 2026-03-12 |  | 2026-09-14 |  | G | [5 empty] | 2027-09-14 |  | 2027-09-14 |  | G | 2027-12-08 |  | 2027-12-08 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.12266
1513 | 115345 | #I81CIP EXTEND SB DECELERATION LANE MM 26.7 TO 26.8 (ID #22) | 0081 | Interstate | Safety | VDOT | Washington County | ABINGDON | Bristol | NonMPO:NonMPO | Infrastructure Investment Division | Tamara D Pritchard | Tamara.Pritchard@VDOT.Virginia.gov | (276) 696-3249 | Brandi Halloway | Brandi.Halloway@vdot.virginia.gov | (276) 696-3254 |  |  |  | 0 |  | 0 | FY2020 | 640000 | 390290 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 7 days early | G | Project is on budget | [5 empty] | 2019-08-02 | 2019-08-02 | 2019-08-08 | 2019-08-08 | G | 2019-08-09 | 2019-08-08 | 2019-09-06 | 2019-09-04 | G | [5 empty] | 2019-09-11 | 2019-09-11 | 2019-09-11 | 2019-09-11 | G | [5 empty] | 2019-08-12 | 2019-08-12 | 2019-08-12 | 2019-08-12 | G | [15 empty] | 2019-12-10 | 2019-12-10 | 2019-12-10 | 2019-12-10 | G | 2020-03-05 | 2020-02-27 | 2020-03-05 | 2020-02-27 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.078301
1514 | 115516 | Battlefield Blvd/Volvo Parkway Intersection Improvements | 0000 | Urban | Reconstruction w/ Added Capacity | Locally | Chesapeake | NORFOLK | Hampton Roads | Hampton Roads:Chesapeake | Infrastructure Investment Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Johndel A Alcaide | John.Alcaide@vdot.virginia.gov | (757) 956-3098 | Troy Eisenberger, PE | teisenberger@cityofchesapeake.net | (757) 382-6383 | 0 |  | 0 | FY2028 | 827500 | 827500 | NO DATES SET YET | G | Agreement with Locality milestone is 1408 days ahead of the expected completion date | Y | Estimate not current | 2024-10-01 |  | 2024-12-30 |  | G | 2024-12-31 |  | 2025-01-03 |  | G | 2025-01-06 |  | 2025-07-11 |  | G | [10 empty] | 2026-07-15 |  | 2026-08-04 |  | G | [5 empty] | 2026-08-06 |  | 2027-05-19 |  | G | 2025-08-18 |  | 2026-04-24 |  | G | [5 empty] | 2027-06-07 |  | 2027-07-02 |  | G | 2027-09-22 |  | 2027-09-22 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.24508
1515 | 116852 | MIDDLE ROAD SIDEWALKS AND BIKE LANES |  | Miscellaneous | Facilities for Pedestrians and Bicycles | Locally | Winchester | EDINBURG | Staunton | Winchester:Winchester | Local Assistance Division | Kimberly Cameron | Kim.Cameron@vdot.virginia.gov | (540) 332-7886 | Kimberly Cameron | Kim.Cameron@vdot.virginia.gov | (540) 332-7886 | Perry Eisenach | perry.eisenach@winchesterva.gov | (540) 667-1815 | 0 |  | 0 | FY2025 | 4020045 | 4020045 | NO DATES SET YET | G | Agreement with Locality milestone is 107 days ahead of the expected completion date | G | Project is on budget | 2021-02-01 |  | 2021-06-08 |  | G | 2021-06-09 |  | 2021-06-29 |  | G | 2022-01-10 |  | 2022-05-04 |  | G | [25 empty] | 2024-01-02 |  | 2024-05-31 |  | G | [5 empty] | 2024-07-30 |  | 2024-08-26 |  | G | 2024-11-15 |  | 2024-11-15 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.17829
1516 | 118308 | DUMFRIES ROAD SIDEWALK INFILL | 0234 | Urban | Facilities for Pedestrians and Bicycles | Locally | Manassas | MANASSAS | Northern Virginia | Northern Virginia:Manassas | Local Assistance Division | Angel Tao | Angel.Tao@vdot.virginia.gov | (703) 259-2377 | Marlene Pinedo Fortich | Sofia.Pinedo@vdot.virginia.gov | (703) 259-1724 | Chloe Delhomme | cedelhomme@manassasva.gov | (703) 257-8235 | 0 |  | 0 | FY2029 | 506858 | 506858 | NO DATES SET YET | G | Agreement with Locality milestone is 1433 days ahead of the expected completion date | G | Project is on budget | 2024-07-01 |  | 2025-01-24 |  | G | 2025-01-27 |  | 2025-02-14 |  | G | 2025-08-21 |  | 2026-02-18 |  | G | [10 empty] | 2027-06-08 |  | 2027-07-13 |  | G | [5 empty] | 2027-07-14 |  | 2028-01-06 |  | G | 2028-03-01 |  | 2028-07-27 |  | G | [5 empty] | 2028-04-12 |  | 2028-06-07 |  | G | 2028-08-25 |  | 2028-10-23 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.13182
1517 | 94724 | RTE. 122 OVER BLACKWATER RIVER (STR. 07771) - BRIDGE REPLACE | 0122 | Primary | Bridge Replacement w/o Added Capacity | VDOT | Franklin County | BEDFORD | Salem | NonMPO:NonMPO | Infrastructure Investment Division | Anthony T Marshall | Todd.Marshall@VDOT.Virginia.gov | (540) 387-5460 | Anthony L Handy | Tony.Handy@VDOT.Virginia.gov | (540) 352-9050 |  |  |  | 0 |  | 0 | FY2019 | 7076130 | 7776060 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 21 days early | Y | Project estimate is between $5M and $10M and is up to $1M over budget | [5 empty] | 2011-02-01 | 2011-02-01 | 2011-02-01 | 2011-02-01 | G | 2014-12-22 | 2014-12-22 | 2015-10-09 | 2015-10-09 | G | 2015-08-13 | 2015-08-13 | 2015-11-02 | 2015-11-02 | G | [5 empty] | 2017-02-27 | 2017-02-27 | 2017-03-14 | 2017-03-14 | G | 2017-08-07 | 2017-08-07 | 2018-01-10 | 2018-01-10 | G | 2017-04-27 | 2017-04-27 | 2018-04-16 | 2018-04-16 | G | 2017-06-20 | 2017-06-20 | 2018-08-13 | 2018-06-19 | G | [5 empty] | 2018-07-13 | 2018-08-14 | 2018-08-14 | 2018-08-14 | G | 2018-08-23 | 2018-12-05 | 2018-12-26 | 2018-12-05 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.1252
1518 | 105722 | #SMART20 - ROUTE 1/ENON ROAD INTERSECTION AND ROADWAY IMP | 0753 | Secondary | Reconstruction w/o Added Capacity | Locally | Stafford County | FREDERICKSBURG | Fredericksburg | Fredericksburg:Stafford County | Local Assistance Division | Khalil Minhas | Khalil.Minhas@vdot.virginia.gov | (540) 374-3369 | Khalil Minhas | Khalil.Minhas@vdot.virginia.gov | (540) 374-3369 | Alex E. Owsiak | AOwsiak@staffordcountyva.gov | (540) 658-4593 | 1 | 2020 | 0 | FY2026 | 10600000 | 10600000 | NO DATES SET YET | G | Agreement with Locality milestone is 247 days ahead of the expected completion date | G | Project is on budget | 2021-08-02 |  | 2021-10-26 |  | G | 2021-10-27 |  | 2021-12-10 |  | G | 2021-12-13 |  | 2022-10-27 |  | G | [10 empty] | 2023-11-09 |  | 2023-12-26 |  | G | [5 empty] | 2023-12-28 |  | 2025-09-02 |  | G | 2023-06-15 |  | 2024-11-06 |  | G | [5 empty] | 2025-10-16 |  | 2025-11-14 |  | G | 2026-02-10 |  | 2026-06-03 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.1648
1519 | 107414 | ROARING SPRINGS ROAD (SR 616) - BIKE/PED IMPROVEMENTS | 0616 | Secondary | Facilities for Pedestrians and Bicycles | VDOT | Gloucester County | SALUDA | Fredericksburg | Hampton Roads:Gloucester County | Infrastructure Investment Division | Catherine C Coffey | Catherine.Coffey@vdot.virginia.gov | (540) 899-4280 | Anastasia Kapitan | Anastasia.Kapitan@vdot.virginia.gov | (540) 899-4292 | Anne Ducey-Ortiz | aducey@gloucesterva.info | (804) 693-1224 | 0 |  | 0 | FY2027 | 2990000 | 2990000 | NO DATES SET YET | G | Start Development milestone is 523 days ahead of the expected completion date | G | Project is on budget | [5 empty] | 2022-07-18 |  | 2022-07-29 |  | G | 2022-08-01 |  | 2023-06-28 |  | G | [5 empty] | 2024-05-03 |  | 2024-05-16 |  | G | 2025-08-21 |  | 2025-09-04 |  | G | 2026-02-04 |  | 2026-08-07 |  | G | 2025-09-22 |  | 2026-04-02 |  | G | 2025-02-11 |  | 2025-08-14 |  | G | [5 empty] | 2026-08-11 |  | 2026-08-11 |  | G | 2026-10-01 |  | 2026-10-22 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.1053
1520 | 107795 | #HB2.FY17 RTE 95 - IMPROVE RAMP AREA AT FRANKLIN ST | 0095 | Interstate | Reconstruction w/o Added Capacity | VDOT | Richmond | ASHLAND | Richmond | Richmond:Richmond | Infrastructure Investment Division | Lawrence Ramsey | Brian.Ramsey@VDOT.Virginia.gov | (804) 585-3579 | Lawrence Ramsey | Brian.Ramsey@VDOT.Virginia.gov | (804) 585-3579 |  |  |  | 1 | 2017 | 0 | FY2019 | 3148000 | 2319992 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 80 days early | G | Project is on budget | [5 empty] | 2015-09-01 | 2015-07-01 | 2015-09-01 | 2015-07-27 | G | 2015-09-01 | 2015-08-18 | 2016-10-03 | 2016-11-22 | R | [5 empty] | 2017-03-20 | 2017-03-20 | 2017-03-28 | 2017-03-28 | G | 2017-09-19 | 2017-09-19 | 2017-09-24 | 2017-09-24 | G | 2017-11-14 | 2017-11-14 | 2017-11-14 | 2017-11-14 | G | 2017-11-03 | 2017-11-03 | 2018-05-15 | 2018-06-05 | R | [10 empty] | 2018-09-11 | 2018-07-10 | 2018-09-11 | 2018-07-10 | G | 2018-11-01 | 2018-09-07 | 2018-11-26 | 2018-09-07 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.081965
1521 | 109084 | SHORT PUMP PARK TRAILS |  | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Henrico County | ASHLAND | Richmond | Richmond:Henrico County | Local Assistance Division | Brian J Lokker | Brian.Lokker@VDOT.Virginia.gov | (804) 524-6010 | Brian J Lokker | Brian.Lokker@VDOT.Virginia.gov | (804) 524-6010 | Michael Aust | AUS019@henrico.us | (804) 501-4019 | 0 |  | 0 | FY2020 | 314215 | 314215 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 1 days early | G | Project is on budget | 2016-10-28 | 2016-10-28 | 2016-12-06 | 2016-12-06 | G | 2017-02-16 | 2017-02-16 | 2017-02-21 | 2017-02-21 | G | 2017-02-22 | 2017-02-22 | 2018-07-16 | 2018-07-12 | G | [35 empty] | 2019-05-30 | 2019-09-04 | 2019-07-15 | 2019-10-18 | R | 2019-07-16 | 2019-10-22 | 2020-01-15 | 2020-01-14 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.43005
1522 | 109509 | Piedmont Avenue Pedestrian Heads | 3305 | Urban | Safety | Locally | Bristol | ABINGDON | Bristol | Bristol:Bristol | Infrastructure Investment Division | Tabitha H Crowder | Tabitha.Crowder@vdot.virginia.gov | (276) 696-3482 | Kenneth R Plummer | KR.Plummer@VDOT.Virginia.gov | (276) 696-3261 | Wallace McCulloch | wallace.mcculloch@bristolva.org | (276) 642-2316 | 0 |  | 0 | FY2020 | 77000 | 158108 | ACTIVITY DATES SET | R | Solicit Bids milestone is 587 days past the expected completion date | R | Project estimate is less than $5M and is 20% or more over budget | 2016-08-01 | 2016-08-01 | 2017-04-07 | 2017-04-07 | G | 2016-09-21 | 2016-09-21 | 2016-09-28 | 2016-09-28 | G | 2016-09-29 | 2016-09-26 | 2018-07-23 | 2018-07-18 | G | [35 empty] | 2019-04-19 | 2020-10-20 | 2019-07-15 |  | R | 2019-07-16 |  | 2019-08-23 |  | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.098428
1524 | 111689 | #SGR18VB - PIGGOTT BOTTOM RD OVER CATOCTIN CR - Fed 11305 | 0711 | Secondary | Bridge Replacement w/o Added Capacity | VDOT | Loudoun County | LEESBURG | Northern Virginia | Northern Virginia:Loudoun County | Infrastructure Investment/Asset Management Division | Gary Runco | Gary.Runco@vdot.virginia.gov | (703) 259-3341 | Dipali Patel | Dipali.Patel@vdot.virginia.gov | (703) 259-2429 |  |  |  | 0 |  | 1 | FY2023 | 2147834 | 2147834 | NO DATES SET YET | R | Start Development milestone is 159 days past the expected completion date | G | Project is on budget | [5 empty] | 2020-09-01 | 2019-08-27 | 2020-09-15 |  | R | 2020-09-16 | 2019-09-02 | 2021-05-12 |  | G | [5 empty] | 2021-08-24 |  | 2021-10-05 |  | G | [15 empty] | 2022-03-28 |  | 2022-06-27 |  | G | [5 empty] | 2022-09-13 |  | 2022-09-13 |  | G | 2022-12-20 |  | 2023-02-17 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.10435
1526 | 113507 | SRTS - GREER/JOUETT BICYCLE AND PEDESTRIAN IMPROVEMENTS | 9885 | Secondary | Facilities for Pedestrians and Bicycles | Locally | Albemarle County | CHARLOTTESVILLE | Culpeper | NonMPO:NonMPO | Local Assistance Division | John P Price | John.Price@VDOT.Virginia.gov | (540) 347-6371 | John P Price | John.Price@VDOT.Virginia.gov | (540) 347-6371 | JACK KESLEY | jkelsey2@albemarle.org |  | 0 |  | 0 | FY2021 | 710000 | 710000 | ADVERTISED | G | Solicit Bids milestone finished 31 days early | G | Project is on budget | 2018-10-01 | 2018-10-01 | 2018-12-28 | 2018-10-17 | G | 2018-12-31 | 2018-10-17 | 2019-01-03 | 2018-10-19 | G | 2019-01-04 | 2018-10-22 | 2019-07-11 | 2019-07-11 | G | [25 empty] | 2019-03-05 | 2019-03-05 | 2019-12-13 | 2019-03-05 | G | [5 empty] | 2020-12-08 | 2020-12-08 | 2021-01-22 | 2020-12-22 | G | 2021-04-13 |  | 2021-05-24 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.20208
1527 | 113860 | SYSTEMIC SIGNAL & PED SAFETY UPGRADES FOR THE TOWN OF ORANGE | 0015 | Urban | Safety | Locally | Orange | LOUISA | Culpeper | NonMPO:NonMPO | Infrastructure Investment Division | Ken Connors |  |  | Thomas Fitzpatrick | Thomas.Fitzpatrick@vdot.virginia.gov |  | John Cooley | townplanner@townoforangeva.org | (540) 672-6917 | 0 |  | 0 | FY2023 | 685000 | 685000 | NO DATES SET YET-PE OPEN | R | Start Development milestone finished 15 days late | G | Project is on budget | 2020-10-01 | 2020-03-18 | 2020-12-30 | 2020-03-23 | G | 2020-12-31 | 2021-01-06 | 2021-01-05 | 2021-01-20 | R | 2021-01-06 | 2021-01-21 | 2021-07-13 |  | G | [25 empty] | 2021-08-18 |  | 2022-04-26 |  | G | [5 empty] | 2022-08-01 |  | 2022-08-26 |  | G | 2022-11-17 |  | 2022-11-17 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.090686
1528 | 113984 | Buchanan County Route 680 Rumble Strips | 0680 | Secondary | Safety | VDOT | Buchanan County | LEBANON | Bristol | NonMPO:NonMPO | Infrastructure Investment Division | John R Watson | JR.Watson@VDOT.Virginia.gov | (276) 202-1240 | Chase R Buchanan | Chase.Buchanan@VDOT.Virginia.gov | (276) 696-3251 |  |  |  | 0 |  | 0 | FY2025 | 1394000 | 1394000 | NO DATES SET YET | G | Start Development milestone is 600 days ahead of the expected completion date | G | Project is on budget | [5 empty] | 2022-10-03 |  | 2022-10-14 |  | G | 2022-10-18 |  | 2023-06-13 |  | G | [5 empty] | 2024-02-22 |  | 2024-04-03 |  | G | [5 empty] | 2024-07-18 |  | 2024-11-08 |  | G | [5 empty] | 2024-07-02 |  | 2024-10-02 |  | G | [5 empty] | 2024-11-12 |  | 2024-11-12 |  | G | 2025-02-07 |  | 2025-02-07 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.070086
1529 | 115298 | PRIMARY EXTENSION PAVING FY20 CITY OF FAIRFAX - RTE 123 | 0123 | Urban | Resurfacing | Locally | Fairfax | FAIRFAX | Northern Virginia | Northern Virginia:Fairfax | Local Assistance Division | Andrew G Beacher | Andrew.Beacher@vdot.virginia.gov | (703) 259-2239 | Rita Hockman | Rita.Hockman@vdot.virginia.gov | (804) 824-7421 | Wendy Sanford | wendy.sanford@fairfaxva.gov | (703) 385-7889 | 0 |  | 1 | FY2020 |  |  | CONSTRUCTION COMPLETED | G | Determine Requirements milestone finished 2 days early | R | Critical information missing | 2019-07-01 | 2019-07-01 | 2019-09-30 | 2019-08-22 | G | [5 empty] | 2019-10-01 | 2019-10-29 | 2019-10-31 | 2019-10-29 | G | [25 empty] | 2019-08-23 | 2019-05-13 | 2019-11-27 | 2019-05-13 | G | [5 empty] | 2019-10-30 | 2019-05-14 | 2019-12-27 | 2019-05-14 | G | 2019-12-30 | 2019-05-14 | 2020-02-26 | 2019-05-14 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.17776
1530 | 108719 | COMPLETE ROADWAY BETWEEN SALEM AVENUE AND W. MAIN ST. | 1006 | Secondary | New Construction Roadway | Locally | Fauquier County | WARRENTON | Culpeper | NonMPO:NonMPO | Local Assistance Division | John P Price | John.Price@VDOT.Virginia.gov | (540) 347-6371 | John P Price | John.Price@VDOT.Virginia.gov | (540) 347-6371 | Adam Shellenberger | Adam.Shellenberger@fauquiercounty.gov | (540) 422-8210 | 0 |  | 0 | FY2021 | 2060000 | 2429710 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 133 days early | Y | Project estimate is less than $5M and is up to 20% over budget | 2016-06-28 | 2016-06-28 | 2016-06-28 | 2016-06-28 | G | 2016-06-28 | 2016-06-28 | 2016-06-28 | 2016-06-28 | G | 2016-06-28 | 2016-06-28 | 2018-07-02 | 2018-06-25 | G | [10 empty] | 2019-07-05 | 2019-02-01 | 2019-07-25 | 2019-02-01 | G | [5 empty] | 2019-07-29 | 2019-02-07 | 2020-05-08 | 2019-10-23 | G | [10 empty] | 2020-05-27 | 2020-03-09 | 2020-08-19 | 2020-04-07 | G | 2020-08-20 | 2020-04-08 | 2020-09-30 | 2020-05-20 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.14282
1531 | 109470 | #HB2.FY17 -- PEDESTRIAN IMPROVEMENTS AT RTE 17/17B INTERSECT | 0017 | Primary | Facilities for Pedestrians and Bicycles | VDOT | Gloucester County | SALUDA | Fredericksburg | Hampton Roads:Gloucester County | Infrastructure Investment Division | Wesley Foor | Wesley.Foor@vdot.virginia.gov | (540) 604-1370 | Wesley Foor | Wesley.Foor@vdot.virginia.gov | (540) 604-1370 |  |  |  | 1 | 2017 | 0 | FY2021 | 950000 | 950000 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 48 days early | G | Project is on budget | [5 empty] | 2017-06-21 | 2017-05-04 | 2017-07-05 | 2017-05-18 | G | 2017-07-06 | 2017-05-19 | 2018-03-28 | 2018-03-26 | G | [5 empty] | 2018-10-05 | 2018-10-05 | 2018-10-19 | 2018-10-15 | G | 2019-05-07 | 2019-04-01 | 2019-05-20 | 2019-04-10 | G | 2019-12-06 | 2019-09-05 | 2020-02-12 | 2019-11-12 | G | 2019-06-06 | 2019-05-13 | 2019-12-05 | 2019-10-22 | G | 2019-01-09 | 2018-09-07 | 2019-10-24 | 2018-09-07 | G | [5 empty] | 2020-03-10 | 2020-02-11 | 2020-03-10 | 2020-02-11 | G | 2020-06-11 | 2020-05-07 | 2020-08-06 | 2020-06-19 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.082582
1532 | 111276 | BRODNAX DEPOT RESTORATION |  | Enhancement | Rehabilitation of Historic Bldgs/Facilities | Locally | Brodnax | SOUTH HILL | Richmond | NonMPO:NonMPO | Local Assistance Division | Jorg Huckabee-Mayfield | Jorg.Huckabee-Mayfield@VDOT.Virginia.gov | (804) 609-5292 | Jorg Huckabee-Mayfield | Jorg.Huckabee-Mayfield@VDOT.Virginia.gov | (804) 609-5292 | Deborah Gosney | dgosney@southsidepdc.org | (434) 447-7101 | 0 |  | 0 | FY2021 | 448285 | 448285 | NO DATES SET YET-PE OPEN | R | Determine Requirements milestone is 839 days past the expected completion date | G | Project is on budget | 2018-02-01 | 2017-12-28 | 2018-04-26 | 2018-03-13 | G | 2018-04-27 | 2018-03-13 | 2018-05-01 | 2018-03-20 | G | 2018-05-02 | 2018-03-05 | 2018-11-05 |  | R | [10 empty] | 2019-11-07 |  | 2019-12-02 |  | R | [5 empty] | 2019-12-04 |  | 2020-09-11 |  | R | 2019-05-22 |  | 2019-08-19 |  | R | [5 empty] | 2020-09-29 |  | 2020-10-27 |  | R | 2020-10-28 |  | 2021-01-21 |  | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.26522
1533 | 111678 | #SGR18VB - LEESBURG PIKE OVER SUGARLAND RUN - Fed 6235 | 0007 | Primary | Bridge Rehab w/o Added Capacity | VDOT | Fairfax County | FAIRFAX | Northern Virginia | Northern Virginia:Fairfax County | Infrastructure Investment/Asset Management Division | Gary Runco | Gary.Runco@vdot.virginia.gov | (703) 259-3341 | Chandraratne B Basnayake | Chan.Basnayake@vdot.virginia.gov | (703) 259-2947 |  |  |  | 0 |  | 1 | FY2021 | 9200000 | 4709641 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 209 days early | G | Project is on budget | [10 empty] | 2020-09-01 | 2014-03-16 | 2020-09-08 | 2014-03-16 | G | [35 empty] | 2020-07-07 | 2020-06-09 | 2020-07-07 | 2020-06-09 | G | 2020-09-25 | 2020-09-02 | 2021-03-30 | 2020-09-02 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.084855
1534 | 111813 | #SMART18 - NB US 29 exit ramp to Fontaine Avenue | 0029 | Primary | Safety | VDOT | Albemarle County | CHARLOTTESVILLE | Culpeper | Charlottesville:Albemarle County | Infrastructure Investment Division | Gregory J Cooley | Gregory.Cooley@vdot.virginia.gov | (434) 906-7979 | William E Stowe | William.Stowe@vdot.virginia.gov | (540) 827-7287 |  |  |  | 1 | 2018 | 0 | FY2019 | 2900000 | 2629600 | CONSTRUCTION STARTED | R | Start Delivery milestone finished 34 days late | G | Project is on budget | [5 empty] | 2018-07-16 | 2017-10-12 | 2018-07-27 | 2017-10-26 | G | 2018-07-30 | 2017-10-27 | 2019-06-26 | 2017-10-27 | G | [10 empty] | 2018-11-01 | 2018-11-01 | 2018-11-14 | 2018-11-14 | G | [20 empty] | 2018-10-30 | 2018-10-30 | 2018-11-27 | 2018-11-27 | G | 2019-05-28 | 2019-06-26 | 2019-06-19 | 2019-07-23 | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | DESIGN BUILD/PPTA | 1 | 1 | 0.36022
1535 | 113117 | JOHN CAPRON ROAD - EXTENSION | 9999 | Urban | New Construction Roadway | Locally | Lynchburg | APPOMATTOX | Lynchburg | Lynchburg:Lynchburg | Local Assistance Division | Gregg Allen | Gregg.Allen@vdot.virginia.gov | (434) 426-5575 | Gregg Allen | Gregg.Allen@vdot.virginia.gov | (434) 426-5575 | Lee Newland, P.E. | lee.newland@lynchburg.gov | (434) 455-3947 | 0 |  | 0 | FY2020 | 3565000 | 3565000 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 169 days early | G | Project is on budget | 2019-01-31 | 2019-01-31 | 2019-04-25 | 2019-02-13 | G | 2019-04-26 | 2019-02-14 | 2019-04-30 | 2019-02-19 | G | 2019-05-01 | 2019-02-20 | 2019-11-04 | 2019-11-04 | G | [10 empty] | 2019-11-05 | 2019-11-05 | 2019-11-05 | 2019-11-05 | G | [5 empty] | 2019-11-05 | 2019-11-05 | 2019-11-05 | 2019-11-05 | G | [10 empty] | 2019-11-22 | 2019-11-22 | 2019-12-23 | 2019-12-23 | G | 2020-03-17 | 2019-12-24 | 2020-06-16 | 2019-12-30 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.11802
1536 | 113701 | #SGR19LB - Turlington Road over Kilby Creek?? | 0688 | Urban | Bridge Rehab w/o Added Capacity | Locally | Suffolk | NORFOLK | Hampton Roads | Hampton Roads:Suffolk | Infrastructure Investment Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Johndel A Alcaide | John.Alcaide@vdot.virginia.gov | (757) 956-3098 | L. Hansen | Lhansen@suffolkva.us | (757) 514-7687 | 0 |  | 1 | FY2024 | 745000 | 745000 | NO DATES SET YET-PE OPEN | G | Start Development milestone finished 506 days early | Y | Estimate not current | 2021-09-15 | 2019-09-11 | 2021-12-13 | 2019-12-09 | G | 2021-12-14 | 2020-07-14 | 2021-12-16 | 2020-07-28 | G | 2021-12-17 |  | 2022-06-24 |  | G | [10 empty] | 2023-04-21 |  | 2023-05-11 |  | G | [5 empty] | 2023-05-15 |  | 2024-02-27 |  | G | 2022-08-02 |  | 2023-04-10 |  | G | [5 empty] | 2024-03-14 |  | 2024-04-10 |  | G | 2024-06-28 |  | 2024-06-28 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.24736
1537 | 113919 | PEDESTRIAN IMPROVEMENTS AT RIDGE/CHERRY | 3405 | Urban | Safety | Locally | Charlottesville | CHARLOTTESVILLE | Culpeper | Charlottesville:Charlottesville | Infrastructure Investment Division | Ken Connors |  |  | Michael D Barnes | MichaelD.Barnes@vdot.virginia.gov | (434) 422-9861 | AMANDA PONCY | PONCY@CHARLOTTESVILLE.ORG | (434) 970-3182 | 0 |  | 0 | FY2025 | 265230 | 265230 | NO DATES SET YET | G | Agreement with Locality milestone is 312 days ahead of the expected completion date | G | Project is on budget | 2021-10-01 |  | 2021-12-30 |  | G | 2022-01-03 |  | 2022-01-05 |  | G | 2022-01-06 |  | 2022-07-13 |  | G | [10 empty] | 2023-07-17 |  | 2023-08-04 |  | G | [5 empty] | 2023-08-08 |  | 2024-05-20 |  | G | 2022-08-18 |  | 2023-04-26 |  | G | [5 empty] | 2024-06-06 |  | 2024-07-03 |  | G | 2024-09-23 |  | 2024-09-23 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.16758
1538 | 114651 | PARK AVE.-CROSSWALK & PEDESTRIAN SIGNAL IMPROVEMENTS | 0000 | Urban | Safety | Locally | Norton | WISE | Bristol | NonMPO:NonMPO | Infrastructure Investment Division | John W Bechtold | John.Bechtold@vdot.virginia.gov | (276) 696-3365 | Kenneth R Plummer | KR.Plummer@VDOT.Virginia.gov | (276) 696-3261 | Fred Ramey | fredr@nortonva.org | (276) 679-1160 | 0 |  | 0 | FY2021 | 469000 | 449000 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 155 days early | G | Project is on budget | 2018-12-13 | 2018-12-03 | 2019-03-13 | 2019-01-17 | G | 2019-03-14 | 2019-01-22 | 2019-03-18 | 2019-01-28 | G | 2019-03-19 | 2019-01-29 | 2019-09-19 | 2019-09-30 | R | [25 empty] | 2019-04-16 | 2019-11-19 | 2019-05-28 | 2019-11-19 | R | [5 empty] | 2019-12-06 | 2020-01-26 | 2020-01-22 | 2020-01-26 | R | 2020-08-07 | 2020-03-25 | 2020-08-27 | 2020-03-25 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.078168
1539 | 115462 | #SMART20 - E. Stuart Drive Sidewalk Project - Phase II | 0058 | Primary | Facilities for Pedestrians and Bicycles | Locally | Galax | MARTINSVILLE | Salem | NonMPO:NonMPO | Infrastructure Investment Division | Jessie Nester | Jessie.Nester@vdot.virginia.gov | (540) 613-4115 | Jessie Nester | Jessie.Nester@vdot.virginia.gov | (540) 613-4115 | Keith Barker | kbarker@galaxva.com | (276) 236-5773 | 1 | 2020 | 0 | FY2027 | 2013000 | 2013000 | NO DATES SET YET | G | Agreement with Locality milestone is 1103 days ahead of the expected completion date | G | Project is on budget | 2023-12-01 |  | 2024-02-29 |  | G | 2024-03-01 |  | 2024-03-05 |  | G | 2024-03-06 |  | 2024-09-06 |  | G | [10 empty] | 2025-09-10 |  | 2025-09-30 |  | G | [5 empty] | 2025-10-02 |  | 2026-07-16 |  | G | 2024-10-14 |  | 2025-06-20 |  | G | [5 empty] | 2026-08-03 |  | 2026-08-28 |  | G | 2026-11-19 |  | 2026-11-19 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.14104
1541 | 115915 | ENHANCED CURVE SIGNING & MARKING - BRISTOL DISTRICTWIDE | 9999 | Primary | Safety | VDOT | Bristol District-wide |  | Bristol | NonMPO:NonMPO | Infrastructure Investment/Asset Management Division | Brian Holt | Brian.Holt@vdot.virginia.gov | (276) 696-3414 | Jeremy J Mullins | Jeremy.Mullins@vdot.virginia.gov | (276) 696-3259 |  |  |  | 0 |  | 0 | FY2024 | 3099956 | 3099956 | NO DATES SET YET-PE OPEN | G | Start Development milestone finished 3 days early | G | Project is on budget | [5 empty] | 2020-09-03 | 2020-09-14 | 2020-09-17 | 2020-09-14 | G | 2020-09-18 | 2020-09-15 | 2021-11-02 |  | G | [35 empty] | 2023-07-11 |  | 2023-07-11 |  | G | 2023-09-29 |  | 2023-09-29 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.081909
1542 | 116413 | NOVA SYSTEMIC EDGELINE/CENTERLINE RUMBLE STRIPS | 9999 | Primary | Safety | VDOT | Northern Virginia District-wide |  | Northern Virginia | Northern Virginia:Northern Virginia District-wide | Infrastructure Investment/Asset Management Division | Nikolaos Dais | Nick.Dais@vdot.virginia.gov | (703) 259-2237 | Anwar A Ansari | Anwar.Ansari@VDOT.Virginia.gov | (703) 334-0204 |  |  |  | 0 |  | 0 | FY2022 | 394917 | 394917 | ACTIVITY DATES SET | G | Determine Requirements milestone finished 5 days early | G | Project is on budget | [5 empty] | 2019-11-26 | 2019-11-26 | 2019-12-11 | 2019-12-06 | G | 2019-12-12 | 2019-12-09 | 2020-04-22 | 2020-04-17 | G | [35 empty] | 2021-08-10 |  | 2021-08-10 |  | G | 2021-11-01 |  | 2021-11-01 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.070048
1543 | 116691 | SYSTEMIC FLASHING YELLOW ARROWS - DISTRICTWIDE | 9999 | Primary | Safety | VDOT | Richmond District-wide |  | Richmond | Richmond:Richmond District-wide | Infrastructure Investment/Asset Management Division | Adam S Brooks | Adam.Brooks@VDOT.Virginia.gov | (804) 609-5274 | Adam S Brooks | Adam.Brooks@VDOT.Virginia.gov | (804) 609-5274 | N\A |  |  | 0 |  | 0 | FY2021 | 1806422 | 1806422 | ACTIVITY DATES SET | G | Engage Public milestone finished 192 days early | G | Project is on budget | [5 empty] | 2020-07-06 | 2020-06-09 | 2020-07-06 | 2020-06-09 | G | 2020-07-07 | 2020-07-07 | 2020-10-13 | 2020-10-13 | G | [5 empty] | 2021-04-12 | 2020-10-13 | 2021-04-23 | 2020-10-13 | G | [25 empty] | 2021-05-11 |  | 2021-05-17 |  | G | 2021-05-18 |  | 2021-05-24 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | WORK/TASK ORDER | 0 | 0 | 0.066007
1544 | 117172 | Main and Calhoun Streets Stormwater Drainage - Galax | 0000 | Urban | Mitigation of Water Pollution Due to Highway Runof | Locally | Galax | MARTINSVILLE | Salem | NonMPO:NonMPO | Local Assistance Division | Jessie Nester | Jessie.Nester@vdot.virginia.gov | (540) 613-4115 | Jessie Nester | Jessie.Nester@vdot.virginia.gov | (540) 613-4115 | Keith Barker | kbarker@GalaxVa.com | (276) 236-5773 | 0 |  | 0 | FY2028 | 1839000 | 1839000 | NO DATES SET YET | G | Agreement with Locality milestone is 1422 days ahead of the expected completion date | G | Project is on budget | 2024-08-30 |  | 2025-01-13 |  | G | 2025-01-14 |  | 2025-02-05 |  | G | 2025-08-12 |  | 2025-12-08 |  | G | [10 empty] | 2027-04-01 |  | 2027-05-05 |  | G | [5 empty] | 2027-05-06 |  | 2027-10-04 |  | G | 2027-08-31 |  | 2028-02-04 |  | G | [5 empty] | 2028-01-12 |  | 2028-02-10 |  | G | 2028-05-01 |  | 2028-05-01 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.095629
1545 | 117708 | POTOMAC YARD - FOUR MILE RUN TRAIL CONNECTION - PH II | 0000 | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Arlington County | FAIRFAX | Northern Virginia | Northern Virginia:Arlington County | Local Assistance Division | Amir Salahshoor | A.Salahshoor@VDOT.Virginia.gov | (703) 259-1957 | Jeffrey S Daily | Jeff.Daily@VDOT.Virginia.gov | (703) 259-2993 | Jason Widstrom | jwidstrom@arlingtonva.us | (703) 228-7525 | 0 |  | 0 | FY2022 | 1453056 | 1453056 | ACTIVITY DATES SET | Y | Obtained Permits milestone is 30 days ahead of the expected completion date and there is a risk of missing this milestone date | G | Project is on budget | 2020-07-31 | 2020-07-08 | 2020-10-26 | 2020-10-26 | G | [5 empty] | 2020-07-31 | 2020-07-08 | 2021-01-29 | 2021-01-25 | G | [25 empty] | 2021-01-26 |  | 2021-03-23 |  | Y | [5 empty] | 2021-05-05 |  | 2021-07-19 |  | G | 2021-10-06 |  | 2022-03-22 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.36951
1546 | 117780 | ITS DEVICES ON-CALL CONTRACT - CENTRAL REGION | 9999 | Interstate | Safety | VDOT | Richmond District-wide |  | Richmond | Richmond:Richmond District-wide | Infrastructure Investment/Asset Management Division | Adam S Brooks | Adam.Brooks@VDOT.Virginia.gov | (804) 609-5274 | Adam S Brooks | Adam.Brooks@VDOT.Virginia.gov | (804) 609-5274 | N\A |  |  | 0 |  | 0 | FY2022 | 11041814 | 11041814 | ACTIVITY DATES SET | G | Determine Requirements milestone finished 154 days early | G | Project is on budget | [10 empty] | 2021-06-28 | 2021-02-01 | 2021-07-12 | 2021-02-08 | G | [35 empty] | 2021-08-10 |  | 2021-08-10 |  | G | 2021-11-01 |  | 2021-11-01 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | REGIONAL ON-CALL CONTRACT | 0 | 0 | 0.070953
1547 | 118193 | #I95 CIP CRO SSP FY21-24 | 0095 | Interstate | Safety | VDOT | Statewide |  | Statewide | Multiple MPOs:Statewide | Infrastructure Investment Division | Ricky A Via | Ricky.Via@vdot.virginia.gov | (804) 371-2396 | Teresa H Butler | Teresa.Butler@VDOT.Virginia.gov | (540) 229-3722 |  |  |  | 0 |  | 0 | FY2022 | 1550000 | 1550000 | ACTIVITY DATES SET | R | Determine Requirements milestone is 54 days past the expected completion date | G | Project is on budget | [10 empty] | 2020-12-15 |  | 2020-12-29 |  | R | [25 empty] | 2020-12-15 | 2020-10-22 | 2021-05-17 | 2020-10-22 | G | [5 empty] | 2021-04-13 |  | 2021-04-13 |  | Y | 2021-07-01 |  | 2021-07-01 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | ADMINISTRATIVE SERVICES | 0 | 1 | 0.30757
1548 | 91227 | Streetscaping improvements along Main Street |  | Enhancement | Landscaping/Beautification | Locally | Fauquier County | WARRENTON | Culpeper | NonMPO:NonMPO | Local Assistance Division | John P Price | John.Price@VDOT.Virginia.gov | (540) 347-6371 | John P Price | John.Price@VDOT.Virginia.gov | (540) 347-6371 | Erin Kozanecki | erin.kozanecki.adm@fauquiercounty.gov | (540) 422-8005 | 0 |  | 0 | FY2019 | 4511975 | 7001441 | AWARDED | R | Start Delivery milestone finished 497 days late | R | Project estimate is less than $5M and is 20% or more over budget | 2010-01-05 | 2010-01-05 | 2010-02-09 | 2010-02-09 | G | 2008-11-01 | 2008-11-01 | 2008-11-20 | 2008-11-20 | G | 2015-04-30 | 2015-04-30 | 2018-08-31 | 2018-08-17 | G | 2015-09-01 | 2015-09-01 | 2015-10-10 | 2015-10-10 | G | [5 empty] | 2016-08-30 | 2016-08-30 | 2018-10-30 | 2018-11-15 | R | [5 empty] | 2017-03-30 | 2017-03-30 | 2018-12-28 | 2019-03-22 | R | [10 empty] | 2018-12-31 | 2019-07-01 | 2019-01-30 | 2019-10-25 | R | 2019-02-01 | 2020-08-26 | 2019-05-30 | 2020-10-08 | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.37227
1549 | 104826 | #SGR17VB - BR Repl-Bull Bun Rd over Little Toms Crk (Fed 19 | 0893 | Secondary | Bridge Replacement w/ Added Capacity | VDOT | Wise County | WISE | Bristol | NonMPO:NonMPO | Infrastructure Investment/Asset Management Division | Gary Lester |  |  | David L Lively | David.Lively@VDOT.Virginia.gov | (276) 696-3388 |  |  |  | 0 |  | 1 | FY2019 | 608000 | 409228 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 3 days early | G | Project is on budget | [5 empty] | 2016-08-01 | 2016-08-01 | 2016-09-30 | 2016-09-15 | G | 2016-09-30 | 2016-09-30 | 2016-11-30 | 2016-11-01 | G | 2016-11-15 | 2016-11-15 | 2017-09-12 | 2017-09-12 | G | [30 empty] | 2018-06-14 | 2018-07-10 | 2018-07-10 | 2018-07-10 | G | 2018-07-10 | 2018-09-07 | 2018-09-10 | 2018-09-07 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.077931
1550 | 115833 | Drainage Improvements in Town of New Castle | 0042 | Primary | Other | VDOT | Craig County | SALEM | Salem | NonMPO:NonMPO | Infrastructure Investment Division | Dennis D Varney | Ray.Varney@VDOT.Virginia.gov | (540) 387-5500 | Steven Palmer | Steve.Palmer@vdot.virginia.gov | (540) 387-5499 |  |  |  | 0 |  | 0 | FY2022 | 186000 | 186000 | NO DATES SET YET | R | Determine Requirements milestone is 33 days past the expected completion date | Y | Estimate not current | [10 empty] | 2021-01-04 |  | 2021-01-19 |  | R | [25 empty] | 2021-01-04 | 2020-12-23 | 2021-06-03 | 2020-12-23 | G | [5 empty] | 2021-04-13 |  | 2021-04-13 |  | Y | 2021-07-01 |  | 2021-07-01 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | SAAP CONTRACT | 0 | 0 | 0.15748
1551 | 115999 | I-95 SB AUXILIARY LANE BETWEEN RTE 123 AND RTE 294 | 0095 | Interstate | Reconstruction w/ Added Capacity | VDOT | Prince William County | MANASSAS | Northern Virginia | Northern Virginia:Prince William County | Infrastructure Investment Division | Claudia H Llana | Claudia.Llana@VDOT.Virginia.gov | (703) 259-1768 | William C Britt | Calvin.Britt@VDOT.Virginia.gov | (703) 259-2961 | Paolo Belita |  |  | 0 |  | 0 | FY2021 | 32000001 | 32000001 | ADVERTISED | G | Solicit Bids milestone finished on-time | G | Project is on budget | [5 empty] | 2019-10-15 | 2019-07-16 | 2019-10-29 | 2019-09-20 | G | 2019-10-30 | 2019-09-20 | 2020-12-10 | 2020-06-16 | G | [5 empty] | 2020-06-17 | 2020-06-17 | 2020-07-16 | 2020-07-24 | R | 2020-02-19 | 2020-02-18 | 2020-02-19 | 2020-02-18 | G | 2019-12-19 | 2019-12-18 | 2019-12-19 | 2019-12-18 | G | 2020-07-16 | 2020-02-18 | 2020-07-16 | 2020-02-18 | G | 2020-07-20 | 2020-07-08 | 2020-10-12 | 2020-09-30 | G | [5 empty] | 2020-12-08 | 2020-12-08 | 2020-12-08 | 2020-12-08 | G | 2021-04-26 |  | 2021-04-26 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.18516
1552 | 116540 | PERSHING DRIVE SIDEWALK & INTERSECTION IMPROVEMENTS PH II | 9999 | Secondary | Facilities for Pedestrians and Bicycles | Locally | Arlington County | FAIRFAX | Northern Virginia | Northern Virginia:Arlington County | Local Assistance Division | Amir Salahshoor | A.Salahshoor@VDOT.Virginia.gov | (703) 259-1957 | Jeffrey S Daily | Jeff.Daily@VDOT.Virginia.gov | (703) 259-2993 | Valerie Mosley | mvmpsley@arlingtonva.us | (703) 228-4938 | 0 |  | 0 | FY2024 | 1163500 | 1163500 | ACTIVITY DATES SET | G | Start Development milestone finished on-time | Y | Estimate not current | 2019-09-03 | 2019-09-03 | 2020-01-16 | 2020-01-16 | G | 2020-01-21 | 2020-01-21 | 2020-02-20 | 2020-02-20 | G | 2016-03-01 | 2016-03-01 | 2020-01-07 | 2020-01-07 | G | [10 empty] | 2022-03-10 |  | 2022-04-13 |  | G | [5 empty] | 2022-04-14 |  | 2022-09-12 |  | G | 2022-08-22 |  | 2023-01-26 |  | G | [5 empty] | 2022-12-19 |  | 2023-04-28 |  | G | 2023-07-19 |  | 2023-11-09 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.23953
1553 | 117167 | #SGR21LP 137-City of Williamsburg 2196 S Henry St | 0132 | Urban | Resurfacing | Locally | Williamsburg | WILLIAMSBURG | Hampton Roads | Hampton Roads:Williamsburg | Infrastructure Investment/Asset Management Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Chessica Villaflores | Chessica.Villaflores@vdot.virginia.gov | (757) 956-3094 | Aaron B. Small | asmall@williamsburgva.gov | (757) 220-6140 | 0 |  | 1 | FY2022 | 258800 | 258800 | NO DATES SET YET | G | Agreement with Locality milestone is 47 days ahead of the expected completion date | G | Project is on budget | 2021-03-01 |  | 2021-04-09 |  | G | 2021-04-12 |  | 2021-04-30 |  | G | 2021-06-01 |  | 2021-07-13 |  | G | [25 empty] | 2021-06-29 |  | 2021-08-10 |  | G | [5 empty] | 2021-10-07 |  | 2021-11-04 |  | G | 2022-02-01 |  | 2022-02-01 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.092414
1554 | 117177 | Town-wide Sidewalk Trip Hazard Removal - Blacksburg | 0000 | Urban | Safety | Locally | Blacksburg | CHRISTIANSBURG | Salem | New River Valley:Blacksburg | Local Assistance Division | Adam J Czesnowski | Adam.Czesnowski@vdot.virginia.gov | (540) 541-1216 | Adam J Czesnowski | Adam.Czesnowski@vdot.virginia.gov | (540) 541-1216 | Randy Formica | rformica@blacksburg.gov | (540) 443-1300 | 0 |  | 0 | FY2028 | 50000 | 50000 | NO DATES SET YET | G | Agreement with Locality milestone is 1422 days ahead of the expected completion date | G | Project is on budget | 2024-08-30 |  | 2025-01-13 |  | G | 2025-01-14 |  | 2025-02-05 |  | G | 2025-08-12 |  | 2025-12-08 |  | G | [25 empty] | 2026-12-03 |  | 2027-05-05 |  | G | [5 empty] | 2027-07-02 |  | 2027-07-30 |  | G | 2027-10-20 |  | 2027-10-20 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.16826
1555 | 117745 | Traffic Calming - N Pinetta Drive | 0755 | Secondary | Traffic Management/Engineering | Locally | Chesterfield County | CHESTERFIELD | Richmond | Richmond:Chesterfield County | Infrastructure Investment Division | Michael S Gray | Mike.Gray@vdot.virginia.gov | (804) 609-5347 | Michael S Gray | Mike.Gray@vdot.virginia.gov | (804) 609-5347 | Nathan Mathis | mathisn@chesterfield.gov | (804) 748-1037 | 0 |  | 0 | FY2022 | 30000 | 30000 | NO DATES SET YET | G | Agreement with Locality milestone finished 193 days early | G | Project is on budget | 2021-04-01 | 2020-10-19 | 2021-08-06 | 2021-01-25 | G | [5 empty] | 2021-08-09 | 2021-01-26 | 2021-08-20 |  | G | [25 empty] | 2021-04-29 |  | 2021-09-27 |  | G | [5 empty] | 2021-11-29 |  | 2021-12-27 |  | G | 2022-03-21 |  | 2022-03-21 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.27052
1556 | 118184 | #SGR21VP - Roanoke FKEY 1370 Riverland Rd SE | 0000 | Urban | Resurfacing | VDOT | Roanoke | SALEM | Salem | Roanoke:Roanoke City | Infrastructure Investment/Asset Management Division | Ibrahim M Abuawad | Ibrahim.Abuawad@vdot.virginia.gov | (217) 418-8827 | Ibrahim M Abuawad | Ibrahim.Abuawad@vdot.virginia.gov | (217) 418-8827 | Mark Jamison | mark.jamison@roanokeva.gov | (540) 853-5471 | 0 |  | 1 | FY2021 | 215000 | 215000 | NO DATES SET YET | R | Determine Requirements milestone is 9 days past the expected completion date | G | Project is on budget | [10 empty] | 2021-02-01 |  | 2021-02-12 |  | R | [35 empty] | 2021-03-09 |  | 2021-03-09 |  | Y | 2021-05-27 |  | 2021-05-27 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.14894
1557 | 13285 | #SGR17VB - RT 682 Bridge and Approaches over Pleasant Run | 0682 | Secondary | Reconstruction w/o Added Capacity | VDOT | Rockingham County | HARRISONBURG | Staunton | Harrisonburg:Rockingham County | Infrastructure Investment/Asset Management Division | Robert Hall |  |  | Alexander Alvarado | Alexander.Alvarado@vdot.virginia.gov | (540) 332-7372 |  |  |  | 0 |  | 1 | FY2021 | 4668569 | 5447424 | ACTIVITY DATES SET | R | Solicit Bids milestone is 131 days past the expected completion date | Y | Estimate not current | [5 empty] | 1999-07-16 | 2000-08-29 | 1999-10-15 | 2005-10-04 | R | 2012-10-01 | 2012-10-01 | 2012-12-21 | 2014-12-22 | R | [5 empty] | 2015-04-07 | 2015-04-07 | 2015-05-15 | 2015-05-15 | G | 2019-05-14 | 2020-02-03 | 2019-06-14 | 2020-02-11 | R | 2020-03-02 | 2020-11-17 | 2020-09-04 | 2020-11-17 | R | 2019-07-01 | 2020-02-19 | 2020-02-28 | 2020-10-19 | R | 2019-09-30 | 2020-03-02 | 2020-07-31 | 2020-07-10 | G | [5 empty] | 2020-09-17 |  | 2020-10-13 |  | R | 2020-11-16 |  | 2021-03-31 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.098589
1558 | 104159 | SIDEWALK (NEW CONSTRUCTION) - VARIOUS LOCATIONS | 0000 | Secondary | Safety and Education of Pedestrians /Bicyclisits | Locally | Albemarle County | CHARLOTTESVILLE | Culpeper | Charlottesville:Albemarle County | Local Assistance Division | Gregory J Cooley | Gregory.Cooley@vdot.virginia.gov | (434) 906-7979 | Thomas Fitzpatrick | Thomas.Fitzpatrick@vdot.virginia.gov |  | David Benish |  |  | 0 |  | 0 | FY2020 | 3739272 | 3739272 | ADVERTISED | R | Start Delivery milestone is 517 days past the expected completion date | G | Project is on budget | 2014-07-01 | 2014-07-01 | 2014-12-01 | 2014-08-27 | G | 2015-01-05 | 2015-01-05 | 2015-01-05 | 2015-01-05 | G | 2016-08-01 | 2016-07-30 | 2016-11-30 | 2016-11-30 | G | [10 empty] | 2018-01-03 | 2018-01-03 | 2018-01-25 | 2018-01-25 | G | [20 empty] | 2019-08-01 | 2020-07-07 | 2019-08-27 | 2020-10-30 | R | 2019-08-27 |  | 2019-09-23 |  | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.27543
1559 | 106995 | NORTHSTAR BLVD EXTENSION ROUTE 50 TO TALL CEDARS PKWY | 9999 | Secondary | New Construction Roadway | Locally | Loudoun County | LEESBURG | Northern Virginia | Northern Virginia:Loudoun County | Local Assistance Division | Amir Salahshoor | A.Salahshoor@VDOT.Virginia.gov | (703) 259-1957 | Susie X Lue | Susie.Lue@vdot.virginia.gov | (703) 259-2918 | Marie Caraballo | marie.caraballo@loudoun.gov | (571) 258-3447 | 0 |  | 0 | FY2022 | 17500000 | 37887000 | ACTIVITY DATES SET | R | Complete Purchasing Right-of-Way milestone is 220 days past the expected completion date | R | Project estimate is greater than $10M and is over budget by (a) 10% or more or (b) $5M or more | 2015-07-01 | 2015-07-01 | 2015-09-24 | 2016-03-01 | R | 2015-09-25 | 2016-03-01 | 2015-10-08 | 2016-03-24 | R | 2015-10-09 | 2015-10-19 | 2016-06-08 | 2016-06-08 | G | [5 empty] | 2017-11-07 | 2017-11-07 | 2018-03-21 | 2018-03-21 | G | 2020-06-24 | 2018-03-22 | 2020-07-08 | 2018-08-10 | G | [5 empty] | 2018-08-13 | 2018-08-13 | 2020-07-16 |  | R | [10 empty] | 2020-08-11 |  | 2021-07-08 |  | G | 2021-07-09 |  | 2021-07-09 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.40696
1560 | 107309 | Dry Hollow Road Safety Improvements | 0649 | Secondary | Safety | VDOT | Roanoke County | SALEM | Salem | Roanoke:Roanoke County | Infrastructure Investment Division | James M Guy | james.guy@vdot.virginia.gov | (540) 387-5247 | Francis Scarpinato | Francis.Scarpinato@vdot.virginia.gov | (540) 375-3593 |  |  |  | 0 |  | 0 | FY2023 | 2185000 | 2185000 | ACTIVITY DATES SET | R | Engage Public milestone is 311 days past the expected completion date | G | Project is on budget | [5 empty] | 2015-10-02 | 2015-10-02 | 2015-10-02 | 2015-10-02 | G | 2015-10-05 | 2015-10-05 | 2018-11-15 | 2018-11-15 | G | [5 empty] | 2020-03-13 |  | 2020-04-16 |  | R | 2021-07-07 |  | 2021-07-20 |  | G | 2021-12-15 |  | 2022-04-05 |  | G | 2021-08-05 |  | 2022-02-15 |  | G | 2020-11-09 | 2020-11-09 | 2022-03-11 |  | G | [5 empty] | 2022-04-12 |  | 2022-05-10 |  | G | 2022-06-30 |  | 2022-10-24 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.13999
1561 | 109576 | #HB2.FY17 ROUTE 17 CORRIDOR IMPROVEMENTS | 0017 | Primary | Safety | VDOT | Essex County | SALUDA | Fredericksburg | NonMPO:NonMPO | Infrastructure Investment Division | Wesley Foor | Wesley.Foor@vdot.virginia.gov | (540) 604-1370 | Wesley Foor | Wesley.Foor@vdot.virginia.gov | (540) 604-1370 |  |  |  | 1 | 2017 | 0 | FY2022 | 1000000 | 1000000 | AWARDED | G | Start Delivery milestone finished 328 days early | G | Project is on budget | [5 empty] | 2018-06-19 | 2018-06-19 | 2018-07-02 | 2018-06-22 | G | 2018-07-03 | 2018-06-22 | 2018-11-27 | 2018-11-26 | G | [5 empty] | 2019-06-19 | 2019-05-07 | 2019-07-17 | 2019-07-17 | G | 2020-06-02 | 2019-08-01 | 2020-06-29 | 2019-08-01 | G | 2021-01-19 | 2020-06-10 | 2021-07-15 | 2020-06-10 | G | 2020-07-16 | 2019-08-02 | 2021-01-19 | 2019-08-02 | G | 2019-10-14 | 2019-10-01 | 2020-03-12 | 2019-10-01 | G | [5 empty] | 2021-08-10 | 2020-10-06 | 2021-08-10 | 2020-10-06 | G | 2021-11-08 | 2020-12-15 | 2021-11-08 | 2020-12-15 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.062797
1562 | 110796 | #SMART18 - US 11 at SR 107 Int. Impr. w/radius | 0011 | Primary | Reconstruction w/o Added Capacity | VDOT | Smyth County | ABINGDON | Bristol | NonMPO:NonMPO | Infrastructure Investment Division | Conrad Hill | Conrad.Hill@vdot.virginia.gov | (804) 773-0170 | Ronald C Flanary | Ronald.Flanary@VDOT.Virginia.gov | (276) 696-3252 |  |  |  | 1 | 2018 | 0 | FY2022 | 3042000 | 3042000 | ACTIVITY DATES SET | G | Relocate Utilities milestone finished 3 days early | G | Project is on budget | [5 empty] | 2017-07-14 | 2017-07-14 | 2017-07-27 | 2017-07-18 | G | 2017-07-28 | 2017-07-19 | 2018-04-19 | 2018-04-24 | R | [5 empty] | 2018-12-31 | 2018-12-31 | 2019-01-14 | 2019-01-14 | G | 2020-03-05 | 2020-01-15 | 2020-03-18 | 2020-01-30 | G | 2020-08-10 | 2020-05-20 | 2021-02-18 | 2021-02-15 | G | 2020-04-03 | 2020-01-22 | 2021-03-22 | 2020-11-09 | G | 2019-08-16 | 2020-01-21 | 2020-02-27 | 2020-02-27 | G | [5 empty] | 2021-06-08 |  | 2021-06-08 |  | G | 2021-07-23 |  | 2021-09-17 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.080129
1563 | 111050 | #SMART18 - (St) PAPERMILL ROAD TURN LANE | 0644 | Secondary | Reconstruction w/ Added Capacity | VDOT | Frederick County | EDINBURG | Staunton | Winchester:Frederick County | Infrastructure Investment Division | Matthew P Dana | Matt.Dana@VDOT.Virginia.gov | (540) 332-7786 | John-Allen L Ennis | JohnAllen.Ennis@VDOT.Virginia.gov | (540) 332-9118 |  |  |  | 1 | 2018 | 0 | FY2019 | 507262 | 507262 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 97 days early | G | Project is on budget | [5 empty] | 2017-08-03 | 2017-07-17 | 2017-08-16 | 2017-07-28 | G | 2017-08-17 | 2017-07-31 | 2017-12-28 | 2017-12-21 | G | [5 empty] | 2018-03-13 | 2018-03-19 | 2018-05-24 | 2018-05-23 | G | 2018-07-11 | 2018-07-17 | 2018-07-24 | 2018-07-24 | G | 2018-05-29 | 2018-05-29 | 2018-08-31 | 2018-07-03 | G | 2018-07-26 | 2018-07-26 | 2018-07-26 | 2018-07-26 | G | 2017-12-14 | 2017-12-14 | 2018-07-31 | 2018-03-30 | G | [5 empty] | 2018-10-09 | 2018-11-20 | 2018-10-09 | 2018-11-20 | R | 2018-11-28 | 2019-01-23 | 2019-04-30 | 2019-01-23 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.086562
1564 | 111261 | #SGR18LB - RT 61 Tazewell Co VA #1807 Federal STR 22548 | 0061 | Urban | Bridge Rehab w/o Added Capacity | VDOT | Tazewell | LEBANON | Bristol | NonMPO:NonMPO | Infrastructure Investment Division | Gary Lester |  |  | Emily V Collins | Emily.Collins@vdot.virginia.gov | (276) 696-3394 |  |  |  | 0 |  | 1 | FY2021 | 1500000 | 1500000 | NO DATES SET YET | R | Start Development milestone is 219 days past the expected completion date | G | Project is on budget | [5 empty] | 2020-07-06 |  | 2020-07-17 |  | R | 2020-07-20 |  | 2020-08-14 |  | R | [35 empty] | 2021-03-09 |  | 2021-03-09 |  | Y | 2021-04-21 |  | 2021-05-11 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.1907
1566 | 112656 | Route 172 (Wythe Creek Road) Milling and Repaving | 0172 | Urban | Resurfacing | Locally | Poquoson | WILLIAMSBURG | Hampton Roads | Hampton Roads:Poquoson | Infrastructure Investment Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Chessica Villaflores | Chessica.Villaflores@vdot.virginia.gov | (757) 956-3094 | Ellen Roberts | Ellen.roberts@poquoson-va.gov | (757) 868-3025 | 0 |  | 0 | FY2021 | 188899 | 187362 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 728 days early | G | Project is on budget | 2018-04-23 | 2018-04-23 | 2018-04-23 | 2018-04-23 | G | 2018-04-23 | 2018-04-23 | 2018-04-23 | 2018-04-23 | G | 2018-04-18 | 2018-04-18 | 2019-03-27 | 2018-07-12 | G | [35 empty] | 2020-02-06 | 2018-08-26 | 2020-04-02 | 2018-08-26 | G | 2020-04-03 | 2018-09-25 | 2020-09-22 | 2018-09-25 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.12609
1567 | 113142 | Downtown Salem - Roanoke Boulevard | 0000 | Urban | Facilities for Pedestrians and Bicycles | Locally | Salem | SALEM | Salem | Roanoke:Salem | Local Assistance Division | Cheryl B Becker | Cheryl.Becker@vdot.virginia.gov | (540) 492-2531 | Cheryl B Becker | Cheryl.Becker@vdot.virginia.gov | (540) 492-2531 | Will Simpson | wsimpson@salemva.gov | (540) 375-3032 | 0 |  | 0 | FY2023 | 1000000 | 1000000 | NO DATES SET YET-PE OPEN | R | Determine Requirements milestone is 202 days past the expected completion date | G | Project is on budget | 2019-08-01 | 2019-07-19 | 2019-10-25 | 2020-03-10 | R | 2019-10-28 | 2020-03-24 | 2019-10-30 | 2020-03-25 | R | 2019-10-31 |  | 2020-08-03 |  | R | [10 empty] | 2021-08-05 |  | 2021-08-25 |  | G | [5 empty] | 2021-08-27 |  | 2022-06-10 |  | G | [10 empty] | 2022-06-13 |  | 2022-07-11 |  | G | 2022-12-06 |  | 2022-12-06 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.2463
1568 | 113716 | RT. 614 - RURAL RUSTIC SURFACE TREAT NON-HARDSURFACE ROAD | 0614 | Secondary | Reconstruction w/o Added Capacity | VDOT | Rappahannock County | WARRENTON | Culpeper | NonMPO:NonMPO | Infrastructure Investment Division | Ken Connors |  |  | Benjamin Davison | Ben.Davison@vdot.virginia.gov | (540) 347-6446 |  |  |  | 0 |  | 0 | FY2025 | 617500 | 617500 | NO DATES SET YET | G | Start Development milestone is 600 days ahead of the expected completion date | Y | Estimate not current | [5 empty] | 2022-10-03 |  | 2022-10-14 |  | G | 2022-10-18 |  | 2023-06-13 |  | G | [5 empty] | 2024-02-22 |  | 2024-04-03 |  | G | [5 empty] | 2024-07-18 |  | 2024-11-08 |  | G | [5 empty] | 2024-07-02 |  | 2024-10-02 |  | G | [5 empty] | 2024-11-12 |  | 2024-11-12 |  | G | 2025-02-07 |  | 2025-02-07 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | SAAP CONTRACT | 0 | 0 | 0.10405
1569 | 113760 | Lee Highway Primary Extension Paving | 0011 | Urban | Resurfacing | Locally | Bristol | ABINGDON | Bristol | Bristol:Bristol | Local Assistance Division | Tabitha H Crowder | Tabitha.Crowder@vdot.virginia.gov | (276) 696-3482 | Tabitha H Crowder | Tabitha.Crowder@vdot.virginia.gov | (276) 696-3482 | Wallace McCulloch | wallacemcculloch@bristolva.org | (276) 642-2316 | 0 |  | 0 | FY2019 | 144000 | 144000 | PROJECT CLOSEOUT COMPLETE | G | Obtained Permits milestone finished on-time | G | Project is on budget | 2019-06-17 | 2018-07-07 | 2019-09-10 | 2019-02-12 | G | [5 empty] | 2019-06-17 | 2019-02-13 | 2019-06-28 | 2019-02-20 | G | [25 empty] | 2019-02-21 | 2019-02-27 | 2019-05-15 | 2019-05-15 | G | [5 empty] | 2019-03-14 | 2019-03-14 | 2019-04-10 | 2019-03-14 | G | 2019-04-10 | 2019-04-10 | 2019-04-16 | 2019-04-16 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.060497
1570 | 109232 | ITTF Arterial Oper. Imprv: US 60, Rt 143 & Rt 199 | 9999 | Primary | Safety | VDOT | Hampton Roads District-wide |  | Hampton Roads | Hampton Roads:Hampton Roads District-wide | Infrastructure Investment Division | Michael J Miller | Michael.Miller@VDOT.Virginia.gov | (757) 605-8741 | Prakriti K Das | Prakriti.Das@VDOT.Virginia.gov | (757) 897-8952 |  |  |  | 0 |  | 0 | FY2019 | 1560000 | 1391601 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 93 days early | G | Project is on budget | [10 empty] | 2017-05-01 | 2017-05-01 | 2017-08-01 | 2017-08-01 | G | [35 empty] | 2018-07-17 | 2018-04-10 | 2018-07-17 | 2018-04-11 | G | 2018-09-06 | 2018-06-25 | 2018-09-26 | 2018-06-25 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.093818
1571 | 110366 | ROUTE 606-RESURFACE UNPAVED ROAD | 0606 | Secondary | Resurfacing | VDOT | Montgomery County | CHRISTIANSBURG | Salem | NonMPO:NonMPO | Infrastructure Investment Division | Paul Brown |  |  | Marvin D Mann | M.Mann@VDOT.Virginia.gov | (540) 378-5055 |  |  |  | 0 |  | 0 | FY2020 | 1572222 | 931325 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 168 days early | G | Project is on budget | [5 empty] | 2019-07-31 | 2018-02-07 | 2019-08-13 | 2018-02-26 | G | 2019-08-14 | 2018-02-27 | 2020-07-13 | 2018-07-06 | G | [5 empty] | 2018-07-13 | 2018-07-13 | 2018-07-13 | 2018-07-13 | G | 2018-10-17 | 2018-10-02 | 2018-10-30 | 2018-10-03 | G | 2018-09-18 | 2018-08-20 | 2018-09-18 | 2018-08-20 | G | 2018-11-16 | 2018-10-05 | 2019-02-15 | 2019-02-14 | G | 2018-07-16 | 2018-08-03 | 2019-03-08 | 2018-10-26 | G | [5 empty] | 2019-05-14 | 2019-03-26 | 2019-05-14 | 2019-03-26 | G | 2019-07-05 | 2019-05-28 | 2019-11-12 | 2019-05-28 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | SAAP CONTRACT | 1 | 0 | 0.072686
1572 | 110803 | #SMART18 - Cleveland Street Phase IV |  | Urban | Reconstruction w/ Added Capacity | Locally | Virginia Beach | NORFOLK | Hampton Roads | Hampton Roads:Virginia Beach | Infrastructure Investment Division | Susan Wilson | Susan.Wilson@vdot.virginia.gov | (757) 956-3099 | Marci Thompson | Marci.Thompson@vdot.virginia.gov | (757) 956-3093 | Katie E. Shannon, PE | KShannon@vbgov.com | (757) 385-1514 | 1 | 2018 | 0 | FY2024 | 23647000 | 24347000 | NO DATES SET YET-PE OPEN | R | Determine Requirements milestone is 172 days past the expected completion date | Y | Project estimate is greater than $10M and is over budget by (a) up to 10% or (b) up to $5M | 2019-06-05 | 2019-09-03 | 2019-08-28 | 2019-11-04 | R | 2019-08-29 | 2019-11-05 | 2019-09-03 | 2019-11-07 | R | 2019-09-04 |  | 2020-09-02 |  | R | [10 empty] | 2020-12-23 |  | 2021-01-14 |  | R | [5 empty] | 2021-01-20 |  | 2023-05-18 |  | G | [10 empty] | 2023-06-06 |  | 2023-07-03 |  | G | 2023-07-05 |  | 2023-09-13 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.24973
1573 | 111177 | #SGR18LB - Florence Ave BR REPLACE over CSX RR(SGR Local) | 5105 | Urban | Bridge Replacement w/o Added Capacity | Locally | Waynesboro | HARRISONBURG | Staunton | SAW:Waynesboro | Local Assistance Division | Michael S Fulcher | Michael.Fulcher@VDOT.Virginia.gov | (540) 332-2243 | Michael S Fulcher | Michael.Fulcher@VDOT.Virginia.gov | (540) 332-2243 | Trafford McRae | McRaeTR@ci.waynesboro.va.us | (540) 942-6624 | 0 |  | 1 | FY2020 | 1827178 | 1827178 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 63 days early | G | Project is on budget | 2018-03-01 | 2018-03-01 | 2018-08-17 | 2018-11-27 | R | 2018-08-20 | 2017-11-01 | 2018-08-22 | 2018-11-05 | R | 2018-08-23 | 2018-11-27 | 2019-09-09 | 2019-03-18 | G | [10 empty] | 2019-07-02 | 2019-07-02 | 2019-07-02 | 2019-07-02 | G | [5 empty] | 2019-07-02 | 2019-07-02 | 2019-07-02 | 2019-07-02 | G | [10 empty] | 2019-08-12 | 2019-06-01 | 2019-09-09 | 2019-07-02 | G | 2019-09-10 | 2019-07-03 | 2019-12-06 | 2019-10-04 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.073445
1574 | 111664 | #SMART18 - ROUTE 7/ROUTE 287 INTERCHANGE | 0007 | Primary | Reconstruction w/ Added Capacity | Locally | Loudoun County | LEESBURG | Northern Virginia | Northern Virginia:Loudoun County | Infrastructure Investment Division | Amir Salahshoor | A.Salahshoor@VDOT.Virginia.gov | (703) 259-1957 | Susie X Lue | Susie.Lue@vdot.virginia.gov | (703) 259-2918 | Mark Hoffman | Mark.Hoffman@loudoun.gov | (703) 771-5323 | 1 | 2018 | 0 | FY2024 | 11390670 | 11206355 | NO DATES SET YET-PE OPEN | G | Start Development milestone finished 1255 days early | G | Project is on budget | 2021-10-01 | 2017-05-22 | 2021-12-30 | 2018-05-10 | G | 2022-01-03 | 2018-07-23 | 2022-01-05 | 2018-07-30 | G | 2022-01-06 | 2020-03-02 | 2023-01-06 |  | G | [5 empty] | 2021-03-01 |  | 2022-02-28 |  | G | [15 empty] | 2022-08-18 |  | 2023-04-26 |  | G | [5 empty] | 2023-08-01 |  | 2023-08-28 |  | G | 2023-08-29 |  | 2023-11-16 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.2599
1575 | 112484 | FRANCONIA RD AND ROSE HILL DR SIGNAL | 0644 | Primary | Safety | VDOT | Fairfax County | FAIRFAX | Northern Virginia | Northern Virginia:Fairfax County | Infrastructure Investment Division | Ivan M Horodyskyj | Ivan.Horodyskyj@VDOT.Virginia.gov | (703) 259-2330 | Tienjung Ho | Tien-Jung.Ho@VDOT.Virginia.gov | (703) 259-2752 |  |  |  | 0 |  | 0 | FY2023 | 475000 | 475000 | ACTIVITY DATES SET | G | Engage Public milestone finished 294 days early | G | Project is on budget | [5 empty] | 2019-02-01 | 2018-12-10 | 2019-02-14 | 2018-12-21 | G | 2019-02-15 | 2018-12-24 | 2020-01-13 | 2020-01-10 | G | [5 empty] | 2020-11-12 | 2020-02-03 | 2020-11-25 | 2020-02-05 | G | 2022-01-21 |  | 2022-02-03 |  | G | 2019-10-18 | 2019-10-18 | 2019-10-18 | 2019-10-18 | G | 2022-02-22 |  | 2022-08-24 |  | G | [10 empty] | 2022-11-08 |  | 2022-11-08 |  | G | 2023-01-04 |  | 2023-01-26 |  | G | Preliminary design and/or investigations are still underway | 2021-02-21 11:00 | 2021-02-21 06:04 | WORK/TASK ORDER | 0 | 0 | 0.051443
1577 | 113256 | S WASHINGTON ST AND ANNANDALE RD INTERSECTION IMPROVEMENTS | 0029 | Urban | Facilities for Pedestrians and Bicycles | Locally | Falls Church | FAIRFAX | Northern Virginia | Northern Virginia:Falls Church | Local Assistance Division | Andrew G Beacher | Andrew.Beacher@vdot.virginia.gov | (703) 259-2239 | Christer P Carshult | Christer.Carshult@vdot.virginia.gov | (703) 259-1765 | Jina Freiberg |  |  | 0 |  | 0 | FY2025 | 950000 | 950000 | NO DATES SET YET-PE OPEN | G | Start Development milestone finished on-time | Y | Estimate not current | 2020-09-01 | 2018-05-15 | 2021-01-29 | 2018-08-13 | G | 2020-03-26 | 2020-03-26 | 2020-04-30 | 2020-04-30 | G | 2021-09-01 |  | 2022-08-31 |  | G | [10 empty] | 2023-08-01 |  | 2023-08-31 |  | G | [5 empty] | 2023-09-01 |  | 2024-07-31 |  | G | 2021-10-01 |  | 2022-06-30 |  | G | [5 empty] | 2024-09-03 |  | 2024-12-31 |  | G | 2025-01-02 |  | 2025-05-30 |  | G | Consultant contract is still in procurement | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.33587
1578 | 113759 | #SGR18VB - I77 over Cove Crk VA 2035&2036 Fed 19565&19566 | 0077 | Interstate | Bridge Replacement w/o Added Capacity | VDOT | Wythe County | WYTHEVILLE | Bristol | NonMPO:NonMPO | Infrastructure Investment/Asset Management Division | Gary Lester |  |  | Haven P Wright | Haven.Wright@VDOT.Virginia.gov | (276) 696-3393 |  |  |  | 0 |  | 0 | FY2021 | 17000000 | 16998784 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 7 days early | G | Project is on budget | [10 empty] | 2019-11-05 | 2017-10-27 | 2019-11-12 | 2017-10-27 | G | [35 empty] | 2020-03-10 | 2020-03-10 | 2020-03-10 | 2020-03-10 | G | 2020-07-21 | 2020-07-14 | 2020-07-21 | 2020-07-14 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.068454
1579 | 113781 | RTE. 856 - RURAL RUSTIC RD (SURFACE TREAT NONHARDSURFACE RD) | 0856 | Secondary | Reconstruction w/o Added Capacity | VDOT | Albemarle County | CHARLOTTESVILLE | Culpeper | NonMPO:NonMPO | Infrastructure Investment Division | Ken Connors |  |  | Harold L Jones | Harold.Jones@VDOT.virginia.gov | (434) 422-9378 |  |  |  | 0 |  | 0 | FY2024 | 70000 | 70000 | NO DATES SET YET | G | Start Development milestone is 235 days ahead of the expected completion date | Y | Estimate not current | [5 empty] | 2021-10-01 |  | 2021-10-14 |  | G | 2021-10-15 |  | 2022-06-13 |  | G | [5 empty] | 2023-02-22 |  | 2023-04-04 |  | G | [5 empty] | 2023-07-19 |  | 2023-11-09 |  | G | [5 empty] | 2023-07-03 |  | 2023-10-03 |  | G | [5 empty] | 2023-11-14 |  | 2023-11-14 |  | G | 2024-02-09 |  | 2024-02-09 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | SAAP CONTRACT | 0 | 0 | 0.15574
1580 | 113820 | Harpersville Road Sidewalk | 0965 | Urban | Facilities for Pedestrians and Bicycles | Locally | Newport News | WILLIAMSBURG | Hampton Roads | Hampton Roads:Newport News | Infrastructure Investment Division | Susan Wilson | Susan.Wilson@vdot.virginia.gov | (757) 956-3099 | Chessica Villaflores | Chessica.Villaflores@vdot.virginia.gov | (757) 956-3094 | Bryan Stilley, P.E. | bstilley@nnva.gov | (757) 926-8699 | 0 |  | 0 | FY2025 | 1272600 | 1272600 | NO DATES SET YET | G | Agreement with Locality milestone is 222 days ahead of the expected completion date | G | Project is on budget | 2021-07-01 |  | 2021-10-01 |  | G | 2021-10-04 |  | 2021-10-15 |  | G | 2021-10-19 |  | 2022-04-28 |  | G | [10 empty] | 2023-05-02 |  | 2023-05-22 |  | G | [5 empty] | 2023-05-24 |  | 2024-03-07 |  | G | 2022-06-06 |  | 2023-02-10 |  | G | [5 empty] | 2024-03-25 |  | 2024-04-19 |  | G | 2024-07-10 |  | 2024-07-10 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.25654
1581 | 113892 | State Route 72 Scott County Rumble Strips | 0072 | Primary | Safety | VDOT | Scott County | WISE | Bristol | Kingsport:Scott County | Infrastructure Investment Division | Joseph Mullins | Joseph.Mullins@vdot.virginia.gov | (276) 321-6463 | Jonathan A Henegar | Jonathan.Henegar@vdot.virginia.gov | (276) 206-0360 |  |  |  | 0 |  | 0 | FY2021 | 233560 | 233560 | ACTIVITY DATES SET | R | Relocate Utilities milestone is 4 days past the expected completion date | G | Project is on budget | [5 empty] | 2018-10-31 | 2018-10-31 | 2018-11-14 | 2018-11-06 | G | 2018-11-15 | 2018-11-07 | 2019-07-11 | 2020-02-26 | R | [5 empty] | 2020-04-24 | 2020-04-24 | 2020-06-05 | 2020-06-05 | G | [5 empty] | 2020-10-20 |  | 2021-02-17 |  | R | [15 empty] | 2021-03-09 |  | 2021-03-09 |  | Y | 2021-05-27 |  | 2021-05-27 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.067919
1582 | 114056 | RTE. 630 RURAL RUSTIC ROAD (SURFACE TREAT NON-HARDSURFACE RD | 0630 | Secondary | Reconstruction w/o Added Capacity | VDOT | Orange County | LOUISA | Culpeper | NonMPO:NonMPO | Infrastructure Investment Division | Ken Connors |  |  | Bethel Kefyalew | Bethel.Kefyalew@vdot.virginia.gov | (540) 603-6015 |  |  |  | 0 |  | 0 | FY2024 | 403000 | 403000 | NO DATES SET YET | G | Start Development milestone is 235 days ahead of the expected completion date | Y | Estimate not current | [5 empty] | 2021-10-01 |  | 2021-10-14 |  | G | 2021-10-15 |  | 2022-06-13 |  | G | [5 empty] | 2023-02-22 |  | 2023-04-04 |  | G | [5 empty] | 2023-07-19 |  | 2023-11-09 |  | G | [5 empty] | 2023-07-03 |  | 2023-10-03 |  | G | [5 empty] | 2023-11-14 |  | 2023-11-14 |  | G | 2024-02-09 |  | 2024-02-09 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | SAAP CONTRACT | 0 | 0 | 0.094467
1583 | 114766 | PEDESTRIAN SIGNAL UPGRADES - TOWN OF VINTON | 9999 | Primary | Safety | VDOT | Vinton | SALEM | Salem | Roanoke:Vinton | Infrastructure Investment Division | Bernard S Grinnell | Sean.Grinnell@VDOT.Virginia.gov | (540) 375-0148 | Bernard S Grinnell | Sean.Grinnell@VDOT.Virginia.gov | (540) 375-0148 |  |  |  | 0 |  | 0 | FY2020 | 260500 | 260500 | CONSTRUCTION STARTED | R | Start Delivery milestone finished 18 days late | G | Project is on budget | [5 empty] | 2019-02-05 | 2019-04-15 | 2019-02-05 | 2019-04-15 | R | 2019-02-06 | 2019-04-04 | 2019-05-15 | 2019-06-26 | R | [5 empty] | 2019-08-01 | 2019-08-01 | 2019-08-14 | 2019-08-14 | G | [25 empty] | 2019-08-30 | 2019-07-02 | 2019-09-06 | 2019-07-25 | G | 2019-09-09 | 2019-10-01 | 2019-09-13 | 2019-10-01 | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | WORK/TASK ORDER | 1 | 0 | 0.17968
1584 | 115305 | #SGR20LP - Primary Extension - C'burg - Radford St NW | 0011 | Urban | Reconstruction w/o Added Capacity | Locally | Christiansburg | CHRISTIANSBURG | Salem | New River Valley:Christiansburg | Local Assistance Division | Adam J Czesnowski | Adam.Czesnowski@vdot.virginia.gov | (540) 541-1216 | Adam J Czesnowski | Adam.Czesnowski@vdot.virginia.gov | (540) 541-1216 | Justin St. Clair | jstclair@christiansburg.org | (540) 382-6120 | 0 |  | 0 | FY2020 | 260368 | 260368 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 155 days early | G | Project is on budget | 2020-01-02 | 2019-07-01 | 2020-03-30 | 2019-08-07 | G | 2020-03-31 | 2019-09-03 | 2020-04-02 | 2019-09-05 | G | 2020-04-03 | 2019-09-19 | 2020-10-06 | 2019-09-20 | G | [35 empty] | 2019-12-31 | 2019-11-22 | 2019-12-31 | 2019-11-24 | G | 2020-01-27 | 2019-11-25 | 2020-06-30 | 2020-01-27 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.08797
1585 | 115509 | #SMART20 Route 171 capacity enhancements BTW Rts. 134 & 1740 | 0171 | Urban | Safety | VDOT | York County | WILLIAMSBURG | Hampton Roads | Hampton Roads:York County | Infrastructure Investment Division | Kenneth Wynne |  |  | Kenneth Wynne |  |  | Timothy Cross | tcross@yorkcounty.gov | (757) 890-3496 | 1 | 2020 | 0 | FY2028 | 3630000 | 3630000 | NO DATES SET YET | G | Start Development milestone is 1016 days ahead of the expected completion date | Y | Estimate not current | [5 empty] | 2023-10-03 |  | 2023-12-04 |  | G | 2023-12-05 |  | 2024-12-05 |  | G | [5 empty] | 2025-10-08 |  | 2025-10-22 |  | G | 2027-02-03 |  | 2027-02-17 |  | G | 2027-07-12 |  | 2028-01-20 |  | G | 2027-03-05 |  | 2027-09-07 |  | G | 2026-07-17 |  | 2027-01-27 |  | G | [5 empty] | 2028-02-08 |  | 2028-02-08 |  | G | 2028-04-28 |  | 2028-04-28 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.16166
1586 | 117110 | #SGR21VB (FED ID 3017) Brid Repl/I77 over Rte. 606 | 0077 | Interstate | Bridge Replacement w/o Added Capacity | VDOT | Bland County | WYTHEVILLE | Bristol | NonMPO:NonMPO | Infrastructure Investment/Asset Management Division | Gary Lester |  |  | Jason A Graham | Jason.Graham@vdot.virginia.gov | (276) 696-3383 |  |  |  | 0 |  | 1 | FY2027 | 15931700 | 15931700 | NO DATES SET YET | G | Start Development milestone is 243 days ahead of the expected completion date | G | Project is on budget | [5 empty] | 2021-10-01 |  | 2021-10-22 |  | G | 2021-10-25 |  | 2023-01-10 |  | G | [5 empty] | 2024-02-08 |  | 2024-03-21 |  | G | 2025-04-11 |  | 2025-05-15 |  | G | 2025-12-08 |  | 2026-04-10 |  | G | 2025-06-09 |  | 2025-12-30 |  | G | 2025-05-12 |  | 2026-01-15 |  | G | [5 empty] | 2026-04-14 |  | 2026-04-14 |  | G | 2026-07-02 |  | 2026-07-02 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.067489
1587 | 118034 | #81 CIP DETOUR IMPROVEMENTS - SIGNAL COMMS SALEM DIST. | 9999 | Primary | Traffic Management/Engineering | VDOT | Roanoke County | SALEM | Salem | Roanoke:Roanoke County | Infrastructure Investment Division | Bernard S Grinnell | Sean.Grinnell@VDOT.Virginia.gov | (540) 375-0148 | Michael Dalmolin | Michael.Dalmolin@vdot.virginia.gov | (540) 375-0157 |  |  |  | 0 |  | 0 | FY2021 | 450000 | 450000 | ACTIVITY DATES SET | G | Determine Requirements milestone finished 2 days early | G | Project is on budget | [10 empty] | 2020-09-01 | 2020-09-01 | 2021-01-13 | 2021-01-11 | G | [35 empty] | 2021-05-03 |  | 2021-05-07 |  | G | 2021-05-10 |  | 2021-05-14 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | WORK/TASK ORDER | 0 | 0 | 0.15103
1588 | 118348 | #SGR21VB(FED ID 06272) SUPERSTR REPL RTE 29 NB OVER CUB RUN | 0029 | Primary | Bridge Rehab w/o Added Capacity | VDOT | Fairfax County | FAIRFAX | Northern Virginia | Northern Virginia:Fairfax County | Infrastructure Investment Division | Gary Runco | Gary.Runco@vdot.virginia.gov | (703) 259-3341 | Sharif Ramsis | Sharif.Ramsis@vdot.virginia.gov | (703) 259-2607 |  |  |  | 0 |  | 0 | FY2024 | 4382702 | 4382702 | NO DATES SET YET | R | Start Development milestone is 132 days past the expected completion date | G | Project is on budget | [5 empty] | 2020-09-22 |  | 2020-10-12 |  | R | 2020-10-13 |  | 2021-08-17 |  | G | [5 empty] | 2022-01-18 |  | 2022-02-14 |  | G | [15 empty] | 2022-09-08 |  | 2023-02-13 |  | G | [5 empty] | 2023-05-09 |  | 2023-05-09 |  | G | 2023-07-28 |  | 2023-07-28 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.090096
1589 | 102866 | Cunningham Drive Sidewalk Project | 0152 | Urban | Facilities for Pedestrians and Bicycles | Locally | Hampton | WILLIAMSBURG | Hampton Roads | Hampton Roads:Hampton | Infrastructure Investment Division | Stephen Rowan | Steve.Rowan@vdot.virginia.gov | (757) 790-9925 | Derrick Williams | Derrick.Williams@vdot.virginia.gov | (757) 956-3097 | Sandon Rogers, P.E. | Sandon.rogers@hampton.gov | (757) 727-6786 | 0 |  | 0 | FY2023 | 920000 | 920000 | NO DATES SET YET | R | Start Development milestone is 159 days past the expected completion date | G | Project is on budget | [5 empty] | 2020-09-01 |  | 2020-09-15 |  | R | 2020-09-16 |  | 2021-09-16 |  | G | [10 empty] | 2021-09-17 |  | 2021-10-05 |  | G | [20 empty] | 2022-09-09 |  | 2022-10-21 |  | G | 2022-11-22 |  | 2023-04-05 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.21967
1590 | 113877 | #SGR19LB??- Pisgah Rd / Fairground Ck Taz VA 8001 Fed 22539 | 0000 | Urban | Bridge Replacement w/o Added Capacity | VDOT | Tazewell | LEBANON | Bristol | NonMPO:NonMPO | Infrastructure Investment/Asset Management Division | Gary Lester |  |  | Emily V Collins | Emily.Collins@vdot.virginia.gov | (276) 696-3394 |  |  |  | 0 |  | 1 | FY2021 | 838315 | 804625 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 6 days early | G | Project is on budget | [5 empty] | 2019-11-25 | 2018-09-11 | 2019-12-10 | 2018-09-24 | G | 2019-12-11 | 2019-05-17 | 2020-03-10 | 2020-04-27 | R | [35 empty] | 2020-06-09 | 2020-06-09 | 2020-06-09 | 2020-06-09 | G | 2020-09-08 | 2020-09-02 | 2020-09-08 | 2020-09-02 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.053253
1591 | 113993 | CONSTRUCT SIDEWALK ON DEACON ROAD | 0607 | Secondary | Facilities for Pedestrians and Bicycles | VDOT | Stafford County | FREDERICKSBURG | Fredericksburg | Fredericksburg:Stafford County | Infrastructure Investment Division | Peter A Hedrich | Peter.Hedrich@vdot.virginia.gov | (540) 899-4540 | Catherine C Coffey | Catherine.Coffey@vdot.virginia.gov | (540) 899-4280 |  |  |  | 0 |  | 0 | FY2028 | 1050000 | 1050000 | NO DATES SET YET | G | Start Development milestone is 953 days ahead of the expected completion date | Y | Estimate not current | [5 empty] | 2023-09-19 |  | 2023-10-02 |  | G | 2023-10-03 |  | 2024-05-10 |  | G | [5 empty] | 2025-03-19 |  | 2025-04-01 |  | G | 2026-04-03 |  | 2026-04-16 |  | G | 2026-11-05 |  | 2027-05-17 |  | G | 2026-05-04 |  | 2026-11-05 |  | G | 2025-09-10 |  | 2026-03-23 |  | G | [5 empty] | 2027-06-08 |  | 2027-06-08 |  | G | 2027-08-27 |  | 2027-08-27 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.075812
1592 | 114065 | UR 6044 - PEDESTRIAN IMPROVEMENTS (OLD FOREST ROAD) | 6044 | Urban | Safety | Locally | Lynchburg | APPOMATTOX | Lynchburg | Lynchburg:Lynchburg | Infrastructure Investment Division | Gregg Allen | Gregg.Allen@vdot.virginia.gov | (434) 426-5575 | Gregg Allen | Gregg.Allen@vdot.virginia.gov | (434) 426-5575 | Don DeBerry | donald.deberry@lynchburgva.gov | (434) 455-3935 | 0 |  | 0 | FY2024 | 1281282 | 1281282 | NO DATES SET YET | G | Agreement with Locality milestone is 64 days ahead of the expected completion date | G | Project is on budget | 2021-02-01 |  | 2021-04-26 |  | G | 2021-04-27 |  | 2021-04-29 |  | G | 2021-04-30 |  | 2021-11-03 |  | G | [10 empty] | 2022-08-30 |  | 2022-09-20 |  | G | [5 empty] | 2022-09-22 |  | 2023-07-06 |  | G | 2021-12-14 |  | 2022-08-17 |  | G | [5 empty] | 2023-07-24 |  | 2023-08-18 |  | G | 2023-11-08 |  | 2023-11-08 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.19353
1593 | 114827 | #SMART20 - ROUTE 50 CORRIDOR IMPROVEMENTS | 0050 | Primary | Traffic Management/Engineering | VDOT | Loudoun County | LEESBURG | Northern Virginia | Northern Virginia:Loudoun County | Infrastructure Investment Division | Kimberly Mccool | Kimberly.McCool@vdot.virginia.gov | (703) 259-3220 | William C Britt | Calvin.Britt@VDOT.Virginia.gov | (703) 259-2961 |  |  |  | 1 | 2020 | 0 | FY2024 | 5000000 | 5000000 | NO DATES SET YET-PE OPEN | R | Determine Requirements milestone is 284 days past the expected completion date | G | Project is on budget | 2019-07-01 | 2019-07-01 | 2020-01-08 | 2020-07-29 | R | 2019-06-03 | 2019-04-05 | 2019-06-14 | 2019-04-05 | G | 2019-06-17 | 2020-02-12 | 2020-05-13 |  | R | [5 empty] | 2021-03-22 |  | 2021-04-02 |  | G | 2022-07-08 |  | 2022-07-21 |  | G | 2022-12-16 |  | 2023-06-23 |  | G | 2022-08-08 |  | 2023-02-16 |  | G | 2021-12-23 |  | 2022-06-30 |  | G | [5 empty] | 2023-07-11 |  | 2023-07-11 |  | G | 2023-09-29 |  | 2023-09-29 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.15719
1594 | 115367 | City of Williamsburg 2089 Capitol Landing Road & Merrimac Tr | 0143 | Urban | Restoration and Rehabilitation | Locally | Williamsburg | WILLIAMSBURG | Hampton Roads | Hampton Roads:Williamsburg | Local Assistance Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Chessica Villaflores | Chessica.Villaflores@vdot.virginia.gov | (757) 956-3094 | Aaron B. Small, P.E. | asmall@williamsburgva.gov | (757) 220-6140 | 0 |  | 0 | FY2020 | 226440 | 281075 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 92 days early | Y | Project estimate is less than $5M and is up to 20% over budget | 2019-11-04 | 2019-11-04 | 2020-02-04 | 2020-01-22 | G | [5 empty] | 2019-11-04 | 2019-11-04 | 2019-11-18 | 2019-11-18 | G | [35 empty] | 2020-05-11 | 2020-03-05 | 2020-06-08 | 2020-03-05 | G | 2020-06-30 | 2020-03-30 | 2020-06-30 | 2020-03-30 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.11636
1595 | 115723 | INSTALLATION OF FLASHING YELLOW ARROWS - DW (CN-ONLY) | 9999 | Primary | Safety | VDOT | Richmond District-wide |  | Richmond | Richmond:Richmond District-wide | Infrastructure Investment Division | Adam S Brooks | Adam.Brooks@VDOT.Virginia.gov | (804) 609-5274 | Adam S Brooks | Adam.Brooks@VDOT.Virginia.gov | (804) 609-5274 |  |  |  | 0 |  | 0 | FY2021 | 600000 | 600000 | ACTIVITY DATES SET | Y | Solicit Bids milestone is 24 days ahead of the expected completion date and there is a risk of missing this milestone date | G | Project is on budget | [10 empty] | 2020-02-03 | 2020-02-03 | 2020-06-09 | 2020-05-27 | G | [35 empty] | 2021-03-11 |  | 2021-03-17 |  | Y | 2021-03-18 |  | 2021-03-24 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | WORK/TASK ORDER | 0 | 0 | 0.066199
1596 | 117133 | Pedestrian Improvements-Warwick Blvd to Bland Blvd South | 0000 | Urban | Facilities for Pedestrians and Bicycles | Locally | Newport News | WILLIAMSBURG | Hampton Roads | Hampton Roads:Newport News | Local Assistance Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Chessica Villaflores | Chessica.Villaflores@vdot.virginia.gov | (757) 956-3094 | Bridjette Parker | parkerbj1@nnva.gov | (757) 926-8314 | 0 |  | 0 | FY2024 | 2800000 | 2800000 | NO DATES SET YET | Y | Agreement with Locality milestone is 11 days ahead of the expected completion date and there is a risk of missing this milestone date | G | Project is on budget | 2020-10-20 |  | 2021-03-04 |  | Y | 2021-03-05 |  | 2021-03-25 |  | G | 2021-09-29 |  | 2022-01-28 |  | G | [10 empty] | 2023-05-18 |  | 2023-06-22 |  | G | [5 empty] | 2023-06-23 |  | 2023-11-22 |  | G | 2023-10-19 |  | 2024-03-25 |  | G | [5 empty] | 2024-03-04 |  | 2024-03-29 |  | G | 2024-06-18 |  | 2024-06-18 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.22264
1597 | 118295 | #SGR21LB - DAIRY ROAD OVER RTE 250 BYPASS (FED ID 20073) | 9999 | Urban | Bridge Replacement w/o Added Capacity | Locally | Charlottesville | CHARLOTTESVILLE | Culpeper | Charlottesville:Charlottesville | Infrastructure Investment Division | Gregory J Cooley | Gregory.Cooley@vdot.virginia.gov | (434) 906-7979 | Michael D Barnes | MichaelD.Barnes@vdot.virginia.gov | (434) 422-9861 | TONY EDWARDS | EDWARDST@CHARLOTTESVILLE.ORG | (434) 970-3992 | 0 |  | 1 | FY2024 | 7210664 | 7210664 | NO DATES SET YET | Y | Agreement with Locality milestone is 25 days ahead of the expected completion date and there is a risk of missing this milestone date | G | Project is on budget | 2020-11-03 |  | 2021-03-18 |  | Y | 2021-03-19 |  | 2021-04-08 |  | G | 2021-10-13 |  | 2022-02-11 |  | G | [25 empty] | 2023-02-08 |  | 2023-07-07 |  | G | [5 empty] | 2023-09-05 |  | 2023-10-02 |  | G | 2023-12-26 |  | 2023-12-26 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.12361
1598 | 140430 | Bridge Repl-Rte 211/522 over N Frk Thrntn Rvr (Fed ID 14633) | 0211 | Primary | Bridge Replacement w/o Added Capacity | VDOT | Rappahannock County | WARRENTON | Culpeper | NonMPO:NonMPO | Infrastructure Investment Division | Dewitt D Sprinkel | Brent.Sprinkel@VDOT.Virginia.gov | (540) 829-7552 | Howard M Tomlinson | Howard.Tomlinson@VDOT.virginia.gov | (540) 829-7436 |  |  |  | 0 |  | 0 | FY2019 | 2425000 | 2116005 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 66 days early | G | Project is on budget | [5 empty] | 2016-10-01 | 2016-09-21 | 2016-10-01 | 2016-09-30 | G | 2016-10-31 | 2016-10-15 | 2017-12-28 | 2017-11-30 | G | [35 empty] | 2018-05-08 | 2018-05-08 | 2018-05-08 | 2018-05-08 | G | 2018-09-20 | 2018-07-16 | 2018-09-20 | 2018-07-16 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.059119
1599 | 107022 | RTE 50 - SAFETY IMPROVEMENTS | 0050 | Primary | Safety | VDOT | Frederick County | EDINBURG | Staunton | Winchester:Frederick County | Infrastructure Investment Division | Keith M Rider | Keith.Rider@VDOT.Virginia.gov | (434) 856-8145 | Kunal Kothawade | Kunal.Kothawade@vdot.virginia.gov | (540) 332-9259 |  |  |  | 0 |  | 0 | FY2022 | 4800000 | 4800000 | ACTIVITY DATES SET | G | Determine Requirements milestone finished 5 days early | G | Project is on budget | [5 empty] | 2019-09-30 | 2019-08-07 | 2019-10-11 | 2019-08-09 | G | 2019-10-14 | 2019-08-12 | 2019-11-12 | 2019-11-07 | G | [35 empty] | 2022-01-18 |  | 2022-01-18 |  | G | 2022-03-03 |  | 2022-03-23 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.06527
1600 | 108638 | RTE 1502 (Ivywood Rd.-Ken Dr.) - SPOT WIDENING | 1502 | Secondary | Reconstruction w/o Added Capacity | Locally | Chesterfield County | CHESTERFIELD | Richmond | Richmond:Chesterfield County | Local Assistance Division | Cynthia Crouch | Cynthia.Crouch@vdot.virginia.gov | (804) 609-5313 | Cynthia Crouch | Cynthia.Crouch@vdot.virginia.gov | (804) 609-5313 | Bill Arel | ArelB@chesterfield.gov | (804) 748-1998 | 0 |  | 0 | FY2021 | 4429998 | 6459506 | ADVERTISED | R | Start Delivery milestone is 174 days past the expected completion date | R | Project estimate is less than $5M and is 20% or more over budget | 2017-01-31 | 2016-10-06 | 2017-04-25 | 2016-10-06 | G | 2017-04-26 | 2016-12-08 | 2017-04-28 | 2016-12-08 | G | 2017-05-01 | 2016-07-12 | 2017-11-02 | 2017-12-20 | R | [10 empty] | 2018-08-29 | 2018-07-25 | 2018-09-19 | 2018-08-02 | G | 2019-07-15 | 2019-07-16 | 2020-07-31 | 2020-10-29 | R | 2018-09-21 | 2018-08-07 | 2019-07-05 | 2019-09-06 | R | [10 empty] | 2020-06-03 | 2020-12-18 | 2020-06-30 | 2020-12-18 | R | 2020-07-01 | 2020-12-21 | 2020-08-31 |  | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.33545
1601 | 109574 | #HB2.FY17 VIRGINIA CENTRAL RAILWAY TRAIL BRIDGE | 0000 | Miscellaneous | Special Bridge | Locally | Fredericksburg | FREDERICKSBURG | Fredericksburg | Fredericksburg:Fredericksburg | Infrastructure Investment Division | Anastasia Kapitan | Anastasia.Kapitan@vdot.virginia.gov | (540) 899-4292 | Anastasia Kapitan | Anastasia.Kapitan@vdot.virginia.gov | (540) 899-4292 | Doug Fawcett | dfawcett@fredericksburg.va.gov | 54037210 | 1 | 2017 | 0 | FY2019 | 160000 | 305000 | ADVERTISED | R | Start Delivery milestone is 852 days past the expected completion date | R | Project estimate is less than $5M and is 20% or more over budget | 2017-04-06 | 2017-02-15 | 2017-06-29 | 2017-06-29 | G | 2017-06-30 | 2017-06-29 | 2017-07-05 | 2017-07-12 | R | 2017-07-06 | 2017-07-12 | 2018-01-16 | 2017-08-23 | G | [35 empty] | 2018-08-03 | 2019-02-21 | 2018-09-11 | 2019-02-21 | R | 2018-09-12 |  | 2018-10-23 |  | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.1136
1602 | 111399 | PROVIDENCE DISTRICT BIKESHARE |  | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Fairfax County | FAIRFAX | Northern Virginia | Northern Virginia:Fairfax County | Local Assistance Division | Terry Yates | Terry.Yates@vdot.virginia.gov | (703) 259-2118 | Rhoderick M Undan | Rhoderick.Undan@vdot.virginia.gov | (703) 259-3347 | David Loss | David.Loss@fairfaxcounty.gov | (703) 877-5619 | 0 |  | 0 | FY2022 | 750000 | 750000 | NO DATES SET YET-PE OPEN | R | Determine Requirements milestone is 391 days past the expected completion date | G | Project is on budget | 2018-02-20 | 2018-02-20 | 2018-03-19 | 2018-03-19 | G | 2018-04-18 | 2018-04-18 | 2018-05-02 | 2018-05-02 | G | 2018-08-27 | 2018-08-27 | 2020-01-27 |  | R | [35 empty] | 2020-12-03 |  | 2021-04-30 |  | G | 2021-05-03 |  | 2021-09-30 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.2551
1603 | 111470 | #SMART18 - ONE LOUDOUN AND WESTERN LOUDOUN PARK & RIDE LOTS | 9999 | Secondary | Other | Locally | Loudoun County | LEESBURG | Northern Virginia | Northern Virginia:Loudoun County | Infrastructure Investment Division | Amir Salahshoor | A.Salahshoor@VDOT.Virginia.gov | (703) 259-1957 | Susie X Lue | Susie.Lue@vdot.virginia.gov | (703) 259-2918 | Tyler Cockrell | Tyler.Cockrell@loudoun.gov | (571) 258-3445 | 1 | 2018 | 0 | FY2020 | 7604400 | 7440756 | NO DATES SET YET-PE OPEN | R | Obtained Permits milestone is 788 days past the expected completion date | G | Project is on budget | 2017-06-16 | 2017-06-06 | 2017-12-18 | 2018-04-17 | R | 2017-12-19 | 2017-11-03 | 2017-12-21 | 2017-11-03 | G | 2018-05-02 | 2019-12-11 | 2019-05-02 |  | R | [5 empty] | 2023-04-25 |  | 2023-12-28 |  | G | [15 empty] | 2018-04-23 |  | 2018-12-26 |  | R | [5 empty] | 2019-04-04 |  | 2019-05-01 |  | R | 2019-05-02 |  | 2019-07-19 |  | R | Delay due to changes in scope of work, project management, plan designs, or resolution of public comments | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.33571
1605 | 112042 | ROUTE 1 IMPROVEMENTS: ASHCAKE RD TO ARBOR OAK DR | 0001 | Urban | Reconstruction w/ Added Capacity | VDOT | Ashland | ASHLAND | Richmond | Richmond:Ashland | Infrastructure Investment Division | William Wheeler | William.Wheeler@vdot.virginia.gov | (804) 609-5280 | William Wheeler | William.Wheeler@vdot.virginia.gov | (804) 609-5280 | Tom Dickerson | TDickerson@ashlandva.gov | (804) 752-6875 | 0 |  | 0 | FY2024 | 9944389 | 11311933 | ACTIVITY DATES SET | R | Start Purchasing Right-of-Way milestone is 198 days past the expected completion date | R | Project estimate is between $5M and $10M and is a $1M or more over budget | [5 empty] | 2017-12-15 | 2017-12-12 | 2017-12-29 | 2017-12-21 | G | 2018-01-02 | 2017-12-22 | 2018-10-24 | 2018-10-24 | G | [5 empty] | 2019-07-25 | 2019-07-25 | 2019-08-07 | 2019-08-07 | G | 2020-07-27 | 2020-11-20 | 2020-08-07 |  | R | 2021-09-27 |  | 2023-01-27 |  | G | 2020-08-25 |  | 2021-08-25 |  | G | 2019-12-09 | 2020-12-07 | 2022-06-03 |  | G | [5 empty] | 2023-03-14 |  | 2023-03-14 |  | G | 2023-06-15 |  | 2023-08-24 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.13024
1606 | 112602 | Grayson County Trail Phase III | 9999 | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Grayson County | WYTHEVILLE | Bristol | NonMPO:NonMPO | Local Assistance Division | John W Bechtold | John.Bechtold@vdot.virginia.gov | (276) 696-3365 | Roger L Musser | Roger.Musser@VDOT.Virginia.gov | (276) 696-3260 | Will Crawford | wcrawford@graysoncountyva.gov | (276) 773-2471 | 0 |  | 0 | FY2021 | 674938 | 674938 | ACTIVITY DATES SET | R | Solicit Bids milestone is 221 days past the expected completion date | G | Project is on budget | 2019-02-20 | 2018-03-01 | 2019-04-16 | 2018-07-05 | G | 2019-04-17 | 2018-07-06 | 2019-04-19 | 2018-08-03 | G | 2019-04-22 | 2018-08-06 | 2019-07-16 | 2019-07-08 | G | [35 empty] | 2020-05-27 | 2020-09-25 | 2020-07-15 |  | R | 2020-07-16 |  | 2020-09-15 |  | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.29299
1607 | 112781 | BRIDGE REPLACEMENT AND WIDENING JERMANTOWN ROAD OVER I66 | 0655 | Secondary | Bridge Replacement w/ Added Capacity | VDOT | Fairfax County | FAIRFAX | Northern Virginia | Northern Virginia:Fairfax County | Infrastructure Investment Division | Harinderbir S Warraich | HS.Warraich@VDOT.Virginia.gov | (571) 459-2362 | Harinderbir S Warraich | HS.Warraich@VDOT.Virginia.gov | (571) 459-2362 |  |  |  | 0 |  | 0 | FY2019 | 11000000 | 11000000 | AWARDED | G | Start Delivery milestone finished on-time | G | Project is on budget | [10 empty] | 2018-02-22 | 2018-02-22 | 2018-06-28 | 2018-06-28 | G | [35 empty] | 2018-07-02 | 2018-07-02 | 2018-07-09 | 2018-07-09 | G | 2018-07-10 | 2018-07-10 | 2018-07-18 | 2018-07-18 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | WORK/TASK ORDER | 1 | 0 | 0.098128
1608 | 113263 | Creighton Road Improvements and Sidewalk | 0000 | Urban | Reconstruction w/o Added Capacity | Locally | Henrico County | ASHLAND | Richmond | Richmond:Henrico County | Local Assistance Division | Cynthia Crouch | Cynthia.Crouch@vdot.virginia.gov | (804) 609-5313 | Cynthia Crouch | Cynthia.Crouch@vdot.virginia.gov | (804) 609-5313 | Kevin Newcomb | NEW038@henrico.us | (804) 501-5532 | 0 |  | 0 | FY2023 | 10405500 | 10405500 | NO DATES SET YET-PE OPEN | G | Complete Purchasing Right-of-Way milestone finished 1071 days early | G | Project is on budget | 2020-07-10 | 2019-07-10 | 2020-10-02 | 2019-11-08 | G | 2020-10-05 | 2019-11-11 | 2020-10-07 | 2019-11-15 | G | 2020-10-08 | 2019-11-18 | 2021-04-20 |  | G | [10 empty] | 2022-04-22 | 2020-03-24 | 2022-05-12 | 2020-03-24 | G | [5 empty] | 2022-05-16 | 2020-03-24 | 2023-02-28 | 2020-03-24 | G | 2021-05-26 |  | 2022-02-02 |  | G | [5 empty] | 2023-03-16 |  | 2023-04-12 |  | G | 2023-06-30 |  | 2023-06-30 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.26088
1609 | 113619 | LEESBURG PRIMARY EXTENSION PAVING FY19 - S. KING STREET | 0015 | Urban | Resurfacing | Locally | Leesburg | LEESBURG | Northern Virginia | Northern Virginia:Leesburg | Local Assistance Division | Amir Salahshoor | A.Salahshoor@VDOT.Virginia.gov | (703) 259-1957 | Rita Hockman | Rita.Hockman@vdot.virginia.gov | (804) 824-7421 | Tom Brandon | tbrandon@leesburgva.gov | (703) 737-6067 | 0 |  | 0 | FY2019 | 400000 | 400000 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 85 days early | G | Project is on budget | 2018-07-02 | 2018-07-02 | 2018-09-25 | 2018-09-04 | G | [5 empty] | 2018-09-26 | 2018-09-05 | 2018-11-28 | 2018-09-05 | G | [35 empty] | 2018-10-11 | 2018-10-16 | 2018-11-08 | 2018-10-16 | G | 2018-11-09 | 2018-10-16 | 2019-01-09 | 2018-10-16 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.29889
1610 | 108671 | Pedestrian Crosswalk Flasher - Berryville | 0340 | Primary | Safety | Locally | Berryville | EDINBURG | Staunton | NonMPO:NonMPO | Local Assistance Division | Kimberly Cameron | Kim.Cameron@vdot.virginia.gov | (540) 332-7886 | Kimberly Cameron | Kim.Cameron@vdot.virginia.gov | (540) 332-7886 | Christy Dunkle | townmanager@berryvilleva.gov | (540) 955-4081 | 0 |  | 0 | FY2019 | 27000 | 27000 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished on-time | G | Project is on budget | 2016-08-01 | 2016-08-01 | 2018-03-13 | 2018-07-25 | R | 2018-03-14 | 2018-07-26 | 2018-03-16 | 2018-07-30 | R | 2018-03-19 | 2018-07-31 | 2018-04-27 | 2018-09-11 | R | [10 empty] | 2019-01-25 | 2019-01-25 | 2019-01-25 | 2019-01-25 | G | [5 empty] | 2019-01-25 | 2019-01-25 | 2019-01-25 | 2019-01-25 | G | [10 empty] | 2019-02-11 | 2019-02-11 | 2019-03-11 | 2019-03-11 | G | 2019-03-12 | 2019-03-12 | 2019-04-19 | 2019-04-19 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.24107
1611 | 109953 | #SGR21LB (FED ID 30099) OAK STREET BRIGE REPLACEMENT | 9999 | Urban | Bridge Replacement w/o Added Capacity | Locally | Falls Church | FAIRFAX | Northern Virginia | Northern Virginia:Falls Church | Infrastructure Investment Division | Amir Salahshoor | A.Salahshoor@VDOT.Virginia.gov | (703) 259-1957 | Susie X Lue | Susie.Lue@vdot.virginia.gov | (703) 259-2918 | Susan Long | slong@fallschurchva.gov | (703) 248-5331 | 0 |  | 0 | FY2023 | 2436186 | 2319394 | ACTIVITY DATES SET | G | Engage Public milestone finished 208 days early | G | Project is on budget | 2016-08-10 | 2016-08-10 | 2017-02-02 | 2017-02-02 | G | 2016-11-04 | 2016-11-04 | 2016-11-08 | 2016-11-08 | G | 2017-05-17 | 2017-05-17 | 2019-04-11 | 2020-04-27 | R | 2020-02-13 | 2020-02-13 | 2021-03-17 | 2020-08-21 | G | [5 empty] | 2021-03-18 | 2021-01-14 | 2021-07-09 |  | G | [5 empty] | 2021-07-13 |  | 2022-01-28 |  | G | 2019-07-09 | 2019-07-16 | 2020-03-16 | 2019-07-17 | G | [5 empty] | 2022-08-04 |  | 2022-12-29 |  | G | 2022-12-30 |  | 2023-05-24 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.27576
1612 | 111469 | #SMART18 - BACKLICK RUN MULTIUSE PATH PHASE I | 9999 | Urban | Facilities for Pedestrians and Bicycles | Locally | Alexandria | FAIRFAX | Northern Virginia | Northern Virginia:Alexandria | Infrastructure Investment Division | Amir Salahshoor | A.Salahshoor@VDOT.Virginia.gov | (703) 259-1957 | Susie X Lue | Susie.Lue@vdot.virginia.gov | (703) 259-2918 | Daphne Kott | Daphne.Kott@alexandriava.gov | (703) 746-4055 | 1 | 2018 | 0 | FY2021 | 7162783 | 7162783 | CRITICAL DECISION NEEDED | R | Determine Requirements milestone is 874 days past the expected completion date | G | Project is on budget | 2017-10-12 | 2017-05-08 | 2018-01-11 | 2017-12-19 | G | 2018-01-16 | 2017-07-03 | 2018-01-18 | 2017-11-22 | G | 2018-02-01 |  | 2018-10-01 |  | R | 2020-06-15 |  | 2020-10-06 |  | R | [5 empty] | 2020-03-19 |  | 2020-03-19 |  | R | [5 empty] | 2020-03-23 |  | 2021-02-01 |  | R | 2020-10-14 |  | 2021-01-13 |  | R | [5 empty] | 2021-03-22 |  | 2021-04-16 |  | Y | 2021-04-19 |  | 2021-05-27 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.23974
1613 | 111544 | #SGR19LP - VIENNA PRIMARY EXT PAVING FY18 - NUTLEY STREET | 0243 | Urban | Resurfacing | Locally | Vienna | FAIRFAX | Northern Virginia | Northern Virginia:Vienna | Local Assistance Division | Amir Salahshoor | A.Salahshoor@VDOT.Virginia.gov | (703) 259-1957 | Rita Hockman | Rita.Hockman@vdot.virginia.gov | (804) 824-7421 | TBD |  |  | 0 |  | 1 | FY2019 |  |  | WAITING FINANCIAL CLOSURE | R | Determine Requirements milestone finished 148 days late | R | Critical information missing | 2017-07-03 | 2017-07-03 | 2017-10-25 | 2017-07-24 | G | [5 empty] | 2017-07-03 | 2017-07-03 | 2017-07-17 | 2017-12-12 | R | [35 empty] | 2017-12-13 | 2017-11-01 | 2018-06-29 | 2017-11-01 | G | 2018-07-02 | 2017-11-01 | 2018-08-10 | 2017-11-01 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.16235
1614 | 111674 | #SMART18 - WAXPOOL RD/LOUDOUN CTY PKWY INTERSECTION IMPROV | 0625 | Secondary | Reconstruction w/ Added Capacity | Locally | Loudoun County | LEESBURG | Northern Virginia | Northern Virginia:Loudoun County | Infrastructure Investment Division | Amir Salahshoor | A.Salahshoor@VDOT.Virginia.gov | (703) 259-1957 | Susie X Lue | Susie.Lue@vdot.virginia.gov | (703) 259-2918 | Suheili Perez-Jimenez | suheili.perez@loudoun.gov | (571) 258-3213 | 1 | 2018 | 0 | FY2023 | 5147160 | 10787196 | ACTIVITY DATES SET | R | Start Purchasing Right-of-Way milestone is 289 days past the expected completion date | R | Project estimate is between $5M and $10M and is a $1M or more over budget | 2017-09-01 | 2017-05-08 | 2017-11-30 | 2018-05-07 | R | 2019-02-08 | 2018-05-07 | 2019-02-12 | 2018-08-10 | G | 2019-02-13 | 2018-07-11 | 2019-08-16 | 2020-05-20 | R | [5 empty] | 2019-01-30 | 2019-01-30 | 2019-05-22 | 2020-01-30 | R | 2020-01-15 |  | 2020-05-08 |  | R | 2021-08-31 |  | 2022-11-30 |  | G | 2020-05-26 |  | 2021-08-30 |  | G | [10 empty] | 2022-05-03 |  | 2022-09-22 |  | G | 2022-09-23 |  | 2023-03-01 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.35309
1615 | 112482 | SIDEWALKS TO METRORAIL - KINSLEY RD BTW FREDERICK & DESALE | 9999 | Urban | Facilities for Pedestrians and Bicycles | Locally | Vienna | FAIRFAX | Northern Virginia | Northern Virginia:Vienna | Infrastructure Investment Division | Terry Yates | Terry.Yates@vdot.virginia.gov | (703) 259-2118 | Susie X Lue | Susie.Lue@vdot.virginia.gov | (703) 259-2918 | Dennis Johnson |  | (703) 255-6382 | 0 |  | 0 | FY2028 | 350001 | 350001 | NO DATES SET YET | G | Agreement with Locality milestone is 424 days ahead of the expected completion date | G | Project is on budget | 2021-07-01 |  | 2022-04-21 |  | G | 2022-04-22 |  | 2022-05-12 |  | G | 2023-03-07 |  | 2024-02-21 |  | G | [10 empty] | 2025-05-05 |  | 2025-08-26 |  | G | [5 empty] | 2025-08-28 |  | 2026-11-10 |  | G | 2025-08-27 |  | 2026-05-05 |  | G | [5 empty] | 2027-09-02 |  | 2027-12-30 |  | G | 2028-01-03 |  | 2028-05-24 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.17863
1616 | 112637 | RTE 693 - SURFACE TREAT UNPAVED ROAD | 0693 | Secondary | Resurfacing | VDOT | Goochland County | ASHLAND | Richmond | NonMPO:NonMPO | Infrastructure Investment Division | Phillip Frazer | Phillip.Frazer@vdot.virginia.gov | (804) 481-0906 | Phillip Frazer | Phillip.Frazer@vdot.virginia.gov | (804) 481-0906 |  |  |  | 0 |  | 0 | FY2019 | 10000 | 10000 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 119 days early | G | Project is on budget | [5 empty] | 2018-01-19 | 2018-01-18 | 2018-02-01 | 2018-01-31 | G | 2018-02-02 | 2018-02-01 | 2018-09-21 | 2018-02-14 | G | [5 empty] | 2018-02-14 | 2018-02-14 | 2018-02-14 | 2018-02-14 | G | [5 empty] | 2018-01-19 | 2018-01-19 | 2018-01-19 | 2018-01-19 | G | [15 empty] | 2018-04-10 | 2018-02-07 | 2018-04-10 | 2018-02-07 | G | 2018-05-24 | 2018-03-23 | 2018-07-20 | 2018-03-23 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NOT APPLICABLE | 1 | 0 | 0.078651
1618 | 113426 | Town of Lebanon Gateway Project |  | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Lebanon | LEBANON | Bristol | NonMPO:NonMPO | Local Assistance Division | John W Bechtold | John.Bechtold@vdot.virginia.gov | (276) 696-3365 | Kenneth R Plummer | KR.Plummer@VDOT.Virginia.gov | (276) 696-3261 | Mike Duty | mlduty@lebanonva.net | (276) 889-2701 | 0 |  | 0 | FY2021 | 183655 | 183655 | ACTIVITY DATES SET | R | Solicit Bids milestone is 24 days past the expected completion date | G | Project is on budget | 2021-08-02 | 2018-10-02 | 2021-10-26 | 2018-10-11 | G | 2021-10-27 | 2018-10-12 | 2021-10-29 | 2018-10-23 | G | 2021-11-01 | 2018-10-24 | 2022-05-11 | 2019-12-10 | G | [25 empty] | 2018-12-03 | 2018-12-03 | 2018-12-12 | 2018-12-12 | G | [5 empty] | 2020-12-29 |  | 2021-01-28 |  | R | 2021-04-19 |  | 2021-05-18 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.25438
1619 | 115107 | EAST BEVERLEY STREET - Primary Extension Paving |  | Urban | Resurfacing | Locally | Staunton | HARRISONBURG | Staunton | SAW:Staunton | Local Assistance Division | Donald F Komara | Donald.Komara@VDOT.Virginia.gov | (540) 434-2587 | Michael S Fulcher | Michael.Fulcher@VDOT.Virginia.gov | (540) 332-2243 | City of Staunton | yanceysc@ci.staunton.va.us | (540) 332-3892 | 0 |  | 0 | FY2020 | 32252 | 32252 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 89 days early | G | Project is on budget | 2019-08-01 | 2019-08-01 | 2019-10-25 | 2019-12-17 | R | [5 empty] | 2019-08-01 | 2019-08-01 | 2019-08-14 | 2019-08-14 | G | [25 empty] | 2019-08-15 | 2019-12-18 | 2019-12-30 | 2019-12-18 | G | [5 empty] | 2019-12-31 | 2020-01-06 | 2020-03-31 | 2020-03-31 | G | 2020-06-18 | 2020-04-01 | 2020-06-30 | 2020-04-02 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.062968
1620 | 115121 | #SMART20 BICYCLE/PEDESTRIAN IMPROVEMENTS ON RTE 17B-MAIN ST | 0017 | Primary | Facilities for Pedestrians and Bicycles | VDOT | Gloucester County | SALUDA | Fredericksburg | Hampton Roads:Gloucester County | Infrastructure Investment Division | Catherine C Coffey | Catherine.Coffey@vdot.virginia.gov | (540) 899-4280 | Anastasia Kapitan | Anastasia.Kapitan@vdot.virginia.gov | (540) 899-4292 |  |  |  | 1 | 2020 | 0 | FY2028 | 7300000 | 7300000 | NO DATES SET YET | G | Start Development milestone is 918 days ahead of the expected completion date | G | Project is on budget | [5 empty] | 2023-08-15 |  | 2023-08-28 |  | G | 2023-08-29 |  | 2024-07-26 |  | G | [5 empty] | 2025-06-03 |  | 2025-06-16 |  | G | 2026-09-21 |  | 2026-10-02 |  | G | 2027-03-05 |  | 2027-09-07 |  | G | 2026-10-21 |  | 2027-04-30 |  | G | 2026-03-12 |  | 2026-09-14 |  | G | [5 empty] | 2027-09-14 |  | 2027-09-14 |  | G | 2027-12-08 |  | 2027-12-08 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.088947
1621 | 115181 | #SMART20 I-81 Exit 317 Accel/Decel Lane Extensions | 0081 | Interstate | Reconstruction w/o Added Capacity | VDOT | Frederick County | EDINBURG | Staunton | Winchester:Frederick County | Infrastructure Investment Division | Randolph S Kiser | Randy.Kiser@VDOT.Virginia.gov | (540) 332-9092 | Anthony E Pelina | Anthony.Pelina@vdot.virginia.gov | (540) 332-9575 |  |  |  | 1 | 2020 | 0 | FY2028 | 3209056 | 3209056 | NO DATES SET YET | G | Start Development milestone is 904 days ahead of the expected completion date | G | Project is on budget | [5 empty] | 2023-08-01 |  | 2023-08-14 |  | G | 2023-08-15 |  | 2024-07-12 |  | G | [5 empty] | 2025-05-19 |  | 2025-06-02 |  | G | 2026-09-04 |  | 2026-09-18 |  | G | 2027-02-19 |  | 2027-08-23 |  | G | 2026-10-06 |  | 2027-04-16 |  | G | 2026-02-26 |  | 2026-08-28 |  | G | [5 empty] | 2027-09-14 |  | 2027-09-14 |  | G | 2027-12-08 |  | 2027-12-08 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.066907
1622 | 115313 | Narrows Lane Drainage Improvements | 0000 | Urban | Mitigation of Water Pollution Due to Highway Runof | Locally | Roanoke | SALEM | Salem | Roanoke:Roanoke City | Local Assistance Division | Cheryl B Becker | Cheryl.Becker@vdot.virginia.gov | (540) 492-2531 | Cheryl B Becker | Cheryl.Becker@vdot.virginia.gov | (540) 492-2531 | Joseph Arthur | Joseph.Arthur@roanokeva.gov | (540) 853-5906 | 0 |  | 0 | FY2021 | 425000 | 425000 | NO DATES SET YET-PE OPEN | R | Determine Requirements milestone is 319 days past the expected completion date | G | Project is on budget | 2019-06-28 | 2019-06-28 | 2019-09-23 | 2020-06-18 | R | 2019-09-24 | 2020-06-19 | 2019-09-26 | 2020-06-19 | R | 2019-09-27 |  | 2020-04-08 |  | R | [25 empty] | 2020-05-14 |  | 2021-01-21 |  | R | [5 empty] | 2021-02-18 |  | 2021-03-18 |  | Y | 2021-06-07 |  | 2021-06-07 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.20372
1623 | 115792 | Primary Extension - Roanoke - Hollins Rd NE | 0115 | Urban | Reconstruction w/o Added Capacity | Locally | Roanoke | SALEM | Salem | Roanoke:Roanoke City | Local Assistance Division | Cheryl B Becker | Cheryl.Becker@vdot.virginia.gov | (540) 492-2531 | Cheryl B Becker | Cheryl.Becker@vdot.virginia.gov | (540) 492-2531 | Mark Jamison | mark.jamison@roanokeva.gov | (540) 853-5471 | 0 |  | 0 | FY2020 | 190000 | 190000 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 141 days early | G | Project is on budget | 2020-01-02 | 2019-07-03 | 2020-03-30 | 2019-10-15 | G | 2020-03-31 | 2019-10-16 | 2020-04-02 | 2019-10-16 | G | 2020-04-03 | 2019-10-16 | 2020-10-06 | 2019-10-16 | G | [35 empty] | 2019-12-31 | 2019-11-15 | 2019-12-31 | 2019-11-18 | G | 2020-01-27 | 2019-12-12 | 2020-06-30 | 2020-02-10 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.17263
1624 | 116483 | LOUDOUN COUNTY ITS (DMS and CCTV) | 0050 | Primary | Traffic Management/Engineering | VDOT | Loudoun County | LEESBURG | Northern Virginia | Northern Virginia:Loudoun County | Infrastructure Investment Division | Timothy S Bean | Timothy.Bean@vdot.virginia.gov | (571) 350-2070 | Anwar A Ansari | Anwar.Ansari@VDOT.Virginia.gov | (703) 334-0204 | Evan Kuznear | Evan.Kuznear@loudoun.gov | (703) 771-5982 | 0 |  | 0 | FY2021 | 850000 | 850000 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 12 days early | G | Project is on budget | 2020-02-03 | 2020-02-03 | 2020-06-09 | 2020-07-08 | R | 2020-06-10 | 2020-06-09 | 2020-06-23 | 2020-06-09 | G | 2020-06-24 | 2020-07-08 | 2020-07-08 | 2020-07-08 | G | [5 empty] | 2020-08-13 | 2020-07-31 | 2020-08-19 | 2020-07-31 | G | [25 empty] | 2020-09-25 | 2020-09-25 | 2020-10-05 | 2020-10-01 | G | 2020-10-06 | 2020-10-02 | 2020-10-14 | 2020-10-02 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | WORK/TASK ORDER | 1 | 0 | 0.14856
1625 | 117135 | Traffic Signal-Jefferson Avenue and Wilcox Lane | 0143 | Urban | Other | Locally | Newport News | WILLIAMSBURG | Hampton Roads | Hampton Roads:Newport News | Local Assistance Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Chessica Villaflores | Chessica.Villaflores@vdot.virginia.gov | (757) 956-3094 | Bridjette Parker | parkerbj1@nnva.gov | (757) 926-8314 | 0 |  | 0 | FY2024 | 500000 | 500000 | NO DATES SET YET | Y | Agreement with Locality milestone is 11 days ahead of the expected completion date and there is a risk of missing this milestone date | G | Project is on budget | 2020-10-20 |  | 2021-03-04 |  | Y | 2021-03-05 |  | 2021-03-25 |  | G | 2021-09-29 |  | 2022-01-28 |  | G | [10 empty] | 2023-05-18 |  | 2023-06-22 |  | G | [5 empty] | 2023-06-23 |  | 2023-11-22 |  | G | 2023-10-19 |  | 2024-03-25 |  | G | [5 empty] | 2024-03-04 |  | 2024-03-29 |  | G | 2024-06-18 |  | 2024-06-18 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.2401
1626 | 118064 | State Route 161 Bike- Phase II |  | Urban | Facilities for Pedestrians and Bicycles | Locally | Richmond | ASHLAND | Richmond | Richmond:Richmond | Local Assistance Division | Jorg Huckabee-Mayfield | Jorg.Huckabee-Mayfield@VDOT.Virginia.gov | (804) 609-5292 | Jorg Huckabee-Mayfield | Jorg.Huckabee-Mayfield@VDOT.Virginia.gov | (804) 609-5292 | Jakob Helmboldt | jakob.helmboldt@richmondgov.com | (804) 646-7141 | 0 |  | 0 | FY2025 | 499778 | 499778 | NO DATES SET YET | G | Agreement with Locality milestone is 199 days ahead of the expected completion date | G | Project is on budget | 2021-05-03 |  | 2021-09-08 |  | G | 2021-09-09 |  | 2021-09-29 |  | G | 2022-04-13 |  | 2022-08-04 |  | G | [10 empty] | 2023-11-28 |  | 2024-01-03 |  | G | [5 empty] | 2024-01-04 |  | 2024-06-04 |  | G | 2024-05-01 |  | 2024-09-27 |  | G | [5 empty] | 2024-09-06 |  | 2024-10-03 |  | G | 2024-12-27 |  | 2024-12-27 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.16695
1627 | 87005 | Pulaski County - New River Trail Extension |  | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Pulaski County | CHRISTIANSBURG | Salem | NonMPO:NonMPO | Local Assistance Division | Anthony W Ford | Anthony.Ford@VDOT.Virginia.gov | (540) 378-5040 | Adam J Czesnowski | Adam.Czesnowski@vdot.virginia.gov | (540) 541-1216 | Jared Linkous | jlinkous@pulaskicounty.org | (540) 980-7710 | 0 |  | 0 | FY2019 | 2055437 | 1245389 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 21 days early | G | Project is on budget | [5 empty] | 2008-06-02 | 2008-08-28 | 2008-06-02 | 2008-08-28 | R | 2011-10-31 | 2009-03-03 | 2012-02-29 | 2017-04-19 | R | [10 empty] | 2018-02-28 | 2018-05-14 | 2018-05-25 | 2018-05-18 | G | [20 empty] | 2018-08-01 | 2018-10-04 | 2018-10-01 | 2018-11-11 | R | 2018-10-02 | 2019-03-04 | 2019-04-01 | 2019-03-11 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.36839
1628 | 104817 | BURWELL RD - UPGRADE GRAVEL RD TO PAVED FACILITY | 0604 | Secondary | Reconstruction w/o Added Capacity | Locally | Prince William County | MANASSAS | Northern Virginia | Northern Virginia:Prince William County | Infrastructure Investment Division | Claudia H Llana | Claudia.Llana@VDOT.Virginia.gov | (703) 259-1768 | Rita Hockman | Rita.Hockman@vdot.virginia.gov | (804) 824-7421 | Ludwik J. Kulczycki | lkulczycki@pwcgov.org | (703) 792-6347 | 0 |  | 0 | FY2019 | 955532 | 790381 | CONSTRUCTION COMPLETED | R | Start Delivery milestone finished 104 days late | G | Project is on budget | 2016-10-03 | 2016-10-03 | 2016-12-30 | 2017-01-04 | R | 2013-11-01 | 2013-10-16 | 2013-11-01 | 2013-10-17 | G | 2017-01-05 | 2017-01-17 | 2017-10-31 | 2017-12-14 | R | [10 empty] | 2018-02-28 | 2018-02-28 | 2018-02-28 | 2018-02-28 | G | [20 empty] | 2018-11-01 | 2018-11-01 | 2018-11-30 | 2019-07-12 | R | 2018-12-03 | 2019-07-15 | 2019-04-02 | 2019-07-15 | R | Delay due to unforeseen issues with utilities, railroad coordination, or right-of-way acquisition | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.33791
1629 | 106268 | HANGING ROCK BATTLEFIELD TRAIL - TRANSPORTATION ALTERNATIVES |  | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Salem | SALEM | Salem | Roanoke:Salem | Local Assistance Division | Anthony W Ford | Anthony.Ford@VDOT.Virginia.gov | (540) 378-5040 | Cheryl B Becker | Cheryl.Becker@vdot.virginia.gov | (540) 492-2531 | City of Salem |  |  | 0 |  | 0 | FY2021 | 1310890 | 818179 | ACTIVITY DATES SET | R | Solicit Bids milestone is 83 days past the expected completion date | G | Project is on budget | [5 empty] | 2014-10-01 | 2015-01-02 | 2015-03-17 | 2015-09-24 | R | 2015-03-18 | 2015-03-18 | 2018-02-28 | 2017-03-01 | G | [10 empty] | 2018-04-27 | 2018-04-26 | 2018-10-31 | 2018-04-26 | G | [20 empty] | 2020-10-16 |  | 2020-11-30 |  | R | 2020-12-01 |  | 2021-03-15 |  | Y |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.45869
1630 | 115132 | #SMART20 US 11 N(North Valley Pike) Sidewalk | 0011 | Primary | Facilities for Pedestrians and Bicycles | VDOT | Rockingham County | HARRISONBURG | Staunton | Harrisonburg:Rockingham County | Infrastructure Investment Division | Randolph S Kiser | Randy.Kiser@VDOT.Virginia.gov | (540) 332-9092 | Alexander Alvarado | Alexander.Alvarado@vdot.virginia.gov | (540) 332-7372 |  |  |  | 1 | 2020 | 0 | FY2025 | 3037558 | 3037558 | NO DATES SET YET-PE OPEN | R | Determine Requirements milestone is 97 days past the expected completion date | G | Project is on budget | [5 empty] | 2019-10-31 | 2019-09-02 | 2019-11-14 | 2019-09-16 | G | 2019-11-15 | 2019-11-15 | 2020-11-16 |  | R | [5 empty] | 2021-09-16 |  | 2021-09-29 |  | G | 2022-12-05 |  | 2022-12-16 |  | G | 2023-05-15 |  | 2023-11-17 |  | G | 2023-01-04 |  | 2023-07-11 |  | G | 2022-11-28 |  | 2023-08-01 |  | G | [5 empty] | 2023-12-12 |  | 2023-12-12 |  | G | 2024-03-07 |  | 2024-08-23 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.08749
1631 | 115247 | City of Hopewell 475 Arlington Road and S 15th Ave | 0036 | Urban | Resurfacing | Locally | Hopewell | PETERSBURG | Richmond | Tri-Cities:Hopewell | Local Assistance Division | James Shepherd | James.Shepherd@vdot.virginia.gov | (804) 609-5305 | Brian J Lokker | Brian.Lokker@VDOT.Virginia.gov | (804) 524-6010 | Austin Anderson | aanderson@hopewellva.gov | (804) 541-2379 | 0 |  | 0 | FY2020 | 377450 | 377450 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 76 days early | G | Project is on budget | 2019-07-01 | 2019-04-16 | 2019-09-24 | 2019-09-19 | G | [5 empty] | 2019-09-25 | 2019-09-25 | 2019-11-27 | 2019-11-21 | G | [25 empty] | 2019-11-22 | 2019-12-09 | 2020-02-04 | 2019-12-09 | G | [5 empty] | 2020-03-05 | 2020-02-28 | 2020-03-19 | 2020-03-10 | G | 2020-05-01 | 2020-03-10 | 2020-06-01 | 2020-03-17 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.049746
1632 | 115725 | #SGR20LP - RECONSTRUCTION -- WILLIAM STREET | 0003 | Urban | Reconstruction w/o Added Capacity | Locally | Fredericksburg | FREDERICKSBURG | Fredericksburg | Fredericksburg:Fredericksburg | Infrastructure Investment Division | Richard A Spurlock | Richard.Spurlock@VDOT.Virginia.gov | (540) 899-4302 | Richard A Spurlock | Richard.Spurlock@VDOT.Virginia.gov | (540) 899-4302 | Erik Nelson | enelson@fredericksburgva.gov | (540) 372-1080 | 0 |  | 1 | FY2021 | 350000 | 349999 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 30 days early | G | Project is on budget | 2019-07-15 | 2018-08-15 | 2019-10-07 | 2018-10-23 | G | [5 empty] | 2019-07-15 | 2019-07-15 | 2019-07-26 | 2019-07-26 | G | [25 empty] | 2019-07-29 | 2019-07-29 | 2019-10-22 | 2019-07-29 | G | [5 empty] | 2020-04-08 | 2020-04-08 | 2020-05-05 | 2020-04-08 | G | 2020-07-24 | 2020-06-24 | 2020-07-24 | 2020-06-24 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.12113
1633 | 115850 | ITTF FY20 I-95 VSL Compliance Monitoring | 9999 | Interstate | Safety | VDOT | Statewide |  | Statewide | Multiple MPOs:Statewide | Infrastructure Investment Division | Catherine C Mcghee | Cathy.McGhee@VDOT.Virginia.gov | (434) 293-1973 | Teresa H Butler | Teresa.Butler@VDOT.Virginia.gov | (540) 229-3722 |  |  |  | 0 |  | 0 | FY2024 | 13100000 | 13100000 | NO DATES SET YET | G | Start Development milestone is 52 days ahead of the expected completion date | G | Project is on budget | [5 empty] | 2021-04-01 |  | 2021-04-14 |  | G | 2021-04-15 |  | 2021-12-07 |  | G | [5 empty] | 2022-08-12 |  | 2022-09-23 |  | G | [5 empty] | 2023-01-17 |  | 2023-05-09 |  | G | [5 empty] | 2022-12-28 |  | 2023-04-03 |  | G | [5 empty] | 2023-06-13 |  | 2023-06-13 |  | G | 2023-09-01 |  | 2023-09-01 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 1 | 0.31711
1634 | 117043 | Ridge Road Sidewalk | 7649 | Secondary | Facilities for Pedestrians and Bicycles | Locally | Henrico County | ASHLAND | Richmond | Richmond:Henrico County | Local Assistance Division | Cynthia Crouch | Cynthia.Crouch@vdot.virginia.gov | (804) 609-5313 | Cynthia Crouch | Cynthia.Crouch@vdot.virginia.gov | (804) 609-5313 | TBD |  | TBD | 0 |  | 0 | FY2029 | 2022298 | 2022298 | NO DATES SET YET | G | Agreement with Locality milestone is 1543 days ahead of the expected completion date | G | Project is on budget | 2025-01-06 |  | 2025-05-14 |  | G | 2025-05-15 |  | 2025-06-05 |  | G | 2025-12-15 |  | 2026-04-10 |  | G | [10 empty] | 2027-07-30 |  | 2027-09-02 |  | G | [5 empty] | 2027-09-03 |  | 2028-02-09 |  | G | 2028-01-05 |  | 2028-06-05 |  | G | [5 empty] | 2028-05-12 |  | 2028-06-09 |  | G | 2028-08-29 |  | 2028-08-29 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.35567
1635 | 117153 | #SGR21VP - 2021 Williamsburg Residency Plant Mix | 0143 | Primary | Resurfacing | VDOT | Multi-jurisdictional: Hampton Roads MPO |  | Hampton Roads | Hampton Roads:Multi-jurisdictional: Hampton Roads MPO | Infrastructure Investment Division | Andrew Mcgilvray | Andrew.McGilvray@vdot.virginia.gov | (757) 956-3171 | Andrew Mcgilvray | Andrew.McGilvray@vdot.virginia.gov | (757) 956-3171 |  |  |  | 0 |  | 1 | FY2021 | 1013295 | 1003283 | ADVERTISED | R | Solicit Bids milestone finished 13 days late | G | Project is on budget | [10 empty] | 2020-12-01 | 2020-06-15 | 2020-12-07 | 2020-10-07 | G | [35 empty] | 2021-01-13 | 2021-01-26 | 2021-01-13 | 2021-01-26 | R | 2021-05-26 |  | 2021-05-26 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.12097
1636 | 118303 | #SGR21VB - Rte 147 over I-195 - Minor Rehab - FED ID 21519 | 0014 | Primary | Bridge Rehab w/o Added Capacity | VDOT | Richmond | ASHLAND | Richmond | Richmond:Richmond | Infrastructure Investment/Asset Management Division | Roy Soto | Roy.Soto@vdot.virginia.gov | (804) 609-5239 | Roy Soto | Roy.Soto@vdot.virginia.gov | (804) 609-5239 |  |  |  | 0 |  | 1 | FY2026 | 11745468 | 11745468 | NO DATES SET YET | G | Start Development milestone is 578 days ahead of the expected completion date | G | Project is on budget | [5 empty] | 2022-09-01 |  | 2022-09-22 |  | G | 2022-09-23 |  | 2023-07-28 |  | G | [5 empty] | 2024-03-04 |  | 2024-03-29 |  | G | 2024-11-18 |  | 2024-12-24 |  | G | 2025-05-28 |  | 2025-09-25 |  | G | 2025-01-10 |  | 2025-06-11 |  | G | 2025-02-21 |  | 2025-07-21 |  | G | [5 empty] | 2025-10-14 |  | 2025-10-14 |  | G | 2026-01-08 |  | 2026-01-08 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.12256
1637 | 102739 | Shore Drive- Safety/Ped Improvements | 0060 | Urban | Facilities for Pedestrians and Bicycles | Locally | Virginia Beach | NORFOLK | Hampton Roads | Hampton Roads:Virginia Beach | Local Assistance Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Marci Thompson | Marci.Thompson@vdot.virginia.gov | (757) 956-3093 | Katie Shannon | KShannon@vbgov.com | (757) 385-1514 | 0 |  | 0 | FY2020 | 24400418 | 30761958 | ACTIVITY DATES SET | R | Solicit Bids milestone is 534 days past the expected completion date | R | Project estimate is greater than $10M and is over budget by (a) 10% or more or (b) $5M or more | [5 empty] | 2012-10-17 | 2012-10-17 | 2012-10-17 | 2012-10-17 | G | 2014-11-17 | 2014-11-17 | 2019-02-01 | 2018-07-18 | G | [10 empty] | 2017-12-01 | 2017-12-01 | 2017-12-15 | 2017-12-15 | G | [20 empty] | 2019-07-19 |  | 2019-09-06 |  | R | 2019-11-13 |  | 2020-02-12 |  | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.18208
1638 | 104994 | #SGR21VB - BR Repl-Water St over Beaver Dam Creek(Fed 19212) | 1203 | Secondary | Bridge Replacement w/o Added Capacity | VDOT | Washington County | ABINGDON | Bristol | NonMPO:NonMPO | Infrastructure Investment Division | Gary Lester |  |  | James R Jones | jamesr.jones@vdot.virginia.gov | (276) 696-3257 |  |  |  | 0 |  | 0 | FY2021 | 2187245 | 3019626 | ACTIVITY DATES SET | R | Solicit Bids milestone is 40 days past the expected completion date | R | Project estimate is less than $5M and is 20% or more over budget | [5 empty] | 2016-07-05 | 2015-12-07 | 2016-07-05 | 2015-12-11 | G | 2016-08-22 | 2016-08-22 | 2018-02-08 | 2018-02-08 | G | [5 empty] | 2018-08-29 | 2018-08-29 | 2018-09-25 | 2018-09-25 | G | 2019-05-21 | 2019-04-19 | 2019-05-21 | 2019-04-29 | G | 2020-09-30 | 2019-09-20 | 2020-12-01 | 2019-11-06 | G | 2019-06-19 | 2019-05-31 | 2020-09-29 | 2020-03-03 | G | 2019-10-11 | 2019-10-11 | 2020-09-29 | 2020-09-17 | G | [5 empty] | 2020-12-16 |  | 2021-01-12 |  | R | 2021-03-12 |  | 2021-04-22 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.064983
1639 | 107080 | 32ND STREET & A STREET INTERSECTION IMPROVEMENTS | 9999 | Secondary | Reconstruction w/o Added Capacity | Locally | Purcellville | LEESBURG | Northern Virginia | Northern Virginia:Purcellville | Local Assistance Division | Amir Salahshoor | A.Salahshoor@VDOT.Virginia.gov | (703) 259-1957 | Rita Hockman | Rita.Hockman@vdot.virginia.gov | (804) 824-7421 | Dale Lehnig | dlehnig@purcellvilleva.gov | (540) 751-2327 | 0 |  | 0 | FY2019 | 2170000 | 2170000 | WAITING FINANCIAL CLOSURE | R | Start Delivery milestone finished 69 days late | G | Project is on budget | 2015-07-01 | 2001-08-07 | 2015-09-24 | 2015-08-07 | G | 2015-09-25 | 2015-08-07 | 2015-10-08 | 2015-08-07 | G | 2015-10-09 | 2015-08-10 | 2016-06-08 | 2017-05-15 | R | [10 empty] | 2018-07-09 | 2018-07-09 | 2018-07-20 | 2018-07-20 | G | [20 empty] | 2018-08-23 | 2018-08-23 | 2018-12-19 | 2018-12-14 | G | 2018-12-20 | 2018-12-17 | 2018-12-20 | 2019-02-27 | R | Project is late due to a decision / action on the part of the locality (Board of Supervisors, Council, officials) | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.38063
1640 | 107796 | #HB2.FY17 RTE 95 - EXTEND NB DECEL LANE AT HERMITAGE RD | 0095 | Interstate | Reconstruction w/o Added Capacity | VDOT | Richmond | ASHLAND | Richmond | Richmond:Richmond | Infrastructure Investment Division | Phillip Frazer | Phillip.Frazer@vdot.virginia.gov | (804) 481-0906 | Lawrence Ramsey | Brian.Ramsey@VDOT.Virginia.gov | (804) 585-3579 |  |  |  | 1 | 2017 | 0 | FY2019 | 2720000 | 2627237 | CONSTRUCTION COMPLETED | R | Start Delivery milestone finished 43 days late | G | Project is on budget | [5 empty] | 2015-09-01 | 2015-07-01 | 2015-09-01 | 2015-07-27 | G | 2015-08-18 | 2015-08-18 | 2016-12-23 | 2016-12-22 | G | [5 empty] | 2017-01-12 | 2017-01-12 | 2017-02-15 | 2017-02-15 | G | 2017-09-07 | 2017-09-07 | 2017-09-21 | 2017-09-21 | G | [5 empty] | 2017-11-30 | 2017-11-30 | 2018-07-18 | 2018-06-18 | G | [10 empty] | 2019-01-08 | 2019-03-26 | 2019-01-08 | 2019-03-26 | R | 2019-03-26 | 2019-05-28 | 2019-04-15 | 2019-05-28 | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.082004
1641 | 108856 | Bicentennial Greenway | 0000 | Miscellaneous | Facilities for Pedestrians and Bicycles | Locally | Blacksburg | CHRISTIANSBURG | Salem | New River Valley:Blacksburg | Local Assistance Division | Adam J Czesnowski | Adam.Czesnowski@vdot.virginia.gov | (540) 541-1216 | Adam J Czesnowski | Adam.Czesnowski@vdot.virginia.gov | (540) 541-1216 | Randy Formica |  |  | 0 |  | 0 | FY2019 | 40000 | 40000 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 334 days early | G | Project is on budget | 2016-07-01 | 2016-07-01 | 2016-09-26 | 2016-08-24 | G | 2016-09-27 | 2016-08-25 | 2016-09-29 | 2016-10-07 | R | 2016-09-30 | 2016-11-07 | 2017-04-12 | 2017-11-15 | R | [35 empty] | 2018-10-03 | 2018-06-08 | 2018-11-15 | 2018-06-08 | G | 2018-11-16 | 2018-06-08 | 2019-05-15 | 2018-06-15 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.15867
1642 | 108955 | Corridor Retiming - Kempsville Rd & Newtown Area |  | Urban | Traffic Management/Engineering | Locally | Virginia Beach | NORFOLK | Hampton Roads | Hampton Roads:Virginia Beach | Infrastructure Investment Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Marci Thompson | Marci.Thompson@vdot.virginia.gov | (757) 956-3093 | Frank Hickman, PE |  |  | 0 |  | 0 | FY2024 | 521180 | 521180 | NO DATES SET YET | G | Agreement with Locality milestone is 219 days ahead of the expected completion date | G | Project is on budget | 2021-07-06 |  | 2021-09-28 |  | G | 2021-09-29 |  | 2021-10-12 |  | G | 2021-10-13 |  | 2022-10-13 |  | G | [35 empty] | 2023-08-25 |  | 2023-10-06 |  | G | 2023-10-09 |  | 2024-01-17 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.24334
1643 | 109988 | #SGR21VB -RT 715 - BR ONLY OVER NEWFOUND RIVER (Fed 9578) | 0715 | Secondary | Bridge Replacement w/ Added Capacity | VDOT | Hanover County | ASHLAND | Richmond | Richmond:Hanover County | Infrastructure Investment Division | William Wheeler | William.Wheeler@vdot.virginia.gov | (804) 609-5280 | William Wheeler | William.Wheeler@vdot.virginia.gov | (804) 609-5280 |  |  |  | 0 |  | 0 | FY2021 | 1535758 | 1758250 | ADVERTISED | R | Solicit Bids milestone finished 56 days late | Y | Project estimate is less than $5M and is up to 20% over budget | [5 empty] | 2016-09-01 | 2016-09-01 | 2016-09-15 | 2016-11-16 | R | 2016-09-16 | 2016-11-17 | 2017-08-15 | 2017-10-23 | R | [5 empty] | 2018-08-20 | 2018-04-06 | 2018-08-31 | 2018-07-05 | G | 2019-10-03 | 2019-03-14 | 2019-10-17 | 2019-03-14 | G | 2020-06-12 | 2019-09-13 | 2020-10-06 | 2020-01-14 | G | 2019-11-04 | 2019-05-28 | 2020-05-13 | 2019-09-12 | G | 2019-01-10 | 2019-08-12 | 2020-03-25 | 2019-11-26 | G | [5 empty] | 2020-10-13 | 2020-12-08 | 2020-10-13 | 2020-12-08 | R | 2020-12-08 |  | 2021-03-08 |  | Y |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.10001
1644 | 110826 | RTE 340 SHOULDER WIDENING & RUMBLE STRIPS | 0340 | Primary | Safety | VDOT | Augusta County | HARRISONBURG | Staunton | NonMPO:NonMPO | Infrastructure Investment/Asset Management Division | Keith M Rider | Keith.Rider@VDOT.Virginia.gov | (434) 856-8145 | Kunal Kothawade | Kunal.Kothawade@vdot.virginia.gov | (540) 332-9259 |  |  |  | 0 |  | 0 | FY2021 | 1800000 | 1800000 | AWARDED | R | Start Delivery milestone finished 36 days late | G | Project is on budget | [5 empty] | 2017-07-12 | 2017-07-12 | 2017-08-08 | 2017-08-08 | G | 2017-08-09 | 2017-08-09 | 2018-03-20 | 2018-03-13 | G | [35 empty] | 2020-10-13 | 2020-11-04 | 2020-10-13 | 2020-11-10 | R | 2020-12-01 | 2021-01-26 | 2020-12-21 | 2021-01-26 | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.11022
1645 | 111053 | #SMART18 - (St) RTE 11 & 704 INTERSECTION REALIGNMENT | 0011 | Primary | Reconstruction w/o Added Capacity | VDOT | Rockingham County | HARRISONBURG | Staunton | Harrisonburg:Rockingham County | Infrastructure Investment Division | Matthew P Dana | Matt.Dana@VDOT.Virginia.gov | (540) 332-7786 | Timothy Gregory | Tim.Gregory@vdot.virginia.gov | (540) 332-7891 |  |  |  | 1 | 2018 | 0 | FY2021 | 3475108 | 3028091 | ACTIVITY DATES SET | R | Start Purchasing Right-of-Way milestone is 482 days past the expected completion date | G | Project is on budget | [5 empty] | 2017-08-03 | 2017-07-24 | 2017-08-16 | 2017-08-03 | G | 2017-08-17 | 2017-08-04 | 2018-07-17 | 2018-02-01 | G | [5 empty] | 2018-11-29 | 2018-11-29 | 2018-12-27 | 2018-12-27 | G | 2019-10-14 |  | 2019-10-28 |  | R | 2020-03-30 |  | 2021-01-14 |  | R | 2019-11-14 |  | 2020-10-14 |  | R | 2019-05-01 |  | 2020-10-13 |  | R | [5 empty] | 2021-02-09 |  | 2021-02-09 |  | R | 2021-03-25 |  | 2021-06-10 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.084619
1646 | 111723 | LANGHORNE ROAD TRAIL EXTENSION |  | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Lynchburg | APPOMATTOX | Lynchburg | Lynchburg:Lynchburg | Local Assistance Division | Gregg Allen | Gregg.Allen@vdot.virginia.gov | (434) 426-5575 | Gregg Allen | Gregg.Allen@vdot.virginia.gov | (434) 426-5575 | David Owen | david.owen@lynchburgva.gov | (434) 455-5879 | 0 |  | 0 | FY2020 | 1314388 | 2000000 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 1 days early | R | Project estimate is less than $5M and is 20% or more over budget | 2017-08-14 | 2017-08-14 | 2017-09-29 | 2017-09-29 | G | 2017-10-02 | 2017-10-02 | 2017-10-27 | 2017-10-27 | G | 2018-01-05 | 2018-01-05 | 2018-08-09 | 2018-07-11 | G | [35 empty] | 2019-07-22 | 2019-07-22 | 2019-08-30 | 2019-08-30 | G | 2019-09-03 | 2019-09-03 | 2019-11-27 | 2019-11-26 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.26371
1647 | 112208 | WATERVIEW DRIVE-UPGRADE GRAVEL ROAD TO PAVED FACILITY | 0715 | Secondary | Reconstruction w/o Added Capacity | Locally | Prince William County | MANASSAS | Northern Virginia | Northern Virginia:Prince William County | Infrastructure Investment Division | Amir Salahshoor | A.Salahshoor@VDOT.Virginia.gov | (703) 259-1957 | Rita Hockman | Rita.Hockman@vdot.virginia.gov | (804) 824-7421 | Mo Ayyoubi | mayyoubi@pwcgov.org | (703) 792-7193 | 0 |  | 0 | FY2021 | 91000 | 70609 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 161 days early | G | Project is on budget | 2018-11-30 | 2018-03-27 | 2019-02-28 | 2018-05-23 | G | 2019-03-01 | 2018-05-24 | 2019-03-05 | 2018-12-18 | G | 2019-03-06 | 2018-12-19 | 2019-09-27 | 2019-06-24 | G | [35 empty] | 2019-11-19 | 2020-01-10 | 2020-04-01 | 2020-01-23 | G | 2020-04-02 | 2020-01-24 | 2020-08-07 | 2020-02-28 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.3342
1648 | 112657 | Rte 171 (Poquoson Ave) Sidewalk & Crosswalk Construction | 0171 | Urban | Safety | Locally | Poquoson | WILLIAMSBURG | Hampton Roads | Hampton Roads:Poquoson | Infrastructure Investment Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Chessica Villaflores | Chessica.Villaflores@vdot.virginia.gov | (757) 956-3094 | Ellen Roberts | ellen.roberts@poquoson-va.gov | (757) 868-3025 | 0 |  | 0 | FY2021 | 320408 | 320408 | ACTIVITY DATES SET | R | Solicit Bids milestone is 180 days past the expected completion date | G | Project is on budget | 2018-01-05 | 2018-01-05 | 2018-04-23 | 2018-04-23 | G | 2018-04-23 | 2018-04-23 | 2018-04-23 | 2018-04-23 | G | 2018-04-18 | 2018-04-18 | 2019-04-24 | 2019-08-19 | R | [35 empty] | 2020-06-30 |  | 2020-08-25 |  | R | 2020-08-26 |  | 2021-02-23 |  | Y |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.22286
1649 | 113223 | MOSEBY DRIVE CULVERT REPLACEMENT | 9999 | Urban | Bridge Replacement w/o Added Capacity | Locally | Manassas Park | MANASSAS | Northern Virginia | Northern Virginia:Manassas Park | Local Assistance Division | Claudia H Llana | Claudia.Llana@VDOT.Virginia.gov | (703) 259-1768 | Veljibhai M Desai | Veljibhai.Desai@vdot.virginia.gov | (703) 259-2927 | Calvin O'Dell | c.odell@manassasparkva.gov | (571) 221-4060 | 0 |  | 0 | FY2022 | 1644000 | 1644000 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 636 days early | Y | Estimate not current | 2018-11-15 | 2018-06-29 | 2019-04-30 | 2018-10-26 | G | [5 empty] | 2018-11-15 | 2019-05-31 | 2019-05-30 | 2020-03-13 | R | [10 empty] | 2020-06-02 | 2020-03-17 | 2020-06-29 | 2020-03-17 | G | 2020-09-23 | 2020-03-18 | 2021-06-29 | 2020-03-19 | G | 2020-06-30 | 2020-03-18 | 2021-06-29 | 2020-03-19 | G | 2020-06-02 | 2020-08-05 | 2020-12-24 | 2020-08-05 | G | [5 empty] | 2021-06-30 | 2020-03-20 | 2021-12-23 | 2020-08-26 | G | 2021-12-27 | 2020-08-27 | 2022-05-31 | 2020-09-02 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.1236
1650 | 108799 | Court/ Bart/ Pavilion Intersection Improvements | 0000 | Urban | Safety | Locally | Portsmouth | NORFOLK | Hampton Roads | Hampton Roads:Portsmouth | Infrastructure Investment Division | Susan Wilson | Susan.Wilson@vdot.virginia.gov | (757) 956-3099 | Marci Thompson | Marci.Thompson@vdot.virginia.gov | (757) 956-3093 | James Wright, P. E. | wrightj@portsmouthva.gov | (757) 393-8592 | 0 |  | 0 | FY2021 | 1323549 | 1634280 | ACTIVITY DATES SET | R | Solicit Bids milestone is 214 days past the expected completion date | Y | Project estimate is less than $5M and is up to 20% over budget | 2016-10-11 | 2016-10-11 | 2017-04-27 | 2017-04-27 | G | 2016-11-18 | 2016-11-18 | 2016-11-22 | 2016-11-22 | G | 2018-03-27 | 2018-03-27 | 2020-01-23 | 2019-11-12 | G | [35 empty] | 2020-05-27 |  | 2020-07-22 |  | R | 2020-07-23 |  | 2021-01-19 |  | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.20105
1651 | 108899 | #HB2.FY17 Multimodal Improvements along Boulevard | 8010 | Urban | Facilities for Pedestrians and Bicycles | Locally | Salem | SALEM | Salem | Roanoke:Salem | Infrastructure Investment Division | Cheryl B Becker | Cheryl.Becker@vdot.virginia.gov | (540) 492-2531 | Cheryl B Becker | Cheryl.Becker@vdot.virginia.gov | (540) 492-2531 | Will Simpson | wsimpson@salemva.gov | (540) 375-3032 | 1 | 2017 | 0 | FY2019 | 884880 | 770032 | CONSTRUCTION COMPLETED | R | Start Delivery milestone finished 377 days late | G | Project is on budget | 2016-07-06 | 2016-07-06 | 2016-08-23 | 2016-08-23 | G | 2016-08-24 | 2016-08-24 | 2016-08-25 | 2016-08-25 | G | 2016-08-26 | 2016-08-26 | 2017-01-25 | 2017-04-03 | R | [10 empty] | 2017-09-22 | 2017-08-07 | 2017-10-12 | 2017-08-07 | G | [20 empty] | 2018-06-05 | 2019-04-05 | 2018-07-02 | 2019-07-28 | R | 2018-07-03 | 2019-07-29 | 2018-09-26 | 2019-10-08 | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.34055
1652 | 109326 | #HB2.FY17 Fox Drive Turn Lanes | 0767 | Secondary | Reconstruction w/ Added Capacity | VDOT | Frederick County | EDINBURG | Staunton | Winchester:Frederick County | Infrastructure Investment Division | Ronald L Tabor | Ronald.Tabor@vdot.virginia.gov | (540) 332-7887 | John-Allen L Ennis | JohnAllen.Ennis@VDOT.Virginia.gov | (540) 332-9118 |  |  |  | 1 | 2017 | 0 | FY2019 | 650996 | 743507 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 391 days early | Y | Project estimate is less than $5M and is up to 20% over budget | [5 empty] | 2016-09-14 | 2016-09-14 | 2016-09-14 | 2016-09-14 | G | 2016-09-16 | 2016-09-16 | 2017-08-15 | 2017-06-06 | G | [5 empty] | 2017-09-15 | 2017-07-10 | 2017-09-21 | 2017-07-28 | G | 2017-11-14 | 2017-11-06 | 2017-11-29 | 2017-11-06 | G | 2017-10-23 | 2017-10-10 | 2017-10-23 | 2017-10-10 | G | 2017-12-08 | 2017-11-16 | 2017-12-29 | 2018-02-16 | R | [10 empty] | 2019-03-12 | 2018-03-13 | 2019-03-12 | 2018-03-13 | G | 2019-04-25 | 2018-05-25 | 2019-06-20 | 2018-05-25 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.086836
1653 | 110330 | ROUTE 29 WIDENING - PH I | 0029 | Primary | Reconstruction w/ Added Capacity | VDOT | Fairfax County | FAIRFAX | Northern Virginia | Northern Virginia:Fairfax County | Infrastructure Investment Division | Terry Yates | Terry.Yates@vdot.virginia.gov | (703) 259-2118 | Chandraratne B Basnayake | Chan.Basnayake@vdot.virginia.gov | (703) 259-2947 | Michael Guarino | michael.guarino@fairfaxcounty. | (703) 877-5731 | 0 |  | 0 | FY2021 | 1600000 | 1600000 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 1153 days early | G | Project is on budget | [5 empty] | 2018-04-03 | 2017-07-10 | 2018-04-16 | 2017-07-17 | G | 2018-04-17 | 2017-03-24 | 2019-03-15 | 2017-12-12 | G | [5 empty] | 2018-08-16 | 2017-09-22 | 2018-08-29 | 2017-12-12 | G | 2018-02-12 | 2018-02-12 | 2018-02-12 | 2018-02-12 | G | [20 empty] | 2021-04-13 | 2018-02-27 | 2021-04-13 | 2018-02-27 | G | 2021-06-03 | 2018-04-27 | 2021-06-23 | 2018-04-27 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.080142
1655 | 111704 | Construct Roundabout | 0646 | Secondary | Reconstruction w/o Added Capacity | VDOT | Prince George County | PETERSBURG | Richmond | Tri-Cities:Prince George County | Infrastructure Investment Division | Dianna M Bryant | Dianna.Bryant@VDOT.Virginia.gov | (804) 863-4004 | Raymond Chapman | Scott.Chapman@vdot.virginia.gov | (804) 609-5277 |  |  |  | 0 |  | 0 | FY2027 | 4058312 | 4058312 | NO DATES SET YET | G | Start Development milestone is 528 days ahead of the expected completion date | G | Project is on budget | [5 empty] | 2022-07-21 |  | 2022-08-03 |  | G | 2022-08-04 |  | 2023-07-03 |  | G | [5 empty] | 2024-05-08 |  | 2024-05-21 |  | G | 2025-08-26 |  | 2025-09-09 |  | G | 2026-02-09 |  | 2026-08-12 |  | G | 2025-09-25 |  | 2026-04-07 |  | G | 2025-02-14 |  | 2025-08-19 |  | G | [5 empty] | 2026-09-08 |  | 2026-09-08 |  | G | 2026-12-15 |  | 2027-02-12 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.12455
1657 | 112536 | SIGNAL UPGRADES - RTE 17/615 (BURLEIGH/SHORT) | 0017 | Primary | Safety | VDOT | Gloucester County | SALUDA | Fredericksburg | Hampton Roads:Gloucester County | Infrastructure Investment Division | Teresa Gardner |  |  | Ronnie Hobson | Ron.Hobson@vdot.virginia.gov | (804) 840-5501 |  |  |  | 0 |  | 0 | FY2019 | 469000 | 469500 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 71 days early | Y | Project estimate is less than $5M and is up to 20% over budget | [5 empty] | 2017-11-01 | 2017-11-01 | 2017-12-04 | 2017-12-04 | G | 2017-12-05 | 2017-12-05 | 2018-03-19 | 2018-03-19 | G | [5 empty] | 2018-03-21 | 2018-03-21 | 2018-04-03 | 2018-04-02 | G | [25 empty] | 2018-04-25 | 2018-04-30 | 2018-04-25 | 2018-04-30 | R | 2018-04-26 | 2018-05-08 | 2018-07-18 | 2018-05-08 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | WORK/TASK ORDER | 1 | 0 | 0.067789
1658 | 113072 | MOULTRIE AVE - RECONSTRUCTION |  | Urban | Reconstruction w/o Added Capacity | Locally | Hopewell | PETERSBURG | Richmond | Tri-Cities:Hopewell | Local Assistance Division | James Shepherd | James.Shepherd@vdot.virginia.gov | (804) 609-5305 | James Shepherd | James.Shepherd@vdot.virginia.gov | (804) 609-5305 | Austin Anderson | AAnderson@HOPEWELLVA.GOV | (804) 541-2319 | 0 |  | 0 | FY2021 | 659490 | 659490 | ACTIVITY DATES SET | R | Solicit Bids milestone is 349 days past the expected completion date | G | Project is on budget | 2018-09-14 | 2018-08-13 | 2018-12-12 | 2018-08-14 | G | 2018-12-13 | 2018-12-17 | 2019-01-04 | 2018-12-18 | G | 2019-01-07 | 2019-01-07 | 2019-04-03 | 2019-04-02 | G | [25 empty] | 2019-05-20 | 2019-12-12 | 2019-12-20 | 2019-12-12 | G | [5 empty] | 2020-02-07 |  | 2020-03-09 |  | R | 2020-03-10 |  | 2020-08-26 |  | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.071806
1659 | 113253 | LED SIGNAL UPGRADES - COUNTYWIDE | 9999 | Miscellaneous | Traffic Management/Engineering | Locally | Arlington County | FAIRFAX | Northern Virginia | Northern Virginia:Arlington County | Local Assistance Division | Amir Salahshoor | A.Salahshoor@VDOT.Virginia.gov | (703) 259-1957 | Rita Hockman | Rita.Hockman@vdot.virginia.gov | (804) 824-7421 | Anup Kafle, P.E. | Akafle@arlingtonva.us | (703) 228-7050 | 0 |  | 0 | FY2020 | 550000 | 550000 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 226 days early | G | Project is on budget | 2018-10-31 | 2018-08-15 | 2019-03-29 | 2018-11-26 | G | 2019-04-01 | 2018-12-18 | 2019-04-30 | 2019-02-15 | G | 2019-11-01 | 2019-08-01 | 2020-10-30 | 2019-08-01 | G | [35 empty] | 2019-09-12 | 2019-09-12 | 2019-12-10 | 2019-10-18 | G | 2019-12-11 | 2019-10-21 | 2020-06-03 | 2019-10-21 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.19572
1660 | 113262 | Grove Subd - Shlder Widening & Pavement/Drainage/Ditch Defi | 9999 | Secondary | Reconstruction w/o Added Capacity | Locally | James City County | WILLIAMSBURG | Hampton Roads | Hampton Roads:James City County | Local Assistance Division | Christopher R Carroll | C.Carroll@VDOT.Virginia.gov | (757) 253-5140 | Keisha Wilkins | Keisha.Wilkins@vdot.virginia.gov | (757) 956-3110 | Tammy Rosario | tammy.rosario@jamescitycountyva.gov | (757) 253-6671 | 0 |  | 0 | FY2023 | 2002700 | 2002700 | NO DATES SET YET-PE OPEN | R | Determine Requirements milestone is 226 days past the expected completion date | G | Project is on budget | 2019-10-01 | 2018-10-01 | 2019-12-30 | 2018-10-01 | G | 2019-12-31 | 2018-09-14 | 2020-01-03 | 2018-09-14 | G | 2020-01-06 |  | 2020-07-10 |  | R | [10 empty] | 2021-05-06 |  | 2021-05-26 |  | G | [5 empty] | 2021-05-28 |  | 2022-03-14 |  | G | 2020-08-17 | 2020-11-24 | 2021-04-23 | 2020-11-24 | G | [5 empty] | 2022-03-30 |  | 2022-04-26 |  | G | 2022-07-15 |  | 2022-07-15 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.24492
1661 | 113352 | Roanoke Street Sidewalk at 460 By-Pass | 0000 | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Christiansburg | CHRISTIANSBURG | Salem | New River Valley:Christiansburg | Local Assistance Division | Adam J Czesnowski | Adam.Czesnowski@vdot.virginia.gov | (540) 541-1216 | Adam J Czesnowski | Adam.Czesnowski@vdot.virginia.gov | (540) 541-1216 | Eli Mannon | emannon@christiansburg.org | (540) 382-6120 | 0 |  | 0 | FY2022 | 958226 | 801885 | ACTIVITY DATES SET | G | Start Purchasing Right-of-Way milestone finished 21 days early | G | Project is on budget | 2018-10-01 | 2018-10-01 | 2018-12-28 | 2019-01-09 | R | 2018-12-31 | 2019-01-09 | 2019-01-03 | 2019-01-16 | R | 2019-01-04 | 2019-01-29 | 2019-08-02 | 2019-08-01 | G | [10 empty] | 2020-10-22 | 2020-10-22 | 2020-11-12 | 2020-10-22 | G | [5 empty] | 2020-11-16 | 2020-10-23 | 2021-09-27 |  | G | 2021-01-27 |  | 2021-09-27 |  | G | [5 empty] | 2021-10-13 |  | 2021-11-10 |  | G | 2022-04-12 |  | 2022-04-12 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.24764
1662 | 113565 | Walnut Avenue Bicycle and Pedestrian Accommodations | 0000 | Urban | Facilities for Pedestrians and Bicycles | Locally | Vinton | SALEM | Salem | Roanoke:Vinton | Infrastructure Investment Division | Jessie Nester | Jessie.Nester@vdot.virginia.gov | (540) 613-4115 | Jessie Nester | Jessie.Nester@vdot.virginia.gov | (540) 613-4115 | Anita McMillan | amcmillan@vintonva.gov | (540) 983-0607 | 0 |  | 0 | FY2023 | 545250 | 545250 | NO DATES SET YET-PE OPEN | R | Determine Requirements milestone is 202 days past the expected completion date | G | Project is on budget | 2019-10-01 | 2019-10-01 | 2019-12-30 | 2020-01-16 | R | 2019-12-31 | 2019-12-12 | 2020-01-03 | 2020-03-03 | R | 2020-01-06 | 2020-07-16 | 2020-08-03 |  | R | [10 empty] | 2021-08-05 |  | 2021-08-25 |  | G | [5 empty] | 2021-08-27 |  | 2022-06-10 |  | G | 2021-10-04 |  | 2022-06-10 |  | G | [5 empty] | 2022-06-28 |  | 2022-07-26 |  | G | 2022-12-21 |  | 2022-12-21 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.26067
1663 | 113768 | RTE.11 SIDEWALK EAST SIDE OF EAST MAIN ST. ABINGDON | 0011 | Primary | Facilities for Pedestrians and Bicycles | Locally | Abingdon | ABINGDON | Bristol | Bristol:Abingdon | Infrastructure Investment Division | Allan D Sumpter | Allan.Sumpter@VDOT.virginia.gov | (276) 525-6461 | Roger L Musser | Roger.Musser@VDOT.Virginia.gov | (276) 696-3260 | Matthew Bolick | mbolick@abingdon.va.gov | (276) 492-2128 | 0 |  | 0 | FY2025 | 49929 | 49929 | NO DATES SET YET | G | Obtained Permits milestone finished 1502 days early | G | Project is on budget | 2023-05-01 |  | 2023-07-25 |  | G | 2023-07-26 |  | 2023-07-28 |  | G | 2023-07-31 |  | 2024-02-08 |  | G | [25 empty] | 2024-03-18 | 2020-10-05 | 2024-11-15 | 2020-10-05 | G | [5 empty] | 2025-02-27 |  | 2025-03-26 |  | G | 2025-06-13 |  | 2025-06-13 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.093534
1664 | 113851 | #SGR19VB - BRIDGE REPLACE RT 644 AQUIA CREEK | 0644 | Secondary | Bridge Replacement w/o Added Capacity | VDOT | Stafford County | FREDERICKSBURG | Fredericksburg | Fredericksburg:Stafford County | Infrastructure Investment/Asset Management Division | Annette F Adams | Annette.Adams@VDOT.Virginia.gov | (540) 372-3583 | Khalil Minhas | Khalil.Minhas@vdot.virginia.gov | (540) 374-3369 |  |  |  | 0 |  | 1 | FY2025 | 6479500 | 6479500 | NO DATES SET YET-PE OPEN | G | Start Development milestone finished 194 days early | G | Project is on budget | [5 empty] | 2020-08-03 | 2020-01-16 | 2020-08-14 | 2020-02-02 | G | 2020-08-17 | 2020-07-06 | 2021-07-15 |  | G | [5 empty] | 2022-06-20 |  | 2022-07-01 |  | G | 2023-09-01 |  | 2023-09-15 |  | G | 2024-02-15 |  | 2024-08-19 |  | G | 2023-10-02 |  | 2024-04-11 |  | G | 2023-08-25 |  | 2024-05-02 |  | G | [5 empty] | 2024-09-10 |  | 2024-09-10 |  | G | 2024-12-04 |  | 2024-12-04 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.054784
1665 | 115135 | #SMART20 Edgewood Road Sidewalk Improvements |  | Urban | Facilities for Pedestrians and Bicycles | Locally | Staunton | HARRISONBURG | Staunton | SAW:Staunton | Infrastructure Investment Division | Randolph S Kiser | Randy.Kiser@VDOT.Virginia.gov | (540) 332-9092 | Michael S Fulcher | Michael.Fulcher@VDOT.Virginia.gov | (540) 332-2243 | Staunton City | millsnd@ci.staunton.va.us | (540) 332-3858 | 1 | 2020 | 0 | FY2026 | 1098071 | 1098071 | NO DATES SET YET | G | Agreement with Locality milestone is 976 days ahead of the expected completion date | G | Project is on budget | 2023-08-01 |  | 2023-10-25 |  | G | 2023-10-26 |  | 2023-10-30 |  | G | 2023-10-31 |  | 2024-05-09 |  | G | [10 empty] | 2025-03-07 |  | 2025-03-27 |  | G | [5 empty] | 2025-03-31 |  | 2026-01-08 |  | G | 2024-06-17 |  | 2025-02-24 |  | G | [5 empty] | 2026-01-28 |  | 2026-02-25 |  | G | 2026-05-14 |  | 2026-05-14 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.10958
1666 | 115339 | #SMART20 Lafayette Street Reconstruction | 0005 | Urban | Reconstruction w/o Added Capacity | Locally | Williamsburg | WILLIAMSBURG | Hampton Roads | Hampton Roads:Williamsburg | Infrastructure Investment Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Chessica Villaflores | Chessica.Villaflores@vdot.virginia.gov | (757) 956-3094 | Aaron Small | asmall@williamsburgva.gov | (757) 220-6140 | 1 | 2020 | 0 | FY2027 | 5870000 | 5870000 | NO DATES SET YET | G | Agreement with Locality milestone is 1264 days ahead of the expected completion date | Y | Estimate not current | 2024-05-15 |  | 2024-08-08 |  | G | 2024-08-09 |  | 2024-08-13 |  | G | 2024-08-14 |  | 2025-02-25 |  | G | [10 empty] | 2026-02-27 |  | 2026-03-19 |  | G | [5 empty] | 2026-03-23 |  | 2026-12-30 |  | G | 2025-04-02 |  | 2025-12-04 |  | G | [5 empty] | 2027-01-20 |  | 2027-02-17 |  | G | 2027-05-06 |  | 2027-05-06 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.24823
1667 | 115457 | #SMART20 - Rte 220 and International Parkway Intersection | 0220 | Primary | Safety | VDOT | Botetourt County | SALEM | Salem | Roanoke:Botetourt County | Infrastructure Investment Division | Thomas W Digiulian | Thomas.DiGiulian@VDOT.Virginia.gov | (540) 387-5356 | C E Cumbie | C.Cumbie@VDOT.Virginia.gov | (540) 387-5561 |  |  |  | 1 | 2020 | 0 | FY2028 | 4551000 | 4551000 | NO DATES SET YET | G | Start Development milestone is 904 days ahead of the expected completion date | G | Project is on budget | [5 empty] | 2023-08-01 |  | 2023-08-14 |  | G | 2023-08-15 |  | 2024-07-12 |  | G | [5 empty] | 2025-05-19 |  | 2025-06-02 |  | G | 2026-09-04 |  | 2026-09-18 |  | G | 2027-02-19 |  | 2027-08-23 |  | G | 2026-10-06 |  | 2027-04-16 |  | G | 2026-02-26 |  | 2026-08-28 |  | G | [5 empty] | 2027-09-14 |  | 2027-09-14 |  | G | 2027-12-08 |  | 2027-12-08 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 1 | 0.26165
1668 | 115804 | #I81CIP SB EXIT 283 EXTEND ACCELERATION LANE (ID #52) | 0081 | Interstate | Reconstruction w/o Added Capacity | VDOT | Shenandoah County | EDINBURG | Staunton | NonMPO:NonMPO | Infrastructure Investment Division | Randolph S Kiser | Randy.Kiser@VDOT.Virginia.gov | (540) 332-9092 | Alexander Alvarado | Alexander.Alvarado@vdot.virginia.gov | (540) 332-7372 |  |  |  | 0 |  | 0 | FY2020 | 2354000 | 784811 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished on-time | G | Project is on budget | [5 empty] | 2019-09-06 | 2019-09-06 | 2019-09-19 | 2019-09-10 | G | 2019-09-20 | 2019-09-08 | 2020-08-18 | 2019-09-08 | G | [5 empty] | 2019-10-25 | 2019-10-25 | 2019-10-25 | 2019-10-25 | G | 2019-11-19 | 2019-11-19 | 2019-11-19 | 2019-11-19 | G | 2019-09-23 | 2019-09-23 | 2019-09-23 | 2019-09-23 | G | 2019-11-19 | 2019-11-19 | 2019-11-19 | 2019-11-19 | G | [10 empty] | 2020-01-07 | 2020-01-07 | 2020-01-07 | 2020-01-07 | G | 2020-03-30 | 2020-03-30 | 2020-03-30 | 2020-03-30 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | SAAP CONTRACT | 1 | 0 | 0.063614
1669 | 117572 | DISTRICTWIDE - TRENCH WIDENING (TOP 100 SEGMENTS) | 9999 | Miscellaneous | Reconstruction w/o Added Capacity | VDOT | Fredericksburg District-wide |  | Fredericksburg | Fredericksburg:Fredericksburg District-wide | Infrastructure Investment Division | Jessica Graves | Jessica.Graves@vdot.virginia.gov | (540) 899-4267 | Jessica Graves | Jessica.Graves@vdot.virginia.gov | (540) 899-4267 |  |  |  | 0 |  | 0 | FY2023 | 1275328 | 1275328 | NO DATES SET YET-PE OPEN | G | Start Development milestone finished 32 days early | G | Project is on budget | [5 empty] | 2020-08-03 | 2020-07-08 | 2020-08-21 | 2020-07-20 | G | 2020-08-24 | 2020-08-24 | 2021-06-28 |  | G | [5 empty] | 2022-02-01 |  | 2022-03-01 |  | G | [5 empty] | 2022-10-19 |  | 2023-02-24 |  | G | [5 empty] | 2022-07-13 |  | 2022-12-13 |  | G | [5 empty] | 2023-03-14 |  | 2023-03-14 |  | G | 2023-06-01 |  | 2023-06-01 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.079485
1670 | 113264 | Audubon Drive Sidewalk | 9999 | Urban | Facilities for Pedestrians and Bicycles | Locally | Henrico County | ASHLAND | Richmond | Richmond:Henrico County | Local Assistance Division | Douglas L Orcutt | Doug.Orcutt@vdot.virginia.gov | (804) 609-5428 | Douglas L Orcutt | Doug.Orcutt@vdot.virginia.gov | (804) 609-5428 | Todd Eure | eur@co.henrico.va.us | (804) 501-4617 | 0 |  | 0 | FY2022 | 220000 | 220000 | ACTIVITY DATES SET | G | Start Purchasing Right-of-Way milestone finished 21 days early | G | Project is on budget | 2019-07-01 | 2019-07-01 | 2019-10-31 | 2019-10-14 | G | 2019-11-01 | 2019-11-01 | 2019-11-15 | 2019-11-05 | G | 2019-11-18 | 2019-11-05 | 2020-01-02 | 2019-12-17 | G | 2020-10-07 | 2020-09-29 | 2020-10-07 | 2020-09-29 | G | [5 empty] | 2020-12-01 | 2020-11-12 | 2020-12-07 | 2020-11-16 | G | 2021-08-03 |  | 2021-12-01 |  | G | 2020-12-09 |  | 2021-08-02 |  | G | 2020-12-04 | 2020-08-27 | 2021-09-21 | 2020-08-27 | G | [5 empty] | 2022-01-03 |  | 2022-01-03 |  | G | 2022-01-04 |  | 2022-04-01 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 |  | 0 | 1 | 0.23459
1671 | 113386 | #SGR19VB - BR DECK REPLACMENT SB I-95 OVER RT 301 & EB 460 | 0095 | Interstate | Bridge Rehab w/o Added Capacity | VDOT | Petersburg | PETERSBURG | Richmond | Tri-Cities:Petersburg | Infrastructure Investment/Asset Management Division | William Wheeler | William.Wheeler@vdot.virginia.gov | (804) 609-5280 | William Wheeler | William.Wheeler@vdot.virginia.gov | (804) 609-5280 |  |  |  | 0 |  | 0 | FY2022 | 5000000 | 7035614 | ACTIVITY DATES SET | G | Start Purchasing Right-of-Way milestone finished on-time | R | Project estimate is between $5M and $10M and is a $1M or more over budget | [5 empty] | 2018-09-04 | 2018-08-16 | 2018-09-17 | 2018-08-23 | G | 2018-09-18 | 2018-08-24 | 2019-08-15 | 2019-08-15 | G | [5 empty] | 2020-08-10 | 2020-08-28 | 2020-08-28 | 2020-09-22 | R | 2020-09-22 | 2020-09-22 | 2020-09-22 | 2020-09-22 | G | 2020-07-28 | 2020-07-28 | 2020-07-28 | 2020-07-28 | G | 2020-09-22 | 2020-08-28 | 2020-09-22 | 2020-08-28 | G | [10 empty] | 2021-09-14 |  | 2021-09-14 |  | G | 2021-12-08 |  | 2022-03-15 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.10224
1672 | 113610 | FAIR LAKES BOULEVARD WALKWAY | 9999 | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Fairfax County | FAIRFAX | Northern Virginia | Northern Virginia:Fairfax County | Local Assistance Division | Andrew G Beacher | Andrew.Beacher@vdot.virginia.gov | (703) 259-2239 | Rhoderick M Undan | Rhoderick.Undan@vdot.virginia.gov | (703) 259-3347 | Todd Minnix | Wesley.Minnix@FairfaxCounty.gov | (703) 877-5749 | 0 |  | 0 | FY2022 | 677500 | 681856 | ADVERTISED | G | Solicit Bids milestone finished 168 days early | Y | Project estimate is less than $5M and is up to 20% over budget | 2019-07-01 | 2018-07-18 | 2020-01-31 | 2019-02-08 | G | 2020-02-03 | 2019-02-11 | 2020-03-31 | 2019-02-25 | G | 2020-04-01 | 2019-07-01 | 2021-01-29 | 2019-12-03 | G | [10 empty] | 2020-07-24 | 2020-02-26 | 2020-07-24 | 2020-02-26 | G | 2020-07-28 | 2020-02-28 | 2020-07-28 | 2020-02-28 | G | 2020-07-27 | 2020-02-27 | 2020-07-27 | 2020-02-27 | G | 2020-07-29 | 2020-03-02 | 2020-10-22 | 2020-03-02 | G | [5 empty] | 2020-11-23 | 2020-09-17 | 2021-03-25 | 2020-10-08 | G | 2021-03-26 | 2020-10-09 | 2021-09-27 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.25481
1673 | 113826 | City of Suffolk Emergency Vehicle Preemption Deployment | 9999 | Miscellaneous | Traffic Management/Engineering | Locally | Suffolk | NORFOLK | Hampton Roads | Hampton Roads:Suffolk | Infrastructure Investment Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Johndel A Alcaide | John.Alcaide@vdot.virginia.gov | (757) 956-3098 | Robert Lewis | relewis@suffolkva.us | (757) 514-7603 | 0 |  | 0 | FY2021 | 192209 | 188663 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 54 days early | G | Project is on budget | 2018-10-01 | 2018-10-01 | 2018-12-28 | 2018-12-05 | G | 2018-12-31 | 2018-12-06 | 2019-01-03 | 2019-02-22 | R | 2019-01-04 | 2019-02-25 | 2019-07-11 | 2019-08-28 | R | [25 empty] | 2019-08-29 | 2019-09-17 | 2020-05-06 | 2019-09-17 | G | [5 empty] | 2020-05-21 | 2020-03-25 | 2020-06-18 | 2020-05-22 | G | 2020-06-19 | 2020-07-10 | 2020-09-04 | 2020-07-12 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.21889
1674 | 113918 | PEDESTRIAN IMPROVEMENTS AT PRESTON AVE/HARRIS ST | 0250 | Urban | Safety | Locally | Charlottesville | CHARLOTTESVILLE | Culpeper | Charlottesville:Charlottesville | Infrastructure Investment Division | Ken Connors |  |  | Michael D Barnes | MichaelD.Barnes@vdot.virginia.gov | (434) 422-9861 | AMANDA PONCY | PONCY@CHARLOTTESVILLE.ORG | (434) 970-3182 | 0 |  | 0 | FY2025 | 245725 | 245725 | NO DATES SET YET | G | Agreement with Locality milestone is 312 days ahead of the expected completion date | G | Project is on budget | 2021-10-01 |  | 2021-12-30 |  | G | 2022-01-03 |  | 2022-01-05 |  | G | 2022-01-06 |  | 2022-07-13 |  | G | [10 empty] | 2023-07-17 |  | 2023-08-04 |  | G | [5 empty] | 2023-08-08 |  | 2024-05-20 |  | G | 2022-08-18 |  | 2023-04-26 |  | G | [5 empty] | 2024-06-06 |  | 2024-07-03 |  | G | 2024-09-23 |  | 2024-09-23 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.16752
1675 | 115295 | #SGR20LP - PRIMARY EXT PAVING FY20 - SEMINARY ROAD E/B - 47 | 0420 | Urban | Resurfacing | Locally | Alexandria | FAIRFAX | Northern Virginia | Northern Virginia:Alexandria | Local Assistance Division | Amir Salahshoor | A.Salahshoor@VDOT.Virginia.gov | (703) 259-1957 | Rita Hockman | Rita.Hockman@vdot.virginia.gov | (804) 824-7421 | Mary Alice Winston | maryalice.winston@alexandriava.gov | (703) 746-4067 | 0 |  | 1 | FY2020 | 210000 | 210000 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 214 days early | G | Project is on budget | 2019-07-01 | 2019-07-01 | 2019-09-30 | 2019-07-01 | G | [5 empty] | 2019-10-01 | 2019-07-15 | 2019-10-31 | 2019-07-15 | G | [25 empty] | 2019-09-27 | 2019-07-16 | 2019-11-27 | 2019-07-16 | G | [5 empty] | 2019-11-26 | 2019-06-28 | 2019-12-31 | 2019-06-28 | G | 2020-01-02 | 2019-07-29 | 2020-02-28 | 2019-07-29 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.19708
1676 | 115346 | #I81CIP EXTEND SB ACCEL LANE MM 25.9 TO MM 26.1 (ID #23) | 0081 | Interstate | Safety | VDOT | Washington County | ABINGDON | Bristol | NonMPO:NonMPO | Infrastructure Investment Division | Tamara D Pritchard | Tamara.Pritchard@VDOT.Virginia.gov | (276) 696-3249 | Brandi Halloway | Brandi.Halloway@vdot.virginia.gov | (276) 696-3254 |  |  |  | 0 |  | 0 | FY2020 | 2005000 | 590669 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 7 days early | G | Project is on budget | [5 empty] | 2019-08-01 | 2019-07-18 | 2019-08-07 | 2019-07-24 | G | 2019-08-08 | 2019-07-25 | 2019-09-05 | 2019-08-21 | G | [5 empty] | 2019-08-26 | 2019-08-26 | 2019-08-26 | 2019-08-26 | G | [5 empty] | 2019-07-26 | 2019-07-16 | 2019-07-26 | 2019-07-26 | G | [15 empty] | 2019-12-10 | 2019-12-10 | 2019-12-10 | 2019-12-10 | G | 2020-03-05 | 2020-02-27 | 2020-03-05 | 2020-02-27 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.078655
1677 | 115614 | ROUTE 1 AND MARKET STREET TURN LANE | 0001 | Primary | Safety | VDOT | Spotsylvania County | FREDERICKSBURG | Fredericksburg | Fredericksburg:Spotsylvania County | Infrastructure Investment Division | Catherine C Coffey | Catherine.Coffey@vdot.virginia.gov | (540) 899-4280 | Anastasia Kapitan | Anastasia.Kapitan@vdot.virginia.gov | (540) 899-4292 |  |  |  | 0 |  | 0 | FY2024 | 7632217 | 7632217 | ACTIVITY DATES SET | G | Determine Requirements milestone finished 1 days early | G | Project is on budget | [5 empty] | 2019-08-01 | 2019-07-22 | 2019-08-14 | 2019-07-26 | G | 2019-08-15 | 2019-07-29 | 2020-07-14 | 2020-07-13 | G | [5 empty] | 2021-06-08 |  | 2021-06-21 |  | G | 2022-09-15 |  | 2022-10-12 |  | G | 2023-05-03 |  | 2023-10-30 |  | G | 2022-10-31 |  | 2023-05-03 |  | G | 2022-10-24 |  | 2023-05-03 |  | G | [5 empty] | 2023-11-14 |  | 2023-11-14 |  | G | 2024-02-09 |  | 2024-02-09 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.067421
1678 | 117080 | #SGR21LP Tazewell Avenue-Primary Extension Paving | 0016 | Urban | Resurfacing | VDOT | Tazewell | LEBANON | Bristol | NonMPO:NonMPO | Infrastructure Investment/Asset Management Division | James B Parsons | James.Parsons@VDOT.Virginia.gov | (276) 696-3288 | David G Morrison | David.Morrison@VDOT.Virginia.gov | (276) 696-3328 |  |  |  | 0 |  | 1 | FY2022 | 172390 | 172390 | NO DATES SET YET-PE OPEN | Y | Determine Requirements milestone is 8 days ahead of the expected completion date and there is a risk of missing this milestone date | G | Project is on budget | [5 empty] | 2020-12-01 | 2020-12-01 | 2020-12-14 | 2020-12-14 | G | 2020-12-15 | 2020-12-15 | 2021-03-01 |  | Y | [35 empty] | 2021-09-14 |  | 2021-09-14 |  | G | 2021-12-08 |  | 2021-12-08 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.062639
1679 | 118077 | SOUTH RIVER GREENWAY PHASE 4 |  | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Waynesboro | HARRISONBURG | Staunton | SAW:Waynesboro | Local Assistance Division | Matthew P Dana | Matt.Dana@VDOT.Virginia.gov | (540) 332-7786 | Jamison Brown | Jamison.Brown@vdot.virginia.gov | (540) 332-7389 | Waynesboro City | jonescd@ci.waynesboro.va.us | (540) 942-6735 | 0 |  | 0 | FY2024 | 772896 | 772896 | NO DATES SET YET | G | Agreement with Locality milestone is 93 days ahead of the expected completion date | G | Project is on budget | 2021-01-19 |  | 2021-05-25 |  | G | 2021-05-26 |  | 2021-06-16 |  | G | 2021-07-16 |  | 2021-11-08 |  | G | [10 empty] | 2023-03-07 |  | 2023-04-10 |  | G | [5 empty] | 2023-04-11 |  | 2023-09-07 |  | G | 2023-08-04 |  | 2024-01-08 |  | G | [5 empty] | 2023-12-14 |  | 2024-01-16 |  | G | 2024-04-04 |  | 2024-04-04 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.31058
1680 | 108889 | PEDESTRIAN IMPROVEMENTS - CITY WIDE |  | Primary | Safety | Locally | Richmond | ASHLAND | Richmond | Richmond:Richmond | Local Assistance Division | Brian J Lokker | Brian.Lokker@VDOT.Virginia.gov | (804) 524-6010 | Brian J Lokker | Brian.Lokker@VDOT.Virginia.gov | (804) 524-6010 | Jian Xu | Jian.Xu@richmondgov.com | (804) 646-5402 | 0 |  | 0 | FY2020 | 3419338 | 3419338 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 371 days early | G | Project is on budget | 2017-04-10 | 2017-04-10 | 2017-04-10 | 2017-04-10 | G | 2016-11-02 | 2016-11-02 | 2016-11-10 | 2016-11-10 | G | 2017-04-10 | 2017-11-02 | 2018-08-01 | 2018-02-21 | G | [35 empty] | 2019-12-03 | 2018-11-21 | 2019-12-31 | 2018-11-21 | G | 2020-01-02 | 2019-01-18 | 2020-02-13 | 2019-02-07 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.19359
1681 | 109579 | Route 220/688 Access Management Improvements | 9999 | Primary | Safety | VDOT | Henry County | MARTINSVILLE | Salem | NonMPO:NonMPO | Infrastructure Investment Division | Alex H Price | Alex.Price@VDOT.Virginia.gov | (540) 378-5053 | Anthony L Handy | Tony.Handy@VDOT.Virginia.gov | (540) 352-9050 |  |  |  | 0 |  | 0 | FY2020 | 364331 | 364331 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 48 days early | G | Project is on budget | [5 empty] | 2016-07-01 | 2016-07-06 | 2016-07-15 | 2016-07-15 | G | 2016-07-18 | 2016-07-18 | 2017-03-14 | 2017-09-12 | R | [5 empty] | 2017-12-15 | 2017-12-15 | 2018-06-29 | 2018-02-16 | G | [5 empty] | 2018-11-06 | 2019-04-23 | 2019-11-26 | 2019-11-26 | G | [15 empty] | 2018-10-09 | 2019-12-10 | 2019-12-10 | 2019-12-10 | G | 2020-01-22 | 2020-02-27 | 2020-04-15 | 2020-02-27 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.06651
1682 | 111040 | #SGR18LB - Longstreet Lane over SomeRTon Creek | 0660 | Urban | Bridge Replacement w/o Added Capacity | Locally | Suffolk | NORFOLK | Hampton Roads | Hampton Roads:Suffolk | Infrastructure Investment Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Johndel A Alcaide | John.Alcaide@vdot.virginia.gov | (757) 956-3098 | L.Hansen | lhansen@suffolkva.us | (757) 514-7687 | 0 |  | 1 | FY2023 | 2589652 | 2589652 | ACTIVITY DATES SET | G | Determine Requirements milestone finished 106 days early | G | Project is on budget | 2019-04-05 | 2017-07-21 | 2019-06-28 | 2017-10-05 | G | 2019-07-01 | 2017-10-06 | 2019-07-15 | 2019-07-15 | G | 2019-07-16 | 2019-07-16 | 2020-06-30 | 2020-03-16 | G | [10 empty] | 2021-04-20 |  | 2021-05-10 |  | G | [5 empty] | 2021-05-12 |  | 2022-04-01 |  | G | [10 empty] | 2022-05-03 |  | 2022-05-31 |  | G | 2022-06-01 |  | 2022-08-30 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.11419
1683 | 111116 | RTE 618 (Old Bermuda Hund near Golf Course) - RECONSTRUCTION | 0618 | Secondary | Reconstruction w/o Added Capacity | Locally | Chesterfield County | CHESTERFIELD | Richmond | Richmond:Chesterfield County | Local Assistance Division | Brian J Lokker | Brian.Lokker@VDOT.Virginia.gov | (804) 524-6010 | Brian J Lokker | Brian.Lokker@VDOT.Virginia.gov | (804) 524-6010 | Nate Mathis | mathisn@chesterfield.gov | (804) 748-1037 | 0 |  | 0 | FY2019 | 3755000 | 3755000 | CONSTRUCTION STARTED | R | Start Delivery milestone finished 41 days late | G | Project is on budget | 2017-06-08 | 2017-06-08 | 2017-06-08 | 2017-06-08 | G | [5 empty] | 2017-07-05 | 2015-08-04 | 2017-07-11 | 2015-10-16 | G | [10 empty] | 2018-01-22 | 2017-06-29 | 2018-02-02 | 2017-07-07 | G | [5 empty] | 2018-02-21 | 2017-07-11 | 2018-08-23 | 2018-07-31 | G | 2015-01-21 | 2014-11-24 | 2015-07-24 | 2014-11-24 | G | [5 empty] | 2019-01-08 | 2018-10-17 | 2019-01-08 | 2018-10-17 | G | 2019-03-04 | 2018-10-19 | 2019-03-22 | 2019-05-02 | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.32193
1684 | 111357 | County of York - Bypass Road Sidewalk |  | Enhancement | Facilities for Pedestrians and Bicycles | Locally | York County | WILLIAMSBURG | Hampton Roads | Hampton Roads:York County | Local Assistance Division | Glenn Brooks | Glenn.Brooks@vdot.virginia.gov | (757) 253-4015 | Keisha Wilkins | Keisha.Wilkins@vdot.virginia.gov | (757) 956-3110 | County of York | tcross@yorkcounty.gov | TimothyCross | 0 |  | 0 | FY2022 | 998464 | 912657 | ACTIVITY DATES SET | G | Start Purchasing Right-of-Way milestone finished 98 days early | G | Project is on budget | 2017-10-02 | 2017-10-02 | 2017-12-29 | 2018-01-29 | R | 2018-01-02 | 2018-01-29 | 2018-01-04 | 2018-03-06 | R | 2018-01-05 | 2020-01-07 | 2018-07-12 | 2020-04-21 | R | [10 empty] | 2020-07-06 | 2020-03-25 | 2020-08-07 | 2020-05-01 | G | [5 empty] | 2020-08-24 |  | 2021-05-14 |  | G | 2020-08-27 | 2021-02-10 | 2021-05-05 |  | G | [5 empty] | 2021-07-01 |  | 2021-07-30 |  | G | 2021-10-20 |  | 2022-01-04 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.31831
1685 | 111711 | #SMART18 - Laskin Road Phase 1-A | 0058 | Urban | Reconstruction w/ Added Capacity | VDOT | Virginia Beach | NORFOLK | Hampton Roads | Hampton Roads:Virginia Beach | Infrastructure Investment Division | Samba Secka | Samba.Secka@vdot.virginia.gov | (757) 956-3058 | John K Arms | John.Arms@vdot.virginia.gov | (757) 995-5156 |  |  |  | 1 | 2018 | 0 | FY2022 | 29000200 | 45590000 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 884 days early | R | Project estimate is greater than $10M and is over budget by (a) 10% or more or (b) $5M or more | [5 empty] | 2021-08-02 | 2017-10-17 | 2021-08-13 | 2017-12-06 | G | 2021-08-16 | 2017-11-22 | 2022-09-23 | 2018-09-25 | G | [5 empty] | 2017-12-15 | 2017-12-15 | 2018-10-10 | 2018-10-10 | G | 2018-09-27 | 2018-09-27 | 2019-03-29 | 2018-10-10 | G | 2019-04-02 | 2018-11-28 | 2021-04-02 | 2019-08-08 | G | 2019-04-16 | 2018-12-03 | 2020-08-31 | 2019-12-04 | G | 2018-10-12 | 2018-10-12 | 2020-12-08 | 2018-10-12 | G | [5 empty] | 2021-06-08 | 2019-01-22 | 2021-06-08 | 2019-01-22 | G | 2021-08-20 | 2019-05-15 | 2021-10-15 | 2019-05-15 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.17656
1686 | 113129 | FY19 RS - Sidewalk Tripping Hazard Removal | 0000 | Urban | Facilities for Pedestrians and Bicycles | Locally | Blacksburg | CHRISTIANSBURG | Salem | New River Valley:Blacksburg | Local Assistance Division | Adam J Czesnowski | Adam.Czesnowski@vdot.virginia.gov | (540) 541-1216 | Adam J Czesnowski | Adam.Czesnowski@vdot.virginia.gov | (540) 541-1216 | Randy Formica | rformica@blacksburg.gov | (540) 961-1121 | 0 |  | 0 | FY2020 | 50000 | 50000 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 215 days early | G | Project is on budget | 2018-08-01 | 2018-08-01 | 2018-10-25 | 2018-08-21 | G | 2018-10-26 | 2018-08-30 | 2018-10-30 | 2018-08-30 | G | 2018-10-31 | 2018-09-27 | 2019-08-01 | 2018-10-19 | G | [35 empty] | 2018-11-02 | 2018-11-02 | 2018-11-03 | 2018-11-03 | G | 2019-04-04 | 2018-11-23 | 2019-07-01 | 2018-11-28 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.16006
1687 | 113365 | Primary Extensions: E Wythe Street Resurfacing | 0036 | Urban | Resurfacing | VDOT | Petersburg | PETERSBURG | Richmond | Tri-Cities:Petersburg | Local Assistance Division | Dianna M Bryant | Dianna.Bryant@VDOT.Virginia.gov | (804) 863-4004 | Dianna M Bryant | Dianna.Bryant@VDOT.Virginia.gov | (804) 863-4004 | Bill Riggleman | bill@petersburg-va.org | (804) 993-1927 | 0 |  | 1 | FY2020 | 419310 | 419310 | AWARDED | G | Start Delivery milestone finished 233 days early | G | Project is on budget | [10 empty] | 2018-05-01 | 2018-10-25 | 2018-05-07 | 2018-12-19 | R | [25 empty] | 2018-11-29 | 2018-11-29 | 2019-03-28 | 2018-11-29 | G | [5 empty] | 2019-05-28 | 2018-12-26 | 2019-05-28 | 2018-12-26 | G | 2019-08-16 | 2018-12-26 | 2019-08-16 | 2018-12-26 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.067472
1688 | 113606 | STONY POINT-HIGHWATER TRAIL PROJECT | 0719 | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Hillsboro | LEESBURG | Northern Virginia | Northern Virginia:Loudoun County | Local Assistance Division | Amir Salahshoor | A.Salahshoor@VDOT.Virginia.gov | (703) 259-1957 | Christer P Carshult | Christer.Carshult@vdot.virginia.gov | (703) 259-1765 | Roger Vance | MayorVance@gmail.com | (703) 431-3031 | 0 |  | 0 | FY2022 | 550050 | 550050 | ACTIVITY DATES SET | G | Start Purchasing Right-of-Way milestone finished on-time | G | Project is on budget | 2019-01-15 | 2018-08-01 | 2019-08-30 | 2018-08-30 | G | 2019-09-03 | 2018-08-31 | 2019-09-30 | 2018-09-16 | G | 2019-10-01 | 2018-09-17 | 2020-07-31 | 2020-08-31 | R | [10 empty] | 2020-09-30 | 2020-10-30 | 2020-10-30 | 2020-10-30 | G | [5 empty] | 2020-11-02 | 2020-11-02 | 2021-05-14 |  | G | [10 empty] | 2021-07-16 |  | 2021-12-30 |  | G | 2022-01-03 |  | 2022-06-30 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.4869
1689 | 114729 | HARRISON ROAD PEDESTRIAN IMPROVEMENTS | 0620 | Secondary | Safety | VDOT | Spotsylvania County | FREDERICKSBURG | Fredericksburg | Fredericksburg:Spotsylvania County | Infrastructure Investment Division | Robert Galen Ridgell | Robert.Ridgell@vdot.virginia.gov | (540) 372-3549 | Robert Galen Ridgell | Robert.Ridgell@vdot.virginia.gov | (540) 372-3549 |  |  |  | 0 |  | 0 | FY2021 | 551100 | 551100 | CONSTRUCTION STARTED | G | Engage Public milestone finished 423 days early | G | Project is on budget | [5 empty] | 2019-01-07 | 2019-02-13 | 2019-01-07 | 2019-02-13 | R | 2019-01-08 | 2019-02-14 | 2019-04-18 | 2019-03-04 | G | [5 empty] | 2020-06-08 | 2019-06-21 | 2020-08-17 | 2019-06-21 | G | [25 empty] | 2020-09-02 | 2019-06-06 | 2020-09-09 | 2019-06-06 | G | 2020-09-10 | 2019-06-07 | 2020-09-16 | 2019-06-07 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | WORK/TASK ORDER | 1 | 0 | 0.068387
1690 | 109439 | #HB2.FY17 Add climbing lane to Rte. 58 Lee Co. | 0058 | Primary | Reconstruction w/o Added Capacity | VDOT | Lee County | WISE | Bristol | NonMPO:NonMPO | Infrastructure Investment Division | Dennis R Harris | Dennis.Harris@VDOT.Virginia.gov | (276) 696-3289 | Ronald C Flanary | Ronald.Flanary@VDOT.Virginia.gov | (276) 696-3252 |  |  |  | 1 | 2017 | 0 | FY2021 | 4995109 | 1979553 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 93 days early | G | Project is on budget | [5 empty] | 2016-08-01 | 2016-08-01 | 2016-08-22 | 2016-08-22 | G | 2016-08-15 | 2016-08-15 | 2017-07-21 | 2017-08-17 | R | [5 empty] | 2018-06-18 | 2018-07-17 | 2018-06-29 | 2018-07-18 | R | 2019-08-20 | 2019-04-02 | 2019-09-03 | 2019-06-12 | G | 2020-02-03 | 2019-08-08 | 2020-08-05 | 2019-11-21 | G | 2019-09-19 | 2019-05-29 | 2020-04-14 | 2019-09-13 | G | 2019-02-08 | 2019-02-08 | 2020-02-10 | 2019-02-25 | G | [5 empty] | 2020-08-11 | 2020-05-05 | 2020-08-11 | 2020-05-05 | G | 2020-10-01 | 2020-07-21 | 2020-10-22 | 2020-07-21 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.091534
1692 | 111044 | #SGR18LB - Southwestern Blvd over Chapel Swamp | 0661 | Urban | Bridge Replacement w/o Added Capacity | Locally | Suffolk | NORFOLK | Hampton Roads | Hampton Roads:Suffolk | Infrastructure Investment Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Johndel A Alcaide | John.Alcaide@vdot.virginia.gov | (757) 956-3098 | L.Hansen | lhansen@suffolkva.us | (757) 514-7687 | 0 |  | 1 | FY2019 | 715212 | 701884 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 92 days early | G | Project is on budget | 2017-07-14 | 2017-07-14 | 2017-11-21 | 2017-10-05 | G | 2017-11-22 | 2017-11-22 | 2017-12-22 | 2017-12-21 | G | 2017-12-26 | 2017-12-22 | 2018-04-06 | 2018-03-16 | G | [35 empty] | 2018-06-20 | 2018-03-30 | 2018-06-20 | 2018-04-01 | G | 2018-06-21 | 2018-05-30 | 2018-09-14 | 2018-06-14 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.10866
1693 | 111280 | #SGR18VB - RT 92 BRIDGE & APPR OVER STAUNTON RIVER Fed 4851 | 0092 | Primary | Bridge Replacement w/o Added Capacity | VDOT | Charlotte County | HALIFAX | Lynchburg | NonMPO:NonMPO | Infrastructure Investment/Asset Management Division | Bryan S Witt | Bryan.Witt@VDOT.Virginia.gov | (434) 856-8319 | Laura J Walton | Laura.Walton@VDOT.Virginia.gov | (434) 856-8286 |  |  |  | 0 |  | 1 | FY2025 | 25224963 | 25224963 | ACTIVITY DATES SET | G | Determine Requirements milestone finished on-time | G | Project is on budget | [5 empty] | 2019-01-29 | 2018-09-04 | 2019-02-11 | 2018-09-17 | G | 2019-02-12 | 2018-09-18 | 2020-03-23 | 2020-03-23 | G | [5 empty] | 2021-07-14 |  | 2021-08-17 |  | G | 2022-11-14 |  | 2022-11-29 |  | G | 2023-09-19 |  | 2024-03-29 |  | G | 2022-12-15 |  | 2023-09-18 |  | G | 2022-05-03 |  | 2023-05-03 |  | G | [5 empty] | 2024-04-09 |  | 2024-04-09 |  | G | 2024-10-22 |  | 2024-10-22 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.081033
1694 | 111440 | #SGR18LB - REPL SUPERSTRUCT & REPAIR SUBSTRUCT(29744 Fed) | 0000 | Miscellaneous | Bridge Rehab w/o Added Capacity | Locally | Buchanan County | LEBANON | Bristol | NonMPO:NonMPO | Infrastructure Investment Division | Tabitha H Crowder | Tabitha.Crowder@vdot.virginia.gov | (276) 696-3482 | Tabitha H Crowder | Tabitha.Crowder@vdot.virginia.gov | (276) 696-3482 | Marcus Stiltner | marcus.stiltner@buchanancounty-va.gov | (276) 935-4013 | 0 |  | 1 | FY2021 | 60000 | 60000 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 295 days early | G | Project is on budget | 2018-05-10 | 2018-02-01 | 2018-08-03 | 2018-04-02 | G | 2018-08-06 | 2018-04-03 | 2018-08-08 | 2018-04-05 | G | 2018-08-09 | 2018-04-06 | 2019-02-20 | 2019-02-19 | G | [35 empty] | 2020-01-14 | 2019-06-01 | 2020-04-09 | 2019-08-26 | G | 2020-04-10 | 2019-08-27 | 2020-07-06 | 2019-09-15 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.10024
1695 | 112969 | #SGR19LP - Resurface Statler Blvd(RT 261N) - Primary EXT | 0261 | Urban | Resurfacing | Locally | Staunton | HARRISONBURG | Staunton | SAW:Staunton | Local Assistance Division | Donald F Komara | Donald.Komara@VDOT.Virginia.gov | (540) 434-2587 | Michael S Fulcher | Michael.Fulcher@VDOT.Virginia.gov | (540) 332-2243 | Steve Yancey | yanceysc@ci.staunton.va.us | (540) 332-3892 | 0 |  | 1 | FY2020 | 240000 | 240000 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 412 days early | G | Project is on budget | 2018-12-31 | 2018-10-05 | 2019-03-28 | 2018-11-05 | G | 2019-03-29 | 2018-11-06 | 2019-04-02 | 2019-03-01 | G | 2019-04-03 | 2019-03-04 | 2019-10-04 | 2019-03-11 | G | [25 empty] | 2019-03-12 | 2019-03-10 | 2019-11-08 | 2019-03-12 | G | [5 empty] | 2020-01-21 | 2019-03-07 | 2020-02-18 | 2019-03-20 | G | 2020-05-06 | 2019-03-20 | 2020-05-06 | 2019-03-21 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.063288
1696 | 113137 | Eastview St. Stormwater Drainage | 0000 | Urban | Mitigation of Water Pollution Due to Highway Runof | Locally | Galax | MARTINSVILLE | Salem | NonMPO:NonMPO | Local Assistance Division | Jessie Nester | Jessie.Nester@vdot.virginia.gov | (540) 613-4115 | Jessie Nester | Jessie.Nester@vdot.virginia.gov | (540) 613-4115 | Keith Barker | kbarker@galaxva.com | (276) 236-5773 | 0 |  | 0 | FY2020 | 1964843 | 1786900 | CONSTRUCTION COMPLETED | R | Start Purchasing Right-of-Way milestone is 527 days past the expected completion date | G | Project is on budget | 2018-08-01 | 2018-08-01 | 2018-10-25 | 2018-09-28 | G | 2018-10-26 | 2018-10-01 | 2018-10-30 | 2018-10-02 | G | 2018-10-31 | 2018-10-03 | 2019-08-01 | 2019-06-10 | G | [10 empty] | 2019-08-23 | 2019-06-14 | 2019-09-13 |  | R | [5 empty] | 2019-09-17 | 2019-06-17 | 2019-11-20 |  | R | [10 empty] | 2019-11-21 | 2019-06-18 | 2019-12-20 | 2019-06-19 | G | 2020-05-18 | 2019-08-07 | 2020-06-22 | 2019-09-10 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.095682
1697 | 113476 | Woodman Road Extended - Multi-Use Trail |  | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Henrico County | ASHLAND | Richmond | Richmond:Henrico County | Local Assistance Division | Jorg Huckabee-Mayfield | Jorg.Huckabee-Mayfield@VDOT.Virginia.gov | (804) 609-5292 | Jorg Huckabee-Mayfield | Jorg.Huckabee-Mayfield@VDOT.Virginia.gov | (804) 609-5292 | Steve Bandura | ban03@henrico.us | (804) 501-5985 | 0 |  | 0 | FY2021 | 365000 | 344088 | ACTIVITY DATES SET | R | Solicit Bids milestone is 23 days past the expected completion date | G | Project is on budget | 2018-10-01 | 2018-09-27 | 2018-12-28 | 2018-09-27 | G | 2018-12-31 | 2019-01-03 | 2019-01-03 | 2019-01-09 | R | 2019-01-04 | 2019-01-10 | 2019-07-11 | 2019-09-24 | R | [25 empty] | 2020-05-01 | 2020-07-30 | 2020-09-30 | 2020-07-30 | G | [5 empty] | 2021-01-29 |  | 2021-01-29 |  | R | 2021-04-01 |  | 2021-04-30 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.43025
1698 | 114410 | Rte. 65 Scott Co. Str. #1098 Fed. ID #16600 | 0065 | Primary | Bridge Replacement w/o Added Capacity | VDOT | Scott County | WISE | Bristol | NonMPO:NonMPO | Infrastructure Investment Division | Dennis R Harris | Dennis.Harris@VDOT.Virginia.gov | (276) 696-3289 | James M Bullins | James.Bullins@VDOT.Virginia.gov | (276) 696-3349 |  |  |  | 0 |  | 0 | FY2022 | 1300000 | 1300000 | ACTIVITY DATES SET | R | Start Purchasing Right-of-Way milestone is 100 days past the expected completion date | G | Project is on budget | [5 empty] | 2019-01-15 | 2019-01-15 | 2019-01-30 | 2019-01-30 | G | 2019-01-31 | 2019-01-31 | 2019-05-23 | 2019-05-23 | G | [5 empty] | 2020-01-27 | 2020-01-27 | 2020-02-07 | 2020-02-07 | G | 2020-10-30 |  | 2020-11-13 |  | R | 2021-04-06 |  | 2021-07-14 |  | G | 2020-12-03 |  | 2021-06-10 |  | G | 2020-07-06 | 2020-07-06 | 2021-06-01 |  | G | [5 empty] | 2021-08-10 |  | 2021-08-10 |  | G | 2021-11-01 |  | 2021-11-01 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.06474
1699 | 115419 | City of Hampton 329 Magruder Blvd - Paving | 0134 | Urban | Restoration and Rehabilitation | Locally | Hampton | WILLIAMSBURG | Hampton Roads | Hampton Roads:Hampton | Local Assistance Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Derrick Williams | Derrick.Williams@vdot.virginia.gov | (757) 956-3097 | Sandon Rogers, P.E. | Sandon.rogers@hampton.gov | (757) 727-6786 | 0 |  | 0 | FY2020 | 91000 | 91000 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 93 days early | G | Project is on budget | 2019-10-03 | 2019-10-03 | 2020-01-02 | 2019-11-06 | G | [5 empty] | 2019-10-03 | 2019-10-03 | 2019-10-16 | 2019-10-16 | G | [35 empty] | 2020-01-22 | 2019-10-10 | 2020-02-19 | 2019-11-07 | G | 2020-05-07 | 2020-02-04 | 2020-05-07 | 2020-02-04 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.10588
1700 | 115529 | #SMART20 Median crossover to Rte 13 | 0013 | Primary | Other | VDOT | Northampton County | ACCOMAC | Hampton Roads | NonMPO:NonMPO | Infrastructure Investment Division | John G Harman | JohnG.Harman@vdot.virginia.gov | (757) 956-3269 | John G Harman | JohnG.Harman@vdot.virginia.gov | (757) 956-3269 | Susan McGhee | smcghee@co.northampton.va..us | (757) 678-0443 | 1 | 2020 | 0 | FY2026 | 1120000 | 1120000 | NO DATES SET YET | G | Start Development milestone is 969 days ahead of the expected completion date | Y | Estimate not current | [5 empty] | 2023-08-15 |  | 2023-10-18 |  | G | 2023-10-19 |  | 2024-10-17 |  | G | [5 empty] | 2025-05-28 |  | 2025-07-09 |  | G | [5 empty] | 2025-10-23 |  | 2026-02-23 |  | G | [5 empty] | 2025-10-07 |  | 2026-01-13 |  | G | [5 empty] | 2026-03-10 |  | 2026-03-10 |  | G | 2026-05-29 |  | 2026-05-29 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.12237
1701 | 115790 | Primary Extension - Blacksburg - S Main St | 0460 | Urban | Reconstruction w/o Added Capacity | Locally | Blacksburg | CHRISTIANSBURG | Salem | New River Valley:Blacksburg | Local Assistance Division | Adam J Czesnowski | Adam.Czesnowski@vdot.virginia.gov | (540) 541-1216 | Adam J Czesnowski | Adam.Czesnowski@vdot.virginia.gov | (540) 541-1216 | John Boyer | jboyer@blacksburg.gov | (540) 443-1204 | 0 |  | 0 | FY2020 | 296813 | 296813 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 193 days early | G | Project is on budget | 2020-01-02 | 2019-07-01 | 2020-03-30 | 2019-07-25 | G | 2020-03-31 | 2019-09-03 | 2020-04-02 | 2019-09-05 | G | 2020-04-03 | 2019-09-18 | 2020-10-06 | 2019-09-19 | G | [35 empty] | 2019-12-31 | 2019-11-22 | 2019-12-31 | 2019-11-22 | G | 2020-01-27 | 2019-11-25 | 2020-06-30 | 2019-12-20 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.15914
1702 | 116384 | #I81CIP NWRO SSP | 0081 | Interstate | Safety | VDOT | Staunton District-wide |  | Staunton | NonMPO:NonMPO | Infrastructure Investment Division | Ricky A Via | Ricky.Via@vdot.virginia.gov | (804) 371-2396 | Roy A Reid | Roy.Reid@VDOT.Virginia.gov | (540) 332-9148 |  |  |  | 0 |  | 0 | FY2021 | 8494617 | 8494617 | CONSTRUCTION STARTED | G | Start Delivery milestone finished on-time | G | Project is on budget | [10 empty] | 2020-06-15 | 2020-06-15 | 2020-10-21 | 2020-07-11 | G | [35 empty] | 2020-08-15 | 2020-08-15 | 2020-08-15 | 2020-08-15 | G | 2020-08-17 | 2020-08-17 | 2020-08-17 | 2020-08-17 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | WORK/TASK ORDER | 1 | 0 | 0.071102
1703 | 116709 | LOUDOUN COUNTY PUB SCHOOL SRTS IMPROVEMENTS - COUNTRYSIDE ES |  | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Loudoun County | LEESBURG | Northern Virginia | Northern Virginia:Loudoun County | Local Assistance Division | Amir Salahshoor | A.Salahshoor@VDOT.Virginia.gov | (703) 259-1957 | Saif-Ur Qargha | Saif.Qargha@vdot.virginia.gov | (703) 259-3223 | Loudoun County Public Schools | Sara.HowardOBrien@lcps.org | (703) 969-8919 | 0 |  | 0 | FY2024 | 512814 | 512814 | NO DATES SET YET-PE OPEN | R | Start Development milestone finished 17 days late | G | Project is on budget | 2020-02-18 | 2020-02-18 | 2020-02-28 | 2020-02-27 | G | 2020-03-02 | 2020-02-28 | 2020-03-31 | 2020-04-17 | R | 2020-04-29 | 2020-04-16 | 2021-04-30 |  | G | [10 empty] | 2022-04-28 |  | 2022-05-31 |  | G | [5 empty] | 2022-06-02 |  | 2022-08-01 |  | G | 2020-11-10 |  | 2021-07-19 |  | G | [5 empty] | 2022-08-17 |  | 2023-01-31 |  | G | 2023-04-20 |  | 2023-08-31 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.48669
1704 | 117087 | #REVSH21 WARDS FERRY - CONSTRUCT TURN LANES AT ATLANTA AVE | 9999 | Urban | Safety | Locally | Lynchburg | APPOMATTOX | Lynchburg | Lynchburg:Lynchburg | Local Assistance Division | Gregg Allen | Gregg.Allen@vdot.virginia.gov | (434) 426-5575 | Gregg Allen | Gregg.Allen@vdot.virginia.gov | (434) 426-5575 | LEE NEWLAND | lee.newland@lynchburgva.gov | (434) 455-3947 | 0 |  | 0 | FY2025 | 1702800 | 1702800 | NO DATES SET YET | G | Agreement with Locality milestone is 106 days ahead of the expected completion date | G | Project is on budget | 2021-01-29 |  | 2021-06-07 |  | G | 2021-06-08 |  | 2021-06-28 |  | G | 2022-01-07 |  | 2022-05-03 |  | G | [10 empty] | 2023-08-22 |  | 2023-09-26 |  | G | [5 empty] | 2023-09-27 |  | 2024-03-04 |  | G | 2024-01-30 |  | 2024-06-26 |  | G | [5 empty] | 2024-06-05 |  | 2024-07-02 |  | G | 2024-09-20 |  | 2024-09-20 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.15046
1705 | 118069 | Heritage Trail Park Trail Head Ramp |  | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Lawrenceville | SOUTH HILL | Richmond | NonMPO:NonMPO | Local Assistance Division | Jorg Huckabee-Mayfield | Jorg.Huckabee-Mayfield@VDOT.Virginia.gov | (804) 609-5292 | Jorg Huckabee-Mayfield | Jorg.Huckabee-Mayfield@VDOT.Virginia.gov | (804) 609-5292 | Ashleigh Zincone | azincone@southsidepdc.org | (434) 447-7101 | 0 |  | 0 | FY2024 | 589765 | 589765 | NO DATES SET YET | G | Agreement with Locality milestone is 199 days ahead of the expected completion date | G | Project is on budget | 2021-05-03 |  | 2021-09-08 |  | G | 2021-09-09 |  | 2021-09-29 |  | G | 2022-04-13 |  | 2022-08-04 |  | G | [25 empty] | 2023-08-01 |  | 2024-01-03 |  | G | [5 empty] | 2024-03-05 |  | 2024-04-01 |  | G | 2024-06-19 |  | 2024-06-19 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.3489
1706 | 100778 | #SGR17VB - Bridge REPLACE RT 250 over Bell Ck (VA Str 1028) | 0250 | Primary | Bridge Replacement w/o Added Capacity | VDOT | Augusta County | HARRISONBURG | Staunton | NonMPO:NonMPO | Infrastructure Investment/Asset Management Division | Junyi Y Meng | Junyi.Meng@VDOT.Virginia.gov | (804) 786-3817 | Amedebrhan Asfaw | Amedebrhan.Asfaw@vdot.virginia.gov | (540) 332-9541 |  |  |  | 0 |  | 1 | FY2021 | 4076711 | 5117279 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 416 days early | R | Project estimate is less than $5M and is 20% or more over budget | [5 empty] | 2015-07-02 | 2013-07-15 | 2015-07-02 | 2013-07-16 | G | 2015-08-03 | 2015-06-16 | 2016-02-05 | 2015-12-16 | G | [10 empty] | 2018-05-09 | 2018-08-31 | 2018-05-22 | 2018-09-17 | R | 2018-12-05 | 2019-02-19 | 2019-06-04 | 2019-08-27 | R | 2018-06-06 | 2018-06-04 | 2018-12-04 | 2019-03-01 | R | 2019-10-30 | 2019-03-01 | 2020-12-10 | 2019-08-21 | G | [5 empty] | 2020-12-11 | 2019-10-08 | 2020-12-11 | 2019-10-08 | G | 2021-01-11 | 2020-01-20 | 2021-03-11 | 2020-01-20 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.070736
1707 | 104292 | RTE 625 - WAXPOOL ROAD INTERSECTION IMPROVEMENT | 0625 | Secondary | Reconstruction w/o Added Capacity | Locally | Loudoun County | LEESBURG | Northern Virginia | Northern Virginia:Loudoun County | Local Assistance Division | Kimberly Mccool | Kimberly.McCool@vdot.virginia.gov | (703) 259-3220 | Susie X Lue | Susie.Lue@vdot.virginia.gov | (703) 259-2918 | Balinger, Robert | Robert.Balinger@loudoun.gov | (571) 258-3548 | 0 |  | 0 | FY2020 | 6600000 | 10400000 | ACTIVITY DATES SET | R | Relocate Utilities milestone is 1138 days past the expected completion date | R | Project estimate is between $5M and $10M and is a $1M or more over budget | 2013-01-02 | 2013-01-02 | 2013-06-30 | 2013-09-25 | R | 2013-07-01 | 2013-10-24 | 2014-03-31 | 2013-10-24 | G | 2015-07-01 | 2015-07-01 | 2017-08-30 | 2017-08-30 | G | [10 empty] | 2016-02-10 | 2016-02-10 | 2016-02-10 | 2016-02-10 | G | 2016-02-11 | 2016-10-03 | 2018-01-10 |  | R | 2016-02-11 | 2016-02-11 | 2019-02-12 |  | R | [10 empty] | 2019-06-17 |  | 2019-10-17 |  | R | 2019-02-04 |  | 2019-07-02 |  | R | Delay due to unforeseen issues with utilities, railroad coordination, or right-of-way acquisition | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.39211
1708 | 106175 | #SGR17VB - BR Repl-Roanoke HIll Rd over RT 63 (Fed 16511) | 0687 | Secondary | Bridge Replacement w/o Added Capacity | VDOT | Russell County | LEBANON | Bristol | NonMPO:NonMPO | Infrastructure Investment/Asset Management Division | Gary Lester |  |  | James R Jones | jamesr.jones@vdot.virginia.gov | (276) 696-3257 |  |  |  | 0 |  | 1 | FY2022 | 4495000 | 4495000 | ACTIVITY DATES SET | R | Engage Public milestone is 143 days past the expected completion date | G | Project is on budget | [5 empty] | 2016-08-23 | 2016-08-23 | 2016-10-14 | 2016-10-14 | G | 2018-08-01 | 2018-08-01 | 2019-01-31 | 2020-06-05 | R | 2020-06-08 | 2020-07-28 | 2020-10-01 |  | R | [5 empty] | 2020-11-02 |  | 2020-11-02 |  | R | 2021-10-12 |  | 2022-01-27 |  | G | 2021-03-26 |  | 2021-10-27 |  | G | [10 empty] | 2021-06-07 |  | 2021-06-07 |  | G | 2021-06-08 |  | 2021-09-29 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.06051
1709 | 107189 | MAGNOLIA DRIVE. - MULTI-USE TRAIL/SIDEWALK | 9999 | Miscellaneous | Other | Locally | West Point | SALUDA | Fredericksburg | NonMPO:NonMPO | Local Assistance Division | Michael Doczi |  |  | Marc S Keenan | Marc.Keenan@VDOT.Virginia.gov | (804) 286-3116 | Holly McGowan | hmcgowan@west-point.va.us |  | 0 |  | 0 | FY2019 | 250000 | 250000 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 153 days early | G | Project is on budget | [5 empty] | 2016-12-09 | 2017-02-28 | 2016-12-22 | 2017-03-06 | R | 2016-12-23 | 2017-04-17 | 2017-01-25 | 2017-08-30 | R | [35 empty] | 2018-04-06 | 2017-08-24 | 2018-04-06 | 2017-12-04 | G | 2018-07-25 | 2018-02-09 | 2018-09-26 | 2018-04-26 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.13557
1710 | 115710 | VIENNA TOWN RS MAINTENANCE - MILL AND OVERLAY | 9999 | Urban | Resurfacing | Locally | Vienna | FAIRFAX | Northern Virginia | Northern Virginia:Vienna | Local Assistance Division | Amir Salahshoor | A.Salahshoor@VDOT.Virginia.gov | (703) 259-1957 | Rita Hockman | Rita.Hockman@vdot.virginia.gov | (804) 824-7421 | Michael Gallagher | mgallagher@viennava.gov | (703) 255-6386 | 0 |  | 0 | FY2021 | 539000 | 539000 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 25 days early | G | Project is on budget | 2019-08-30 | 2019-08-22 | 2020-05-29 | 2019-08-22 | G | [5 empty] | 2020-06-01 | 2019-08-22 | 2020-09-30 | 2019-12-30 | G | [35 empty] | 2020-01-15 | 2019-12-31 | 2020-03-30 | 2020-01-15 | G | 2020-06-17 | 2020-06-11 | 2020-08-21 | 2020-07-27 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.16139
1711 | 116268 | #I81CIP SB MM 296 TO 299, 3-LANE WIDENING (ID #50) | 0081 | Interstate | Reconstruction w/ Added Capacity | VDOT | Shenandoah County | EDINBURG | Staunton | NonMPO:NonMPO | Infrastructure Investment Division | John-Allen L Ennis | JohnAllen.Ennis@VDOT.Virginia.gov | (540) 332-9118 | Scott A Alexander | Scott.Alexander@VDOT.Virginia.gov | (540) 332-9030 |  |  |  | 0 |  | 0 | FY2025 | 117561403 | 117561403 | NO DATES SET YET-PE OPEN | G | Start Development milestone finished 159 days early | G | Project is on budget | [5 empty] | 2020-07-01 | 2020-01-27 | 2020-07-15 | 2020-02-07 | G | 2020-07-16 | 2020-02-10 | 2021-08-24 |  | G | [5 empty] | 2022-08-23 |  | 2022-09-06 |  | G | 2023-12-05 |  | 2023-12-18 |  | G | 2024-05-15 |  | 2024-11-19 |  | G | 2024-01-05 |  | 2024-07-11 |  | G | 2023-05-22 |  | 2024-01-29 |  | G | [5 empty] | 2024-12-10 |  | 2024-12-10 |  | G | 2025-04-03 |  | 2025-04-03 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.12902
1712 | 116488 | FY20 Interstate HFST Botetourt Co. LM2B-011-F20 | 0081 | Interstate | Safety | VDOT | Botetourt County | SALEM | Salem | Roanoke:Botetourt County | Infrastructure Investment Division | Francis Scarpinato | Francis.Scarpinato@vdot.virginia.gov | (540) 375-3593 | Ibrahim M Abuawad | Ibrahim.Abuawad@vdot.virginia.gov | (217) 418-8827 |  |  |  | 0 |  | 0 | FY2020 | 1000000 | 1000000 | CONSTRUCTION STARTED | R | Start Delivery milestone finished 84 days late | G | Project is on budget | [10 empty] | 2019-12-18 | 2018-06-22 | 2019-12-24 | 2020-02-25 | R | [35 empty] | 2019-11-05 | 2020-04-07 | 2019-11-05 | 2020-04-07 | R | 2020-02-03 | 2020-06-25 | 2020-04-02 | 2020-06-25 | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 1 | 0.27992
1713 | 116967 | #SGR21LP ROUTE 340 PRIMARY EXTENSION PAVING |  | Primary | Resurfacing | VDOT | Luray | HARRISONBURG | Staunton | NonMPO:NonMPO | Infrastructure Investment Division | Joel D Denunzio | Joel.DeNunzio@VDOT.virginia.gov | (540) 332-9093 | Mark W Hisey | Mark.Hisey@VDOT.Virginia.gov | (540) 280-4820 |  |  |  | 0 |  | 1 | FY2021 | 56312 | 56312 | ACTIVITY DATES SET | Y | Solicit Bids milestone is 51 days ahead of the expected completion date and there is a risk of missing this milestone date | G | Project is on budget | [5 empty] | 2021-01-11 | 2020-11-03 | 2021-02-02 | 2020-11-24 | G | 2021-02-03 | 2020-11-25 | 2021-12-03 | 2021-01-11 | G | [5 empty] | 2021-01-12 | 2021-01-12 | 2021-01-12 | 2021-01-12 | G | [5 empty] | 2020-12-28 | 2021-01-14 | 2021-04-12 | 2021-01-19 | G | [15 empty] | 2021-04-13 |  | 2021-04-13 |  | Y | 2021-06-30 |  | 2021-06-30 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.060465
1714 | 117129 | Johnstown Road Widening | 8663 | Urban | Reconstruction w/o Added Capacity | Locally | Chesapeake | NORFOLK | Hampton Roads | Hampton Roads:Chesapeake | Infrastructure Investment Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Johndel A Alcaide | John.Alcaide@vdot.virginia.gov | (757) 956-3098 | Sam Sawan | sawan@cityofchesapeake.net | (757) 382-8263 | 0 |  | 0 | FY2026 | 22500000 | 22500000 | NO DATES SET YET | R | Agreement with Locality milestone is 72 days past the expected completion date | G | Project is on budget | 2020-08-03 |  | 2020-12-11 |  | R | 2020-12-14 |  | 2021-01-05 |  | R | 2021-07-14 |  | 2022-03-22 |  | G | [10 empty] | 2024-06-19 |  | 2024-07-24 |  | G | [5 empty] | 2024-07-25 |  | 2025-02-19 |  | G | 2024-04-23 |  | 2024-12-26 |  | G | [5 empty] | 2025-05-22 |  | 2025-06-19 |  | G | 2025-09-09 |  | 2025-09-09 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.25801
1715 | 118091 | Lakeside Community Trail Phase 2 |  | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Henrico County | ASHLAND | Richmond | Richmond:Henrico County | Local Assistance Division | Jorg Huckabee-Mayfield | Jorg.Huckabee-Mayfield@VDOT.Virginia.gov | (804) 609-5292 | Jorg Huckabee-Mayfield | Jorg.Huckabee-Mayfield@VDOT.Virginia.gov | (804) 609-5292 | Michael Aust | aus019@henrico.us | (804) 501-4019 | 0 |  | 0 | FY2025 | 2971330 | 2971330 | NO DATES SET YET | G | Agreement with Locality milestone is 80 days ahead of the expected completion date | G | Project is on budget | 2021-01-04 |  | 2021-05-12 |  | G | 2021-05-13 |  | 2021-06-03 |  | G | 2021-12-13 |  | 2022-04-08 |  | G | [10 empty] | 2023-07-28 |  | 2023-08-31 |  | G | [5 empty] | 2023-09-01 |  | 2024-02-07 |  | G | 2023-10-09 |  | 2024-03-14 |  | G | [5 empty] | 2024-05-10 |  | 2024-06-07 |  | G | 2024-08-27 |  | 2024-08-27 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.44356
1716 | 103469 | RTE 636 - BRIDGE REPLACEMENT (FED ID 5271) | 0636 | Secondary | Bridge Replacement w/o Added Capacity | VDOT | Chesterfield County | CHESTERFIELD | Richmond | Tri-Cities:Chesterfield County | Infrastructure Investment Division | Robert F Poutier | Robert.Poutier@vdot.virginia.gov | (804) 609-5368 | Jeremy B Cobb | Jeremy.Cobb@vdot.virginia.gov | (804) 586-2255 |  |  |  | 0 |  | 0 | FY2019 | 2876930 | 2876930 | CONSTRUCTION COMPLETED | R | Start Delivery milestone finished 22 days late | G | Project is on budget | [5 empty] | 2013-07-01 | 2013-09-06 | 2013-07-01 | 2013-09-06 | R | 2016-10-27 | 2016-10-27 | 2017-05-05 | 2017-05-05 | G | [5 empty] | 2017-05-04 | 2017-05-04 | 2017-07-19 | 2017-07-19 | G | 2018-04-19 | 2018-04-19 | 2018-04-30 | 2018-04-30 | G | 2018-12-17 | 2018-11-19 | 2019-04-17 | 2019-03-22 | G | 2018-05-15 | 2018-05-15 | 2018-11-15 | 2018-10-16 | G | 2017-09-26 | 2017-09-26 | 2018-05-30 | 2018-05-30 | G | [5 empty] | 2018-11-06 | 2018-12-04 | 2018-11-06 | 2018-12-04 | R | 2019-01-02 | 2019-02-22 | 2019-01-31 | 2019-02-22 | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 1 | 0.2289
1717 | 105660 | RTE 271 - ADD SIDEWALK | 0271 | Secondary | Facilities for Pedestrians and Bicycles | Locally | Henrico County | ASHLAND | Richmond | Richmond:Henrico County | Local Assistance Division | Brian J Lokker | Brian.Lokker@VDOT.Virginia.gov | (804) 524-6010 | Brian J Lokker | Brian.Lokker@VDOT.Virginia.gov | (804) 524-6010 | Paul Smith | smi91@henrico.us | (804) 501-5092 | 0 |  | 0 | FY2019 | 1342062 | 1342062 | CONSTRUCTION STARTED | R | Start Delivery milestone finished 454 days late | G | Project is on budget | 2014-11-30 | 2014-11-07 | 2014-11-30 | 2014-11-18 | G | 2014-11-01 | 2014-12-02 | 2014-11-01 | 2014-12-02 | R | 2016-02-02 | 2017-04-20 | 2016-04-01 | 2017-05-11 | R | [10 empty] | 2017-11-06 | 2017-11-06 | 2017-11-17 | 2017-11-17 | G | [5 empty] | 2017-09-01 | 2017-09-01 | 2018-06-04 | 2018-10-29 | R | [10 empty] | 2018-07-01 | 2019-06-03 | 2018-07-01 | 2019-11-03 | R | 2018-10-01 | 2019-11-04 | 2018-10-31 | 2020-01-28 | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.35206
1718 | 107117 | #SGR17VB - I-81 STRUCTURES 17470 & 17472 OVER RT 686 | 0081 | Interstate | Bridge Replacement w/o Added Capacity | VDOT | Smyth County | ABINGDON | Bristol | NonMPO:NonMPO | Infrastructure Investment/Asset Management Division | Gary Lester |  |  | David L Lively | David.Lively@VDOT.Virginia.gov | (276) 696-3388 |  |  |  | 0 |  | 1 | FY2019 | 14200000 | 12783860 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished on-time | G | Project is on budget | [10 empty] | 2017-10-18 | 2017-10-17 | 2017-10-24 | 2017-10-24 | G | [35 empty] | 2018-05-08 | 2018-05-08 | 2018-05-08 | 2018-05-08 | G | 2018-07-23 | 2018-09-17 | 2018-09-17 | 2018-09-17 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.063904
1719 | 108853 | East Main Street / College Avenue - Pedestrian Improvements | 0460 | Urban | Facilities for Pedestrians and Bicycles | Locally | Salem | SALEM | Salem | Roanoke:Salem | Local Assistance Division | Cheryl B Becker | Cheryl.Becker@vdot.virginia.gov | (540) 492-2531 | Cheryl B Becker | Cheryl.Becker@vdot.virginia.gov | (540) 492-2531 | Will Simpson | wsimpson@salemva.gov | (540) 375-3032 | 0 |  | 0 | FY2020 | 1001000 | 1572574 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 153 days early | R | Project estimate is less than $5M and is 20% or more over budget | 2016-08-12 | 2016-08-12 | 2018-05-31 | 2018-03-01 | G | 2018-06-01 | 2018-04-19 | 2018-06-05 | 2018-04-23 | G | 2017-06-13 | 2017-06-13 | 2018-06-13 | 2018-04-24 | G | [35 empty] | 2019-09-16 | 2019-08-05 | 2019-10-11 | 2019-09-01 | G | 2019-10-14 | 2019-09-03 | 2020-03-12 | 2019-10-11 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.24793
1720 | 109436 | #HB2.FY17 Leatherwood Lane | 9999 | Urban | Reconstruction w/ Added Capacity | VDOT | Bluefield | LEBANON | Bristol | NonMPO:NonMPO | Infrastructure Investment Division | Dennis R Harris | Dennis.Harris@VDOT.Virginia.gov | (276) 696-3289 | James R Jones | jamesr.jones@vdot.virginia.gov | (276) 696-3257 |  |  |  | 1 | 2017 | 0 | FY2018 | 1271749 | 561700 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 31 days early | G | Project is on budget | [5 empty] | 2016-08-01 | 2016-08-01 | 2016-08-24 | 2016-08-24 | G | 2016-08-15 | 2016-08-15 | 2017-01-10 | 2017-01-10 | G | [5 empty] | 2017-04-24 | 2017-04-24 | 2017-05-05 | 2017-05-05 | G | [5 empty] | 2017-06-23 | 2017-06-23 | 2017-10-17 | 2017-06-23 | G | [15 empty] | 2017-11-14 | 2017-11-07 | 2017-11-14 | 2017-11-07 | G | 2018-01-03 | 2018-01-30 | 2018-03-02 | 2018-01-30 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.095766
1721 | 109581 | #HB2.FY17 - KING & QUEEN COUNTY BUSINESS/TELEWORK CENTER | 0033 | Primary | Traffic Management/Engineering | Locally | King & Queen County | SALUDA | Fredericksburg | NonMPO:NonMPO | Infrastructure Investment Division | Anastasia Kapitan | Anastasia.Kapitan@vdot.virginia.gov | (540) 899-4292 | Anastasia Kapitan | Anastasia.Kapitan@vdot.virginia.gov | (540) 899-4292 | Thomas j. Swartzwolder | tswartzwelder@kingandqueenco.n | (804) 785-5975 | 1 | 2017 | 0 | FY2022 | 752350 | 752350 | ACTIVITY DATES SET | Y | Solicit Bids milestone is 36 days ahead of the expected completion date and there is a risk of missing this milestone date | G | Project is on budget | 2018-04-04 | 2018-01-31 | 2018-06-27 | 2018-10-23 | R | 2018-06-28 | 2018-06-19 | 2018-07-02 | 2018-10-23 | R | 2018-07-03 | 2018-10-23 | 2018-11-27 | 2018-11-27 | G | [35 empty] | 2021-02-01 |  | 2021-03-29 |  | Y | 2021-03-30 |  | 2021-09-23 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.13994
1722 | 111084 | CORRIDOR SIGNAL TIMING OPTIMIZATION PROG |  | Urban | Safety | Locally | Harrisonburg | HARRISONBURG | Staunton | Harrisonburg:Harrisonburg | Infrastructure Investment Division | Keith M Rider | Keith.Rider@VDOT.Virginia.gov | (434) 856-8145 | Kunal Kothawade | Kunal.Kothawade@vdot.virginia.gov | (540) 332-9259 | Harrisonburg City |  |  | 0 |  | 0 | FY2022 | 199675 | 199675 | ACTIVITY DATES SET | G | Determine Requirements milestone finished 85 days early | G | Project is on budget | 2017-07-13 | 2018-12-07 | 2019-05-03 | 2019-01-07 | G | 2019-05-06 | 2019-01-08 | 2019-09-25 | 2019-07-25 | G | 2019-09-26 | 2019-07-01 | 2020-08-27 | 2020-06-03 | G | [35 empty] | 2021-10-28 |  | 2021-11-29 |  | G | 2021-11-30 |  | 2022-04-11 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.078154
1723 | 111753 | #HB2.FY17 - ROUTE 1 at POTOMAC CREEK DR TURN LANE | 0001 | Primary | Safety | VDOT | Stafford County | FREDERICKSBURG | Fredericksburg | Fredericksburg:Stafford County | Infrastructure Investment Division | Khalil Minhas | Khalil.Minhas@vdot.virginia.gov | (540) 374-3369 | Sylvester C Okpala | Sylvester.Okpala@VDOT.Virginia.gov | (540) 907-8174 | Keith Dayton | kdayton@co.stafford.va.us | (540) 658-5125 | 1 | 2017 | 0 | FY2020 | 1800000 | 1976338 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 75 days early | Y | Project estimate is less than $5M and is up to 20% over budget | [5 empty] | 2017-06-21 | 2017-06-28 | 2017-07-05 | 2017-07-12 | R | 2017-07-06 | 2017-07-13 | 2018-01-30 | 2018-01-22 | G | [5 empty] | 2018-06-11 | 2018-04-04 | 2018-06-15 | 2018-06-01 | G | 2018-06-14 | 2018-06-11 | 2018-06-27 | 2018-06-12 | G | 2018-11-21 | 2018-06-14 | 2019-05-31 | 2019-05-31 | G | 2018-07-16 | 2018-06-20 | 2019-01-24 | 2019-01-07 | G | 2018-07-17 | 2018-07-17 | 2019-05-06 | 2019-02-21 | G | [5 empty] | 2019-06-11 | 2019-06-11 | 2019-06-11 | 2019-06-11 | G | 2019-09-11 | 2019-08-23 | 2019-11-06 | 2019-08-23 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.061768
1724 | 112983 | GRASTY STREET - MILLING, PAVING & RECONSTRUCTION | 9999 | Primary | Resurfacing | Locally | Orange | LOUISA | Culpeper | NonMPO:NonMPO | Local Assistance Division | Ken Connors |  |  | Bobby J Jenkins | Bobby.JenkinsJr@VDOT.Virginia.gov | (540) 829-7694 | JOHN COOLEY | townplanner@townoforangeva.org | (540) 672-6917 | 0 |  | 0 | FY2019 | 23640 | 23640 | WAITING FINANCIAL CLOSURE | G | Obtained Permits milestone finished on-time | G | Project is on budget | 2020-02-24 | 2018-06-01 | 2020-05-15 | 2018-07-09 | G | [5 empty] | 2020-02-24 | 2018-11-01 | 2020-03-06 | 2018-11-30 | G | [25 empty] | 2019-07-22 | 2019-07-22 | 2019-07-23 | 2019-07-23 | G | [5 empty] | 2018-12-06 | 2018-12-06 | 2019-01-15 | 2019-01-15 | G | 2019-01-16 | 2019-01-16 | 2019-02-01 | 2019-02-01 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.079597
1725 | 113691 | #SGR19LP - Kempsville Road, Segment 3 | 0190 | Urban | Resurfacing | Locally | Chesapeake | NORFOLK | Hampton Roads | Hampton Roads:Chesapeake | Infrastructure Investment Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Johndel A Alcaide | John.Alcaide@vdot.virginia.gov | (757) 956-3098 | Sam Sawan | sawan@cityofchesapeake.net | (757) 382-8263 | 0 |  | 1 | FY2019 | 172000 | 172000 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 29 days early | G | Project is on budget | 2018-09-04 | 2018-07-31 | 2018-11-30 | 2018-09-04 | G | 2018-12-03 | 2018-10-25 | 2018-12-05 | 2018-11-19 | G | 2018-12-06 | 2018-11-20 | 2019-06-13 | 2019-05-15 | G | [25 empty] | 2019-05-16 | 2019-05-15 | 2019-05-30 | 2019-05-16 | G | [5 empty] | 2019-06-10 | 2019-05-30 | 2019-06-10 | 2019-05-30 | G | 2019-06-28 | 2019-05-30 | 2019-06-28 | 2019-05-30 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.11581
1726 | 114576 | Streetscape Enhancement Project - Phase III | 0055 | Primary | Reconstruction w/o Added Capacity | Locally | Strasburg | EDINBURG | Staunton | NonMPO:NonMPO | Local Assistance Division | Kimberly Cameron | Kim.Cameron@vdot.virginia.gov | (540) 332-7886 | Jamison Brown | Jamison.Brown@vdot.virginia.gov | (540) 332-7389 | Wyatt Pearson | wpearson@strsburgva.com | (540) 465-9197 | 0 |  | 0 | FY2020 | 959216 | 1469856 | AWARDED | R | Start Delivery milestone finished 368 days late | R | Project estimate is less than $5M and is 20% or more over budget | 2018-12-03 | 2018-12-03 | 2019-03-01 | 2019-01-28 | G | 2019-03-04 | 2019-01-29 | 2019-03-06 | 2019-09-04 | R | 2019-03-07 | 2019-03-07 | 2019-09-09 | 2019-08-15 | G | [25 empty] | 2019-08-07 | 2019-09-05 | 2020-04-22 | 2019-09-05 | G | [5 empty] | 2019-08-26 | 2019-08-26 | 2019-09-23 | 2020-11-05 | R | 2019-12-16 | 2020-12-18 | 2019-12-16 | 2020-12-18 | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.28334
1727 | 115119 | #SMART20 DIXON STREET/LANSDOWNE ROAD INX IMPROVEMENTS | 0002 | Urban | Reconstruction w/ Added Capacity | VDOT | Fredericksburg | FREDERICKSBURG | Fredericksburg | Fredericksburg:Fredericksburg | Infrastructure Investment Division | Catherine C Coffey | Catherine.Coffey@vdot.virginia.gov | (540) 899-4280 | Curtis B Holloway | Curtis.Holloway@vdot.virginia.gov | (540) 374-3367 | Erik Nelson | ENELSON@FREDERICKSBURGVA.GOV | (540) 937-0572 | 1 | 2020 | 0 | FY2027 | 2200000 | 2200000 | NO DATES SET YET | G | Start Development milestone is 974 days ahead of the expected completion date | G | Project is on budget | [5 empty] | 2023-10-02 |  | 2023-10-23 |  | G | 2023-10-24 |  | 2024-08-26 |  | G | [5 empty] | 2025-04-01 |  | 2025-04-28 |  | G | 2025-12-18 |  | 2026-01-27 |  | G | 2026-06-25 |  | 2026-10-26 |  | G | 2026-02-11 |  | 2026-07-10 |  | G | 2026-03-19 |  | 2026-08-14 |  | G | [5 empty] | 2026-11-10 |  | 2026-11-10 |  | G | 2027-02-05 |  | 2027-02-05 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.15032
1728 | 115556 | #SMART20 - US 33 Leigh St Streetscape Improvements | 9999 | Urban | Facilities for Pedestrians and Bicycles | Locally | Richmond | ASHLAND | Richmond | Richmond:Richmond | Infrastructure Investment Division | Melinda G Baicy | Melinda.Baicy@vdot.virginia.gov | (804) 609-5390 | Melinda G Baicy | Melinda.Baicy@vdot.virginia.gov | (804) 609-5390 | Lamont Benjamin |  |  | 1 | 2020 | 0 | FY2027 | 6608000 | 6608000 | NO DATES SET YET | G | Agreement with Locality milestone is 1073 days ahead of the expected completion date | G | Project is on budget | 2023-10-30 |  | 2024-01-30 |  | G | 2024-01-31 |  | 2024-02-02 |  | G | 2024-02-05 |  | 2024-08-07 |  | G | [10 empty] | 2025-06-04 |  | 2025-06-24 |  | G | 2025-06-26 |  | 2026-04-09 |  | G | [5 empty] | 2024-09-13 |  | 2025-05-21 |  | G | [5 empty] | 2026-04-27 |  | 2026-05-22 |  | G | 2026-08-12 |  | 2026-08-12 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.14434
1729 | 116694 | 22nd Street & Cove Road Drainage Improvements | 0000 | Urban | Mitigation of Water Pollution Due to Highway Runof | Locally | Roanoke | SALEM | Salem | Roanoke:Roanoke City | Local Assistance Division | Cheryl B Becker | Cheryl.Becker@vdot.virginia.gov | (540) 492-2531 | Cheryl B Becker | Cheryl.Becker@vdot.virginia.gov | (540) 492-2531 | Joseph Arthur | Joseph.Arthur@roanokeva.gov | (540) 853-5901 | 0 |  | 0 | FY2024 | 790000 | 790000 | ACTIVITY DATES SET | G | Determine Requirements milestone finished on-time | G | Project is on budget | 2020-04-03 | 2020-04-03 | 2020-06-26 | 2020-06-18 | G | 2020-06-29 | 2020-06-19 | 2020-07-01 | 2020-06-24 | G | 2020-07-02 | 2020-06-25 | 2021-01-11 | 2021-01-11 | G | [25 empty] | 2021-02-11 |  | 2021-10-12 |  | G | [5 empty] | 2023-07-05 |  | 2023-08-01 |  | G | 2023-10-20 |  | 2023-10-20 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.20547
1730 | 109478 | #HB2.FY17 RTE 3 PASSING LANES POTOMAC MILLS/FLAT IRON | 0003 | Primary | Reconstruction w/ Added Capacity | VDOT | Westmoreland County | NORTHERN NECK | Fredericksburg | NonMPO:NonMPO | Infrastructure Investment Division | Khalil Minhas | Khalil.Minhas@vdot.virginia.gov | (540) 374-3369 | Benjamin Ernst | Benjamin.Ernst@vdot.virginia.gov | (571) 585-0902 |  |  |  | 1 | 2017 | 0 | FY2021 | 12750000 | 11078226 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 44 days early | G | Project is on budget | [5 empty] | 2016-06-29 | 2016-06-29 | 2016-06-29 | 2016-06-29 | G | 2016-08-01 | 2016-08-01 | 2017-07-07 | 2017-07-07 | G | [5 empty] | 2017-12-28 | 2017-12-15 | 2018-01-11 | 2017-12-15 | G | 2019-02-07 | 2018-11-28 | 2019-02-21 | 2018-11-30 | G | 2020-01-10 | 2019-12-02 | 2020-08-13 | 2020-08-10 | G | 2019-03-11 | 2018-12-18 | 2020-03-10 | 2020-03-03 | G | 2018-01-17 | 2017-12-04 | 2019-01-15 | 2019-03-20 | R | [5 empty] | 2020-09-08 | 2020-09-08 | 2020-09-08 | 2020-09-08 | G | 2020-11-02 | 2020-11-17 | 2020-12-31 | 2020-11-17 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.090175
1731 | 110932 | #SMART18 - TWIN LAKE-KENSINGTON BIKE/PED CONNECTOR | 0001 | Primary | Facilities for Pedestrians and Bicycles | VDOT | Fredericksburg | FREDERICKSBURG | Fredericksburg | Fredericksburg:Fredericksburg | Infrastructure Investment Division | Anastasia Kapitan | Anastasia.Kapitan@vdot.virginia.gov | (540) 899-4292 | Anastasia Kapitan | Anastasia.Kapitan@vdot.virginia.gov | (540) 899-4292 | Erik Nelson | enelson@fredericksburgva.gov | (540) 372-1080 | 1 | 2018 | 0 | FY2023 | 1981550 | 1981550 | NO DATES SET YET-PE OPEN | R | Determine Requirements milestone is 662 days past the expected completion date | G | Project is on budget | [5 empty] | 2018-07-26 | 2020-05-14 | 2018-08-08 | 2020-05-14 | R | 2018-08-09 | 2020-05-15 | 2019-05-01 |  | R | [5 empty] | 2020-09-23 |  | 2020-10-21 |  | R | 2021-06-16 |  | 2021-07-21 |  | G | 2021-12-22 |  | 2022-04-26 |  | G | 2021-08-05 |  | 2022-01-07 |  | G | 2021-09-09 |  | 2022-02-14 |  | G | [5 empty] | 2022-05-10 |  | 2022-05-10 |  | G | 2022-07-29 |  | 2022-07-29 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.11675
1732 | 111538 | CITY OF FAIRFAX PRIMARY EXTENSION PAVING FY18 - LEE HWY | 0029 | Urban | Resurfacing | Locally | Fairfax | FAIRFAX | Northern Virginia | Northern Virginia:Fairfax | Local Assistance Division | Amir Salahshoor | A.Salahshoor@VDOT.Virginia.gov | (703) 259-1957 | Rita Hockman | Rita.Hockman@vdot.virginia.gov | (804) 824-7421 | Peter Millard | peter.millard@fairfaxva.gov | (703) 246-6330 | 0 |  | 0 | FY2019 | 220134 | 220134 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 140 days early | G | Project is on budget | 2017-07-03 | 2017-07-03 | 2017-10-25 | 2017-07-28 | G | [5 empty] | 2017-07-03 | 2012-11-09 | 2017-07-17 | 2017-12-12 | R | [35 empty] | 2017-12-13 | 2017-12-13 | 2018-06-29 | 2018-03-21 | G | 2018-07-02 | 2018-03-23 | 2018-08-10 | 2018-03-23 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.17555
1733 | 112750 | Route 11 Structure 1021 over Sinking Creek - Fed ID 18844 | 0011 | Primary | Bridge Replacement w/o Added Capacity | VDOT | Washington County | ABINGDON | Bristol | Bristol:Washington County | Infrastructure Investment Division | Allan D Sumpter | Allan.Sumpter@VDOT.virginia.gov | (276) 525-6461 | Brandi Halloway | Brandi.Halloway@vdot.virginia.gov | (276) 696-3254 |  |  |  | 0 |  | 0 | FY2022 | 1960792 | 1960792 | ACTIVITY DATES SET | G | Relocate Utilities milestone finished 419 days early | G | Project is on budget | [5 empty] | 2018-09-13 | 2018-09-13 | 2018-10-03 | 2018-09-25 | G | 2018-10-04 | 2018-09-26 | 2019-08-08 | 2020-03-19 | R | [5 empty] | 2020-09-30 | 2020-09-30 | 2020-10-28 | 2020-10-28 | G | 2021-04-20 | 2020-12-31 | 2021-05-24 | 2020-12-31 | G | 2021-10-22 | 2020-12-16 | 2022-03-01 | 2021-01-06 | G | 2021-06-09 | 2020-12-31 | 2021-11-05 | 2020-12-31 | G | [10 empty] | 2022-03-08 |  | 2022-03-08 |  | G | 2022-05-25 |  | 2022-05-25 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.060447
1734 | 112986 | MASON STREET - MILLING, PAVEMENT & RECONSTRUCTION | 9999 | Primary | Resurfacing | Locally | Orange | LOUISA | Culpeper | NonMPO:NonMPO | Local Assistance Division | Ken Connors |  |  | Bobby J Jenkins | Bobby.JenkinsJr@VDOT.Virginia.gov | (540) 829-7694 | John Cooley | townplanner@townoforangeva.org | (540) 672-6917 | 0 |  | 0 | FY2019 | 24848 | 24848 | WAITING FINANCIAL CLOSURE | G | Obtained Permits milestone finished on-time | G | Project is on budget | 2020-02-24 | 2018-06-01 | 2020-05-15 | 2018-07-09 | G | [5 empty] | 2020-02-24 | 2018-11-01 | 2020-03-06 | 2018-11-30 | G | [25 empty] | 2019-07-22 | 2019-07-22 | 2019-07-23 | 2019-07-23 | G | [5 empty] | 2018-12-06 | 2018-12-06 | 2019-01-15 | 2019-01-15 | G | 2019-01-16 | 2019-01-16 | 2019-02-01 | 2019-02-01 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.079599
1735 | 113879 | #SGR19LB??- Goodson St / Beaver Crk Bristol VA 1802 Fed 1997 | 0000 | Urban | Bridge Replacement w/o Added Capacity | Locally | Bristol | ABINGDON | Bristol | Bristol:Bristol | Infrastructure Investment/Asset Management Division | John W Bechtold | John.Bechtold@vdot.virginia.gov | (276) 696-3365 | Kenneth R Plummer | KR.Plummer@VDOT.Virginia.gov | (276) 696-3261 | Wallace McCulloch | wallace.mcculloch@bristolva.org | (276) 642-2316 | 0 |  | 1 | FY2023 | 1957937 | 1957937 | NO DATES SET YET-PE OPEN | R | Determine Requirements milestone is 26 days past the expected completion date | G | Project is on budget | 2019-11-05 | 2019-10-01 | 2020-05-04 | 2020-01-14 | G | 2020-05-05 | 2020-01-15 | 2020-06-16 | 2020-01-16 | G | 2020-06-17 | 2020-03-02 | 2021-01-26 |  | R | [25 empty] | 2021-04-22 |  | 2022-01-27 |  | G | [5 empty] | 2022-07-07 |  | 2022-09-08 |  | G | 2022-12-01 |  | 2022-12-01 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.060425
1736 | 114671 | RECTANGULAR RAPID FLASHING BEACON GEORGE MASON DR & 4TH ST N | 6710 | Secondary | Safety | Locally | Arlington County | FAIRFAX | Northern Virginia | Northern Virginia:Arlington County | Infrastructure Investment Division | Terry Yates | Terry.Yates@vdot.virginia.gov | (703) 259-2118 | Rita Hockman | Rita.Hockman@vdot.virginia.gov | (804) 824-7421 | Dan Nabors | dnabors@arlingtonva.us | (703) 228-3726 | 0 |  | 0 | FY2020 | 40000 | 40000 | CONSTRUCTION COMPLETED | R | Start Delivery milestone finished 71 days late | G | Project is on budget | 2019-02-01 | 2019-02-01 | 2019-04-26 | 2019-04-17 | G | 2019-04-29 | 2019-04-18 | 2019-05-01 | 2019-05-01 | G | 2019-05-02 | 2019-05-02 | 2019-06-27 | 2019-05-24 | G | [35 empty] | 2019-09-06 | 2019-09-12 | 2019-09-12 | 2019-09-12 | G | 2019-12-05 | 2020-02-14 | 2019-12-05 | 2020-02-14 | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.27509
1737 | 115302 | PRIMARY EXTENSION PAVING FY20 - HERNDON PARKWAY - 2442 | 0228 | Urban | Resurfacing | Locally | Herndon | FAIRFAX | Northern Virginia | Northern Virginia:Herndon | Local Assistance Division | Andrew G Beacher | Andrew.Beacher@vdot.virginia.gov | (703) 259-2239 | Rita Hockman | Rita.Hockman@vdot.virginia.gov | (804) 824-7421 | John Irish | john.irish@herndonva.gov | (703) 435-6853 | 0 |  | 1 | FY2019 |  |  | WAITING FINANCIAL CLOSURE | G | Determine Requirements milestone finished 16 days early | R | Critical information missing | 2019-07-01 | 2019-07-01 | 2019-09-30 | 2019-09-30 | G | [5 empty] | 2019-10-01 | 2019-10-15 | 2019-10-31 | 2019-10-15 | G | [25 empty] | 2019-10-01 | 2019-05-01 | 2019-11-27 | 2019-05-01 | G | [5 empty] | 2019-12-02 | 2019-05-03 | 2019-12-31 | 2019-05-03 | G | 2019-05-03 | 2019-05-03 | 2019-05-03 | 2019-05-03 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.1737
1738 | 116474 | ROUTE 7 DYNAMIC FLASHERS AT ROUTE 601 INTERSECTION | 0007 | Primary | Safety | VDOT | Clarke County | EDINBURG | Staunton | NonMPO:NonMPO | Infrastructure Investment Division | Matthew Bond | Matthew.Bond@vdot.virginia.gov | (540) 332-9275 | Michael L Surratt | Michael.Surratt@VDOT.Virginia.gov | (540) 332-9325 |  |  |  | 0 |  | 0 | FY2020 | 100000 | 100000 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 80 days early | G | Project is on budget | [5 empty] | 2019-10-22 | 2019-10-22 | 2019-10-22 | 2019-12-27 | R | 2019-10-23 | 2019-10-23 | 2020-02-06 | 2020-01-16 | G | [5 empty] | 2020-03-27 | 2020-02-05 | 2020-04-09 | 2020-02-06 | G | [25 empty] | 2020-04-27 | 2020-02-12 | 2020-05-01 | 2020-02-14 | G | 2020-05-04 | 2020-02-17 | 2020-05-08 | 2020-02-18 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | WORK/TASK ORDER | 1 | 0 | 0.060936
1739 | 116720 | ROUTE 360 AT OTTERDALE ROAD - INSTALL TRAFFIC SIGNAL | 0360 | Primary | Other | VDOT | Chesterfield County | CHESTERFIELD | Richmond | Richmond:Chesterfield County | Infrastructure Investment Division | Rebecca J Worley | Rebecca.Worley@vdot.virginia.gov | (804) 674-2775 | Adam S Brooks | Adam.Brooks@VDOT.Virginia.gov | (804) 609-5274 |  |  |  | 0 |  | 0 | FY2022 | 509528 | 509528 | ACTIVITY DATES SET | G | Determine Requirements milestone finished on-time | G | Project is on budget | [10 empty] | 2020-07-01 | 2020-07-01 | 2020-11-06 | 2020-11-06 | G | [35 empty] | 2021-08-18 |  | 2021-08-24 |  | G | 2021-08-25 |  | 2021-08-31 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | WORK/TASK ORDER | 0 | 0 | 0.10879
1740 | 117144 | #SGR21LP 109-City of Emporia 274 Main St N | 0301 | Urban | Resurfacing | Locally | Emporia | FRANKLIN | Hampton Roads | Hampton Roads:Emporia | Infrastructure Investment/Asset Management Division | Susan Wilson | Susan.Wilson@vdot.virginia.gov | (757) 956-3099 | Marci Thompson | Marci.Thompson@vdot.virginia.gov | (757) 956-3093 | Alton Mason | alton.mason@ci.emporia.va.us | (434) 634-4500 | 0 |  | 1 | FY2024 | 409065 | 409065 | NO DATES SET YET | R | Agreement with Locality milestone is 39 days past the expected completion date | G | Project is on budget | 2020-09-01 |  | 2021-01-13 |  | R | 2021-01-14 |  | 2021-02-05 |  | R | 2021-08-12 |  | 2021-12-08 |  | G | [25 empty] | 2022-12-05 |  | 2023-05-05 |  | G | [5 empty] | 2023-07-05 |  | 2023-08-01 |  | G | 2023-10-20 |  | 2023-10-20 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.10064
1741 | 117387 | HSIP HR High-Visibility Backplates #2 | 9999 | Miscellaneous | Safety | VDOT | Hampton Roads District-wide |  | Hampton Roads | Hampton Roads:Hampton Roads District-wide | Infrastructure Investment/Asset Management Division | Mark S Winslow | Mark.Winslow@VDOT.Virginia.gov | (757) 925-1528 | Mark S Winslow | Mark.Winslow@VDOT.Virginia.gov | (757) 925-1528 |  |  |  | 0 |  | 0 | FY2021 | 259000 | 259000 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 56 days early | G | Project is on budget | [10 empty] | 2021-07-13 | 2020-06-15 | 2021-11-18 | 2020-07-08 | G | [35 empty] | 2020-09-14 | 2020-07-29 | 2020-09-18 | 2020-07-30 | G | 2020-09-21 | 2020-07-31 | 2020-09-25 | 2020-07-31 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | WORK/TASK ORDER | 1 | 0 | 0.076311
1742 | 70578 | PED AND ADA IMPROVEMENTS @ MAIN ST & MAPLE AVE-PURCELLVILLE | 0007 | Urban | Safety | Locally | Purcellville | LEESBURG | Northern Virginia | Northern Virginia:Purcellville | Infrastructure Investment Division | Amir Salahshoor | A.Salahshoor@VDOT.Virginia.gov | (703) 259-1957 | Rita Hockman | Rita.Hockman@vdot.virginia.gov | (804) 824-7421 | Dale Lehnig | dlehnig@purcellvilleva.gov | (540) 751-2314 | 0 |  | 0 | FY2019 | 200000 | 578000 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 91 days early | R | Project estimate is less than $5M and is 20% or more over budget | 2009-09-01 | 2009-09-01 | 2009-09-01 | 2009-09-01 | G | 2005-01-03 | 2004-06-03 | 2005-01-31 | 2004-09-30 | G | 2005-02-01 | 2005-02-01 | 2005-07-31 | 2005-07-31 | G | [10 empty] | 2018-01-31 | 2018-01-31 | 2018-02-08 | 2018-02-08 | G | [20 empty] | 2018-10-01 | 2018-10-01 | 2018-12-28 | 2018-12-07 | G | 2019-03-15 | 2019-02-25 | 2019-06-14 | 2019-03-15 | G | Awaiting authorization before work can proceed | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.28219
1743 | 98883 | RTE 144 (TEMPLE AVE) - SIGNAL COORDINATION | 0144 | Urban | Safety | Locally | Colonial Heights | CHESTERFIELD | Richmond | Tri-Cities:Colonial Heights | Infrastructure Investment Division | Brian J Lokker | Brian.Lokker@VDOT.Virginia.gov | (804) 524-6010 | Brian J Lokker | Brian.Lokker@VDOT.Virginia.gov | (804) 524-6010 | Keith A Chisolm | chisolmk@colonialheightsva.gov | (804) 520-9215 | 0 |  | 0 | FY2020 | 568620 | 623429 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 61 days early | Y | Project estimate is less than $5M and is up to 20% over budget | 2013-06-03 | 2018-07-01 | 2018-11-30 | 2018-08-14 | G | 2015-11-02 | 2013-07-12 | 2016-11-30 | 2013-07-12 | G | 2015-12-10 | 2015-12-10 | 2019-02-28 | 2019-02-24 | G | [5 empty] | 2019-06-17 | 2019-05-28 | 2019-07-05 | 2019-05-29 | G | [15 empty] | 2019-06-28 | 2019-05-14 | 2019-09-27 | 2019-05-14 | G | [5 empty] | 2019-09-30 | 2019-09-26 | 2019-09-30 | 2019-09-26 | G | 2019-12-05 | 2019-10-03 | 2019-12-31 | 2019-10-31 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.15297
1744 | 103025 | Portsmouth Traffic Signal Upgrades | 0000 | Urban | Safety | Locally | Portsmouth | NORFOLK | Hampton Roads | Hampton Roads:Portsmouth | Infrastructure Investment Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Marci Thompson | Marci.Thompson@vdot.virginia.gov | (757) 956-3093 | James E. Wright, Jr., PE | wrightj@portsmouthva.gov | (757) 393-8592 | 0 |  | 0 | FY2022 | 4936344 | 4936344 | ACTIVITY DATES SET | G | Engage Public milestone finished 83 days early | G | Project is on budget | [5 empty] | 2017-01-05 | 2017-01-05 | 2017-06-29 | 2017-06-29 | G | 2018-01-31 | 2018-08-28 | 2019-03-08 | 2019-08-13 | R | 2019-11-25 | 2019-10-18 | 2020-01-09 | 2019-10-18 | G | [30 empty] | 2021-08-04 |  | 2021-09-15 |  | G | 2021-12-08 |  | 2022-04-19 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NOT APPLICABLE | 0 | 1 | 0.2172
1745 | 105495 | #HB2.FY17 CONN. ROAD - 2 LANES WITH CURB & GUTTER - PHASE II | 0000 | Urban | New Construction Roadway | VDOT | Wytheville | WYTHEVILLE | Bristol | NonMPO:NonMPO | Infrastructure Investment Division | Tamara D Pritchard | Tamara.Pritchard@VDOT.Virginia.gov | (276) 696-3249 | James M Bullins | James.Bullins@VDOT.Virginia.gov | (276) 696-3349 |  |  |  | 1 | 2017 | 0 | FY2017 | 6107013 | 6325951 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished on-time | Y | Project estimate is between $5M and $10M and is up to $1M over budget | [5 empty] | 2014-05-01 | 2014-09-23 | 2014-10-01 | 2014-09-30 | G | 2015-11-05 | 2015-11-05 | 2015-11-09 | 2015-11-09 | G | [15 empty] | 2016-09-06 | 2016-09-06 | 2017-02-17 | 2017-02-17 | G | [15 empty] | 2016-11-08 | 2016-11-08 | 2016-11-08 | 2016-11-08 | G | 2017-01-27 | 2017-01-27 | 2017-01-27 | 2017-01-27 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.10481
1746 | 107921 | RURAL RETREAT SIDEWALKS, PHASE 9 & 10 |  | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Rural Retreat | WYTHEVILLE | Bristol | NonMPO:NonMPO | Local Assistance Division | Tabitha H Crowder | Tabitha.Crowder@vdot.virginia.gov | (276) 696-3482 | Roger L Musser | Roger.Musser@VDOT.Virginia.gov | (276) 696-3260 | Town of Rural Retreat |  |  | 0 |  | 0 | FY2019 | 610000 | 1054000 | ACTIVITY DATES SET | R | Solicit Bids milestone is 866 days past the expected completion date | R | Project estimate is less than $5M and is 20% or more over budget | 2016-07-01 | 2016-07-01 | 2016-09-26 | 2016-09-26 | G | 2016-09-27 | 2016-09-27 | 2016-10-11 | 2016-10-10 | G | 2016-10-12 | 2016-10-11 | 2017-06-09 | 2017-06-09 | G | [10 empty] | 2018-05-01 | 2018-05-01 | 2018-05-14 | 2018-05-14 | G | [20 empty] | 2018-06-18 | 2019-07-17 | 2018-10-09 |  | R | 2019-06-27 |  | 2019-06-27 |  | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.29392
1747 | 110900 | RT 635 INTERSECTION IMPROVEMENT AT RT 1035 | 0635 | Primary | Safety | VDOT | Spotsylvania County | FREDERICKSBURG | Fredericksburg | Fredericksburg:Spotsylvania County | Infrastructure Investment Division | Peter A Hedrich | Peter.Hedrich@vdot.virginia.gov | (540) 899-4540 | Khalil Minhas | Khalil.Minhas@vdot.virginia.gov | (540) 374-3369 |  |  |  | 0 |  | 0 | FY2026 | 657500 | 657500 | NO DATES SET YET | G | Start Development milestone is 235 days ahead of the expected completion date | G | Project is on budget | [5 empty] | 2021-10-01 |  | 2021-10-14 |  | G | 2021-10-15 |  | 2022-09-14 |  | G | [5 empty] | 2023-07-21 |  | 2023-08-03 |  | G | 2024-11-07 |  | 2024-11-21 |  | G | 2025-04-22 |  | 2025-10-24 |  | G | 2024-12-11 |  | 2025-06-18 |  | G | 2024-04-29 |  | 2024-10-31 |  | G | [5 empty] | 2025-11-10 |  | 2025-11-10 |  | G | 2025-12-30 |  | 2026-02-27 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.063081
1749 | 111264 | #SGR18LB - RT 19 Tazewell Co VA #1804 Federal STR 22546 | 0019 | Urban | Bridge Rehab w/o Added Capacity | VDOT | Tazewell | LEBANON | Bristol | NonMPO:NonMPO | Infrastructure Investment Division | Gary Lester |  |  | Haven P Wright | Haven.Wright@VDOT.Virginia.gov | (276) 696-3393 |  |  |  | 0 |  | 1 | FY2019 | 1100000 | 1019630 | CONSTRUCTION COMPLETED | R | Start Delivery milestone finished 136 days late | G | Project is on budget | [5 empty] | 2017-07-03 | 2017-07-26 | 2017-07-17 | 2017-07-26 | R | 2017-07-18 | 2017-08-01 | 2017-08-14 | 2017-08-01 | G | [35 empty] | 2019-01-08 | 2019-05-07 | 2019-01-08 | 2019-05-07 | R | 2019-02-25 | 2019-07-29 | 2019-03-15 | 2019-07-29 | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.18963
1750 | 117181 | OBMS Cycle Track | 0000 | Urban | Facilities for Pedestrians and Bicycles | Locally | Blacksburg | CHRISTIANSBURG | Salem | New River Valley:Blacksburg | Local Assistance Division | Adam J Czesnowski | Adam.Czesnowski@vdot.virginia.gov | (540) 541-1216 | Adam J Czesnowski | Adam.Czesnowski@vdot.virginia.gov | (540) 541-1216 | Randy Formica | rformica@blacksburg.gov | (540) 443-1300 | 0 |  | 0 | FY2028 | 681699 | 681699 | NO DATES SET YET | G | Agreement with Locality milestone is 1422 days ahead of the expected completion date | G | Project is on budget | 2024-08-30 |  | 2025-01-13 |  | G | 2025-01-14 |  | 2025-02-05 |  | G | 2025-08-12 |  | 2025-12-08 |  | G | [25 empty] | 2026-12-03 |  | 2027-05-05 |  | G | [5 empty] | 2027-07-02 |  | 2027-07-30 |  | G | 2027-10-20 |  | 2027-10-20 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.1623
1751 | 118173 | #SGR21LP - Pulaski FKEY 1144 W Main St | 0000 | Urban | Resurfacing | Locally | Pulaski | CHRISTIANSBURG | Salem | NonMPO:NonMPO | Infrastructure Investment/Asset Management Division | Adam J Czesnowski | Adam.Czesnowski@vdot.virginia.gov | (540) 541-1216 | Adam J Czesnowski | Adam.Czesnowski@vdot.virginia.gov | (540) 541-1216 | Rick Tawney | rtawney@pulaskitown.org | (540) 994-8618 | 0 |  | 1 | FY2024 | 155815 | 155815 | NO DATES SET YET | G | Agreement with Locality milestone is 50 days ahead of the expected completion date | G | Project is on budget | 2020-12-01 |  | 2021-04-12 |  | G | 2021-04-13 |  | 2021-05-03 |  | G | 2021-11-08 |  | 2022-03-09 |  | G | [25 empty] | 2023-03-06 |  | 2023-08-01 |  | G | [5 empty] | 2023-09-28 |  | 2023-10-26 |  | G | 2024-01-23 |  | 2024-01-23 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.06639
1752 | 77384 | #HB2.FY17 CONST INTER RTE 15/17/29 AT RTE 15/17/29 BUS | 0029 | Primary | Reconstruction w/o Added Capacity | VDOT | Fauquier County | WARRENTON | Culpeper | Northern Virginia:Fauquier | Infrastructure Investment Division | Ken Connors |  |  | William E Stowe | William.Stowe@vdot.virginia.gov | (540) 827-7287 |  |  |  | 1 | 2017 | 0 | FY2018 | 26930540 | 26930540 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 26 days early | G | Project is on budget | [5 empty] | 2012-09-12 | 2012-08-17 | 2012-09-12 | 2012-08-17 | G | 2012-08-17 | 2012-08-17 | 2017-09-19 | 2017-04-24 | G | [5 empty] | 2018-08-10 | 2017-08-11 | 2018-08-24 | 2017-08-24 | G | 2017-04-18 | 2017-04-18 | 2017-04-21 | 2017-04-21 | G | [20 empty] | 2017-04-26 | 2017-07-18 | 2017-07-18 | 2017-07-18 | G | 2018-03-21 | 2018-01-23 | 2018-04-18 | 2018-03-23 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | DESIGN BUILD/PPTA | 1 | 0 | 0.16162
1753 | 100920 | Croaker Road - Four Lane Widening From Library to Rte 60 | 0607 | Secondary | Reconstruction w/ Added Capacity | VDOT | James City County | WILLIAMSBURG | Hampton Roads | Hampton Roads:James City County | Infrastructure Investment Division | Kenneth D Mckinna | Kenneth.McKinna@VDOT.Virginia.gov | (757) 956-3271 | Wali Zaman | Wali.Zaman@VDOT.Virginia.gov | (757) 956-3272 | Allen Murphy | ajmurphy@james-city.va.us | (757) 253-6674 | 0 |  | 0 | FY2024 | 18611690 | 21244018 | ACTIVITY DATES SET | G | Start Purchasing Right-of-Way milestone finished 279 days early | R | Project estimate is greater than $10M and is over budget by (a) 10% or more or (b) $5M or more | [5 empty] | 2012-06-29 | 2012-02-08 | 2012-06-29 | 2012-02-08 | G | 2012-07-30 | 2012-07-30 | 2019-02-20 | 2019-05-06 | R | [5 empty] | 2020-02-28 | 2020-02-28 | 2020-03-26 | 2020-03-03 | G | 2021-08-03 | 2020-11-10 | 2021-08-30 | 2020-11-24 | G | 2022-06-23 |  | 2023-06-09 |  | G | 2021-09-16 |  | 2022-06-08 |  | G | 2020-09-18 | 2020-09-18 | 2021-05-26 |  | G | [5 empty] | 2023-12-12 |  | 2023-12-12 |  | G | 2024-02-29 |  | 2024-04-24 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 1 | 0.36807
1754 | 103085 | #HB2.FY17 RTE 1/630 AREA CORRIDOR ROAD IMPROVEMENTS | 0001 | Primary | Reconstruction w/ Added Capacity | Locally | Stafford County | FREDERICKSBURG | Fredericksburg | Fredericksburg:Stafford County | Local Assistance Division | Khalil Minhas | Khalil.Minhas@vdot.virginia.gov | (540) 374-3369 | Khalil Minhas | Khalil.Minhas@vdot.virginia.gov | (540) 374-3369 | Alexander E. Owsiak (540) 658-4593 | AOwsiak@staffordcountyva.gov | (540) 658-4593 | 1 | 2017 | 0 | FY2021 | 13280300 | 19940000 | ACTIVITY DATES SET | R | Solicit Bids milestone is 173 days past the expected completion date | R | Project estimate is greater than $10M and is over budget by (a) 10% or more or (b) $5M or more | [5 empty] | 2012-11-21 | 2012-11-21 | 2013-01-21 | 2013-01-21 | G | 2013-01-21 | 2013-01-21 | 2018-07-31 | 2016-01-14 | G | [5 empty] | 2016-03-18 | 2016-03-18 | 2017-09-20 | 2017-09-20 | G | 2018-02-08 | 2018-02-08 | 2018-02-15 | 2018-02-15 | G | [20 empty] | 2020-08-05 |  | 2020-09-01 |  | R | 2020-10-15 |  | 2020-12-17 |  | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.23279
1755 | 107079 | QUARRY STREET SIDEWALK | 9999 | Urban | Facilities for Pedestrians and Bicycles | Locally | Manassas | MANASSAS | Northern Virginia | Northern Virginia:Manassas | Local Assistance Division | Amir Salahshoor | A.Salahshoor@VDOT.Virginia.gov | (703) 259-1957 | Saif-Ur Qargha | Saif.Qargha@vdot.virginia.gov | (703) 259-3223 | William Springer | wspringer@ci.manassas.va.us | 70325784 | 0 |  | 0 | FY2023 | 427000 | 596000 | ACTIVITY DATES SET | R | Determine Requirements milestone finished 389 days late | R | Project estimate is less than $5M and is 20% or more over budget | 2015-06-18 | 2015-06-18 | 2015-09-01 | 2015-09-01 | G | 2015-09-14 | 2015-09-14 | 2015-09-16 | 2015-09-16 | G | 2015-09-17 | 2015-09-17 | 2019-05-30 | 2020-06-22 | R | [10 empty] | 2021-04-14 | 2021-01-03 | 2021-07-29 |  | G | [5 empty] | 2021-08-02 |  | 2021-12-27 |  | G | [10 empty] | 2022-07-06 |  | 2022-12-19 |  | G | 2022-12-20 |  | 2023-05-19 |  | G | Delay due to changes in scope of work, project management, plan designs, or resolution of public comments | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.13189
1756 | 110764 | #SMART18 - ARNETT BLVD - SIDEWALKS, BIKE LANES, CROSSWALKS | 9999 | Urban | Facilities for Pedestrians and Bicycles | Locally | Danville | HALIFAX | Lynchburg | Danville:Danville | Infrastructure Investment Division | Gregg Allen | Gregg.Allen@vdot.virginia.gov | (434) 426-5575 | Gregg Allen | Gregg.Allen@vdot.virginia.gov | (434) 426-5575 | Brian Dunevant | dunevbl@danvilleva.gov | (434) 799-8919 | 1 | 2018 | 0 | FY2022 | 500588 | 500588 | NO DATES SET YET-PE OPEN | R | Determine Requirements milestone is 12 days past the expected completion date | G | Project is on budget | 2019-07-15 | 2019-07-15 | 2019-09-27 | 2019-09-20 | G | 2019-09-30 | 2019-09-23 | 2020-04-06 | 2019-09-24 | G | 2020-04-07 | 2019-09-25 | 2021-02-09 |  | R | [10 empty] | 2021-05-18 |  | 2021-06-08 |  | G | [5 empty] | 2021-06-10 |  | 2022-03-24 |  | G | [10 empty] | 2022-04-11 |  | 2022-05-06 |  | G | 2022-05-09 |  | 2022-06-17 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.084692
1758 | 111082 | CITY-WIDE AUDIBLE PEDESTRIAN SIGNAL PROG |  | Urban | Safety | Locally | Harrisonburg | HARRISONBURG | Staunton | Harrisonburg:Harrisonburg | Infrastructure Investment Division | Keith M Rider | Keith.Rider@VDOT.Virginia.gov | (434) 856-8145 | Kunal Kothawade | Kunal.Kothawade@vdot.virginia.gov | (540) 332-9259 | Aaron Rhoney, City of Harrisonburg | Aaron.Rhoney@harrisonburgva.gov | (540) 434-5928 | 0 |  | 0 | FY2022 | 445500 | 373513 | AWARDED | G | Start Delivery milestone finished 529 days early | G | Project is on budget | 2017-07-13 | 2018-12-07 | 2019-05-03 | 2019-01-07 | G | 2019-05-06 | 2019-01-08 | 2019-09-25 | 2019-07-25 | G | 2019-09-26 | 2019-07-01 | 2020-08-27 | 2020-06-03 | G | [35 empty] | 2021-10-28 | 2020-09-14 | 2021-11-29 | 2020-09-14 | G | 2021-11-30 | 2020-09-15 | 2022-04-11 | 2020-10-29 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.078453
1759 | 111265 | #SGR18VB - I-81 NBL Smyth Co VA #2034 Federal STRUCT #17478 | 0081 | Interstate | Bridge Replacement w/o Added Capacity | VDOT | Smyth County | ABINGDON | Bristol | NonMPO:NonMPO | Infrastructure Investment/Asset Management Division | Gary Lester |  |  | Jason A Graham | Jason.Graham@vdot.virginia.gov | (276) 696-3383 |  |  |  | 0 |  | 1 | FY2019 | 13613798 | 13613798 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 98 days early | G | Project is on budget | [10 empty] | 2019-01-02 | 2018-02-01 | 2019-01-08 | 2019-01-08 | G | [35 empty] | 2019-01-09 | 2018-08-28 | 2019-01-09 | 2018-08-28 | G | 2019-06-27 | 2019-03-21 | 2019-06-27 | 2019-03-21 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.064157
1760 | 111683 | #SMART18 - SHARON ROAD PARK AND RIDE | 0360 | Secondary | Safety | VDOT | King William County | SALUDA | Fredericksburg | NonMPO:NonMPO | Infrastructure Investment Division | Jessica Graves | Jessica.Graves@vdot.virginia.gov | (540) 899-4267 | Jessica Graves | Jessica.Graves@vdot.virginia.gov | (540) 899-4267 |  |  |  | 1 | 2018 | 0 | FY2022 | 614000 | 601361 | ACTIVITY DATES SET | R | Engage Public milestone finished 91 days late | G | Project is on budget | [5 empty] | 2019-07-19 | 2019-07-10 | 2019-08-01 | 2019-07-31 | G | 2019-08-02 | 2019-08-01 | 2020-03-25 | 2020-03-23 | G | [5 empty] | 2020-06-03 | 2020-09-04 | 2020-07-15 | 2020-10-14 | R | [5 empty] | 2020-12-29 | 2020-08-20 | 2021-04-23 | 2020-08-20 | G | [15 empty] | 2021-05-11 |  | 2021-05-11 |  | G | 2021-08-13 |  | 2021-10-08 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.071223
1761 | 112901 | PROVIDE ADVANCED SIGNAL DETECTION | 9999 | Primary | Safety | VDOT | Staunton District-wide |  | Staunton | NonMPO:NonMPO | Infrastructure Investment Division | Keith M Rider | Keith.Rider@VDOT.Virginia.gov | (434) 856-8145 | Kunal Kothawade | Kunal.Kothawade@vdot.virginia.gov | (540) 332-9259 |  |  |  | 0 |  | 0 | FY2023 | 933000 | 933000 | NO DATES SET YET | G | Start Development milestone is 617 days ahead of the expected completion date | G | Project is on budget | [5 empty] | 2022-10-31 |  | 2022-10-31 |  | G | 2022-11-01 |  | 2023-02-15 |  | G | [5 empty] | 2023-03-01 |  | 2023-03-14 |  | G | [25 empty] | 2023-03-30 |  | 2023-04-05 |  | G | 2023-04-06 |  | 2023-04-12 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | WORK/TASK ORDER | 0 | 0 | 0.068202
1762 | 113445 | RTE 60 (SEMMES AVE) - PED IMPRV PH II | 0060 | Primary | Facilities for Pedestrians and Bicycles | Locally | Richmond | ASHLAND | Richmond | Richmond:Richmond | Local Assistance Division | Jorg Huckabee-Mayfield | Jorg.Huckabee-Mayfield@VDOT.Virginia.gov | (804) 609-5292 | Jorg Huckabee-Mayfield | Jorg.Huckabee-Mayfield@VDOT.Virginia.gov | (804) 609-5292 | Winston Phillips | Winston.Phillips@Richmondgov.com | (804) 646-5994 | 0 |  | 0 | FY2023 | 500000 | 500000 | NO DATES SET YET-PE OPEN | Y | Determine Requirements milestone is 18 days ahead of the expected completion date and there is a risk of missing this milestone date | G | Project is on budget | 2019-10-02 | 2019-10-02 | 2020-02-14 | 2019-10-23 | G | 2020-02-25 | 2019-06-11 | 2020-03-09 | 2019-09-11 | G | 2020-08-28 |  | 2021-03-11 |  | Y | [25 empty] | 2020-11-09 |  | 2021-07-16 |  | G | [5 empty] | 2022-03-30 |  | 2022-04-26 |  | G | 2022-10-10 |  | 2022-10-10 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.21496
1763 | 113846 | Early Settlers Rd Sidewalk: Robius Rd to Hospital/Park | 1775 | Secondary | Facilities for Pedestrians and Bicycles | Locally | Chesterfield County | CHESTERFIELD | Richmond | Richmond:Chesterfield County | Infrastructure Investment Division | Michael S Gray | Mike.Gray@vdot.virginia.gov | (804) 609-5347 | Michael S Gray | Mike.Gray@vdot.virginia.gov | (804) 609-5347 | Barb Smith | smithbk@chesterfield.gov | 7481037 | 0 |  | 0 | FY2024 | 1170000 | 1170000 | NO DATES SET YET | G | Agreement with Locality milestone is 215 days ahead of the expected completion date | G | Project is on budget | 2021-07-01 |  | 2021-09-24 |  | G | 2021-09-27 |  | 2021-09-29 |  | G | 2021-09-30 |  | 2022-04-12 |  | G | [10 empty] | 2023-02-07 |  | 2023-02-28 |  | G | [5 empty] | 2023-03-02 |  | 2023-12-08 |  | G | 2022-05-18 |  | 2023-01-25 |  | G | [5 empty] | 2023-12-27 |  | 2024-01-26 |  | G | 2024-04-16 |  | 2024-04-16 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.23553
1764 | 114638 | Install Flashing Beacons on Intersection Warning Signs | 0122 | Primary | Safety | VDOT | Bedford County | BEDFORD | Salem | Roanoke:Bedford County | Infrastructure Investment Division | Bernard S Grinnell | Sean.Grinnell@VDOT.Virginia.gov | (540) 375-0148 | Bernard S Grinnell | Sean.Grinnell@VDOT.Virginia.gov | (540) 375-0148 | N/a |  |  | 0 |  | 0 | FY2019 | 66505 | 66505 | CONSTRUCTION COMPLETED | R | Start Delivery milestone finished 39 days late | G | Project is on budget | [5 empty] | 2019-02-05 | 2019-01-14 | 2019-02-05 | 2019-01-30 | G | 2019-02-06 | 2019-01-31 | 2019-05-15 | 2019-05-15 | G | [5 empty] | 2019-05-16 | 2019-05-16 | 2019-05-30 | 2019-05-16 | G | [25 empty] | 2019-06-17 | 2019-06-18 | 2019-06-21 | 2019-06-24 | R | 2019-06-24 | 2019-06-25 | 2019-06-28 | 2019-08-06 | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | WORK/TASK ORDER | 1 | 1 | 0.31988
1765 | 115404 | #SMART20 - ITS SIGNAL UPGRADES | 0060 | Primary | Traffic Management/Engineering | VDOT | Chesterfield County | CHESTERFIELD | Richmond | Richmond:Chesterfield County | Infrastructure Investment Division | Adam S Brooks | Adam.Brooks@VDOT.Virginia.gov | (804) 609-5274 | Adam S Brooks | Adam.Brooks@VDOT.Virginia.gov | (804) 609-5274 |  |  |  | 1 | 2020 | 0 | FY2028 | 10440000 | 10440000 | NO DATES SET YET-PE OPEN | G | Start Development milestone finished 1464 days early | G | Project is on budget | [5 empty] | 2023-09-01 | 2019-08-15 | 2023-09-15 | 2019-09-12 | G | 2023-09-18 |  | 2024-08-14 |  | G | [5 empty] | 2025-06-20 |  | 2025-07-03 |  | G | 2026-10-08 |  | 2026-10-22 |  | G | 2027-03-24 |  | 2027-09-24 |  | G | 2026-11-09 |  | 2027-05-19 |  | G | 2026-03-31 |  | 2026-10-01 |  | G | [5 empty] | 2027-10-12 |  | 2027-10-12 |  | G | 2028-01-07 |  | 2028-01-07 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | REGIONAL ON-CALL CONTRACT | 0 | 0 | 0.14365
1766 | 115461 | #SMART20 - Camp Jaycee Rd Rte 697 Int at US 460 | 0460 | Primary | Safety | VDOT | Bedford County | BEDFORD | Salem | NonMPO:NonMPO | Infrastructure Investment Division | Alex H Price | Alex.Price@VDOT.Virginia.gov | (540) 378-5053 | Timothy M Dowdy | Tim.Dowdy@VDOT.Virginia.gov | (540) 387-5332 |  |  |  | 1 | 2020 | 0 | FY2028 | 3733000 | 3733000 | NO DATES SET YET | G | Start Development milestone is 904 days ahead of the expected completion date | G | Project is on budget | [5 empty] | 2023-08-01 |  | 2023-08-14 |  | G | 2023-08-15 |  | 2024-07-12 |  | G | [5 empty] | 2025-05-19 |  | 2025-06-02 |  | G | 2026-09-04 |  | 2026-09-18 |  | G | 2027-02-19 |  | 2027-08-23 |  | G | 2026-10-06 |  | 2027-04-16 |  | G | 2026-02-26 |  | 2026-08-28 |  | G | [5 empty] | 2027-09-14 |  | 2027-09-14 |  | G | 2027-12-08 |  | 2027-12-08 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.18802
1767 | 115610 | Town Wide Pavement Overlay - Various Routes | 9999 | Urban | Resurfacing | Locally | Tazewell | LEBANON | Bristol | NonMPO:NonMPO | Local Assistance Division | John W Bechtold | John.Bechtold@vdot.virginia.gov | (276) 696-3365 | Roger L Musser | Roger.Musser@VDOT.Virginia.gov | (276) 696-3260 | Todd Day | tazmanager@taztown.org | (276) 988-2501 | 0 |  | 0 | FY2021 | 1055774 | 1000000 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 119 days early | G | Project is on budget | 2020-04-01 | 2020-03-01 | 2020-06-24 | 2020-03-31 | G | [5 empty] | 2020-04-01 | 2020-04-01 | 2020-04-14 | 2020-04-14 | G | [25 empty] | 2020-04-15 | 2020-08-11 | 2020-10-02 | 2020-08-11 | G | [5 empty] | 2020-10-05 | 2020-08-12 | 2020-11-02 | 2020-09-09 | G | 2021-01-28 | 2020-09-15 | 2021-01-28 | 2020-10-01 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.050018
1768 | 116156 | #I81CIP NB MM32.4 TRUCK CLIMBING LANE (ID #3) | 0081 | Interstate | Reconstruction w/ Added Capacity | VDOT | Washington County | ABINGDON | Bristol | NonMPO:NonMPO | Infrastructure Investment Division | Donald A Necessary | Donald.Necessary@VDOT.Virginia.gov | (276) 696-3285 | James R Jones | jamesr.jones@vdot.virginia.gov | (276) 696-3257 |  |  |  | 0 |  | 0 | FY2024 | 21320300 | 16905323 | ACTIVITY DATES SET | G | Determine Requirements milestone finished 362 days early | G | Project is on budget | [5 empty] | 2020-07-01 | 2020-01-03 | 2020-07-15 | 2020-01-16 | G | 2020-07-16 | 2020-01-21 | 2021-08-24 | 2020-08-27 | G | [5 empty] | 2021-05-11 |  | 2021-05-24 |  | G | 2022-05-11 |  | 2022-05-24 |  | G | 2022-10-19 |  | 2023-04-28 |  | G | 2022-06-10 |  | 2023-02-02 |  | G | 2021-10-29 |  | 2023-04-13 |  | G | [5 empty] | 2023-06-13 |  | 2023-06-13 |  | G | 2023-10-02 |  | 2023-10-02 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.093798
1769 | 117026 | RT. 648 - WIDEN SHELTON SHOP ROAD | 0648 | Secondary | Reconstruction w/o Added Capacity | Locally | Stafford County | FREDERICKSBURG | Fredericksburg | Fredericksburg:Stafford County | Local Assistance Division | Catherine C Coffey | Catherine.Coffey@vdot.virginia.gov | (540) 899-4280 | Catherine C Coffey | Catherine.Coffey@vdot.virginia.gov | (540) 899-4280 | ALEX OWSIAK | aowsiak@staffordcountyva.gov | (540) 658-4593 | 0 |  | 0 | FY2030 | 22700000 | 22700000 | NO DATES SET YET | G | Agreement with Locality milestone is 1453 days ahead of the expected completion date | G | Project is on budget | 2024-10-01 |  | 2025-02-13 |  | G | 2025-02-14 |  | 2025-03-07 |  | G | 2025-09-11 |  | 2026-05-19 |  | G | [10 empty] | 2028-08-17 |  | 2028-09-21 |  | G | [5 empty] | 2028-09-22 |  | 2029-04-18 |  | G | 2028-06-21 |  | 2029-02-28 |  | G | [5 empty] | 2029-07-23 |  | 2029-08-17 |  | G | 2029-11-07 |  | 2029-11-07 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.20154
1770 | 112710 | NORTH UNION STREET - RECONSTRUCTION | 9999 | Urban | Reconstruction w/o Added Capacity | Locally | Danville | HALIFAX | Lynchburg | Danville:Danville | Infrastructure Investment Division | Sharon S White | Sharon.White@VDOT.Virginia.gov | (434) 856-8220 | John E Neblett | John.Neblett@VDOT.Virginia.gov | (434) 856-8202 | BRIAN DUNEVANT | dunebl@ci.danville.va.us | (434) 799-5019 | 0 |  | 0 | FY2019 | 704000 | 704000 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished on-time | G | Project is on budget | 2018-01-08 | 2018-01-08 | 2018-04-04 | 2018-03-16 | G | 2018-04-05 | 2018-04-05 | 2018-04-09 | 2018-04-09 | G | 2018-04-10 | 2018-04-10 | 2018-10-11 | 2018-04-10 | G | [10 empty] | 2018-05-17 | 2018-05-17 | 2018-05-17 | 2018-05-17 | G | [5 empty] | 2018-05-17 | 2018-05-17 | 2018-05-17 | 2018-05-17 | G | [10 empty] | 2018-05-28 | 2018-05-28 | 2018-06-14 | 2018-06-14 | G | 2017-10-17 | 2017-10-17 | 2018-07-09 | 2018-07-09 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.07959
1771 | 113176 | WEST MAIN ST. PHASE I - RIDGE ST. TO 6TH ST. NW | 9999 | Urban | Facilities for Pedestrians and Bicycles | Locally | Charlottesville | CHARLOTTESVILLE | Culpeper | NonMPO:NonMPO | Local Assistance Division | Ken Connors |  |  | Michael D Barnes | MichaelD.Barnes@vdot.virginia.gov | (434) 422-9861 | Jeanette Janiczek | janiczekj@charlottesville.gov | (434) 970-3182 | 0 |  | 0 | FY2025 | 12587500 | 12587500 | ACTIVITY DATES SET | Y | Start Purchasing Right-of-Way milestone is 19 days ahead of the expected completion date and there is a risk of missing this milestone date | G | Project is on budget | 2019-03-01 | 2019-03-01 | 2019-05-23 | 2019-04-11 | G | 2019-05-24 | 2019-04-12 | 2019-05-29 | 2019-04-16 | G | 2019-05-30 | 2019-04-17 | 2020-05-29 | 2020-05-29 | G | [10 empty] | 2021-02-19 |  | 2021-03-12 |  | Y | [5 empty] | 2021-03-30 |  | 2022-09-30 |  | G | [10 empty] | 2022-10-11 |  | 2024-04-09 |  | G | 2024-06-27 |  | 2024-08-13 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.174
1772 | 113700 | #SGR19LB??- Pittmantown Road over Mill Swamp | 0668 | Urban | Bridge Replacement w/o Added Capacity | Locally | Suffolk | NORFOLK | Hampton Roads | Hampton Roads:Suffolk | Infrastructure Investment Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Johndel A Alcaide | John.Alcaide@vdot.virginia.gov | (757) 956-3098 | L. Hansen | lhansen@suffolkva.us | (757) 514-7687 | 0 |  | 1 | FY2024 | 1420000 | 1420000 | NO DATES SET YET | G | Agreement with Locality milestone is 295 days ahead of the expected completion date | G | Project is on budget | 2021-09-15 |  | 2021-12-13 |  | G | 2021-12-14 |  | 2021-12-16 |  | G | 2021-12-17 |  | 2022-06-24 |  | G | [10 empty] | 2023-04-21 |  | 2023-05-11 |  | G | [5 empty] | 2023-05-15 |  | 2024-02-27 |  | G | 2022-08-02 |  | 2023-04-10 |  | G | [5 empty] | 2024-03-14 |  | 2024-04-10 |  | G | 2024-06-28 |  | 2024-06-28 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.11072
1773 | 113868 | ROSSLYN BALLSTON CORRIDOR ADA IMPROVEMENTS - PHASE 2 |  | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Arlington County | FAIRFAX | Northern Virginia | Northern Virginia:Arlington County | Local Assistance Division | Amir Salahshoor | A.Salahshoor@VDOT.Virginia.gov | (703) 259-1957 | Marlene Pinedo Fortich | Sofia.Pinedo@vdot.virginia.gov | (703) 259-1724 | Olivia Daniszewski | odaniszewski@arlingtonva.us | (703) 228-7548 | 0 |  | 0 | FY2024 | 980000 | 980000 | NO DATES SET YET-PE OPEN | R | Determine Requirements milestone is 23 days past the expected completion date | G | Project is on budget | 2019-07-30 | 2018-12-04 | 2020-02-28 | 2018-12-04 | G | 2020-03-02 | 2019-06-25 | 2020-03-30 | 2019-06-25 | G | 2020-03-31 |  | 2021-01-29 |  | R | [10 empty] | 2022-02-01 |  | 2022-03-30 |  | G | [5 empty] | 2022-03-31 |  | 2022-12-29 |  | G | 2020-09-30 | 2020-10-19 | 2021-02-26 | 2020-10-19 | G | [5 empty] | 2023-02-01 |  | 2023-06-30 |  | G | 2023-07-03 |  | 2024-01-09 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.36731
1774 | 115182 | Appomattox River Trail, Phase IV | 9999 | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Colonial Heights | CHESTERFIELD | Richmond | Tri-Cities:Colonial Heights | Infrastructure Investment Division | Brian J Lokker | Brian.Lokker@VDOT.Virginia.gov | (804) 524-6010 | Brian J Lokker | Brian.Lokker@VDOT.Virginia.gov | (804) 524-6010 | Keith Chisholm | chisolmk@colonialheightsva.gov | (804) 641-9106 | 0 |  | 0 | FY2020 | 561751 | 561751 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 105 days early | G | Project is on budget | 2019-05-29 | 2019-05-07 | 2019-08-21 | 2019-06-20 | G | 2019-08-22 | 2019-06-24 | 2019-08-26 | 2019-06-27 | G | 2019-08-27 | 2019-09-25 | 2020-03-09 | 2019-09-25 | G | [35 empty] | 2020-02-03 | 2019-12-05 | 2020-03-02 | 2019-12-24 | G | 2020-05-19 | 2019-11-26 | 2020-06-30 | 2020-03-17 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.28037
1775 | 115413 | #SMART20 - Intersection Improvements at Route 460 & Queen St | 0460 | Primary | Safety | VDOT | Prince George County | PETERSBURG | Richmond | Tri-Cities:Prince George County | Infrastructure Investment Division | Evan Roberts | Evan.Roberts@vdot.virginia.gov | (804) 609-5427 | Evan Roberts | Evan.Roberts@vdot.virginia.gov | (804) 609-5427 |  |  |  | 1 | 2020 | 0 | FY2028 | 3469550 | 3469550 | NO DATES SET YET-PE OPEN | G | Start Development milestone finished 1399 days early | G | Project is on budget | [5 empty] | 2023-08-01 | 2019-09-18 | 2023-08-14 | 2019-10-15 | G | 2023-08-15 | 2020-02-26 | 2024-07-12 |  | G | [5 empty] | 2025-05-19 |  | 2025-06-02 |  | G | 2026-09-04 |  | 2026-09-18 |  | G | 2027-02-19 |  | 2027-08-23 |  | G | 2026-10-06 |  | 2027-04-16 |  | G | 2026-02-26 |  | 2026-08-28 |  | G | [5 empty] | 2027-09-14 |  | 2027-09-14 |  | G | 2027-12-08 |  | 2027-12-08 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.065516
1776 | 115480 | #SMART20-SR 89 AT SR 613 Realignment (App ID# 3704) | 0089 | Primary | Reconstruction w/o Added Capacity | VDOT | Grayson County | WYTHEVILLE | Bristol | NonMPO:NonMPO | Infrastructure Investment Division | Dennis R Harris | Dennis.Harris@VDOT.Virginia.gov | (276) 696-3289 | Ronald C Flanary | Ronald.Flanary@VDOT.Virginia.gov | (276) 696-3252 |  |  |  | 1 | 2020 | 0 | FY2024 | 4068990 | 4068990 | ACTIVITY DATES SET | G | Determine Requirements milestone finished on-time | G | Project is on budget | [5 empty] | 2020-04-03 | 2020-04-03 | 2020-04-16 | 2020-04-16 | G | 2020-04-17 | 2020-04-17 | 2021-01-06 | 2021-01-06 | G | [5 empty] | 2021-10-08 |  | 2021-10-22 |  | G | 2022-12-14 |  | 2022-12-28 |  | G | 2023-05-24 |  | 2023-11-30 |  | G | 2023-01-18 |  | 2023-12-01 |  | G | 2022-06-01 |  | 2023-08-11 |  | G | [5 empty] | 2024-02-13 |  | 2024-02-13 |  | G | 2024-05-03 |  | 2024-05-03 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.091732
1777 | 115709 | LEESBURG TOWN MAINTENANCE RS - MILL AND OVERLAY | 9999 | Urban | Resurfacing | Locally | Leesburg | LEESBURG | Northern Virginia | Northern Virginia:Leesburg | Local Assistance Division | Amir Salahshoor | A.Salahshoor@VDOT.Virginia.gov | (703) 259-1957 | Veljibhai M Desai | Veljibhai.Desai@vdot.virginia.gov | (703) 259-2927 | Bud Siegel | BSiegel@LEESBURGVA.GOV | (703) 771-2743 | 0 |  | 0 | FY2020 | 2000000 | 2000000 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished on-time | G | Project is on budget | 2019-09-03 | 2019-09-16 | 2020-03-31 | 2019-09-16 | G | [5 empty] | 2020-04-01 | 2019-10-30 | 2020-07-31 | 2020-01-30 | G | [35 empty] | 2020-02-01 | 2020-02-01 | 2020-02-01 | 2020-02-01 | G | 2020-02-10 | 2020-02-10 | 2020-02-10 | 2020-02-10 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.30802
1778 | 116606 | NOVA SYSTEMIC HIGH VISIBILITY BACKPLATES PH1B | 9999 | Miscellaneous | Safety | VDOT | Northern Virginia District-wide |  | Northern Virginia | Northern Virginia:Northern Virginia District-wide | Infrastructure Investment/Asset Management Division | Waqar A Siddiqui | Sid.Siddiqui@VDOT.Virginia.gov | (703) 259-3225 | Tienjung Ho | Tien-Jung.Ho@VDOT.Virginia.gov | (703) 259-2752 |  |  |  | 0 |  | 0 | FY2020 | 1400000 | 1400000 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 45 days early | G | Project is on budget | [5 empty] | 2019-10-23 | 2019-10-23 | 2020-02-14 | 2020-02-14 | G | 2020-02-18 | 2020-02-18 | 2020-03-30 | 2020-02-27 | G | [5 empty] | 2020-02-27 | 2020-02-27 | 2020-02-28 | 2020-02-28 | G | [25 empty] | 2020-05-04 | 2020-03-25 | 2020-05-08 | 2020-03-25 | G | 2020-05-11 | 2020-03-27 | 2020-05-11 | 2020-03-27 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | WORK/TASK ORDER | 1 | 0 | 0.065814
1779 | 117053 | E. Laburnum Avenue Sidewalk | 7555 | Secondary | Facilities for Pedestrians and Bicycles | Locally | Henrico County | ASHLAND | Richmond | Richmond:Henrico County | Local Assistance Division | Cynthia Crouch | Cynthia.Crouch@vdot.virginia.gov | (804) 609-5313 | Cynthia Crouch | Cynthia.Crouch@vdot.virginia.gov | (804) 609-5313 | TBD |  | TBD | 0 |  | 0 | FY2029 | 458680 | 458680 | NO DATES SET YET | G | Agreement with Locality milestone is 1543 days ahead of the expected completion date | G | Project is on budget | 2025-01-06 |  | 2025-05-14 |  | G | 2025-05-15 |  | 2025-06-05 |  | G | 2025-12-15 |  | 2026-04-10 |  | G | [10 empty] | 2027-07-30 |  | 2027-09-02 |  | G | [5 empty] | 2027-09-03 |  | 2028-02-09 |  | G | 2028-01-05 |  | 2028-06-05 |  | G | [5 empty] | 2028-05-12 |  | 2028-06-09 |  | G | 2028-08-29 |  | 2028-08-29 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.3473
1780 | 117149 | #SGR21LP 134-City of Virginia Beach 2078 S Military Hwy | 0013 | Urban | Resurfacing | Locally | Virginia Beach | NORFOLK | Hampton Roads | Hampton Roads:Virginia Beach | Infrastructure Investment/Asset Management Division | Susan Wilson | Susan.Wilson@vdot.virginia.gov | (757) 956-3099 | Marci Thompson | Marci.Thompson@vdot.virginia.gov | (757) 956-3093 | Jimmy Evans | jrevans@vbgov.com | (757) 385-1505 | 0 |  | 1 | FY2022 | 855803 | 855803 | NO DATES SET YET | G | Agreement with Locality milestone is 80 days ahead of the expected completion date | G | Project is on budget | 2021-01-04 |  | 2021-05-12 |  | G | 2021-05-13 |  | 2021-06-03 |  | G | 2021-07-02 |  | 2021-07-30 |  | G | [25 empty] | 2021-07-02 |  | 2021-07-30 |  | G | [5 empty] | 2021-09-28 |  | 2021-10-26 |  | G | 2022-01-21 |  | 2022-01-21 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.066026
1781 | 118155 | Rt 33-60-Beulah Roundabout | 0033 | Primary | Safety | Locally | Henrico County | ASHLAND | Richmond | Richmond:Henrico County | Infrastructure Investment Division | Douglas L Orcutt | Doug.Orcutt@vdot.virginia.gov | (804) 609-5428 | Douglas L Orcutt | Doug.Orcutt@vdot.virginia.gov | (804) 609-5428 | Conner Barnes | bar136@henrico.us | (804) 501-4244 | 0 |  | 0 | FY2028 | 5519000 | 5519000 | NO DATES SET YET | G | Agreement with Locality milestone is 1179 days ahead of the expected completion date | G | Project is on budget | 2024-01-08 |  | 2024-05-15 |  | G | 2024-05-16 |  | 2024-06-06 |  | G | 2024-12-16 |  | 2025-04-11 |  | G | [10 empty] | 2026-07-31 |  | 2026-09-03 |  | G | [5 empty] | 2026-09-04 |  | 2027-02-10 |  | G | 2027-01-06 |  | 2027-06-07 |  | G | [5 empty] | 2027-05-14 |  | 2027-06-11 |  | G | 2027-08-31 |  | 2027-08-31 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.1247
1782 | 103583 | Thalia Creek Greenway Phase 2 |  | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Virginia Beach | NORFOLK | Hampton Roads | Hampton Roads:Virginia Beach | Local Assistance Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Marci Thompson | Marci.Thompson@vdot.virginia.gov | (757) 956-3093 | Katie Shannon | kshannon@vbgov.com | (757) 385-1514 | 0 |  | 0 | FY2019 | 982000 | 1438277 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 256 days early | R | Project estimate is less than $5M and is 20% or more over budget | [5 empty] | 2012-10-01 | 2013-08-28 | 2012-10-01 | 2013-08-30 | R | 2012-10-01 | 2013-06-19 | 2013-08-30 | 2013-07-22 | G | [10 empty] | 2014-10-20 | 2014-10-20 | 2014-11-12 | 2014-11-12 | G | [20 empty] | 2015-10-22 | 2015-10-22 | 2017-04-30 | 2017-04-30 | G | 2017-10-02 | 2017-10-02 | 2018-10-02 | 2018-01-19 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.27851
1783 | 105563 | VAN DORN ST-BEAUREGARD ST MULTI-USE TRAIL | 9999 | Urban | Facilities for Pedestrians and Bicycles | Locally | Alexandria | FAIRFAX | Northern Virginia | Northern Virginia:Alexandria | Infrastructure Investment Division | Terry Yates | Terry.Yates@vdot.virginia.gov | (703) 259-2118 | Marlene Pinedo Fortich | Sofia.Pinedo@vdot.virginia.gov | (703) 259-1724 | Alexandria Carroll | alexandria.carroll@alexandriava.gov | (703) 746-4408 | 0 |  | 0 | FY2025 | 1458869 | 1458869 | NO DATES SET YET-PE OPEN | G | Start Development milestone finished 623 days early | G | Project is on budget | 2019-02-15 | 2018-06-26 | 2020-08-27 | 2018-12-26 | G | 2020-08-28 | 2019-01-09 | 2020-09-25 | 2019-01-11 | G | 2021-08-24 |  | 2022-08-31 |  | G | [5 empty] | 2022-09-01 |  | 2023-02-01 |  | G | [15 empty] | 2023-07-06 |  | 2023-10-30 |  | G | [5 empty] | 2024-07-24 |  | 2024-12-31 |  | G | 2025-02-03 |  | 2025-06-30 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.21912
1784 | 108717 | Pughsville Area Drainage Improvements | 0000 | Urban | Other | Locally | Suffolk | NORFOLK | Hampton Roads | Hampton Roads:Suffolk | Local Assistance Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Johndel A Alcaide | John.Alcaide@vdot.virginia.gov | (757) 956-3098 | Luke Drylie | ldrylie@suffolkva.us | (757) 514-7708 | 0 |  | 0 | FY2021 | 3784000 | 3784000 | NO DATES SET YET-PE OPEN | R | Determine Requirements milestone is 758 days past the expected completion date | G | Project is on budget | 2016-10-03 | 2016-10-03 | 2016-12-30 | 2016-12-30 | G | 2017-01-03 | 2017-01-03 | 2017-01-05 | 2017-01-05 | G | 2017-01-06 |  | 2019-01-25 |  | R | [10 empty] | 2019-11-15 |  | 2019-12-09 |  | R | [5 empty] | 2019-12-11 |  | 2020-09-18 |  | R | [10 empty] | 2020-10-06 |  | 2020-11-03 |  | R | 2020-11-04 |  | 2021-04-30 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.1272
1785 | 109568 | Granby Street Bridge Repairs | 0460 | Urban | Bridge Rehab w/o Added Capacity | Locally | Norfolk | NORFOLK | Hampton Roads | Hampton Roads:Norfolk | Infrastructure Investment Division | Stephen Rowan | Steve.Rowan@vdot.virginia.gov | (757) 790-9925 | Derrick Williams | Derrick.Williams@vdot.virginia.gov | (757) 956-3097 | Olga Beltsar, P. E. | Olga.beltsar@norfolk.gov | (757) 664-7305 | 0 |  | 0 | FY2019 | 6818176 | 6818176 | CONSTRUCTION STARTED | R | Start Delivery milestone finished 373 days late | Y | Estimate not current | 2016-09-15 | 2017-02-28 | 2016-12-13 | 2017-03-16 | R | 2016-12-14 | 2017-03-17 | 2016-12-16 | 2017-03-29 | R | 2016-12-19 | 2016-12-19 | 2017-06-26 | 2017-10-12 | R | [35 empty] | 2018-07-20 | 2018-07-20 | 2018-12-03 | 2019-01-22 | R | 2018-12-04 | 2019-01-23 | 2019-05-28 | 2020-06-04 | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.41127
1786 | 109702 | ADAPTIVE SIGNAL CONTROL - RIVERMONT AVENUE | 0501 | Urban | Safety | Locally | Lynchburg | APPOMATTOX | Lynchburg | Lynchburg:Lynchburg | Infrastructure Investment Division | Gregg Allen | Gregg.Allen@vdot.virginia.gov | (434) 426-5575 | Gregg Allen | Gregg.Allen@vdot.virginia.gov | (434) 426-5575 | Lee Newland | gregg.allen@vdot.virginia.gov | (434) 455-3947 | 0 |  | 0 | FY2019 | 510000 | 469024 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 175 days early | G | Project is on budget | 2016-10-17 | 2016-09-13 | 2017-01-17 | 2016-09-22 | G | 2017-01-18 | 2016-11-08 | 2017-01-20 | 2016-11-10 | G | 2017-01-23 | 2017-01-24 | 2017-07-26 | 2017-03-23 | G | [35 empty] | 2018-02-02 | 2018-08-09 | 2018-03-02 | 2018-08-20 | R | 2019-05-02 | 2018-10-08 | 2019-05-30 | 2018-12-06 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.19148
1787 | 110753 | GREAT BRIDGE BLVD. RIGHT TURN LANE |  | Urban | Safety | Locally | Chesapeake | NORFOLK | Hampton Roads | Hampton Roads:Chesapeake | Infrastructure Investment Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Johndel A Alcaide | John.Alcaide@vdot.virginia.gov | (757) 956-3098 | Troy Eisenberger, PE | teisenberger@cityofchesapeake.net | (757) 382-6383 | 0 |  | 0 | FY2022 | 1210000 | 1210000 | NO DATES SET YET-PE OPEN | R | Determine Requirements milestone is 584 days past the expected completion date | G | Project is on budget | 2018-03-01 | 2018-03-01 | 2018-07-02 | 2018-03-21 | G | 2018-07-03 | 2018-03-21 | 2018-07-17 | 2018-07-06 | G | 2018-07-18 |  | 2019-07-18 |  | R | [10 empty] | 2020-07-22 |  | 2020-08-10 |  | R | [5 empty] | 2020-08-12 |  | 2021-05-25 |  | G | [10 empty] | 2021-06-11 |  | 2021-07-23 |  | G | 2021-07-26 |  | 2022-01-20 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.20848
1789 | 111029 | SHOULDER RUMBLE STRIPS - DISTRICT WIDE | 9999 | Primary | Safety | VDOT | Stafford County | FREDERICKSBURG | Fredericksburg | NonMPO:NonMPO | Infrastructure Investment Division | Jessica Graves | Jessica.Graves@vdot.virginia.gov | (540) 899-4267 | Jessica Graves | Jessica.Graves@vdot.virginia.gov | (540) 899-4267 |  |  |  | 0 |  | 0 | FY2022 | 720000 | 720000 | NO DATES SET YET | G | Start Development milestone is 222 days ahead of the expected completion date | G | Project is on budget | [5 empty] | 2021-09-13 |  | 2021-10-01 |  | G | 2021-10-04 |  | 2022-01-19 |  | G | [5 empty] | 2022-02-01 |  | 2022-02-14 |  | G | [25 empty] | 2022-03-03 |  | 2022-03-09 |  | G | 2022-03-10 |  | 2022-03-16 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | WORK/TASK ORDER | 0 | 0 | 0.066707
1790 | 117221 | Franklin Road Sidewalk Improvements - Rt. 220 B- Phase 2 | 0220 | Urban | Facilities for Pedestrians and Bicycles | Locally | Roanoke | SALEM | Salem | Roanoke:Roanoke City | Infrastructure Investment Division | Cheryl B Becker | Cheryl.Becker@vdot.virginia.gov | (540) 492-2531 | Cheryl B Becker | Cheryl.Becker@vdot.virginia.gov | (540) 492-2531 | James Nuckles | james.nuckles@roanokeva.gov | (540) 853-2953 | 0 |  | 0 | FY2022 | 1791406 | 1791406 | NO DATES SET YET | R | Start Development milestone is 207 days past the expected completion date | G | Project is on budget | 2020-04-30 | 2020-08-25 | 2020-07-24 | 2021-01-22 | R | 2020-07-27 | 2021-01-28 | 2020-07-29 |  | R | 2020-07-30 |  | 2021-02-09 |  | R | [25 empty] | 2021-03-18 | 2021-02-17 | 2021-11-17 | 2021-02-17 | G | [5 empty] | 2022-03-01 |  | 2022-03-28 |  | G | 2022-06-15 |  | 2022-06-15 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.32917
1791 | 101241 | #SGR17VB - RT 630 - BRIDGE REPLACEMENT | 0630 | Secondary | Bridge Replacement w/o Added Capacity | VDOT | Brunswick County | SOUTH HILL | Richmond | NonMPO:NonMPO | Infrastructure Investment/Asset Management Division | Susan Warr | Susan.Warr@VDOT.Virginia.gov | (804) 720-5478 | Susan Warr | Susan.Warr@VDOT.Virginia.gov | (804) 720-5478 |  |  |  | 0 |  | 1 | FY2020 | 1193318 | 1171067 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 55 days early | G | Project is on budget | [10 empty] | 2016-08-24 | 2016-08-24 | 2017-11-15 | 2017-11-08 | G | 2017-12-26 | 2017-12-26 | 2018-04-19 | 2018-04-12 | G | [20 empty] | 2018-08-06 | 2018-07-23 | 2018-12-31 | 2018-10-16 | G | [5 empty] | 2019-05-14 | 2019-06-11 | 2019-07-09 | 2019-06-11 | G | 2019-08-22 | 2019-08-23 | 2019-10-17 | 2019-08-23 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.064706
1792 | 104889 | RT 10 (Whitepine to Frith) WIDENING | 0010 | Primary | Reconstruction w/ Added Capacity | Locally | Chesterfield County | CHESTERFIELD | Richmond | Richmond:Chesterfield County | Infrastructure Investment Division | Michael S Gray | Mike.Gray@vdot.virginia.gov | (804) 609-5347 | Michael S Gray | Mike.Gray@vdot.virginia.gov | (804) 609-5347 | Steve Adams | AdamsSt@chesterfield.gov | (804) 748-1037 | 0 |  | 0 | FY2024 | 15200000 | 15170914 | ACTIVITY DATES SET | G | Complete Purchasing Right-of-Way milestone finished 608 days early | G | Project is on budget | 2017-11-20 | 2017-11-20 | 2017-11-20 | 2017-11-20 | G | 2017-12-05 | 2017-12-05 | 2017-12-05 | 2017-12-05 | G | 2018-01-16 | 2018-01-16 | 2019-02-01 | 2019-01-28 | G | [5 empty] | 2020-06-30 | 2020-01-08 | 2020-06-30 | 2020-01-08 | G | 2020-09-01 | 2020-02-04 | 2020-09-01 | 2020-02-04 | G | [5 empty] | 2020-11-02 | 2020-02-21 | 2022-05-02 | 2020-09-01 | G | [10 empty] | 2023-09-01 | 2020-10-20 | 2023-09-01 |  | G | 2023-12-15 |  | 2024-01-31 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.15271
1793 | 108699 | Reconstruction - High Street | 9999 | Secondary | Reconstruction w/o Added Capacity | Locally | Hopewell | PETERSBURG | Richmond | Tri-Cities:Hopewell | Local Assistance Division | Brian J Lokker | Brian.Lokker@VDOT.Virginia.gov | (804) 524-6010 | Brian J Lokker | Brian.Lokker@VDOT.Virginia.gov | (804) 524-6010 | Austin Anderson | aanderson@hopewellva.gov | (804) 541-2379 | 0 |  | 0 | FY2019 | 350000 | 350000 | CONSTRUCTION STARTED | G | Start Delivery milestone finished on-time | G | Project is on budget | 2017-07-12 | 2016-09-13 | 2017-10-04 | 2016-09-13 | G | 2017-10-05 | 2017-06-01 | 2017-10-10 | 2017-06-02 | G | 2017-10-11 | 2017-06-05 | 2018-04-20 | 2018-03-09 | G | [35 empty] | 2018-04-30 | 2018-06-05 | 2018-06-29 | 2018-06-29 | G | 2018-07-02 | 2018-06-29 | 2018-08-20 | 2018-08-20 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.10514
1794 | 108791 | Chesapeake Battlefield B/vd FYA | 0168 | Urban | Safety | Locally | Chesapeake | NORFOLK | Hampton Roads | Hampton Roads:Chesapeake | Infrastructure Investment Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Johndel A Alcaide | John.Alcaide@vdot.virginia.gov | (757) 956-3098 | Kevin A. Eppley | keppley@cityofchesapeake.net | (757) 382-6501 | 0 |  | 0 | FY2019 | 453300 | 363475 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 73 days early | G | Project is on budget | 2016-07-01 | 2016-07-01 | 2016-09-26 | 2017-03-21 | R | 2016-09-27 | 2016-09-23 | 2016-09-29 | 2017-03-31 | R | 2016-09-30 | 2017-04-03 | 2017-04-12 | 2017-05-30 | R | [35 empty] | 2018-02-23 | 2018-07-23 | 2018-03-22 | 2018-11-04 | R | 2018-09-04 | 2018-11-05 | 2019-03-01 | 2018-12-18 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.20498
1795 | 109588 | ROUTE 20/231 ROUNDABOUT AT OLD SOMERSET HSIP | 0020 | Primary | Safety | VDOT | Orange County | LOUISA | Culpeper | NonMPO:NonMPO | Infrastructure Investment Division | Gregory J Cooley | Gregory.Cooley@vdot.virginia.gov | (434) 906-7979 | Gabriel M Brown | Gabe.Brown@VDOT.Virginia.gov | (434) 422-9792 |  |  |  | 0 |  | 0 | FY2021 | 3140000 | 3140000 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 442 days early | G | Project is on budget | [5 empty] | 2016-11-01 | 2016-11-01 | 2016-11-01 | 2016-11-01 | G | 2016-11-16 | 2016-11-16 | 2018-03-05 | 2018-02-16 | G | [5 empty] | 2018-05-10 | 2018-04-12 | 2018-08-31 | 2018-04-16 | G | 2019-10-10 | 2018-10-11 | 2019-10-24 | 2018-10-31 | G | 2020-05-20 | 2019-05-23 | 2020-11-24 | 2019-09-24 | G | 2019-11-12 | 2018-11-12 | 2020-05-20 | 2019-05-23 | G | [10 empty] | 2020-12-08 | 2019-11-05 | 2020-12-08 | 2019-11-05 | G | 2021-02-02 | 2020-01-20 | 2021-04-06 | 2020-01-20 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.074825
1796 | 110627 | RTE 17 - WIDENING PHASE 1 - GEORGE WASHINGTON MEMORIAL HIGHW | 0017 | Primary | Safety | VDOT | Gloucester County | SALUDA | Fredericksburg | Hampton Roads:Gloucester County | Infrastructure Investment Division | Stephen P Haynes | Stephen.Haynes@VDOT.Virginia.gov | (540) 899-4709 | Curtis B Holloway | Curtis.Holloway@vdot.virginia.gov | (540) 374-3367 | Brian Lewis | blewis@gloucesterva.info | (804) 693-5480 | 0 |  | 0 | FY2027 | 30673073 | 30673073 | NO DATES SET YET | G | Start Development milestone is 530 days ahead of the expected completion date | G | Project is on budget | [5 empty] | 2022-07-18 |  | 2022-08-05 |  | G | 2022-08-08 |  | 2023-10-19 |  | G | [5 empty] | 2024-11-15 |  | 2024-12-31 |  | G | 2026-01-26 |  | 2026-03-02 |  | G | 2026-09-17 |  | 2027-01-25 |  | G | 2026-03-24 |  | 2026-10-08 |  | G | 2026-03-10 |  | 2026-11-06 |  | G | [5 empty] | 2027-02-09 |  | 2027-02-09 |  | G | 2027-04-29 |  | 2027-04-29 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.10379
1799 | 111056 | #SMART18 - (St) I-81 EXIT 315 NORTHBOUND DECEL LANE EXT | 0081 | Interstate | Reconstruction w/o Added Capacity | VDOT | Frederick County | EDINBURG | Staunton | Winchester:Frederick County | Infrastructure Investment Division | Matthew P Dana | Matt.Dana@VDOT.Virginia.gov | (540) 332-7786 | Anthony E Pelina | Anthony.Pelina@vdot.virginia.gov | (540) 332-9575 |  |  |  | 1 | 2018 | 0 | FY2019 | 643134 | 561731 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 42 days early | G | Project is on budget | [5 empty] | 2017-08-03 | 2017-07-17 | 2017-08-16 | 2017-07-26 | G | 2017-08-17 | 2017-08-15 | 2018-06-29 | 2018-05-14 | G | [5 empty] | 2018-06-07 | 2018-06-06 | 2018-06-18 | 2018-06-07 | G | [5 empty] | 2018-07-02 | 2018-04-17 | 2018-07-02 | 2018-04-17 | G | [5 empty] | 2018-08-27 | 2018-08-27 | 2018-10-08 | 2018-08-27 | G | [5 empty] | 2019-01-08 | 2019-01-08 | 2019-01-08 | 2019-01-08 | G | 2019-02-26 | 2019-04-19 | 2019-05-31 | 2019-04-19 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.064838
1800 | 111274 | Town of Rural Retreat Sidewalks, Ph. 11 |  | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Rural Retreat | WYTHEVILLE | Bristol | NonMPO:NonMPO | Local Assistance Division | Tabitha H Crowder | Tabitha.Crowder@vdot.virginia.gov | (276) 696-3482 | Roger L Musser | Roger.Musser@VDOT.Virginia.gov | (276) 696-3260 | Town of Rural Retreat |  |  | 0 |  | 0 | FY2022 | 583677 | 583677 | NO DATES SET YET-PE OPEN | R | Determine Requirements milestone is 508 days past the expected completion date | G | Project is on budget | 2018-06-05 | 2018-04-17 | 2018-12-11 | 2018-06-21 | G | 2018-12-12 | 2018-06-22 | 2018-12-14 | 2018-07-20 | G | 2018-12-17 |  | 2019-10-02 |  | R | [10 empty] | 2020-07-24 |  | 2020-08-13 |  | R | [5 empty] | 2020-08-17 |  | 2021-05-07 |  | G | [10 empty] | 2021-05-25 |  | 2021-06-22 |  | G | 2021-06-23 |  | 2021-08-03 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.29257
1801 | 113251 | RTE 15 BUS. SB - PRIMARY EXTENSION PAVEMENT OVERLAY | 0015 | Urban | Resurfacing | Locally | Warrenton | WARRENTON | Culpeper | Northern Virginia:Warrenton | Local Assistance Division | John P Price | John.Price@VDOT.Virginia.gov | (540) 347-6371 | John P Price | John.Price@VDOT.Virginia.gov | (540) 347-6371 | Paul Bernard | pbernard@warrentonva.gov | (540) 347-1858 | 0 |  | 0 | FY2019 | 68038 | 68038 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 201 days early | G | Project is on budget | 2018-08-17 | 2018-07-12 | 2018-11-13 | 2018-07-12 | G | [5 empty] | 2018-08-17 | 2018-08-09 | 2018-08-30 | 2018-08-09 | G | [25 empty] | 2018-08-15 | 2018-08-15 | 2018-11-08 | 2018-08-15 | G | [5 empty] | 2018-11-09 | 2018-08-15 | 2018-12-11 | 2018-08-15 | G | 2019-03-06 | 2018-08-17 | 2019-03-06 | 2018-08-17 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.078376
1802 | 113684 | SOUTH RIVER GREENWAY PHASE 2B |  | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Waynesboro | HARRISONBURG | Staunton | SAW:Waynesboro | Local Assistance Division | Donald F Komara | Donald.Komara@VDOT.Virginia.gov | (540) 434-2587 | Michael S Fulcher | Michael.Fulcher@VDOT.Virginia.gov | (540) 332-2243 | Dwayne Jones | jonescd@ci.waynesboro.va.us | (540) 942-6735 | 0 |  | 0 | FY2023 | 787826 | 787826 | ACTIVITY DATES SET | G | Start Purchasing Right-of-Way milestone finished 385 days early | Y | Estimate not current | 2018-11-01 | 2018-11-01 | 2019-02-01 | 2018-12-26 | G | 2019-02-04 | 2018-12-27 | 2019-02-06 | 2019-02-01 | G | 2019-02-07 | 2019-08-30 | 2019-08-12 | 2020-02-06 | R | [10 empty] | 2021-02-05 | 2020-01-02 | 2021-02-26 | 2020-02-07 | G | [5 empty] | 2021-03-02 |  | 2022-04-06 |  | G | [10 empty] | 2022-04-22 |  | 2022-05-19 |  | G | 2022-08-09 |  | 2022-08-09 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.31066
1803 | 113986 | Canon Boulevard Signal - Oyster Point Access Improvements | 9999 | Urban | Reconstruction w/ Added Capacity | Locally | Newport News | WILLIAMSBURG | Hampton Roads | Hampton Roads:Newport News | Infrastructure Investment Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Chessica Villaflores | Chessica.Villaflores@vdot.virginia.gov | (757) 956-3094 | Bryan Stilley | bstilley@nnva.gov | (757) 926-8699 | 0 |  | 0 | FY2022 | 778359 | 979638 | ADVERTISED | G | Solicit Bids milestone finished 449 days early | R | Project estimate is less than $5M and is 20% or more over budget | 2018-10-01 | 2018-10-01 | 2018-12-28 | 2019-05-13 | R | 2018-12-31 | 2019-05-14 | 2019-01-03 | 2019-05-20 | R | 2019-01-04 | 2019-05-21 | 2019-07-11 | 2019-08-19 | R | [10 empty] | 2020-12-01 | 2019-12-10 | 2020-12-21 | 2019-12-31 | G | [5 empty] | 2020-12-23 | 2020-01-03 | 2021-10-01 | 2020-01-03 | G | [10 empty] | 2021-10-20 | 2020-07-25 | 2021-11-17 | 2020-08-25 | G | 2021-11-18 |  | 2022-01-03 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.32969
1804 | 115140 | #SMART20 North Augusta Sidewalk - Terry St. to Meadowbrook |  | Urban | Facilities for Pedestrians and Bicycles | Locally | Staunton | HARRISONBURG | Staunton | SAW:Staunton | Infrastructure Investment Division | Randolph S Kiser | Randy.Kiser@VDOT.Virginia.gov | (540) 332-9092 | Michael S Fulcher | Michael.Fulcher@VDOT.Virginia.gov | (540) 332-2243 | City of Staunton | millsnd@ci.staunton.va.us | (540) 332-3858 | 1 | 2020 | 0 | FY2027 | 1058211 | 1058211 | NO DATES SET YET | G | Agreement with Locality milestone is 976 days ahead of the expected completion date | G | Project is on budget | 2023-08-01 |  | 2023-10-25 |  | G | 2023-10-26 |  | 2023-10-30 |  | G | 2023-10-31 |  | 2024-05-09 |  | G | [10 empty] | 2025-05-09 |  | 2025-05-30 |  | G | [5 empty] | 2025-06-03 |  | 2026-03-17 |  | G | 2024-06-17 |  | 2025-02-24 |  | G | [5 empty] | 2026-04-02 |  | 2026-04-29 |  | G | 2026-07-20 |  | 2026-07-20 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.1095
1805 | 115517 | Mt. Pleasant Road/Route 168 Great Bridge Bypass Interchange | 0168 | Urban | Traffic Management/Engineering | Locally | Chesapeake | NORFOLK | Hampton Roads | Hampton Roads:Chesapeake | Infrastructure Investment Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Johndel A Alcaide | John.Alcaide@vdot.virginia.gov | (757) 956-3098 | Troy Eisenberger, PE | teisenberger@cityofchesapeake.net | (757) 382-6383 | 0 |  | 0 | FY2027 | 4875000 | 4875000 | NO DATES SET YET | G | Agreement with Locality milestone is 1408 days ahead of the expected completion date | Y | Estimate not current | 2024-10-01 |  | 2024-12-30 |  | G | 2024-12-31 |  | 2025-01-03 |  | G | 2025-01-06 |  | 2025-07-11 |  | G | [25 empty] | 2025-08-18 |  | 2026-04-24 |  | G | [5 empty] | 2026-07-30 |  | 2026-08-26 |  | G | 2026-11-17 |  | 2026-11-17 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.3293
1806 | 115938 | HSIP HR Pedestrian Crossings | 9999 | Miscellaneous | Safety | VDOT | Hampton Roads District-wide |  | Hampton Roads | Hampton Roads:Hampton Roads District-wide | Infrastructure Investment/Asset Management Division | Dawn Odom | Dawn.Odom@vdot.virginia.gov | (000) 000-0000 | Laird-Robert Mcleish | Laird-Robert.McLeish@vdot.virginia.gov | (757) 956-3167 |  |  |  | 0 |  | 0 | FY2022 | 5552994 | 5552994 | ACTIVITY DATES SET | G | Determine Requirements milestone finished 1 days early | G | Project is on budget | [5 empty] | 2020-09-03 | 2020-05-15 | 2020-09-24 | 2020-05-27 | G | 2020-09-25 | 2020-05-28 | 2021-01-08 | 2021-01-07 | G | [5 empty] | 2022-02-18 |  | 2022-03-04 |  | G | [25 empty] | 2022-03-22 |  | 2022-03-22 |  | G | 2022-03-23 |  | 2022-05-17 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | WORK/TASK ORDER | 0 | 0 | 0.082728
1807 | 116162 | #I81CIP NB MM 67.3 EXTEND DECEL LANE (ID #8) | 0081 | Interstate | Reconstruction w/o Added Capacity | VDOT | Wytheville | WYTHEVILLE | Bristol | NonMPO:NonMPO | Infrastructure Investment Division | Donald A Necessary | Donald.Necessary@VDOT.Virginia.gov | (276) 696-3285 | Marvin E Holley | Gene.Holley@VDOT.Virginia.gov | (276) 696-3255 |  |  |  | 0 |  | 0 | FY2022 | 1560000 | 1460000 | ACTIVITY DATES SET | G | Relocate Utilities milestone finished 36 days early | G | Project is on budget | [5 empty] | 2020-07-01 | 2020-01-03 | 2020-07-15 | 2020-01-03 | G | 2020-07-16 | 2020-01-06 | 2021-06-14 | 2020-07-14 | G | [5 empty] | 2020-10-08 | 2020-08-11 | 2020-10-22 | 2020-08-11 | G | 2021-03-19 | 2020-11-19 | 2021-04-01 | 2020-12-04 | G | 2021-02-18 | 2021-01-13 | 2021-02-18 | 2021-01-13 | G | 2021-04-19 | 2020-12-21 | 2021-09-08 | 2020-12-21 | G | 2021-01-20 | 2021-01-21 | 2021-09-03 |  | G | [5 empty] | 2021-11-09 |  | 2021-11-09 |  | G | 2022-02-07 |  | 2022-02-07 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.085329
1808 | 117127 | Yorktown Road Sidewalk | 0706 | Urban | Facilities for Pedestrians and Bicycles | Locally | York County | WILLIAMSBURG | Hampton Roads | Hampton Roads:York County | Local Assistance Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Keisha Wilkins | Keisha.Wilkins@vdot.virginia.gov | (757) 956-3110 | Timothy Cross | tcross@yorkcounty.gov | (757) 890-3496 | 0 |  | 0 | FY2025 | 258390 | 258390 | NO DATES SET YET | G | Agreement with Locality milestone is 232 days ahead of the expected completion date | G | Project is on budget | 2021-06-04 |  | 2021-10-11 |  | G | 2021-10-12 |  | 2021-11-02 |  | G | 2022-05-16 |  | 2022-09-07 |  | G | [10 empty] | 2024-01-02 |  | 2024-02-07 |  | G | [5 empty] | 2024-02-08 |  | 2024-07-08 |  | G | 2024-06-04 |  | 2024-10-31 |  | G | [5 empty] | 2024-10-09 |  | 2024-11-06 |  | G | 2025-02-03 |  | 2025-02-03 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.12244
1809 | 117176 | Town-wide Guardrail Installaion - Blacksburg | 0000 | Urban | Safety | Locally | Blacksburg | CHRISTIANSBURG | Salem | New River Valley:Blacksburg | Local Assistance Division | Adam J Czesnowski | Adam.Czesnowski@vdot.virginia.gov | (540) 541-1216 | Adam J Czesnowski | Adam.Czesnowski@vdot.virginia.gov | (540) 541-1216 | Randy Formica | rformica@blacksburg.gov | (540) 443-1300 | 0 |  | 0 | FY2028 | 60000 | 60000 | NO DATES SET YET | G | Agreement with Locality milestone is 1422 days ahead of the expected completion date | G | Project is on budget | 2024-08-30 |  | 2025-01-13 |  | G | 2025-01-14 |  | 2025-02-05 |  | G | 2025-08-12 |  | 2025-12-08 |  | G | [25 empty] | 2026-12-03 |  | 2027-05-05 |  | G | [5 empty] | 2027-07-02 |  | 2027-07-30 |  | G | 2027-10-20 |  | 2027-10-20 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.1683
1810 | 111788 | #SMART18 - I-264 W Off-Ramp at Ballentine Boulevard | 0264 | Interstate | Traffic Management/Engineering | VDOT | Norfolk | NORFOLK | Hampton Roads | Hampton Roads:Norfolk | Infrastructure Investment Division | Peter G Reilly | Peter.Reilly@vdot.virginia.gov | (757) 858-6748 | Nancy R Marshall | Nancy.Marshall@VDOT.Virginia.gov | (757) 956-3266 | Christine Armstrong | christine.armstrong@norfolk.gov | (757) 664-7459 | 1 | 2018 | 0 | FY2024 | 1710000 | 1710000 | NO DATES SET YET-PE OPEN | R | Determine Requirements milestone is 586 days past the expected completion date | G | Project is on budget | [5 empty] | 2018-08-02 | 2019-11-15 | 2018-08-15 | 2019-11-25 | R | 2018-08-16 |  | 2019-07-16 |  | R | [5 empty] | 2021-05-17 |  | 2021-05-28 |  | G | 2022-06-30 |  | 2022-07-14 |  | G | 2022-12-09 |  | 2023-09-12 |  | G | 2022-08-01 |  | 2023-02-09 |  | G | 2021-12-16 |  | 2022-06-23 |  | G | [5 empty] | 2023-10-10 |  | 2023-10-10 |  | G | 2023-11-29 |  | 2024-01-29 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 1 | 0.34238
1811 | 113354 | McArthur St. & W. Stuart Dr. Sidewalk | 0000 | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Galax | MARTINSVILLE | Salem | NonMPO:NonMPO | Local Assistance Division | Jessie Nester | Jessie.Nester@vdot.virginia.gov | (540) 613-4115 | Jessie Nester | Jessie.Nester@vdot.virginia.gov | (540) 613-4115 | Keith Barker | kbarker@GalaxVa.com | (276) 236-5773 | 0 |  | 0 | FY2023 | 612899 | 601410 | ACTIVITY DATES SET | G | Complete Purchasing Right-of-Way milestone finished 170 days early | G | Project is on budget | 2018-10-01 | 2018-10-01 | 2018-12-28 | 2018-11-29 | G | 2018-12-31 | 2018-12-04 | 2019-01-03 | 2018-12-17 | G | 2019-01-04 | 2019-07-18 | 2019-08-01 | 2019-08-01 | G | [10 empty] | 2020-06-22 | 2020-06-22 | 2020-09-28 | 2020-09-11 | G | [5 empty] | 2020-10-02 | 2020-09-17 | 2021-04-01 | 2020-10-13 | G | 2020-07-24 | 2020-02-21 | 2021-04-01 | 2020-02-21 | G | [5 empty] | 2021-12-17 |  | 2022-01-03 |  | G | 2022-05-27 |  | 2022-09-12 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.33044
1812 | 113793 | RTE 823 - RURAL RUSTIC RD (SURFACE TREAT NON-HARDSURFACE RD) | 0823 | Secondary | Reconstruction w/o Added Capacity | VDOT | Fauquier County | WARRENTON | Culpeper | NonMPO:NonMPO | Infrastructure Investment Division | Ken Connors |  |  | Benjamin Davison | Ben.Davison@vdot.virginia.gov | (540) 347-6446 |  |  |  | 0 |  | 0 | FY2024 | 330000 | 330000 | NO DATES SET YET | G | Start Development milestone is 235 days ahead of the expected completion date | G | Project is on budget | [5 empty] | 2021-10-01 | 2020-11-23 | 2021-10-14 |  | G | 2021-10-15 | 2020-11-23 | 2022-06-13 |  | G | [5 empty] | 2023-03-22 |  | 2023-05-02 |  | G | [5 empty] | 2023-08-16 |  | 2023-12-12 |  | G | [5 empty] | 2023-08-01 |  | 2023-11-01 |  | G | [5 empty] | 2024-01-09 |  | 2024-01-09 |  | G | 2024-03-04 |  | 2024-03-22 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | SAAP CONTRACT | 0 | 0 | 0.10358
1813 | 114734 | PEDESTRIAN IMPROVEMENTS ON DUMFRIES ROAD | 0234 | Primary | Safety | VDOT | Manassas | MANASSAS | Northern Virginia | Northern Virginia:Manassas | Infrastructure Investment Division | Claudia H Llana | Claudia.Llana@VDOT.Virginia.gov | (703) 259-1768 | Tienjung Ho | Tien-Jung.Ho@VDOT.Virginia.gov | (703) 259-2752 | Chloe Delhomme | cdelhomme@manassasva.gov | (703) 257-8235 | 0 |  | 0 | FY2020 | 80900 | 80900 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 3 days early | G | Project is on budget | [5 empty] | 2019-05-01 | 2019-03-07 | 2019-05-01 | 2019-03-07 | G | 2019-05-02 | 2019-03-08 | 2019-08-09 | 2019-08-09 | G | [5 empty] | 2019-10-23 | 2019-10-23 | 2019-11-05 | 2019-11-05 | G | [25 empty] | 2019-12-09 | 2019-12-09 | 2019-12-13 | 2019-12-13 | G | 2019-12-16 | 2019-12-16 | 2019-12-20 | 2019-12-17 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | WORK/TASK ORDER | 1 | 0 | 0.07342
1814 | 115474 | #SMART20 - ROUNDABOUT - RTE. 3 AND MCDEVITT DR. INT. | 0003 | Primary | Reconstruction w/o Added Capacity | VDOT | Culpeper | WARRENTON | Culpeper | NonMPO:NonMPO | Infrastructure Investment Division | Gregory J Cooley | Gregory.Cooley@vdot.virginia.gov | (434) 906-7979 | John Rose | John.Rose1@vdot.virginia.gov | (540) 829-7429 |  |  |  | 1 | 2020 | 0 | FY2024 | 6200000 | 6200000 | NO DATES SET YET-PE OPEN | R | Determine Requirements milestone is 163 days past the expected completion date | G | Project is on budget | [5 empty] | 2019-10-01 | 2019-09-16 | 2019-10-14 | 2019-09-27 | G | 2019-10-15 |  | 2020-09-11 |  | R | [5 empty] | 2021-07-20 |  | 2021-08-02 |  | G | 2022-07-14 |  | 2022-07-27 |  | G | 2023-04-21 |  | 2023-10-25 |  | G | 2022-08-12 |  | 2023-04-20 |  | G | 2022-02-01 |  | 2022-08-04 |  | G | [5 empty] | 2023-11-14 |  | 2023-11-14 |  | G | 2024-03-11 |  | 2024-03-11 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.10162
1815 | 115888 | SYSTEMIC PEDESTRIAN CROSSINGS - DISTRICTWIDE | 9999 | Miscellaneous | Safety | VDOT | Richmond District-wide |  | Richmond | Richmond:Richmond District-wide | Infrastructure Investment/Asset Management Division | Adam S Brooks | Adam.Brooks@VDOT.Virginia.gov | (804) 609-5274 | Adam S Brooks | Adam.Brooks@VDOT.Virginia.gov | (804) 609-5274 | N\A |  |  | 0 |  | 0 | FY2022 | 3687188 | 3687188 | ACTIVITY DATES SET | G | Determine Requirements milestone finished 1 days early | G | Project is on budget | [5 empty] | 2020-12-31 | 2020-02-10 | 2021-01-13 | 2020-02-10 | G | 2021-01-14 | 2020-02-11 | 2021-02-12 | 2021-02-11 | G | [35 empty] | 2021-09-14 |  | 2021-09-14 |  | G | 2021-12-08 |  | 2021-12-08 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.059615
1816 | 116086 | TELEGRAPH ROAD AT HAYFIELD ROAD - ADD NORTHBOUND THRU LANE | 0611 | Secondary | Reconstruction w/ Added Capacity | VDOT | Fairfax County | FAIRFAX | Northern Virginia | Northern Virginia:Fairfax County | Infrastructure Investment Division | Andrew G Beacher | Andrew.Beacher@vdot.virginia.gov | (703) 259-2239 | Hong Ha | Hong.Ha@VDOT.Virginia.gov | (703) 259-2907 | Michael Guarino | Michael.Guarino@fairfaxcounty.gov | (703) 877-5600 | 0 |  | 0 | FY2024 | 3000000 | 3000000 | NO DATES SET YET-PE OPEN | R | Determine Requirements milestone is 192 days past the expected completion date | Y | Estimate not current | 2019-10-01 | 2019-10-01 | 2019-10-16 | 2019-10-16 | G | 2019-09-03 | 2019-10-14 | 2019-09-16 | 2019-10-18 | R | 2019-09-17 | 2019-10-22 | 2020-08-13 |  | R | [5 empty] | 2021-06-21 |  | 2021-07-02 |  | G | 2022-10-07 |  | 2022-10-21 |  | G | 2023-03-23 |  | 2023-09-25 |  | G | 2022-11-08 |  | 2023-05-18 |  | G | 2022-03-30 | 2019-12-16 | 2022-09-30 | 2019-12-16 | G | [5 empty] | 2023-10-10 |  | 2023-10-10 |  | G | 2024-01-05 |  | 2024-01-05 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.14236
1817 | 116977 | #SGR21VP Harrisonburg Res. Plant Mix Schedule (PM-8O-21) | 9999 | Interstate | Resurfacing | VDOT | Rockingham County | HARRISONBURG | Staunton | NonMPO:NonMPO | Infrastructure Investment/Asset Management Division | Joel D Denunzio | Joel.DeNunzio@VDOT.virginia.gov | (540) 332-9093 | Mark W Hisey | Mark.Hisey@VDOT.Virginia.gov | (540) 280-4820 |  |  |  | 0 |  | 1 | FY2021 | 1346244 | 1346244 | ADVERTISED | G | Solicit Bids milestone finished 84 days early | G | Project is on budget | [10 empty] | 2020-06-01 | 2020-09-29 | 2020-06-05 | 2020-09-30 | R | 2020-10-15 | 2020-10-15 | 2020-11-13 | 2020-10-19 | G | [30 empty] | 2020-12-08 | 2020-12-15 | 2021-03-09 | 2020-12-15 | G | 2021-05-27 |  | 2021-05-27 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.07017
1818 | 117128 | Villa Way Sidewalk | 1545 | Urban | Facilities for Pedestrians and Bicycles | Locally | York County | WILLIAMSBURG | Hampton Roads | Hampton Roads:York County | Infrastructure Investment Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Keisha Wilkins | Keisha.Wilkins@vdot.virginia.gov | (757) 956-3110 | Timothy Cross | tcross@yorkcounty.gov | (757) 890-3496 | 0 |  | 0 | FY2024 | 449882 | 449882 | NO DATES SET YET | R | Agreement with Locality milestone is 132 days past the expected completion date | G | Project is on budget | 2020-06-05 |  | 2020-10-12 |  | R | 2020-10-13 |  | 2020-11-03 |  | R | 2021-05-17 |  | 2021-09-08 |  | G | [10 empty] | 2023-01-03 |  | 2023-02-08 |  | G | [5 empty] | 2023-02-09 |  | 2023-07-10 |  | G | 2023-06-06 |  | 2023-11-02 |  | G | [5 empty] | 2023-10-11 |  | 2023-11-08 |  | G | 2024-02-05 |  | 2024-02-05 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.16848
1819 | 118375 | SPSA Interchange Improvement | 0058 | Primary | Safety | VDOT | Suffolk | NORFOLK | Hampton Roads | Hampton Roads:Suffolk | Infrastructure Investment Division | Salvija Hofheimer | Salvija.Hofheimer@vdot.virginia.gov | (757) 956-3082 | Claudia A Walsh | Claudia.Walsh@vdot.virginia.gov | (757) 956-3043 |  |  |  | 0 |  | 0 | FY2026 | 39266210 | 39266210 | NO DATES SET YET | G | Start Development milestone is 141 days ahead of the expected completion date | G | Project is on budget | [5 empty] | 2021-06-21 |  | 2021-07-12 |  | G | 2021-07-13 |  | 2022-09-22 |  | G | [5 empty] | 2023-10-20 |  | 2023-12-05 |  | G | 2024-12-26 |  | 2025-02-03 |  | G | 2025-08-21 |  | 2025-12-24 |  | G | 2025-02-26 |  | 2025-09-12 |  | G | 2025-02-12 |  | 2025-10-13 |  | G | [5 empty] | 2026-01-13 |  | 2026-01-13 |  | G | 2026-04-06 |  | 2026-04-06 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.17463
1820 | 118405 | #SGR21VB(FED ID 00746) BR REPLACE RTE. 680 OVER LICKINGHOLE | 0680 | Secondary | Bridge Replacement w/o Added Capacity | VDOT | Albemarle County | CHARLOTTESVILLE | Culpeper | NonMPO:NonMPO | Infrastructure Investment Division | Braden C Chapman | Braden.Chapman@VDOT.Virginia.gov | (540) 829-7421 | Brian A Arnold | Brian.Arnold@VDOT.Virginia.gov | (540) 829-7557 |  |  |  | 0 |  | 0 | FY2025 | 4632162 | 4632162 | NO DATES SET YET | G | Start Development milestone is 225 days ahead of the expected completion date | G | Project is on budget | [5 empty] | 2021-09-14 |  | 2021-10-04 |  | G | 2021-10-05 |  | 2022-08-09 |  | G | [5 empty] | 2023-03-15 |  | 2023-04-11 |  | G | 2023-12-01 |  | 2024-01-08 |  | G | 2024-06-07 |  | 2024-10-07 |  | G | 2024-01-25 |  | 2024-06-21 |  | G | 2024-02-15 |  | 2024-07-15 |  | G | [5 empty] | 2024-10-08 |  | 2024-10-08 |  | G | 2025-01-02 |  | 2025-01-02 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.1046
1821 | 50100 | #SMART18 - WIDEN E ELDEN ST FROM VAN BUREN ST TO FXCO PKWY |  | Urban | Reconstruction w/ Added Capacity | VDOT | Herndon | FAIRFAX | Northern Virginia | Northern Virginia:Herndon | Infrastructure Investment Division | Terry Yates | Terry.Yates@vdot.virginia.gov | (703) 259-2118 | Hamid R Misaghian | H.Misaghian@VDOT.Virginia.gov | (703) 259-1795 |  |  |  | 1 | 2018 | 0 | FY2023 | 43995010 | 50745909 | ACTIVITY DATES SET | R | Complete Purchasing Right-of-Way milestone is 88 days past the expected completion date | R | Project estimate is greater than $10M and is over budget by (a) 10% or more or (b) $5M or more | [5 empty] | 2001-01-02 | 2001-12-11 | 2001-01-31 | 2001-12-12 | R | 2011-12-20 | 2011-12-30 | 2012-03-06 | 2012-03-19 | R | [5 empty] | 2017-03-08 | 2017-03-08 | 2017-10-31 | 2017-10-31 | G | 2018-10-01 | 2019-03-06 | 2018-10-01 | 2019-04-04 | R | 2020-11-02 |  | 2022-09-01 |  | G | 2019-01-02 | 2019-05-09 | 2020-11-25 |  | R | 2017-10-31 |  | 2021-11-30 |  | G | [5 empty] | 2022-09-01 |  | 2022-09-01 |  | G | 2022-10-03 |  | 2022-12-23 |  | G | Delay due to changes in scope of work, project management, plan designs, or resolution of public comments | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 1 | 0.24975
1822 | 101028 | RTE 600 (Matoaca/Hickory) - ROUNDABOUT | 0600 | Secondary | Safety | Locally | Chesterfield County | CHESTERFIELD | Richmond | Tri-Cities:Chesterfield County | Infrastructure Investment Division | Brian J Lokker | Brian.Lokker@VDOT.Virginia.gov | (804) 524-6010 | Brian J Lokker | Brian.Lokker@VDOT.Virginia.gov | (804) 524-6010 | Chessa Faulkner | faulknerc@chesterfield.gov | (807) 748-1037 | 0 |  | 0 | FY2021 | 3025000 | 3430727 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 350 days early | Y | Project estimate is less than $5M and is up to 20% over budget | 2014-01-29 | 2014-01-29 | 2014-01-29 | 2014-01-29 | G | 2013-09-27 | 2013-09-27 | 2013-09-27 | 2013-09-27 | G | 2017-04-18 | 2017-04-18 | 2017-04-18 | 2017-04-18 | G | [5 empty] | 2017-04-18 | 2017-06-18 | 2017-04-18 | 2017-06-18 | R | 2017-04-27 | 2017-04-27 | 2017-05-10 | 2017-05-10 | G | [5 empty] | 2017-05-16 | 2017-05-16 | 2018-08-31 | 2018-04-02 | G | [10 empty] | 2020-01-23 | 2019-04-30 | 2020-01-23 | 2019-04-30 | G | 2020-05-15 | 2019-06-24 | 2020-07-14 | 2019-07-30 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.24183
1823 | 102994 | Suffolk Bypass ITS Improvements | 0058 | Urban | Traffic Management/Engineering | Locally | Suffolk | NORFOLK | Hampton Roads | Hampton Roads:Suffolk | Infrastructure Investment Division | Stephen Rowan | Steve.Rowan@vdot.virginia.gov | (757) 790-9925 | Johndel A Alcaide | John.Alcaide@vdot.virginia.gov | (757) 956-3098 | Jaason Souders | jsouders@suffolkva.us | (757) 514-7649 | 0 |  | 0 | FY2020 | 1650000 | 1892274 | AWARDED | R | Start Delivery milestone is 268 days past the expected completion date | Y | Project estimate is less than $5M and is up to 20% over budget | 2017-08-07 | 2017-08-07 | 2017-11-07 | 2017-11-07 | G | 2018-01-18 | 2018-01-18 | 2018-01-23 | 2018-01-23 | G | 2018-04-02 | 2018-04-02 | 2018-11-08 | 2019-11-12 | R | [35 empty] | 2020-01-29 | 2020-07-31 | 2020-02-28 | 2020-12-15 | R | 2020-04-01 |  | 2020-05-29 |  | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.28474
1824 | 104965 | #SGR17VB - Bridge (Fed 17757) RT 308 Over Three Creek | 0308 | Primary | Bridge Replacement w/o Added Capacity | VDOT | Southampton County | FRANKLIN | Hampton Roads | NonMPO:NonMPO | Infrastructure Investment/Asset Management Division | Mohamed A Ali | Mohamed.Ali@VDOT.Virginia.gov | (757) 956-3206 | John K Arms | John.Arms@vdot.virginia.gov | (757) 995-5156 |  |  |  | 0 |  | 1 | FY2019 | 3872413 | 3872413 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 196 days early | G | Project is on budget | [5 empty] | 2016-09-15 | 2013-07-09 | 2016-09-15 | 2013-07-09 | G | 2016-10-18 | 2013-07-17 | 2017-02-15 | 2017-02-15 | G | 2016-08-01 | 2016-08-01 | 2016-08-26 | 2016-08-26 | G | [10 empty] | 2017-07-12 | 2017-07-12 | 2017-09-29 | 2017-09-29 | G | [15 empty] | 2018-02-13 | 2018-02-13 | 2018-02-13 | 2018-02-13 | G | 2018-09-13 | 2018-04-27 | 2018-11-09 | 2018-04-27 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.11772
1825 | 106962 | ALEXANDRIA BUS SHELTERS FY'21 | 9999 | Urban | Other | Locally | Alexandria | FAIRFAX | Northern Virginia | Northern Virginia:Alexandria | Infrastructure Investment Division | Amir Salahshoor | A.Salahshoor@VDOT.Virginia.gov | (703) 259-1957 | Susie X Lue | Susie.Lue@vdot.virginia.gov | (703) 259-2918 | Murphy Ng | Murphy.ng@Alexandriava.gov | (703) 746-4699 | 0 |  | 0 | FY2028 | 2185743 | 2185743 | NO DATES SET YET-PE OPEN | G | Start Development milestone finished on-time | G | Project is on budget | 2018-03-12 | 2018-03-12 | 2018-07-24 | 2018-07-24 | G | 2018-07-25 | 2018-07-25 | 2018-07-30 | 2018-07-30 | G | 2022-12-01 |  | 2023-11-29 |  | G | 2024-08-05 |  | 2025-01-30 |  | G | [20 empty] | 2026-02-26 |  | 2026-10-27 |  | G | [5 empty] | 2026-06-03 |  | 2026-12-30 |  | G | 2027-03-31 |  | 2027-08-26 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.3213
1826 | 109202 | LAKEFIELD ROAD - RECONSTRUCT AND PAVE AS A RURAL RUSTIC ROAD | 0791 | Secondary | Reconstruction w/o Added Capacity | VDOT | Loudoun County | LEESBURG | Northern Virginia | Northern Virginia:Loudoun County | Infrastructure Investment Division | Kimberly Mccool | Kimberly.McCool@vdot.virginia.gov | (703) 259-3220 | Mehrdad Naderi | Mehrdad.Naderi@vdot.virginia.gov | (703) 259-2217 | Susan Glass, Loudoun County Dept. of Transportation and Capital Infrastructure | susan.glass@loudoun.gov | (703) 777-0551 | 0 |  | 0 | FY2021 | 422530 | 422530 | AWARDED | G | Start Delivery milestone finished 101 days early | G | Project is on budget | [5 empty] | 2020-07-01 | 2018-12-03 | 2020-07-01 | 2018-12-03 | G | 2020-07-02 | 2018-12-03 | 2020-10-09 | 2020-10-22 | R | [5 empty] | 2019-01-25 | 2019-01-25 | 2019-01-25 | 2019-01-25 | G | [25 empty] | 2021-01-29 | 2020-10-22 | 2021-01-29 | 2020-10-22 | G | 2021-02-01 | 2020-10-23 | 2021-02-01 | 2020-10-23 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | WORK/TASK ORDER | 1 | 1 | 0.21325
1827 | 109507 | Pedestrian Intersection Safety Initiative | 9999 | Miscellaneous | Safety | VDOT | Bristol District-wide |  | Bristol | NonMPO:NonMPO | Infrastructure Investment Division | Jeffrey Buchanan | Jeff.Buchanan@vdot.virginia.gov | (276) 415-3440 | Jeremy J Mullins | Jeremy.Mullins@vdot.virginia.gov | (276) 696-3259 |  |  |  | 0 |  | 0 | FY2020 | 305000 | 183796 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished on-time | G | Project is on budget | [5 empty] | 2016-09-14 | 2016-08-02 | 2016-10-26 | 2016-08-02 | G | 2016-10-27 | 2016-08-02 | 2017-04-24 | 2018-08-06 | R | [5 empty] | 2019-05-09 | 2019-03-27 | 2019-06-20 | 2019-05-07 | G | [5 empty] | 2019-07-12 | 2019-05-29 | 2019-07-12 | 2019-05-29 | G | [5 empty] | 2019-06-26 | 2018-10-23 | 2019-09-26 | 2018-10-23 | G | [5 empty] | 2020-01-14 | 2020-03-10 | 2020-01-16 | 2020-03-10 | R | 2020-03-11 | 2020-03-11 | 2020-03-31 | 2020-03-31 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.067895
1828 | 109586 | BUS 29 - CONSTRUCT SIDEWALK (MADISON HEIGHTS) | 7029 | Primary | Safety | VDOT | Amherst County | APPOMATTOX | Lynchburg | Lynchburg:Amherst County | Infrastructure Investment Division | Raina A Rosado | Raina.Rosado@VDOT.Virginia.gov | (434) 856-8318 | Lindsey S Hodges | Lindsey.Hodges@vdot.virginia.gov | (434) 856-8143 |  |  |  | 0 |  | 0 | FY2020 | 1656337 | 2295487 | CONSTRUCTION STARTED | R | Start Delivery milestone finished 129 days late | R | Project estimate is less than $5M and is 20% or more over budget | [5 empty] | 2016-11-16 | 2016-11-16 | 2017-01-18 | 2017-01-18 | G | 2017-01-19 | 2017-01-19 | 2018-03-26 | 2018-07-06 | R | [5 empty] | 2018-10-17 | 2018-10-30 | 2018-10-30 | 2018-10-30 | G | 2019-05-01 | 2019-05-01 | 2019-05-14 | 2019-05-21 | R | 2019-09-09 | 2019-09-16 | 2020-03-05 | 2020-02-04 | G | 2019-05-17 | 2019-05-22 | 2019-12-09 | 2019-12-06 | G | [10 empty] | 2020-03-10 | 2020-07-07 | 2020-03-13 | 2020-07-07 | R | 2020-05-04 | 2020-09-28 | 2020-05-22 | 2020-09-28 | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.17079
1829 | 110886 | PEDESTRIAN IMPROVEMENTS AT OAK GROVE ELEMENTARY SCHOOL |  | Miscellaneous | Safety | Locally | Richmond | ASHLAND | Richmond | Richmond:Richmond | Infrastructure Investment Division | Evan Austin | Evan.Austin@vdot.virginia.gov | (804) 609-5384 | Evan Austin | Evan.Austin@vdot.virginia.gov | (804) 609-5384 | Maritza Feliz Reyes | Maritza.Reyes@richmondgov.com | (804) 646-6334 | 0 |  | 0 | FY2022 | 284200 | 283929 | ACTIVITY DATES SET | G | Obtained Permits milestone finished 132 days early | G | Project is on budget | 2019-07-01 | 2019-02-11 | 2019-09-24 | 2019-08-22 | G | 2019-09-25 | 2019-08-26 | 2019-09-27 | 2019-09-04 | G | 2019-09-30 | 2019-09-05 | 2020-04-09 | 2020-02-26 | G | [25 empty] | 2020-12-24 | 2020-11-19 | 2021-03-31 | 2020-11-19 | G | [5 empty] | 2021-04-28 |  | 2021-05-25 |  | G | 2021-05-26 |  | 2021-11-18 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.079566
1830 | 18003 | #HB2.FY17 RTE 277 - WIDEN TO 5 LANES | 0277 | Primary | Reconstruction w/ Added Capacity | VDOT | Frederick County | EDINBURG | Staunton | Winchester:Frederick County | Infrastructure Investment Division | Randolph S Kiser | Randy.Kiser@VDOT.Virginia.gov | (540) 332-9092 | John-Allen L Ennis | JohnAllen.Ennis@VDOT.Virginia.gov | (540) 332-9118 |  |  |  | 1 | 2017 | 0 | FY2020 | 35934878 | 42144286 | CONSTRUCTION STARTED | R | Start Delivery milestone finished 82 days late | R | Project estimate is greater than $10M and is over budget by (a) 10% or more or (b) $5M or more | [5 empty] | 1997-10-01 | 1997-09-17 | 1997-10-31 | 1997-09-17 | G | 2012-04-16 | 2012-03-14 | 2014-03-28 | 2014-05-22 | R | [5 empty] | 2014-06-23 | 2014-06-23 | 2015-04-14 | 2015-04-14 | G | 2016-02-01 | 2016-02-01 | 2016-12-09 | 2016-12-09 | G | 2018-12-03 | 2018-10-22 | 2019-10-01 | 2020-10-23 | R | 2016-12-16 | 2016-12-16 | 2018-11-16 | 2018-10-29 | G | 2018-07-02 | 2019-01-08 | 2019-07-12 | 2019-08-05 | R | [5 empty] | 2019-10-09 | 2020-01-07 | 2019-11-12 | 2020-01-07 | R | 2020-01-06 | 2020-05-20 | 2020-02-28 | 2020-05-20 | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.12933
1831 | 82510 | #SGR17VB - RT 711 - BR & APPROACHES OVER NS RR (Fed 4328) | 0711 | Secondary | Bridge Replacement w/o Added Capacity | VDOT | Campbell County | APPOMATTOX | Lynchburg | NonMPO:NonMPO | Infrastructure Investment/Asset Management Division | Veljibhai M Desai | Veljibhai.Desai@vdot.virginia.gov | (703) 259-2927 | Veljibhai M Desai | Veljibhai.Desai@vdot.virginia.gov | (703) 259-2927 |  |  |  | 0 |  | 1 | FY2019 | 2647667 | 4082181 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 44 days early | R | Project estimate is less than $5M and is 20% or more over budget | [5 empty] | 2009-08-12 | 2009-08-14 | 2009-10-26 | 2009-08-14 | G | 2009-08-18 | 2009-08-18 | 2009-12-10 | 2009-11-23 | G | [5 empty] | 2013-07-29 | 2013-07-29 | 2013-07-29 | 2013-07-29 | G | 2014-04-14 | 2014-04-14 | 2014-04-14 | 2014-04-14 | G | 2014-12-17 | 2014-12-17 | 2015-09-01 | 2015-09-01 | G | 2014-04-15 | 2014-04-15 | 2015-04-03 | 2015-04-03 | G | 2009-10-01 | 2009-10-01 | 2009-10-05 | 2009-10-05 | G | [5 empty] | 2018-04-13 | 2018-05-08 | 2018-05-08 | 2018-05-08 | G | 2018-07-05 | 2018-07-16 | 2018-08-29 | 2018-07-16 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.058071
1832 | 101302 | CONNER DRIVE - EXTENSION | 0000 | Urban | New Construction Roadway | Locally | Manassas Park | MANASSAS | Northern Virginia | Northern Virginia:Manassas Park | Local Assistance Division | Amir Salahshoor | A.Salahshoor@VDOT.Virginia.gov | (703) 259-1957 | Rhoderick M Undan | Rhoderick.Undan@vdot.virginia.gov | (703) 259-3347 | Calvin Odell | c.odell@manassasparkva.gov | (703) 335-0019 | 0 |  | 0 | FY2020 | 1413160 | 2355684 | ACTIVITY DATES SET | R | Complete Purchasing Right-of-Way milestone is 662 days past the expected completion date | R | Project estimate is less than $5M and is 20% or more over budget | 2011-08-30 | 2011-08-30 | 2011-08-30 | 2011-08-30 | G | 2011-07-01 | 2011-08-30 | 2011-07-01 | 2011-08-30 | R | 2012-06-01 | 2011-08-30 | 2012-07-05 | 2011-08-30 | G | [10 empty] | 2016-07-01 | 2016-07-01 | 2016-07-01 | 2016-07-01 | G | [5 empty] | 2016-07-05 | 2016-07-05 | 2019-05-01 |  | R | [10 empty] | 2019-05-01 |  | 2019-05-31 |  | R | 2019-06-03 |  | 2019-09-30 |  | R | Delay due to unforeseen issues with utilities, railroad coordination, or right-of-way acquisition | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.17293
1833 | 104179 | #SGR21VB - RT 608 OVER NSRR (STR 2685) -BRIDGE REPLACEMENT | 0608 | Secondary | Bridge Replacement w/o Added Capacity | VDOT | Bedford County | BEDFORD | Salem | NonMPO:NonMPO | Infrastructure Investment Division | Anthony T Marshall | Todd.Marshall@VDOT.Virginia.gov | (540) 387-5460 | Matthew S Prosser | Matt.Prosser@vdot.virginia.gov | (540) 387-5330 |  |  |  | 0 |  | 0 | FY2022 | 3554984 | 5578551 | ACTIVITY DATES SET | G | Complete Purchasing Right-of-Way milestone finished 375 days early | R | Project estimate is less than $5M and is 20% or more over budget | [5 empty] | 2016-07-12 | 2013-06-21 | 2016-07-12 | 2013-06-21 | G | 2016-01-04 | 2016-01-04 | 2017-06-15 | 2017-06-13 | G | [5 empty] | 2017-04-21 | 2017-04-21 | 2017-04-21 | 2017-04-21 | G | 2019-03-01 | 2019-04-30 | 2019-05-08 | 2019-05-09 | R | 2020-03-23 | 2019-03-23 | 2021-09-13 | 2019-03-23 | G | 2019-03-25 | 2019-06-21 | 2021-09-13 | 2020-09-03 | G | [10 empty] | 2021-08-20 |  | 2021-09-14 |  | G | 2021-10-28 |  | 2022-02-28 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.10223
1834 | 106144 | ARLINGTON SRTS IMPROVEMENTS - ASHLAWN ELEM & WILLIAMSBURG MS |  | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Arlington County | FAIRFAX | Northern Virginia | Northern Virginia:Arlington County | Local Assistance Division | Jeffrey S Daily | Jeff.Daily@VDOT.Virginia.gov | (703) 259-2993 | Rita Hockman | Rita.Hockman@vdot.virginia.gov | (804) 824-7421 | Peter Rigby | prigby@arlingtonva.us | (703) 228-3604 | 0 |  | 0 | FY2019 | 250065 | 250065 | CONSTRUCTION STARTED | R | Start Delivery milestone finished 87 days late | Y | Estimate not current | 2015-04-30 | 2015-04-30 | 2015-04-30 | 2015-04-30 | G | 2014-10-01 | 2015-08-06 | 2014-10-01 | 2015-08-06 | R | 2014-10-31 | 2014-10-31 | 2015-02-28 | 2015-02-28 | G | [35 empty] | 2019-04-04 | 2019-02-28 | 2019-04-04 | 2019-02-28 | G | 2019-04-18 | 2019-03-14 | 2019-05-17 | 2019-08-12 | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.36387
1835 | 108956 | Independence Blvd/Edwin Drive Intersection Improvements | 0225 | Urban | Traffic Management/Engineering | Locally | Virginia Beach | NORFOLK | Hampton Roads | Hampton Roads:Virginia Beach | Infrastructure Investment Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Marci Thompson | Marci.Thompson@vdot.virginia.gov | (757) 956-3093 | Dempsey Bruton |  |  | 0 |  | 0 | FY2025 | 647000 | 647000 | NO DATES SET YET | G | Agreement with Locality milestone is 220 days ahead of the expected completion date | G | Project is on budget | 2021-07-07 |  | 2021-09-29 |  | G | 2021-09-30 |  | 2021-10-13 |  | G | 2021-10-14 |  | 2022-09-30 |  | G | [10 empty] | 2023-07-28 |  | 2023-08-17 |  | G | [5 empty] | 2023-08-21 |  | 2024-06-03 |  | G | [10 empty] | 2024-06-19 |  | 2024-07-17 |  | G | 2024-07-18 |  | 2024-10-17 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.24399
1836 | 109302 | #HB2.FY17 General Thomas Highway Signalization Project | 0671 | Secondary | Reconstruction w/o Added Capacity | VDOT | Southampton County | FRANKLIN | Hampton Roads | NonMPO:NonMPO | Infrastructure Investment Division | Jesse Alan Williams | Alan.Williams@vdot.virginia.gov | (757) 925-1574 | Jesse Alan Williams | Alan.Williams@vdot.virginia.gov | (757) 925-1574 |  |  |  | 1 | 2017 | 0 | FY2017 | 650000 | 650000 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 69 days early | G | Project is on budget | [5 empty] | 2016-07-13 | 2016-07-13 | 2016-07-14 | 2016-07-14 | G | 2016-08-02 | 2016-08-02 | 2016-10-12 | 2016-10-12 | G | [5 empty] | 2016-08-18 | 2016-08-18 | 2016-08-18 | 2016-08-18 | G | [25 empty] | 2016-12-13 | 2016-12-13 | 2016-12-13 | 2016-12-13 | G | 2016-12-14 | 2016-12-14 | 2017-02-21 | 2016-12-14 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | WORK/TASK ORDER | 1 | 0 | 0.18594
1837 | 109513 | US Route 21 Rumble Stripe Initiative | 0021 | Primary | Safety | VDOT | Bristol District-wide |  | Bristol | NonMPO:NonMPO | Infrastructure Investment Division | Jeffrey Buchanan | Jeff.Buchanan@vdot.virginia.gov | (276) 415-3440 | Chase R Buchanan | Chase.Buchanan@VDOT.Virginia.gov | (276) 696-3251 |  |  |  | 0 |  | 0 | FY2020 | 4565000 | 4565000 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 61 days early | Y | Estimate not current | [5 empty] | 2017-08-01 | 2017-07-17 | 2017-08-14 | 2017-07-17 | G | 2017-08-15 | 2017-08-14 | 2018-04-11 | 2019-02-21 | R | [5 empty] | 2019-06-03 | 2019-06-03 | 2019-06-14 | 2019-06-14 | G | [5 empty] | 2019-06-06 | 2019-06-06 | 2019-06-06 | 2019-06-06 | G | [15 empty] | 2019-12-10 | 2019-12-10 | 2019-12-10 | 2019-12-10 | G | 2020-02-04 | 2020-02-27 | 2020-04-28 | 2020-02-27 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.071793
1840 | 111018 | #SMART18 - IRONBOUND ROAD IMPROVEMENTS - PHASE 2 | 7081 | Urban | Reconstruction w/ Added Capacity | Locally | Williamsburg | WILLIAMSBURG | Hampton Roads | Hampton Roads:Williamsburg | Infrastructure Investment Division | Dawn Odom | Dawn.Odom@vdot.virginia.gov | (000) 000-0000 | Chessica Villaflores | Chessica.Villaflores@vdot.virginia.gov | (757) 956-3094 | Aaron Small | ASmall@williamsburgva.gov | (757) 220-6140 | 1 | 2018 | 0 | FY2025 | 1922700 | 1922700 | NO DATES SET YET | G | Agreement with Locality milestone is 276 days ahead of the expected completion date | Y | Estimate not current | 2021-10-01 |  | 2021-11-24 |  | G | 2021-11-29 |  | 2021-12-01 |  | G | 2021-12-02 |  | 2022-06-09 |  | G | [10 empty] | 2023-06-13 |  | 2023-06-30 |  | G | [5 empty] | 2023-07-05 |  | 2024-05-16 |  | G | [10 empty] | 2024-06-04 |  | 2024-07-01 |  | G | 2024-07-02 |  | 2024-09-11 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.29005
1841 | 111026 | Exmore Controller Actuated Beacons | 0013 | Primary | Traffic Management/Engineering | VDOT | Exmore | ACCOMAC | Hampton Roads | NonMPO:NonMPO | Infrastructure Investment Division | Todd M Halacy | Todd.Halacy@VDOT.Virginia.gov | (757) 956-3010 | Jesse Alan Williams | Alan.Williams@vdot.virginia.gov | (757) 925-1574 | Exmore |  |  | 0 |  | 0 | FY2019 | 350916 | 322752 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 6 days early | G | Project is on budget | [5 empty] | 2018-10-01 | 2018-08-06 | 2018-10-01 | 2018-08-06 | G | 2018-10-02 | 2018-08-07 | 2019-01-15 | 2018-12-11 | G | [5 empty] | 2019-01-30 | 2019-01-30 | 2019-02-12 | 2019-02-12 | G | [25 empty] | 2019-05-14 | 2019-05-14 | 2019-05-14 | 2019-05-14 | G | 2019-05-15 | 2019-05-15 | 2019-05-21 | 2019-05-15 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | WORK/TASK ORDER | 1 | 0 | 0.15026
1842 | 111290 | #SGR18VB - REHAB BRIDGE, HENRICO COUNTY, STR 9612 CN ONLY | 7667 | Secondary | Bridge Rehab w/o Added Capacity | VDOT | Henrico County | ASHLAND | Richmond | Richmond:Henrico County | Infrastructure Investment/Asset Management Division | Clayton M Thomas | Clay.Thomas@VDOT.Virginia.gov | (804) 609-5429 | Clayton M Thomas | Clay.Thomas@VDOT.Virginia.gov | (804) 609-5429 |  |  |  | 0 |  | 1 | FY2023 | 5200000 | 6125893 | ACTIVITY DATES SET | G | Determine Requirements milestone finished 903 days early | Y | Project estimate is between $5M and $10M and is up to $1M over budget | [10 empty] | 2022-04-01 | 2018-10-10 | 2022-04-07 | 2019-10-17 | G | [35 empty] | 2022-05-10 |  | 2022-05-10 |  | G | 2022-08-26 |  | 2022-10-24 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 1 | 0.20383
1843 | 112900 | I-81 - INSTALL HIGH TENSION CABLE BARRIER | 0081 | Interstate | Safety | VDOT | Frederick County | EDINBURG | Staunton | NonMPO:NonMPO | Infrastructure Investment Division | Keith M Rider | Keith.Rider@VDOT.Virginia.gov | (434) 856-8145 | Kunal Kothawade | Kunal.Kothawade@vdot.virginia.gov | (540) 332-9259 |  |  |  | 0 |  | 0 | FY2024 | 2240000 | 2240000 | NO DATES SET YET | G | Start Development milestone is 264 days ahead of the expected completion date | G | Project is on budget | [5 empty] | 2021-10-29 |  | 2021-11-12 |  | G | 2021-11-15 |  | 2022-07-11 |  | G | [5 empty] | 2023-03-21 |  | 2023-05-01 |  | G | [5 empty] | 2023-08-15 |  | 2023-12-11 |  | G | [5 empty] | 2023-07-31 |  | 2023-10-31 |  | G | [5 empty] | 2023-12-12 |  | 2023-12-12 |  | G | 2024-03-07 |  | 2024-03-07 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.060099
1844 | 113277 | Frontage Road 171-Unpaved Rd.- to add to Secondary System | 9999 | Secondary | Reconstruction w/o Added Capacity | Locally | York County | WILLIAMSBURG | Hampton Roads | Hampton Roads:York County | Local Assistance Division | Christopher R Carroll | C.Carroll@VDOT.Virginia.gov | (757) 253-5140 | Keisha Wilkins | Keisha.Wilkins@vdot.virginia.gov | (757) 956-3110 | Tim Cross | tcross@yorkcounty.gov | (757) 890-3496 | 0 |  | 0 | FY2022 | 547770 | 547770 | ACTIVITY DATES SET | G | Determine Requirements milestone finished 4 days early | G | Project is on budget | 2019-10-01 | 2019-09-01 | 2019-12-30 | 2019-10-07 | G | 2019-12-31 | 2019-10-11 | 2020-01-03 | 2019-10-16 | G | 2020-01-06 | 2020-01-06 | 2020-07-10 | 2020-07-06 | G | [35 empty] | 2021-07-26 |  | 2021-10-19 |  | G | 2022-01-12 |  | 2022-05-06 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.17495
1845 | 113480 | #SGR19LB??- Wilkinson Rd over Upham Brook - Replace Culvert | 9999 | Urban | Bridge Rehab w/ Added Capacity | Locally | Henrico County | ASHLAND | Richmond | Richmond:Henrico County | Local Assistance Division | Douglas L Orcutt | Doug.Orcutt@vdot.virginia.gov | (804) 609-5428 | Douglas L Orcutt | Doug.Orcutt@vdot.virginia.gov | (804) 609-5428 | Paul Smith | smi91@henrico.us | (804) 501-5092 | 0 |  | 1 | FY2022 | 3063461 | 3063461 | NO DATES SET YET-PE OPEN | R | Determine Requirements milestone is 346 days past the expected completion date | G | Project is on budget | 2019-07-01 | 2019-07-01 | 2019-09-24 | 2020-09-10 | R | 2019-09-25 | 2020-09-22 | 2019-09-27 | 2020-09-24 | R | 2019-09-30 |  | 2020-03-12 |  | R | [10 empty] | 2020-10-14 |  | 2020-11-04 |  | R | [5 empty] | 2020-11-06 |  | 2021-08-19 |  | G | 2020-05-15 |  | 2021-01-22 |  | R | [5 empty] | 2021-09-07 |  | 2021-10-04 |  | G | 2021-12-28 |  | 2021-12-28 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.22084
1846 | 113853 | #SGR19VB - BRIDGE REPLACE RT 652 POLECAT CREEK ID 04485 | 0652 | Secondary | Bridge Replacement w/o Added Capacity | VDOT | Caroline County | FREDERICKSBURG | Fredericksburg | NonMPO:NonMPO | Infrastructure Investment/Asset Management Division | Anastasia Kapitan | Anastasia.Kapitan@vdot.virginia.gov | (540) 899-4292 | Anastasia Kapitan | Anastasia.Kapitan@vdot.virginia.gov | (540) 899-4292 |  |  |  | 0 |  | 1 | FY2023 | 2500000 | 2500000 | ACTIVITY DATES SET | Y | Engage Public milestone is 5 days ahead of the expected completion date and there is a risk of missing this milestone date | G | Project is on budget | [5 empty] | 2020-08-17 | 2019-02-01 | 2020-08-28 | 2019-02-14 | G | 2020-08-31 | 2019-02-15 | 2021-07-29 | 2021-02-04 | G | [5 empty] | 2020-11-30 |  | 2021-02-26 |  | Y | 2021-05-06 |  | 2021-05-19 |  | G | 2021-12-13 |  | 2022-06-20 |  | G | 2021-06-04 |  | 2021-12-10 |  | G | 2020-09-23 | 2020-09-23 | 2022-04-14 |  | G | [5 empty] | 2022-07-12 |  | 2022-07-12 |  | G | 2022-09-30 |  | 2022-09-30 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.058717
1847 | 113996 | ROUTE 301 J TURN AT PORT CONWAY | 0301 | Primary | Safety | VDOT | King George County | FREDERICKSBURG | Fredericksburg | NonMPO:NonMPO | Infrastructure Investment Division | Peter A Hedrich | Peter.Hedrich@vdot.virginia.gov | (540) 899-4540 | Michelle G Kimble | Michelle.Kimble@VDOT.Virginia.gov | (804) 609-5331 |  |  |  | 0 |  | 0 | FY2026 | 585015 | 585015 | WAITING FINANCIAL CLOSURE | G | Start Development milestone is 953 days ahead of the expected completion date | Y | Estimate not current | [5 empty] | 2023-09-19 |  | 2023-10-02 |  | G | 2023-10-03 |  | 2024-04-05 |  | G | [5 empty] | 2024-09-23 |  | 2024-11-04 |  | G | [5 empty] | 2025-04-23 |  | 2025-08-14 |  | G | [5 empty] | 2025-02-10 |  | 2025-05-12 |  | G | [5 empty] | 2025-09-09 |  | 2025-09-09 |  | G | 2025-12-03 |  | 2025-12-03 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.066621
1848 | 115417 | #SMART20 - W Broad St Pedestrian and Transit Improvements | 0250 | Primary | Facilities for Pedestrians and Bicycles | VDOT | Henrico County | ASHLAND | Richmond | Richmond:Henrico County | Infrastructure Investment Division | William Wheeler | William.Wheeler@vdot.virginia.gov | (804) 609-5280 | William Wheeler | William.Wheeler@vdot.virginia.gov | (804) 609-5280 |  |  |  | 1 | 2020 | 0 | FY2028 | 10857000 | 10857000 | NO DATES SET YET-PE OPEN | G | Obtained Permits milestone finished 2388 days early | G | Project is on budget | [5 empty] | 2023-08-01 | 2019-09-18 | 2023-08-14 | 2019-10-15 | G | 2023-08-15 |  | 2024-07-12 |  | G | [5 empty] | 2025-05-19 |  | 2025-06-02 |  | G | 2026-09-04 |  | 2026-09-18 |  | G | 2027-02-19 |  | 2027-08-23 |  | G | 2026-10-06 |  | 2027-04-16 |  | G | 2026-02-26 | 2020-02-13 | 2026-08-28 | 2020-02-13 | G | [5 empty] | 2027-09-14 |  | 2027-09-14 |  | G | 2027-12-08 |  | 2027-12-08 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.10889
1849 | 115476 | #SMART20 - 5TH STREET SW CORRIDOR IMPROVEMENTS | 9999 | Urban | Facilities for Pedestrians and Bicycles | Locally | Charlottesville | CHARLOTTESVILLE | Culpeper | Charlottesville:Charlottesville | Infrastructure Investment Division | Gregory J Cooley | Gregory.Cooley@vdot.virginia.gov | (434) 906-7979 | Michael D Barnes | MichaelD.Barnes@vdot.virginia.gov | (434) 422-9861 | BRENNAN DUNCAN | DUNCANB@CHARLOTTESVILLE.ORG | (434) 970-3993 | 1 | 2020 | 0 | FY2028 | 6103034 | 6103034 | NO DATES SET YET | G | Agreement with Locality milestone is 1061 days ahead of the expected completion date | G | Project is on budget | 2023-11-01 |  | 2024-01-18 |  | G | 2024-01-19 |  | 2024-02-01 |  | G | 2024-02-02 |  | 2025-06-25 |  | G | [10 empty] | 2026-07-29 |  | 2026-08-18 |  | G | [5 empty] | 2026-08-20 |  | 2027-08-27 |  | G | 2024-09-05 |  | 2025-05-13 |  | G | [5 empty] | 2027-09-15 |  | 2027-12-13 |  | G | 2028-03-07 |  | 2028-05-30 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.18065
1850 | 111022 | #SMART18 - CAPITOL LANDING ROAD AT BYPASS ROAD INTERSECTION | 0005 | Urban | Reconstruction w/o Added Capacity | Locally | Williamsburg | WILLIAMSBURG | Hampton Roads | Hampton Roads:Williamsburg | Infrastructure Investment Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Chessica Villaflores | Chessica.Villaflores@vdot.virginia.gov | (757) 956-3094 | Aaron Small | asmall@williamsburgva.gov | (757) 220-6140 | 1 | 2018 | 0 | FY2025 | 2144760 | 2144760 | NO DATES SET YET | G | Agreement with Locality milestone is 200 days ahead of the expected completion date | Y | Estimate not current | 2021-06-16 |  | 2021-09-09 |  | G | 2021-09-10 |  | 2021-09-14 |  | G | 2021-09-15 |  | 2022-03-28 |  | G | [10 empty] | 2024-02-12 |  | 2024-03-01 |  | G | [5 empty] | 2024-03-05 |  | 2024-07-17 |  | G | [10 empty] | 2024-08-02 |  | 2024-08-29 |  | G | 2024-08-30 |  | 2024-11-12 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.22308
1851 | 111289 | #SGR18VB - REHAB BRIDGE, HANOVER COUNTY, STR 9412 CN ONLY | 0156 | Primary | Bridge Rehab w/o Added Capacity | VDOT | Hanover County | ASHLAND | Richmond | Richmond:Hanover County | Infrastructure Investment/Asset Management Division | Thomas Kendrick | Thomas.Kendrick@vdot.virginia.gov | (804) 609-5281 | Lawrence Ramsey | Brian.Ramsey@VDOT.Virginia.gov | (804) 585-3579 |  |  |  | 0 |  | 1 | FY2021 | 2400000 | 2000000 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 162 days early | G | Project is on budget | [10 empty] | 2022-05-02 | 2019-09-12 | 2022-05-06 | 2019-10-17 | G | [35 empty] | 2020-03-10 | 2020-03-10 | 2020-03-10 | 2020-03-10 | G | 2020-05-29 | 2020-06-25 | 2020-12-04 | 2020-06-25 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.099907
1852 | 111362 | #SMART18 - Summit View Regional Business Park Project | 0697 | Secondary | New Construction Roadway | Locally | Franklin County | BEDFORD | Salem | NonMPO:NonMPO | Infrastructure Investment Division | Jessie Nester | Jessie.Nester@vdot.virginia.gov | (540) 613-4115 | Jessie Nester | Jessie.Nester@vdot.virginia.gov | (540) 613-4115 | Lisa Cooper | lisa.cooper@franklincountyva.gov | (540) 483-6642 | 1 | 2018 | 0 | FY2027 | 22056050 | 5018684 | NO DATES SET YET | G | Agreement with Locality milestone is 593 days ahead of the expected completion date | G | Project is on budget | 2022-07-15 |  | 2022-10-07 |  | G | 2022-10-10 |  | 2022-10-12 |  | G | 2022-10-13 |  | 2023-10-13 |  | G | [5 empty] | 2025-01-16 |  | 2025-01-31 |  | G | [25 empty] | 2026-03-05 |  | 2026-04-01 |  | G | 2026-04-02 |  | 2026-07-17 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.27111
1853 | 113269 | Effingham St.Improvements at Portsmouth Naval Medical Center | 0923 | Urban | Reconstruction w/ Added Capacity | Locally | Portsmouth | NORFOLK | Hampton Roads | Hampton Roads:Portsmouth | Local Assistance Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Marci Thompson | Marci.Thompson@vdot.virginia.gov | (757) 956-3093 | James Wright, P.E. | wrightj@portsmouthva.gov | (757) 393-8592 | 0 |  | 0 | FY2022 | 500000 | 500000 | ACTIVITY DATES SET | G | Engage Public milestone finished 38 days early | G | Project is on budget | 2018-09-04 | 2018-09-04 | 2018-11-30 | 2019-02-26 | R | 2018-12-03 | 2019-02-27 | 2018-12-05 | 2019-03-08 | R | 2018-12-06 | 2019-03-11 | 2019-06-13 | 2020-06-30 | R | 2020-09-11 | 2020-09-11 | 2020-10-23 | 2020-09-15 | G | [20 empty] | 2019-08-08 | 2019-08-08 | 2019-09-05 | 2019-09-05 | G | [5 empty] | 2021-11-29 |  | 2021-12-27 |  | G | 2022-03-21 |  | 2022-05-27 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.15987
1854 | 113468 | Parliament Drive Sidewalk Phase II | 0000 | Urban | Facilities for Pedestrians and Bicycles | Locally | Virginia Beach | NORFOLK | Hampton Roads | Hampton Roads:Virginia Beach | Local Assistance Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Marci Thompson | Marci.Thompson@vdot.virginia.gov | (757) 956-3093 | Katie Shannon | kshannon@vbgov.com | (757) 385-1514 | 0 |  | 0 | FY2023 | 966353 | 966353 | ACTIVITY DATES SET | R | Determine Requirements milestone finished 616 days late | G | Project is on budget | 2018-08-31 | 2018-08-31 | 2018-11-29 | 2019-04-04 | R | 2018-11-30 | 2019-04-10 | 2018-12-04 | 2019-04-16 | R | 2018-12-05 | 2019-04-17 | 2019-06-12 | 2021-02-17 | R | [10 empty] | 2022-04-04 |  | 2022-04-22 |  | G | [5 empty] | 2022-04-26 |  | 2023-02-07 |  | G | 2022-01-25 |  | 2022-09-23 |  | G | [5 empty] | 2023-02-24 |  | 2023-03-23 |  | G | 2023-06-12 |  | 2023-06-12 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.095773
1855 | 113699 | #SGR19LB -??Freeman Mill Road over Spivey Swamp | 0668 | Urban | Bridge Replacement w/o Added Capacity | Locally | Suffolk | NORFOLK | Hampton Roads | Hampton Roads:Suffolk | Infrastructure Investment Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Johndel A Alcaide | John.Alcaide@vdot.virginia.gov | (757) 956-3098 | L. Hansen | lhansen@suffolkva.us | (757) 514-7687 | 0 |  | 1 | FY2025 | 1193000 | 1193000 | NO DATES SET YET | G | Agreement with Locality milestone is 625 days ahead of the expected completion date | Y | Estimate not current | 2022-08-15 |  | 2022-11-08 |  | G | 2022-11-09 |  | 2022-11-14 |  | G | 2022-11-15 |  | 2023-05-24 |  | G | [10 empty] | 2024-03-21 |  | 2024-04-10 |  | G | [5 empty] | 2024-04-12 |  | 2025-01-24 |  | G | 2023-06-30 |  | 2024-03-08 |  | G | [5 empty] | 2025-02-11 |  | 2025-03-11 |  | G | 2025-05-29 |  | 2025-05-29 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.11006
1856 | 113883 | Virginia Avenue Primary Extension Paving | 0000 | Urban | Resurfacing | Locally | Bluefield | LEBANON | Bristol | NonMPO:NonMPO | Local Assistance Division | Tabitha H Crowder | Tabitha.Crowder@vdot.virginia.gov | (276) 696-3482 | Tabitha H Crowder | Tabitha.Crowder@vdot.virginia.gov | (276) 696-3482 | Mike Watson - Town Manager | watson@bluefieldva.org | (276) 322-4626 | 0 |  | 0 | FY2020 | 456023 | 456023 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 84 days early | G | Project is on budget | 2019-06-17 | 2018-08-18 | 2019-09-10 | 2018-12-26 | G | [5 empty] | 2019-06-17 | 2019-06-17 | 2019-06-28 | 2019-06-28 | G | [25 empty] | 2019-07-01 | 2019-06-28 | 2019-11-06 | 2019-06-28 | G | [5 empty] | 2019-10-01 | 2019-09-15 | 2019-11-27 | 2019-10-15 | G | 2020-02-24 | 2019-12-01 | 2020-02-24 | 2019-12-02 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.049287
1857 | 115406 | #SMART20 - Route 106/ Route 5 Roundabout | 0005 | Primary | Safety | VDOT | Charles City County | ASHLAND | Richmond | Richmond:Charles City County | Infrastructure Investment Division | Raymond Chapman | Scott.Chapman@vdot.virginia.gov | (804) 609-5277 | Raymond Chapman | Scott.Chapman@vdot.virginia.gov | (804) 609-5277 |  |  |  | 1 | 2020 | 0 | FY2028 | 4110000 | 4110000 | NO DATES SET YET | G | Start Development milestone is 936 days ahead of the expected completion date | G | Project is on budget | [5 empty] | 2023-09-01 |  | 2023-09-15 |  | G | 2023-09-18 |  | 2024-08-14 |  | G | [5 empty] | 2025-06-20 |  | 2025-07-03 |  | G | 2026-10-08 |  | 2026-10-22 |  | G | 2027-03-24 |  | 2027-09-24 |  | G | 2026-11-09 |  | 2027-05-19 |  | G | 2026-03-31 |  | 2026-10-01 |  | G | [5 empty] | 2027-10-12 |  | 2027-10-12 |  | G | 2028-01-07 |  | 2028-01-07 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.065609
1858 | 115473 | #SGR17VB - RT 813 OVER ROANOKE RIVER (STR12363) SUB REPAIRS | 0813 | Secondary | Bridge Rehab w/o Added Capacity | VDOT | Roanoke County | SALEM | Salem | Roanoke:Roanoke County | Infrastructure Investment/Asset Management Division | Anthony T Marshall | Todd.Marshall@VDOT.Virginia.gov | (540) 387-5460 | Bryan D Smith | BryanD.Smith@vdot.virginia.gov | (540) 375-3575 |  |  |  | 0 |  | 1 | FY2020 | 2411233 | 2411233 | NO DATES SET YET-PE OPEN | R | Determine Requirements milestone is 562 days past the expected completion date | G | Project is on budget | [5 empty] | 2019-06-28 | 2019-07-26 | 2019-07-12 | 2019-08-06 | R | 2019-07-15 | 2019-08-07 | 2019-08-09 |  | R | [25 empty] | 2019-11-18 |  | 2022-07-20 |  | G | [5 empty] | 2020-03-10 |  | 2020-03-10 |  | R | 2020-05-29 |  | 2020-05-29 |  | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.16188
1859 | 115504 | #SMART20 Warwick Blvd & Oyster Point Rd Intersection Improve | 0060 | Primary | Safety | Locally | Newport News | WILLIAMSBURG | Hampton Roads | Hampton Roads:Newport News | Infrastructure Investment Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Chessica Villaflores | Chessica.Villaflores@vdot.virginia.gov | (757) 956-3094 | Bryan Stilley | bstilley@nnva.gov | (757) 926-8699 | 1 | 2020 | 0 | FY2026 | 5445737 | 5445737 | NO DATES SET YET | G | Agreement with Locality milestone is 953 days ahead of the expected completion date | G | Project is on budget | 2023-07-10 |  | 2023-10-02 |  | G | 2023-10-03 |  | 2023-10-05 |  | G | 2023-10-06 |  | 2024-04-17 |  | G | [10 empty] | 2025-04-21 |  | 2025-05-09 |  | G | [5 empty] | 2025-05-13 |  | 2026-02-25 |  | G | 2024-05-23 |  | 2025-01-30 |  | G | [5 empty] | 2026-03-13 |  | 2026-04-09 |  | G | 2026-06-29 |  | 2026-06-29 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.23845
1860 | 116040 | ROUTE 11 AND I-81 RAMP IMPROVEMENTS EXIT 307 AND 317 | 0011 | Interstate | Safety | VDOT | Frederick County | EDINBURG | Staunton | Winchester:Frederick County | Infrastructure Investment Division | Matthew Bond | Matthew.Bond@vdot.virginia.gov | (540) 332-9275 | Michael L Surratt | Michael.Surratt@VDOT.Virginia.gov | (540) 332-9325 |  |  |  | 0 |  | 0 | FY2020 | 630355 | 630355 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 57 days early | G | Project is on budget | [5 empty] | 2019-08-01 | 2019-09-24 | 2019-08-01 | 2019-09-24 | R | 2019-08-02 | 2019-09-25 | 2019-11-12 | 2019-11-12 | G | [5 empty] | 2019-11-25 | 2019-11-25 | 2019-12-10 | 2019-12-10 | G | [25 empty] | 2019-12-26 | 2019-12-26 | 2020-04-30 | 2020-03-05 | G | 2020-05-01 | 2020-03-06 | 2020-05-29 | 2020-04-02 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | WORK/TASK ORDER | 1 | 0 | 0.06359
1861 | 116918 | SRTS GRACE MILLER ELEMENTARY SCHOOL |  | Primary | Facilities for Pedestrians and Bicycles | Locally | Fauquier County | WARRENTON | Culpeper | NonMPO:NonMPO | Local Assistance Division | Gregory J Cooley | Gregory.Cooley@vdot.virginia.gov | (434) 906-7979 | John P Price | John.Price@VDOT.Virginia.gov | (540) 347-6371 | Donnie Kozanecki | donnie.kozanecki@fauquiercounty.gov | (540) 422-8476 | 0 |  | 0 | FY2024 | 678075 | 678075 | NO DATES SET YET | Y | Start Development milestone is 16 days ahead of the expected completion date and there is a risk of missing this milestone date | G | Project is on budget | 2020-10-01 | 2020-10-01 | 2021-02-15 | 2021-02-10 | G | 2021-02-16 |  | 2021-03-09 |  | Y | 2021-09-13 |  | 2022-01-10 |  | G | [10 empty] | 2023-05-02 |  | 2023-06-06 |  | G | [5 empty] | 2023-06-07 |  | 2023-11-03 |  | G | 2023-10-02 |  | 2024-03-07 |  | G | [5 empty] | 2024-02-14 |  | 2024-03-13 |  | G | 2024-05-31 |  | 2024-05-31 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.19878
1863 | 102992 | Shoulders Hill Road Multi-Use Path | 0000 | Urban | Facilities for Pedestrians and Bicycles | Locally | Suffolk | NORFOLK | Hampton Roads | Hampton Roads:Suffolk | Infrastructure Investment Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Johndel A Alcaide | John.Alcaide@vdot.virginia.gov | (757) 956-3098 | Sandon Rogers | srogers@suffolkva.us | (757) 514-7683 | 0 |  | 0 | FY2023 | 272000 | 272000 | NO DATES SET YET-PE OPEN | G | Start Development milestone finished 14 days early | G | Project is on budget | 2020-07-01 | 2020-07-15 | 2020-09-24 | 2020-07-22 | G | 2020-09-25 | 2020-09-14 | 2020-10-08 | 2020-09-24 | G | 2020-10-09 |  | 2021-09-24 |  | G | [35 empty] | 2022-07-07 |  | 2022-08-17 |  | G | 2022-08-18 |  | 2023-02-14 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.15343
1864 | 104887 | RTE 60 - BRIDGE REHABILITATION | 0060 | Urban | Bridge Rehab w/o Added Capacity | Locally | Richmond | ASHLAND | Richmond | Richmond:Richmond | Infrastructure Investment Division | Brian J Lokker | Brian.Lokker@VDOT.Virginia.gov | (804) 524-6010 | Brian J Lokker | Brian.Lokker@VDOT.Virginia.gov | (804) 524-6010 | LAMONT BENJAMIN | lamont.benjamin@richmondgov.com | (804) 646-6339 | 0 |  | 0 | FY2019 | 2020000 | 2020000 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 24 days early | G | Project is on budget | 2015-02-02 | 2015-01-26 | 2015-02-28 | 2015-01-26 | G | 2015-03-02 | 2015-02-10 | 2015-03-31 | 2015-02-10 | G | 2015-09-01 | 2015-08-26 | 2018-02-28 | 2018-02-15 | G | [35 empty] | 2018-03-14 | 2018-03-14 | 2018-04-30 | 2018-04-27 | G | 2018-05-30 | 2018-05-30 | 2018-11-19 | 2018-10-26 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.20012
1865 | 105785 | ARLINGTON BOULEVARD TRAIL IMPROVEMENTS | 0050 | Primary | Facilities for Pedestrians and Bicycles | Locally | Arlington County | FAIRFAX | Northern Virginia | Northern Virginia:Arlington County | Local Assistance Division | Amir Salahshoor | A.Salahshoor@VDOT.Virginia.gov | (703) 259-1957 | Rita Hockman | Rita.Hockman@vdot.virginia.gov | (804) 824-7421 | Kelly Cornell | kcornell@arlingtonva.us | (703) 228-0088 | 0 |  | 0 | FY2019 | 41250 | 41250 | WAITING FINANCIAL CLOSURE | R | Start Delivery milestone finished 311 days late | Y | Estimate not current | [10 empty] | 2014-04-01 | 2014-04-01 | 2014-04-30 | 2014-04-30 | G | [35 empty] | 2018-05-22 | 2018-05-22 | 2018-06-29 | 2018-05-22 | G | 2018-07-02 | 2019-08-05 | 2018-09-28 | 2019-08-05 | R | Delay due to changes in scope of work, project management, plan designs, or resolution of public comments | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.20564
1866 | 108696 | QUIOCASSIN ROAD - CONSTRUCT NEW SIDEWALK | 9999 | Secondary | Facilities for Pedestrians and Bicycles | Locally | Henrico County | ASHLAND | Richmond | Richmond:Henrico County | Local Assistance Division | Brian J Lokker | Brian.Lokker@VDOT.Virginia.gov | (804) 524-6010 | Brian J Lokker | Brian.Lokker@VDOT.Virginia.gov | (804) 524-6010 | Pau Smith | smi91@HENRICO.US | (804) 501-5092 | 0 |  | 0 | FY2020 | 930000 | 930000 | CONSTRUCTION COMPLETED | R | Start Delivery milestone finished 60 days late | G | Project is on budget | 2017-01-30 | 2016-07-01 | 2017-04-24 | 2016-10-18 | G | 2017-04-25 | 2016-12-12 | 2017-04-27 | 2016-12-14 | G | 2017-04-28 | 2017-08-02 | 2017-11-01 | 2017-09-07 | G | [10 empty] | 2018-08-28 | 2018-01-22 | 2018-09-18 | 2018-01-26 | G | [5 empty] | 2018-09-20 | 2018-01-28 | 2019-07-03 | 2019-10-02 | R | [10 empty] | 2019-07-22 | 2019-10-11 | 2019-08-16 | 2019-10-11 | R | 2019-08-19 | 2019-11-06 | 2019-09-27 | 2019-11-26 | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.34985
1867 | 109056 | PHASE I - RTE 645 - CONSTRUCT SIDEWALK | 0645 | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Charlotte C.H. | HALIFAX | Lynchburg | NonMPO:NonMPO | Local Assistance Division | Sharon S White | Sharon.White@VDOT.Virginia.gov | (434) 856-8220 | John E Neblett | John.Neblett@VDOT.Virginia.gov | (434) 856-8202 | Karen Price | clerk@towncch.com | (434) 542-5781 | 0 |  | 0 | FY2020 | 314820 | 675000 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 238 days early | R | Project estimate is less than $5M and is 20% or more over budget | 2017-04-18 | 2017-04-18 | 2017-05-01 | 2017-05-01 | G | 2017-07-13 | 2017-07-13 | 2017-07-17 | 2017-07-17 | G | 2018-05-08 | 2018-04-20 | 2018-11-09 | 2018-10-12 | G | [10 empty] | 2019-04-26 | 2019-04-26 | 2019-05-16 | 2019-04-26 | G | [5 empty] | 2019-05-20 | 2019-04-30 | 2019-08-23 | 2019-08-05 | G | [10 empty] | 2019-09-11 | 2019-08-28 | 2019-10-08 | 2019-09-30 | G | 2019-10-09 | 2019-10-01 | 2020-06-30 | 2019-11-05 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.25982
1868 | 109306 | #HB2.FY17 WEST BROAD - STREETSCAPE | 0250 | Urban | Landscaping/Beautification | Locally | Richmond | ASHLAND | Richmond | Richmond:Richmond | Infrastructure Investment Division | Douglas L Orcutt | Doug.Orcutt@vdot.virginia.gov | (804) 609-5428 | Douglas L Orcutt | Doug.Orcutt@vdot.virginia.gov | (804) 609-5428 | Yongping Wang | yongping.wang@Richmondgov.com | (804) 646-2467 | 1 | 2017 | 0 | FY2020 | 6020287 | 6020287 | ACTIVITY DATES SET | R | Solicit Bids milestone is 447 days past the expected completion date | G | Project is on budget | 2016-10-03 | 2016-08-25 | 2016-12-30 | 2017-01-12 | R | 2017-01-03 | 2017-01-12 | 2017-01-05 | 2017-01-13 | R | 2017-01-06 | 2017-01-17 | 2018-01-08 | 2017-12-18 | G | [5 empty] | 2018-12-13 | 2020-08-12 | 2018-12-13 | 2020-08-12 | R | [25 empty] | 2019-11-07 |  | 2019-12-02 |  | R | 2019-12-03 |  | 2020-01-14 |  | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.20637
1869 | 109612 | DOWNTOWN STREETSCAPE IMPROVEMENTS |  | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Salem | SALEM | Salem | Roanoke:Salem | Local Assistance Division | James M Guy | james.guy@vdot.virginia.gov | (540) 387-5247 | Cheryl B Becker | Cheryl.Becker@vdot.virginia.gov | (540) 492-2531 | Will Simpson | wsimpson@salemva.gov | (540) 375-3032 | 0 |  | 0 | FY2020 | 613000 | 1130397 | CONSTRUCTION STARTED | R | Start Delivery milestone finished 224 days late | R | Project estimate is less than $5M and is 20% or more over budget | 2016-08-01 | 2016-08-01 | 2016-09-29 | 2016-09-29 | G | 2016-10-18 | 2016-10-18 | 2016-12-02 | 2016-12-02 | G | 2017-06-13 | 2017-06-13 | 2018-04-03 | 2018-04-24 | R | [35 empty] | 2019-07-08 | 2019-08-15 | 2019-08-02 | 2019-09-08 | R | 2019-08-05 | 2019-09-09 | 2019-12-30 | 2020-08-10 | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.45821
1870 | 116905 | CONNECTOR ROAD FROM BERKMAR DR. EXT. TO AIRPORT ROAD | 9999 | Secondary | New Construction Roadway | VDOT | Albemarle County | CHARLOTTESVILLE | Culpeper | Charlottesville:Albemarle County | Local Assistance Division | Gregory J Cooley | Gregory.Cooley@vdot.virginia.gov | (434) 906-7979 | Michael Jacobs | Mike.Jacobs@VDOT.Virginia.gov | (540) 829-7502 |  |  |  | 0 |  | 0 | FY2024 | 11096200 | 11096200 | NO DATES SET YET | R | Start Development milestone is 122 days past the expected completion date | G | Project is on budget | [5 empty] | 2020-10-01 |  | 2020-10-22 |  | R | 2020-10-23 |  | 2021-08-26 |  | G | [5 empty] | 2022-04-01 |  | 2022-04-28 |  | G | 2022-12-20 |  | 2023-01-27 |  | G | 2023-06-27 |  | 2023-10-26 |  | G | 2023-02-13 |  | 2023-07-12 |  | G | 2023-03-22 |  | 2023-08-17 |  | G | [5 empty] | 2023-11-14 |  | 2023-11-14 |  | G | 2024-02-08 |  | 2024-02-08 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 1 | 0.35534
1871 | 118060 | Green ES SRTS Phase II |  | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Richmond | ASHLAND | Richmond | Richmond:Richmond | Local Assistance Division | James Shepherd | James.Shepherd@vdot.virginia.gov | (804) 609-5305 | James Shepherd | James.Shepherd@vdot.virginia.gov | (804) 609-5305 | Adel Edward | adel.edward@richmondgov.com | (804) 646-6581 | 0 |  | 0 | FY2024 | 675000 | 675000 | NO DATES SET YET | G | Agreement with Locality milestone is 199 days ahead of the expected completion date | G | Project is on budget | 2021-05-03 |  | 2021-09-08 |  | G | 2021-09-09 |  | 2021-09-29 |  | G | 2022-04-13 |  | 2022-08-04 |  | G | [25 empty] | 2023-08-01 |  | 2024-01-03 |  | G | [5 empty] | 2024-03-05 |  | 2024-04-01 |  | G | 2024-06-19 |  | 2024-06-19 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.35356
1872 | 102937 | Rte. 1 over S. River, Bridge Rehabilitation, Ex Fed ID 04358 | 0001 | Primary | Bridge Rehab w/o Added Capacity | VDOT | Caroline County | FREDERICKSBURG | Fredericksburg | NonMPO:NonMPO | Infrastructure Investment Division | Curtis B Holloway | Curtis.Holloway@vdot.virginia.gov | (540) 374-3367 | Curtis B Holloway | Curtis.Holloway@vdot.virginia.gov | (540) 374-3367 |  |  |  | 0 |  | 0 | FY2023 | 3365158 | 3365158 | ACTIVITY DATES SET | G | Start Purchasing Right-of-Way milestone finished 56 days early | G | Project is on budget | [5 empty] | 2017-02-16 | 2017-02-16 | 2017-03-02 | 2017-02-24 | G | 2017-03-03 | 2017-02-27 | 2018-03-28 | 2018-03-27 | G | [5 empty] | 2018-12-31 | 2018-12-31 | 2019-02-19 | 2019-02-19 | G | 2020-12-11 | 2020-10-29 | 2020-12-24 | 2020-10-29 | G | 2021-07-20 |  | 2022-01-28 |  | G | 2021-01-12 | 2020-11-09 | 2021-07-19 |  | G | 2019-02-20 | 2019-02-20 | 2019-05-01 | 2019-05-01 | G | [5 empty] | 2022-02-08 |  | 2022-02-08 |  | G | 2022-05-12 |  | 2022-07-08 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.12611
1873 | 103393 | ASHLAND TROLLEY LINE TRAIL | 0000 | Miscellaneous | Facilities for Pedestrians and Bicycles | Locally | Ashland | ASHLAND | Richmond | Richmond:Ashland | Infrastructure Investment Division | Brian J Lokker | Brian.Lokker@VDOT.Virginia.gov | (804) 524-6010 | Brian J Lokker | Brian.Lokker@VDOT.Virginia.gov | (804) 524-6010 | Tom Dickerson | tdickerson@ashlandva.gov | (804) 299-3225 | 0 |  | 0 | FY2019 | 1161620 | 1575156 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 129 days early | R | Project estimate is less than $5M and is 20% or more over budget | 2016-08-31 | 2016-11-02 | 2016-10-31 | 2016-11-02 | R | 2016-11-30 | 2016-11-16 | 2016-11-30 | 2016-11-16 | G | 2017-10-16 | 2017-08-31 | 2017-10-16 | 2017-10-11 | G | [5 empty] | 2017-10-26 | 2017-10-26 | 2017-11-15 | 2017-11-15 | G | 2017-11-15 | 2017-11-15 | 2017-12-13 | 2017-12-13 | G | [20 empty] | 2018-08-31 | 2018-07-25 | 2018-08-31 | 2018-07-25 | G | 2018-11-30 | 2018-11-20 | 2019-03-29 | 2018-11-20 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.09418
1874 | 105772 | FY15 RS - Drainage Improvements - Hans Meadow Dr | 0000 | Urban | Other | Locally | Christiansburg | CHRISTIANSBURG | Salem | New River Valley:Christiansburg | Local Assistance Division | Adam J Czesnowski | Adam.Czesnowski@vdot.virginia.gov | (540) 541-1216 | Adam J Czesnowski | Adam.Czesnowski@vdot.virginia.gov | (540) 541-1216 | Wayne Nelson | wnelson@christiansburg.org | (540) 382-6120 | 0 |  | 0 | FY2019 | 1092500 | 1092500 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 119 days early | G | Project is on budget | [5 empty] | 2014-08-01 | 2014-09-09 | 2014-08-01 | 2014-09-11 | R | 2014-09-02 | 2014-09-24 | 2014-12-31 | 2017-01-23 | R | [10 empty] | 2018-02-01 | 2018-01-31 | 2018-04-27 | 2018-01-31 | G | [20 empty] | 2018-07-02 | 2018-07-01 | 2018-07-02 | 2018-07-01 | G | 2018-07-16 | 2018-07-13 | 2019-01-02 | 2018-09-05 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.12966
1875 | 107513 | TOBACCO HERITAGE TRAIL - ALBERTA SECTION - TAP |  | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Alberta | SOUTH HILL | Richmond | NonMPO:NonMPO | Local Assistance Division | Jorg Huckabee-Mayfield | Jorg.Huckabee-Mayfield@VDOT.Virginia.gov | (804) 609-5292 | Jorg Huckabee-Mayfield | Jorg.Huckabee-Mayfield@VDOT.Virginia.gov | (804) 609-5292 | Curtis Williams | mayorofalbertava@gmail.com | (434) 949-7443 | 0 |  | 0 | FY2020 | 508654 | 438537 | ADVERTISED | R | Start Delivery milestone is 599 days past the expected completion date | G | Project is on budget | 2016-09-06 | 2016-09-06 | 2016-09-06 | 2016-09-06 | G | 2016-10-05 | 2016-10-05 | 2016-10-14 | 2016-10-14 | G | 2017-10-11 | 2017-10-11 | 2018-07-02 | 2018-07-02 | G | [10 empty] | 2016-09-06 | 2016-09-06 | 2016-09-06 | 2016-09-06 | G | [20 empty] | 2019-01-24 | 2019-09-17 | 2019-02-27 | 2019-10-23 | R | 2019-02-28 |  | 2019-07-03 |  | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.34831
1876 | 109024 | BESSIE WELLER ELEMENTARY SRTS |  | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Staunton | HARRISONBURG | Staunton | SAW:Staunton | Local Assistance Division | Michael S Fulcher | Michael.Fulcher@VDOT.Virginia.gov | (540) 332-2243 | Michael S Fulcher | Michael.Fulcher@VDOT.Virginia.gov | (540) 332-2243 | City of Staunton |  |  | 0 |  | 0 | FY2021 | 378798 | 378798 | ADVERTISED | G | Solicit Bids milestone finished 547 days early | G | Project is on budget | 2016-10-03 | 2016-10-03 | 2016-11-16 | 2016-11-16 | G | 2016-11-01 | 2016-11-01 | 2016-11-03 | 2016-11-03 | G | 2016-11-04 | 2018-06-15 | 2018-08-27 | 2019-05-31 | R | [10 empty] | 2020-03-24 | 2019-03-04 | 2020-04-13 | 2019-05-10 | G | [5 empty] | 2020-04-15 | 2019-05-14 | 2021-01-27 | 2019-07-02 | G | [10 empty] | 2021-02-12 | 2019-07-29 | 2021-03-12 | 2019-09-12 | G | 2021-03-15 |  | 2021-04-22 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.27047
1877 | 109146 | ROUTE 28 NB WIDENING - AREA 5 | 0028 | Primary | Preliminary Engineering | VDOT | Loudoun County | LEESBURG | Northern Virginia | Northern Virginia:Loudoun County | Infrastructure Investment Division | Sanjeev Suri | Sanjeev.Suri@VDOT.Virginia.gov | (703) 259-2232 | Sanjeev Suri | Sanjeev.Suri@VDOT.Virginia.gov | (703) 259-2232 |  |  |  | 0 |  | 0 | FY2021 | 3364000 | 22364000 | WAITING FINANCIAL CLOSURE | G | Obtained Permits milestone finished 243 days early | R | Project estimate is less than $5M and is 20% or more over budget | [5 empty] | 2016-05-05 | 2016-05-05 | 2016-05-18 | 2016-05-18 | G | 2016-05-19 | 2016-05-19 | 2017-06-28 | 2017-06-28 | G | [5 empty] | 2018-06-27 | 2018-06-27 | 2018-07-11 | 2018-07-11 | G | 2019-09-30 | 2018-01-30 | 2019-10-11 | 2018-01-31 | G | 2020-03-16 | 2018-02-01 | 2020-09-16 | 2018-10-30 | G | 2019-10-30 | 2018-02-01 | 2020-05-08 | 2018-10-30 | G | 2019-03-27 | 2019-03-27 | 2019-11-26 | 2019-03-28 | G | [5 empty] | 2020-10-13 | 2018-10-09 | 2020-10-13 | 2018-10-30 | G | 2021-02-09 | 2018-11-01 | 2021-02-09 | 2018-11-01 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.14179
1878 | 109474 | #HB2.FY17 -- NEW COMMUTER PRKG LOT RTE 1 AT COMMONWEALTH DR | 0001 | Primary | Safety | VDOT | Spotsylvania County | FREDERICKSBURG | Fredericksburg | Fredericksburg:Spotsylvania County | Infrastructure Investment Division | Curtis B Holloway | Curtis.Holloway@vdot.virginia.gov | (540) 374-3367 | Curtis B Holloway | Curtis.Holloway@vdot.virginia.gov | (540) 374-3367 |  |  |  | 1 | 2017 | 0 | FY2021 | 16947336 | 16947336 | ADVERTISED | R | Relocate Utilities milestone is 426 days past the expected completion date | G | Project is on budget | [5 empty] | 2016-07-06 | 2016-07-06 | 2016-08-02 | 2016-08-02 | G | 2016-08-03 | 2016-08-03 | 2017-07-20 | 2017-07-18 | G | [5 empty] | 2018-05-25 | 2018-03-05 | 2018-06-08 | 2018-03-23 | G | 2019-05-02 | 2018-10-26 | 2019-05-15 | 2018-10-26 | G | 2019-09-25 | 2019-08-15 | 2019-12-23 |  | R | 2019-06-03 | 2018-12-18 | 2019-11-21 | 2020-07-17 | R | 2018-06-12 | 2018-03-26 | 2019-06-12 | 2019-03-20 | G | [5 empty] | 2020-03-10 | 2021-02-09 | 2020-03-10 | 2021-02-09 | R | 2020-06-04 |  | 2020-07-30 |  | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.075695
1879 | 110279 | Strasburg Streetscape - C502 |  | Enhancement | Landscaping/Beautification | Locally | Strasburg | EDINBURG | Staunton | NonMPO:NonMPO | Local Assistance Division | Edwin Z Carter | Edwin.Carter@vdot.virginia.gov | (540) 534-3204 | Kimberly Cameron | Kim.Cameron@vdot.virginia.gov | (540) 332-7886 | Wyatt Pearson | wpearson@strasburgva.com | (540) 465-3025 | 0 |  | 0 | FY2019 | 1093581 | 1669759 | CONSTRUCTION COMPLETED | R | Start Delivery milestone finished 329 days late | R | Project estimate is less than $5M and is 20% or more over budget | 2018-02-01 | 2018-02-01 | 2018-04-26 | 2018-04-26 | G | [5 empty] | 2018-02-01 | 2018-02-01 | 2018-02-14 | 2018-02-14 | G | [35 empty] | 2018-05-14 | 2018-11-27 | 2018-06-11 | 2019-03-21 | R | 2018-06-12 | 2019-03-22 | 2018-07-23 | 2019-06-17 | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.42682
1880 | 110765 | #SMART18 - RTE 460 - DYNAMIC FLASHERS AT RTE 626 | 6460 | Primary | Safety | VDOT | Prince Edward County | DILLWYN | Lynchburg | NonMPO:NonMPO | Infrastructure Investment Division | Craig Manges |  |  | John E Neblett | John.Neblett@VDOT.Virginia.gov | (434) 856-8202 |  |  |  | 1 | 2018 | 0 | FY2018 | 216955 | 216955 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 24 days early | G | Project is on budget | [5 empty] | 2017-07-17 | 2017-07-07 | 2017-07-17 | 2017-07-07 | G | 2017-07-18 | 2017-07-10 | 2017-11-27 | 2017-10-06 | G | [5 empty] | 2017-10-27 | 2017-10-11 | 2017-10-30 | 2017-10-11 | G | [25 empty] | 2017-11-27 | 2017-11-01 | 2017-12-01 | 2017-11-02 | G | 2017-12-04 | 2017-11-03 | 2017-12-08 | 2017-11-14 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | WORK/TASK ORDER | 1 | 0 | 0.093234
1881 | 111311 | City of Galax - McArthur St. Sidewalk |  | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Galax | MARTINSVILLE | Salem | NonMPO:NonMPO | Local Assistance Division | Jessie Nester | Jessie.Nester@vdot.virginia.gov | (540) 613-4115 | Jessie Nester | Jessie.Nester@vdot.virginia.gov | (540) 613-4115 | Edwin Ward | eward@galaxva.com | (276) 236-2422 | 0 |  | 0 | FY2020 | 294028 | 372800 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 145 days early | R | Project estimate is less than $5M and is 20% or more over budget | 2017-10-02 | 2017-10-02 | 2018-02-14 | 2017-12-13 | G | 2018-02-15 | 2018-01-09 | 2018-02-20 | 2018-01-09 | G | 2018-02-21 | 2018-06-29 | 2019-02-22 | 2018-09-04 | G | [35 empty] | 2019-10-10 | 2019-08-15 | 2019-11-07 | 2019-09-18 | G | 2019-11-08 | 2019-10-31 | 2020-04-07 | 2019-11-14 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.32919
1882 | 111421 | #SGR18VB - RT 647 SUPERSTRUCTURE REPLACE. STR. 6037 | 0647 | Secondary | Bridge Rehab w/o Added Capacity | VDOT | Louisa County | LOUISA | Culpeper | NonMPO:NonMPO | Infrastructure Investment Division | Braden C Chapman | Braden.Chapman@VDOT.Virginia.gov | (540) 829-7421 | Brian A Arnold | Brian.Arnold@VDOT.Virginia.gov | (540) 829-7557 |  |  |  | 0 |  | 1 | FY2022 | 1750000 | 1750000 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 400 days early | G | Project is on budget | [5 empty] | 2021-09-15 | 2018-07-16 | 2021-09-28 | 2018-07-16 | G | 2021-09-29 | 2018-01-29 | 2022-08-26 | 2019-02-12 | G | [5 empty] | 2019-03-22 | 2019-03-22 | 2019-03-22 | 2019-03-22 | G | 2020-09-22 | 2019-10-25 | 2020-10-05 | 2019-11-27 | G | [5 empty] | 2020-10-21 | 2019-12-03 | 2021-04-30 | 2020-06-10 | G | 2020-09-15 | 2019-06-11 | 2021-05-21 | 2020-06-25 | G | [5 empty] | 2021-08-10 | 2020-10-06 | 2021-08-10 | 2020-10-06 | G | 2022-01-19 | 2020-12-15 | 2022-01-19 | 2020-12-15 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.15556
1883 | 113030 | #SGR19VB - RT178 over Occohannock Creek (Fed 356) REPLACE | 0178 | Primary | Bridge Replacement w/o Added Capacity | VDOT | Accomack County | ACCOMAC | Hampton Roads | NonMPO:NonMPO | Infrastructure Investment/Asset Management Division | Mark Wagner |  |  | Nancy R Marshall | Nancy.Marshall@VDOT.Virginia.gov | (757) 956-3266 |  |  |  | 0 |  | 1 | FY2023 | 5475507 | 6219960 | ACTIVITY DATES SET | R | Engage Public milestone is 317 days past the expected completion date | Y | Project estimate is between $5M and $10M and is up to $1M over budget | [5 empty] | 2018-08-27 | 2018-07-05 | 2018-09-10 | 2018-07-30 | G | 2018-09-11 | 2018-07-31 | 2019-08-08 | 2019-07-29 | G | [5 empty] | 2020-03-30 |  | 2020-04-10 |  | R | 2021-03-26 |  | 2021-04-08 |  | G | 2021-11-30 |  | 2022-09-15 |  | G | 2021-04-23 |  | 2021-11-10 |  | G | 2021-03-19 |  | 2022-02-18 |  | G | [5 empty] | 2022-12-13 |  | 2022-12-13 |  | G | 2023-03-09 |  | 2023-03-09 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.10764
1884 | 113258 | Woodman Rd/Greenwood Rd. Roundabout (CN Only) | 9999 | Secondary | Reconstruction w/o Added Capacity | Locally | Henrico County | ASHLAND | Richmond | Richmond:Henrico County | Local Assistance Division | Brian J Lokker | Brian.Lokker@VDOT.Virginia.gov | (804) 524-6010 | Brian J Lokker | Brian.Lokker@VDOT.Virginia.gov | (804) 524-6010 | Paul Smith | smi91@henrico.us | (804) 501-5092 | 0 |  | 0 | FY2020 | 4000000 | 4000000 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 72 days early | G | Project is on budget | 2018-07-02 | 2018-07-02 | 2018-10-31 | 2018-09-27 | G | [5 empty] | 2018-07-02 | 2018-07-02 | 2018-09-25 | 2019-04-04 | R | [25 empty] | 2019-04-05 | 2019-08-05 | 2019-08-09 | 2019-08-06 | G | [5 empty] | 2019-08-12 | 2019-10-11 | 2019-08-20 | 2019-10-11 | R | 2019-08-21 | 2019-12-10 | 2020-02-20 | 2019-12-10 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.34573
1885 | 113317 | N Parham Road - Sidewalk | 7518 | Secondary | Facilities for Pedestrians and Bicycles | Locally | Henrico County | ASHLAND | Richmond | Richmond:Henrico County | Local Assistance Division | Cynthia Crouch | Cynthia.Crouch@vdot.virginia.gov | (804) 609-5313 | Cynthia Crouch | Cynthia.Crouch@vdot.virginia.gov | (804) 609-5313 | Steve Bandura | ban03@henrico.us | (804) 501-5985 | 0 |  | 0 | FY2022 | 91000 | 91000 | ACTIVITY DATES SET | G | Obtained Permits milestone finished 324 days early | G | Project is on budget | 2019-07-01 | 2019-07-01 | 2019-09-24 | 2019-10-16 | R | 2019-11-01 | 2019-10-17 | 2019-11-05 | 2019-11-01 | G | 2019-11-06 | 2019-11-04 | 2020-01-07 | 2019-12-17 | G | [10 empty] | 2020-12-14 | 2019-12-30 | 2021-01-04 | 2019-12-30 | G | 2021-06-03 | 2019-12-30 | 2021-10-01 | 2019-12-30 | G | 2021-01-06 | 2019-12-30 | 2021-06-02 | 2019-12-30 | G | 2021-05-28 | 2021-01-11 | 2021-12-01 | 2021-01-11 | G | [5 empty] | 2022-01-03 |  | 2022-01-03 |  | G | 2022-03-25 |  | 2022-03-25 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.3453
1886 | 113814 | F Roadway Conversions - Citywide Phase II | 9999 | Miscellaneous | Safety | Locally | Richmond | ASHLAND | Richmond | Richmond:Richmond | Local Assistance Division | Melinda G Baicy | Melinda.Baicy@vdot.virginia.gov | (804) 609-5390 | Melinda G Baicy | Melinda.Baicy@vdot.virginia.gov | (804) 609-5390 | Jakob Helmboldt | jakob.helmboldt@richmondgov.com | 80464671 | 0 |  | 0 | FY2025 | 1500000 | 1500000 | NO DATES SET YET | G | Agreement with Locality milestone is 647 days ahead of the expected completion date | G | Project is on budget | 2022-09-01 |  | 2022-11-30 |  | G | 2022-12-01 |  | 2022-12-05 |  | G | 2022-12-06 |  | 2023-06-13 |  | G | [25 empty] | 2023-07-20 |  | 2024-03-27 |  | G | [5 empty] | 2024-07-01 |  | 2024-07-29 |  | G | 2024-10-16 |  | 2024-10-16 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.12957
1887 | 113839 | #SGR19VB - BRIDGE REHAB RT 3 CSX RR BEAM END ID 18067 | 0003 | Primary | Bridge Rehab w/o Added Capacity | VDOT | Stafford County | FREDERICKSBURG | Fredericksburg | Fredericksburg:Stafford County | Infrastructure Investment/Asset Management Division | Annette F Adams | Annette.Adams@VDOT.Virginia.gov | (540) 372-3583 | Benjamin Ernst | Benjamin.Ernst@vdot.virginia.gov | (571) 585-0902 |  |  |  | 0 |  | 1 | FY2021 | 1000000 | 2185101 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 91 days early | R | Project estimate is less than $5M and is 20% or more over budget | [10 empty] | 2020-08-03 | 2019-05-06 | 2020-08-14 | 2019-05-08 | G | [35 empty] | 2020-09-08 | 2020-05-05 | 2020-09-08 | 2020-05-05 | G | 2020-12-02 | 2020-09-02 | 2020-12-02 | 2020-09-02 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.090506
1888 | 114379 | Graybill Road Drainage Improvements | 0000 | Urban | Mitigation of Water Pollution Due to Highway Runof | Locally | Roanoke | SALEM | Salem | Roanoke:Roanoke City | Local Assistance Division | Cheryl B Becker | Cheryl.Becker@vdot.virginia.gov | (540) 492-2531 | Cheryl B Becker | Cheryl.Becker@vdot.virginia.gov | (540) 492-2531 | Joseph Arthur | Joseph.Arthur@roanokeva.gov | (540) 853-5901 | 0 |  | 0 | FY2021 | 312595 | 312595 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 544 days early | G | Project is on budget | 2018-10-01 | 2018-10-01 | 2018-12-28 | 2018-11-27 | G | 2018-12-31 | 2018-11-28 | 2019-01-03 | 2018-11-28 | G | 2019-01-04 | 2018-11-29 | 2019-07-11 | 2018-11-30 | G | [25 empty] | 2019-01-07 | 2019-01-09 | 2019-09-09 | 2019-01-09 | G | [5 empty] | 2020-05-21 | 2018-12-06 | 2020-06-18 | 2018-12-28 | G | 2020-09-08 | 2018-12-29 | 2020-09-08 | 2019-03-14 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.20319
1889 | 114813 | PAVEMENT OVERLAY - RTE. 617, RTE 627 AND RTE 701 | 0627 | Secondary | Resurfacing | VDOT | Orange County | LOUISA | Culpeper | NonMPO:NonMPO | Infrastructure Investment Division | Gregory J Cooley | Gregory.Cooley@vdot.virginia.gov | (434) 906-7979 | Bethel Kefyalew | Bethel.Kefyalew@vdot.virginia.gov | (540) 603-6015 |  |  |  | 0 |  | 0 | FY2019 | 485000 | 485000 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished on-time | G | Project is on budget | [5 empty] | 2019-03-11 | 2019-02-25 | 2019-03-22 | 2019-03-21 | G | 2019-03-25 | 2019-02-25 | 2019-11-12 | 2019-03-21 | G | [5 empty] | 2019-04-08 | 2019-04-08 | 2019-04-08 | 2019-04-08 | G | [5 empty] | 2019-02-25 | 2019-02-25 | 2019-02-25 | 2019-02-25 | G | [15 empty] | 2019-05-21 | 2019-04-12 | 2019-05-21 | 2019-04-23 | G | 2019-06-26 | 2019-06-26 | 2019-06-26 | 2019-06-26 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.066615
1890 | 111035 | Jefferson Avenue@ Pavilion Place New Traffic Signal | 0143 | Urban | Traffic Management/Engineering | Locally | Newport News | WILLIAMSBURG | Hampton Roads | Hampton Roads:Newport News | Infrastructure Investment Division | Dawn Odom | Dawn.Odom@vdot.virginia.gov | (000) 000-0000 | Chessica Villaflores | Chessica.Villaflores@vdot.virginia.gov | (757) 956-3094 | Mohamed Elrahhal | melrahhal@nnva.gov | (757) 926-8667 | 0 |  | 0 | FY2023 | 621852 | 621852 | NO DATES SET YET-PE OPEN | R | Determine Requirements milestone is 136 days past the expected completion date | G | Project is on budget | 2019-07-01 | 2019-07-01 | 2019-09-24 | 2019-12-02 | R | 2019-09-25 | 2019-12-02 | 2019-10-08 | 2019-12-06 | R | 2019-10-09 |  | 2020-10-08 |  | R | [10 empty] | 2021-08-05 |  | 2021-08-25 |  | G | [5 empty] | 2021-08-27 |  | 2022-06-17 |  | G | [10 empty] | 2022-07-06 |  | 2022-08-30 |  | G | 2022-08-31 |  | 2023-02-28 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.34885
1891 | 111342 | #SGR18VB - RT 40 over Otterdam Swamp (Fed 18185) REPLACE | 0040 | Primary | Bridge Replacement w/o Added Capacity | VDOT | Surry County | WILLIAMSBURG | Hampton Roads |  | Infrastructure Investment Division | Mohamed A Ali | Mohamed.Ali@VDOT.Virginia.gov | (757) 956-3206 | Nancy R Marshall | Nancy.Marshall@VDOT.Virginia.gov | (757) 956-3266 |  |  |  | 0 |  | 1 | FY2024 | 5042283 | 5042283 | ACTIVITY DATES SET | R | Determine Requirements milestone finished 100 days late | G | Project is on budget | [10 empty] | 2020-10-01 | 2020-10-01 | 2020-10-07 | 2021-01-15 | R | [5 empty] | 2021-03-17 |  | 2021-07-02 |  | G | [25 empty] | 2023-06-13 |  | 2023-06-13 |  | G | 2023-09-15 |  | 2023-11-13 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.10262
1892 | 111729 | ROUTE 250 / 240 / 680 ROUNDABOUT | 0250 | Primary | Safety | VDOT | Albemarle County | CHARLOTTESVILLE | Culpeper | Charlottesville:Albemarle County | Infrastructure Investment Division | Gregory J Cooley | Gregory.Cooley@vdot.virginia.gov | (434) 906-7979 | Harold L Jones | Harold.Jones@VDOT.virginia.gov | (434) 422-9378 |  |  |  | 0 |  | 0 | FY2022 | 3550000 | 3550000 | NO DATES SET YET-PE OPEN | R | Determine Requirements milestone is 892 days past the expected completion date | G | Project is on budget | [5 empty] | 2017-10-02 | 2017-08-16 | 2017-10-13 | 2017-08-16 | G | 2017-10-17 | 2017-10-17 | 2018-09-13 |  | R | [5 empty] | 2019-07-22 |  | 2019-08-02 |  | R | 2020-11-06 |  | 2020-11-20 |  | R | 2021-04-21 |  | 2021-10-25 |  | G | 2020-12-10 |  | 2021-06-17 |  | G | 2020-04-28 | 2020-09-17 | 2020-10-30 | 2020-09-17 | G | [5 empty] | 2021-11-09 |  | 2021-11-09 |  | G | 2022-02-18 |  | 2022-04-15 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 1 | 0.3626
1893 | 113126 | Pitchkettle Road Realignment | 0604 | Urban | Reconstruction w/o Added Capacity | Locally | Suffolk | NORFOLK | Hampton Roads | Hampton Roads:Suffolk | Local Assistance Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Johndel A Alcaide | John.Alcaide@vdot.virginia.gov | (757) 956-3098 | Robert Lewis | rlewis@suffolkva.us | (757) 514-7621 | 0 |  | 0 | FY2024 | 7762500 | 7762500 | ACTIVITY DATES SET | R | Determine Requirements milestone finished 637 days late | G | Project is on budget | 2018-07-31 | 2018-07-31 | 2018-10-24 | 2018-09-28 | G | 2018-10-25 | 2018-10-15 | 2018-10-29 | 2018-10-16 | G | 2018-10-30 | 2018-10-17 | 2019-05-09 | 2021-02-04 | R | [10 empty] | 2021-10-15 |  | 2021-10-29 |  | G | [5 empty] | 2021-11-02 |  | 2023-03-16 |  | G | [10 empty] | 2023-04-03 |  | 2023-04-28 |  | G | 2023-05-01 |  | 2023-07-28 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.11417
1894 | 113261 | Creighton Road Sidewalk | 9999 | Urban | Facilities for Pedestrians and Bicycles | Locally | Henrico County | ASHLAND | Richmond | Richmond:Henrico County | Local Assistance Division | Douglas L Orcutt | Doug.Orcutt@vdot.virginia.gov | (804) 609-5428 | Douglas L Orcutt | Doug.Orcutt@vdot.virginia.gov | (804) 609-5428 | Todd Eure | eur@co.henrico.va.us | (804) 501-4617 | 0 |  | 0 | FY2022 | 362000 | 362000 | ACTIVITY DATES SET | G | Complete Purchasing Right-of-Way milestone finished 200 days early | G | Project is on budget | 2019-07-01 | 2019-07-01 | 2019-10-31 | 2019-10-14 | G | 2019-11-01 | 2019-11-01 | 2019-11-15 | 2019-11-05 | G | 2019-11-18 | 2019-11-05 | 2020-01-02 | 2019-12-17 | G | 2020-10-30 | 2020-09-29 | 2020-10-30 | 2020-09-29 | G | [5 empty] | 2020-12-15 | 2020-11-12 | 2020-12-15 | 2020-11-16 | G | 2021-08-03 |  | 2021-12-01 |  | G | 2020-12-17 | 2020-11-17 | 2021-08-02 | 2021-01-14 | G | 2021-02-15 |  | 2021-12-01 |  | G | [5 empty] | 2022-02-01 |  | 2022-02-01 |  | G | 2022-02-02 |  | 2022-05-02 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.23526
1895 | 113749 | Mercury Blvd Pedestrian Improvements | 0258 | Primary | Facilities for Pedestrians and Bicycles | Locally | Hampton | WILLIAMSBURG | Hampton Roads | Hampton Roads:Hampton | Infrastructure Investment Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Derrick Williams | Derrick.Williams@vdot.virginia.gov | (757) 956-3097 | Lynne M. Keenan | lynne.keenan@hampton.gov | (757) 727-6859 | 0 |  | 0 | FY2024 | 467000 | 467000 | NO DATES SET YET | G | Agreement with Locality milestone is 291 days ahead of the expected completion date | Y | Estimate not current | 2021-09-13 |  | 2021-12-09 |  | G | 2021-12-10 |  | 2021-12-14 |  | G | 2021-12-15 |  | 2022-06-22 |  | G | [25 empty] | 2022-07-29 |  | 2023-04-06 |  | G | [5 empty] | 2023-05-04 |  | 2023-06-01 |  | G | 2023-08-21 |  | 2023-08-21 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.19561
1896 | 113827 | Citywide Flashing Yellow Arrow | 9999 | Urban | Safety | Locally | Williamsburg | WILLIAMSBURG | Hampton Roads | Hampton Roads:Williamsburg | Infrastructure Investment Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Chessica Villaflores | Chessica.Villaflores@vdot.virginia.gov | (757) 956-3094 | Aaron Small | ASmall@williamsburgva.gov | (757) 220-6140 | 0 |  | 0 | FY2024 | 243000 | 243000 | NO DATES SET YET | G | Agreement with Locality milestone is 282 days ahead of the expected completion date | Y | Estimate not current | 2021-09-01 |  | 2021-11-30 |  | G | 2021-12-01 |  | 2021-12-03 |  | G | 2021-12-06 |  | 2022-06-13 |  | G | [25 empty] | 2022-06-14 |  | 2023-02-21 |  | G | [5 empty] | 2023-04-25 |  | 2023-05-22 |  | G | 2023-05-23 |  | 2023-08-09 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.23593
1897 | 113857 | RTE 648-RURAL RUSTIC RD (SURFACE TREAT NON-HARD SURFACE RD) | 0648 | Secondary | Reconstruction w/o Added Capacity | VDOT | Fauquier County | WARRENTON | Culpeper | NonMPO:NonMPO | Infrastructure Investment Division | Ken Connors |  |  | Benjamin Davison | Ben.Davison@vdot.virginia.gov | (540) 347-6446 |  |  |  | 0 |  | 0 | FY2025 | 420000 | 420000 | NO DATES SET YET | G | Start Development milestone is 600 days ahead of the expected completion date | Y | Estimate not current | [5 empty] | 2022-10-03 |  | 2022-10-14 |  | G | 2022-10-18 |  | 2023-06-13 |  | G | [5 empty] | 2024-02-22 |  | 2024-04-03 |  | G | [5 empty] | 2024-07-18 |  | 2024-11-08 |  | G | [5 empty] | 2024-07-02 |  | 2024-10-02 |  | G | [5 empty] | 2024-11-12 |  | 2024-11-12 |  | G | 2025-02-07 |  | 2025-02-07 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | SAAP CONTRACT | 0 | 0 | 0.10373
1898 | 114765 | PEDESTRIAN SIGNAL UPGRADES - CITY OF ROANOKE | 9999 | Urban | Safety | Locally | Roanoke | SALEM | Salem | Roanoke:Roanoke City | Infrastructure Investment Division | Bernard S Grinnell | Sean.Grinnell@VDOT.Virginia.gov | (540) 375-0148 | Cheryl B Becker | Cheryl.Becker@vdot.virginia.gov | (540) 492-2531 | Hong Liu | hong.liu@roanokeva.gov | (540) 853-2686 | 0 |  | 0 | FY2021 | 230000 | 230000 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 258 days early | G | Project is on budget | 2019-08-01 | 2019-07-02 | 2019-10-25 | 2019-09-19 | G | [5 empty] | 2019-08-01 | 2019-08-01 | 2019-08-14 | 2019-08-14 | G | [25 empty] | 2020-03-10 | 2019-09-06 | 2020-06-02 | 2019-09-06 | G | [5 empty] | 2020-06-03 | 2020-01-15 | 2020-06-30 | 2020-02-12 | G | 2020-07-23 | 2020-02-13 | 2020-12-16 | 2020-04-02 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.28951
1899 | 115122 | #SMART20 INTERSECTION IMPROVEMENT AT STEFANGIA/MOUNTAIN VIEW | 0627 | Secondary | Reconstruction w/o Added Capacity | Locally | Stafford County | FREDERICKSBURG | Fredericksburg | Fredericksburg:Stafford County | Infrastructure Investment Division | Catherine C Coffey | Catherine.Coffey@vdot.virginia.gov | (540) 899-4280 | Khalil Minhas | Khalil.Minhas@vdot.virginia.gov | (540) 374-3369 | Alex Owsiak | AOWSIAK@STAFFORDCOUNTYVA.GOV | (540) 658-4593 | 1 | 2020 | 0 | FY2027 | 3700000 | 3700000 | NO DATES SET YET | G | Agreement with Locality milestone is 1041 days ahead of the expected completion date | G | Project is on budget | 2023-10-02 |  | 2023-12-29 |  | G | 2024-01-02 |  | 2024-01-04 |  | G | 2024-01-05 |  | 2024-07-11 |  | G | [10 empty] | 2025-07-15 |  | 2025-08-04 |  | G | [5 empty] | 2025-08-06 |  | 2026-05-19 |  | G | 2024-08-16 |  | 2025-04-24 |  | G | [5 empty] | 2026-06-05 |  | 2026-07-02 |  | G | 2026-09-22 |  | 2026-09-22 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.10919
1900 | 115477 | #SMART20 - RTE. 250 & RTE. 20 INTERSECTION IMPROVEMENTS | 0250 | Primary | Safety | VDOT | Albemarle County | CHARLOTTESVILLE | Culpeper | Charlottesville:Albemarle County | Infrastructure Investment Division | Gregory J Cooley | Gregory.Cooley@vdot.virginia.gov | (434) 906-7979 | Michael Jacobs | Mike.Jacobs@VDOT.Virginia.gov | (540) 829-7502 |  |  |  | 1 | 2020 | 0 | FY2025 | 8800000 | 8800000 | NO DATES SET YET-PE OPEN | R | Start Development milestone finished 7 days late | G | Project is on budget | [5 empty] | 2020-08-03 | 2020-08-03 | 2020-08-14 | 2020-08-21 | R | 2020-08-17 |  | 2021-09-10 |  | G | [5 empty] | 2022-07-19 |  | 2022-08-01 |  | G | 2023-07-31 |  | 2023-08-11 |  | G | 2024-05-07 |  | 2024-11-08 |  | G | 2023-08-29 |  | 2024-05-06 |  | G | 2023-03-10 |  | 2023-09-12 |  | G | [5 empty] | 2024-11-12 |  | 2024-11-12 |  | G | 2025-03-10 |  | 2025-03-10 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 1 | 0.3754
1901 | 116203 | #I81CIP MM136 TO MM142 ADD LANE IN EACH DIRECTION (ID #39) | 0081 | Interstate | Reconstruction w/ Added Capacity | VDOT | Roanoke County | SALEM | Salem | Roanoke:Roanoke County | Infrastructure Investment Division | Thomas W Digiulian | Thomas.DiGiulian@VDOT.Virginia.gov | (540) 387-5356 | Craig S Moore | Craig.Moore@vdot.virginia.gov | (540) 375-3556 |  |  |  | 0 |  | 0 | FY2022 | 292480260 | 292480260 | ADVERTISED | R | Start Purchasing Right-of-Way milestone baseline missing | G | Project is on budget | [5 empty] | 2020-01-02 | 2020-01-03 | 2020-01-15 | 2020-01-03 | G | 2020-01-02 | 2020-01-06 | 2021-08-24 |  | G | [11 empty] | 2020-10-23 |  | 2020-10-26 | R | [20 empty] | 2020-12-03 | 2020-10-27 | 2021-08-26 | 2020-10-28 | G | 2022-03-11 |  | 2022-04-07 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | DESIGN BUILD/PPTA | 0 | 0 | 0.1349
1902 | 116886 | DABNEY STREET - MILLING, PAVEMENT & RECONSTRUCTION | 9999 | Urban | Resurfacing | Locally | Orange | LOUISA | Culpeper | NonMPO:NonMPO | Local Assistance Division | Gregory J Cooley | Gregory.Cooley@vdot.virginia.gov | (434) 906-7979 | John P Price | John.Price@VDOT.Virginia.gov | (540) 347-6371 | John Cooley | townplanner@townoforangeva.org | (540) 672-6917 | 0 |  | 0 | FY2023 | 31672 | 31672 | NO DATES SET YET | G | Agreement with Locality milestone is 326 days ahead of the expected completion date | G | Project is on budget | 2021-09-01 |  | 2022-01-13 |  | G | [5 empty] | 2022-01-18 |  | 2022-01-31 |  | G | [25 empty] | 2021-09-30 |  | 2022-03-08 |  | G | [5 empty] | 2022-05-04 |  | 2022-06-01 |  | G | 2022-08-19 |  | 2022-08-19 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.047861
1903 | 116935 | #SGR21LP Park Avenue NE-Primary Extension Paving | 0000 | Urban | Resurfacing | VDOT | Norton | WISE | Bristol | NonMPO:NonMPO | Infrastructure Investment/Asset Management Division | James B Parsons | James.Parsons@VDOT.Virginia.gov | (276) 696-3288 | David G Morrison | David.Morrison@VDOT.Virginia.gov | (276) 696-3328 |  |  |  | 0 |  | 1 | FY2022 | 418124 | 418124 | ADVERTISED | G | Solicit Bids milestone finished 217 days early | G | Project is on budget | [5 empty] | 2020-12-01 | 2020-12-01 | 2020-12-14 | 2020-12-14 | G | 2020-12-15 | 2020-12-15 | 2021-03-01 | 2021-02-09 | G | [35 empty] | 2021-09-14 | 2021-02-09 | 2021-09-14 | 2021-02-09 | G | 2021-12-08 |  | 2021-12-08 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.069328
1904 | 117093 | #REVSH21 LAKESIDE DRIVE - RECONSTRUCTION | 0221 | Urban | Reconstruction w/o Added Capacity | Locally | Lynchburg | APPOMATTOX | Lynchburg | Lynchburg:Lynchburg | Local Assistance Division | Gregg Allen | Gregg.Allen@vdot.virginia.gov | (434) 426-5575 | Gregg Allen | Gregg.Allen@vdot.virginia.gov | (434) 426-5575 | LEE NEWLAND | lee.newland@lynchburgva.gov | (434) 455-3947 | 0 |  | 0 | FY2025 | 2506100 | 2506100 | NO DATES SET YET | G | Agreement with Locality milestone is 106 days ahead of the expected completion date | G | Project is on budget | 2021-01-29 |  | 2021-06-07 |  | G | 2021-06-08 |  | 2021-06-28 |  | G | 2022-01-07 |  | 2022-05-03 |  | G | [10 empty] | 2023-08-22 |  | 2023-09-26 |  | G | [5 empty] | 2023-09-27 |  | 2024-03-04 |  | G | 2024-01-30 |  | 2024-06-26 |  | G | [5 empty] | 2024-06-05 |  | 2024-07-02 |  | G | 2024-09-20 |  | 2024-09-20 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.11161
1905 | 117136 | Complete Streets-16th Street | 0000 | Urban | Reconstruction w/o Added Capacity | Locally | Newport News | WILLIAMSBURG | Hampton Roads | Hampton Roads:Newport News | Local Assistance Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Chessica Villaflores | Chessica.Villaflores@vdot.virginia.gov | (757) 956-3094 | Bridjette Parker | parkerbj1@nnav.gov | (757) 926-8314 | 0 |  | 0 | FY2024 | 6200000 | 6200000 | NO DATES SET YET | Y | Agreement with Locality milestone is 11 days ahead of the expected completion date and there is a risk of missing this milestone date | G | Project is on budget | 2020-10-20 |  | 2021-03-04 |  | Y | 2021-03-05 |  | 2021-03-25 |  | G | 2021-09-29 |  | 2022-01-28 |  | G | [10 empty] | 2023-05-18 |  | 2023-06-22 |  | G | [5 empty] | 2023-06-23 |  | 2023-11-22 |  | G | 2023-10-19 |  | 2024-03-25 |  | G | [5 empty] | 2024-03-04 |  | 2024-03-29 |  | G | 2024-06-18 |  | 2024-06-18 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.27555
1906 | 118162 | Campbell Avenue 2 Drainage Improvement | 0000 | Urban | Mitigation of Water Pollution Due to Highway Runof | Locally | Roanoke | SALEM | Salem | Roanoke:Roanoke City | Local Assistance Division | Cheryl B Becker | Cheryl.Becker@vdot.virginia.gov | (540) 492-2531 | Cheryl B Becker | Cheryl.Becker@vdot.virginia.gov | (540) 492-2531 | Joseph Arthur | Joseph.Arthur@roanokeva.gov | (540) 853-5901 | 0 |  | 0 | FY2028 | 1000000 | 1000000 | NO DATES SET YET | G | Agreement with Locality milestone is 1422 days ahead of the expected completion date | G | Project is on budget | 2024-08-30 |  | 2025-01-13 |  | G | 2025-01-14 |  | 2025-02-05 |  | G | 2025-08-12 |  | 2025-12-08 |  | G | [10 empty] | 2027-04-01 |  | 2027-05-05 |  | G | [5 empty] | 2027-05-06 |  | 2027-10-04 |  | G | 2027-08-31 |  | 2028-02-04 |  | G | [5 empty] | 2028-01-12 |  | 2028-02-10 |  | G | 2028-05-01 |  | 2028-05-01 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.20647
1907 | 81125 | VIRGINIA CREEPER TRAIL - CONSTRUCT RESTROOM & PARK EXPANSION |  | Primary | Rehabilitation of Historic Bldgs/Facilities | Locally | Washington County | ABINGDON | Bristol | NonMPO:NonMPO | Local Assistance Division | Chase R Buchanan | Chase.Buchanan@VDOT.Virginia.gov | (276) 696-3251 | Tabitha H Crowder | Tabitha.Crowder@vdot.virginia.gov | (276) 696-3482 | Town Of Abingdon |  |  | 0 |  | 0 | FY2024 | 850000 | 850000 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 4955 days early | Y | Estimate not current | [5 empty] | 2006-10-02 | 2006-09-18 | 2006-10-31 | 2006-09-20 | G | 2008-11-25 | 2008-11-25 | 2009-07-17 | 2009-07-17 | G | [35 empty] | 2024-01-05 | 2010-06-04 | 2024-02-05 | 2010-08-06 | G | 2024-02-06 | 2010-08-07 | 2024-03-18 | 2010-08-24 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.11019
1908 | 100765 | Bridge Repl Rt 620 over Smith Creek VA Str 6351 Fed ID 17119 | 0620 | Secondary | Bridge Replacement w/o Added Capacity | VDOT | Shenandoah County | EDINBURG | Staunton | NonMPO:NonMPO | Infrastructure Investment Division | Junyi Y Meng | Junyi.Meng@VDOT.Virginia.gov | (804) 786-3817 | James T Johnston | james.johnston@VDOT.virginia.gov | (540) 332-7795 |  |  |  | 0 |  | 0 | FY2020 | 1034252 | 1889762 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished on-time | R | Project estimate is less than $5M and is 20% or more over budget | [5 empty] | 2013-07-02 | 2013-07-01 | 2013-07-02 | 2013-07-02 | G | 2013-08-01 | 2013-07-23 | 2017-11-14 | 2017-11-13 | G | [5 empty] | 2017-08-23 | 2017-08-23 | 2017-09-06 | 2017-09-06 | G | 2018-04-02 | 2018-04-02 | 2018-04-27 | 2018-04-27 | G | 2018-10-30 | 2018-08-22 | 2019-02-28 | 2019-01-10 | G | 2018-05-01 | 2018-05-01 | 2018-10-30 | 2018-09-19 | G | 2018-05-02 | 2018-05-18 | 2019-05-02 | 2019-05-06 | R | [5 empty] | 2019-10-16 | 2019-10-10 | 2019-11-12 | 2019-11-05 | G | 2019-11-21 | 2019-11-21 | 2020-03-12 | 2020-03-12 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.05248
1909 | 104148 | SADLER RD - RECONSTRUCTION | 9999 | Secondary | Reconstruction w/o Added Capacity | Locally | Henrico County | ASHLAND | Richmond | Richmond:Henrico County | Infrastructure Investment Division | Cynthia Crouch | Cynthia.Crouch@vdot.virginia.gov | (804) 609-5313 | Cynthia Crouch | Cynthia.Crouch@vdot.virginia.gov | (804) 609-5313 | Sharon Smidler | smi20@henrico.us | (804) 501-4621 | 0 |  | 0 | FY2022 | 9900000 | 27106587 | ACTIVITY DATES SET | R | Complete Purchasing Right-of-Way milestone is 23 days past the expected completion date | R | Project estimate is between $5M and $10M and is a $1M or more over budget | 2014-10-01 | 2014-10-01 | 2015-06-01 | 2015-05-27 | G | [5 empty] | 2017-11-30 | 2003-11-01 | 2017-11-30 | 2003-12-15 | G | [10 empty] | 2019-11-30 | 2019-12-03 | 2019-11-30 | 2019-12-03 | R | 2020-02-28 |  | 2021-01-29 |  | R | 2019-12-30 | 2020-05-27 | 2021-01-29 |  | R | [10 empty] | 2021-05-31 |  | 2021-05-31 |  | G | 2021-08-02 |  | 2021-10-29 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.30909
1910 | 116015 | District-wide Centerline Rumble Strips Installations | 9999 | Miscellaneous | Safety | VDOT | Culpeper District-wide |  | Culpeper | NonMPO:NonMPO | Infrastructure Investment/Asset Management Division | Gregory J Cooley | Gregory.Cooley@vdot.virginia.gov | (434) 906-7979 | Caroline Awua-Mensah | Caroline.Awua-Mensah@vdot.virginia.gov | (540) 829-7618 |  |  |  | 0 |  | 0 | FY2021 | 211969 | 211969 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 284 days early | G | Project is on budget | [5 empty] | 2020-04-02 | 2020-04-02 | 2020-04-15 | 2020-04-15 | G | 2020-04-16 | 2020-04-16 | 2020-06-25 | 2020-04-20 | G | [35 empty] | 2020-11-10 | 2020-04-22 | 2020-11-10 | 2020-04-22 | G | 2021-02-08 | 2020-04-30 | 2021-02-08 | 2020-04-30 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | WORK/TASK ORDER | 1 | 0 | 0.10383
1911 | 116695 | 19th Street & Chapman Avenue Drainage Improvements | 0000 | Urban | Mitigation of Water Pollution Due to Highway Runof | Locally | Roanoke | SALEM | Salem | Roanoke:Roanoke City | Local Assistance Division | Cheryl B Becker | Cheryl.Becker@vdot.virginia.gov | (540) 492-2531 | Cheryl B Becker | Cheryl.Becker@vdot.virginia.gov | (540) 492-2531 | Joseph Arthur | Joseph.Arthur@roanokeva.gov | (540) 853-5901 | 0 |  | 0 | FY2022 | 475000 | 475000 | NO DATES SET YET-PE OPEN | R | Determine Requirements milestone is 11 days past the expected completion date | G | Project is on budget | 2020-05-01 | 2020-05-01 | 2020-07-27 | 2020-06-18 | G | 2020-07-28 | 2020-06-19 | 2020-07-30 | 2020-06-19 | G | 2020-07-31 |  | 2021-02-10 |  | R | [25 empty] | 2021-03-19 |  | 2021-11-18 |  | G | [5 empty] | 2021-12-20 |  | 2022-01-20 |  | G | 2022-04-11 |  | 2022-04-11 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.20396
1912 | 116889 | HARPER DRIVE - MILLING, PAVEMENT & RECONSTRUCTION | 9999 | Urban | Resurfacing | Locally | Orange | LOUISA | Culpeper | NonMPO:NonMPO | Local Assistance Division | Gregory J Cooley | Gregory.Cooley@vdot.virginia.gov | (434) 906-7979 | John P Price | John.Price@VDOT.Virginia.gov | (540) 347-6371 | John Cooley | townplanner@townoforangeva.org | (540) 672-6917 | 0 |  | 0 | FY2022 | 36654 | 36654 | NO DATES SET YET | R | Agreement with Locality milestone is 39 days past the expected completion date | G | Project is on budget | 2020-09-01 |  | 2021-01-13 |  | R | [5 empty] | 2021-01-14 |  | 2021-01-29 |  | R | [25 empty] | 2020-09-30 |  | 2021-03-08 |  | Y | [5 empty] | 2021-05-04 |  | 2021-06-01 |  | G | 2021-08-19 |  | 2021-08-19 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.047867
1913 | 116980 | #SGR21LB (FED ID 22403) BRIDGE REPL - MCGHEE ST OVER NSRR | 0000 | Urban | Bridge Replacement w/o Added Capacity | Locally | Bedford | BEDFORD | Salem | NonMPO:NonMPO | Infrastructure Investment Division | Anthony T Marshall | Todd.Marshall@VDOT.Virginia.gov | (540) 387-5460 | Jessie Nester | Jessie.Nester@vdot.virginia.gov | (540) 613-4115 | Town of Bedford |  |  | 0 |  | 1 | FY2026 | 5988525 | 5988525 | NO DATES SET YET | G | Agreement with Locality milestone is 625 days ahead of the expected completion date | G | Project is on budget | 2022-07-01 |  | 2022-11-08 |  | G | 2022-11-09 |  | 2022-12-02 |  | G | 2023-06-13 |  | 2023-10-04 |  | G | [10 empty] | 2025-01-30 |  | 2025-03-06 |  | G | [5 empty] | 2025-03-07 |  | 2025-08-04 |  | G | 2025-07-01 |  | 2025-12-02 |  | G | [5 empty] | 2025-11-06 |  | 2025-12-08 |  | G | 2026-03-03 |  | 2026-03-03 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.14612
1914 | 117103 | Route 637 -- Advisory signs | 0637 | Secondary | Safety | Locally | Chesterfield County | CHESTERFIELD | Richmond | Richmond:Chesterfield County | Infrastructure Investment Division | Michael S Gray | Mike.Gray@vdot.virginia.gov | (804) 609-5347 | Michael S Gray | Mike.Gray@vdot.virginia.gov | (804) 609-5347 | Nathan Mathis | mathisn@chesterfield.gov | (804) 717-6662 | 0 |  | 0 | FY2022 | 50000 | 50000 | NO DATES SET YET | G | Agreement with Locality milestone finished 51 days early | G | Project is on budget | 2020-11-02 | 2020-11-02 | 2021-03-17 | 2021-01-25 | G | [5 empty] | 2021-03-18 | 2021-01-26 | 2021-03-31 |  | G | [25 empty] | 2020-12-03 |  | 2021-05-05 |  | G | [5 empty] | 2021-07-02 |  | 2021-07-30 |  | G | 2021-10-20 |  | 2021-10-20 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.18413
1915 | 118122 | UNSIGNALIZED INTERSECTIONS - BRISTOL DISTRICTWIDE | 9999 | Primary | Safety | VDOT | Bristol District-wide |  | Bristol | NonMPO:NonMPO | Infrastructure Investment/Asset Management Division | Brian Holt | Brian.Holt@vdot.virginia.gov | (276) 696-3414 | Jeremy J Mullins | Jeremy.Mullins@vdot.virginia.gov | (276) 696-3259 |  |  |  | 0 |  | 0 | FY2022 | 1255555 | 1255555 | NO DATES SET YET-PE OPEN | R | Determine Requirements milestone is 53 days past the expected completion date | G | Project is on budget | [5 empty] | 2020-10-01 | 2020-10-01 | 2020-10-14 | 2020-10-14 | G | 2020-10-15 | 2020-10-15 | 2020-12-30 |  | R | [35 empty] | 2021-08-10 |  | 2021-08-10 |  | G | 2021-11-01 |  | 2021-11-01 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.080261
1916 | 56900 | I-81 SOUTHBOUND BRIDGE REPLACEMENT OVER THE NEW RIVER | 0081 | Interstate | Bridge Replacement w/o Added Capacity | VDOT | Pulaski County | CHRISTIANSBURG | Salem | NonMPO:NonMPO | Infrastructure Investment Division | Thomas W Digiulian | Thomas.DiGiulian@VDOT.Virginia.gov | (540) 387-5356 | Timothy M Dowdy | Tim.Dowdy@VDOT.Virginia.gov | (540) 387-5332 | John Maddox |  |  | 0 |  | 0 | FY2033 | 47601057 | 56907891 | ACTIVITY DATES SET | G | Determine Requirements milestone finished 10 days early | R | Project estimate is greater than $10M and is over budget by (a) 10% or more or (b) $5M or more | [5 empty] | 2001-04-02 | 2001-04-17 | 2001-04-30 | 2001-04-24 | G | 2009-12-21 | 2009-12-21 | 2014-07-31 | 2014-07-21 | G | [5 empty] | 2013-05-09 | 2013-05-09 | 2013-07-29 | 2013-07-29 | G | [25 empty] | 2032-06-08 |  | 2032-07-16 |  | G | 2032-08-19 |  | 2032-12-17 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.11202
1917 | 96938 | #HB2.FY17 Route 53/618 Roundabout | 0053 | Primary | Safety | VDOT | Fluvanna County | LOUISA | Culpeper | NonMPO:NonMPO | Infrastructure Investment Division | Gregory J Cooley | Gregory.Cooley@vdot.virginia.gov | (434) 906-7979 | Mike Brown | Mike.Brown@VDOT.Virginia.gov | (434) 422-9789 |  |  |  | 1 | 2017 | 0 | FY2020 | 3674062 | 3674062 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 39 days early | G | Project is on budget | [5 empty] | 2016-07-01 | 2016-07-01 | 2011-01-01 | 2016-07-04 | R | 2016-07-05 | 2016-07-05 | 2017-06-01 | 2017-05-12 | G | [5 empty] | 2017-07-18 | 2017-07-18 | 2017-07-24 | 2017-07-24 | G | 2018-06-19 | 2018-06-01 | 2018-07-02 | 2018-06-07 | G | 2019-04-12 | 2019-04-10 | 2019-11-07 | 2019-09-04 | G | 2018-08-03 | 2018-07-27 | 2019-04-11 | 2019-04-10 | G | 2019-01-14 | 2019-01-09 | 2020-01-14 | 2019-01-09 | G | [5 empty] | 2019-11-18 | 2019-11-05 | 2019-11-18 | 2019-11-05 | G | 2020-01-16 | 2020-01-20 | 2020-02-28 | 2020-01-20 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.075361
1918 | 102997 | Rte. 608 Construct Right Turn Lane | 0608 | Secondary | Reconstruction w/ Added Capacity | VDOT | Augusta County | HARRISONBURG | Staunton | SAW:Augusta County | Local Assistance Division | Donald F Komara | Donald.Komara@VDOT.Virginia.gov | (540) 434-2587 | Anthony E Pelina | Anthony.Pelina@vdot.virginia.gov | (540) 332-9575 |  |  |  | 0 |  | 0 | FY2019 | 125160 | 284203 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 35 days early | R | Project estimate is less than $5M and is 20% or more over budget | [5 empty] | 2012-07-02 | 2012-08-22 | 2012-07-31 | 2012-08-22 | R | 2012-08-30 | 2012-08-30 | 2013-03-29 | 2013-03-13 | G | [10 empty] | 2015-03-02 | 2016-01-08 | 2018-08-29 | 2016-01-08 | G | [20 empty] | 2018-08-20 | 2018-10-04 | 2018-10-26 | 2018-11-20 | R | 2019-02-27 | 2019-01-23 | 2019-02-27 | 2019-01-23 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | SAAP CONTRACT | 1 | 0 | 0.1447
1919 | 104216 | #SMART20 - CSX BRIDGE REPLACEMENT FOR WALKING AND BIKING | 0360 | Urban | Bridge Rehab w/o Added Capacity | Locally | Richmond | ASHLAND | Richmond | Richmond:Richmond | Local Assistance Division | Evan Austin | Evan.Austin@vdot.virginia.gov | (804) 609-5384 | Evan Austin | Evan.Austin@vdot.virginia.gov | (804) 609-5384 | THOMAS WESTBROOK | thomas.westbrook@richmondgov.com | (804) 646-3421 | 1 | 2020 | 0 | FY2024 | 13613000 | 13613000 | NO DATES SET YET-PE OPEN | R | Determine Requirements milestone is 258 days past the expected completion date | G | Project is on budget | 2013-10-25 | 2013-10-18 | 2013-11-08 | 2013-11-01 | G | 2013-11-11 | 2013-11-11 | 2013-11-12 | 2013-11-12 | G | 2019-10-01 | 2019-12-02 | 2020-06-08 |  | R | [10 empty] | 2021-07-12 |  | 2021-07-29 |  | G | [5 empty] | 2021-08-02 |  | 2023-08-01 |  | G | 2022-12-21 |  | 2023-08-24 |  | G | [5 empty] | 2023-09-22 |  | 2023-10-30 |  | G | 2024-01-25 |  | 2024-01-25 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.2928
1920 | 104831 | Bridge Repl-Watauga Rd over Fifteen Mile Creek(Fed ID 19098) | 0677 | Secondary | Bridge Replacement w/o Added Capacity | VDOT | Washington County | ABINGDON | Bristol | NonMPO:NonMPO | Infrastructure Investment Division | Gary Lester |  |  | Ronald C Flanary | Ronald.Flanary@VDOT.Virginia.gov | (276) 696-3252 |  |  |  | 0 |  | 0 | FY2019 | 3400027 | 3350069 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 13 days early | G | Project is on budget | [5 empty] | 2014-07-01 | 2014-06-23 | 2014-07-01 | 2014-07-14 | R | 2014-09-02 | 2014-01-21 | 2015-05-18 | 2015-08-13 | R | [5 empty] | 2016-01-25 | 2016-01-25 | 2016-01-26 | 2016-01-26 | G | 2016-08-18 | 2016-08-18 | 2016-12-05 | 2016-12-05 | G | 2018-01-09 | 2018-01-09 | 2018-04-12 | 2018-08-17 | R | 2016-12-07 | 2016-12-07 | 2017-10-16 | 2017-10-16 | G | 2017-03-21 | 2017-03-21 | 2018-03-28 | 2018-03-28 | G | [5 empty] | 2018-07-05 | 2018-07-10 | 2018-07-10 | 2018-07-10 | G | 2018-08-22 | 2018-09-07 | 2018-09-20 | 2018-09-07 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.065707
1921 | 105535 | #SGR17VB - RT 3(BUS) RAPP RIVER, BR REHABILITATION, ID 18073 | 0003 | Primary | Bridge Rehab w/o Added Capacity | VDOT | Stafford County | FREDERICKSBURG | Fredericksburg | Fredericksburg:Stafford County | Infrastructure Investment/Asset Management Division | Annette F Adams | Annette.Adams@VDOT.Virginia.gov | (540) 372-3583 | Robert Galen Ridgell | Robert.Ridgell@vdot.virginia.gov | (540) 372-3549 |  |  |  | 0 |  | 1 | FY2021 | 20000000 | 20841368 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 293 days early | Y | Project estimate is greater than $10M and is over budget by (a) up to 10% or (b) up to $5M | [5 empty] | 2014-12-09 | 2014-12-09 | 2014-12-10 | 2014-12-10 | G | 2014-12-12 | 2014-12-12 | 2018-06-01 | 2018-05-30 | G | [5 empty] | 2018-02-07 | 2018-02-07 | 2018-06-29 | 2018-06-14 | G | 2019-05-01 | 2019-03-18 | 2019-05-14 | 2019-04-05 | G | 2019-12-02 | 2019-06-26 | 2020-10-07 | 2020-06-19 | G | 2019-05-31 | 2019-04-25 | 2020-06-01 | 2020-03-02 | G | 2018-09-27 | 2018-09-27 | 2020-04-02 | 2019-12-27 | G | [5 empty] | 2020-10-13 | 2020-01-07 | 2020-10-13 | 2020-01-07 | G | 2021-02-08 | 2020-04-21 | 2021-02-08 | 2020-04-21 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.10797
1922 | 107279 | Citywide Sidewalk Construction | 0000 | Urban | Safety | Locally | Newport News | WILLIAMSBURG | Hampton Roads | Hampton Roads:Newport News | Local Assistance Division | Stephen Rowan | Steve.Rowan@vdot.virginia.gov | (757) 790-9925 | Chessica Villaflores | Chessica.Villaflores@vdot.virginia.gov | (757) 956-3094 | Bryan Stilley | bstilley@nnva.gov | (757) 926-8699 | 0 |  | 0 | FY2020 | 199018 | 172071 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 337 days early | G | Project is on budget | 2015-08-27 | 2015-08-27 | 2015-08-27 | 2015-08-27 | G | 2015-08-27 | 2015-08-27 | 2015-08-27 | 2015-08-27 | G | 2015-08-28 | 2015-08-28 | 2017-06-20 | 2018-02-01 | R | [10 empty] | 2018-06-22 | 2018-06-15 | 2018-07-06 | 2018-06-15 | G | [20 empty] | 2018-10-09 | 2018-04-30 | 2019-04-30 | 2018-06-15 | G | 2019-05-01 | 2018-07-20 | 2019-10-18 | 2018-11-15 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.24435
1923 | 108718 | INT. IMPROVEMENTS AT JAMES MADISON HWY AND FALMOUTH ST. | 0000 | Primary | Safety | Locally | Warrenton | WARRENTON | Culpeper | Northern Virginia:Warrenton | Local Assistance Division | John P Price | John.Price@VDOT.Virginia.gov | (540) 347-6371 | John P Price | John.Price@VDOT.Virginia.gov | (540) 347-6371 | Paul Bernard | pbernard@warrentonva.gov | (540) 347-1858 | 0 |  | 0 | FY2019 | 434000 | 434000 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 249 days early | G | Project is on budget | 2016-07-18 | 2016-07-18 | 2016-07-18 | 2016-07-18 | G | 2016-07-18 | 2016-07-18 | 2016-07-18 | 2016-07-18 | G | 2016-07-18 | 2016-07-18 | 2018-10-23 | 2018-03-01 | G | [35 empty] | 2019-03-20 | 2018-06-22 | 2019-04-16 | 2018-07-20 | G | 2019-04-17 | 2018-07-23 | 2019-05-28 | 2018-09-21 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.1709
1924 | 109307 | #HB2.FY17 TRAFFIC ADAPTIVE SIGNAL CONTROL | 0236 | Urban | Traffic Management/Engineering | Locally | Alexandria | FAIRFAX | Northern Virginia | Northern Virginia:Alexandria | Infrastructure Investment Division | Terry Yates | Terry.Yates@vdot.virginia.gov | (703) 259-2118 | Robert J Strevell | Robert.Strevell@vdot.virginia.gov | (703) 259-1988 | Daphne Kott | Daphne.Kott@alexandriava.gov | (703) 746-4055 | 1 | 2017 | 0 | FY2019 | 7000000 | 7000000 | NO DATES SET YET-PE OPEN | R | Determine Requirements milestone is 1083 days past the expected completion date | G | Project is on budget | 2016-11-28 | 2016-11-28 | 2017-02-28 | 2017-03-20 | R | 2017-03-01 | 2016-09-08 | 2017-03-03 | 2016-09-08 | G | 2017-03-06 | 2017-01-03 | 2018-03-06 |  | R | [35 empty] | 2019-04-26 |  | 2019-04-26 |  | R | 2019-04-29 |  | 2019-06-06 |  | R | Consultant contract is still in procurement | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.34615
1925 | 109580 | Rt. 220 Safety Improvements | 0220 | Primary | Safety | VDOT | Henry County | MARTINSVILLE | Salem | NonMPO:NonMPO | Infrastructure Investment Division | Alex H Price | Alex.Price@VDOT.Virginia.gov | (540) 378-5053 | Anthony L Handy | Tony.Handy@VDOT.Virginia.gov | (540) 352-9050 |  |  |  | 0 |  | 0 | FY2021 | 5253042 | 3752926 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 555 days early | G | Project is on budget | [5 empty] | 2016-07-12 | 2016-07-12 | 2016-07-12 | 2016-07-12 | G | 2017-01-10 | 2017-01-10 | 2019-03-28 | 2019-02-25 | G | [5 empty] | 2019-11-06 | 2019-05-15 | 2019-11-06 | 2019-05-15 | G | [5 empty] | 2020-03-11 | 2019-05-22 | 2020-06-03 | 2019-06-12 | G | [5 empty] | 2019-01-24 | 2019-01-24 | 2020-04-07 | 2019-01-24 | G | [5 empty] | 2021-03-09 | 2019-10-08 | 2021-03-09 | 2019-10-08 | G | 2021-04-28 | 2019-12-16 | 2021-06-23 | 2019-12-16 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.070061
1926 | 110931 | #SGR19LB - Commerce Street Bridge Replacement | 4602 | Urban | Bridge Replacement w/o Added Capacity | Locally | Pulaski | CHRISTIANSBURG | Salem | NonMPO:NonMPO | Local Assistance Division | Adam J Czesnowski | Adam.Czesnowski@vdot.virginia.gov | (540) 541-1216 | Adam J Czesnowski | Adam.Czesnowski@vdot.virginia.gov | (540) 541-1216 | William D. Pedigo | bpedigo@pulaskitown.org | (540) 994-8616 | 0 |  | 0 | FY2022 | 2176294 | 2176294 | NO DATES SET YET-PE OPEN | R | Determine Requirements milestone is 375 days past the expected completion date | G | Project is on budget | 2018-01-03 | 2018-01-03 | 2018-10-01 | 2019-03-14 | R | 2018-10-02 | 2019-03-27 | 2018-10-18 | 2019-05-09 | R | 2019-05-30 |  | 2020-02-12 |  | R | [10 empty] | 2020-09-30 |  | 2020-10-21 |  | R | [5 empty] | 2020-10-23 |  | 2021-06-16 |  | G | [10 empty] | 2021-07-02 |  | 2021-07-30 |  | G | 2021-08-02 |  | 2022-01-27 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.078352
1927 | 111000 | Portsmouth Boulevard Sidewalk Segment 3 | 0000 | Urban | Facilities for Pedestrians and Bicycles | Locally | Suffolk | NORFOLK | Hampton Roads | Hampton Roads:Suffolk | Infrastructure Investment Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Johndel A Alcaide | John.Alcaide@vdot.virginia.gov | (757) 956-3098 | LJ Hansen | lhansen@suffolkva.us | (757) 514-7687 | 0 |  | 0 | FY2022 | 863346 | 848369 | ACTIVITY DATES SET | G | Start Purchasing Right-of-Way milestone finished 149 days early | G | Project is on budget | 2017-08-01 | 2017-08-01 | 2017-10-25 | 2017-10-24 | G | 2017-10-26 | 2017-10-25 | 2017-10-30 | 2017-11-14 | R | 2017-10-31 | 2017-11-15 | 2018-05-10 | 2019-04-05 | R | [10 empty] | 2020-04-09 | 2019-11-06 | 2020-04-29 | 2019-12-02 | G | [5 empty] | 2020-05-01 |  | 2021-05-28 |  | G | 2018-07-23 | 2019-03-28 | 2019-03-29 | 2019-03-28 | G | [5 empty] | 2021-06-03 |  | 2021-06-30 |  | G | 2021-09-20 |  | 2021-11-08 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.15554
1928 | 111223 | COURTHOUSE PEDESTRIAN FACILITY - TAP | 0014 | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Gloucester County | SALUDA | Fredericksburg | Hampton Roads:Gloucester County | Local Assistance Division | Anastasia Kapitan | Anastasia.Kapitan@vdot.virginia.gov | (540) 899-4292 | Anastasia Kapitan | Anastasia.Kapitan@vdot.virginia.gov | (540) 899-4292 | Lindy Harper | bharper@gloucesterva.info | (804) 693-6175 | 0 |  | 0 | FY2022 | 296706 | 296706 | ACTIVITY DATES SET | G | Determine Requirements milestone finished 5 days early | G | Project is on budget | 2017-07-05 | 2017-07-05 | 2017-11-06 | 2017-11-06 | G | 2017-07-05 | 2017-07-05 | 2017-08-03 | 2017-08-03 | G | 2017-08-03 | 2017-08-03 | 2019-05-28 | 2019-05-23 | G | [35 empty] | 2021-05-27 |  | 2021-10-04 |  | G | 2021-10-05 |  | 2022-04-01 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.31678
1929 | 111282 | #SGR18VB - RT 621 BR & APPR OVER APPOMATTOX RIVER (Fed 5741) | 0621 | Secondary | Bridge Replacement w/o Added Capacity | VDOT | Cumberland County | DILLWYN | Lynchburg | NonMPO:NonMPO | Infrastructure Investment/Asset Management Division | Vincent A Mayberry | Vincent.Mayberry@vdot.virginia.gov | (434) 856-8289 | Vincent A Mayberry | Vincent.Mayberry@vdot.virginia.gov | (434) 856-8289 |  |  |  | 0 |  | 1 | FY2022 | 3277443 | 3277443 | ACTIVITY DATES SET | G | Obtained Permits milestone finished 183 days early | G | Project is on budget | [10 empty] | 2020-12-07 | 2020-05-19 | 2020-12-11 | 2020-08-24 | G | [25 empty] | 2020-04-20 | 2020-04-20 | 2021-04-20 | 2020-10-19 | G | [5 empty] | 2021-07-13 |  | 2021-07-13 |  | G | 2021-09-01 |  | 2022-05-24 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.061859
1930 | 104898 | #SGR17VB - Bridge Repl - RT 23 NBL over NSRR (Fed 10697) | 0023 | Primary | Bridge Replacement w/ Added Capacity | VDOT | Lee County | WISE | Bristol | NonMPO:NonMPO | Infrastructure Investment/Asset Management Division | Gary Lester |  |  | John E Sproles | John.Sproles@VDOT.Virginia.gov | (276) 696-3391 |  |  |  | 0 |  | 1 | FY2023 | 1900000 | 3865120 | ACTIVITY DATES SET | G | Determine Requirements milestone finished on-time | R | Project estimate is less than $5M and is 20% or more over budget | [5 empty] | 2014-09-05 | 2014-08-19 | 2014-10-03 | 2014-09-16 | G | 2018-07-11 | 2018-07-20 | 2019-01-04 | 2019-01-04 | G | [35 empty] | 2023-01-10 |  | 2023-01-10 |  | G | 2023-01-10 |  | 2023-05-03 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.086961
1931 | 106274 | SPRINGFIELD CBC COMMUTER PARKING GARAGE | 0644 | Secondary | Other | Locally | Fairfax County | FAIRFAX | Northern Virginia | Northern Virginia:Fairfax County | Infrastructure Investment Division | Amir Salahshoor | A.Salahshoor@VDOT.Virginia.gov | (703) 259-1957 | Rhoderick M Undan | Rhoderick.Undan@vdot.virginia.gov | (703) 259-3347 | David Franklin | David.Franklin@fairfaxcounty.gov | (703) 324-2473 | 0 |  | 0 | FY2020 | 63810000 | 63789900 | ADVERTISED | R | Start Delivery milestone is 256 days past the expected completion date | G | Project is on budget | 2016-06-01 | 2016-06-14 | 2016-09-30 | 2017-01-04 | R | 2016-07-01 | 2016-07-11 | 2016-07-01 | 2016-07-11 | R | 2016-10-03 | 2016-09-29 | 2016-12-30 | 2017-02-22 | R | [5 empty] | 2017-02-17 | 2017-02-17 | 2017-07-28 | 2017-07-28 | G | 2017-08-16 | 2017-08-16 | 2017-12-16 | 2017-12-16 | G | [5 empty] | 2018-02-15 | 2018-02-15 | 2019-07-31 | 2020-01-22 | R | [10 empty] | 2019-10-02 | 2020-06-17 | 2019-12-02 | 2020-07-10 | R | 2020-01-10 | 2020-07-13 | 2020-06-10 |  | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.27886
1932 | 108377 | eCorridor Regional Park Southwest Trail (Phase II) |  | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Scott County | WISE | Bristol | NonMPO:NonMPO | Local Assistance Division | Tabitha H Crowder | Tabitha.Crowder@vdot.virginia.gov | (276) 696-3482 | Kenneth R Plummer | KR.Plummer@VDOT.Virginia.gov | (276) 696-3261 | John Kilgore | jkilgore@scottcountyva.com | (276) 386-2525 | 0 |  | 0 | FY2019 | 186669 | 235023 | WAITING FINANCIAL CLOSURE | R | Start Delivery milestone finished 197 days late | R | Project estimate is less than $5M and is 20% or more over budget | 2016-06-01 | 2016-06-01 | 2017-01-24 | 2016-06-01 | G | [5 empty] | 2016-06-01 | 2016-06-01 | 2017-01-24 | 2017-01-24 | G | [35 empty] | 2017-11-07 | 2017-11-07 | 2018-07-23 | 2019-03-14 | R | 2018-10-18 | 2019-05-31 | 2018-11-15 | 2019-05-31 | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.34583
1933 | 108898 | #HB2.FY17 Cranberry Road Improvements | 4060 | Urban | Reconstruction w/o Added Capacity | Locally | Galax | MARTINSVILLE | Salem | NonMPO:NonMPO | Infrastructure Investment Division | Jessie Nester | Jessie.Nester@vdot.virginia.gov | (540) 613-4115 | Jessie Nester | Jessie.Nester@vdot.virginia.gov | (540) 613-4115 | Keith Barker | kbarker@galaxva.com | (276) 236-5773 | 1 | 2017 | 0 | FY2020 | 3067161 | 2422579 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 47 days early | G | Project is on budget | 2016-07-01 | 2016-07-01 | 2016-08-10 | 2016-08-10 | G | 2016-06-28 | 2016-06-28 | 2016-06-29 | 2016-06-28 | G | 2016-09-23 | 2017-01-27 | 2017-03-08 | 2017-06-02 | R | [10 empty] | 2018-01-16 | 2018-09-20 | 2018-03-01 | 2019-01-30 | R | [5 empty] | 2018-03-05 | 2019-02-07 | 2019-03-11 | 2019-11-14 | R | [10 empty] | 2019-12-19 | 2019-12-09 | 2020-01-15 | 2020-01-13 | G | 2020-01-16 | 2020-02-25 | 2020-05-04 | 2020-03-18 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.09489
1934 | 109482 | Richmond Transportation Operations Center Upgrade | 0095 | Interstate | Other | VDOT | Richmond District-wide |  | Richmond | Richmond:Richmond District-wide | Infrastructure Investment Division | Lezlie H Ellis | Lezlie.Ellis@VDOT.Virginia.gov | (804) 609-5266 | Lezlie H Ellis | Lezlie.Ellis@VDOT.Virginia.gov | (804) 609-5266 |  |  |  | 0 |  | 0 | FY2020 | 10000000 | 10000000 | AWARDED | G | Start Delivery milestone finished 141 days early | G | Project is on budget | [10 empty] | 2019-02-04 | 2019-02-04 | 2019-02-15 | 2019-02-15 | G | [35 empty] | 2019-05-14 | 2019-02-20 | 2019-05-14 | 2019-02-21 | G | 2019-06-27 | 2019-02-26 | 2019-07-18 | 2019-02-27 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | ADMINISTRATIVE SERVICES | 1 | 0 | 0.084403
1935 | 109814 | ROLLING ROAD-RTE 638-PHASE I-ADDITION OF NB LEFT-TURN LANE | 0638 | Secondary | Reconstruction w/ Added Capacity | VDOT | Fairfax County | FAIRFAX | Northern Virginia | Northern Virginia:Fairfax County | Local Assistance Division | Terry Yates | Terry.Yates@vdot.virginia.gov | (703) 259-2118 | Christopher Barksdale | Chris.Barksdale@vdot.virginia.gov | (703) 259-2768 |  |  |  | 0 |  | 0 | FY2020 | 4755091 | 5745727 | CONSTRUCTION STARTED | R | Start Delivery milestone finished 319 days late | Y | Project estimate is less than $5M and is up to 20% over budget | [10 empty] | 2017-05-24 | 2016-12-14 | 2017-05-31 | 2018-02-27 | R | [5 empty] | 2018-02-28 | 2018-03-30 | 2018-05-30 | 2018-10-01 | R | 2018-09-04 | 2019-05-29 | 2018-11-30 | 2019-06-11 | R | 2019-05-31 | 2019-04-01 | 2020-01-31 | 2021-01-04 | R | 2018-12-03 | 2019-07-29 | 2019-05-30 | 2020-09-10 | R | 2019-05-31 | 2017-05-24 | 2019-08-30 | 2017-05-24 | G | [5 empty] | 2019-09-03 | 2020-10-06 | 2019-11-05 | 2020-10-06 | R | 2019-11-21 | 2020-12-15 | 2020-01-31 | 2020-12-15 | R | Design plans are being revised | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 1 | 0.23621
1937 | 111033 | #SGR18LB - Carolina Road over Cypress Swamp | 0032 | Urban | Bridge Replacement w/o Added Capacity | Locally | Suffolk | NORFOLK | Hampton Roads | Hampton Roads:Suffolk | Infrastructure Investment Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Johndel A Alcaide | John.Alcaide@vdot.virginia.gov | (757) 956-3098 | L.Hansen | lhansen@suffolkva.us | (757) 514-7687 | 0 |  | 1 | FY2023 | 3226571 | 3226571 | NO DATES SET YET-PE OPEN | G | Start Development milestone finished 57 days early | G | Project is on budget | 2020-04-15 | 2017-07-13 | 2020-07-09 | 2017-10-05 | G | 2020-07-10 | 2020-03-24 | 2020-07-23 | 2020-05-27 | G | 2020-07-24 |  | 2021-07-09 |  | G | [25 empty] | 2021-03-12 | 2020-02-20 | 2021-11-10 | 2020-02-20 | G | [5 empty] | 2022-05-20 |  | 2022-06-17 |  | G | 2022-06-20 |  | 2023-01-11 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.11612
1938 | 111224 | ONVILLE ROAD SIDEWALK - TAP | 0641 | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Stafford County | FREDERICKSBURG | Fredericksburg | Fredericksburg:Stafford County | Local Assistance Division | Khalil Minhas | Khalil.Minhas@vdot.virginia.gov | (540) 374-3369 | Khalil Minhas | Khalil.Minhas@vdot.virginia.gov | (540) 374-3369 | Thomas O'Connor | toconnor@staffordcountyva.gov | (540) 658-4610 | 0 |  | 0 | FY2022 | 1047661 | 1399303 | ACTIVITY DATES SET | G | Start Purchasing Right-of-Way milestone finished 189 days early | R | Project estimate is less than $5M and is 20% or more over budget | 2017-04-06 | 2017-04-06 | 2017-10-30 | 2017-10-30 | G | 2017-06-30 | 2017-06-30 | 2017-07-18 | 2017-07-18 | G | 2017-07-19 | 2017-07-19 | 2018-12-13 | 2018-12-13 | G | [10 empty] | 2020-02-10 | 2019-08-23 | 2020-03-02 | 2019-08-26 | G | [5 empty] | 2020-03-04 | 2020-11-04 | 2021-05-13 |  | G | [10 empty] | 2021-06-01 |  | 2021-06-28 |  | G | 2021-06-29 |  | 2021-11-04 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.27991
1939 | 111699 | Replace two bridges with box culverts in Prince George Co | 9999 | Secondary | Bridge Rehab w/o Added Capacity | VDOT | Prince George County | PETERSBURG | Richmond | NonMPO:NonMPO | Infrastructure Investment/Asset Management Division | Noyan F Erermis | Noyan.Erermis@vdot.virginia.gov | (804) 819-9653 | Noyan F Erermis | Noyan.Erermis@vdot.virginia.gov | (804) 819-9653 |  |  |  | 0 |  | 0 | FY2023 | 2325000 | 2325000 | ACTIVITY DATES SET | R | Start Purchasing Right-of-Way milestone finished 46 days late | G | Project is on budget | [5 empty] | 2017-07-31 | 2017-07-17 | 2017-08-08 | 2017-07-27 | G | 2017-08-09 | 2018-04-23 | 2019-01-11 | 2019-06-12 | R | [5 empty] | 2019-11-26 | 2019-11-26 | 2019-12-11 | 2019-12-11 | G | 2020-08-03 | 2020-08-18 | 2020-09-04 | 2020-10-20 | R | 2021-03-08 |  | 2022-01-19 |  | G | 2020-09-22 | 2020-12-10 | 2021-04-09 |  | Y | 2018-01-11 |  | 2021-10-13 |  | G | [5 empty] | 2022-03-08 |  | 2022-03-08 |  | G | 2022-04-27 |  | 2022-07-28 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.1351
1940 | 111789 | #SMART18 - Intersection of Colonial Trail East and Route 617 | 0010 | Primary | Reconstruction w/o Added Capacity | VDOT | Surry County | WILLIAMSBURG | Hampton Roads | NonMPO:NonMPO | Infrastructure Investment Division | Emmanuel Eod Ofori-Darko | Emmanuel.Darko@VDOT.Virginia.gov | (757) 956-3261 | Kenneth D Mckinna | Kenneth.McKinna@VDOT.Virginia.gov | (757) 956-3271 |  |  |  | 1 | 2018 | 0 | FY2024 | 6017450 | 5993663 | ACTIVITY DATES SET | G | Engage Public milestone finished on-time | G | Project is on budget | [5 empty] | 2019-08-21 | 2019-08-02 | 2019-09-03 | 2019-08-02 | G | 2019-09-04 | 2019-08-05 | 2019-12-31 | 2019-12-20 | G | [5 empty] | 2020-10-08 | 2020-12-08 | 2020-12-08 | 2020-12-08 | G | 2021-12-08 |  | 2021-12-21 |  | G | 2022-11-28 |  | 2023-08-29 |  | G | 2022-01-10 |  | 2022-11-08 |  | G | 2021-12-28 | 2020-04-27 | 2023-02-13 | 2020-04-27 | G | [5 empty] | 2023-10-10 |  | 2023-10-10 |  | G | 2024-01-31 |  | 2024-03-27 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.15279
1941 | 113373 | Replace Two Small Bridges on Rtes 611 & 624 in Dinwiddie Co | 9999 | Secondary | Bridge Replacement w/o Added Capacity | VDOT | Dinwiddie County | PETERSBURG | Richmond | NonMPO:NonMPO | Infrastructure Investment Division | Noyan F Erermis | Noyan.Erermis@vdot.virginia.gov | (804) 819-9653 | Noyan F Erermis | Noyan.Erermis@vdot.virginia.gov | (804) 819-9653 |  |  |  | 0 |  | 0 | FY2024 | 2175000 | 2175000 | NO DATES SET YET-PE OPEN | R | Determine Requirements milestone is 192 days past the expected completion date | G | Project is on budget | [5 empty] | 2019-09-03 | 2018-12-12 | 2019-09-16 | 2018-12-20 | G | 2019-09-17 | 2018-12-21 | 2020-08-13 |  | R | [5 empty] | 2021-07-20 |  | 2021-08-02 |  | G | 2022-10-03 |  | 2022-10-14 |  | G | 2023-03-17 |  | 2023-09-19 |  | G | 2022-11-01 |  | 2023-05-11 |  | G | 2022-09-26 |  | 2023-06-02 |  | G | [5 empty] | 2023-10-10 |  | 2023-10-10 |  | G | 2024-01-05 |  | 2024-01-05 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.061281
1942 | 113763 | #SGR19LP - PORTRFIELD HIGHWAY PRIMARY EXTENSION PAVING | 0019 | Urban | Resurfacing | Locally | Abingdon | ABINGDON | Bristol | Bristol:Abingdon | Infrastructure Investment Division | Tabitha H Crowder | Tabitha.Crowder@vdot.virginia.gov | (276) 696-3482 | Tabitha H Crowder | Tabitha.Crowder@vdot.virginia.gov | (276) 696-3482 | Michael Surrett | msurrett@abingdon-va.gov | (276) 628-3167 | 0 |  | 1 | FY2019 | 233316 | 233316 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished on-time | G | Project is on budget | 2019-06-12 | 2018-08-01 | 2019-09-05 | 2018-09-10 | G | [5 empty] | 2019-06-12 | 2018-09-12 | 2019-06-25 | 2018-09-28 | G | [25 empty] | 2018-10-08 | 2018-10-08 | 2018-10-30 | 2018-10-30 | G | [5 empty] | 2018-11-06 | 2018-11-06 | 2018-11-20 | 2018-11-20 | G | 2018-12-03 | 2018-12-03 | 2018-12-03 | 2018-12-03 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.062587
1943 | 115484 | #SMART20-Russell Rd & Poplar St Int Imp (APP ID# 4031) | 6058 | Urban | Reconstruction w/o Added Capacity | VDOT | Abingdon | ABINGDON | Bristol | Bristol:Abingdon | Infrastructure Investment Division | Dennis R Harris | Dennis.Harris@VDOT.Virginia.gov | (276) 696-3289 | Brandi Halloway | Brandi.Halloway@vdot.virginia.gov | (276) 696-3254 |  |  |  | 1 | 2020 | 0 | FY2024 | 765000 | 765000 | ACTIVITY DATES SET | G | Determine Requirements milestone finished on-time | G | Project is on budget | [5 empty] | 2020-03-06 | 2020-03-06 | 2020-03-19 | 2020-03-19 | G | 2020-03-20 | 2020-03-20 | 2020-11-04 | 2020-11-04 | G | [5 empty] | 2021-07-08 |  | 2021-07-21 |  | G | 2022-06-14 |  | 2022-06-27 |  | G | 2022-11-21 |  | 2023-05-31 |  | G | 2022-07-14 |  | 2023-01-24 |  | G | 2022-01-06 |  | 2022-07-13 |  | G | [5 empty] | 2023-06-13 |  | 2023-06-13 |  | G | 2023-09-01 |  | 2024-02-29 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.093365
1944 | 116236 | #I81CIP NB EXIT 302 EXTEND ACCELERATION LANE (ID #47) | 0081 | Interstate | Reconstruction w/o Added Capacity | VDOT | Frederick County | EDINBURG | Staunton | NonMPO:NonMPO | Infrastructure Investment Division | John-Allen L Ennis | JohnAllen.Ennis@VDOT.Virginia.gov | (540) 332-9118 | Alexander Alvarado | Alexander.Alvarado@vdot.virginia.gov | (540) 332-7372 |  |  |  | 0 |  | 0 | FY2020 | 1172975 | 1172975 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished on-time | G | Project is on budget | [5 empty] | 2020-07-01 | 2019-09-06 | 2020-07-15 | 2019-09-19 | G | 2020-07-16 | 2019-09-20 | 2021-03-12 | 2019-11-11 | G | [5 empty] | 2019-10-17 | 2019-10-17 | 2019-10-17 | 2019-10-17 | G | [5 empty] | 2019-08-23 | 2019-08-23 | 2019-08-23 | 2019-08-23 | G | [15 empty] | 2020-01-07 | 2020-01-07 | 2020-01-07 | 2020-01-07 | G | 2020-03-30 | 2020-03-30 | 2020-03-30 | 2020-03-30 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | SAAP CONTRACT | 1 | 0 | 0.063486
1945 | 116690 | BURKEVILLE NORFOLK SOUTHERN RAIlLWAY STATION- PHASE V |  | Enhancement | Rehabilitation of Historic Bldgs/Facilities | Locally | Burkeville | PETERSBURG | Richmond | NonMPO:NonMPO | Local Assistance Division | Jorg Huckabee-Mayfield | Jorg.Huckabee-Mayfield@VDOT.Virginia.gov | (804) 609-5292 | Jorg Huckabee-Mayfield | Jorg.Huckabee-Mayfield@VDOT.Virginia.gov | (804) 609-5292 | JOE MORRISETTE, Mayor | burkeville1@embarqmail.com | (434) 767-4095 | 0 |  | 0 | FY2023 | 120698 | 120698 | NO DATES SET YET-PE OPEN | R | Agreement with Locality milestone finished 41 days late | G | Project is on budget | 2020-03-02 | 2020-03-02 | 2020-07-30 | 2020-09-09 | R | 2020-08-14 | 2020-09-02 | 2020-09-11 | 2020-09-02 | G | 2021-03-01 |  | 2021-09-30 |  | G | [25 empty] | 2022-02-02 |  | 2022-10-03 |  | G | [5 empty] | 2023-01-31 |  | 2023-01-31 |  | G | 2023-05-23 |  | 2023-05-23 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.21538
1946 | 117749 | JTHG Graphic & Visual Identity - Sign Installation |  | Enhancement | Scenic or Historic Highway Programs | VDOT | Statewide |  | Statewide | NonMPO:NonMPO | Local Assistance Division | Synthia Waymack | Synthia.Waymack@vdot.virginia.gov | (804) 786-2586 | Synthia Waymack | Synthia.Waymack@vdot.virginia.gov | (804) 786-2586 | Journey Through Hallowed Ground Partnership |  |  | 0 |  | 0 | FY2021 | 195114 | 195114 | NO DATES SET YET | R | Determine Requirements milestone is 72 days past the expected completion date | G | Project is on budget | [10 empty] | 2020-08-03 |  | 2020-12-11 |  | R | [35 empty] | 2020-12-15 |  | 2020-12-21 |  | R | 2020-12-22 |  | 2020-12-29 |  | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | WORK/TASK ORDER | 0 | 1 | 0.32203
1947 | 118374 | #SGR21LB-Indian Crk over Indian Crk-Bridge Repl-FED ID 21799 | 0939 | Urban | Bridge Replacement w/o Added Capacity | Locally | Chesapeake | NORFOLK | Hampton Roads | Hampton Roads:Chesapeake | Infrastructure Investment/Asset Management Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Johndel A Alcaide | John.Alcaide@vdot.virginia.gov | (757) 956-3098 | Sam Sawan | ssawan@cityofchesapeake.net | (757) 382-8263 | 0 |  | 1 | FY2025 | 3580000 | 3580000 | NO DATES SET YET | G | Agreement with Locality milestone is 260 days ahead of the expected completion date | G | Project is on budget | 2021-07-01 |  | 2021-11-08 |  | G | 2021-11-09 |  | 2021-12-02 |  | G | 2022-06-13 |  | 2022-10-04 |  | G | [10 empty] | 2024-01-31 |  | 2024-03-06 |  | G | [5 empty] | 2024-03-07 |  | 2024-08-02 |  | G | 2024-04-11 |  | 2024-09-09 |  | G | [5 empty] | 2024-11-06 |  | 2024-12-06 |  | G | 2025-03-03 |  | 2025-03-03 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.094011
1948 | 100519 | RTE 121 CFX - POUND CONNECTOR | 0121 | Primary | New Construction Roadway | VDOT | Wise County | WISE | Bristol | NonMPO:NonMPO | Infrastructure Investment Division | Marty R Halloway | Marty.Halloway@VDOT.Virginia.gov | (276) 696-3367 | Robert C Leonard | Robert.Leonard@VDOT.Virginia.gov | (276) 696-3258 |  |  |  | 0 |  | 0 | FY2025 | 52000000 | 52000000 | NO DATES SET YET | G | Start Development milestone is 940 days ahead of the expected completion date | G | Project is on budget | [5 empty] | 2011-07-01 | 2012-02-10 | 2023-09-19 |  | G | 2023-07-31 |  | 2023-11-30 |  | G | [10 empty] | 2024-11-15 |  | 2024-11-15 |  | G | [20 empty] | 2024-11-15 |  | 2024-11-29 |  | G | 2024-12-17 |  | 2024-12-31 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | DESIGN BUILD/PPTA | 0 | 0 | 0.18185
1949 | 104600 | RTE 29 NBL - BRIDGE & APPR. OVER NS RR FED. ID. NO. (04144) | 0029 | Primary | Bridge Replacement w/o Added Capacity | VDOT | Campbell County | APPOMATTOX | Lynchburg | Lynchburg:Campbell County | Infrastructure Investment Division | Brian J Casto | Brian.Casto@VDOT.Virginia.gov | (434) 856-8276 | Lindsey S Hodges | Lindsey.Hodges@vdot.virginia.gov | (434) 856-8143 |  |  |  | 0 |  | 0 | FY2021 | 9925194 | 19056280 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 15 days early | R | Project estimate is between $5M and $10M and is a $1M or more over budget | [5 empty] | 2015-08-24 | 2015-08-24 | 2015-09-30 | 2015-08-24 | G | 2015-10-15 | 2015-10-15 | 2017-03-16 | 2017-03-10 | G | [5 empty] | 2017-08-25 | 2017-08-25 | 2017-09-20 | 2017-09-20 | G | 2018-07-20 | 2018-07-20 | 2018-08-09 | 2018-08-09 | G | 2019-09-13 | 2019-09-26 | 2020-06-09 | 2020-07-21 | R | 2018-09-18 | 2018-09-06 | 2019-09-13 | 2019-09-13 | G | 2019-04-01 | 2019-04-01 | 2020-03-18 | 2019-12-04 | G | [5 empty] | 2020-09-08 | 2020-09-08 | 2020-09-08 | 2020-09-08 | G | 2020-11-17 | 2020-12-09 | 2021-01-14 | 2020-12-30 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.067255
1950 | 113018 | LEE HWY - TRAFFIC SIGNAL SYNCHRONIZATION | 0029 | Urban | Traffic Management/Engineering | Locally | Warrenton | WARRENTON | Culpeper | NonMPO:NonMPO | Local Assistance Division | Ken Connors |  |  | John P Price | John.Price@VDOT.Virginia.gov | (540) 347-6371 | Paul Bernard | pbernard@warrentonva.gov | (540) 347-1858 | 0 |  | 0 | FY2021 | 105060 | 105060 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 333 days early | G | Project is on budget | 2018-11-01 | 2018-06-26 | 2019-02-01 | 2018-07-02 | G | 2019-02-04 | 2019-02-26 | 2019-02-06 | 2019-03-01 | R | 2019-02-07 | 2019-03-04 | 2019-08-12 | 2019-09-04 | R | [25 empty] | 2019-10-10 | 2019-09-11 | 2020-06-17 | 2019-09-12 | G | [5 empty] | 2020-07-16 | 2019-12-04 | 2020-08-12 | 2019-12-04 | G | 2020-11-02 | 2019-12-05 | 2020-11-02 | 2019-12-05 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.11279
1951 | 113611 | Vienna Metro Station Bicycle and Pedestrian Improvements | 6154 | Enhancement | Facilities for Pedestrians and Bicycles | VDOT | Fairfax County | FAIRFAX | Northern Virginia | Northern Virginia:Fairfax County | Local Assistance Division | Andrew G Beacher | Andrew.Beacher@vdot.virginia.gov | (703) 259-2239 | Zamir A Mirza | Zamir.Mirza@VDOT.Virginia.gov | (703) 259-1794 | Lauren Delmare | lauren.delmare@FairfaxCounty.gov | (703) 877-5781 | 0 |  | 0 | FY2024 | 6494990 | 6494990 | NO DATES SET YET-PE OPEN | R | Determine Requirements milestone is 103 days past the expected completion date | G | Project is on budget | 2019-12-30 | 2019-12-30 | 2019-12-30 | 2019-12-30 | G | 2019-12-03 | 2019-08-08 | 2019-12-16 | 2019-08-08 | G | 2019-12-17 | 2019-12-17 | 2020-11-10 |  | R | [5 empty] | 2021-09-16 |  | 2021-09-29 |  | G | 2023-01-10 |  | 2023-01-25 |  | G | 2023-06-19 |  | 2023-12-26 |  | G | 2023-02-10 |  | 2023-08-15 |  | G | 2022-06-24 |  | 2023-01-03 |  | G | [5 empty] | 2024-01-09 |  | 2024-01-09 |  | G | 2024-04-02 |  | 2024-04-02 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 1 | 0.19799
1952 | 113770 | RTE. 23 INSTALL RUMBLE STRIPS, GUARDRAIL, DRAINAGE IMPROV. | 0023 | Primary | Safety | VDOT | Scott County | WISE | Bristol | Kingsport:Scott County | Infrastructure Investment Division | Allan D Sumpter | Allan.Sumpter@VDOT.virginia.gov | (276) 525-6461 | Chase R Buchanan | Chase.Buchanan@VDOT.Virginia.gov | (276) 696-3251 |  |  |  | 0 |  | 0 | FY2025 | 563334 | 563334 | NO DATES SET YET | G | Start Development milestone is 571 days ahead of the expected completion date | G | Project is on budget | [5 empty] | 2022-09-01 |  | 2022-09-15 |  | G | 2022-09-16 |  | 2023-05-12 |  | G | [5 empty] | 2024-01-23 |  | 2024-03-05 |  | G | [5 empty] | 2024-06-18 |  | 2024-10-09 |  | G | [5 empty] | 2024-06-03 |  | 2024-09-03 |  | G | [5 empty] | 2024-11-12 |  | 2024-11-12 |  | G | 2025-02-07 |  | 2025-02-07 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.06819
1953 | 116016 | District-wide Edgeline Rumble Strips Installations | 9999 | Miscellaneous | Safety | VDOT | Culpeper District-wide |  | Culpeper | NonMPO:NonMPO | Infrastructure Investment/Asset Management Division | Gregory J Cooley | Gregory.Cooley@vdot.virginia.gov | (434) 906-7979 | Caroline Awua-Mensah | Caroline.Awua-Mensah@vdot.virginia.gov | (540) 829-7618 |  |  |  | 0 |  | 0 | FY2024 | 253456 | 253456 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 1278 days early | G | Project is on budget | [5 empty] | 2020-06-23 | 2020-03-24 | 2020-07-07 | 2020-04-01 | G | 2020-07-08 | 2020-04-02 | 2020-08-04 | 2020-04-17 | G | [35 empty] | 2021-03-09 | 2020-04-20 | 2023-08-08 | 2020-04-20 | G | 2023-10-30 | 2020-04-30 | 2023-10-30 | 2020-04-30 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | WORK/TASK ORDER | 1 | 0 | 0.10387
1954 | 116394 | BOUNDARY CHANNEL DR AT I-395 INTERCHANGE - FY 14 RVSH | 6587 | Secondary | Reconstruction w/o Added Capacity | VDOT | Arlington County | FAIRFAX | Northern Virginia | Northern Virginia:Arlington County | Infrastructure Investment Division | Andrew G Beacher | Andrew.Beacher@vdot.virginia.gov | (703) 259-2239 | Christopher Barksdale | Chris.Barksdale@vdot.virginia.gov | (703) 259-2768 | Jon Lawler | jlawler@arlingtonva.us | (703) 228-3724 | 0 |  | 0 | FY2022 | 20311990 | 20311990 | ACTIVITY DATES SET | Y | Start Purchasing Right-of-Way milestone is 25 days ahead of the expected completion date and there is a risk of missing this milestone date | G | Project is on budget | 2019-10-22 | 2019-10-22 | 2020-01-14 | 2020-01-14 | G | 2020-01-23 | 2020-01-23 | 2020-02-02 | 2020-02-02 | G | 2019-10-22 | 2019-10-22 | 2020-12-16 | 2020-11-20 | G | [10 empty] | 2021-01-12 |  | 2021-03-18 |  | Y | [20 empty] | 2021-03-19 |  | 2021-03-29 |  | Y | 2021-08-12 |  | 2021-09-09 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | DESIGN BUILD/PPTA | 0 | 1 | 0.22941
1955 | 117085 | #REVSH21 BREEZEWOOD DRIVE - RECONSTRUCTION | 9999 | Urban | Reconstruction w/o Added Capacity | Locally | Lynchburg | APPOMATTOX | Lynchburg | Lynchburg:Lynchburg | Local Assistance Division | Gregg Allen | Gregg.Allen@vdot.virginia.gov | (434) 426-5575 | Gregg Allen | Gregg.Allen@vdot.virginia.gov | (434) 426-5575 | LEE NEWLAND | lee.newland@lynchburgva.gov | (434) 455-3947 | 0 |  | 0 | FY2025 | 6003180 | 6003180 | NO DATES SET YET | G | Agreement with Locality milestone is 106 days ahead of the expected completion date | G | Project is on budget | 2021-01-29 |  | 2021-06-07 |  | G | 2021-06-08 |  | 2021-06-28 |  | G | 2022-01-07 |  | 2022-05-03 |  | G | [10 empty] | 2023-08-22 |  | 2023-09-26 |  | G | [5 empty] | 2023-09-27 |  | 2024-03-04 |  | G | 2024-01-30 |  | 2024-06-26 |  | G | [5 empty] | 2024-06-05 |  | 2024-07-02 |  | G | 2024-09-20 |  | 2024-09-20 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.12048
1956 | 117998 | S. Franklin/First Ped. Improvements |  | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Christiansburg | CHRISTIANSBURG | Salem | New River Valley:Christiansburg | Local Assistance Division | Adam J Czesnowski | Adam.Czesnowski@vdot.virginia.gov | (540) 541-1216 | Adam J Czesnowski | Adam.Czesnowski@vdot.virginia.gov | (540) 541-1216 | Justin St. Clair | jstclair@christiansburg.org | (540) 382-6120 | 0 |  | 0 | FY2025 | 203292 | 203292 | NO DATES SET YET | G | Agreement with Locality milestone is 50 days ahead of the expected completion date | G | Project is on budget | 2020-12-01 |  | 2021-04-12 |  | G | 2021-04-13 |  | 2021-05-03 |  | G | 2021-11-08 |  | 2022-03-09 |  | G | [10 empty] | 2023-06-27 |  | 2023-08-01 |  | G | [5 empty] | 2023-08-02 |  | 2024-01-04 |  | G | 2023-11-30 |  | 2024-05-01 |  | G | [5 empty] | 2024-04-10 |  | 2024-05-07 |  | G | 2024-07-26 |  | 2024-07-26 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.24498
1957 | 17534 | RTE 58 - CORRIDOR DEVELOPMENT PROG - 4 LANES (Crooked Oak) | 0058 | Primary | Reconstruction w/ Added Capacity | VDOT | Carroll County | MARTINSVILLE | Salem | NonMPO:NonMPO | Infrastructure Investment Division | Robert P Williams | Robbie.Williams@VDOT.Virginia.gov | (276) 229-9954 | Brian H Becker | Brian.Becker@VDOT.Virginia.gov | (540) 204-7959 |  |  |  | 0 |  | 0 | FY2026 | 9907000 | 293000000 | ACTIVITY DATES SET | G | Start Purchasing Right-of-Way milestone finished on-time | R | Project estimate is between $5M and $10M and is a $1M or more over budget | [5 empty] | 1997-07-01 | 1997-07-07 | 1997-07-31 | 1997-07-08 | G | 1997-08-01 | 1997-01-28 | 1998-01-30 | 1997-04-26 | G | [5 empty] | 1998-12-03 | 1998-12-03 | 1998-12-17 | 1998-12-17 | G | 1999-09-20 | 1999-09-20 | 1999-11-02 | 1999-11-02 | G | [5 empty] | 2000-02-25 | 2000-02-25 | 2022-12-13 |  | G | 1998-10-19 |  | 2022-12-12 |  | G | [5 empty] | 2025-12-09 |  | 2025-12-09 |  | G | 2025-12-23 |  | 2026-01-22 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.087046
1958 | 102944 | Centerville Road Intersection Improvements at News Road | 0614 | Secondary | Traffic Management/Engineering | VDOT | James City County | WILLIAMSBURG | Hampton Roads | Hampton Roads:James City County | Infrastructure Investment Division | Wali Zaman | Wali.Zaman@VDOT.Virginia.gov | (757) 956-3272 | James A Klotz | James.Klotz@vdot.virginia.gov | (757) 274-2552 | Paul Holt | Paul.Holt@JamesCityCountyva.gov | (757) 253-6671 | 0 |  | 0 | FY2020 | 3259663 | 4071513 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 124 days early | Y | Project estimate is less than $5M and is up to 20% over budget | [5 empty] | 2014-08-04 | 2014-08-04 | 2014-08-04 | 2014-08-04 | G | 2014-08-04 | 2014-08-04 | 2016-12-13 | 2016-12-13 | G | [5 empty] | 2016-12-09 | 2016-12-09 | 2016-12-22 | 2016-12-22 | G | 2017-11-08 | 2017-11-08 | 2017-11-09 | 2017-11-09 | G | 2018-06-04 | 2018-06-14 | 2019-01-25 | 2019-01-25 | G | 2017-11-16 | 2017-11-16 | 2018-06-01 | 2018-06-28 | R | [10 empty] | 2019-11-12 | 2019-08-13 | 2019-11-12 | 2019-08-13 | G | 2020-01-16 | 2019-11-13 | 2020-03-16 | 2019-11-13 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 1 | 0.28462
1959 | 105960 | #SGR21VB - Bridge Repl - Rte 23 SBL over NSRR (Fed ID 10696) | 0023 | Primary | Bridge Replacement w/ Added Capacity | VDOT | Lee County | WISE | Bristol | NonMPO:NonMPO | Infrastructure Investment Division | Gary Lester |  |  | John E Sproles | John.Sproles@VDOT.Virginia.gov | (276) 696-3391 |  |  |  | 0 |  | 0 | FY2023 | 3400000 | 3941771 | ACTIVITY DATES SET | G | Determine Requirements milestone finished on-time | Y | Project estimate is less than $5M and is up to 20% over budget | [5 empty] | 2017-08-07 | 2017-08-07 | 2017-09-07 | 2017-08-22 | G | 2018-07-11 | 2018-07-23 | 2019-01-04 | 2019-01-04 | G | [35 empty] | 2023-01-10 |  | 2023-01-10 |  | G | 2023-01-10 |  | 2023-05-03 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.073535
1960 | 106188 | NORTH ES - SIDEWALKS | 0004 | Urban | Facilities for Pedestrians and Bicycles | Locally | Colonial Heights | CHESTERFIELD | Richmond | Tri-Cities:Colonial Heights | Local Assistance Division | Brian J Lokker | Brian.Lokker@VDOT.Virginia.gov | (804) 524-6010 | Evan Austin | Evan.Austin@vdot.virginia.gov | (804) 609-5384 | Keith A Chistolm | chisolmk@colonialheightsva.gov | (804) 520-9215 | 0 |  | 0 | FY2024 | 769500 | 799500 | ACTIVITY DATES SET | R | Start Purchasing Right-of-Way milestone finished 15 days late | Y | Project estimate is less than $5M and is up to 20% over budget | 2014-10-01 | 2014-10-01 | 2014-11-01 | 2014-11-17 | R | 2014-10-01 | 2014-12-09 | 2014-10-01 | 2014-12-09 | R | 2014-12-10 | 2018-11-05 | 2018-12-31 | 2020-10-21 | R | [5 empty] | 2020-10-22 | 2020-10-22 | 2020-11-16 | 2020-11-16 | G | 2020-11-17 | 2020-11-17 | 2021-01-19 | 2021-02-03 | R | 2021-07-16 |  | 2022-04-29 |  | G | 2021-01-20 |  | 2021-07-15 |  | G | 2023-01-23 |  | 2023-04-24 |  | G | [5 empty] | 2023-05-01 |  | 2023-05-01 |  | G | 2023-05-02 |  | 2023-10-30 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.14911
1961 | 107035 | George Washington Highway Corridor Improvements | 0017 | Urban | Safety | Locally | Portsmouth | NORFOLK | Hampton Roads | Hampton Roads:Portsmouth | Infrastructure Investment Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Marci Thompson | Marci.Thompson@vdot.virginia.gov | (757) 956-3093 | James E. Wright, P.E. | wrightj@portsmouthva.gov | (757) 393-8592 | 0 |  | 0 | FY2025 | 5950000 | 5950000 | NO DATES SET YET | G | Agreement with Locality milestone is 47 days ahead of the expected completion date | G | Project is on budget | 2021-01-13 |  | 2021-04-09 |  | G | 2021-04-12 |  | 2021-04-23 |  | G | 2021-04-26 |  | 2022-04-26 |  | G | [10 empty] | 2023-04-28 |  | 2023-05-18 |  | G | [5 empty] | 2023-06-12 |  | 2024-03-25 |  | G | [10 empty] | 2024-04-10 |  | 2024-06-05 |  | G | 2024-06-06 |  | 2024-11-26 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.22198
1962 | 107154 | ORANGE TRANSPORTATION CENTER - SIDEWALKS - PHASE 4 |  | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Orange | LOUISA | Culpeper | NonMPO:NonMPO | Local Assistance Division | Dewitt D Sprinkel | Brent.Sprinkel@VDOT.Virginia.gov | (540) 829-7552 | John P Price | John.Price@VDOT.Virginia.gov | (540) 347-6371 | John Cooley, Town of Orange | townplanner@townoforangeva.org | (540) 672-6719 | 0 |  | 0 | FY2021 | 770000 | 1012325 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 29 days early | R | Project estimate is less than $5M and is 20% or more over budget | 2015-03-16 | 2015-03-16 | 2016-05-23 | 2016-05-23 | G | 2015-04-17 | 2015-04-17 | 2015-04-20 | 2015-04-20 | G | 2015-04-17 | 2015-04-17 | 2018-11-27 | 2018-11-26 | G | 2018-11-26 | 2018-11-26 | 2018-11-26 | 2018-11-26 | G | [5 empty] | 2019-04-09 | 2019-01-05 | 2019-08-14 | 2019-04-15 | G | [5 empty] | 2019-08-15 | 2019-01-15 | 2020-01-10 | 2019-04-01 | G | [10 empty] | 2020-02-12 | 2019-08-07 | 2020-06-04 | 2019-09-27 | G | 2020-06-05 | 2020-05-22 | 2020-08-07 | 2020-07-09 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.27374
1963 | 108905 | #HB2.FY17 Lila Dr / Rte 115 Intersection Safety Improvements | 0115 | Primary | Reconstruction w/o Added Capacity | VDOT | Roanoke County | SALEM | Salem | Roanoke:Roanoke County | Infrastructure Investment Division | Ashley Smith | Ashley.Smith@vdot.virginia.gov | (540) 387-5312 | Ashley Smith | Ashley.Smith@vdot.virginia.gov | (540) 387-5312 | David Holladay | dholladay@roanokecountyva.gov | (540) 772-2080 | 1 | 2017 | 0 | FY2020 | 1269396 | 1269396 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 61 days early | G | Project is on budget | [5 empty] | 2016-08-17 | 2016-08-17 | 2016-08-25 | 2016-08-25 | G | 2016-08-23 | 2016-08-23 | 2017-07-26 | 2017-07-26 | G | [5 empty] | 2018-05-09 | 2018-02-16 | 2018-05-22 | 2018-02-16 | G | 2019-02-12 | 2018-06-21 | 2019-02-26 | 2018-08-07 | G | 2019-07-19 | 2019-03-03 | 2019-09-13 | 2019-04-26 | G | 2019-03-14 | 2018-10-18 | 2019-09-16 | 2020-02-28 | R | 2018-10-02 | 2018-05-10 | 2019-10-02 | 2018-05-10 | G | [5 empty] | 2019-12-10 | 2019-12-17 | 2019-12-10 | 2019-12-17 | R | 2020-02-04 | 2020-02-27 | 2020-04-28 | 2020-02-27 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.13294
1964 | 109570 | Orange Avenue/ Hollins Road Signal Upgrade - City of Roanoke | 0460 | Primary | Safety | VDOT | Roanoke | SALEM | Salem | Roanoke:Roanoke City | Infrastructure Investment Division | Cheryl B Becker | Cheryl.Becker@vdot.virginia.gov | (540) 492-2531 | Jeffrey A Echols | Jeff.Echols@VDOT.Virginia.gov | (540) 375-3595 | Mark Jamison |  |  | 0 |  | 0 | FY2020 | 545000 | 551533 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 6 days early | Y | Project estimate is less than $5M and is up to 20% over budget | [5 empty] | 2016-07-12 | 2016-07-12 | 2016-07-13 | 2016-07-13 | G | 2018-01-08 | 2018-01-08 | 2018-04-18 | 2018-04-11 | G | [5 empty] | 2018-04-17 | 2018-04-17 | 2018-04-17 | 2018-04-17 | G | [25 empty] | 2019-08-30 | 2019-03-12 | 2019-09-10 | 2019-03-12 | G | 2019-10-25 | 2020-02-27 | 2020-03-04 | 2020-02-27 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | WORK/TASK ORDER | 1 | 1 | 0.25703
1965 | 109920 | I-81 Median Guardrail - Smyth Co. | 0081 | Interstate | Safety | VDOT | Smyth County | ABINGDON | Bristol | NonMPO:NonMPO | Infrastructure Investment Division | Jeffrey Buchanan | Jeff.Buchanan@vdot.virginia.gov | (276) 415-3440 | Chase R Buchanan | Chase.Buchanan@VDOT.Virginia.gov | (276) 696-3251 |  |  |  | 0 |  | 0 | FY2020 | 1765000 | 1276443 | CONSTRUCTION COMPLETED | R | Start Delivery milestone finished 29 days late | G | Project is on budget | [5 empty] | 2017-08-01 | 2017-08-01 | 2017-08-14 | 2018-05-21 | R | 2017-08-15 | 2017-08-09 | 2018-04-11 | 2019-04-17 | R | [5 empty] | 2019-06-03 | 2019-06-03 | 2019-07-15 | 2019-07-15 | G | [5 empty] | 2019-05-10 | 2019-11-01 | 2019-05-10 | 2019-11-01 | R | [15 empty] | 2019-11-12 | 2019-12-10 | 2019-11-12 | 2019-12-10 | R | 2020-01-07 | 2020-02-27 | 2020-01-29 | 2020-02-27 | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.078904
1966 | 110801 | Chesapeake Signal System - Phase 4 |  | Urban | Traffic Management/Engineering | Locally | Chesapeake | NORFOLK | Hampton Roads | Hampton Roads:Chesapeake | Infrastructure Investment Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Johndel A Alcaide | John.Alcaide@vdot.virginia.gov | (757) 956-3098 | Steve Froncillo, PE | sfroncillo@cityofchesapeake.net | (757) 382-6002 | 0 |  | 0 | FY2025 | 500000 | 500000 | NO DATES SET YET | G | Agreement with Locality milestone is 677 days ahead of the expected completion date | Y | Estimate not current | 2022-10-03 |  | 2022-12-30 |  | G | 2023-01-03 |  | 2023-01-18 |  | G | 2023-01-19 |  | 2024-01-19 |  | G | [35 empty] | 2024-11-25 |  | 2024-12-24 |  | G | 2024-12-26 |  | 2025-04-01 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.29903
1967 | 111368 | #SMART18 - Intersection Rte 609/Rte 683 Safety Improvements | 0609 | Secondary | Safety | VDOT | Henry County | MARTINSVILLE | Salem | NonMPO:NonMPO | Infrastructure Investment Division | Alex H Price | Alex.Price@VDOT.Virginia.gov | (540) 378-5053 | David M Kiser | David.Kiser@VDOT.Virginia.gov | (276) 627-1501 | Lee Clark | leclark@co.henry.va.us | (276) 634-4620 | 1 | 2018 | 0 | FY2020 | 430877 | 430877 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 135 days early | G | Project is on budget | [5 empty] | 2017-07-03 | 2017-06-22 | 2017-07-17 | 2017-06-27 | G | 2017-07-18 | 2017-07-18 | 2017-11-08 | 2017-11-01 | G | [5 empty] | 2018-05-30 | 2018-05-29 | 2018-06-12 | 2018-11-27 | R | 2018-12-21 | 2018-12-20 | 2019-01-07 | 2018-12-20 | G | 2019-02-22 | 2018-12-27 | 2019-05-16 | 2018-12-27 | G | 2019-01-25 | 2018-12-27 | 2019-04-19 | 2019-01-30 | G | 2018-08-17 | 2018-07-23 | 2019-01-14 | 2018-07-23 | G | [5 empty] | 2019-06-11 | 2019-06-10 | 2019-06-14 | 2019-06-11 | G | 2019-07-31 | 2019-06-11 | 2019-10-24 | 2019-06-11 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | STATE FORCES/HIRED EQUIPMENT | 1 | 0 | 0.070188
1968 | 111471 | #SMART18 - ROUTE 123 AND ROUTE 243 SIGNAL UPGRADES | 0123 | Urban | Traffic Management/Engineering | Locally | Vienna | FAIRFAX | Northern Virginia | Northern Virginia:Vienna | Infrastructure Investment Division | Amir Salahshoor | A.Salahshoor@VDOT.Virginia.gov | (703) 259-1957 | Saif-Ur Qargha | Saif.Qargha@vdot.virginia.gov | (703) 259-3223 | Michael Gallagher | michael.gallagher@viennava.gov | (703) 255-6389 | 1 | 2018 | 0 | FY2024 | 2092110 | 2507917 | ACTIVITY DATES SET | G | Determine Requirements milestone finished on-time | Y | Project estimate is less than $5M and is up to 20% over budget | 2017-07-05 | 2017-07-05 | 2018-02-05 | 2017-08-21 | G | 2017-12-01 | 2017-08-22 | 2017-12-01 | 2017-08-31 | G | 2017-12-04 | 2017-09-01 | 2018-12-27 | 2018-12-27 | G | [10 empty] | 2020-01-13 | 2020-01-13 | 2021-12-07 |  | G | [5 empty] | 2021-12-09 |  | 2022-07-15 |  | G | [10 empty] | 2022-07-25 |  | 2023-01-31 |  | G | 2023-02-01 |  | 2023-07-31 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.27345
1969 | 111543 | LEESBURG PRIMARY EXTENSION PAVING FY18 - ROUTE 7 | 0007 | Urban | Resurfacing | Locally | Leesburg | LEESBURG | Northern Virginia | Northern Virginia:Leesburg | Local Assistance Division | Amir Salahshoor | A.Salahshoor@VDOT.Virginia.gov | (703) 259-1957 | Rita Hockman | Rita.Hockman@vdot.virginia.gov | (804) 824-7421 | TBD |  |  | 0 |  | 0 | FY2019 |  |  | WAITING FINANCIAL CLOSURE | R | Determine Requirements milestone finished 148 days late | R | Critical information missing | 2017-07-03 | 2017-07-03 | 2017-10-25 | 2017-08-30 | G | [5 empty] | 2017-07-03 | 2017-11-09 | 2017-07-17 | 2017-12-12 | R | [35 empty] | 2017-12-13 | 2016-10-13 | 2018-06-29 | 2016-10-13 | G | 2018-07-02 | 2017-05-13 | 2018-08-10 | 2017-05-15 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.30125
1970 | 106689 | #HB2.FY17 I-64 CAPACITY IMPROVEMENTS - SEGMENT III | 0064 | Interstate | Reconstruction w/ Added Capacity | VDOT | Hampton Roads District-wide | WILLIAMSBURG | Hampton Roads | Hampton Roads:Hampton Roads District-wide | Infrastructure Investment Division | Janet M Hedrick | Janet.Hedrick@VDOT.Virginia.gov | (757) 956-3071 | Janet M Hedrick | Janet.Hedrick@VDOT.Virginia.gov | (757) 956-3071 |  |  |  | 1 | 2017 | 0 | FY2018 | 166376067 | 166376067 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 42 days early | G | Project is on budget | [5 empty] | 2016-03-01 | 2016-03-01 | 2016-03-01 | 2016-03-01 | G | 2016-03-01 | 2016-03-01 | 2017-03-21 | 2017-03-21 | G | [5 empty] | 2017-06-15 | 2017-06-14 | 2017-07-17 | 2017-06-14 | G | 2017-07-19 | 2017-06-21 | 2017-07-19 | 2017-06-21 | G | 2017-08-16 | 2017-04-25 | 2017-08-16 | 2017-04-25 | G | 2017-10-11 | 2017-06-21 | 2017-10-11 | 2017-06-21 | G | [10 empty] | 2017-07-19 | 2017-06-21 | 2017-07-19 | 2017-06-21 | G | 2017-12-08 | 2017-12-06 | 2018-01-17 | 2017-12-06 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | DESIGN BUILD/PPTA | 1 | 0 | 0.083414
1971 | 107055 | Route 11 & 117 Roanoke Co. - Pedestrian Safety Improvements | 9999 | Primary | Safety | VDOT | Roanoke County | SALEM | Salem | Roanoke:Roanoke County | Infrastructure Investment Division | Bernard S Grinnell | Sean.Grinnell@VDOT.Virginia.gov | (540) 375-0148 | Timothy M Dowdy | Tim.Dowdy@VDOT.Virginia.gov | (540) 387-5332 |  |  |  | 0 |  | 0 | FY2022 | 1325400 | 1325400 | ADVERTISED | G | Solicit Bids milestone finished 245 days early | G | Project is on budget | [5 empty] | 2019-07-15 | 2016-07-26 | 2019-07-26 | 2016-09-08 | G | 2019-07-29 | 2016-09-12 | 2020-01-23 | 2019-07-19 | G | [5 empty] | 2019-10-23 | 2019-07-22 | 2019-11-05 | 2019-07-26 | G | 2020-06-24 | 2020-02-05 | 2020-07-08 | 2020-02-11 | G | 2021-04-16 |  | 2021-08-23 |  | G | 2020-07-24 | 2020-02-28 | 2021-04-15 | 2020-12-03 | G | [10 empty] | 2021-09-14 | 2021-01-12 | 2021-09-14 | 2021-01-12 | G | 2021-10-29 |  | 2022-01-31 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.12845
1972 | 107267 | Pruden Blvd/Prudence Road Intersection Improvements | 0000 | Urban | Reconstruction w/ Added Capacity | Locally | Suffolk | NORFOLK | Hampton Roads | Hampton Roads:Suffolk | Local Assistance Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Johndel A Alcaide | John.Alcaide@vdot.virginia.gov | (757) 956-3098 | Luke Drylie | ldrylie@suffolkva.us | (757) 514-7708 | 0 |  | 0 | FY2022 | 4767254 | 4767254 | ACTIVITY DATES SET | G | Start Purchasing Right-of-Way milestone finished 7 days early | Y | Estimate not current | 2017-08-19 | 2017-08-19 | 2017-09-21 | 2017-09-21 | G | 2018-01-05 | 2018-01-05 | 2018-01-11 | 2018-01-11 | G | 2018-01-16 | 2018-01-16 | 2019-03-28 | 2019-03-27 | G | [10 empty] | 2020-02-18 | 2020-02-18 | 2020-03-02 | 2020-02-24 | G | [20 empty] | 2021-05-03 |  | 2021-08-24 |  | G | 2021-08-25 |  | 2021-11-30 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.14837
1973 | 108976 | #SGR18VB - CN for RT 671 over Nottoway River | 0671 | Secondary | Bridge Replacement w/o Added Capacity | VDOT | Southampton County | FRANKLIN | Hampton Roads | NonMPO:NonMPO | Infrastructure Investment/Asset Management Division | Diane Geouge |  |  | Miranda S Kidd | miranda.kidd@vdot.virginia.gov | (757) 956-3342 |  |  |  | 0 |  | 1 | FY2020 | 6846663 | 7297305 | CONSTRUCTION STARTED | R | Start Delivery milestone finished 324 days late | Y | Project estimate is between $5M and $10M and is up to $1M over budget | [10 empty] | 2019-03-01 | 2019-01-24 | 2019-03-07 | 2019-01-24 | G | [35 empty] | 2019-07-09 | 2020-06-09 | 2019-07-09 | 2020-06-09 | R | 2019-10-28 | 2020-09-16 | 2019-10-28 | 2020-09-16 | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.14794
1975 | 110111 | #SGR17VB - BRIDGE REPLACEMENT RT 207 WB MATTAPONI ID 04398 | 0207 | Primary | Bridge Replacement w/o Added Capacity | VDOT | Caroline County | FREDERICKSBURG | Fredericksburg | NonMPO:NonMPO | Infrastructure Investment/Asset Management Division | Wesley Foor | Wesley.Foor@vdot.virginia.gov | (540) 604-1370 | Wesley Foor | Wesley.Foor@vdot.virginia.gov | (540) 604-1370 |  |  |  | 0 |  | 1 | FY2020 | 9060970 | 8060970 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 84 days early | G | Project is on budget | [5 empty] | 2016-11-01 | 2016-10-26 | 2016-11-15 | 2016-10-26 | G | 2016-11-16 | 2016-10-28 | 2017-12-28 | 2017-08-04 | G | [5 empty] | 2018-04-26 | 2018-03-01 | 2018-05-09 | 2018-03-06 | G | 2018-12-27 | 2018-11-30 | 2019-01-10 | 2018-11-30 | G | 2019-01-30 | 2018-10-18 | 2019-08-02 | 2019-07-31 | G | 2020-05-07 | 2019-01-17 | 2020-11-10 | 2019-01-17 | G | 2018-09-04 | 2018-09-04 | 2019-05-10 | 2019-05-03 | G | [5 empty] | 2019-08-13 | 2019-08-13 | 2019-08-13 | 2019-08-13 | G | 2019-11-08 | 2019-10-17 | 2020-01-09 | 2019-10-17 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.069895
1976 | 111313 | #SMART18 - RTE 501 - INTERSECTION IMPROVEMENTS AT RTE 628 | 0501 | Primary | Safety | VDOT | Halifax County | HALIFAX | Lynchburg | NonMPO:NonMPO | Infrastructure Investment Division | Brian J Casto | Brian.Casto@VDOT.Virginia.gov | (434) 856-8276 | Daniel J Brown | Daniel.Brown@VDOT.Virginia.gov | (434) 856-8265 |  |  |  | 1 | 2018 | 0 | FY2024 | 4192835 | 4192835 | ACTIVITY DATES SET | R | Determine Requirements milestone finished 112 days late | G | Project is on budget | [5 empty] | 2019-07-15 | 2019-06-25 | 2019-07-26 | 2019-07-03 | G | 2019-07-29 | 2019-07-05 | 2020-04-17 | 2020-08-07 | R | [5 empty] | 2021-07-26 |  | 2021-08-06 |  | G | 2022-07-28 |  | 2022-08-10 |  | G | 2023-08-15 |  | 2024-03-11 |  | G | 2022-08-26 |  | 2023-08-14 |  | G | [10 empty] | 2023-10-10 |  | 2023-10-10 |  | G | 2023-11-29 |  | 2024-04-09 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.081345
1977 | 111465 | #SMART18 - I-95/I-64 Overlap: Emergency Pull-Offs | 0095 | Interstate | Safety | VDOT | Richmond | ASHLAND | Richmond | Richmond:Richmond | Infrastructure Investment Division | Ronald Svejkovsky |  |  | Anthony S Haverly | Anthony.Haverly@vdot.virginia.gov | (804) 609-5225 |  |  |  | 1 | 2018 | 0 | FY2021 | 7665612 | 2746465 | AWARDED | G | Start Delivery milestone finished 141 days early | G | Project is on budget | [5 empty] | 2017-07-03 | 2017-06-26 | 2017-07-17 | 2017-07-07 | G | 2017-07-18 | 2017-07-10 | 2018-04-11 | 2018-04-04 | G | [5 empty] | 2018-08-22 | 2018-09-12 | 2018-10-09 | 2018-10-03 | G | 2019-06-10 | 2019-06-26 | 2019-07-08 | 2019-07-10 | R | 2020-06-18 | 2019-12-05 | 2020-06-18 | 2019-12-05 | G | 2019-07-24 | 2019-12-04 | 2020-07-24 | 2020-07-23 | G | 2018-12-11 | 2018-09-07 | 2019-11-25 | 2018-09-07 | G | [5 empty] | 2020-10-13 | 2020-10-06 | 2020-12-08 | 2020-10-06 | G | 2021-02-25 | 2020-12-15 | 2021-05-05 | 2020-12-15 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.072638
1978 | 111534 | CITY OF FAIRFAX PRIMARY EXTENSION PAVING FY18 - RTE 29SB | 0029 | Urban | Resurfacing | Locally | Fairfax | FAIRFAX | Northern Virginia | Northern Virginia:Fairfax | Local Assistance Division | Amir Salahshoor | A.Salahshoor@VDOT.Virginia.gov | (703) 259-1957 | Rita Hockman | Rita.Hockman@vdot.virginia.gov | (804) 824-7421 | Wendy Sanford | wendy.sanford@fairfaxva.gov | (703) 385-7889 | 0 |  | 0 | FY2019 | 109520 | 109520 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 140 days early | G | Project is on budget | 2017-07-03 | 2017-07-03 | 2017-10-25 | 2017-07-28 | G | [5 empty] | 2017-07-03 | 2017-11-09 | 2017-07-17 | 2017-12-12 | R | [35 empty] | 2017-12-13 | 2017-12-13 | 2018-06-29 | 2018-03-15 | G | 2018-07-02 | 2018-03-23 | 2018-08-10 | 2018-03-23 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.17514
1979 | 111648 | #SMART18 - INT. IMPROVEMENTS AT FROST AVE. & BROADVIEW AVE. | 0017 | Urban | Safety | VDOT | Warrenton | WARRENTON | Culpeper | Northern Virginia:Warrenton | Infrastructure Investment Division | Gregory J Cooley | Gregory.Cooley@vdot.virginia.gov | (434) 906-7979 | James D Cubbage | David.Cubbage@VDOT.Virginia.gov | (540) 727-7129 |  |  |  | 1 | 2018 | 0 | FY2022 | 3730303 | 3730303 | ACTIVITY DATES SET | R | Start Purchasing Right-of-Way milestone is 192 days past the expected completion date | G | Project is on budget | [5 empty] | 2017-11-01 | 2017-09-08 | 2017-11-15 | 2017-09-21 | G | 2017-11-16 | 2017-09-22 | 2018-08-07 | 2019-09-13 | R | [5 empty] | 2019-10-22 | 2019-10-11 | 2020-01-22 | 2020-01-21 | G | 2020-07-28 |  | 2020-08-13 |  | R | 2021-06-07 |  | 2021-12-13 |  | G | 2020-08-31 |  | 2021-08-31 |  | G | [10 empty] | 2021-12-14 |  | 2021-12-14 |  | G | 2022-03-31 |  | 2022-05-25 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.14027
1980 | 111694 | Construct Roundabout at Route 40 and Route 750 | 0040 | Primary | Safety | VDOT | Nottoway County | PETERSBURG | Richmond | NonMPO:NonMPO | Infrastructure Investment Division | Dianna M Bryant | Dianna.Bryant@VDOT.Virginia.gov | (804) 863-4004 | Dianna M Bryant | Dianna.Bryant@VDOT.Virginia.gov | (804) 863-4004 |  |  |  | 0 |  | 0 | FY2027 | 1700000 | 1700000 | NO DATES SET YET | G | Start Development milestone is 442 days ahead of the expected completion date | Y | Estimate not current | [5 empty] | 2022-04-26 |  | 2022-05-09 |  | G | 2022-05-10 |  | 2023-04-07 |  | G | [5 empty] | 2024-02-13 |  | 2024-02-27 |  | G | 2025-06-02 |  | 2025-06-13 |  | G | 2025-11-06 |  | 2026-05-18 |  | G | 2025-07-01 |  | 2026-01-08 |  | G | 2024-11-14 |  | 2025-05-23 |  | G | [5 empty] | 2026-06-09 |  | 2026-06-09 |  | G | 2026-09-11 |  | 2026-11-06 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.055092
1981 | 112500 | Install High Tension Cable Guardrail in Median | 0264 | Interstate | Safety | VDOT | Virginia Beach | NORFOLK | Hampton Roads | Hampton Roads:Virginia Beach | Infrastructure Investment Division | SH Stephenson |  |  | John K Arms | John.Arms@vdot.virginia.gov | (757) 995-5156 |  |  |  | 0 |  | 0 | FY2019 | 443590 | 443590 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 37 days early | G | Project is on budget | [10 empty] | 2018-01-10 | 2018-01-10 | 2018-01-25 | 2018-04-23 | R | [35 empty] | 2018-08-14 | 2018-08-14 | 2018-08-14 | 2018-08-14 | G | 2018-09-28 | 2018-10-22 | 2018-11-28 | 2018-10-22 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.10652
1982 | 113321 | Main Street Improvements - Phase 2B | 0040 | Urban | Reconstruction w/o Added Capacity | Locally | Blackstone | PETERSBURG | Richmond | NonMPO:NonMPO | Local Assistance Division | James Shepherd | James.Shepherd@vdot.virginia.gov | (804) 609-5305 | James Shepherd | James.Shepherd@vdot.virginia.gov | (804) 609-5305 | Philip Vannoorbeck | philip@townofblackstoneva.com | (434) 292-7251 | 0 |  | 0 | FY2021 | 920603 | 1188100 | ADVERTISED | G | Solicit Bids milestone finished 23 days early | R | Project estimate is less than $5M and is 20% or more over budget | 2018-07-02 | 2018-08-29 | 2018-09-25 | 2018-09-07 | G | 2018-09-26 | 2018-10-18 | 2018-11-07 | 2018-10-23 | G | 2018-11-08 | 2018-10-24 | 2019-05-20 | 2019-05-14 | G | [10 empty] | 2019-11-13 | 2019-11-14 | 2019-12-11 | 2019-12-11 | G | [5 empty] | 2019-12-13 | 2019-12-13 | 2020-09-22 | 2020-10-13 | R | 2019-03-14 | 2020-09-17 | 2020-03-04 | 2020-10-16 | R | [5 empty] | 2020-10-08 | 2020-12-16 | 2021-01-29 | 2021-01-06 | G | 2021-02-01 |  | 2021-04-29 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.080194
1983 | 113777 | RTE 707 - RURAL RUSTIC RD (SURFACE TREAT NON-HARDSURFACE RD) | 0707 | Secondary | Reconstruction w/o Added Capacity | VDOT | Albemarle County | CHARLOTTESVILLE | Culpeper | Charlottesville:Albemarle County | Infrastructure Investment Division | Ken Connors |  |  | Harold L Jones | Harold.Jones@VDOT.virginia.gov | (434) 422-9378 |  |  |  | 0 |  | 0 | FY2023 | 110000 | 110000 | NO DATES SET YET | R | Start Development milestone is 130 days past the expected completion date | Y | Estimate not current | [5 empty] | 2020-10-01 |  | 2020-10-14 |  | R | 2020-10-15 |  | 2021-06-11 |  | G | [5 empty] | 2022-03-22 |  | 2022-05-02 |  | G | [5 empty] | 2022-08-16 |  | 2022-12-12 |  | G | [5 empty] | 2022-08-01 |  | 2022-11-01 |  | G | [5 empty] | 2023-01-10 |  | 2023-01-10 |  | G | 2023-03-06 |  | 2023-03-24 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | SAAP CONTRACT | 0 | 1 | 0.33439
1984 | 113822 | Frederick/Airline Neighborhood Pedestrian Improvements | 0017 | Urban | Facilities for Pedestrians and Bicycles | Locally | Portsmouth | NORFOLK | Hampton Roads | Hampton Roads:Portsmouth | Infrastructure Investment Division | Susan Wilson | Susan.Wilson@vdot.virginia.gov | (757) 956-3099 | Marci Thompson | Marci.Thompson@vdot.virginia.gov | (757) 956-3093 | James Wright, P.E. | wrightj@portsmouthva.gov | (757) 393-8592 | 0 |  | 0 | FY2023 | 810500 | 810500 | NO DATES SET YET | G | Agreement with Locality milestone is 221 days ahead of the expected completion date | G | Project is on budget | 2021-07-01 |  | 2021-09-30 |  | G | 2021-10-01 |  | 2021-10-14 |  | G | 2021-10-15 |  | 2022-04-27 |  | G | [25 empty] | 2022-06-03 |  | 2023-02-09 |  | G | [5 empty] | 2023-03-10 |  | 2023-04-06 |  | G | 2023-06-26 |  | 2023-06-26 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.18472
1985 | 115127 | #SMART20 Rte. 340/522 SB/I-66 WB On-Ramp Ext | 0066 | Interstate | Reconstruction w/o Added Capacity | VDOT | Warren County | EDINBURG | Staunton | NonMPO:NonMPO | Infrastructure Investment Division | Randolph S Kiser | Randy.Kiser@VDOT.Virginia.gov | (540) 332-9092 | Ronald L Tabor | Ronald.Tabor@vdot.virginia.gov | (540) 332-7887 |  |  |  | 1 | 2020 | 0 | FY2026 | 518664 | 518664 | NO DATES SET YET | G | Start Development milestone is 904 days ahead of the expected completion date | G | Project is on budget | [5 empty] | 2023-08-01 |  | 2023-08-14 |  | G | 2023-08-15 |  | 2024-04-10 |  | G | [5 empty] | 2024-12-16 |  | 2025-01-30 |  | G | [5 empty] | 2025-05-15 |  | 2025-09-08 |  | G | [5 empty] | 2025-04-30 |  | 2025-07-31 |  | G | [5 empty] | 2025-09-09 |  | 2025-09-09 |  | G | 2025-12-03 |  | 2025-12-03 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.063002
1986 | 115512 | #SMART20 Longhill Road Shared Use Path |  | Urban | Facilities for Pedestrians and Bicycles | VDOT | James City County | WILLIAMSBURG | Hampton Roads | Hampton Roads:James City County | Infrastructure Investment Division | Kenneth Wynne |  |  | John G Harman | JohnG.Harman@vdot.virginia.gov | (757) 956-3269 | Tammy Rosario | tammy.rosario@jamescitycountyva.gov | (757) 253-6688 | 1 | 2020 | 0 | FY2024 | 4400000 | 4400000 | NO DATES SET YET-PE OPEN | R | Determine Requirements milestone is 79 days past the expected completion date | G | Project is on budget | [5 empty] | 2019-09-26 | 2019-09-26 | 2019-12-02 | 2019-12-02 | G | 2019-12-03 | 2019-12-03 | 2020-12-04 |  | R | [5 empty] | 2021-10-07 |  | 2021-10-21 |  | G | 2023-02-02 |  | 2023-02-15 |  | G | 2023-07-11 |  | 2024-01-19 |  | G | 2023-03-06 |  | 2023-09-06 |  | G | 2022-07-18 |  | 2023-01-26 |  | G | [5 empty] | 2024-02-13 |  | 2024-02-13 |  | G | 2024-05-03 |  | 2024-05-03 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 1 | 0.20119
1987 | 115715 | #SMART20 WOODROW WILSON COMPLEX SHORT TERM ACCESS | 0358 | Primary | Reconstruction w/ Added Capacity | VDOT | Augusta County | HARRISONBURG | Staunton | SAW:Augusta County | Infrastructure Investment Division | John-Allen L Ennis | JohnAllen.Ennis@VDOT.Virginia.gov | (540) 332-9118 | Anthony E Pelina | Anthony.Pelina@vdot.virginia.gov | (540) 332-9575 |  |  |  | 1 | 2020 | 0 | FY2024 | 4294032 | 4294032 | NO DATES SET YET-PE OPEN | R | Determine Requirements milestone is 145 days past the expected completion date | G | Project is on budget | [5 empty] | 2019-10-17 | 2019-10-17 | 2019-10-31 | 2019-10-31 | G | 2019-11-01 |  | 2020-09-29 |  | R | [5 empty] | 2021-08-05 |  | 2021-08-18 |  | G | 2023-03-13 |  | 2023-03-24 |  | G | 2023-08-16 |  | 2024-02-27 |  | G | 2023-04-11 |  | 2023-10-12 |  | G | 2022-08-23 |  | 2023-03-06 |  | G | [5 empty] | 2024-03-12 |  | 2024-03-12 |  | G | 2024-05-31 |  | 2024-05-31 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.092121
1988 | 115732 | #SGR20LP - City of NewpoRT News 690 J Clyde Morris Blvd | 0312 | Urban | Restoration and Rehabilitation | Locally | Newport News | WILLIAMSBURG | Hampton Roads | Hampton Roads:Newport News | Infrastructure Investment/Asset Management Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Chessica Villaflores | Chessica.Villaflores@vdot.virginia.gov | (757) 956-3094 | Bridjette Parker | bjparker@nnva.gov | (757) 926-8314 | 0 |  | 1 | FY2020 | 433379 | 433279 | AWARDED | G | Start Delivery milestone finished 65 days early | G | Project is on budget | 2019-10-31 | 2019-11-18 | 2020-01-31 | 2019-11-19 | G | [5 empty] | 2019-10-31 | 2019-10-31 | 2019-11-14 | 2019-11-14 | G | [35 empty] | 2020-05-06 | 2020-02-20 | 2020-06-03 | 2020-04-14 | G | 2020-06-25 | 2020-04-14 | 2020-06-25 | 2020-04-21 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.1341
1989 | 115823 | Brunswick Rte. 706 Rural Rustic | 0706 | Secondary | Resurfacing | VDOT | Brunswick County | SOUTH HILL | Richmond | NonMPO:NonMPO | Infrastructure Investment/Asset Management Division | Todd E Wilson | Todd.Wilson@vdot.virginia.gov | (434) 774-2313 | Todd E Wilson | Todd.Wilson@vdot.virginia.gov | (434) 774-2313 | Charlotte Woolridge |  |  | 0 |  | 0 | FY2024 | 62000 | 62000 | NO DATES SET YET | G | Determine Requirements milestone is 803 days ahead of the expected completion date | G | Project is on budget | [10 empty] | 2023-05-01 |  | 2023-05-05 |  | G | [25 empty] | 2023-05-01 |  | 2023-11-02 |  | G | [5 empty] | 2023-12-12 |  | 2023-12-12 |  | G | 2024-03-07 |  | 2024-03-07 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 |  | 0 | 0 | 0.074981
1990 | 112481 | COLUMBIA PIKE & JOHN MARR DR /CHATELAIN RD TRAFFIC SIGNAL | 0244 | Primary | Safety | VDOT | Fairfax County | FAIRFAX | Northern Virginia | Northern Virginia:Fairfax County | Infrastructure Investment Division | Ivan M Horodyskyj | Ivan.Horodyskyj@VDOT.Virginia.gov | (703) 259-2330 | Anwar A Ansari | Anwar.Ansari@VDOT.Virginia.gov | (703) 334-0204 |  |  |  | 0 |  | 0 | FY2021 | 924818 | 699856 | ACTIVITY DATES SET | R | Solicit Bids milestone is 40 days past the expected completion date | G | Project is on budget | [5 empty] | 2018-10-01 | 2018-07-01 | 2018-10-12 | 2018-07-16 | G | 2018-10-16 | 2018-09-12 | 2019-09-12 | 2019-09-12 | G | [5 empty] | 2019-12-12 | 2019-12-03 | 2019-12-13 | 2019-12-05 | G | 2020-06-04 | 2020-04-20 | 2020-06-17 | 2020-06-12 | G | 2020-05-06 | 2019-10-18 | 2020-05-06 | 2019-10-18 | G | 2020-07-06 | 2020-07-10 | 2020-10-27 | 2021-01-15 | R | [10 empty] | 2021-01-12 |  | 2021-01-12 |  | R | 2021-03-08 |  | 2021-03-26 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | WORK/TASK ORDER | 0 | 0 | 0.051651
1991 | 113201 | Little Creek Rd/Shore Drive Intersection Improvements | 0060 | Urban | Reconstruction w/o Added Capacity | Locally | Norfolk | NORFOLK | Hampton Roads | Hampton Roads:Norfolk | Local Assistance Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Derrick Williams | Derrick.Williams@vdot.virginia.gov | (757) 956-3097 | Olga Beltsar, P. E. | Olga.beltsar@norfolk.gov | (757) 664-7336 | 0 |  | 0 | FY2022 | 1262800 | 1886036 | ACTIVITY DATES SET | Y | Solicit Bids milestone is 8 days ahead of the expected completion date and there is a risk of missing this milestone date | R | Project estimate is less than $5M and is 20% or more over budget | 2018-09-28 | 2018-09-28 | 2018-12-27 | 2018-10-02 | G | 2018-12-28 | 2018-09-19 | 2019-01-02 | 2018-10-02 | G | 2019-01-03 | 2018-10-03 | 2019-07-10 | 2019-10-04 | R | [25 empty] | 2019-11-05 | 2019-11-05 | 2020-06-26 | 2019-11-07 | G | [5 empty] | 2020-10-28 |  | 2021-03-01 |  | Y | 2021-05-18 |  | 2021-11-05 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.13201
1992 | 113542 | PEDESTRIAN CROSSINGS & SIGNAL SAFETY MODIFICATIONS | 9999 | Primary | Safety | VDOT | Fredericksburg District-wide |  | Fredericksburg | Fredericksburg:Fredericksburg District-wide | Infrastructure Investment Division | Robert W Alexander | Robert.Alexander@VDOT.Virginia.gov | (804) 609-5332 | Ronnie Hobson | Ron.Hobson@vdot.virginia.gov | (804) 840-5501 |  |  |  | 0 |  | 0 | FY2019 | 151017 | 151017 | CONSTRUCTION STARTED | G | Start Delivery milestone finished on-time | G | Project is on budget | [10 empty] | 2018-05-14 | 2018-05-14 | 2018-09-19 | 2018-06-20 | G | [35 empty] | 2018-06-26 | 2018-06-26 | 2018-07-02 | 2018-07-02 | G | 2018-07-03 | 2018-07-03 | 2018-07-16 | 2018-07-16 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | WORK/TASK ORDER | 1 | 0 | 0.067016
1993 | 113813 | Bus Transfer Center - Pedestrian Improvements @US360 SR161 | 9999 | Urban | Safety | Locally | Richmond | ASHLAND | Richmond | Richmond:Richmond | Local Assistance Division | Olena Fecek | Olena.Fecek@vdot.virginia.gov | (804) 524-6368 | Olena Fecek | Olena.Fecek@vdot.virginia.gov | (804) 524-6368 | Sandra Christian | Sandra.christian@richmondgov.com | (804) 646-3777 | 0 |  | 0 | FY2023 | 640341 | 640341 | NO DATES SET YET-PE OPEN | G | Start Development milestone finished 107 days early | G | Project is on budget | 2020-09-01 | 2019-02-19 | 2020-11-30 | 2019-07-10 | G | 2020-12-01 | 2020-07-22 | 2020-12-03 | 2020-08-18 | G | 2020-12-04 |  | 2021-06-11 |  | G | [25 empty] | 2021-07-20 |  | 2022-03-28 |  | G | [5 empty] | 2022-06-30 |  | 2022-07-28 |  | G | 2022-10-18 |  | 2022-10-18 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.17468
1994 | 114905 | GEORGE ST & PRINCESS ANNE ST INTERSECTION IMPROVEMENTS | 0001 | Urban | Safety | Locally | Fredericksburg | FREDERICKSBURG | Fredericksburg | Fredericksburg:Fredericksburg | Infrastructure Investment Division | Peter A Hedrich | Peter.Hedrich@vdot.virginia.gov | (540) 899-4540 | Anastasia Kapitan | Anastasia.Kapitan@vdot.virginia.gov | (540) 899-4292 | Erik Nelson |  |  | 0 |  | 0 | FY2026 | 351600 | 351600 | NO DATES SET YET | G | Agreement with Locality milestone is 976 days ahead of the expected completion date | Y | Estimate not current | 2023-08-01 |  | 2023-10-25 |  | G | 2023-10-26 |  | 2023-10-30 |  | G | 2023-10-31 |  | 2024-05-09 |  | G | [25 empty] | 2024-06-17 |  | 2025-02-24 |  | G | [5 empty] | 2025-05-29 |  | 2025-06-25 |  | G | 2025-09-15 |  | 2025-09-15 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.14586
1995 | 115481 | #SMART20-Hillman Hwy & Old Eleven Drive Int Imp (APP ID#4029 | 0609 | Urban | Reconstruction w/o Added Capacity | VDOT | Abingdon | ABINGDON | Bristol | Bristol:Abingdon | Infrastructure Investment Division | Dennis R Harris | Dennis.Harris@VDOT.Virginia.gov | (276) 696-3289 | Brandi Halloway | Brandi.Halloway@vdot.virginia.gov | (276) 696-3254 |  |  |  | 1 | 2020 | 0 | FY2024 | 668000 | 668000 | ACTIVITY DATES SET | G | Determine Requirements milestone finished on-time | G | Project is on budget | [5 empty] | 2020-03-06 | 2020-03-06 | 2020-03-19 | 2020-03-19 | G | 2020-03-20 | 2020-03-20 | 2020-10-06 | 2020-10-06 | G | [5 empty] | 2021-06-09 |  | 2021-06-22 |  | G | 2022-08-10 |  | 2022-08-23 |  | G | 2023-01-24 |  | 2023-07-27 |  | G | 2022-09-09 |  | 2023-03-22 |  | G | 2022-01-31 |  | 2023-06-08 |  | G | [5 empty] | 2023-08-08 |  | 2023-08-08 |  | G | 2023-10-30 |  | 2024-04-24 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.093237
1996 | 115632 | #SMART20 ROUTE 624 - EXPANDED TURN LANE FOR FLAT IRON ROAD | 0003 | Primary | Reconstruction w/ Added Capacity | VDOT | Westmoreland County | NORTHERN NECK | Fredericksburg | NonMPO:NonMPO | Infrastructure Investment Division | Catherine C Coffey | Catherine.Coffey@vdot.virginia.gov | (540) 899-4280 | Benjamin Ernst | Benjamin.Ernst@vdot.virginia.gov | (571) 585-0902 |  |  |  | 1 | 2020 | 0 | FY2021 | 1000000 | 815805 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 140 days early | G | Project is on budget | [5 empty] | 2019-09-03 | 2019-08-26 | 2019-09-30 | 2019-09-11 | G | 2019-10-01 | 2019-09-12 | 2020-05-22 | 2020-03-25 | G | [5 empty] | 2020-03-24 | 2020-03-24 | 2020-03-25 | 2020-03-24 | G | 2020-03-18 | 2020-03-18 | 2020-04-02 | 2020-04-02 | G | 2020-10-23 | 2020-06-29 | 2020-12-22 | 2020-06-29 | G | 2020-04-20 | 2020-04-13 | 2020-10-22 | 2020-06-25 | G | 2020-03-27 | 2020-03-27 | 2020-06-19 | 2020-04-15 | G | [5 empty] | 2021-01-12 | 2020-09-08 | 2021-01-12 | 2020-09-08 | G | 2021-04-06 | 2020-11-17 | 2021-04-06 | 2020-11-17 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.080344
1997 | 115727 | #SMART20 - ROUTE 360/619 INTERSECTION IMPROVEMENTS | 0360 | Primary | Safety | VDOT | Richmond County | NORTHERN NECK | Fredericksburg | NonMPO:NonMPO | Infrastructure Investment Division | Catherine C Coffey | Catherine.Coffey@vdot.virginia.gov | (540) 899-4280 | Anastasia Kapitan | Anastasia.Kapitan@vdot.virginia.gov | (540) 899-4292 |  |  |  | 1 | 2020 | 0 | FY2023 | 1300000 | 1300000 | ACTIVITY DATES SET | R | Engage Public milestone is 6 days past the expected completion date | G | Project is on budget | [5 empty] | 2019-09-03 | 2019-09-03 | 2019-09-30 | 2019-09-25 | G | 2019-10-01 | 2019-09-26 | 2020-04-03 | 2020-06-12 | R | [5 empty] | 2021-02-02 |  | 2021-02-15 |  | R | 2021-09-28 |  | 2021-10-26 |  | G | 2022-05-24 |  | 2022-11-30 |  | G | 2021-11-12 |  | 2022-05-23 |  | G | 2021-05-19 |  | 2021-11-23 |  | G | [5 empty] | 2022-12-13 |  | 2022-12-13 |  | G | 2023-04-04 |  | 2023-04-04 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.06232
1998 | 115784 | Meadowdale Blvd (Dalebrook Drive to Beulah Rd) Ped-Bike Imps | 0770 | Primary | Facilities for Pedestrians and Bicycles | Locally | Chesterfield County | CHESTERFIELD | Richmond | Richmond:Chesterfield County | Infrastructure Investment Division | Michael S Gray | Mike.Gray@vdot.virginia.gov | (804) 609-5347 | Michael S Gray | Mike.Gray@vdot.virginia.gov | (804) 609-5347 | TBD | Smithbk@chesterfield.gov | TBD | 0 |  | 0 | FY2026 | 3660000 | 3660000 | NO DATES SET YET | G | Agreement with Locality milestone is 285 days ahead of the expected completion date | G | Project is on budget | 2021-09-07 |  | 2021-12-03 |  | G | 2022-01-05 |  | 2022-01-20 |  | G | 2022-01-21 |  | 2022-07-26 |  | G | [10 empty] | 2023-07-28 |  | 2023-08-17 |  | G | 2024-08-29 |  | 2025-02-28 |  | G | 2023-08-28 |  | 2024-08-28 |  | G | 2024-08-29 |  | 2025-05-07 |  | G | [5 empty] | 2025-05-22 |  | 2025-07-03 |  | G | 2025-11-14 |  | 2025-11-14 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.13782
1999 | 115856 | ITTF FY20 Parking Demand Management System | 9999 | Interstate | Traffic Management/Engineering | VDOT | Fredericksburg District-wide |  | Fredericksburg | Fredericksburg:Fredericksburg District-wide | Infrastructure Investment Division | Catherine C Mcghee | Cathy.McGhee@VDOT.Virginia.gov | (434) 293-1973 | Teresa H Butler | Teresa.Butler@VDOT.Virginia.gov | (540) 229-3722 |  |  |  | 0 |  | 0 | FY2022 | 1950000 | 1950000 | NO DATES SET YET | G | Start Development milestone is 100 days ahead of the expected completion date | G | Project is on budget | [5 empty] | 2021-06-01 |  | 2021-06-01 |  | G | 2021-06-02 |  | 2021-09-09 |  | G | [5 empty] | 2021-09-22 |  | 2021-10-05 |  | G | [25 empty] | 2021-10-22 |  | 2021-10-28 |  | G | 2021-10-29 |  | 2021-11-04 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | WORK/TASK ORDER | 0 | 0 | 0.12134
2000 | 116725 | #I95 CIP - INSTALL ITS DEVICES, SOUTHERN REGION | 0095 | Interstate | Safety | VDOT | Richmond District-wide |  | Richmond | Richmond:Richmond District-wide | Infrastructure Investment/Asset Management Division | Adam S Brooks | Adam.Brooks@VDOT.Virginia.gov | (804) 609-5274 | Adam S Brooks | Adam.Brooks@VDOT.Virginia.gov | (804) 609-5274 | N\A |  |  | 0 |  | 0 | FY2022 | 5333671 | 5333671 | NO DATES SET YET-PE OPEN | G | Start Development milestone finished 398 days early | G | Project is on budget | [5 empty] | 2021-10-04 | 2020-09-01 | 2021-10-25 | 2020-09-22 | G | 2021-10-26 |  | 2022-02-09 |  | G | [5 empty] | 2022-02-23 |  | 2022-03-08 |  | G | [25 empty] | 2022-03-24 |  | 2022-03-30 |  | G | 2022-03-31 |  | 2022-04-06 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | WORK/TASK ORDER | 0 | 0 | 0.06773
2001 | 116859 | RIVERWALK PHASE 2 |  | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Bridgewater | HARRISONBURG | Staunton | Harrisonburg:Bridgewater | Local Assistance Division | Kimberly Cameron | Kim.Cameron@vdot.virginia.gov | (540) 332-7886 | Jeffery A Lineberry | Jeff.Lineberry@VDOT.Virginia.gov | (540) 332-2265 | Alex Wilmer | reuben.rhodes@vdot.virginia.gov | (540) 908-4212 | 0 |  | 0 | FY2024 | 271085 | 271085 | NO DATES SET YET | G | Agreement with Locality milestone is 57 days ahead of the expected completion date | G | Project is on budget | 2020-12-08 |  | 2021-04-19 |  | G | 2021-04-20 |  | 2021-05-10 |  | G | 2021-06-09 |  | 2021-09-30 |  | G | [25 empty] | 2022-09-27 |  | 2023-03-03 |  | G | [5 empty] | 2023-05-01 |  | 2023-05-26 |  | G | 2023-08-16 |  | 2023-08-16 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.27301
2002 | 19035 | JAHNKE ROAD - 2 LANE IMPROVEMENTS |  | Urban | Reconstruction w/o Added Capacity | Locally | Richmond | ASHLAND | Richmond | Richmond:Richmond | Infrastructure Investment Division | Brian J Lokker | Brian.Lokker@VDOT.Virginia.gov | (804) 524-6010 | Evan Austin | Evan.Austin@vdot.virginia.gov | (804) 609-5384 | Marvin Tart | Marvin.Tart@richmondgov.com | (804) 646-6396 | 0 |  | 0 | FY2019 | 500000 | 15079805 | ACTIVITY DATES SET | R | Solicit Bids milestone is 968 days past the expected completion date | R | Project estimate is less than $5M and is 20% or more over budget | [5 empty] | 2004-06-01 | 2004-05-20 | 2004-06-30 | 2004-05-28 | G | 2004-08-02 | 2004-05-26 | 2005-02-28 | 2005-02-28 | G | [10 empty] | 2011-07-22 | 2011-07-22 | 2011-07-29 | 2011-07-29 | G | [20 empty] | 2018-06-01 | 2018-06-04 | 2018-06-29 |  | R | 2018-07-30 |  | 2018-07-30 |  | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.14003
2003 | 80271 | #HB2.FY17 RTE 616 - RECONSTRUCTION - DAM TOWN ROAD (MR) | 0616 | Secondary | Reconstruction w/o Added Capacity | VDOT | Augusta County | HARRISONBURG | Staunton | NonMPO:NonMPO | Infrastructure Investment Division | Timothy Fitzgerald |  |  | Charles W Gardner | Charles.Gardner@VDOT.Virginia.gov | (540) 332-7893 |  |  |  | 1 | 2017 | 0 | FY2019 | 4083541 | 4083541 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 122 days early | G | Project is on budget | [5 empty] | 2008-07-01 | 2008-04-30 | 2008-07-01 | 2008-04-30 | G | 2009-08-01 | 2009-08-19 | 2010-03-31 | 2010-11-22 | R | [5 empty] | 2015-12-30 | 2015-12-30 | 2016-01-19 | 2016-01-19 | G | 2016-11-09 | 2016-11-09 | 2016-11-28 | 2016-11-28 | G | 2017-11-01 | 2017-11-01 | 2019-05-03 | 2018-04-12 | G | 2016-11-28 | 2016-11-28 | 2017-10-27 | 2017-10-27 | G | 2017-08-18 | 2017-08-18 | 2018-02-13 | 2018-02-13 | G | [5 empty] | 2018-04-13 | 2018-05-08 | 2018-07-10 | 2018-05-08 | G | 2018-09-04 | 2018-07-16 | 2018-11-15 | 2018-07-16 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.087082
2004 | 101276 | Construct Paved Shoulders - (Cook Rd) | 0704 | Secondary | Utilities | Locally | York County | WILLIAMSBURG | Hampton Roads | Hampton Roads:York County | Local Assistance Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Keisha Wilkins | Keisha.Wilkins@vdot.virginia.gov | (757) 956-3110 | Elizabeth Mertz-Guinn | Elizabeth.Mertz-Guinn@yorkcounty.gov | (757) 890-3785 | 0 |  | 0 | FY2019 | 435042 | 535219 | WAITING FINANCIAL CLOSURE | R | Start Delivery milestone finished 104 days late | Y | Project estimate is less than $5M and is up to 20% over budget | [5 empty] | 2011-08-01 | 2011-08-01 | 2011-08-01 | 2011-10-03 | R | 2013-04-11 | 2013-04-11 | 2018-04-10 | 2013-08-23 | G | [35 empty] | 2018-05-01 | 2018-05-09 | 2018-06-01 | 2018-09-18 | R | 2018-07-03 | 2018-09-20 | 2018-08-01 | 2018-11-13 | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.17679
2005 | 102887 | SIDEWALK CONST. FOR CITY OF CHARLOTTESVILLE (FY13 RS) |  | Urban | Safety and Education of Pedestrians /Bicyclisits | Locally | Charlottesville | CHARLOTTESVILLE | Culpeper | Charlottesville:Charlottesville | Local Assistance Division | Ken Connors |  |  | Michael D Barnes | MichaelD.Barnes@vdot.virginia.gov | (434) 422-9861 | Tim Motsch | motscht@charlottesville.gov | (434) 970-3182 | 0 |  | 0 | FY2019 | 1000000 | 1000000 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 36 days early | G | Project is on budget | 2012-07-05 | 2012-07-05 | 2012-12-28 | 2012-12-10 | G | 2013-02-01 | 2012-01-31 | 2013-03-01 | 2012-03-30 | G | 2015-01-30 | 2015-01-30 | 2017-01-31 | 2017-01-31 | G | [10 empty] | 2017-08-11 | 2017-08-11 | 2017-08-11 | 2017-08-11 | G | [20 empty] | 2018-07-01 | 2018-06-01 | 2018-07-01 | 2018-06-22 | G | 2018-07-30 | 2018-06-25 | 2018-07-31 | 2018-06-25 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.11263
2006 | 104354 | MULTI-USE TRAIL REHABILITATION AND PAVING- CITY OF FAIRFAX | 0000 | Urban | Facilities for Pedestrians and Bicycles | Locally | Fairfax | FAIRFAX | Northern Virginia | Northern Virginia:Fairfax | Infrastructure Investment Division | Terry Yates | Terry.Yates@vdot.virginia.gov | (703) 259-2118 | Rita Hockman | Rita.Hockman@vdot.virginia.gov | (804) 824-7421 | Cathy Salgado | cathy.salgado@fairfaxva.gov | (703) 385-7853 | 0 |  | 0 | FY2022 | 460000 | 395410 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 419 days early | G | Project is on budget | 2018-03-15 | 2018-03-15 | 2018-08-31 | 2018-06-18 | G | 2018-09-04 | 2018-07-20 | 2018-10-31 | 2018-07-26 | G | 2018-11-01 | 2018-11-01 | 2019-06-28 | 2019-06-28 | G | [35 empty] | 2020-05-27 | 2020-07-15 | 2020-12-23 | 2020-10-20 | G | 2021-03-25 | 2020-12-01 | 2022-01-24 | 2020-12-01 | G | Preliminary design and/or investigations are still underway | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.18863
2007 | 106246 | CANNON CREEK GREENWAY |  | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Richmond | ASHLAND | Richmond | Richmond:Richmond | Local Assistance Division | Brian J Lokker | Brian.Lokker@VDOT.Virginia.gov | (804) 524-6010 | Brian J Lokker | Brian.Lokker@VDOT.Virginia.gov | (804) 524-6010 | Lamont Benjamin | Thomas.Westbrook@richmondgov.com | (804) 646-3421 | 0 |  | 0 | FY2019 | 961000 | 1003632 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished on-time | Y | Project estimate is less than $5M and is up to 20% over budget | 2015-01-06 | 2015-04-20 | 2015-05-07 | 2015-04-27 | G | 2014-10-01 | 2015-08-10 | 2014-10-01 | 2016-06-24 | R | 2016-03-01 | 2017-12-13 | 2016-05-30 | 2018-01-12 | R | [35 empty] | 2018-10-01 | 2018-07-23 | 2018-10-29 | 2018-07-27 | G | 2018-10-30 | 2018-10-30 | 2018-10-30 | 2018-10-30 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.35502
2008 | 108866 | Sidewalk Replacement - Various Routes within Town Limits | 0000 | Urban | Facilities for Pedestrians and Bicycles | Locally | Christiansburg | CHRISTIANSBURG | Salem | New River Valley:Christiansburg | Local Assistance Division | Adam J Czesnowski | Adam.Czesnowski@vdot.virginia.gov | (540) 541-1216 | Adam J Czesnowski | Adam.Czesnowski@vdot.virginia.gov | (540) 541-1216 | Wayne Nelson |  |  | 0 |  | 0 | FY2019 | 106000 | 106000 | NO DATES SET YET | G | Start Delivery milestone finished 246 days early | G | Project is on budget | 2016-07-01 | 2016-07-01 | 2016-08-29 | 2016-08-29 | G | 2016-10-05 | 2016-10-05 | 2016-10-12 | 2016-10-12 | G | 2016-10-13 | 2016-10-13 | 2018-02-14 | 2018-02-02 | G | [35 empty] | 2018-07-17 | 2018-03-07 | 2018-07-30 | 2018-04-03 | G | 2018-07-31 | 2018-05-29 | 2019-01-30 | 2018-05-29 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.09539
2009 | 109381 | #HB2.FY17 Centerville Turnpike - Phase III |  | Urban | Reconstruction w/ Added Capacity | Locally | Virginia Beach | NORFOLK | Hampton Roads | Hampton Roads:Virginia Beach | Infrastructure Investment Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Marci Thompson | Marci.Thompson@vdot.virginia.gov | (757) 956-3093 | Dave Jarman, PE | djarman@vbgov.com | (757) 385-4144 | 1 | 2017 | 0 | FY2023 | 30095500 | 38046825 | NO DATES SET YET-PE OPEN | R | Determine Requirements milestone is 1285 days past the expected completion date | R | Project estimate is greater than $10M and is over budget by (a) 10% or more or (b) $5M or more | 2016-07-15 | 2016-07-15 | 2017-01-11 | 2017-03-20 | R | 2016-10-26 | 2016-10-26 | 2016-10-26 | 2016-10-26 | G | 2016-10-27 | 2016-10-27 | 2017-08-16 |  | R | [10 empty] | 2019-07-01 |  | 2019-07-01 |  | R | [5 empty] | 2019-07-03 |  | 2022-06-01 |  | G | [10 empty] | 2022-06-17 |  | 2022-08-01 |  | G | 2022-08-02 |  | 2022-09-30 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.24939
2010 | 116851 | GREEN CIRCLE TRAIL WIDENING |  | Miscellaneous | Reconstruction w/ Added Capacity | Locally | Winchester | EDINBURG | Staunton | Winchester:Winchester | Local Assistance Division | Kimberly Cameron | Kim.Cameron@vdot.virginia.gov | (540) 332-7886 | Kimberly Cameron | Kim.Cameron@vdot.virginia.gov | (540) 332-7886 | Perry Eisenach | perry.eisenach@winchesterva.gov | (540) 667-1815 | 0 |  | 0 | FY2025 | 1173500 | 1173500 | NO DATES SET YET | G | Agreement with Locality milestone is 107 days ahead of the expected completion date | G | Project is on budget | 2021-02-01 |  | 2021-06-08 |  | G | 2021-06-09 |  | 2021-06-29 |  | G | 2021-07-29 |  | 2021-11-22 |  | G | [10 empty] | 2023-03-20 |  | 2023-04-21 |  | G | [5 empty] | 2023-04-24 |  | 2023-09-20 |  | G | 2024-01-04 |  | 2024-06-04 |  | G | [5 empty] | 2024-08-01 |  | 2024-08-28 |  | G | 2024-11-19 |  | 2024-11-19 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.16776
2011 | 117571 | HAYCOCK RD PEDESTRIAN HAWK SIGNAL | 0703 | Secondary | Safety | Locally | Falls Church | FAIRFAX | Northern Virginia | Northern Virginia:Falls Church | Local Assistance Division | Amir Salahshoor | A.Salahshoor@VDOT.Virginia.gov | (703) 259-1957 | Christer P Carshult | Christer.Carshult@vdot.virginia.gov | (703) 259-1765 | Jeff Sikes | jsikes@fallschurchva.gov | (703) 248-5296 | 0 |  | 0 | FY2025 | 750000 | 750000 | NO DATES SET YET | Y | Agreement with Locality milestone is 5 days ahead of the expected completion date and there is a risk of missing this milestone date | G | Project is on budget | 2020-07-31 |  | 2021-02-26 |  | Y | 2021-03-01 |  | 2021-03-31 |  | G | 2021-11-01 |  | 2022-06-30 |  | G | [10 empty] | 2023-05-01 |  | 2023-05-31 |  | G | [5 empty] | 2023-06-02 |  | 2024-03-29 |  | G | 2021-11-10 |  | 2022-07-29 |  | G | [5 empty] | 2024-04-01 |  | 2024-08-30 |  | G | 2024-09-03 |  | 2025-01-31 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.39059
2012 | 77378 | EISENHOWER AVENUE WIDENING AND REMOVE TRAFFIC CIRCLE |  | Urban | Reconstruction w/ Added Capacity | Locally | Alexandria | FAIRFAX | Northern Virginia | Northern Virginia:Alexandria | Infrastructure Investment Division | Terry Yates | Terry.Yates@vdot.virginia.gov | (703) 259-2118 | Rita Hockman | Rita.Hockman@vdot.virginia.gov | (804) 824-7421 | Demond Frazier | Demond.Frazier@alexandriava.gov | (703) 746-4632 | 0 |  | 0 | FY2020 | 6500000 | 11560836 | CONSTRUCTION STARTED | R | Start Delivery milestone finished 101 days late | R | Project estimate is between $5M and $10M and is a $1M or more over budget | 2006-07-02 | 2006-07-02 | 2006-07-02 | 2006-07-02 | G | 2005-11-28 | 2006-09-11 | 2005-12-01 | 2006-09-12 | R | 2007-06-01 | 2007-05-17 | 2010-08-27 | 2011-02-15 | R | [10 empty] | 2012-09-21 | 2012-09-21 | 2012-09-21 | 2012-09-21 | G | [20 empty] | 2019-03-14 | 2019-06-17 | 2019-05-17 | 2019-08-23 | R | 2019-08-19 | 2019-08-26 | 2019-12-17 | 2020-03-27 | R | Delay due to changes in scope of work, project management, plan designs, or resolution of public comments | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.3658
2013 | 80272 | #HB2.FY17 RTE 610 - RECONSTRUCTION (SR) | 0610 | Secondary | Reconstruction w/o Added Capacity | VDOT | Augusta County | HARRISONBURG | Staunton | SAW:Augusta County | Infrastructure Investment Division | Lester Kodger |  |  | Michael S Fulcher | Michael.Fulcher@VDOT.Virginia.gov | (540) 332-2243 |  |  |  | 1 | 2017 | 0 | FY2018 | 4855016 | 5042037 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished on-time | Y | Project estimate is less than $5M and is up to 20% over budget | [5 empty] | 2011-04-01 | 2011-01-04 | 2011-04-01 | 2011-01-04 | G | 2011-04-15 | 2011-04-15 | 2012-10-31 | 2012-10-31 | G | [5 empty] | 2014-01-15 | 2014-01-15 | 2014-03-31 | 2014-03-31 | G | 2015-08-14 | 2015-08-14 | 2015-09-23 | 2015-09-23 | G | 2016-09-16 | 2016-09-16 | 2017-06-16 | 2017-06-16 | G | 2016-01-29 | 2016-01-29 | 2016-12-07 | 2016-12-07 | G | [10 empty] | 2017-05-09 | 2017-05-09 | 2017-05-09 | 2017-05-09 | G | 2017-07-11 | 2017-07-11 | 2017-07-11 | 2017-07-11 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.11111
2014 | 101379 | Bridge Replacement Rte 627 over Copper Ck (VA Str 6140) | 0627 | Secondary | Bridge Replacement w/ Added Capacity | VDOT | Scott County | WISE | Bristol | NonMPO:NonMPO | Infrastructure Investment Division | Gary Lester |  |  | James R Jones | jamesr.jones@vdot.virginia.gov | (276) 696-3257 |  |  |  | 0 |  | 0 | FY2019 | 2630000 | 2850617 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 42 days early | Y | Project estimate is less than $5M and is up to 20% over budget | [5 empty] | 2011-08-01 | 2011-10-24 | 2011-08-01 | 2011-10-24 | R | 2011-08-31 | 2011-08-31 | 2016-03-11 | 2016-04-19 | R | [5 empty] | 2016-06-21 | 2016-06-21 | 2016-06-22 | 2016-06-22 | G | 2016-11-03 | 2016-11-03 | 2016-11-16 | 2016-11-16 | G | 2017-05-01 | 2017-05-01 | 2017-07-27 | 2018-03-20 | R | 2016-12-28 | 2016-12-28 | 2017-04-10 | 2017-04-10 | G | 2017-03-17 | 2017-03-17 | 2017-12-12 | 2017-12-12 | G | [5 empty] | 2018-05-17 | 2018-06-12 | 2018-06-12 | 2018-06-12 | G | 2018-08-13 | 2018-08-13 | 2018-09-24 | 2018-08-13 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.084116
2015 | 104182 | #SGR19VB - Bridge (Fed 16958) RT 11 Over NF Shen River | 0011 | Primary | Bridge Replacement w/ Added Capacity | VDOT | Shenandoah County | EDINBURG | Staunton | NonMPO:NonMPO | Infrastructure Investment/Asset Management Division | Rex L Pearce | Rex.Pearce@vdot.virginia.gov | (540) 332-9104 | Anthony E Pelina | Anthony.Pelina@vdot.virginia.gov | (540) 332-9575 |  |  |  | 0 |  | 0 | FY2021 | 5144428 | 7872809 | ACTIVITY DATES SET | R | Start Purchasing Right-of-Way milestone is 515 days past the expected completion date | R | Project estimate is between $5M and $10M and is a $1M or more over budget | [5 empty] | 2015-04-15 | 2013-07-15 | 2015-04-15 | 2013-07-15 | G | 2013-07-15 | 2013-07-15 | 2015-01-09 | 2015-01-09 | G | [5 empty] | 2018-10-04 | 2019-08-02 | 2018-12-14 | 2019-10-08 | R | 2019-08-01 |  | 2019-09-25 |  | R | 2020-06-15 |  | 2020-09-15 |  | R | 2019-12-02 | 2020-10-05 | 2020-06-12 |  | R | 2019-09-05 | 2019-09-05 | 2020-06-10 | 2021-02-05 | R | [5 empty] | 2020-10-13 |  | 2020-10-13 |  | R | 2020-11-12 |  | 2021-01-06 |  | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.096529
2016 | 105108 | RTE 13 - REPLACE BRIDGE WITH BOX CULVERT (Fed. ID 13826) | 0013 | Primary | Bridge Replacement w/o Added Capacity | VDOT | Powhatan County | CHESTERFIELD | Richmond | NonMPO:NonMPO | Infrastructure Investment Division | Robert F Poutier | Robert.Poutier@vdot.virginia.gov | (804) 609-5368 | Jeremy B Cobb | Jeremy.Cobb@vdot.virginia.gov | (804) 586-2255 |  |  |  | 0 |  | 0 | FY2020 | 2050003 | 1885536 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 93 days early | G | Project is on budget | [5 empty] | 2014-12-15 | 2013-07-12 | 2014-12-15 | 2013-07-12 | G | 2015-01-14 | 2015-02-05 | 2017-01-17 | 2017-01-17 | G | [5 empty] | 2017-09-08 | 2017-09-08 | 2017-11-28 | 2017-11-28 | G | 2018-08-01 | 2018-05-24 | 2018-10-01 | 2018-07-24 | G | 2019-05-17 | 2019-02-11 | 2019-09-10 | 2019-08-23 | G | 2018-10-17 | 2018-09-13 | 2019-05-10 | 2019-02-23 | G | 2018-04-02 | 2018-04-02 | 2019-04-04 | 2018-04-02 | G | [5 empty] | 2019-09-10 | 2019-09-10 | 2019-09-10 | 2019-09-10 | G | 2019-11-18 | 2019-11-13 | 2020-02-14 | 2019-11-13 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.068039
2017 | 108745 | STRUCTURAL REHABILITATION OF ASPHALT CONCRETE - VAR. RTES. | 9999 | Secondary | Restoration and Rehabilitation | VDOT | Dickenson County | WISE | Bristol | NonMPO:NonMPO | Local Assistance Division | Allan D Sumpter | Allan.Sumpter@VDOT.virginia.gov | (276) 525-6461 | Brandon C Bennett | Brandon.Bennett@VDOT.Virginia.gov | (276) 321-6453 |  |  |  | 0 |  | 0 | FY2020 | 2300000 | 2361394 | CONSTRUCTION COMPLETED | R | Start Delivery milestone finished 196 days late | Y | Project estimate is less than $5M and is up to 20% over budget | [5 empty] | 2017-05-01 | 2017-05-01 | 2017-05-12 | 2017-05-12 | G | 2017-05-15 | 2017-05-15 | 2018-01-08 | 2017-06-12 | G | [5 empty] | 2018-09-12 | 2018-09-12 | 2018-10-24 | 2018-10-24 | G | [5 empty] | 2019-03-15 | 2019-02-14 | 2019-07-08 | 2019-06-07 | G | [15 empty] | 2019-08-13 | 2019-09-10 | 2019-08-13 | 2019-09-10 | R | 2019-10-03 | 2020-05-07 | 2019-10-24 | 2020-05-07 | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.19157
2018 | 109320 | #HB2.FY17 SB I95 Belvidere St Interchange Safety Improvement | 0095 | Interstate | Safety | VDOT | Richmond | ASHLAND | Richmond | Richmond:Richmond | Infrastructure Investment Division | Roy Soto | Roy.Soto@vdot.virginia.gov | (804) 609-5239 | Roy Soto | Roy.Soto@vdot.virginia.gov | (804) 609-5239 |  |  |  | 1 | 2017 | 0 | FY2022 | 10229243 | 10229243 | ACTIVITY DATES SET | R | Complete Purchasing Right-of-Way milestone is 26 days past the expected completion date | G | Project is on budget | [5 empty] | 2017-06-20 | 2017-06-26 | 2017-07-03 | 2017-07-07 | R | 2017-07-05 | 2017-07-10 | 2018-08-13 | 2018-01-31 | G | [5 empty] | 2019-02-04 | 2019-02-04 | 2019-05-29 | 2019-05-24 | G | 2020-06-23 | 2020-09-14 | 2020-07-07 | 2020-09-22 | R | 2021-02-25 |  | 2021-10-19 |  | G | 2020-07-16 | 2020-10-02 | 2021-01-26 |  | R | [10 empty] | 2021-11-09 |  | 2021-11-09 |  | G | 2022-02-28 |  | 2022-03-11 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.075671
2019 | 109602 | DUMFRIES ROAD SIDEWALK | 0234 | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Prince William County | MANASSAS | Northern Virginia | Northern Virginia:Prince William County | Local Assistance Division | Bud Siegel |  |  | Rita Hockman | Rita.Hockman@vdot.virginia.gov | (804) 824-7421 | Ludwik J. Kulczycki | lkulczycki@pwcgov.org | (703) 792-6347 | 0 |  | 0 | FY2021 | 985450 | 985450 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 476 days early | G | Project is on budget | 2016-10-03 | 2016-10-03 | 2017-01-12 | 2017-01-12 | G | 2017-01-03 | 2017-01-03 | 2017-02-06 | 2017-02-06 | G | 2017-08-21 | 2017-08-21 | 2018-12-31 | 2018-10-01 | G | 2018-10-02 | 2017-11-27 | 2019-01-31 | 2018-06-04 | G | [5 empty] | 2018-10-10 | 2018-10-10 | 2018-10-11 | 2018-10-11 | G | [5 empty] | 2018-10-01 | 2018-10-01 | 2018-10-11 | 2018-10-11 | G | [10 empty] | 2020-06-02 | 2019-08-02 | 2020-10-22 | 2019-08-29 | G | 2020-10-23 | 2019-08-05 | 2021-03-23 | 2019-12-03 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.41213
2020 | 110130 | RTE 635 JETER'S CHAPEL RD - RURAL RUSTIC FY14 SSYP | 0635 | Secondary | Resurfacing | VDOT | Bedford County | BEDFORD | Salem | NonMPO:NonMPO | Infrastructure Investment Division | Todd K Daniel | Todd.Daniel@VDOT.Virginia.gov | (540) 682-7000 | Jason L Patrick | Jason.Patrick@vdot.virginia.gov | (540) 381-7178 |  |  |  | 0 |  | 0 | FY2027 | 1241001 | 1241001 | NO DATES SET YET-PE OPEN | G | Start Development milestone finished 798 days early | G | Project is on budget | [5 empty] | 2022-07-04 | 2020-05-06 | 2022-07-15 | 2020-05-08 | G | 2022-07-18 | 2020-05-11 | 2023-05-30 |  | G | [5 empty] | 2024-03-20 |  | 2024-04-02 |  | G | 2025-06-18 |  | 2025-07-01 |  | G | 2025-11-19 |  | 2026-05-19 |  | G | 2025-07-17 |  | 2026-01-14 |  | G | 2024-12-12 |  | 2025-08-06 |  | G | [5 empty] | 2026-05-20 |  | 2026-05-20 |  | G | 2026-07-09 |  | 2026-07-29 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | SAAP CONTRACT | 0 | 0 | 0.12178
2021 | 110902 | #SMART18 - RTE 738/639 INTERSECTION SAFETY IMPROVEMENTS | 0639 | Secondary | Safety | VDOT | Caroline County | FREDERICKSBURG | Fredericksburg | NonMPO:NonMPO | Infrastructure Investment Division | Catherine C Coffey | Catherine.Coffey@vdot.virginia.gov | (540) 899-4280 | Khalil Minhas | Khalil.Minhas@vdot.virginia.gov | (540) 374-3369 |  |  |  | 1 | 2018 | 0 | FY2022 | 2110000 | 2110000 | ACTIVITY DATES SET | G | Complete Purchasing Right-of-Way milestone finished 29 days early | G | Project is on budget | [5 empty] | 2018-07-19 | 2018-06-12 | 2018-08-01 | 2018-06-25 | G | 2018-08-02 | 2018-06-26 | 2019-01-29 | 2018-11-26 | G | [5 empty] | 2019-07-22 | 2019-06-17 | 2019-08-02 | 2019-07-08 | G | 2020-03-25 | 2019-12-23 | 2020-04-21 | 2020-01-14 | G | 2021-01-13 | 2020-06-30 | 2021-09-15 |  | G | 2020-05-07 | 2020-04-03 | 2021-01-12 | 2020-12-14 | G | [10 empty] | 2021-10-12 |  | 2021-10-12 |  | G | 2022-01-24 |  | 2022-03-21 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.067451
2022 | 111401 | Holmes Run Trail Connector |  | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Alexandria | FAIRFAX | Northern Virginia | Northern Virginia:Alexandria | Local Assistance Division | Bud Siegel |  |  | Susie X Lue | Susie.Lue@vdot.virginia.gov | (703) 259-2918 | Alex Carroll | alexandria.carroll@alexandriava.gov | (703) 746-4408 | 0 |  | 0 | FY2026 | 3568279 | 3568279 | NO DATES SET YET-PE OPEN | G | Start Development milestone finished 723 days early | G | Project is on budget | 2017-09-26 | 2017-09-26 | 2020-12-29 | 2019-01-11 | G | 2020-12-30 | 2019-01-22 | 2021-01-22 | 2019-01-30 | G | 2021-11-08 |  | 2022-08-26 |  | G | 2023-12-13 |  | 2024-04-09 |  | G | [20 empty] | 2022-11-28 |  | 2023-05-19 |  | G | [5 empty] | 2025-01-30 |  | 2025-06-20 |  | G | 2025-06-23 |  | 2025-10-29 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.377
2023 | 111777 | #SGR18VB - RT 647 - REPLACE BRIDGE STR. 6053 | 0647 | Secondary | Bridge Replacement w/o Added Capacity | VDOT | Fauquier County | WARRENTON | Culpeper | NonMPO:NonMPO | Infrastructure Investment Division | Braden C Chapman | Braden.Chapman@VDOT.Virginia.gov | (540) 829-7421 | Howard M Tomlinson | Howard.Tomlinson@VDOT.virginia.gov | (540) 829-7436 |  |  |  | 0 |  | 1 | FY2026 | 2600000 | 2600000 | ACTIVITY DATES SET | G | Engage Public milestone finished on-time | G | Project is on budget | [5 empty] | 2022-03-15 | 2019-02-04 | 2022-03-28 | 2019-02-07 | G | 2022-03-29 | 2019-02-08 | 2023-02-24 | 2019-11-15 | G | [5 empty] | 2020-09-15 | 2020-09-15 | 2020-09-15 | 2020-09-15 | G | 2024-06-27 |  | 2024-07-11 |  | G | 2024-12-06 |  | 2025-06-13 |  | G | 2024-07-26 |  | 2025-02-05 |  | G | 2024-06-20 |  | 2025-02-27 |  | G | [5 empty] | 2025-07-08 |  | 2025-07-08 |  | G | 2025-09-26 |  | 2025-09-26 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.066091
2024 | 113385 | LIBRARY AVE. EXTENSION TO PARKSIDE VILLAGE | 0867 | Secondary | New Construction Roadway | Locally | Albemarle County | CHARLOTTESVILLE | Culpeper | NonMPO:NonMPO | Local Assistance Division | Ken Connors |  |  | Thomas Fitzpatrick | Thomas.Fitzpatrick@vdot.virginia.gov |  | JACK KELSEY |  |  | 0 |  | 0 | FY2022 | 4986700 | 4986700 | NO DATES SET YET-PE OPEN | R | Determine Requirements milestone is 430 days past the expected completion date | G | Project is on budget | 2019-03-15 | 2018-08-01 | 2019-06-07 | 2018-08-21 | G | 2019-06-10 | 2018-11-01 | 2019-06-12 | 2018-11-27 | G | 2019-06-13 |  | 2019-12-19 |  | R | [10 empty] | 2020-12-22 |  | 2021-01-13 |  | R | [5 empty] | 2021-01-19 |  | 2021-10-25 |  | G | 2020-01-30 | 2018-10-29 | 2020-09-29 | 2018-10-29 | G | [5 empty] | 2021-11-10 |  | 2021-12-10 |  | G | 2022-03-07 |  | 2022-03-07 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.19411
2025 | 113737 | RTE 639 - RURAL RUSTIC (SURFACE TREAT NON-HARDSURFACE ROAD) | 0639 | Secondary | Reconstruction w/o Added Capacity | VDOT | Orange County | LOUISA | Culpeper | NonMPO:NonMPO | Infrastructure Investment Division | Ken Connors |  |  | Bethel Kefyalew | Bethel.Kefyalew@vdot.virginia.gov | (540) 603-6015 |  |  |  | 0 |  | 0 | FY2025 | 164300 | 164300 | NO DATES SET YET | G | Start Development milestone is 600 days ahead of the expected completion date | Y | Estimate not current | [5 empty] | 2022-10-03 |  | 2022-10-14 |  | G | 2022-10-18 |  | 2023-06-13 |  | G | [5 empty] | 2024-02-22 |  | 2024-04-03 |  | G | [5 empty] | 2024-07-18 |  | 2024-11-08 |  | G | [5 empty] | 2024-07-02 |  | 2024-10-02 |  | G | [5 empty] | 2024-11-12 |  | 2024-11-12 |  | G | 2025-02-07 |  | 2025-02-07 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | SAAP CONTRACT | 0 | 0 | 0.094111
2026 | 115103 | #SGR20LP - NORTH SHENANDOAH AVE Primary Extension Paving |  | Urban | Resurfacing | Locally | Front Royal | EDINBURG | Staunton | NonMPO:NonMPO | Local Assistance Division | Edwin Z Carter | Edwin.Carter@vdot.virginia.gov | (540) 534-3204 | Kimberly Cameron | Kim.Cameron@vdot.virginia.gov | (540) 332-7886 | Town of Front Royal | sscheulen@frontroyalva.com | (540) 635-7819 | 0 |  | 1 | FY2020 | 121000 | 121000 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 144 days early | G | Project is on budget | 2019-08-01 | 2019-08-01 | 2019-10-25 | 2019-09-19 | G | [5 empty] | 2019-08-01 | 2019-08-01 | 2019-08-14 | 2019-08-14 | G | [25 empty] | 2019-08-15 | 2019-10-01 | 2019-11-08 | 2019-10-03 | G | [5 empty] | 2019-11-13 | 2019-09-23 | 2019-12-12 | 2019-10-04 | G | 2020-03-06 | 2019-10-07 | 2020-03-06 | 2019-10-14 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.081668
2028 | 116243 | #I81CIP SB EXIT 279 EXTEND ACCELERATION LANE (ID #53) | 0081 | Interstate | Reconstruction w/o Added Capacity | VDOT | Shenandoah County | EDINBURG | Staunton | NonMPO:NonMPO | Infrastructure Investment Division | John-Allen L Ennis | JohnAllen.Ennis@VDOT.Virginia.gov | (540) 332-9118 | Alexander Alvarado | Alexander.Alvarado@vdot.virginia.gov | (540) 332-7372 |  |  |  | 0 |  | 0 | FY2020 | 2248000 | 646665 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished on-time | G | Project is on budget | [5 empty] | 2020-07-01 | 2019-09-06 | 2020-07-15 | 2019-09-19 | G | 2020-07-16 | 2019-09-05 | 2021-03-12 | 2019-09-05 | G | [5 empty] | 2019-10-17 | 2019-10-17 | 2019-10-17 | 2019-10-17 | G | [5 empty] | 2019-08-23 | 2019-08-23 | 2019-08-23 | 2019-08-23 | G | [15 empty] | 2020-01-07 | 2020-01-07 | 2020-01-07 | 2020-01-07 | G | 2020-03-30 | 2020-03-30 | 2020-03-30 | 2020-03-30 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | SAAP CONTRACT | 1 | 0 | 0.063518
2029 | 116409 | NOVA SYSTEMIC UNSIGNALIZED INTERSECTION | 9999 | Miscellaneous | Safety | VDOT | Northern Virginia District-wide |  | Northern Virginia | Northern Virginia:Northern Virginia District-wide | Infrastructure Investment/Asset Management Division | Nikolaos Dais | Nick.Dais@vdot.virginia.gov | (703) 259-2237 | Jessica Paris | Jessica.Paris@vdot.virginia.gov | (703) 259-2409 |  |  |  | 0 |  | 0 | FY2022 | 927778 | 927778 | ACTIVITY DATES SET | G | Determine Requirements milestone finished 2 days early | G | Project is on budget | [5 empty] | 2019-12-02 | 2019-11-19 | 2019-12-13 | 2019-11-27 | G | 2019-12-16 | 2019-12-02 | 2020-09-30 | 2020-09-28 | G | [5 empty] | 2021-08-18 |  | 2021-08-31 |  | G | [25 empty] | 2021-10-15 |  | 2021-10-22 |  | G | 2021-10-25 |  | 2021-10-29 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | WORK/TASK ORDER | 0 | 0 | 0.065492
2030 | 110846 | RTE 156 - INTERSECTION IMPROVEMENTS | 0156 | Urban | Safety | Locally | Hopewell | PETERSBURG | Richmond | Tri-Cities:Hopewell | Infrastructure Investment Division | James Shepherd | James.Shepherd@vdot.virginia.gov | (804) 609-5305 | James Shepherd | James.Shepherd@vdot.virginia.gov | (804) 609-5305 | Johnny Butler | jbutler@hopewellva.gov | (804) 541-2319 | 0 |  | 0 | FY2024 | 515000 | 515000 | NO DATES SET YET | R | Relocate Utilities milestone baseline missing | G | Project is on budget | 2020-12-01 | 2020-12-01 | 2021-04-12 | 2021-01-26 | G | 2021-04-13 |  | 2021-05-03 |  | G | 2021-06-02 |  | 2021-09-23 |  | G | [9 empty] | R | 2023-01-20 |  | 2023-02-24 |  | G |  |  |  |  | R | 2023-02-27 |  | 2023-07-25 |  | G | 2023-06-21 |  | 2023-11-20 |  | G | [5 empty] | 2023-10-27 |  | 2023-11-28 |  | G | 2024-02-21 |  | 2024-02-21 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.081667
2031 | 111294 | #SGR18VB - BRIDGE REHAB 1-64/5TH ST OVER I-95 | 0064 | Interstate | Bridge Rehab w/o Added Capacity | VDOT | Richmond | ASHLAND | Richmond | Richmond:Richmond | Infrastructure Investment/Asset Management Division | Anthony S Haverly | Anthony.Haverly@vdot.virginia.gov | (804) 609-5225 | Anthony S Haverly | Anthony.Haverly@vdot.virginia.gov | (804) 609-5225 |  |  |  | 0 |  | 1 | FY2022 | 8629387 | 8629387 | NO DATES SET YET-PE OPEN | G | Start Development milestone finished on-time | G | Project is on budget | [5 empty] | 2017-09-01 | 2017-09-01 | 2017-09-11 | 2017-09-11 | G | 2017-09-12 | 2019-12-23 | 2021-06-30 |  | G | [10 empty] | 2021-06-25 |  | 2021-07-16 |  | G | [20 empty] | 2021-07-19 |  | 2021-08-16 |  | G | 2022-02-16 |  | 2022-03-16 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | DESIGN BUILD/PPTA | 0 | 0 | 0.1095
2032 | 111466 | #SMART18 - I-95 Aux Lanes (nb & sb) b/w Rte. 288 & Rte. 10 | 0095 | Interstate | Reconstruction w/ Added Capacity | VDOT | Chesterfield County | CHESTERFIELD | Richmond | Richmond:Chesterfield County | Infrastructure Investment Division | William Wheeler | William.Wheeler@vdot.virginia.gov | (804) 609-5280 | William Wheeler | William.Wheeler@vdot.virginia.gov | (804) 609-5280 |  |  |  | 1 | 2018 | 0 | FY2022 | 28770000 | 27912261 | ACTIVITY DATES SET | R | Complete Purchasing Right-of-Way milestone is 80 days past the expected completion date | G | Project is on budget | [5 empty] | 2017-11-01 | 2017-10-19 | 2017-11-15 | 2017-10-25 | G | 2017-11-16 | 2017-10-26 | 2018-05-18 | 2018-05-16 | G | [5 empty] | 2019-02-26 | 2019-03-01 | 2019-03-11 | 2019-03-07 | G | 2020-01-10 | 2019-12-20 | 2020-02-13 | 2019-12-20 | G | 2021-01-05 | 2020-06-18 | 2021-10-05 | 2020-06-18 | G | 2020-03-04 | 2020-09-02 | 2020-12-03 |  | R | 2020-12-04 | 2020-12-04 | 2021-06-11 |  | G | [5 empty] | 2022-01-11 |  | 2022-01-11 |  | G | 2022-03-29 |  | 2022-06-28 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.12769
2033 | 112465 | TRAFFIC CALMING, CITY OF FALLS CHURCH | 9999 | Urban | Safety | Locally | Falls Church | FAIRFAX | Northern Virginia | Northern Virginia:Falls Church | Infrastructure Investment Division | Ivan M Horodyskyj | Ivan.Horodyskyj@VDOT.Virginia.gov | (703) 259-2330 | Susie X Lue | Susie.Lue@vdot.virginia.gov | (703) 259-2918 | Jeffrey Sikes | jsikes@fallschurchva.gov | (571) 243-0839 | 0 |  | 0 | FY2028 | 636000 | 636000 | NO DATES SET YET-PE OPEN | G | Start Development milestone finished 175 days early | G | Project is on budget | 2019-10-01 | 2019-08-13 | 2020-07-21 | 2020-02-19 | G | 2020-07-22 | 2020-02-20 | 2020-08-25 | 2020-03-03 | G | 2021-12-01 |  | 2022-11-30 |  | G | [10 empty] | 2024-04-29 |  | 2024-08-20 |  | G | [5 empty] | 2024-08-22 |  | 2026-01-22 |  | G | [10 empty] | 2026-10-23 |  | 2027-03-23 |  | G | 2027-03-24 |  | 2027-08-19 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.35927
2034 | 113544 | CITYWIDE - INSTALL HIGH VISIBILITY TRAFFIC SIGNAL BACKPLATES | 9999 | Urban | Safety | Locally | Danville | HALIFAX | Lynchburg | Danville:Danville | Infrastructure Investment Division | Sharon S White | Sharon.White@VDOT.Virginia.gov | (434) 856-8220 | Sharon S White | Sharon.White@VDOT.Virginia.gov | (434) 856-8220 | Brian Dunevant | dunevbl@danvilleva.gov | (434) 799-5019 | 0 |  | 0 | FY2021 | 70830 | 70830 | AWARDED | G | Start Delivery milestone finished 200 days early | G | Project is on budget | 2019-07-01 | 2018-07-20 | 2019-09-24 | 2018-07-25 | G | 2019-09-25 | 2019-02-20 | 2019-09-27 | 2019-02-22 | G | 2019-09-30 | 2019-09-30 | 2020-04-09 | 2020-04-09 | G | [35 empty] | 2020-07-21 | 2020-07-21 | 2020-08-17 | 2020-08-17 | G | 2020-08-18 | 2020-08-18 | 2021-05-10 | 2020-10-22 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.08773
2035 | 114091 | RTES 1520 & 9070 - CONSTRUCT SIDEWALK | 1520 | Secondary | Safety | VDOT | Campbell County | APPOMATTOX | Lynchburg | Lynchburg:Campbell County | Infrastructure Investment Division | Keith M Rider | Keith.Rider@VDOT.Virginia.gov | (434) 856-8145 | Keith M Rider | Keith.Rider@VDOT.Virginia.gov | (434) 856-8145 |  |  |  | 0 |  | 0 | FY2027 | 633550 | 633550 | NO DATES SET YET | G | Start Development milestone is 522 days ahead of the expected completion date | G | Project is on budget | [5 empty] | 2022-07-15 |  | 2022-07-28 |  | G | 2022-07-29 |  | 2023-06-27 |  | G | [5 empty] | 2024-05-02 |  | 2024-05-15 |  | G | 2025-08-20 |  | 2025-09-03 |  | G | 2026-02-03 |  | 2026-08-06 |  | G | 2025-09-19 |  | 2026-04-01 |  | G | 2025-02-10 |  | 2025-08-13 |  | G | [5 empty] | 2026-08-11 |  | 2026-08-11 |  | G | 2026-11-02 |  | 2026-11-02 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.11121
2036 | 115117 | #SMART20 US ROUTE 1/FALL HILL AVE INTERSECTION IMPROVEMENTS | 0001 | Primary | Traffic Management/Engineering | VDOT | Fredericksburg | FREDERICKSBURG | Fredericksburg | Fredericksburg:Fredericksburg | Infrastructure Investment Division | Catherine C Coffey | Catherine.Coffey@vdot.virginia.gov | (540) 899-4280 | Curtis B Holloway | Curtis.Holloway@vdot.virginia.gov | (540) 374-3367 |  |  |  | 1 | 2020 | 0 | FY2025 | 7200000 | 7200000 | ACTIVITY DATES SET | G | Determine Requirements milestone finished 2 days early | G | Project is on budget | [5 empty] | 2020-02-03 | 2019-12-27 | 2020-03-02 | 2019-12-27 | G | 2020-03-03 | 2019-12-30 | 2021-01-28 | 2021-01-26 | G | [5 empty] | 2021-11-29 |  | 2021-12-10 |  | G | 2023-03-22 |  | 2023-04-18 |  | G | 2023-11-08 |  | 2024-07-09 |  | G | 2023-05-04 |  | 2023-11-07 |  | G | 2023-07-28 |  | 2024-02-07 |  | G | [5 empty] | 2024-05-14 |  | 2024-05-14 |  | G | 2024-08-05 |  | 2024-08-05 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.14099
2037 | 116202 | #I81CIP EXTEND LANES AT TROUTVILLE SAFETY REST AREA (ID #37) | 0081 | Interstate | Safety | VDOT | Botetourt County | SALEM | Salem | NonMPO:NonMPO | Infrastructure Investment Division | Thomas W Digiulian | Thomas.DiGiulian@VDOT.Virginia.gov | (540) 387-5356 | Craig S Moore | Craig.Moore@vdot.virginia.gov | (540) 375-3556 |  |  |  | 0 |  | 0 | FY2025 | 10042040 | 10042040 | NO DATES SET YET-PE OPEN | G | Start Development milestone finished 194 days early | G | Project is on budget | [5 empty] | 2020-07-01 | 2020-01-03 | 2020-07-15 | 2020-01-03 | G | 2020-07-16 | 2020-01-06 | 2021-06-14 |  | G | [5 empty] | 2022-04-20 |  | 2022-05-03 |  | G | 2023-08-08 |  | 2023-08-21 |  | G | 2024-01-22 |  | 2024-07-24 |  | G | 2023-09-07 |  | 2024-03-19 |  | G | 2023-01-27 |  | 2023-08-01 |  | G | [5 empty] | 2024-08-13 |  | 2024-08-13 |  | G | 2024-11-04 |  | 2024-11-04 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.13904
2038 | 116244 | #I81CIP SB EXIT 296 EXTEND ACCELERATION LANE (ID #51) | 0081 | Interstate | Reconstruction w/o Added Capacity | VDOT | Shenandoah County | EDINBURG | Staunton | NonMPO:NonMPO | Infrastructure Investment Division | John-Allen L Ennis | JohnAllen.Ennis@VDOT.Virginia.gov | (540) 332-9118 | Timothy Gregory | Tim.Gregory@vdot.virginia.gov | (540) 332-7891 |  |  |  | 0 |  | 0 | FY2021 | 1647718 | 745550 | ADVERTISED | G | Solicit Bids milestone finished 97 days early | G | Project is on budget | [5 empty] | 2020-07-01 | 2020-01-21 | 2020-07-15 | 2020-02-02 | G | 2020-07-16 | 2020-02-03 | 2021-06-14 | 2020-05-15 | G | [5 empty] | 2020-05-18 | 2020-05-18 | 2020-10-22 | 2020-10-22 | G | 2020-12-02 | 2020-12-02 | 2020-12-02 | 2020-12-02 | G | 2020-10-02 | 2020-10-02 | 2020-10-02 | 2020-10-02 | G | 2020-12-02 | 2020-12-02 | 2020-12-02 | 2020-12-02 | G | 2020-11-09 | 2020-10-26 | 2021-02-24 | 2020-10-26 | G | [5 empty] | 2021-03-09 | 2020-12-08 | 2021-03-15 | 2020-12-08 | G | 2021-06-03 |  | 2021-06-03 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.063404
2039 | 116693 | SYSTEMIC UNSIGNALIZED INTERSECTION TREATMENTS - DISTRICTWIDE | 9999 | Miscellaneous | Safety | VDOT | Richmond District-wide |  | Richmond | Richmond:Richmond District-wide | Infrastructure Investment/Asset Management Division | Adam S Brooks | Adam.Brooks@VDOT.Virginia.gov | (804) 609-5274 | Adam S Brooks | Adam.Brooks@VDOT.Virginia.gov | (804) 609-5274 | N\A |  |  | 0 |  | 0 | FY2025 | 927777 | 927777 | NO DATES SET YET | G | Start Development milestone is 477 days ahead of the expected completion date | G | Project is on budget | [5 empty] | 2022-05-31 |  | 2022-06-13 |  | G | 2022-06-14 |  | 2023-02-08 |  | G | [5 empty] | 2023-10-11 |  | 2023-11-27 |  | G | [5 empty] | 2024-03-15 |  | 2024-07-08 |  | G | [5 empty] | 2024-02-29 |  | 2024-05-30 |  | G | [5 empty] | 2024-07-09 |  | 2024-07-09 |  | G | 2024-09-27 |  | 2024-09-27 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.060653
2040 | 117049 | S. Laburnum/Route 5 Intersection Improvements | 7555 | Secondary | Reconstruction w/o Added Capacity | Locally | Henrico County | ASHLAND | Richmond | Richmond:Henrico County | Local Assistance Division | Cynthia Crouch | Cynthia.Crouch@vdot.virginia.gov | (804) 609-5313 | Cynthia Crouch | Cynthia.Crouch@vdot.virginia.gov | (804) 609-5313 | TBD |  | TBD | 0 |  | 0 | FY2029 | 289746 | 289746 | NO DATES SET YET | G | Agreement with Locality milestone is 1543 days ahead of the expected completion date | G | Project is on budget | 2025-01-06 |  | 2025-05-14 |  | G | 2025-05-15 |  | 2025-06-05 |  | G | 2025-12-15 |  | 2026-04-10 |  | G | [10 empty] | 2027-07-30 |  | 2027-09-02 |  | G | [5 empty] | 2027-09-03 |  | 2028-02-09 |  | G | 2028-01-05 |  | 2028-06-05 |  | G | [5 empty] | 2028-05-12 |  | 2028-06-09 |  | G | 2028-08-29 |  | 2028-08-29 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.32165
2041 | 118430 | #SGR21VB(FED ID 07739) BR REPLACE RTE. 759 OVER MECHUNK CRK | 0759 | Secondary | Bridge Replacement w/o Added Capacity | VDOT | Fluvanna County | LOUISA | Culpeper | NonMPO:NonMPO | Infrastructure Investment Division | Braden C Chapman | Braden.Chapman@VDOT.Virginia.gov | (540) 829-7421 | Brian A Arnold | Brian.Arnold@VDOT.Virginia.gov | (540) 829-7557 |  |  |  | 0 |  | 1 | FY2025 | 6954915 | 6954915 | NO DATES SET YET | G | Start Development milestone is 176 days ahead of the expected completion date | G | Project is on budget | [5 empty] | 2021-07-27 |  | 2021-08-16 |  | G | 2021-08-17 |  | 2022-06-21 |  | G | [5 empty] | 2023-01-25 |  | 2023-02-22 |  | G | 2023-10-10 |  | 2023-11-15 |  | G | 2024-04-19 |  | 2024-08-19 |  | G | 2023-12-04 |  | 2024-05-03 |  | G | 2024-01-18 |  | 2024-06-14 |  | G | [5 empty] | 2024-09-10 |  | 2024-09-10 |  | G | 2024-12-03 |  | 2024-12-03 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.064759
2042 | 90173 | Rte 623 - REPLACE BRIDGE Over Cedar Creek VA str. 6908 | 0623 | Secondary | Bridge Replacement w/o Added Capacity | VDOT | Frederick County | EDINBURG | Staunton | NonMPO:NonMPO | Infrastructure Investment Division | Keith P Weakley | Keith.Weakley@VDOT.Virginia.gov | (703) 298-8428 | John-Allen L Ennis | JohnAllen.Ennis@VDOT.Virginia.gov | (540) 332-9118 |  |  |  | 0 |  | 0 | FY2020 | 1653217 | 2822291 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 162 days early | R | Project estimate is less than $5M and is 20% or more over budget | [5 empty] | 2010-07-01 | 2010-07-19 | 2010-07-01 | 2010-07-19 | R | 2011-01-03 | 2010-10-04 | 2012-01-16 | 2012-09-04 | R | [5 empty] | 2016-06-22 | 2016-06-22 | 2016-07-14 | 2016-07-14 | G | 2017-03-31 | 2017-03-31 | 2017-08-31 | 2017-08-31 | G | [5 empty] | 2017-11-10 | 2017-11-10 | 2018-02-06 | 2018-02-06 | G | 2018-10-11 | 2018-04-06 | 2019-10-17 | 2019-04-01 | G | [5 empty] | 2019-10-17 | 2019-11-05 | 2019-11-12 | 2019-11-05 | G | 2020-03-02 | 2020-01-20 | 2020-06-30 | 2020-01-20 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.053289
2043 | 100501 | Route 1 and Westover Avenue intersection | 9024 | Urban | Safety | Locally | Colonial Heights | CHESTERFIELD | Richmond | Tri-Cities:Colonial Heights | Infrastructure Investment Division | Evan Austin | Evan.Austin@vdot.virginia.gov | (804) 609-5384 | Evan Austin | Evan.Austin@vdot.virginia.gov | (804) 609-5384 | Keith Chisolm | chisolmk@colonialheightsva.gov | (804) 520-9215 | 0 |  | 0 | FY2022 | 465990 | 1085166 | ACTIVITY DATES SET | R | Start Purchasing Right-of-Way milestone is 251 days past the expected completion date | R | Project estimate is less than $5M and is 20% or more over budget | 2018-07-02 | 2018-07-02 | 2018-09-17 | 2018-09-04 | G | 2018-09-19 | 2018-12-12 | 2019-01-28 | 2018-12-17 | G | 2019-01-29 | 2018-12-18 | 2019-08-19 | 2019-08-19 | G | [5 empty] | 2020-04-21 | 2020-04-21 | 2020-05-15 | 2020-05-15 | G | 2020-05-18 |  | 2020-06-15 |  | R | [5 empty] | 2020-06-16 |  | 2020-10-15 |  | R | [10 empty] | 2021-02-02 |  | 2021-03-01 |  | Y | 2021-09-01 |  | 2021-09-01 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.1536
2044 | 104888 | #SGR18LB - RT 360 - REHAB MAYO BRIDGE |  | Urban | Bridge Rehab w/o Added Capacity | Locally | Richmond | ASHLAND | Richmond | Richmond:Richmond | Infrastructure Investment Division | Olena Fecek | Olena.Fecek@vdot.virginia.gov | (804) 524-6368 | Olena Fecek | Olena.Fecek@vdot.virginia.gov | (804) 524-6368 | Thomas Westbrook | Thomaswestbrook@richmond.gov | (804) 646-3421 | 0 |  | 1 | FY2020 | 18313601 | 18313601 | NO DATES SET YET-PE OPEN | R | Determine Requirements milestone is 751 days past the expected completion date | G | Project is on budget | 2018-07-02 | 2018-02-02 | 2018-08-30 | 2018-06-19 | G | 2018-08-31 | 2018-06-20 | 2018-08-31 | 2018-06-25 | G | 2018-10-01 | 2019-12-02 | 2019-02-01 |  | R | [35 empty] | 2019-07-01 |  | 2019-07-01 |  | R | 2019-07-30 |  | 2020-01-24 |  | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.24403
2045 | 106489 | RTE 234 DUMFRIES ROAD SHARED USE PATH EXTENSION | 0234 | Primary | Facilities for Pedestrians and Bicycles | Locally | Prince William County | MANASSAS | Northern Virginia | Northern Virginia:Prince William County | Infrastructure Investment Division | Amir Salahshoor | A.Salahshoor@VDOT.Virginia.gov | (703) 259-1957 | Rita Hockman | Rita.Hockman@vdot.virginia.gov | (804) 824-7421 | Gladis Arboleda | garboleda@pwcgov.org | (703) 792-5276 | 0 |  | 0 | FY2021 | 2976193 | 3269000 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 713 days early | Y | Project estimate is less than $5M and is up to 20% over budget | 2016-04-14 | 2016-04-14 | 2016-10-14 | 2016-09-28 | G | 2016-10-15 | 2016-09-16 | 2016-10-15 | 2016-09-16 | G | 2016-12-05 | 2016-11-04 | 2018-12-01 | 2018-01-05 | G | [35 empty] | 2018-03-05 | 2018-03-05 | 2018-08-27 | 2018-06-13 | G | 2020-04-02 | 2018-07-27 | 2020-09-15 | 2018-10-03 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.25283
2046 | 107312 | Belle Meade Drive Drainage Improvements | 1633 | Secondary | Mitigation of Water Pollution Due to Highway Runof | Locally | Roanoke County | SALEM | Salem | Roanoke:Roanoke County | Local Assistance Division | Adam J Czesnowski | Adam.Czesnowski@vdot.virginia.gov | (540) 541-1216 | Adam J Czesnowski | Adam.Czesnowski@vdot.virginia.gov | (540) 541-1216 | David Henderson | DHENDERSON@roanokecountyva.gov | (540) 772-2083 | 0 |  | 0 | FY2019 | 50000 | 50000 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 71 days early | G | Project is on budget | 2015-11-02 | 2015-09-05 | 2016-02-02 | 2015-09-14 | G | 2016-02-03 | 2016-02-08 | 2016-02-17 | 2016-03-09 | R | 2016-02-18 | 2016-03-17 | 2016-10-07 | 2017-05-10 | R | [10 empty] | 2017-08-29 | 2017-09-12 | 2017-09-12 | 2017-09-12 | G | [20 empty] | 2017-09-18 | 2018-06-26 | 2018-02-14 | 2018-06-26 | R | 2018-07-03 | 2018-06-27 | 2019-01-04 | 2018-10-25 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.17306
2047 | 109303 | #HB2.FY17 Norfollk Traffic Control System Platform Upgrade | 0000 | Urban | Traffic Management/Engineering | Locally | Norfolk | NORFOLK | Hampton Roads | Hampton Roads:Norfolk | Infrastructure Investment Division | Stephen Rowan | Steve.Rowan@vdot.virginia.gov | (757) 790-9925 | Derrick Williams | Derrick.Williams@vdot.virginia.gov | (757) 956-3097 | Deborah Mangiaracina, P.E.. | Deborah.Mangiaracina@norfolk.gov | (757) 664-7459 | 1 | 2017 | 0 | FY2018 | 3000000 | 2966746 | CONSTRUCTION STARTED | R | Start Delivery milestone finished 506 days late | G | Project is on budget | 2016-12-05 | 2016-12-05 | 2016-12-28 | 2017-01-09 | R | 2016-12-29 | 2017-01-10 | 2017-01-11 | 2017-01-30 | R | 2017-01-12 | 2017-01-31 | 2017-01-20 | 2017-04-24 | R | [35 empty] | 2017-09-18 | 2018-06-15 | 2017-10-02 | 2018-09-06 | R | 2017-10-03 | 2018-09-07 | 2017-11-14 | 2019-04-04 | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.42574
2048 | 109921 | U.S. Route 11 Shoulder Initiative - Washington Co. | 0011 | Primary | Safety | VDOT | Washington County | ABINGDON | Bristol | NonMPO:NonMPO | Infrastructure Investment Division | Jeffrey Buchanan | Jeff.Buchanan@vdot.virginia.gov | (276) 415-3440 | Brandi Halloway | Brandi.Halloway@vdot.virginia.gov | (276) 696-3254 |  |  |  | 0 |  | 0 | FY2020 | 2025000 | 1611762 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished on-time | G | Project is on budget | [5 empty] | 2017-09-01 | 2017-09-01 | 2017-09-15 | 2017-09-15 | G | 2017-09-18 | 2017-09-18 | 2018-07-09 | 2018-07-09 | G | [5 empty] | 2019-04-18 | 2019-04-18 | 2019-05-30 | 2019-05-29 | G | [5 empty] | 2019-09-13 | 2019-12-11 | 2020-01-10 | 2020-04-06 | R | [15 empty] | 2020-02-11 | 2020-02-11 | 2020-02-11 | 2020-02-11 | G | 2020-05-07 | 2020-05-07 | 2020-05-07 | 2020-05-07 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.062373
2049 | 110100 | HSIP - Shoulder Widening/ GR Improvements | 0220 | Primary | Safety | VDOT | Franklin County | BEDFORD | Salem | NonMPO:NonMPO | Infrastructure Investment Division | Bernard S Grinnell | Sean.Grinnell@VDOT.Virginia.gov | (540) 375-0148 | Anthony L Handy | Tony.Handy@VDOT.Virginia.gov | (540) 352-9050 |  |  |  | 0 |  | 0 | FY2021 | 2409164 | 2409164 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 68 days early | G | Project is on budget | [10 empty] | 2020-11-16 | 2016-01-07 | 2020-11-20 | 2018-05-01 | G | [35 empty] | 2020-06-09 | 2020-06-09 | 2020-06-09 | 2020-06-09 | G | 2020-07-23 | 2020-09-02 | 2020-11-09 | 2020-09-02 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.18484
2050 | 117965 | ENHANCED CURVE SIGNING & MARKING - BRISTOL DISTRICTWIDE | 9999 | Primary | Safety | VDOT | Bristol District-wide |  | Bristol | NonMPO:NonMPO | Infrastructure Investment/Asset Management Division | Brian Holt | Brian.Holt@vdot.virginia.gov | (276) 696-3414 | Jeremy J Mullins | Jeremy.Mullins@vdot.virginia.gov | (276) 696-3259 |  |  |  | 0 |  | 0 | FY2022 | 2823723 | 2823723 | NO DATES SET YET-PE OPEN | R | Determine Requirements milestone is 53 days past the expected completion date | G | Project is on budget | [5 empty] | 2020-10-01 | 2020-10-01 | 2020-10-14 | 2020-10-14 | G | 2020-10-15 | 2020-10-15 | 2020-12-30 |  | R | [35 empty] | 2021-08-10 |  | 2021-08-10 |  | G | 2021-11-01 |  | 2021-11-01 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.081654
2051 | 118480 | #SGR21LP - City of Petersburg 1048 S Crater Rd | 0301 | Urban | Resurfacing | VDOT | Petersburg | PETERSBURG | Richmond | Tri-Cities:Petersburg | Infrastructure Investment/Asset Management Division | Raymond Chapman | Scott.Chapman@vdot.virginia.gov | (804) 609-5277 | Raymond Chapman | Scott.Chapman@vdot.virginia.gov | (804) 609-5277 |  |  |  | 0 |  | 1 | FY2023 | 464200 | 464200 | NO DATES SET YET | G | Start Development milestone is 190 days ahead of the expected completion date | G | Project is on budget | [5 empty] | 2021-08-17 |  | 2021-08-30 |  | G | 2021-08-31 |  | 2021-11-10 |  | G | [35 empty] | 2022-06-14 |  | 2022-06-14 |  | G | 2022-09-02 |  | 2022-09-02 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.060645
2052 | 97712 | RTE 644 OVER BIG OTTER RIVER (STR 2753 - )BRIDGE REPL. - | 0644 | Secondary | Bridge Replacement w/o Added Capacity | VDOT | Bedford County | BEDFORD | Salem | NonMPO:NonMPO | Infrastructure Investment Division | Anthony T Marshall | Todd.Marshall@VDOT.Virginia.gov | (540) 387-5460 | Anthony L Handy | Tony.Handy@VDOT.Virginia.gov | (540) 352-9050 |  |  |  | 0 |  | 0 | FY2020 | 3891170 | 3891169 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 248 days early | G | Project is on budget | [5 empty] | 2015-10-01 | 2010-12-09 | 2015-11-01 | 2010-12-09 | G | 2015-09-28 | 2015-09-28 | 2017-05-05 | 2017-05-05 | G | [5 empty] | 2016-08-18 | 2016-08-18 | 2016-08-25 | 2016-08-25 | G | 2017-10-11 | 2017-10-11 | 2017-10-30 | 2017-10-30 | G | 2018-01-04 | 2019-04-17 | 2019-11-12 | 2019-04-17 | G | 2017-11-08 | 2017-11-08 | 2019-10-17 | 2018-04-30 | G | 2016-10-11 | 2018-06-28 | 2018-07-20 | 2019-01-30 | R | [5 empty] | 2019-10-17 | 2019-05-07 | 2019-11-12 | 2019-05-07 | G | 2019-12-02 | 2019-07-29 | 2020-04-02 | 2019-07-29 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.10065
2053 | 104185 | #SGR17VB - RT 666 OVER NSRR (STR 02780) - BRIDGE REPLACE | 0666 | Secondary | Bridge Replacement w/o Added Capacity | VDOT | Bedford County | BEDFORD | Salem | NonMPO:NonMPO | Infrastructure Investment/Asset Management Division | Anthony T Marshall | Todd.Marshall@VDOT.Virginia.gov | (540) 387-5460 | Anthony L Handy | Tony.Handy@VDOT.Virginia.gov | (540) 352-9050 |  |  |  | 0 |  | 1 | FY2020 | 3873419 | 3873419 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 238 days early | G | Project is on budget | [5 empty] | 2017-08-12 | 2013-06-21 | 2017-08-12 | 2013-06-21 | G | 2016-08-22 | 2016-08-22 | 2017-05-11 | 2017-05-11 | G | [5 empty] | 2017-04-11 | 2017-04-11 | 2017-05-11 | 2017-05-11 | G | 2017-12-15 | 2017-12-15 | 2018-03-05 | 2018-03-05 | G | 2018-08-09 | 2018-10-09 | 2019-07-08 | 2019-01-11 | G | 2018-04-06 | 2018-04-06 | 2019-07-09 | 2018-10-22 | G | [10 empty] | 2019-06-03 | 2018-01-08 | 2019-07-09 | 2019-01-08 | G | 2019-08-09 | 2019-04-19 | 2019-12-13 | 2019-04-19 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.088476
2054 | 105784 | RIVERSIDE PARKWAY-4 LANE CONSTRUCTION ON NEW ALIGNMENT | 2401 | Secondary | New Construction Roadway | Locally | Loudoun County | LEESBURG | Northern Virginia | Northern Virginia:Loudoun County | Local Assistance Division | Susie X Lue | Susie.Lue@vdot.virginia.gov | (703) 259-2918 | Veljibhai M Desai | Veljibhai.Desai@vdot.virginia.gov | (703) 259-2927 | Bruce Thornberry | bruce.thornberry@loudoun.gov | (571) 258-3548 | 0 |  | 0 | FY2021 | 10186000 | 16069483 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 602 days early | R | Project estimate is greater than $10M and is over budget by (a) 10% or more or (b) $5M or more | 2014-03-03 | 2014-03-01 | 2014-08-30 | 2014-08-26 | G | 2014-09-01 | 2014-09-01 | 2014-09-01 | 2014-09-01 | G | 2014-10-01 | 2014-10-01 | 2017-04-24 | 2017-04-24 | G | [10 empty] | 2017-04-24 | 2017-04-24 | 2017-04-24 | 2017-04-24 | G | 2019-09-30 | 2018-04-20 | 2020-09-30 | 2019-05-02 | G | 2017-07-30 | 2017-07-30 | 2019-09-27 | 2019-04-02 | G | 2017-04-25 | 2017-04-25 | 2020-10-01 | 2017-04-25 | G | [5 empty] | 2020-10-01 | 2019-03-19 | 2021-02-01 | 2019-05-30 | G | 2021-02-02 | 2019-05-31 | 2021-06-01 | 2019-10-08 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.38868
2055 | 106996 | FARMWELL ROAD INTERSECTION, PED & BICYCLE IMPROVEMENT | 0625 | Secondary | Reconstruction w/ Added Capacity | Locally | Loudoun County | LEESBURG | Northern Virginia | Northern Virginia:Loudoun County | Local Assistance Division | Amir Salahshoor | A.Salahshoor@VDOT.Virginia.gov | (703) 259-1957 | Susie X Lue | Susie.Lue@vdot.virginia.gov | (703) 259-2918 | Suheili P??rez-Jim??nez | Suheili.Perez@loudoun.gov | 571258321 | 0 |  | 0 | FY2025 | 32100000 | 32100000 | ACTIVITY DATES SET | R | Determine Requirements milestone finished 11 days late | G | Project is on budget | 2015-07-01 | 2015-07-01 | 2016-03-01 | 2016-03-01 | G | 2016-03-01 | 2016-03-01 | 2016-03-01 | 2016-03-01 | G | 2015-10-09 | 2015-10-09 | 2020-05-22 | 2020-06-02 | R | [5 empty] | 2022-01-12 |  | 2022-07-05 |  | G | 2023-03-01 |  | 2023-03-14 |  | G | [5 empty] | 2023-03-15 |  | 2024-08-19 |  | G | 2023-03-01 |  | 2024-02-29 |  | G | [5 empty] | 2024-09-20 |  | 2025-02-10 |  | G | 2025-02-11 |  | 2025-02-11 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.45375
2056 | 107956 | Thalia Creek Greenway Phase III |  | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Virginia Beach | NORFOLK | Hampton Roads | Hampton Roads:Virginia Beach | Local Assistance Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Marci Thompson | Marci.Thompson@vdot.virginia.gov | (757) 956-3093 | Katie E. Shannon, PE | kshannon@vbgov.com | (757) 385-1514 | 0 |  | 0 | FY2019 | 2750000 | 2796197 | ACTIVITY DATES SET | R | Solicit Bids milestone is 844 days past the expected completion date | Y | Project estimate is less than $5M and is up to 20% over budget | 2015-12-16 | 2015-12-01 | 2016-03-15 | 2016-02-08 | G | [5 empty] | 2016-10-03 | 2016-10-03 | 2017-03-17 | 2017-03-17 | G | [10 empty] | 2017-09-25 | 2019-08-07 | 2017-10-31 | 2019-08-18 | R | [20 empty] | 2018-10-03 |  | 2018-10-31 |  | R | 2018-11-26 |  | 2019-03-22 |  | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.28624
2057 | 109419 | #HB2.FY17 I-81 at State Route 75 (Exit 17) Interchange Mod. | 0081 | Interstate | Reconstruction w/ Added Capacity | VDOT | Multi-jurisdictional: Bristol MPO |  | Bristol | Bristol:Multi-jurisdictional: Bristol MPO | Infrastructure Investment Division | Conrad Hill | Conrad.Hill@vdot.virginia.gov | (804) 773-0170 | Ronald C Flanary | Ronald.Flanary@VDOT.Virginia.gov | (276) 696-3252 |  |  |  | 1 | 2017 | 0 | FY2022 | 21200000 | 32035536 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 245 days early | R | Project estimate is greater than $10M and is over budget by (a) 10% or more or (b) $5M or more | [5 empty] | 2016-08-01 | 2016-08-01 | 2016-08-12 | 2016-08-12 | G | 2016-08-15 | 2016-08-15 | 2017-09-22 | 2017-07-18 | G | [5 empty] | 2018-05-16 | 2018-03-01 | 2018-06-27 | 2018-03-09 | G | 2019-08-14 | 2019-04-18 | 2019-08-27 | 2019-05-13 | G | 2020-01-29 | 2020-02-11 | 2021-05-21 | 2021-01-21 | G | 2019-09-13 | 2019-05-20 | 2021-01-12 | 2020-05-29 | G | 2017-07-18 | 2017-07-18 | 2020-09-14 | 2019-12-02 | G | [5 empty] | 2021-06-08 | 2020-09-08 | 2021-06-08 | 2020-09-08 | G | 2021-07-22 | 2020-12-09 | 2021-08-11 | 2020-12-09 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.11072
2058 | 109924 | U.S. 58 Rumble Stripe Initiative | 0058 | Primary | Safety | VDOT | Bristol District-wide |  | Bristol | NonMPO:NonMPO | Infrastructure Investment Division | Jeffrey Buchanan | Jeff.Buchanan@vdot.virginia.gov | (276) 415-3440 | Brandi Halloway | Brandi.Halloway@vdot.virginia.gov | (276) 696-3254 |  |  |  | 0 |  | 0 | FY2021 | 3125000 | 3649821 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 323 days early | Y | Project estimate is less than $5M and is up to 20% over budget | [5 empty] | 2018-10-01 | 2018-10-01 | 2018-10-15 | 2018-10-17 | R | 2018-10-16 | 2018-10-16 | 2019-06-11 | 2019-06-11 | G | [5 empty] | 2020-02-20 | 2019-12-03 | 2020-04-01 | 2019-12-03 | G | [5 empty] | 2020-07-30 | 2019-12-11 | 2020-11-23 | 2020-02-10 | G | [15 empty] | 2021-01-12 | 2020-02-11 | 2021-01-12 | 2020-02-11 | G | 2021-03-08 | 2020-05-07 | 2021-03-26 | 2020-05-07 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.070692
2060 | 111309 | #SGR18VB - RT 40 OVER THARP CREEK (STR 7757) - SUPER REPLACE | 0040 | Primary | Bridge Rehab w/o Added Capacity | VDOT | Franklin County | BEDFORD | Salem | NonMPO:NonMPO | Infrastructure Investment/Asset Management Division | Anthony T Marshall | Todd.Marshall@VDOT.Virginia.gov | (540) 387-5460 | Leslie T Repass | Todd.Repass@VDOT.Virginia.gov | (540) 381-7195 |  |  |  | 0 |  | 1 | FY2021 | 1240199 | 1240199 | CONSTRUCTION STARTED | R | Start Delivery milestone finished 5 days late | G | Project is on budget | [5 empty] | 2017-07-05 | 2019-09-17 | 2020-07-08 | 2019-11-18 | G | 2020-07-09 | 2019-10-01 | 2020-08-05 | 2019-12-27 | G | [35 empty] | 2020-09-08 | 2020-09-08 | 2020-09-08 | 2020-09-08 | G | 2020-10-22 | 2020-11-17 | 2020-11-12 | 2020-11-17 | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 1 | 0.34139
2061 | 112658 | Capitol Landing Road Corridor Improvements | 0005 | Urban | Reconstruction w/o Added Capacity | Locally | Williamsburg | WILLIAMSBURG | Hampton Roads | Hampton Roads:Williamsburg | Infrastructure Investment Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Chessica Villaflores | Chessica.Villaflores@vdot.virginia.gov | (757) 956-3094 | Aaron Small | asmall@williamsburgva.gov | (757) 220-6140 | 0 |  | 0 | FY2022 | 6360000 | 6360000 | NO DATES SET YET-PE OPEN | R | Determine Requirements milestone is 496 days past the expected completion date | G | Project is on budget | 2018-01-05 | 2018-01-05 | 2018-09-27 | 2018-08-09 | G | 2018-09-28 | 2018-08-23 | 2018-10-11 | 2018-09-06 | G | 2018-10-12 |  | 2019-10-14 |  | R | [10 empty] | 2020-10-15 |  | 2020-11-05 |  | R | [5 empty] | 2020-11-09 |  | 2021-08-20 |  | G | [10 empty] | 2021-09-21 |  | 2021-10-19 |  | G | 2021-10-20 |  | 2022-04-15 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.25157
2062 | 113364 | Primary Extensions: S Jefferson Street Resurfacing | 1005 | Urban | Resurfacing | VDOT | Petersburg | PETERSBURG | Richmond | Tri-Cities:Petersburg | Local Assistance Division | Dianna M Bryant | Dianna.Bryant@VDOT.Virginia.gov | (804) 863-4004 | Dianna M Bryant | Dianna.Bryant@VDOT.Virginia.gov | (804) 863-4004 | Bill Riggleman | bill@petersburg-va.org | (804) 993-1927 | 0 |  | 1 | FY2020 | 70500 | 70500 | AWARDED | G | Start Delivery milestone finished 233 days early | G | Project is on budget | [10 empty] | 2018-05-01 | 2018-10-25 | 2018-05-07 | 2018-12-19 | R | [25 empty] | 2018-11-29 | 2018-11-29 | 2019-03-28 | 2018-11-29 | G | [5 empty] | 2019-05-28 | 2018-12-26 | 2019-05-28 | 2018-12-26 | G | 2019-08-16 | 2018-12-26 | 2019-08-16 | 2018-12-26 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.067082
2063 | 113615 | MANASSAS CITY PRIMARY EXTENSION PAVING FY19 - SUDLEY ROAD | 0234 | Urban | Resurfacing | Locally | Manassas | MANASSAS | Northern Virginia | Northern Virginia:Manassas | Local Assistance Division | Gaby Y Hakim | Gaby.Hakim@VDOT.Virginia.gov | (703) 691-6742 | Rita Hockman | Rita.Hockman@vdot.virginia.gov | (804) 824-7421 | Chloe Delhomme | cdelhomme@ci.manassas.va.us | (703) 257-8476 | 0 |  | 1 | FY2019 | 35164 | 35164 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 58 days early | G | Project is on budget | 2018-07-02 | 2018-07-02 | 2018-09-25 | 2018-10-12 | R | [5 empty] | 2018-09-26 | 2018-09-26 | 2018-11-28 | 2018-10-16 | G | [25 empty] | 2018-10-01 | 2018-10-01 | 2018-10-16 | 2018-10-16 | G | [5 empty] | 2018-10-15 | 2018-10-15 | 2018-10-16 | 2018-10-16 | G | 2018-10-17 | 2018-10-16 | 2018-12-13 | 2018-10-16 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.094027
2064 | 113855 | Arconic Pedestrian Improvements | 9999 | Urban | Facilities for Pedestrians and Bicycles | Locally | Hampton | WILLIAMSBURG | Hampton Roads | Hampton Roads:Hampton | Infrastructure Investment Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Derrick Williams | Derrick.Williams@vdot.virginia.gov | (757) 956-3097 | Philippe Fenouil, P.E. | philippe.fenouli@hampton.gov | (757) 727-6197 | 0 |  | 0 | FY2027 | 471000 | 471000 | NO DATES SET YET | G | Agreement with Locality milestone is 1012 days ahead of the expected completion date | Y | Estimate not current | 2023-09-01 |  | 2023-11-30 |  | G | 2023-12-01 |  | 2023-12-05 |  | G | 2023-12-06 |  | 2024-06-12 |  | G | [10 empty] | 2025-06-16 |  | 2025-07-07 |  | G | [5 empty] | 2025-07-09 |  | 2026-04-21 |  | G | 2024-07-19 |  | 2025-03-27 |  | G | [5 empty] | 2026-05-07 |  | 2026-06-04 |  | G | 2026-08-24 |  | 2026-08-24 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.21705
2065 | 114737 | LEAVELLS ROAD PEDESTRIAN IMPROVEMENTS | 0639 | Secondary | Safety | VDOT | Spotsylvania County | FREDERICKSBURG | Fredericksburg | Fredericksburg:Spotsylvania County | Infrastructure Investment Division | Robert Galen Ridgell | Robert.Ridgell@vdot.virginia.gov | (540) 372-3549 | Robert Galen Ridgell | Robert.Ridgell@vdot.virginia.gov | (540) 372-3549 |  |  |  | 0 |  | 0 | FY2021 | 563500 | 563500 | AWARDED | G | Start Delivery milestone finished 401 days early | G | Project is on budget | [5 empty] | 2019-01-07 | 2019-02-13 | 2019-01-07 | 2019-02-13 | R | 2019-01-08 | 2019-02-14 | 2019-04-18 | 2019-03-04 | G | [5 empty] | 2020-06-15 | 2019-06-25 | 2020-08-24 | 2019-06-25 | G | [25 empty] | 2020-09-10 | 2019-08-19 | 2020-09-16 | 2019-08-19 | G | 2020-09-17 | 2019-08-19 | 2020-09-23 | 2019-08-19 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | WORK/TASK ORDER | 1 | 0 | 0.068395
2066 | 115507 | #SMART20 HWY 301S Sidewalk Greensville Project | 0301 | Urban | Safety | VDOT | Greensville County | FRANKLIN | Hampton Roads |  | Infrastructure Investment Division | Hayden Hill | Hayden.Hill@volkert.com | (703) 642-8100 | Hayden Hill | Hayden.Hill@volkert.com | (703) 642-8100 | Katherine Howerton | khowerton@greensvillecountyva.gov | (434) 348-4205 | 1 | 2020 | 0 | FY2028 | 576903 | 576903 | NO DATES SET YET | G | Start Development milestone is 968 days ahead of the expected completion date | Y | Estimate not current | [5 empty] | 2023-08-15 |  | 2023-10-17 |  | G | 2023-10-18 |  | 2024-10-18 |  | G | [5 empty] | 2025-08-26 |  | 2025-09-09 |  | G | 2026-12-17 |  | 2026-12-31 |  | G | 2027-05-27 |  | 2027-12-03 |  | G | 2027-01-21 |  | 2027-07-26 |  | G | 2026-06-04 |  | 2026-12-10 |  | G | [5 empty] | 2027-12-14 |  | 2027-12-14 |  | G | 2028-03-09 |  | 2028-03-09 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.17439
2067 | 115543 | Nimmo Parkway Phase VIIB | 0000 | Urban | New Construction Roadway | Locally | Virginia Beach | NORFOLK | Hampton Roads | Hampton Roads:Virginia Beach | Infrastructure Investment Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Marci Thompson | Marci.Thompson@vdot.virginia.gov | (757) 956-3093 | Katie Shannon | kshannon@vbgov.com | (757) 385-1514 | 0 |  | 0 | FY2029 | 41911500 | 41911500 | NO DATES SET YET | G | Agreement with Locality milestone is 1192 days ahead of the expected completion date | G | Project is on budget | 2024-03-05 |  | 2024-05-28 |  | G | 2024-05-29 |  | 2024-06-11 |  | G | 2024-06-12 |  | 2025-05-29 |  | G | [10 empty] | 2026-06-11 |  | 2026-07-01 |  | G | [5 empty] | 2026-11-10 |  | 2027-11-10 |  | G | 2025-01-29 |  | 2025-11-12 |  | G | [5 empty] | 2027-12-01 |  | 2028-06-21 |  | G | 2028-09-11 |  | 2029-01-24 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.23819
2068 | 116835 | Trail Master Plan - High Knob Access Enhancements | 0018 | Miscellaneous | Facilities for Pedestrians and Bicycles | Locally | Norton | WISE | Bristol | NonMPO:NonMPO | Local Assistance Division | Kenneth R Plummer | KR.Plummer@VDOT.Virginia.gov | (276) 696-3261 | Kenneth R Plummer | KR.Plummer@VDOT.Virginia.gov | (276) 696-3261 | Fred Ramey | fredr@nortonva.org | (276) 679-1160 | 0 |  | 0 | FY2023 | 853750 | 853750 | NO DATES SET YET-PE OPEN | G | Start Development milestone finished 99 days early | G | Project is on budget | 2020-04-29 | 2020-04-29 | 2020-09-03 | 2020-04-29 | G | 2020-09-04 | 2020-05-21 | 2020-09-25 | 2020-06-18 | G | 2021-04-09 |  | 2021-08-02 |  | G | [25 empty] | 2022-07-28 |  | 2022-12-29 |  | G | [5 empty] | 2023-03-02 |  | 2023-03-29 |  | G | 2023-06-16 |  | 2023-06-16 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.12976
2069 | 117038 | Church Street Pedestrian Improvements | 8575 | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Norfolk | NORFOLK | Hampton Roads | Hampton Roads:Norfolk | Local Assistance Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Derrick Williams | Derrick.Williams@vdot.virginia.gov | (757) 956-3097 | Deborah Mangiaracina | robert.brown@norfolk.gov | (757) 664-7459 | 0 |  | 0 | FY2024 | 500000 | 500000 | NO DATES SET YET | G | Agreement with Locality milestone is 80 days ahead of the expected completion date | G | Project is on budget | 2021-01-04 |  | 2021-05-12 |  | G | 2021-05-13 |  | 2021-06-03 |  | G | 2021-11-05 |  | 2022-03-09 |  | G | [25 empty] | 2022-11-16 |  | 2023-04-06 |  | G | [5 empty] | 2023-06-05 |  | 2023-06-30 |  | G | 2023-09-20 |  | 2023-09-20 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.39646
2070 | 111715 | #SMART18 - Courthouse Rd Tr (Salem Ch Rd to Cts Complex Rd) | 2099 | Secondary | Safety | Locally | Chesterfield County | CHESTERFIELD | Richmond | Richmond:Chesterfield County | Infrastructure Investment Division | Michael S Gray | Mike.Gray@vdot.virginia.gov | (804) 609-5347 | Michael S Gray | Mike.Gray@vdot.virginia.gov | (804) 609-5347 | Nate Mathis | mathisn@chesterfield.gov | 7481037 | 1 | 2018 | 0 | FY2022 | 1200000 | 1200000 | ACTIVITY DATES SET | G | Complete Purchasing Right-of-Way milestone finished 234 days early | G | Project is on budget | 2019-07-01 | 2018-09-28 | 2019-09-24 | 2018-10-20 | G | 2019-09-25 | 2018-10-22 | 2021-09-30 | 2018-11-29 | G | 2019-09-30 | 2018-11-30 | 2020-04-09 | 2019-08-08 | G | [5 empty] | 2020-07-29 | 2020-05-15 | 2020-07-29 | 2020-05-15 | G | 2020-08-06 | 2020-05-26 | 2020-08-27 | 2020-06-22 | G | [5 empty] | 2020-08-31 | 2020-07-09 | 2021-04-15 | 2020-08-24 | G | 2019-11-14 | 2020-07-20 | 2020-07-21 | 2020-07-20 | G | [5 empty] | 2022-01-19 |  | 2022-01-19 |  | G | 2022-04-12 |  | 2022-04-12 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.1874
2071 | 112984 | GOODWIN ROAD - MILLING, PAVING AND RECONSTRUCTION | 9999 | Urban | Resurfacing | Locally | Orange | LOUISA | Culpeper | NonMPO:NonMPO | Local Assistance Division | Ken Connors |  |  | John P Price | John.Price@VDOT.Virginia.gov | (540) 347-6371 | JOHN COOLEY | townplanner@townoforange.org | (540) 672-6917 | 0 |  | 0 | FY2019 | 29464 | 29464 | WAITING FINANCIAL CLOSURE | G | Obtained Permits milestone finished 5 days early | G | Project is on budget | 2019-02-21 | 2018-07-01 | 2019-05-15 | 2018-07-09 | G | [5 empty] | 2019-02-21 | 2018-12-01 | 2019-03-06 | 2018-12-01 | G | [25 empty] | 2019-03-01 | 2019-03-01 | 2019-03-06 | 2019-03-01 | G | [5 empty] | 2018-12-17 | 2018-12-17 | 2019-01-15 | 2019-01-03 | G | 2019-01-16 | 2019-01-16 | 2019-02-01 | 2019-02-01 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.047858
2072 | 113492 | CANAL WALK (CAP TRAIL CONN) PH II |  | Primary | Facilities for Pedestrians and Bicycles | Locally | Richmond | ASHLAND | Richmond | Richmond:Richmond | Local Assistance Division | Jorg Huckabee-Mayfield | Jorg.Huckabee-Mayfield@VDOT.Virginia.gov | (804) 609-5292 | Jorg Huckabee-Mayfield | Jorg.Huckabee-Mayfield@VDOT.Virginia.gov | (804) 609-5292 | Yongping Wang | Yongping.Wang@Richmondgov.com | (804) 646-2467 | 0 |  | 0 | FY2023 | 550000 | 550000 | NO DATES SET YET-PE OPEN | Y | Determine Requirements milestone is 19 days ahead of the expected completion date and there is a risk of missing this milestone date | G | Project is on budget | 2019-10-02 | 2019-10-02 | 2020-02-14 | 2019-10-25 | G | 2020-02-25 | 2019-09-11 | 2020-03-09 | 2019-09-11 | G | 2020-08-31 |  | 2021-03-12 |  | Y | [25 empty] | 2020-11-09 |  | 2021-07-16 |  | G | [5 empty] | 2022-03-31 |  | 2022-04-27 |  | G | 2022-10-11 |  | 2022-10-11 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.21515
2074 | 114095 | RTE 29 - SHOULDER WIDENING, RUMBLE STRIPS, GR (NELSON) | 6029 | Primary | Safety | VDOT | Nelson County | APPOMATTOX | Lynchburg | NonMPO:NonMPO | Infrastructure Investment Division | Anthony W Revelle | Anthony.Revelle@vdot.virginia.gov | (434) 856-8258 | Anthony W Revelle | Anthony.Revelle@vdot.virginia.gov | (434) 856-8258 |  |  |  | 0 |  | 0 | FY2022 | 8524100 | 8524100 | NO DATES SET YET | G | Determine Requirements milestone is 150 days ahead of the expected completion date | G | Project is on budget | [10 empty] | 2021-07-15 |  | 2021-07-21 |  | G | [25 empty] | 2021-07-15 |  | 2022-01-25 |  | G | [5 empty] | 2022-03-08 |  | 2022-03-08 |  | G | 2022-05-26 |  | 2022-05-26 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.10554
2075 | 115377 | Traffic Signal System Communications Network Upgrades |  | Urban | Traffic Management/Engineering | Locally | Norfolk | NORFOLK | Hampton Roads | Hampton Roads:Norfolk | Infrastructure Investment Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Derrick Williams | Derrick.Williams@vdot.virginia.gov | (757) 956-3097 | Rob Brown | Robert.Brown@norfolk.gov | (757) 664-7305 | 0 |  | 0 | FY2027 | 1000000 | 1000000 | NO DATES SET YET | G | Agreement with Locality milestone is 1432 days ahead of the expected completion date | Y | Estimate not current | 2024-10-23 |  | 2025-01-23 |  | G | 2025-01-24 |  | 2025-01-28 |  | G | 2025-01-29 |  | 2025-08-01 |  | G | [25 empty] | 2025-09-09 |  | 2026-05-15 |  | G | [5 empty] | 2026-08-20 |  | 2026-09-17 |  | G | 2026-12-10 |  | 2026-12-10 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.41095
2076 | 115526 | #SMART20 Mt Pleasant Rd/Great Bridge BYP Interchange Imprvmt | 0168 | Urban | Reconstruction w/o Added Capacity | Locally | Chesapeake | NORFOLK | Hampton Roads | Hampton Roads:Chesapeake | Infrastructure Investment Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Johndel A Alcaide | John.Alcaide@vdot.virginia.gov | (757) 956-3098 | Troy Eisenberger | teisenberger@cityofchesapeake.net | (757) 382-6283 | 1 | 2020 | 0 | FY2026 | 6000708 | 6000708 | NO DATES SET YET | G | Agreement with Locality milestone is 918 days ahead of the expected completion date | Y | Estimate not current | 2023-06-05 |  | 2023-08-28 |  | G | 2023-08-29 |  | 2023-08-31 |  | G | 2023-09-01 |  | 2024-03-14 |  | G | [25 empty] | 2024-04-19 |  | 2024-12-23 |  | G | [5 empty] | 2025-04-02 |  | 2025-04-29 |  | G | 2025-07-18 |  | 2025-07-18 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.19638
2077 | 116804 | ITTF HIGH SPEED COMMUNICATIONS ARTERIALS - CENTRAL | 9999 | Miscellaneous | Traffic Management/Engineering | VDOT | Statewide |  | Statewide | NonMPO:NonMPO | Infrastructure Investment Division | Catherine C Mcghee | Cathy.McGhee@VDOT.Virginia.gov | (434) 293-1973 | Anastasia Kapitan | Anastasia.Kapitan@vdot.virginia.gov | (540) 899-4292 |  |  |  | 0 |  | 0 | FY2020 | 469700 | 469700 | ACTIVITY DATES SET | R | Solicit Bids milestone is 257 days past the expected completion date | G | Project is on budget | [10 empty] | 2020-04-13 | 2020-05-04 | 2020-08-18 | 2020-05-04 | G | [35 empty] | 2020-06-03 |  | 2020-06-09 |  | R | 2020-06-10 |  | 2020-06-16 |  | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | WORK/TASK ORDER | 0 | 1 | 0.25869
2078 | 116866 | PLEASANT VALLEY ROAD TRAFFIC IMPROVEMENTS |  | Urban | Reconstruction w/ Added Capacity | Locally | Winchester | EDINBURG | Staunton | Winchester:Winchester | Local Assistance Division | Kimberly Cameron | Kim.Cameron@vdot.virginia.gov | (540) 332-7886 | Kimberly Cameron | Kim.Cameron@vdot.virginia.gov | (540) 332-7886 | Perry Eisenach | perry.eisenach@winchesterva.gov | (540) 667-1815 | 0 |  | 0 | FY2025 | 1000000 | 1000000 | NO DATES SET YET | G | Agreement with Locality milestone is 107 days ahead of the expected completion date | G | Project is on budget | 2021-02-01 |  | 2021-06-08 |  | G | 2021-06-09 |  | 2021-06-29 |  | G | 2021-07-29 |  | 2021-11-22 |  | G | [25 empty] | 2024-01-04 |  | 2024-06-04 |  | G | [5 empty] | 2024-08-01 |  | 2024-08-28 |  | G | 2024-11-19 |  | 2024-11-19 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.16899
2079 | 117039 | Maude Trevvett Elementary Connection - Sidewalk | 7663 | Secondary | Facilities for Pedestrians and Bicycles | Locally | Henrico County | ASHLAND | Richmond | Richmond:Henrico County | Local Assistance Division | Cynthia Crouch | Cynthia.Crouch@vdot.virginia.gov | (804) 609-5313 | Cynthia Crouch | Cynthia.Crouch@vdot.virginia.gov | (804) 609-5313 | TBD |  | TBD | 0 |  | 0 | FY2029 | 506068 | 506068 | NO DATES SET YET | G | Agreement with Locality milestone is 1543 days ahead of the expected completion date | G | Project is on budget | 2025-01-06 |  | 2025-05-14 |  | G | 2025-05-15 |  | 2025-06-05 |  | G | 2025-12-15 |  | 2026-04-10 |  | G | [10 empty] | 2027-07-30 |  | 2027-09-02 |  | G | [5 empty] | 2027-09-03 |  | 2028-02-09 |  | G | 2028-01-05 |  | 2028-06-05 |  | G | [5 empty] | 2028-05-12 |  | 2028-06-09 |  | G | 2028-08-29 |  | 2028-08-29 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.34756
2080 | 117083 | RANDOM HILLS RD AND POST FOREST DR SHARED USE PATHS | 9999 | Secondary | Facilities for Pedestrians and Bicycles | VDOT | Fairfax County | FAIRFAX | Northern Virginia | Northern Virginia:Fairfax County | Infrastructure Investment Division | Andrew G Beacher | Andrew.Beacher@vdot.virginia.gov | (703) 259-2239 | Hong Ha | Hong.Ha@VDOT.Virginia.gov | (703) 259-2907 | Lauren Delmare | lauren.delmare@fairfaxcounty.gov | (703) 877-5781 | 0 |  | 0 | FY2025 | 4880000 | 4880000 | NO DATES SET YET-PE OPEN | G | Start Development milestone finished 5 days early | G | Project is on budget | 2019-11-12 | 2020-04-22 | 2020-04-22 | 2020-04-22 | G | 2020-04-23 | 2020-05-12 | 2020-05-20 | 2020-05-15 | G | 2020-05-21 | 2020-05-18 | 2022-03-08 |  | G | [5 empty] | 2022-02-25 |  | 2022-04-07 |  | G | 2023-04-06 |  | 2023-04-19 |  | G | 2023-12-12 |  | 2024-09-12 |  | G | 2023-05-05 |  | 2024-02-09 |  | G | 2022-09-19 |  | 2023-03-30 |  | G | [5 empty] | 2024-10-08 |  | 2024-10-08 |  | G | 2025-01-03 |  | 2025-01-03 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.082429
2081 | 117140 | Hoffler Creek Parkway Active Transportation Improvements | 0949 | Urban | Facilities for Pedestrians and Bicycles | Locally | Portsmouth | NORFOLK | Hampton Roads | Hampton Roads:Portsmouth | Local Assistance Division | Susan Wilson | Susan.Wilson@vdot.virginia.gov | (757) 956-3099 | Marci Thompson | Marci.Thompson@vdot.virginia.gov | (757) 956-3093 | James Wright | wrightj@portsmouthva.gov | (757) 393-8592 | 0 |  | 0 | FY2024 | 600000 | 600000 | NO DATES SET YET | R | Agreement with Locality milestone is 72 days past the expected completion date | G | Project is on budget | 2020-08-03 |  | 2020-12-11 |  | R | 2020-12-14 |  | 2021-01-05 |  | R | 2021-07-14 |  | 2021-11-04 |  | G | [25 empty] | 2022-11-01 |  | 2023-04-06 |  | G | [5 empty] | 2023-06-05 |  | 2023-06-30 |  | G | 2023-09-20 |  | 2023-09-20 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.11858
2082 | 118495 | OLD BRIDGE RD SW-OAKWOOD TO FOREST HILLS |  | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Prince William County | MANASSAS | Northern Virginia | Northern Virginia:Prince William County | Local Assistance Division | Angel Tao | Angel.Tao@vdot.virginia.gov | (703) 259-2377 | Saif-Ur Qargha | Saif.Qargha@vdot.virginia.gov | (703) 259-3223 | Khattab Shammout | kshammout@pwcgov.org | (703) 792-6826 | 0 |  | 0 | FY2025 | 1700000 | 1700000 | NO DATES SET YET | G | Agreement with Locality milestone is 107 days ahead of the expected completion date | G | Project is on budget | 2021-02-01 |  | 2021-06-08 |  | G | 2021-06-09 |  | 2021-06-29 |  | G | 2022-01-10 |  | 2022-05-04 |  | G | [10 empty] | 2023-08-23 |  | 2023-09-27 |  | G | [5 empty] | 2023-09-28 |  | 2024-03-05 |  | G | 2024-10-30 |  | 2025-04-04 |  | G | [5 empty] | 2024-06-06 |  | 2024-10-31 |  | G | 2025-01-28 |  | 2025-06-30 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.41587
2083 | 102715 | Bridge Replacement - Churchland Bridge | 0017 | Urban | Bridge Replacement w/o Added Capacity | Locally | Portsmouth | NORFOLK | Hampton Roads | Hampton Roads:Portsmouth | Local Assistance Division | Stephen Rowan | Steve.Rowan@vdot.virginia.gov | (757) 790-9925 | Marci Thompson | Marci.Thompson@vdot.virginia.gov | (757) 956-3093 | James E. Wright Jr., PE | wrightj@portsmouthva.gov | (757) 393-8592 | 0 |  | 0 | FY2019 | 35461000 | 34724044 | CONSTRUCTION STARTED | R | Start Delivery milestone finished 376 days late | Y | Estimate not current | [5 empty] | 2012-08-01 | 2013-10-31 | 2012-11-01 | 2013-10-31 | R | 2014-06-02 | 2013-08-13 | 2014-10-01 | 2013-09-13 | G | [10 empty] | 2014-10-31 | 2014-10-31 | 2014-10-31 | 2014-10-31 | G | [20 empty] | 2014-11-03 | 2014-11-03 | 2016-06-01 | 2019-04-18 | R | 2016-07-01 | 2016-12-06 | 2018-11-29 | 2019-12-10 | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.22694
2084 | 104875 | RTE 606 - ROUNDABOUT | 0606 | Secondary | Safety | Locally | Hanover County | ASHLAND | Richmond | Richmond:Hanover County | Infrastructure Investment Division | Brian J Lokker | Brian.Lokker@VDOT.Virginia.gov | (804) 524-6010 | Brian J Lokker | Brian.Lokker@VDOT.Virginia.gov | (804) 524-6010 | Joe Vidunas | jevidunas@co.hanover.va.us | (804) 365-6176 | 0 |  | 0 | FY2019 | 1745000 | 2654000 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 131 days early | R | Project estimate is less than $5M and is 20% or more over budget | 2013-08-22 | 2013-08-21 | 2013-12-31 | 2014-03-14 | R | 2014-03-31 | 2014-04-16 | 2014-03-31 | 2014-04-16 | R | 2015-07-31 | 2015-06-16 | 2015-07-31 | 2015-07-22 | G | [10 empty] | 2016-04-04 | 2016-04-04 | 2016-04-13 | 2016-04-13 | G | [20 empty] | 2018-02-01 | 2018-02-01 | 2018-02-28 | 2018-02-28 | G | 2018-09-30 | 2018-05-22 | 2018-09-30 | 2018-05-22 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.1398
2085 | 107121 | Roadway Departure Chevron Initiative | 9999 | Primary | Safety | VDOT | Bristol District-wide |  | Bristol | NonMPO:NonMPO | Infrastructure Investment Division | Brian Holt | Brian.Holt@vdot.virginia.gov | (276) 696-3414 | Jeremy J Mullins | Jeremy.Mullins@vdot.virginia.gov | (276) 696-3259 |  |  |  | 0 |  | 0 | FY2020 | 1120000 | 2667502 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished on-time | R | Project estimate is less than $5M and is 20% or more over budget | [5 empty] | 2016-07-01 | 2016-07-01 | 2016-07-15 | 2016-07-15 | G | 2016-07-18 | 2016-07-18 | 2018-09-14 | 2018-08-27 | G | [35 empty] | 2019-06-05 | 2019-06-11 | 2019-06-05 | 2019-06-11 | R | 2019-07-19 | 2019-08-08 | 2019-08-08 | 2019-08-08 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.069417
2086 | 107962 | RTE 7 - INTERSECTION IMPROVEMENTS AT BEAUREGARD, PHASE II | 0007 | Urban | Reconstruction w/ Added Capacity | Locally | Alexandria | FAIRFAX | Northern Virginia | Northern Virginia:Alexandria | Infrastructure Investment Division | Amir Salahshoor | A.Salahshoor@VDOT.Virginia.gov | (703) 259-1957 | Susie X Lue | Susie.Lue@vdot.virginia.gov | (703) 259-2918 | Tafesse Gyes | Tafesse.Gyes@alexandriava.gov | (703) 746-4051 | 0 |  | 0 | FY2022 | 6727512 | 6727512 | ACTIVITY DATES SET | R | Determine Requirements milestone finished 862 days late | G | Project is on budget | [5 empty] | 2015-09-15 | 2015-09-15 | 2015-09-28 | 2017-02-06 | R | 2015-09-29 | 2017-01-10 | 2015-10-27 | 2018-03-07 | R | [35 empty] | 2020-11-03 |  | 2021-05-27 |  | G | 2021-10-06 |  | 2022-01-05 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.35595
2087 | 109190 | LABURNUM AVENUE SIDEWALK | 9999 | Secondary | Facilities for Pedestrians and Bicycles | Locally | Henrico County | ASHLAND | Richmond | Richmond:Henrico County | Infrastructure Investment Division | Douglas L Orcutt | Doug.Orcutt@vdot.virginia.gov | (804) 609-5428 | Douglas L Orcutt | Doug.Orcutt@vdot.virginia.gov | (804) 609-5428 | Kevin Newcomb, Henrico County | new038@henrico.us | (804) 501-5532 | 0 |  | 0 | FY2022 | 833973 | 1219203 | ACTIVITY DATES SET | R | Complete Purchasing Right-of-Way milestone is 33 days past the expected completion date | R | Project estimate is less than $5M and is 20% or more over budget | 2016-07-01 | 2016-07-01 | 2017-08-21 | 2017-08-21 | G | 2016-09-08 | 2016-09-08 | 2016-09-08 | 2016-09-08 | G | 2017-09-17 | 2017-09-17 | 2018-06-15 | 2018-05-29 | G | [5 empty] | 2019-05-15 | 2019-10-02 | 2019-11-01 | 2020-01-09 | R | 2019-11-04 | 2020-06-15 | 2019-12-18 | 2020-07-28 | R | [5 empty] | 2019-12-31 | 2020-07-29 | 2021-01-19 |  | R | [10 empty] | 2021-03-18 |  | 2021-04-26 |  | G | 2021-04-27 |  | 2021-10-26 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.26115
2088 | 110038 | #SMART20 - S. WASHINGTON STREET MULTI-MODAL IMPROVEMENTS | 0029 | Urban | Facilities for Pedestrians and Bicycles | Locally | Falls Church | FAIRFAX | Northern Virginia | Northern Virginia:Falls Church | Infrastructure Investment Division | Amir Salahshoor | A.Salahshoor@VDOT.Virginia.gov | (703) 259-1957 | Rita Hockman | Rita.Hockman@vdot.virginia.gov | (804) 824-7421 | Susan Long | slong@fallschurchva.gov | (703) 248-5401 | 1 | 2020 | 0 | FY2019 | 9009337 | 9009337 | CONSTRUCTION STARTED | R | Start Delivery milestone finished 428 days late | G | Project is on budget | 2016-09-01 | 2016-09-01 | 2016-11-30 | 2016-11-30 | G | 2016-12-01 | 2016-12-01 | 2016-12-05 | 2016-12-05 | G | 2016-12-06 | 2016-12-06 | 2017-06-13 | 2017-06-13 | G | [10 empty] | 2018-04-10 | 2018-04-10 | 2018-04-30 | 2018-04-30 | G | [5 empty] | 2018-05-02 | 2018-05-02 | 2019-02-13 | 2019-02-13 | G | [10 empty] | 2019-03-04 | 2019-10-01 | 2019-03-29 | 2020-02-14 | R | 2019-04-01 | 2020-02-18 | 2019-05-09 | 2020-07-10 | R | Project has been delayed due to unresolved funding issues | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.33625
2089 | 110624 | #SGR18VB - RT 11 OVER NSRR (STR. 12118) - DECK REPLACE | 0011 | Primary | Bridge Rehab w/o Added Capacity | VDOT | Montgomery County | CHRISTIANSBURG | Salem | Roanoke:Montgomery County | Infrastructure Investment/Asset Management Division | Anthony T Marshall | Todd.Marshall@VDOT.Virginia.gov | (540) 387-5460 | Leslie T Repass | Todd.Repass@VDOT.Virginia.gov | (540) 381-7195 |  |  |  | 0 |  | 1 | FY2021 | 2625000 | 2625000 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 94 days early | G | Project is on budget | [5 empty] | 2017-03-30 | 2017-03-30 | 2017-04-14 | 2017-04-14 | G | 2017-04-17 | 2017-04-17 | 2019-01-07 | 2019-01-07 | G | [10 empty] | 2019-03-19 | 2019-03-19 | 2019-04-29 | 2019-04-29 | G | 2019-04-30 | 2019-04-30 | 2019-09-05 | 2020-09-01 | R | [5 empty] | 2018-09-06 | 2018-09-06 | 2018-09-18 | 2018-09-18 | G | [5 empty] | 2020-09-08 | 2020-09-08 | 2020-09-08 | 2020-09-08 | G | 2020-10-29 | 2020-11-17 | 2021-02-19 | 2020-11-17 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.13366
2090 | 117121 | Portsmouth Pedestrian Enhancements |  | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Portsmouth | NORFOLK | Hampton Roads | Hampton Roads:Portsmouth | Local Assistance Division | Susan Wilson | Susan.Wilson@vdot.virginia.gov | (757) 956-3099 | Marci Thompson | Marci.Thompson@vdot.virginia.gov | (757) 956-3093 | James, E. Wright, Jr. PE | wrightj@portsmouthva.gov | (757) 393-8592 | 0 |  | 0 | FY2024 | 388625 | 388625 | NO DATES SET YET | G | Agreement with Locality milestone is 80 days ahead of the expected completion date | G | Project is on budget | 2021-01-04 |  | 2021-05-12 |  | G | 2021-05-13 |  | 2021-06-03 |  | G | 2021-12-13 |  | 2022-04-08 |  | G | [25 empty] | 2023-04-05 |  | 2023-08-31 |  | G | [5 empty] | 2023-10-31 |  | 2023-11-30 |  | G | 2024-02-23 |  | 2024-02-23 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.36616
2091 | 118309 | GRANT AVENUE | 0234 | Urban | Reconstruction w/o Added Capacity | Locally | Manassas | MANASSAS | Northern Virginia | Northern Virginia:Manassas | Local Assistance Division | Angel Tao | Angel.Tao@vdot.virginia.gov | (703) 259-2377 | Marlene Pinedo Fortich | Sofia.Pinedo@vdot.virginia.gov | (703) 259-1724 | Chloe Delhomme | cedelhomme@manassasva.gov | (703) 257-8235 | 0 |  | 0 | FY2028 | 6403590 | 6403590 | NO DATES SET YET | G | Agreement with Locality milestone is 1433 days ahead of the expected completion date | G | Project is on budget | 2024-07-01 |  | 2025-01-24 |  | G | 2025-01-27 |  | 2025-02-14 |  | G | 2025-08-21 |  | 2026-02-18 |  | G | [25 empty] | 2027-03-15 |  | 2027-08-10 |  | G | [5 empty] | 2027-09-09 |  | 2027-11-04 |  | G | 2028-02-01 |  | 2028-03-28 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.15291
2092 | 101039 | SOUTH CRATER ROAD AREA - SIGNAL COORDINATION | 0301 | Urban | Safety | Locally | Petersburg | PETERSBURG | Richmond | Tri-Cities:Petersburg | Infrastructure Investment Division | James Shepherd | James.Shepherd@vdot.virginia.gov | (804) 609-5305 | James Shepherd | James.Shepherd@vdot.virginia.gov | (804) 609-5305 | Bill Riggleman, City of Petersburg | briggleman@petersburg-va.gov | (804) 733-2355 | 0 |  | 0 | FY2021 | 1900000 | 2029255 | ACTIVITY DATES SET | R | Start Purchasing Right-of-Way milestone is 254 days past the expected completion date | Y | Project estimate is less than $5M and is up to 20% over budget | 2013-07-01 | 2013-07-01 | 2014-01-10 | 2014-01-10 | G | 2013-09-27 | 2013-09-27 | 2013-09-27 | 2013-09-27 | G | 2015-03-16 | 2015-03-16 | 2019-05-22 | 2019-05-17 | G | [5 empty] | 2020-12-04 | 2020-12-04 | 2020-12-24 | 2020-12-18 | G | 2020-06-01 | 2020-05-27 | 2020-06-12 |  | R | 2021-01-12 |  | 2021-02-25 |  | Y | 2020-06-15 |  | 2021-01-11 |  | R | 2019-07-22 | 2020-04-17 | 2020-05-29 | 2020-04-17 | G | [5 empty] | 2021-02-24 |  | 2021-03-09 |  | Y | 2021-06-01 |  | 2021-06-30 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.10682
2093 | 102969 | Streetscaping, storm, sanitary, underground utilites | 0000 | Urban | New Construction Roadway | Locally | Newport News | WILLIAMSBURG | Hampton Roads | Hampton Roads:Newport News | Local Assistance Division | Vincent P Urbano | urbanovp@nnva.gov | (757) 251-8287 | Chessica Villaflores | Chessica.Villaflores@vdot.virginia.gov | (757) 956-3094 | Vincent Urbano | vurbano@nngov.com | (757) 926-3977 | 0 |  | 0 | FY2021 | 900000 | 12170724 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 655 days early | R | Project estimate is less than $5M and is 20% or more over budget | [5 empty] | 2012-05-02 | 2013-05-07 | 2012-05-02 | 2013-05-24 | R | 2012-06-01 | 2012-05-20 | 2012-10-01 | 2013-05-10 | R | [10 empty] | 2015-07-01 | 2015-07-01 | 2015-11-02 | 2015-11-02 | G | [20 empty] | 2017-07-17 | 2018-04-30 | 2018-04-30 | 2018-06-18 | R | 2020-01-14 | 2018-07-20 | 2020-07-06 | 2018-09-20 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.27103
2094 | 106929 | ALINE AVENUE WALKWAY | 3402 | Secondary | Facilities for Pedestrians and Bicycles | Locally | Fairfax County | FAIRFAX | Northern Virginia | Northern Virginia:Fairfax County | Infrastructure Investment Division | Amir Salahshoor | A.Salahshoor@VDOT.Virginia.gov | (703) 259-1957 | Rita Hockman | Rita.Hockman@vdot.virginia.gov | (804) 824-7421 | Brook Khorashadi | fereshteh.khorashadi@fairfaxco | (703) 877-5737 | 0 |  | 0 | FY2019 | 575000 | 465000 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 358 days early | Y | Estimate not current | [10 empty] | 2015-03-03 | 2015-03-03 | 2015-03-03 | 2015-03-03 | G | [10 empty] | 2016-03-31 | 2016-03-31 | 2016-04-13 | 2016-04-13 | G | 2017-11-21 | 2017-05-17 | 2018-05-31 | 2017-11-21 | G | 2016-04-29 | 2016-04-29 | 2016-11-02 | 2016-04-29 | G | [10 empty] | 2018-09-04 | 2017-09-15 | 2018-09-04 | 2017-09-15 | G | 2018-10-18 | 2017-11-14 | 2018-11-07 | 2017-11-14 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.12568
2095 | 107283 | Sidewalk Missing Links - Various Locations | 0000 | Urban | Facilities for Pedestrians and Bicycles | Locally | Blacksburg | CHRISTIANSBURG | Salem | New River Valley:Blacksburg | Local Assistance Division | James M Guy | james.guy@vdot.virginia.gov | (540) 387-5247 | Adam J Czesnowski | Adam.Czesnowski@vdot.virginia.gov | (540) 541-1216 | Randy Formica | rformica@blacksburg.gov |  | 0 |  | 0 | FY2019 | 152838 | 311838 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 222 days early | R | Project estimate is less than $5M and is 20% or more over budget | 2015-11-02 | 2015-07-27 | 2016-02-02 | 2015-07-27 | G | 2016-02-03 | 2015-09-28 | 2016-02-17 | 2015-09-28 | G | 2016-02-18 | 2015-07-28 | 2016-10-07 | 2017-01-18 | R | [10 empty] | 2017-08-29 | 2017-09-12 | 2017-09-12 | 2017-09-12 | G | [20 empty] | 2018-01-09 | 2018-01-30 | 2018-06-01 | 2018-01-31 | G | 2018-06-04 | 2018-02-01 | 2018-12-03 | 2018-04-25 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.16076
2096 | 108794 | Warwick Blvd/Harpersville Road Intersection Improvements | 0060 | Urban | Traffic Management/Engineering | Locally | Newport News | WILLIAMSBURG | Hampton Roads | Hampton Roads:Newport News | Infrastructure Investment Division | Stephen Rowan | Steve.Rowan@vdot.virginia.gov | (757) 790-9925 | Chessica Villaflores | Chessica.Villaflores@vdot.virginia.gov | (757) 956-3094 | Bryan Stilley | bstilley@nnva.gov | (757) 926-8699 | 0 |  | 0 | FY2023 | 661541 | 750491 | ACTIVITY DATES SET | R | Determine Requirements milestone finished 387 days late | Y | Project estimate is less than $5M and is up to 20% over budget | 2017-02-27 | 2017-02-27 | 2017-02-27 | 2017-02-27 | G | 2016-08-16 | 2016-08-16 | 2016-08-16 | 2016-08-16 | G | 2016-08-17 | 2016-08-17 | 2019-04-01 | 2020-04-22 | R | [10 empty] | 2021-04-26 |  | 2021-05-14 |  | G | [5 empty] | 2021-05-18 |  | 2022-07-29 |  | G | [10 empty] | 2022-08-16 |  | 2022-11-09 |  | G | 2022-11-10 |  | 2023-05-08 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.34963
2097 | 109377 | #HB2.FY17 I-81 Exit 220 and Exit 221 Decel/Accel Extensions | 0081 | Interstate | Safety | VDOT | Augusta County | HARRISONBURG | Staunton | SAW:Augusta County | Infrastructure Investment Division | Ronald L Tabor | Ronald.Tabor@vdot.virginia.gov | (540) 332-7887 | Ronald L Tabor | Ronald.Tabor@vdot.virginia.gov | (540) 332-7887 |  |  |  | 1 | 2017 | 0 | FY2018 | 5612938 | 5612938 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 33 days early | G | Project is on budget | [5 empty] | 2016-08-01 | 2016-08-01 | 2016-08-11 | 2016-08-11 | G | 2016-08-15 | 2016-08-15 | 2017-04-11 | 2017-04-11 | G | [5 empty] | 2017-07-17 | 2017-04-25 | 2017-07-17 | 2017-04-25 | G | [5 empty] | 2017-08-18 | 2017-08-22 | 2017-12-14 | 2017-08-22 | G | [5 empty] | 2017-08-03 | 2017-08-03 | 2017-11-03 | 2017-08-03 | G | [5 empty] | 2018-01-09 | 2018-01-09 | 2018-01-09 | 2018-01-09 | G | 2018-03-05 | 2018-04-27 | 2018-05-30 | 2018-04-27 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.082477
2098 | 110367 | ROUTE 643-RESURFACE UNPAVED ROAD | 0643 | Secondary | Resurfacing | VDOT | Montgomery County | CHRISTIANSBURG | Salem | New River Valley:Montgomery County | Infrastructure Investment Division | Paul Brown |  |  | Audra Parson | Audra.Parson@vdot.virginia.gov | (540) 951-3727 |  |  |  | 0 |  | 0 | FY2023 | 1583943 | 1439948 | ACTIVITY DATES SET | G | Start Purchasing Right-of-Way milestone finished on-time | G | Project is on budget | [5 empty] | 2020-07-23 | 2019-01-28 | 2020-08-05 | 2019-03-01 | G | 2020-08-06 | 2019-03-04 | 2021-06-28 | 2020-09-09 | G | [5 empty] | 2020-09-09 | 2020-09-09 | 2020-09-09 | 2020-09-09 | G | 2020-10-22 | 2020-10-22 | 2020-10-22 | 2020-10-22 | G | 2020-08-31 | 2020-08-31 | 2020-08-31 | 2020-08-31 | G | 2020-10-23 | 2020-10-23 | 2022-04-08 |  | G | [10 empty] | 2022-06-14 |  | 2022-06-14 |  | G | 2022-08-04 |  | 2022-12-14 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | SAAP CONTRACT | 0 | 0 | 0.0944
2100 | 111027 | #SMART18 - (St) GREEN CIRCLE TRAIL - FINAL PHASES |  | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Winchester | EDINBURG | Staunton | Winchester:Winchester | Infrastructure Investment Division | Clifton Balderson | clifton.balderson@dbiservices.com | (540) 460-1313 | Kimberly Cameron | Kim.Cameron@vdot.virginia.gov | (540) 332-7886 | Perry Eisenach | perry.eisenach@winchesterva.gov | (540) 667-2085 | 1 | 2018 | 0 | FY2024 | 5754500 | 5492000 | NO DATES SET YET-PE OPEN | G | Start Development milestone finished 577 days early | G | Project is on budget | 2021-08-03 | 2020-02-18 | 2021-08-03 | 2020-02-18 | G | 2021-10-27 | 2020-02-18 | 2021-10-29 | 2020-03-31 | G | 2021-11-01 |  | 2022-05-11 |  | G | [10 empty] | 2023-05-12 |  | 2023-06-02 |  | G | [5 empty] | 2023-06-06 |  | 2024-03-19 |  | G | [10 empty] | 2024-04-04 |  | 2024-05-01 |  | G | 2024-05-02 |  | 2024-06-12 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.30638
2101 | 111537 | CITY OF FAIRFAX PRIMARY EXTENSION PAVING FY18 - RTE 123 | 0123 | Urban | Resurfacing | Locally | Fairfax | FAIRFAX | Northern Virginia | Northern Virginia:Fairfax | Local Assistance Division | Amir Salahshoor | A.Salahshoor@VDOT.Virginia.gov | (703) 259-1957 | Rita Hockman | Rita.Hockman@vdot.virginia.gov | (804) 824-7421 | Peter Millard | peter.millard@fairfaxva.gov | (703) 246-6330 | 0 |  | 0 | FY2019 | 120471 | 120471 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 140 days early | G | Project is on budget | 2017-07-03 | 2017-07-03 | 2017-10-25 | 2017-07-28 | G | [5 empty] | 2017-07-03 | 2017-11-09 | 2017-07-17 | 2017-12-12 | R | [35 empty] | 2017-12-13 | 2017-12-13 | 2018-06-29 | 2018-03-15 | G | 2018-07-02 | 2018-03-23 | 2018-08-10 | 2018-03-23 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.17518
2102 | 113267 | Hyman Street and Ballard Avenue Improvements | 0000 | Urban | Reconstruction w/o Added Capacity | Locally | Portsmouth | NORFOLK | Hampton Roads | Hampton Roads:Portsmouth | Local Assistance Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Marci Thompson | Marci.Thompson@vdot.virginia.gov | (757) 956-3093 | James Wright, P.E. | wrightj@portsmouthva.gov | (757) 393-8592 | 0 |  | 0 | FY2021 | 1341000 | 1341000 | NO DATES SET YET-PE OPEN | R | Determine Requirements milestone is 591 days past the expected completion date | G | Project is on budget | 2018-10-01 | 2018-10-01 | 2018-12-28 | 2019-02-26 | R | 2018-12-31 | 2019-02-27 | 2019-01-03 | 2019-03-08 | R | 2019-01-04 |  | 2019-07-11 |  | R | [25 empty] | 2019-08-16 | 2019-09-11 | 2020-04-23 | 2019-11-04 | G | [5 empty] | 2020-05-21 |  | 2020-06-18 |  | R | 2020-09-08 |  | 2020-09-08 |  | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.11083
2103 | 113724 | #SGR19LP - Primary EXT Paving -Hampton Blvd / 39 St / 49 St | 0337 | Urban | Resurfacing | Locally | Norfolk | NORFOLK | Hampton Roads | Hampton Roads:Norfolk | Infrastructure Investment Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Derrick Williams | Derrick.Williams@vdot.virginia.gov | (757) 956-3097 | Deborah Mangiaracina, P.E. | Deborah.Mangiaracina@norfolk.gov | (757) 664-7459 | 0 |  | 1 | FY2019 | 174524 | 174524 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished on-time | G | Project is on budget | 2018-09-04 | 2018-09-04 | 2018-11-30 | 2019-01-07 | R | 2018-12-03 | 2019-01-08 | 2018-12-05 | 2019-01-16 | R | 2018-12-06 | 2019-01-16 | 2019-06-13 | 2019-01-16 | G | [25 empty] | 2018-05-11 | 2019-01-16 | 2019-01-16 | 2019-01-16 | G | [5 empty] | 2018-12-18 | 2018-12-18 | 2019-01-16 | 2019-01-16 | G | 2019-01-16 | 2019-01-16 | 2019-01-16 | 2019-01-16 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.15088
2104 | 113917 | PEDESTRIAN IMPROVEMENTS AT MONTICELLO AVE/2ND | 3402 | Urban | Safety | Locally | Charlottesville | CHARLOTTESVILLE | Culpeper | Charlottesville:Charlottesville | Infrastructure Investment Division | Ken Connors |  |  | Michael D Barnes | MichaelD.Barnes@vdot.virginia.gov | (434) 422-9861 | Tim Motsch | Motscht@charlottesville.gov | (434) 970-3182 | 0 |  | 0 | FY2021 | 338230 | 485177 | ACTIVITY DATES SET | R | Complete Purchasing Right-of-Way milestone is 97 days past the expected completion date | R | Project estimate is less than $5M and is 20% or more over budget | 2021-10-01 | 2018-11-01 | 2021-12-30 | 2018-12-07 | G | 2022-01-03 | 2019-01-08 | 2022-01-05 | 2019-02-15 | G | 2022-01-06 | 2019-01-10 | 2022-07-13 | 2019-01-11 | G | [10 empty] | 2020-01-15 | 2019-09-26 | 2020-02-06 | 2020-02-12 | R | [5 empty] | 2020-02-10 | 2020-02-13 | 2020-11-16 |  | R | [10 empty] | 2020-12-04 |  | 2021-01-04 |  | R | 2021-03-26 |  | 2021-03-26 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.16805
2105 | 114380 | Sunrise Avenue & Oakland Boulevard Drainage Improvements | 0000 | Urban | Mitigation of Water Pollution Due to Highway Runof | Locally | Roanoke | SALEM | Salem | Roanoke:Roanoke City | Local Assistance Division | Cheryl B Becker | Cheryl.Becker@vdot.virginia.gov | (540) 492-2531 | Cheryl B Becker | Cheryl.Becker@vdot.virginia.gov | (540) 492-2531 | Joseph Arthur | Joseph.Arthur@roanokeva.gov | (540) 853-5906 | 0 |  | 0 | FY2021 | 838711 | 1421497 | ACTIVITY DATES SET | R | Solicit Bids milestone is 248 days past the expected completion date | R | Project estimate is less than $5M and is 20% or more over budget | 2018-10-01 | 2018-10-01 | 2018-12-28 | 2018-11-27 | G | 2018-12-31 | 2018-11-28 | 2019-01-03 | 2018-11-28 | G | 2019-01-04 | 2018-11-29 | 2019-07-11 | 2019-01-04 | G | [25 empty] | 2019-01-07 | 2019-01-14 | 2019-09-09 | 2019-01-14 | G | [5 empty] | 2020-05-21 |  | 2020-06-18 |  | R | 2020-09-08 |  | 2020-09-08 |  | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.20735
2106 | 115106 | NORTH MAIN STREET - Primary Extension Paving |  | Urban | Resurfacing | Locally | Lexington | LEXINGTON | Staunton | NonMPO:NonMPO | Local Assistance Division | Susan E Hammond | Susan.Hammond@VDOT.Virginia.gov | (540) 462-6990 | Michael L Branscome | Michael.Branscome@VDOT.Virginia.gov | (540) 332-2377 | City of Lexington | jmartone@lexingtonva.gov | (540) 463-3154 | 0 |  | 0 | FY2021 | 52120 | 52120 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 78 days early | G | Project is on budget | 2019-03-07 | 2020-03-05 | 2019-05-30 | 2020-03-09 | R | [5 empty] | 2019-03-07 | 2020-03-10 | 2019-03-20 | 2020-03-23 | R | [35 empty] | 2020-03-24 | 2020-03-24 | 2020-05-26 | 2020-05-26 | G | 2020-08-13 | 2020-05-27 | 2020-08-13 | 2020-05-27 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.061879
2107 | 115489 | #SMART20 RIVERMONT AND BEDFORD AVE INTERSECTION IMPROVEMENT | 9999 | Urban | Safety | Locally | Lynchburg | APPOMATTOX | Lynchburg | Lynchburg:Lynchburg | Infrastructure Investment Division | Robert F Guercia | Robert.Guercia@VDOT.Virginia.gov | (434) 841-6864 | Gregg Allen | Gregg.Allen@vdot.virginia.gov | (434) 426-5575 | LEE NEWLAND | lee.newland@lynchburgva.gov | (434) 455-3947 | 1 | 2020 | 0 | FY2027 | 485000 | 485000 | NO DATES SET YET-PE OPEN | G | Start Development milestone finished 1341 days early | G | Project is on budget | 2024-01-31 | 2020-06-01 | 2024-04-24 | 2020-07-08 | G | 2024-04-25 | 2020-08-25 | 2024-04-29 | 2020-08-27 | G | 2024-04-30 | 2020-08-28 | 2024-11-01 |  | G | [10 empty] | 2025-11-05 |  | 2025-11-26 |  | G | [5 empty] | 2025-12-02 |  | 2026-09-10 |  | G | 2024-12-12 | 2020-07-27 | 2025-08-15 | 2020-07-27 | G | [5 empty] | 2026-09-28 |  | 2026-10-26 |  | G | 2027-01-21 |  | 2027-01-21 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.19147
2108 | 116167 | #I81CIP SB MM 42.8 EXTEND ACCEL LANE (ID #17) | 0081 | Interstate | Reconstruction w/o Added Capacity | VDOT | Smyth County | ABINGDON | Bristol | NonMPO:NonMPO | Infrastructure Investment Division | Donald A Necessary | Donald.Necessary@VDOT.Virginia.gov | (276) 696-3285 | Marvin E Holley | Gene.Holley@VDOT.Virginia.gov | (276) 696-3255 |  |  |  | 0 |  | 0 | FY2022 | 2400000 | 2400000 | ACTIVITY DATES SET | G | Engage Public milestone finished 104 days early | G | Project is on budget | [5 empty] | 2020-07-01 | 2020-01-02 | 2020-07-15 | 2020-01-09 | G | 2020-07-16 | 2020-01-10 | 2021-03-12 | 2020-08-05 | G | [5 empty] | 2021-03-02 | 2020-11-13 | 2021-04-12 | 2020-12-29 | G | [5 empty] | 2021-07-27 |  | 2021-11-18 |  | G | [5 empty] | 2021-07-12 |  | 2021-10-11 |  | G | [5 empty] | 2021-12-14 |  | 2021-12-14 |  | G | 2022-03-10 |  | 2022-03-10 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.080985
2109 | 116326 | #I81CIP SWRO MAINTENANCE FOR NEW CMS & CAMERAS FY20-25 | 0081 | Interstate | Safety | VDOT | Roanoke County | SALEM | Salem | Roanoke:Roanoke County | Infrastructure Investment Division | Ricky A Via | Ricky.Via@vdot.virginia.gov | (804) 371-2396 | Timothy L Martin | TimL.Martin@VDOT.Virginia.gov | (540) 375-0113 |  |  |  | 0 |  | 0 | FY2020 | 1346024 | 1346024 | CONSTRUCTION STARTED | G | Start Delivery milestone finished on-time | G | Project is on budget | [10 empty] | 2019-09-19 | 2019-08-23 | 2020-02-03 | 2020-01-06 | G | [35 empty] | 2020-01-08 | 2020-01-08 | 2020-01-14 | 2020-01-14 | G | 2020-01-15 | 2020-01-15 | 2020-01-23 | 2020-01-23 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | WORK/TASK ORDER | 1 | 0 | 0.13046
2110 | 111065 | Rock Landing Drive @ Omni Boulevard New Traffic Signal | 9999 | Urban | Traffic Management/Engineering | Locally | Newport News | WILLIAMSBURG | Hampton Roads | Hampton Roads:Newport News | Infrastructure Investment Division | Dawn Odom | Dawn.Odom@vdot.virginia.gov | (000) 000-0000 | Chessica Villaflores | Chessica.Villaflores@vdot.virginia.gov | (757) 956-3094 | Brian Stilley | bstilley@nnva.gov | (757) 926-8699 | 0 |  | 0 | FY2023 | 1083519 | 1083519 | NO DATES SET YET-PE OPEN | R | Determine Requirements milestone is 136 days past the expected completion date | G | Project is on budget | 2019-07-01 | 2019-07-01 | 2019-09-24 | 2019-11-20 | R | 2019-09-25 | 2019-11-21 | 2019-10-08 | 2019-12-13 | R | 2019-10-09 |  | 2020-10-08 |  | R | [10 empty] | 2021-08-05 |  | 2021-08-25 |  | G | [5 empty] | 2021-08-27 |  | 2022-06-10 |  | G | [10 empty] | 2022-06-28 |  | 2022-08-09 |  | G | 2022-08-10 |  | 2023-02-06 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.35275
2111 | 113141 | Downtown Salem - Main Street, Union Street to Broad Street | 0000 | Urban | Facilities for Pedestrians and Bicycles | Locally | Salem | SALEM | Salem | Roanoke:Salem | Local Assistance Division | Cheryl B Becker | Cheryl.Becker@vdot.virginia.gov | (540) 492-2531 | Cheryl B Becker | Cheryl.Becker@vdot.virginia.gov | (540) 492-2531 | Will Simpson | wsimpson@salemva.gov | (540) 375-3032 | 0 |  | 0 | FY2023 | 1000000 | 1000000 | ACTIVITY DATES SET | R | Determine Requirements milestone finished 441 days late | G | Project is on budget | 2018-08-01 | 2018-08-01 | 2018-10-25 | 2019-03-28 | R | 2018-10-26 | 2019-03-29 | 2018-10-30 | 2019-03-29 | R | 2018-10-31 | 2019-04-01 | 2019-08-01 | 2020-10-15 | R | [10 empty] | 2021-10-20 |  | 2021-11-09 |  | G | [5 empty] | 2021-11-12 |  | 2022-08-24 |  | G | [10 empty] | 2022-08-25 |  | 2022-09-22 |  | G | 2023-02-23 |  | 2023-02-23 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.2463
2112 | 113286 | Route 660 (Old Cox Rd) reconstruction | 0660 | Primary | Reconstruction w/ Added Capacity | Locally | Mecklenburg County | SOUTH HILL | Richmond | NonMPO:NonMPO | Local Assistance Division | James Shepherd | James.Shepherd@vdot.virginia.gov | (804) 609-5305 | James Shepherd | James.Shepherd@vdot.virginia.gov | (804) 609-5305 | Wayne Carter | wayne.carter@mecklenburgva.com | (434) 738-6191 | 0 |  | 0 | FY2022 | 5354840 | 5351376 | ACTIVITY DATES SET | G | Obtained Permits milestone finished 39 days early | G | Project is on budget | 2018-07-02 | 2018-08-08 | 2018-10-02 | 2018-08-15 | G | 2018-10-03 | 2018-11-07 | 2018-11-26 | 2018-11-14 | G | 2018-11-27 | 2018-11-15 | 2019-06-04 | 2019-05-24 | G | [10 empty] | 2020-01-29 | 2020-01-29 | 2020-06-30 | 2020-04-29 | G | [5 empty] | 2020-07-02 |  | 2021-07-30 |  | G | 2019-03-07 | 2019-03-07 | 2020-11-30 | 2020-10-22 | G | [5 empty] | 2021-08-17 |  | 2022-02-28 |  | G | 2022-05-17 |  | 2022-05-31 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 |  | 0 | 1 | 0.20177
2113 | 113890 | #SGR19VB - RT 63 1042 over Russell Fork River - Fed 5792 | 0063 | Primary | Bridge Rehab w/o Added Capacity | VDOT | Dickenson County | WISE | Bristol | NonMPO:NonMPO | Infrastructure Investment/Asset Management Division | Gary Lester |  |  | Darshan K Bansal | Darshan.Bansal@vdot.virginia.gov | (276) 696-3364 |  |  |  | 0 |  | 1 | FY2023 | 7445332 | 7445332 | NO DATES SET YET | G | Determine Requirements milestone is 632 days ahead of the expected completion date | G | Project is on budget | [10 empty] | 2022-11-01 |  | 2022-11-15 |  | G | [35 empty] | 2022-12-13 |  | 2022-12-13 |  | G | 2023-03-09 |  | 2023-03-09 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 |  | 0 | 0 | 0.17507
2114 | 114015 | Glyndon & Carver Lanes - Rural Addition | 9999 | Secondary | Reconstruction w/o Added Capacity | VDOT | Sussex County | FRANKLIN | Hampton Roads | NonMPO:NonMPO | Infrastructure Investment Division | Charles T Catlett | Tommy.Catlett@vdot.virginia.gov | (757) 346-3078 | Sherry L Parker | Sherry.Parker@vdot.virginia.gov | (757) 346-3080 |  |  |  | 0 |  | 0 | FY2022 | 149127 | 149127 | NO DATES SET YET | R | Start Development milestone is 738 days past the expected completion date | G | Project is on budget | [5 empty] | 2019-02-01 |  | 2019-02-14 |  | R | 2019-02-15 |  | 2019-10-04 |  | R | [5 empty] | 2020-06-15 |  | 2020-07-27 |  | R | [5 empty] | 2020-11-10 |  | 2021-03-11 |  | Y | [5 empty] | 2020-10-26 |  | 2021-02-02 |  | R | [5 empty] | 2021-04-13 |  | 2021-04-13 |  | Y | 2021-05-27 |  | 2021-07-23 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | SAAP CONTRACT | 0 | 0 | 0.18406
2115 | 115095 | West Lee Highway Primary Extension Paving | 0011 | Urban | Resurfacing | Locally | Wytheville | WYTHEVILLE | Bristol | NonMPO:NonMPO | Local Assistance Division | John W Bechtold | John.Bechtold@vdot.virginia.gov | (276) 696-3365 | John W Bechtold | John.Bechtold@vdot.virginia.gov | (276) 696-3365 | Brian Freeman | bfreeman@wytheville.org | (276) 223-3450 | 0 |  | 0 | FY2020 | 108554 | 108554 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 5 days early | G | Project is on budget | 2019-07-01 | 2019-07-01 | 2019-09-24 | 2019-09-23 | G | [5 empty] | 2019-07-01 | 2019-07-01 | 2019-07-15 | 2019-07-15 | G | [25 empty] | 2019-07-16 | 2019-07-15 | 2019-10-08 | 2019-07-15 | G | [5 empty] | 2019-10-10 | 2019-10-09 | 2019-11-07 | 2019-11-04 | G | 2020-02-04 | 2020-01-30 | 2020-02-04 | 2020-01-30 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.057664
2116 | 115423 | George Washington Highway Widening | 0017 | Urban | Traffic Management/Engineering | Locally | Chesapeake | NORFOLK | Hampton Roads | Hampton Roads:Chesapeake | Infrastructure Investment Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Johndel A Alcaide | John.Alcaide@vdot.virginia.gov | (757) 956-3098 | Troy Eisenberger, PE | teisenberger@cityofchesapeake.net | (757) 382-6383 | 0 |  | 0 | FY2028 | 22364556 | 22364556 | NO DATES SET YET | G | Agreement with Locality milestone is 1408 days ahead of the expected completion date | Y | Estimate not current | 2024-10-01 |  | 2024-12-30 |  | G | 2024-12-31 |  | 2025-01-03 |  | G | 2025-01-06 |  | 2026-01-06 |  | G | [10 empty] | 2027-01-21 |  | 2027-02-10 |  | G | [5 empty] | 2027-02-12 |  | 2027-11-19 |  | G | 2025-08-18 |  | 2026-04-24 |  | G | [5 empty] | 2027-12-09 |  | 2028-01-07 |  | G | 2028-03-30 |  | 2028-03-30 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.39865
2117 | 115505 | #SMART20 Monticello Ave-Richmond Rd-Lafayette St Roundabout | 0005 | Urban | Reconstruction w/o Added Capacity | VDOT | Williamsburg | WILLIAMSBURG | Hampton Roads | Hampton Roads:Williamsburg | Infrastructure Investment Division | Kenneth D Mckinna | Kenneth.McKinna@VDOT.Virginia.gov | (757) 956-3271 | Kenneth D Mckinna | Kenneth.McKinna@VDOT.Virginia.gov | (757) 956-3271 | Aaron Small | asmall@williamsburgva.gov | (757) 220-6140 | 1 | 2020 | 0 | FY2029 | 6381090 | 6381090 | NO DATES SET YET | G | Start Development milestone is 1303 days ahead of the expected completion date | Y | Estimate not current | [5 empty] | 2024-07-15 |  | 2024-09-16 |  | G | 2024-09-17 |  | 2025-09-17 |  | G | [5 empty] | 2026-07-24 |  | 2026-08-06 |  | G | 2027-11-12 |  | 2027-11-29 |  | G | 2028-04-25 |  | 2028-10-27 |  | G | 2027-12-15 |  | 2028-06-21 |  | G | 2027-05-03 |  | 2027-11-04 |  | G | [5 empty] | 2028-11-14 |  | 2028-11-14 |  | G | 2029-02-09 |  | 2029-02-09 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 1 | 0.20948
2118 | 116173 | #I81CIP SB MM 38.7 Epoxy Overlay & Animal fence (ID #20) | 0081 | Interstate | Safety | VDOT | Smyth County | ABINGDON | Bristol | NonMPO:NonMPO | Infrastructure Investment Division | Donald A Necessary | Donald.Necessary@VDOT.Virginia.gov | (276) 696-3285 | Marvin E Holley | Gene.Holley@VDOT.Virginia.gov | (276) 696-3255 |  |  |  | 0 |  | 0 | FY2022 | 2100000 | 2100000 | ACTIVITY DATES SET | Y | Engage Public milestone is 18 days ahead of the expected completion date and there is a risk of missing this milestone date | G | Project is on budget | [5 empty] | 2020-07-01 | 2020-01-02 | 2020-07-15 | 2020-01-09 | G | 2020-07-16 | 2020-01-10 | 2021-06-14 | 2021-01-20 | G | [5 empty] | 2021-02-26 |  | 2021-03-11 |  | Y | 2021-05-10 |  | 2021-05-10 |  | G | 2021-03-16 | 2020-12-21 | 2021-03-16 | 2020-12-21 | G | 2021-05-12 |  | 2021-05-12 |  | G | [10 empty] | 2021-07-13 |  | 2021-07-13 |  | G | 2021-10-01 |  | 2021-10-01 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.079338
2119 | 117071 | Fort Hill Road (State Route 686) |  | Secondary | Resurfacing | VDOT | Brunswick County | SOUTH HILL | Richmond | NonMPO:NonMPO | Local Assistance Division | Todd E Wilson | Todd.Wilson@vdot.virginia.gov | (434) 774-2313 | Todd E Wilson | Todd.Wilson@vdot.virginia.gov | (434) 774-2313 | TBD |  | TBD | 0 |  | 0 | FY2025 | 50000 | 50000 | NO DATES SET YET | G | Determine Requirements milestone is 1430 days ahead of the expected completion date | G | Project is on budget | [10 empty] | 2025-01-06 |  | 2025-01-21 |  | G | [25 empty] | 2025-01-06 |  | 2025-06-05 |  | G | [5 empty] | 2025-04-08 |  | 2025-04-08 |  | G | 2025-06-26 |  | 2025-06-26 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.093681
2120 | 117095 | #REVSH21 MERRITT HILLS SUBDIVISION - DRAINAGE IMPROVEMENTS | 9999 | Urban | Reconstruction w/o Added Capacity | Locally | South Boston | HALIFAX | Lynchburg | NonMPO:NonMPO | Local Assistance Division | Gregg Allen | Gregg.Allen@vdot.virginia.gov | (434) 426-5575 | Gregg Allen | Gregg.Allen@vdot.virginia.gov | (434) 426-5575 | CW CROWDER | cwcrowder@southbostonva.us | (434) 575-4261 | 0 |  | 0 | FY2025 | 909646 | 909646 | NO DATES SET YET | G | Agreement with Locality milestone is 106 days ahead of the expected completion date | G | Project is on budget | 2021-01-29 |  | 2021-06-07 |  | G | 2021-06-08 |  | 2021-06-28 |  | G | 2022-01-07 |  | 2022-05-03 |  | G | [10 empty] | 2023-08-22 |  | 2023-09-26 |  | G | [5 empty] | 2023-09-27 |  | 2024-03-04 |  | G | 2024-01-30 |  | 2024-06-26 |  | G | [5 empty] | 2024-06-05 |  | 2024-07-02 |  | G | 2024-09-20 |  | 2024-09-20 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.073189
2121 | 118061 | State Route 161 Bike- Phase I |  | Primary | Facilities for Pedestrians and Bicycles | Locally | Richmond | ASHLAND | Richmond | Richmond:Richmond | Local Assistance Division | James Shepherd | James.Shepherd@vdot.virginia.gov | (804) 609-5305 | James Shepherd | James.Shepherd@vdot.virginia.gov | (804) 609-5305 | Jakob Helmbolt | jakob.helmbolt@richmondgov.com | (804) 646-7141 | 0 |  | 0 | FY2024 | 500000 | 500000 | NO DATES SET YET | G | Agreement with Locality milestone is 199 days ahead of the expected completion date | G | Project is on budget | 2021-05-03 |  | 2021-09-08 |  | G | 2021-09-09 |  | 2021-09-29 |  | G | 2022-04-13 |  | 2022-08-04 |  | G | [25 empty] | 2023-08-01 |  | 2024-01-03 |  | G | [5 empty] | 2024-03-05 |  | 2024-04-01 |  | G | 2024-06-19 |  | 2024-06-19 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.21496
2122 | 17630 | #SMART18 - I-264/WITCHDUCK RD INTERCHANGE & RAMP EXTENSION | 0264 | Interstate | Reconstruction w/ Added Capacity | VDOT | Virginia Beach | NORFOLK | Hampton Roads | Hampton Roads:Virginia Beach | Infrastructure Investment Division | James A Klotz | James.Klotz@vdot.virginia.gov | (757) 274-2552 | James E Poff | James.Poff@vdot.virginia.gov | (757) 956-3344 |  |  |  | 1 | 2018 | 0 | FY2018 | 66754194 |  | CONSTRUCTION STARTED | G | Start Delivery milestone finished on-time | R | Critical information missing | [5 empty] | 2000-12-01 | 2000-12-04 | 2000-12-21 | 2000-12-08 | G | 2006-09-10 | 2005-12-01 | 2007-02-10 | 2006-03-27 | G | [5 empty] | 2011-07-14 | 2011-07-14 | 2014-10-22 | 2014-10-22 | G | 2015-01-30 | 2015-01-30 | 2015-04-30 | 2015-04-30 | G | 2017-01-18 | 2017-01-18 | 2018-07-02 | 2018-07-31 | R | 2015-11-04 | 2015-11-04 | 2017-07-06 | 2017-07-06 | G | 2011-08-22 | 2011-08-22 | 2016-10-31 | 2016-10-31 | G | [5 empty] | 2017-07-25 | 2017-07-25 | 2017-07-25 | 2017-07-25 | G | 2017-12-06 | 2017-12-06 | 2017-12-06 | 2017-12-06 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.11948
2123 | 78214 | TOWN OF FRIES - Welcome Center & Trailhead construction |  | Primary | Facilities for Pedestrians and Bicycles | Locally | Fries | WYTHEVILLE | Bristol | NonMPO:NonMPO | Local Assistance Division | Tabitha H Crowder | Tabitha.Crowder@vdot.virginia.gov | (276) 696-3482 | Roger L Musser | Roger.Musser@VDOT.Virginia.gov | (276) 696-3260 | Aaron Sizemore | asizemore@mrpdc.org | (276) 783-5103 | 0 |  | 0 | FY2021 | 1158309 | 1073500 | CONSTRUCTION STARTED | G | Start Delivery milestone finished on-time | G | Project is on budget | 2019-03-27 | 2019-03-27 | 2019-08-01 | 2019-08-01 | G | 2015-03-26 | 2015-03-26 | 2015-03-27 | 2015-03-27 | G | 2019-08-02 | 2019-08-02 | 2019-12-12 | 2019-12-12 | G | [35 empty] | 2020-04-24 | 2020-04-24 | 2020-04-24 | 2020-04-24 | G | 2020-07-15 | 2020-07-15 | 2020-07-15 | 2020-07-15 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.16594
2124 | 105295 | ROSSLYN-BALLSTON CORRIDOR ACCESSIBILITY IMPROVEMENTS, PH 1 |  | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Arlington County | FAIRFAX | Northern Virginia | Northern Virginia:Arlington County | Local Assistance Division | Pamela M Liston | Pamela.Liston@VDOT.Virginia.gov | (804) 786-2734 | Rita Hockman | Rita.Hockman@vdot.virginia.gov | (804) 824-7421 | Richard Viola | rviola@arlingtonva.us | (703) 228-3699 | 0 |  | 0 | FY2019 | 330000 | 1006212 | CONSTRUCTION STARTED | R | Start Delivery milestone finished 164 days late | R | Project estimate is less than $5M and is 20% or more over budget | 2014-02-04 | 2014-02-04 | 2014-02-04 | 2014-02-04 | G | 2014-01-15 | 2014-12-15 | 2014-01-15 | 2014-12-19 | R | 2014-02-14 | 2014-02-14 | 2014-06-14 | 2014-06-14 | G | [35 empty] | 2019-02-01 | 2019-02-28 | 2019-02-01 | 2019-02-28 | R | 2019-03-01 | 2019-03-27 | 2019-03-01 | 2019-08-12 | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.36618
2125 | 107437 | TOWN CENTER PARKWAY AT SUNSET HILLS SIDEWALK | 9999 | Secondary | Facilities for Pedestrians and Bicycles | Locally | Fairfax County | FAIRFAX | Northern Virginia | Northern Virginia:Fairfax County | Infrastructure Investment Division | Amir Salahshoor | A.Salahshoor@VDOT.Virginia.gov | (703) 259-1957 | Rita Hockman | Rita.Hockman@vdot.virginia.gov | (804) 824-7421 | Wesley Minnix | Wesley.Minnix@fairfaxcounty.gov | (703) 877-5749 | 0 |  | 0 | FY2020 | 450000 | 247145 | CONSTRUCTION COMPLETED | R | Start Delivery milestone finished 140 days late | G | Project is on budget | [10 empty] | 2015-05-01 | 2015-05-01 | 2015-07-01 | 2015-07-01 | G | [10 empty] | 2015-08-05 | 2015-08-05 | 2015-08-28 | 2015-08-28 | G | 2015-08-11 | 2015-08-11 | 2015-08-11 | 2015-08-11 | G | 2015-10-06 | 2015-10-06 | 2015-10-26 | 2015-10-26 | G | [10 empty] | 2018-02-12 | 2018-02-12 | 2018-11-13 | 2019-09-17 | R | 2019-02-13 | 2019-10-31 | 2019-07-30 | 2019-12-17 | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.12526
2126 | 108500 | ROUTE 50 SIDEWALK FROM GRAHAM RD TO WOODLEY LANE | 0050 | Primary | Safety | Locally | Fairfax County | FAIRFAX | Northern Virginia | Northern Virginia:Fairfax County | Infrastructure Investment Division | Amir Salahshoor | A.Salahshoor@VDOT.Virginia.gov | (703) 259-1957 | Rita Hockman | Rita.Hockman@vdot.virginia.gov | (804) 824-7421 | Thomas Cutler | Thomas.Cutler@fairfaxcounty.gov | (703) 324-5139 | 0 |  | 0 | FY2020 | 275001 | 220402 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 376 days early | G | Project is on budget | 2015-03-06 | 2015-12-30 | 2015-05-29 | 2016-03-28 | R | 2015-06-01 | 2015-06-01 | 2015-06-03 | 2015-06-30 | R | 2015-06-04 | 2015-04-02 | 2015-12-10 | 2015-09-30 | G | [10 empty] | 2017-09-05 | 2017-09-05 | 2017-09-25 | 2017-09-25 | G | [5 empty] | 2017-09-27 | 2017-09-25 | 2018-07-11 | 2017-09-25 | G | [10 empty] | 2018-07-27 | 2018-09-14 | 2020-01-27 | 2018-10-16 | G | 2020-01-28 | 2018-08-08 | 2020-03-09 | 2019-02-27 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.075676
2127 | 109481 | #HB2.FY17 RTE 17 AT US RTE 258 INT CAPACITY IMPROVEMENTS | 0017 | Primary | Reconstruction w/ Added Capacity | VDOT | Isle of Wight County | FRANKLIN | Hampton Roads | Hampton Roads:Isle of Wight County | Infrastructure Investment Division | Charles T Catlett | Tommy.Catlett@vdot.virginia.gov | (757) 346-3078 | Wali Zaman | Wali.Zaman@VDOT.Virginia.gov | (757) 956-3272 | Charles Catlett |  |  | 1 | 2017 | 0 | FY2022 | 6770000 | 5371584 | ADVERTISED | R | Relocate Utilities milestone is 55 days past the expected completion date | G | Project is on budget | [5 empty] | 2016-10-11 | 2016-10-11 | 2016-10-24 | 2016-10-24 | G | 2016-10-25 | 2016-10-25 | 2017-06-02 | 2018-04-03 | R | [5 empty] | 2018-09-21 | 2018-07-12 | 2018-10-19 | 2018-07-12 | G | 2019-08-15 | 2019-08-15 | 2019-09-12 | 2019-08-19 | G | 2020-04-09 | 2019-09-20 | 2020-12-28 |  | R | 2019-09-27 | 2019-09-05 | 2020-03-25 | 2019-09-17 | G | 2016-11-30 | 2016-11-30 | 2019-06-28 | 2019-02-05 | G | [5 empty] | 2021-04-13 | 2020-11-04 | 2021-04-13 | 2020-11-04 | G | 2021-05-26 |  | 2021-07-22 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.17936
2128 | 109583 | US 52 Safety Improvements: HSIP | 0052 | Primary | Safety | VDOT | Carroll County | MARTINSVILLE | Salem | NonMPO:NonMPO | Infrastructure Investment Division | Alex H Price | Alex.Price@VDOT.Virginia.gov | (540) 378-5053 | Anthony L Handy | Tony.Handy@VDOT.Virginia.gov | (540) 352-9050 |  |  |  | 0 |  | 0 | FY2019 | 1400000 | 1400000 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 95 days early | G | Project is on budget | [5 empty] | 2016-07-01 | 2016-07-01 | 2016-07-13 | 2016-07-13 | G | 2017-09-26 | 2017-09-26 | 2018-04-20 | 2018-04-11 | G | [5 empty] | 2018-09-05 | 2018-05-02 | 2018-09-11 | 2018-05-08 | G | [5 empty] | 2019-01-08 | 2018-10-03 | 2019-01-08 | 2018-10-03 | G | [5 empty] | 2018-05-02 | 2018-05-20 | 2018-10-24 | 2018-05-20 | G | [5 empty] | 2019-01-08 | 2018-12-18 | 2019-01-08 | 2018-12-18 | G | 2019-05-28 | 2019-02-22 | 2019-05-28 | 2019-02-22 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.067372
2129 | 111338 | #SGR18VB - RT 258BUS over Cypress Ck Bridge Repair | 0258 | Urban | Bridge Rehab w/o Added Capacity | VDOT | Smithfield | FRANKLIN | Hampton Roads | Hampton Roads:Smithfield | Infrastructure Investment Division | Mohamed A Ali | Mohamed.Ali@VDOT.Virginia.gov | (757) 956-3206 | Songjian Mao | Steve.Mao@VDOT.Virginia.gov | (757) 956-3211 |  |  |  | 0 |  | 1 | FY2023 | 5000000 | 5000000 | ACTIVITY DATES SET | G | Determine Requirements milestone finished on-time | G | Project is on budget | [10 empty] | 2020-01-06 | 2020-01-06 | 2020-01-10 | 2020-01-10 | G | [35 empty] | 2022-06-14 |  | 2022-06-14 |  | G | 2022-08-04 |  | 2022-08-24 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 1 | 0.30805
2130 | 117175 | Town-wide Roadway Full Depth Reconstruction - Blacksburg | 0000 | Urban | Reconstruction w/o Added Capacity | Locally | Blacksburg | CHRISTIANSBURG | Salem | New River Valley:Blacksburg | Local Assistance Division | Adam J Czesnowski | Adam.Czesnowski@vdot.virginia.gov | (540) 541-1216 | Adam J Czesnowski | Adam.Czesnowski@vdot.virginia.gov | (540) 541-1216 | Randy Formica | rformica@blacksburg.gov | (540) 443-1300 | 0 |  | 0 | FY2028 | 919667 | 919667 | NO DATES SET YET | G | Agreement with Locality milestone is 1422 days ahead of the expected completion date | G | Project is on budget | 2024-08-30 |  | 2025-01-13 |  | G | 2025-01-14 |  | 2025-02-05 |  | G | 2025-08-12 |  | 2025-12-08 |  | G | [25 empty] | 2026-12-03 |  | 2027-05-05 |  | G | [5 empty] | 2027-07-02 |  | 2027-07-30 |  | G | 2027-10-20 |  | 2027-10-20 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.16149
2131 | 118068 | Pedestrian HAWK Signal at RT 1 & Marina |  | Primary | Facilities for Pedestrians and Bicycles | Locally | Chesterfield County | CHESTERFIELD | Richmond | Richmond:Chesterfield County | Local Assistance Division | Jorg Huckabee-Mayfield | Jorg.Huckabee-Mayfield@VDOT.Virginia.gov | (804) 609-5292 | Jorg Huckabee-Mayfield | Jorg.Huckabee-Mayfield@VDOT.Virginia.gov | (804) 609-5292 | Barbara Smith | smithbk@chesterfield.gov | (804) 748-1037 | 0 |  | 0 | FY2025 | 476000 | 476000 | NO DATES SET YET | G | Agreement with Locality milestone is 199 days ahead of the expected completion date | G | Project is on budget | 2021-05-03 |  | 2021-09-08 |  | G | 2021-09-09 |  | 2021-09-29 |  | G | 2021-10-29 |  | 2022-03-01 |  | G | [10 empty] | 2023-06-19 |  | 2023-07-24 |  | G | [5 empty] | 2023-07-25 |  | 2023-12-26 |  | G | 2023-11-20 |  | 2024-04-23 |  | G | [5 empty] | 2024-04-02 |  | 2024-04-29 |  | G | 2024-07-18 |  | 2024-07-18 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.20328
2132 | 19005 | I-264/LYNNHAVEN INTERCHANGE IMPROVEMENTS (PHASE II) | 0044 | Interstate | Reconstruction w/o Added Capacity | VDOT | Virginia Beach | NORFOLK | Hampton Roads | Hampton Roads:Virginia Beach | Infrastructure Investment Division | Timothy K Haynam | Timothy.Haynam@VDOT.Virginia.gov | (757) 956-3055 | Timothy K Haynam | Timothy.Haynam@VDOT.Virginia.gov | (757) 956-3055 |  |  |  | 0 |  | 0 | FY2025 | 126157253 | 126157253 | NO DATES SET YET-PE OPEN | R | Determine Requirements milestone is 61 days past the expected completion date | Y | Estimate not current | [5 empty] | 2003-04-01 | 2001-09-24 | 2003-04-30 | 2001-10-01 | G | 2020-07-15 |  | 2020-12-22 |  | R | [10 empty] | 2022-11-22 |  | 2023-01-18 |  | G | [20 empty] | 2024-01-16 |  | 2024-02-06 |  | G | 2024-07-08 |  | 2024-08-30 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.11553
2133 | 104303 | #HB2.FY17 WIDEN ROUTE 1 TO SIX LANES | 0001 | Primary | Reconstruction w/ Added Capacity | Locally | Prince William County | MANASSAS | Northern Virginia | Northern Virginia:Prince William County | Infrastructure Investment Division | Claudia H Llana | Claudia.Llana@VDOT.Virginia.gov | (703) 259-1768 | Veljibhai M Desai | Veljibhai.Desai@vdot.virginia.gov | (703) 259-2927 | Javier Ibe | JIbe@pwcgov.org | (703) 792-8164 | 1 | 2017 | 0 | FY2019 | 96390840 | 88061934 | CONSTRUCTION STARTED | R | Start Delivery milestone finished 547 days late | G | Project is on budget | 2015-10-01 | 2015-10-01 | 2016-12-31 | 2016-11-30 | G | 2015-10-01 | 2016-03-24 | 2015-12-31 | 2016-03-28 | R | 2015-09-01 | 2015-07-08 | 2016-01-13 | 2016-01-13 | G | [5 empty] | 2017-01-10 | 2017-01-10 | 2017-04-03 | 2017-04-03 | G | 2017-03-04 | 2017-03-04 | 2017-04-04 | 2017-04-04 | G | [5 empty] | 2017-05-02 | 2017-04-05 | 2018-07-02 | 2019-02-19 | R | [10 empty] | 2019-01-10 | 2020-05-18 | 2019-01-10 | 2020-06-26 | R | 2019-02-19 | 2020-06-29 | 2019-03-11 | 2020-09-08 | R | Delay due to unforeseen issues with utilities, railroad coordination, or right-of-way acquisition | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.24227
2134 | 107282 | Traffic Signal - Glade Road at University City Boulevard | 0000 | Urban | Traffic Management/Engineering | Locally | Blacksburg | CHRISTIANSBURG | Salem | New River Valley:Blacksburg | Local Assistance Division | James M Guy | james.guy@vdot.virginia.gov | (540) 387-5247 | Adam J Czesnowski | Adam.Czesnowski@vdot.virginia.gov | (540) 541-1216 | Randy Formica | rformica@blacksburg.gov | (540) 961-1121 | 0 |  | 0 | FY2019 | 513868 | 624154 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 3 days early | Y | Project estimate is less than $5M and is up to 20% over budget | 2015-11-02 | 2015-07-27 | 2016-02-02 | 2015-07-27 | G | 2016-02-03 | 2015-09-28 | 2016-02-17 | 2015-09-28 | G | 2016-02-18 | 2015-07-28 | 2016-10-07 | 2017-01-18 | R | [10 empty] | 2017-08-29 | 2017-08-29 | 2017-09-12 | 2017-09-12 | G | [20 empty] | 2018-04-13 | 2018-12-28 | 2018-09-04 | 2019-01-11 | R | 2018-09-05 | 2019-01-14 | 2019-03-14 | 2019-03-11 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.17587
2135 | 108165 | RTE F906 - CONSTRUCT SIDEWALK & INSTALL ROADWAY LIGHTING | 0906 | Urban | Safety | VDOT | Lynchburg | APPOMATTOX | Lynchburg | Lynchburg:Lynchburg | Infrastructure Investment Division | Laura J Walton | Laura.Walton@VDOT.Virginia.gov | (434) 856-8286 | Lindsey S Hodges | Lindsey.Hodges@vdot.virginia.gov | (434) 856-8143 |  |  |  | 0 |  | 0 | FY2019 | 533906 | 533906 | WAITING FINANCIAL CLOSURE | R | Start Delivery milestone finished 28 days late | G | Project is on budget | [5 empty] | 2016-10-03 | 2016-11-17 | 2016-10-17 | 2016-11-22 | R | 2016-10-18 | 2017-01-19 | 2017-09-14 | 2017-05-11 | G | [5 empty] | 2017-10-13 | 2017-10-11 | 2017-11-03 | 2017-11-03 | G | 2018-04-20 | 2018-04-20 | 2018-05-03 | 2018-05-03 | G | 2018-08-15 | 2018-11-26 | 2018-11-27 | 2018-11-27 | G | 2018-05-21 | 2018-05-08 | 2018-08-14 | 2018-07-13 | G | 2017-06-07 | 2017-06-07 | 2017-10-12 | 2017-06-07 | G | [5 empty] | 2019-01-08 | 2019-01-08 | 2019-01-08 | 2019-01-08 | G | 2019-03-04 | 2019-04-19 | 2019-03-22 | 2019-04-19 | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 1 | 0.20744
2136 | 108725 | Independence Boulevard - New Roadway |  | Urban | New Construction Roadway | Locally | Newport News | WILLIAMSBURG | Hampton Roads | Hampton Roads:Newport News | Local Assistance Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Chessica Villaflores | Chessica.Villaflores@vdot.virginia.gov | (757) 956-3094 | Everett Skipper, Director of Engineering |  |  | 0 |  | 0 | FY2022 | 15250000 | 15250000 | NO DATES SET YET-PE OPEN | R | Determine Requirements milestone is 403 days past the expected completion date | G | Project is on budget | 2018-10-01 | 2018-10-01 | 2018-12-28 | 2018-12-28 | G | 2018-12-31 | 2018-12-31 | 2019-01-14 | 2019-01-14 | G | 2019-01-15 |  | 2020-01-15 |  | R | [10 empty] | 2020-03-31 |  | 2020-04-13 |  | R | [5 empty] | 2020-04-21 |  | 2021-01-26 |  | R | [10 empty] | 2021-02-25 |  | 2021-04-21 |  | Y | 2021-04-22 |  | 2021-10-11 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.33832
2137 | 109508 | Bonham Road/Paulena Drive Sidewalk Initiative | 3328 | Urban | Safety | Locally | Bristol | ABINGDON | Bristol | Bristol:Bristol | Infrastructure Investment Division | Tabitha H Crowder | Tabitha.Crowder@vdot.virginia.gov | (276) 696-3482 | Kenneth R Plummer | KR.Plummer@VDOT.Virginia.gov | (276) 696-3261 | Wallace McCulloch |  |  | 0 |  | 0 | FY2021 | 141350 | 141350 | ACTIVITY DATES SET | R | Solicit Bids milestone is 171 days past the expected completion date | G | Project is on budget | 2016-10-03 | 2016-10-03 | 2018-01-24 | 2018-01-24 | G | 2018-01-25 | 2018-01-25 | 2018-01-25 | 2018-01-25 | G | 2018-01-26 | 2018-01-26 | 2018-09-14 | 2018-09-05 | G | [35 empty] | 2020-06-18 |  | 2020-09-03 |  | R | 2020-09-04 |  | 2020-10-15 |  | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.098455
2138 | 110891 | #SGR18LB - BR MAINTENANCE - RT 250 BYPASS OVER RUGBY AVE | 0250 | Urban | Bridge Rehab w/o Added Capacity | Locally | Charlottesville | CHARLOTTESVILLE | Culpeper | Charlottesville:Charlottesville | Infrastructure Investment Division | Ken Connors |  |  | Michael D Barnes | MichaelD.Barnes@vdot.virginia.gov | (434) 422-9861 | Kyle Kling | klingk@charlottesville.gov | (434) 970-3182 | 0 |  | 1 | FY2022 | 2488292 | 2403128 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 423 days early | G | Project is on budget | 2019-01-02 | 2019-01-02 | 2019-03-29 | 2019-01-10 | G | 2019-04-01 | 2019-01-10 | 2019-04-03 | 2019-01-24 | G | 2019-04-04 | 2019-01-25 | 2019-10-07 | 2019-06-11 | G | [10 empty] | 2020-10-08 | 2020-07-06 | 2020-10-29 | 2020-07-24 | G | [5 empty] | 2020-11-02 | 2020-07-28 | 2021-08-13 | 2020-08-10 | G | [10 empty] | 2021-08-31 | 2020-08-24 | 2021-09-28 | 2020-09-11 | G | 2021-09-29 | 2020-09-12 | 2022-01-06 | 2020-11-09 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.21048
2139 | 111426 | RIVERWALK SHARED USE PATH PROJECT (PHASE I) |  | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Bridgewater | HARRISONBURG | Staunton | Harrisonburg:Bridgewater | Local Assistance Division | Matthew P Dana | Matt.Dana@VDOT.Virginia.gov | (540) 332-7786 | Michael S Fulcher | Michael.Fulcher@VDOT.Virginia.gov | (540) 332-2243 | Alex Wilmer | reuben.rhodes@vdot.virginia.gov | (540) 908-4212 | 0 |  | 0 | FY2022 | 237111 | 338601 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 379 days early | R | Project estimate is less than $5M and is 20% or more over budget | 2018-02-01 | 2017-10-15 | 2018-04-26 | 2017-11-09 | G | 2018-04-27 | 2017-11-10 | 2018-05-01 | 2018-02-14 | G | 2018-05-02 | 2019-02-15 | 2019-05-16 | 2019-08-15 | R | [10 empty] | 2020-06-11 | 2019-07-01 | 2020-07-01 | 2019-08-30 | G | [5 empty] | 2020-07-06 | 2019-09-04 | 2021-04-16 | 2020-02-27 | G | [10 empty] | 2021-05-04 | 2020-03-16 | 2021-06-01 | 2020-04-10 | G | 2021-06-02 | 2020-04-10 | 2021-07-13 | 2020-06-29 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.27314
2140 | 112026 | RTE 60 EAST MADISON STREET - FY18 PRIMARY EXT | 0060 | Urban | Restoration and Rehabilitation | Locally | Covington | LEXINGTON | Staunton | NonMPO:NonMPO | Local Assistance Division | Michael L Branscome | Michael.Branscome@VDOT.Virginia.gov | (540) 332-2377 | Michael L Branscome | Michael.Branscome@VDOT.Virginia.gov | (540) 332-2377 | City of Lexington | adressler@covington.va.us | (540) 965-6300 | 0 |  | 0 | FY2019 | 150500 | 150500 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished on-time | Y | Estimate not current | 2017-09-01 | 2018-11-30 | 2017-11-30 | 2018-12-05 | R | [5 empty] | 2017-09-01 | 2018-12-10 | 2017-09-15 | 2018-12-11 | R | [35 empty] | 2018-12-08 | 2018-12-08 | 2019-01-24 | 2019-01-24 | G | 2019-01-25 | 2019-01-25 | 2019-02-28 | 2019-02-28 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.085241
2141 | 112780 | MONUMENT DRIVE BRIDGE PEDESTRIAN FACILITY | 7969 | Secondary | Facilities for Pedestrians and Bicycles | VDOT | Fairfax County | FAIRFAX | Northern Virginia | Northern Virginia:Fairfax County | Infrastructure Investment Division | Harinderbir S Warraich | HS.Warraich@VDOT.Virginia.gov | (571) 459-2362 | Harinderbir S Warraich | HS.Warraich@VDOT.Virginia.gov | (571) 459-2362 |  |  |  | 0 |  | 0 | FY2019 | 3800000 | 3800000 | AWARDED | G | Start Delivery milestone finished on-time | G | Project is on budget | [10 empty] | 2018-02-22 | 2018-02-22 | 2018-06-28 | 2018-06-28 | G | [35 empty] | 2018-07-02 | 2018-07-02 | 2018-07-09 | 2018-07-09 | G | 2018-07-10 | 2018-07-10 | 2018-07-18 | 2018-07-18 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | WORK/TASK ORDER | 1 | 0 | 0.081024
2142 | 113190 | ADA Ramps Upgrade - Phase 4 | 9999 | Urban | Facilities for Pedestrians and Bicycles | Locally | Norfolk | NORFOLK | Hampton Roads | Hampton Roads:Norfolk | Local Assistance Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Derrick Williams | Derrick.Williams@vdot.virginia.gov | (757) 956-3097 | Eric Berger | Eric.berger@norfolk.gov | (757) 823-4039 | 0 |  | 0 | FY2021 |  |  | CONSTRUCTION COMPLETED | G | Obtained Permits milestone finished 251 days early | R | Critical information missing | 2018-08-30 | 2018-08-30 | 2018-11-28 | 2018-10-02 | G | 2018-11-29 | 2018-09-19 | 2018-12-03 | 2018-10-02 | G | 2018-12-04 | 2018-10-03 | 2019-06-11 | 2019-10-03 | R | [25 empty] | 2019-10-04 | 2019-09-04 | 2020-06-11 | 2019-10-04 | G | [5 empty] | 2020-06-26 | 2019-03-01 | 2020-08-07 | 2019-03-01 | G | 2020-08-10 | 2019-03-04 | 2021-02-04 | 2019-05-01 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.1378
2143 | 113310 | Primary Extension - Rte 40 (Old Franklin Turnpike) | 0000 | Urban | Resurfacing | Locally | Rocky Mount | BEDFORD | Salem | NonMPO:NonMPO | Local Assistance Division | Jessie Nester | Jessie.Nester@vdot.virginia.gov | (540) 613-4115 | Jessie Nester | Jessie.Nester@vdot.virginia.gov | (540) 613-4115 | Jessica Heckman | jheckman@rockymountva.org | (540) 483-0907 | 0 |  | 0 | FY2019 | 253053 | 253053 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 107 days early | G | Project is on budget | 2018-10-01 | 2018-07-05 | 2018-12-28 | 2018-09-10 | G | 2018-12-31 | 2018-09-18 | 2019-01-03 | 2018-09-18 | G | 2019-01-04 | 2018-10-23 | 2019-03-22 | 2018-10-23 | G | [35 empty] | 2018-12-03 | 2018-10-23 | 2018-12-31 | 2018-12-14 | G | 2019-05-28 | 2019-01-14 | 2019-06-28 | 2019-03-13 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.10305
2144 | 113508 | SRTS - CALE ELEMENTARY SCHOOL - PED. & BICYCLE IMPROVEMENTS | 0742 | Secondary | Facilities for Pedestrians and Bicycles | Locally | Albemarle County | CHARLOTTESVILLE | Culpeper | NonMPO:NonMPO | Local Assistance Division | John P Price | John.Price@VDOT.Virginia.gov | (540) 347-6371 | Thomas Fitzpatrick | Thomas.Fitzpatrick@vdot.virginia.gov |  | JACK KELSEY | jkelsey2@albemarle.org | (434) 760-1272 | 0 |  | 0 | FY2021 | 512094 | 597094 | ADVERTISED | R | Start Delivery milestone is 12 days past the expected completion date | Y | Project estimate is less than $5M and is up to 20% over budget | 2018-10-01 | 2018-10-01 | 2018-12-28 | 2018-10-17 | G | 2018-12-31 | 2018-10-17 | 2019-01-03 | 2018-10-19 | G | 2019-01-04 | 2018-10-22 | 2019-07-11 | 2019-07-08 | G | [35 empty] | 2020-09-03 | 2020-05-07 | 2020-10-30 | 2020-06-02 | G | 2021-01-27 |  | 2021-02-09 |  | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.20148
2145 | 113620 | ALEXANDRIA PRIMARY EXTENSION PAVING FY19 - DUKE ST EB | 0236 | Urban | Resurfacing | Locally | Alexandria | FAIRFAX | Northern Virginia | Northern Virginia:Alexandria | Local Assistance Division | Amir Salahshoor | A.Salahshoor@VDOT.Virginia.gov | (703) 259-1957 | Rita Hockman | Rita.Hockman@vdot.virginia.gov | (804) 824-7421 | Mary Winston | maryalice.winston@alexandriava.gov | (703) 746-4067 | 0 |  | 0 | FY2019 |  |  | WAITING FINANCIAL CLOSURE | G | Obtained Permits milestone finished on-time | R | Critical information missing | 2018-07-02 | 2018-07-02 | 2018-09-25 | 2018-09-13 | G | [5 empty] | 2018-09-26 | 2018-09-14 | 2018-11-28 | 2018-11-14 | G | [25 empty] | 2018-09-19 | 2018-09-19 | 2018-11-16 | 2018-11-16 | G | [5 empty] | 2018-11-19 | 2018-09-21 | 2018-12-18 | 2018-09-21 | G | 2018-12-19 | 2018-09-07 | 2019-02-15 | 2018-09-21 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.19956
2146 | 113787 | RTE 1046 -RURAL RUSTIC RD (SURFACE TREAT NON-HARDSURFACE RD) | 1046 | Secondary | Resurfacing | VDOT | Louisa | LOUISA | Culpeper | NonMPO:NonMPO | Infrastructure Investment Division | Ken Connors |  |  | Bethel Kefyalew | Bethel.Kefyalew@vdot.virginia.gov | (540) 603-6015 |  |  |  | 0 |  | 0 | FY2025 | 75000 | 75000 | NO DATES SET YET | G | Start Development milestone is 600 days ahead of the expected completion date | Y | Estimate not current | [5 empty] | 2022-10-03 |  | 2022-10-14 |  | G | 2022-10-18 |  | 2023-06-13 |  | G | [5 empty] | 2024-02-22 |  | 2024-04-03 |  | G | [5 empty] | 2024-07-18 |  | 2024-11-08 |  | G | [5 empty] | 2024-07-02 |  | 2024-10-02 |  | G | [5 empty] | 2024-11-12 |  | 2024-11-12 |  | G | 2025-02-07 |  | 2025-02-07 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | SAAP CONTRACT | 0 | 0 | 0.066218
2147 | 114619 | RTE 29/120 LEE HWY INTX IMPR AT N. GLEBE RD | 0029 | Primary | Safety | Locally | Arlington County | FAIRFAX | Northern Virginia | Northern Virginia:Arlington County | Local Assistance Division | Bud Siegel |  |  | Rita Hockman | Rita.Hockman@vdot.virginia.gov | (804) 824-7421 | Jon Lawler | jlawler@arlingtonva.us | (703) 228-3724 | 0 |  | 0 | FY2020 | 4137000 | 4137000 | CONSTRUCTION STARTED | G | Start Delivery milestone finished on-time | Y | Estimate not current | 2018-08-31 | 2019-03-08 | 2019-04-30 | 2019-04-09 | G | [5 empty] | 2019-05-01 | 2019-04-22 | 2019-05-31 | 2019-05-21 | G | [35 empty] | 2019-08-05 | 2019-08-05 | 2019-09-05 | 2019-09-05 | G | 2019-09-06 | 2019-09-06 | 2019-12-16 | 2019-12-16 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.24567
2148 | 115008 | I-64 HRBT Expansion Project - Design-Build Contract | 0064 | Interstate | Bridge, New Construction | VDOT | Multi-jurisdictional: Hampton Roads MPO |  | Hampton Roads | Hampton Roads:Multi-jurisdictional: Hampton Roads MPO | Infrastructure Investment Division | James S Utterback | James.Utterback@VDOT.virginia.gov | (757) 858-6778 | Christopher E Eggleston | Christopher.Eggleston@vdot.virginia.gov | (757) 857-8955 |  |  |  | 0 |  | 0 | FY2019 |  |  | CONSTRUCTION STARTED | G | Start Delivery milestone finished on-time | R | Critical information missing | [5 empty] | 2017-01-03 | 2017-01-03 | 2017-01-03 | 2017-01-03 | G | 2018-04-01 | 2018-04-01 | 2018-05-21 | 2018-05-21 | G | [35 empty] | 2018-05-21 | 2018-05-21 | 2018-05-22 | 2018-05-22 | G | 2018-05-23 | 2018-05-23 | 2019-04-02 | 2019-04-02 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | DESIGN BUILD/PPTA | 1 | 0 | 0.16647
2150 | 112297 | FEATHERBED LANE-UPGRADE GRAVEL ROAD TO PAVED FACILITY | 0622 | Secondary | Reconstruction w/o Added Capacity | Locally | Prince William County | MANASSAS | Northern Virginia | Northern Virginia:Prince William County | Infrastructure Investment Division | Amir Salahshoor | A.Salahshoor@VDOT.Virginia.gov | (703) 259-1957 | Rita Hockman | Rita.Hockman@vdot.virginia.gov | (804) 824-7421 | John Flemming | John.Flemming@pwcgov.org | (703) 792-8164 | 0 |  | 0 | FY2022 | 483865 | 474656 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 853 days early | G | Project is on budget | 2018-01-23 | 2018-01-23 | 2018-05-22 | 2018-05-22 | G | 2018-05-23 | 2018-05-23 | 2018-05-31 | 2018-05-31 | G | 2018-08-29 | 2018-08-29 | 2019-05-30 | 2019-03-11 | G | [10 empty] | 2020-03-26 | 2019-05-29 | 2020-04-30 | 2019-06-14 | G | [5 empty] | 2020-05-04 | 2019-06-18 | 2021-02-26 | 2019-07-22 | G | [10 empty] | 2021-03-16 | 2019-09-30 | 2021-08-31 | 2019-09-30 | G | 2021-09-01 | 2019-10-01 | 2022-01-31 | 2019-10-01 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.33611
2151 | 112818 | NUTLEY STREET SW SHARED USE PATH | 0243 | Urban | Facilities for Pedestrians and Bicycles | Locally | Vienna | FAIRFAX | Northern Virginia | Northern Virginia:Vienna | Infrastructure Investment Division | Amir Salahshoor | A.Salahshoor@VDOT.Virginia.gov | (703) 259-1957 | Susie X Lue | Susie.Lue@vdot.virginia.gov | (703) 259-2918 | Andrew Jinks | Andrew.Jinks@viennava.gov | (703) 255-6381 | 0 |  | 0 | FY2025 | 295001 | 295001 | NO DATES SET YET-PE OPEN | R | Determine Requirements milestone is 83 days past the expected completion date | G | Project is on budget | 2018-04-02 | 2018-04-02 | 2018-12-26 | 2018-06-21 | G | 2018-12-27 | 2018-07-16 | 2019-01-28 | 2018-07-18 | G | 2019-11-27 | 2019-07-30 | 2020-11-30 |  | R | 2020-12-01 |  | 2021-03-22 |  | Y | [5 empty] | 2022-04-14 |  | 2022-08-26 |  | G | [5 empty] | 2022-08-29 |  | 2024-02-27 |  | G | 2021-05-13 |  | 2022-01-20 |  | G | [5 empty] | 2024-10-29 |  | 2025-02-27 |  | G | 2025-02-28 |  | 2025-06-20 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.17846
2152 | 113306 | #SGR19LP - Primary EXT-Roanoke St-Tower Rd to Dunlap Dr | 0000 | Urban | Resurfacing | Locally | Christiansburg | CHRISTIANSBURG | Salem | New River Valley:Christiansburg | Local Assistance Division | Adam J Czesnowski | Adam.Czesnowski@vdot.virginia.gov | (540) 541-1216 | Adam J Czesnowski | Adam.Czesnowski@vdot.virginia.gov | (540) 541-1216 | Wayne Nelson | wnelson@christiansburg.org | (540) 382-6120 | 0 |  | 0 | FY2019 | 246159 | 246159 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 163 days early | G | Project is on budget | 2018-10-01 | 2018-08-01 | 2018-12-28 | 2018-08-16 | G | 2018-12-31 | 2018-09-26 | 2019-01-03 | 2018-10-02 | G | 2019-01-04 | 2018-10-01 | 2019-03-22 | 2018-10-02 | G | [35 empty] | 2018-12-03 | 2018-12-03 | 2018-12-31 | 2018-12-12 | G | 2019-05-28 | 2019-01-02 | 2019-06-28 | 2019-01-16 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.060039
2153 | 113327 | SIMONS RUN - CONSTRUCT CONNECTOR ROAD | 9999 | Urban | New Construction Roadway | Locally | Campbell County | APPOMATTOX | Lynchburg | Lynchburg:Campbell County | Local Assistance Division | Sharon S White | Sharon.White@VDOT.Virginia.gov | (434) 856-8220 | Sharon S White | Sharon.White@VDOT.Virginia.gov | (434) 856-8220 | Clifton Tweedy | cmtweedy@co.campbell.va.us | (434) 332-9621 | 0 |  | 0 | FY2019 | 2677730 | 2677730 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 64 days early | G | Project is on budget | 2019-01-31 | 2018-10-23 | 2019-04-25 | 2018-10-23 | G | 2019-04-26 | 2018-10-23 | 2019-04-30 | 2018-10-23 | G | 2019-05-01 | 2018-10-24 | 2019-11-04 | 2018-10-30 | G | [10 empty] | 2020-05-06 | 2019-02-15 | 2020-05-27 | 2019-02-15 | G | [5 empty] | 2020-05-29 | 2019-02-15 | 2021-03-12 | 2019-02-15 | G | [10 empty] | 2019-02-17 | 2019-02-15 | 2019-03-18 | 2019-02-17 | G | 2019-06-05 | 2019-04-02 | 2019-06-05 | 2019-04-02 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.091008
2154 | 113572 | ROADWAY DEPARTURE CRASH MITIGATION ROUND 3-NOVA |  | Primary | Safety | VDOT | Northern Virginia District-wide |  | Northern Virginia | Northern Virginia:Northern Virginia District-wide | Infrastructure Investment Division | Ivan M Horodyskyj | Ivan.Horodyskyj@VDOT.Virginia.gov | (703) 259-2330 | Anwar A Ansari | Anwar.Ansari@VDOT.Virginia.gov | (703) 334-0204 |  |  |  | 0 |  | 0 | FY2019 | 500000 | 488785 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 31 days early | G | Project is on budget | [5 empty] | 2018-08-20 | 2018-08-22 | 2018-08-31 | 2018-09-14 | R | 2018-09-04 | 2018-09-04 | 2019-04-30 | 2018-11-27 | G | [5 empty] | 2018-12-26 | 2018-12-19 | 2018-12-26 | 2018-12-26 | G | [5 empty] | 2018-12-03 | 2018-12-03 | 2018-12-03 | 2018-12-03 | G | [15 empty] | 2019-04-09 | 2019-03-12 | 2019-04-09 | 2019-03-12 | G | 2019-06-28 | 2019-05-28 | 2019-06-28 | 2019-05-28 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.06805
2155 | 113705 | #SGR19LP - Primary Extension RT 58 Westbound, Segment 2 | 0058 | Urban | Resurfacing | Locally | Suffolk | NORFOLK | Hampton Roads | Hampton Roads:Suffolk | Infrastructure Investment/Asset Management Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Johndel A Alcaide | John.Alcaide@vdot.virginia.gov | (757) 956-3098 | Ed Heide | eheide@suffolkva.us | (757) 514-7615 | 0 |  | 1 | FY2019 | 344000 | 344000 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished on-time | G | Project is on budget | 2018-09-04 | 2018-09-24 | 2018-11-30 | 2018-10-04 | G | 2018-12-03 | 2018-10-25 | 2018-12-05 | 2018-11-19 | G | 2018-12-06 | 2018-11-20 | 2019-06-13 | 2019-05-15 | G | [25 empty] | 2019-02-22 | 2019-02-22 | 2019-04-04 | 2019-02-22 | G | [5 empty] | 2019-06-10 | 2019-06-10 | 2019-06-10 | 2019-06-10 | G | 2019-06-28 | 2019-06-27 | 2019-06-28 | 2019-06-28 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.068048
2156 | 114188 | SHOULDER WIDENING AND RUMBLE STRIPS - FAUQUIER COUNTY | 0211 | Primary | Safety | VDOT | Fauquier County | WARRENTON | Culpeper | NonMPO:NonMPO | Infrastructure Investment Division | Ken Connors |  |  | Caroline Awua-Mensah | Caroline.Awua-Mensah@vdot.virginia.gov | (540) 829-7618 |  |  |  | 0 |  | 0 | FY2019 |  |  | WAITING FINANCIAL CLOSURE | G | Determine Requirements milestone finished on-time | R | Critical information missing | [10 empty] | 2019-03-11 | 2019-03-11 | 2019-03-15 | 2019-03-15 | G | [35 empty] | 2018-12-04 | 2018-12-04 | 2018-12-04 | 2018-12-04 | G | 2019-01-16 | 2019-01-16 | 2019-01-16 | 2019-01-16 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.080728
2157 | 114666 | PSAP - Pedestrian Facility Improvements in Albemarle County | 0029 | Primary | Safety | VDOT | Albemarle County | CHARLOTTESVILLE | Culpeper | Charlottesville:Albemarle County | Infrastructure Investment Division | Gregory J Cooley | Gregory.Cooley@vdot.virginia.gov | (434) 906-7979 | Caroline Awua-Mensah | Caroline.Awua-Mensah@vdot.virginia.gov | (540) 829-7618 |  |  |  | 0 |  | 0 | FY2020 | 407340 | 407340 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 16 days early | G | Project is on budget | [5 empty] | 2019-02-01 | 2018-12-21 | 2019-02-01 | 2019-01-31 | G | 2019-02-04 | 2019-02-04 | 2019-05-13 | 2019-05-13 | G | [5 empty] | 2019-09-18 | 2019-09-18 | 2019-10-30 | 2019-10-30 | G | [25 empty] | 2019-12-24 | 2019-12-17 | 2020-02-07 | 2020-01-28 | G | 2020-02-10 | 2020-01-29 | 2020-02-14 | 2020-01-29 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | WORK/TASK ORDER | 1 | 1 | 0.35304
2158 | 115470 | #SMART20-US Rte 52 Int Safety Enhancements (APP ID#3617) | 0052 | Primary | Reconstruction w/o Added Capacity | VDOT | Bland County | WYTHEVILLE | Bristol | NonMPO:NonMPO | Infrastructure Investment Division | Dennis R Harris | Dennis.Harris@VDOT.Virginia.gov | (276) 696-3289 | Ronald C Flanary | Ronald.Flanary@VDOT.Virginia.gov | (276) 696-3252 |  |  |  | 1 | 2020 | 0 | FY2025 | 4491045 | 4491045 | NO DATES SET YET-PE OPEN | Y | Determine Requirements milestone is 24 days ahead of the expected completion date and there is a risk of missing this milestone date | G | Project is on budget | [5 empty] | 2020-04-03 | 2020-04-03 | 2020-04-16 | 2020-04-16 | G | 2020-04-17 | 2020-04-17 | 2021-03-17 |  | Y | [5 empty] | 2022-01-21 |  | 2022-02-03 |  | G | 2023-05-10 |  | 2023-05-23 |  | G | 2023-10-17 |  | 2024-04-25 |  | G | 2023-06-09 |  | 2023-12-15 |  | G | 2022-10-24 |  | 2023-05-03 |  | G | [5 empty] | 2024-05-14 |  | 2024-05-14 |  | G | 2024-08-05 |  | 2024-08-05 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.09234
2159 | 115604 | COMPTON ROAD SHARED USE PATH | 0658 | Secondary | Facilities for Pedestrians and Bicycles | VDOT | Fairfax County | FAIRFAX | Northern Virginia | Northern Virginia:Fairfax County | Infrastructure Investment Division | Andrew G Beacher | Andrew.Beacher@vdot.virginia.gov | (703) 259-2239 | Khalid L Gandhi | disabled-Khalid.Gandhi@VDOT.Virginia.gov | (703) 259-2397 | Lauren Delmare | Lauren.Delmare@fairfaxcounty.gov | (703) 877-5781 | 0 |  | 0 | FY2024 | 4500000 | 4500000 | NO DATES SET YET-PE OPEN | R | Determine Requirements milestone is 144 days past the expected completion date | G | Project is on budget | 2019-05-22 | 2019-07-08 | 2019-09-30 | 2019-08-09 | G | 2019-10-01 | 2019-10-22 | 2019-10-31 | 2019-10-24 | G | 2019-11-01 | 2020-01-29 | 2020-09-30 |  | R | [5 empty] | 2021-09-02 |  | 2021-09-16 |  | G | 2022-11-18 |  | 2022-12-05 |  | G | 2023-05-02 |  | 2023-11-03 |  | G | 2022-12-20 |  | 2023-06-27 |  | G | 2022-11-10 |  | 2023-07-19 |  | G | [5 empty] | 2023-11-14 |  | 2023-11-14 |  | G | 2024-02-09 |  | 2024-02-09 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.081929
2160 | 116319 | FAIRFAX COUNTY CIVIL WAR BICYCLE TOUR- WAYFINDING SIGNS |  | Enhancement | Safety and Education of Pedestrians /Bicyclisits | Locally | Fairfax County | FAIRFAX | Northern Virginia | Northern Virginia:Fairfax County | Local Assistance Division | Amir Salahshoor | A.Salahshoor@VDOT.Virginia.gov | (703) 259-1957 | Jeffrey S Daily | Jeff.Daily@VDOT.Virginia.gov | (703) 259-2993 | Nigin Askarzadeh | Negin.Askarzadeh@fairfaxcounty.gov | (703) 877-5773 | 0 |  | 0 | FY2021 | 30000 | 22891 | ADVERTISED | R | Solicit Bids milestone finished 188 days late | G | Project is on budget | 2019-10-01 | 2019-09-30 | 2019-10-31 | 2019-10-30 | G | [5 empty] | 2019-11-01 | 2019-10-31 | 2019-11-15 | 2019-11-16 | R | [35 empty] | 2020-03-02 | 2020-03-02 | 2020-06-30 | 2021-01-04 | R | 2020-09-18 |  | 2021-02-26 |  | Y |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.25207
2161 | 117062 | #SGR21VP CY21 LEE PRIMARY PM1K | 9999 | Primary | Resurfacing | VDOT | Bristol District-wide |  | Bristol | NonMPO:NonMPO | Infrastructure Investment Division | James B Parsons | James.Parsons@VDOT.Virginia.gov | (276) 696-3288 | David G Morrison | David.Morrison@VDOT.Virginia.gov | (276) 696-3328 |  |  |  | 0 |  | 1 | FY2021 | 1917278 | 1917278 | ADVERTISED | Y | Start Delivery milestone is 4 days ahead of the expected completion date and there is a risk of missing this milestone date | G | Project is on budget | [10 empty] | 2021-01-27 | 2021-01-28 | 2021-02-02 | 2021-01-28 | G | [35 empty] | 2020-12-01 | 2020-12-01 | 2020-12-01 | 2020-12-01 | G | 2021-02-25 |  | 2021-02-25 |  | Y |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.070801
2162 | 117178 | Blacksburg - Curb, Gutter, and Sidewalk Rebuild - FY21 | 0000 | Urban | Reconstruction w/o Added Capacity | Locally | Blacksburg | CHRISTIANSBURG | Salem | New River Valley:Blacksburg | Local Assistance Division | Adam J Czesnowski | Adam.Czesnowski@vdot.virginia.gov | (540) 541-1216 | Adam J Czesnowski | Adam.Czesnowski@vdot.virginia.gov | (540) 541-1216 | Randy Formica | rformica@blacksburg.gov | (540) 443-1300 | 0 |  | 0 | FY2028 | 120000 | 120000 | NO DATES SET YET | G | Agreement with Locality milestone is 1422 days ahead of the expected completion date | G | Project is on budget | 2024-08-30 |  | 2025-01-13 |  | G | 2025-01-14 |  | 2025-02-05 |  | G | 2025-08-12 |  | 2025-12-08 |  | G | [25 empty] | 2026-12-03 |  | 2027-05-05 |  | G | [5 empty] | 2027-07-02 |  | 2027-07-30 |  | G | 2027-10-20 |  | 2027-10-20 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.15848
2163 | 117992 | East Main Street Sidewalk Improvements - Radford |  | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Radford | CHRISTIANSBURG | Salem | NonMPO:NonMPO | Local Assistance Division | Adam J Czesnowski | Adam.Czesnowski@vdot.virginia.gov | (540) 541-1216 | Adam J Czesnowski | Adam.Czesnowski@vdot.virginia.gov | (540) 541-1216 | Jay Eanes | jay.eanes@radfordva.gov | (540) 267-3176 | 0 |  | 0 | FY2025 | 476924 | 476924 | NO DATES SET YET | G | Agreement with Locality milestone is 50 days ahead of the expected completion date | G | Project is on budget | 2020-12-01 |  | 2021-04-12 |  | G | 2021-04-13 |  | 2021-05-03 |  | G | 2021-11-08 |  | 2022-03-09 |  | G | [10 empty] | 2023-06-27 |  | 2023-08-01 |  | G | [5 empty] | 2023-08-02 |  | 2024-01-04 |  | G | 2023-11-30 |  | 2024-05-01 |  | G | [5 empty] | 2024-04-10 |  | 2024-05-07 |  | G | 2024-07-26 |  | 2024-07-26 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.36296
2164 | 68760 | VILLAGE OF LUCKETTS - SAFETY IMPROVEMENTS IN LOUDOUN COUNTY | 0015 | Primary | Safety | VDOT | Loudoun County | LEESBURG | Northern Virginia | Northern Virginia:Loudoun County | Infrastructure Investment Division | Kimberly Mccool | Kimberly.McCool@vdot.virginia.gov | (703) 259-3220 | Hamid R Misaghian | H.Misaghian@VDOT.Virginia.gov | (703) 259-1795 |  |  |  | 0 |  | 0 | FY2021 | 9069158 | 3912562 | ACTIVITY DATES SET | R | Engage Public milestone is 1040 days past the expected completion date | G | Project is on budget | [5 empty] | 2004-10-29 | 2004-08-26 | 2004-11-19 | 2004-09-02 | G | 2005-06-20 | 2005-12-02 | 2013-05-31 | 2013-05-31 | G | [5 empty] | 2018-01-02 |  | 2018-04-18 |  | R | 2018-10-01 |  | 2018-12-31 |  | R | 2018-12-18 |  | 2019-12-17 |  | R | 2018-11-05 |  | 2020-04-30 |  | R | [10 empty] | 2020-01-28 |  | 2020-06-26 |  | R | 2020-06-29 |  | 2020-10-27 |  | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.11441
2165 | 100702 | #HB2.FY17 MODIFY I-95 SB OFF RAMP AT SR 784 ADD SIGNAL | 0784 | Secondary | Safety | VDOT | Prince William County | MANASSAS | Northern Virginia | Northern Virginia:Prince William County | Infrastructure Investment Division | Claudia H Llana | Claudia.Llana@VDOT.Virginia.gov | (703) 259-1768 | Mehrdad Naderi | Mehrdad.Naderi@vdot.virginia.gov | (703) 259-2217 |  |  |  | 1 | 2017 | 0 | FY2017 | 1856857 | 1856857 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 40 days early | G | Project is on budget | [5 empty] | 2011-10-01 | 2011-07-21 | 2011-10-01 | 2011-07-21 | G | 2011-10-20 | 2011-10-20 | 2016-09-01 | 2016-07-22 | G | [5 empty] | 2015-12-09 | 2015-12-09 | 2015-12-11 | 2015-12-09 | G | [25 empty] | 2013-04-19 | 2016-10-11 | 2016-12-30 | 2016-10-11 | G | 2017-01-13 | 2017-01-03 | 2017-02-12 | 2017-01-03 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.14613
2166 | 103504 | Bridge (Fed ID 17509) Rte 800 Over St. Clair Creek VA # 6002 | 0800 | Secondary | Bridge Replacement w/o Added Capacity | VDOT | Smyth County | ABINGDON | Bristol | NonMPO:NonMPO | Infrastructure Investment Division | Gary Lester |  |  | Jason A Graham | Jason.Graham@vdot.virginia.gov | (276) 696-3383 |  |  |  | 0 |  | 0 | FY2020 | 104424 | 73348 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished on-time | G | Project is on budget | [5 empty] | 2012-11-15 | 2012-08-06 | 2012-11-15 | 2012-08-10 | G | 2014-05-09 | 2013-08-15 | 2019-11-30 | 2018-03-12 | G | 2017-12-07 | 2017-12-07 | 2018-04-05 | 2018-04-05 | G | [30 empty] | 2019-04-16 | 2019-04-16 | 2019-05-10 | 2019-05-10 | G | 2019-07-11 | 2019-07-11 | 2019-07-24 | 2019-07-24 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.062285
2167 | 105109 | REHABILITATE BRIDGES -VARIOUS LOCATIONS | 9999 | Urban | Bridge Rehab w/o Added Capacity | Locally | Colonial Heights | CHESTERFIELD | Richmond | Tri-Cities:Colonial Heights | Infrastructure Investment Division | Brian J Lokker | Brian.Lokker@VDOT.Virginia.gov | (804) 524-6010 | Brian J Lokker | Brian.Lokker@VDOT.Virginia.gov | (804) 524-6010 | Keith Chisolm | chisolmk@colonialheightsva.gov | (804) 520-9215 | 0 |  | 0 | FY2020 | 859495 | 837500 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 29 days early | G | Project is on budget | 2013-07-01 | 2018-07-01 | 2018-09-04 | 2018-09-14 | R | 2013-10-28 | 2013-10-28 | 2013-10-28 | 2013-10-28 | G | 2018-09-26 | 2018-12-11 | 2018-11-07 | 2019-02-22 | R | [5 empty] | 2019-03-18 | 2019-05-17 | 2019-07-17 | 2019-06-27 | G | 2019-07-17 | 2019-06-27 | 2019-07-17 | 2019-06-27 | G | [10 empty] | 2019-03-12 | 2019-05-01 | 2019-07-02 | 2019-09-23 | R | [5 empty] | 2019-10-01 | 2019-10-10 | 2019-10-15 | 2019-10-10 | G | 2020-01-03 | 2019-12-30 | 2020-03-31 | 2020-03-02 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.25214
2168 | 105964 | RTE 673 - Grade, Drain, Stabilize, and Plant Mix Unpaved rd. | 0673 | Secondary | Reconstruction w/o Added Capacity | VDOT | Giles County | CHRISTIANSBURG | Salem | NonMPO:NonMPO | Infrastructure Investment Division | Christopher L Price | Christopher.Price@VDOT.Virginia.gov | (540) 381-7182 | Audra Parson | Audra.Parson@vdot.virginia.gov | (540) 951-3727 |  |  |  | 0 |  | 0 | FY2022 | 1207936 | 1207936 | ACTIVITY DATES SET | G | Start Purchasing Right-of-Way milestone finished on-time | G | Project is on budget | [5 empty] | 2019-09-02 | 2018-10-16 | 2019-09-02 | 2018-11-27 | G | 2019-10-02 | 2018-12-28 | 2020-02-02 | 2020-01-29 | G | [10 empty] | 2020-07-30 | 2020-08-26 | 2020-08-26 | 2020-08-26 | G | [20 empty] | 2021-06-30 |  | 2021-06-30 |  | G | 2021-07-01 |  | 2021-12-09 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | SAAP CONTRACT | 0 | 0 | 0.1073
2169 | 106563 | ITS INTEGRATION - PHASEIII | 9999 | Urban | Traffic Management/Engineering | Locally | Alexandria | FAIRFAX | Northern Virginia | Northern Virginia:Alexandria | Infrastructure Investment Division | Andrew G Beacher | Andrew.Beacher@vdot.virginia.gov | (703) 259-2239 | Robert J Strevell | Robert.Strevell@vdot.virginia.gov | (703) 259-1988 | Daphne Kott | Daphne.Kott@alexandriava.gov | (703) 838-4411 | 0 |  | 0 | FY2022 | 3028344 | 4103345 | ACTIVITY DATES SET | R | Determine Requirements milestone finished 339 days late | R | Project estimate is less than $5M and is 20% or more over budget | 2017-04-17 | 2017-04-17 | 2017-04-17 | 2017-04-17 | G | 2017-07-12 | 2017-07-12 | 2017-07-13 | 2017-07-13 | G | 2018-11-02 | 2019-03-18 | 2019-11-26 | 2020-10-30 | R | [35 empty] | 2020-11-02 |  | 2021-12-30 |  | G | 2022-01-03 |  | 2022-06-29 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.3317
2170 | 116463 | WIDEN RTE 15 PHASE II LANDSCAPE | 0015 | Urban | Landscaping/Beautification | Locally | Leesburg | LEESBURG | Northern Virginia | Northern Virginia:Leesburg | Infrastructure Investment Division | Amir Salahshoor | A.Salahshoor@VDOT.Virginia.gov | (703) 259-1957 | Veljibhai M Desai | Veljibhai.Desai@vdot.virginia.gov | (703) 259-2927 | Karin Franklin | kfranklin@leesburgva.gov | (703) 771-6674 | 0 |  | 0 | FY2021 | 209356 | 209356 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 238 days early | G | Project is on budget | 2019-10-17 | 2019-10-17 | 2020-01-16 | 2020-01-07 | G | 2020-01-21 | 2020-01-08 | 2020-01-23 | 2020-01-14 | G | 2020-01-24 | 2020-01-15 | 2020-07-28 | 2020-04-15 | G | [35 empty] | 2020-06-25 | 2020-05-27 | 2020-11-30 | 2020-08-11 | G | 2021-02-23 | 2020-10-30 | 2021-06-29 | 2020-11-03 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.37882
2171 | 117074 | Add 3rd lane on Rte 1N from 85 ovrpss to Washington Street | 0001 | Primary | Reconstruction w/ Added Capacity | VDOT | Dinwiddie County | PETERSBURG | Richmond | Tri-Cities:Dinwiddie County | Infrastructure Investment Division | Dianna M Bryant | Dianna.Bryant@VDOT.Virginia.gov | (804) 863-4004 | Dianna M Bryant | Dianna.Bryant@VDOT.Virginia.gov | (804) 863-4004 |  |  |  | 0 |  | 0 | FY2030 | 4264151 | 4264151 | NO DATES SET YET | G | Start Development milestone is 1977 days ahead of the expected completion date | G | Project is on budget | [5 empty] | 2026-07-01 |  | 2026-07-22 |  | G | 2026-07-23 |  | 2027-05-26 |  | G | [5 empty] | 2027-12-28 |  | 2028-01-27 |  | G | 2028-09-14 |  | 2028-10-19 |  | G | 2029-03-27 |  | 2029-07-25 |  | G | 2028-11-03 |  | 2029-04-10 |  | G | 2028-12-18 |  | 2029-05-18 |  | G | [5 empty] | 2029-08-14 |  | 2029-08-14 |  | G | 2029-11-02 |  | 2029-11-02 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.082667
2172 | 117848 | #81CIP DETOUR THREE INTERSECTION IMPROVEMENTS - ROUTE 11 | 0011 | Primary | Other | VDOT | Rockbridge County | LEXINGTON | Staunton | NonMPO:NonMPO | Infrastructure Investment Division | Keith M Rider | Keith.Rider@VDOT.Virginia.gov | (434) 856-8145 | Kunal Kothawade | Kunal.Kothawade@vdot.virginia.gov | (540) 332-9259 |  |  |  | 0 |  | 0 | FY2023 | 200000 | 200000 | NO DATES SET YET-PE OPEN | G | Obtained Permits milestone finished 791 days early | G | Project is on budget | [5 empty] | 2020-08-04 | 2020-08-04 | 2020-08-24 | 2020-08-07 | G | 2020-08-25 | 2020-08-10 | 2021-06-29 |  | G | [5 empty] | 2022-02-02 |  | 2022-03-02 |  | G | [5 empty] | 2022-10-20 |  | 2023-02-27 |  | G | [5 empty] | 2022-07-13 | 2020-08-18 | 2022-12-13 | 2020-10-13 | G | [5 empty] | 2023-03-14 |  | 2023-03-14 |  | G | 2023-06-01 |  | 2023-06-01 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.086668
2173 | 18107 | RTE 669 - RECONSTRUCTION | 0669 | Secondary | Reconstruction w/o Added Capacity | VDOT | Carroll County | MARTINSVILLE | Salem | NonMPO:NonMPO | Infrastructure Investment Division | Robert P Williams | Robbie.Williams@VDOT.Virginia.gov | (276) 229-9954 | Brian H Becker | Brian.Becker@VDOT.Virginia.gov | (540) 204-7959 |  |  |  | 0 |  | 0 | FY2026 | 1923000 | 19200000 | ACTIVITY DATES SET | G | Relocate Utilities milestone finished on-time | R | Project estimate is less than $5M and is 20% or more over budget | [5 empty] | 1998-03-18 | 1998-03-18 | 1998-03-19 | 1998-03-19 | G | 1996-09-11 | 1997-12-05 | 1997-01-01 | 1998-01-05 | R | [5 empty] | 1998-12-03 | 1998-12-03 | 1998-12-17 | 1998-12-17 | G | 1999-06-17 | 1999-06-17 | 1999-06-25 | 1999-06-25 | G | 2000-10-18 | 2000-10-18 | 2002-08-12 | 2002-08-12 | G | 1999-10-15 | 1999-10-15 | 2001-05-24 | 2001-05-24 | G | [10 empty] | 2025-07-30 |  | 2025-12-09 |  | G | 2025-09-09 |  | 2025-10-28 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.11234
2174 | 90018 | CEDAR LEVEL RD - WIDENING | 9047 | Urban | Reconstruction w/o Added Capacity | VDOT | Hopewell | PETERSBURG | Richmond | Tri-Cities:Hopewell | Infrastructure Investment Division | Susan Warr | Susan.Warr@VDOT.Virginia.gov | (804) 720-5478 | Susan Warr | Susan.Warr@VDOT.Virginia.gov | (804) 720-5478 |  |  |  | 0 |  | 0 | FY2019 | 10652000 | 9381257 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 43 days early | G | Project is on budget | [5 empty] | 2011-09-01 | 2011-09-09 | 2011-09-01 | 2011-09-09 | R | 2011-09-02 | 2011-09-09 | 2011-12-30 | 2015-03-24 | R | [5 empty] | 2015-04-23 | 2015-04-23 | 2015-08-18 | 2015-08-18 | G | [25 empty] | 2018-07-10 | 2018-07-10 | 2018-07-10 | 2018-07-10 | G | 2018-08-22 | 2018-09-18 | 2018-10-31 | 2018-09-18 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.083037
2175 | 102859 | Shirlington Bridge Rehabiliation and Pedestrian Impr RVSH13 | 6721 | Secondary | Bridge Rehab w/o Added Capacity | Locally | Arlington County | FAIRFAX | Northern Virginia | Northern Virginia:Arlington County | Local Assistance Division | Amir Salahshoor | A.Salahshoor@VDOT.Virginia.gov | (703) 259-1957 | Susie X Lue | Susie.Lue@vdot.virginia.gov | (703) 259-2918 | Rene Haris | rharris1@arlingtonva.us | (703) 364-8741 | 0 |  | 0 | FY2024 | 5297400 | 5297400 | NO DATES SET YET-PE OPEN | R | Determine Requirements milestone is 604 days past the expected completion date | G | Project is on budget | 2015-05-27 | 2015-05-27 | 2015-06-10 | 2015-06-10 | G | 2014-10-01 | 2014-10-01 | 2014-10-02 | 2014-10-02 | G | 2018-02-01 | 2018-02-01 | 2019-06-28 |  | R | [5 empty] | 2022-05-11 |  | 2022-10-31 |  | G | [15 empty] | 2023-05-10 |  | 2023-09-29 |  | G | [5 empty] | 2022-09-01 |  | 2023-02-24 |  | G | 2023-02-27 |  | 2023-07-31 |  | G | Preliminary design and/or investigations are still underway | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.36977
2176 | 104953 | #SGR17VB - RT 360 - REPLACE WBL BRIDGE (Fed 1224; CN ONLY) | 0360 | Primary | Bridge Replacement w/o Added Capacity | VDOT | Amelia County | CHESTERFIELD | Richmond | NonMPO:NonMPO | Infrastructure Investment/Asset Management Division | Jeremy B Cobb | Jeremy.Cobb@vdot.virginia.gov | (804) 586-2255 | Jeremy B Cobb | Jeremy.Cobb@vdot.virginia.gov | (804) 586-2255 |  |  |  | 0 |  | 1 | FY2021 | 4384600 | 4384600 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 76 days early | G | Project is on budget | [10 empty] | 2015-08-13 | 2015-08-13 | 2017-10-03 | 2017-10-03 | G | [5 empty] | 2018-02-20 | 2018-02-20 | 2018-02-23 | 2018-02-23 | G | [25 empty] | 2020-07-14 | 2020-06-09 | 2020-07-14 | 2020-06-09 | G | 2020-09-02 | 2020-09-16 | 2020-12-01 | 2020-09-16 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.070009
2177 | 105622 | Intersection Improvements- VB Blvd and First Colonial Rd | 0058 | Urban | Reconstruction w/o Added Capacity | Locally | Virginia Beach | NORFOLK | Hampton Roads | Hampton Roads:Virginia Beach | Local Assistance Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Marci Thompson | Marci.Thompson@vdot.virginia.gov | (757) 956-3093 | Katie Shannon | kshannon@vbgov.com | (757) 385-1514 | 0 |  | 0 | FY2019 | 27601664 | 31748721 | ACTIVITY DATES SET | R | Solicit Bids milestone is 997 days past the expected completion date | R | Project estimate is greater than $10M and is over budget by (a) 10% or more or (b) $5M or more | [5 empty] | 2014-08-01 | 2014-08-01 | 2014-08-01 | 2014-08-01 | G | 2014-09-02 | 2015-07-20 | 2014-12-31 | 2015-09-15 | R | [10 empty] | 2015-08-06 | 2015-08-06 | 2015-08-10 | 2015-08-10 | G | [20 empty] | 2018-04-16 |  | 2018-05-31 |  | R | 2018-10-31 |  | 2018-11-06 |  | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.18522
2178 | 106513 | US 58 Rumble Strips - Lee County | 0058 | Primary | Safety | VDOT | Lee County | WISE | Bristol | NonMPO:NonMPO | Infrastructure Investment Division | John W Bechtold | John.Bechtold@vdot.virginia.gov | (276) 696-3365 | Brandi Halloway | Brandi.Halloway@vdot.virginia.gov | (276) 696-3254 |  |  |  | 0 |  | 0 | FY2020 | 865863 | 799586 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 1 days early | G | Project is on budget | [5 empty] | 2018-07-01 | 2018-06-21 | 2018-07-01 | 2018-06-21 | G | 2018-07-31 | 2018-07-23 | 2019-02-28 | 2019-02-20 | G | [35 empty] | 2019-07-12 | 2019-07-09 | 2019-07-12 | 2019-07-09 | G | 2019-07-15 | 2019-07-24 | 2019-08-23 | 2019-08-22 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.066378
2179 | 106960 | PED. & BIKE FACILITIES UPGRADES TO TRAFFIC SIGNALS | 0000 | Primary | Safety | VDOT | Albemarle County | CHARLOTTESVILLE | Culpeper | Charlottesville:Albemarle County | Infrastructure Investment Division | Nathan Umberger |  |  | Caroline Awua-Mensah | Caroline.Awua-Mensah@vdot.virginia.gov | (540) 829-7618 |  |  |  | 0 |  | 0 | FY2019 | 800000 | 800000 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 147 days early | G | Project is on budget | [5 empty] | 2016-07-01 | 2016-07-06 | 2016-07-15 | 2016-09-06 | R | 2016-07-18 | 2016-07-17 | 2016-08-12 | 2016-12-06 | R | [35 empty] | 2017-07-06 | 2017-07-11 | 2017-07-06 | 2017-07-11 | R | 2017-08-24 | 2018-09-20 | 2019-02-14 | 2018-09-20 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | WORK/TASK ORDER | 1 | 1 | 0.3543
2180 | 106994 | NORTHSTAR BLVD EXTENSION SHREVEPORT DR TO ROUTE 50 | 9999 | Secondary | New Construction Roadway | Locally | Loudoun County | LEESBURG | Northern Virginia | Northern Virginia:Loudoun County | Local Assistance Division | Amir Salahshoor | A.Salahshoor@VDOT.Virginia.gov | (703) 259-1957 | Susie X Lue | Susie.Lue@vdot.virginia.gov | (703) 259-2918 | Marie Caraballo | Marie.Caraballo@loudoun.gov | (703) 771-5352 | 0 |  | 0 | FY2021 | 89997000 | 89997000 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 78 days early | G | Project is on budget | 2015-07-01 | 2015-07-01 | 2016-06-16 | 2016-06-16 | G | 2016-05-26 | 2016-05-26 | 2016-05-26 | 2016-05-26 | G | 2017-01-04 | 2017-01-04 | 2020-03-23 | 2020-03-31 | R | [5 empty] | 2019-11-01 | 2019-11-01 | 2020-03-31 | 2020-03-31 | G | 2020-02-03 | 2020-02-03 | 2020-05-26 | 2020-04-17 | G | [20 empty] | 2020-05-27 | 2020-02-03 | 2020-07-24 | 2020-04-22 | G | 2020-07-27 | 2020-04-23 | 2021-03-02 | 2020-12-14 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.2278
2181 | 107059 | RTE 604 (Genito/Otterdale) - CONSTRUCT ROUNDABOUT | 0604 | Secondary | Safety | Locally | Chesterfield County | CHESTERFIELD | Richmond | Richmond:Chesterfield County | Local Assistance Division | Brian J Lokker | Brian.Lokker@VDOT.Virginia.gov | (804) 524-6010 | Brian J Lokker | Brian.Lokker@VDOT.Virginia.gov | (804) 524-6010 | Brent Epps | eppsb@chesterfield.gov | (804) 748-1037 | 0 |  | 0 | FY2019 | 3835000 | 3928000 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 93 days early | Y | Project estimate is less than $5M and is up to 20% over budget | 2015-07-01 | 2015-09-29 | 2015-09-24 | 2015-09-29 | R | 2015-09-25 | 2015-10-21 | 2015-10-08 | 2015-10-21 | R | 2015-10-09 | 2016-12-19 | 2016-06-08 | 2016-12-19 | R | [10 empty] | 2017-04-28 | 2017-01-20 | 2017-05-11 | 2017-01-20 | G | [5 empty] | 2017-01-27 | 2017-01-27 | 2018-01-23 | 2018-01-23 | G | [10 empty] | 2018-01-05 | 2018-01-05 | 2018-05-01 | 2018-03-22 | G | 2018-05-02 | 2018-04-30 | 2018-08-01 | 2018-04-30 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.24274
2182 | 108765 | BEECH AVENUE - DRAINAGE AND PAVING IMPROVEMENTS | 9999 | Urban | Restoration and Rehabilitation | Locally | Danville | HALIFAX | Lynchburg | Danville:Danville | Local Assistance Division | Sharon S White | Sharon.White@VDOT.Virginia.gov | (434) 856-8220 | Sharon S White | Sharon.White@VDOT.Virginia.gov | (434) 856-8220 | Brian Dunevant, P.E. | dunevbl@danvilleva.gov | (434) 799-5019 | 0 |  | 0 | FY2020 | 750000 | 750000 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 277 days early | G | Project is on budget | 2016-10-03 | 2016-04-26 | 2016-12-30 | 2016-07-20 | G | 2017-01-03 | 2017-03-14 | 2017-01-05 | 2017-03-14 | R | 2017-01-06 | 2016-08-31 | 2017-07-13 | 2017-12-21 | R | [35 empty] | 2018-07-24 | 2018-07-24 | 2018-08-10 | 2018-09-28 | R | 2019-08-13 | 2018-12-13 | 2019-10-15 | 2019-01-11 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.067988
2183 | 108906 | #HB2.FY17 I-81 Auxiliary Lanes from Exit 141 to 143 | 0081 | Interstate | Reconstruction w/ Added Capacity | VDOT | Roanoke County | SALEM | Salem | Roanoke:Roanoke County | Infrastructure Investment Division | Thomas W Digiulian | Thomas.DiGiulian@VDOT.Virginia.gov | (540) 387-5356 | Jeffrey A Echols | Jeff.Echols@VDOT.Virginia.gov | (540) 375-3595 |  |  |  | 1 | 2017 | 0 | FY2021 | 29830716 | 29830716 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 342 days early | G | Project is on budget | [5 empty] | 2016-06-20 | 2016-06-20 | 2016-07-01 | 2016-07-01 | G | 2016-07-05 | 2016-07-05 | 2017-07-19 | 2017-07-18 | G | [5 empty] | 2018-03-01 | 2018-01-23 | 2018-03-14 | 2018-01-24 | G | 2019-01-04 | 2018-06-14 | 2019-01-22 | 2018-06-15 | G | 2019-11-04 | 2019-09-20 | 2020-06-04 | 2020-01-15 | G | 2019-02-11 | 2018-06-18 | 2020-01-03 | 2019-02-20 | G | 2018-12-11 | 2018-07-23 | 2020-06-11 | 2019-07-11 | G | [5 empty] | 2020-08-11 | 2019-09-10 | 2020-08-11 | 2019-09-24 | G | 2020-09-24 | 2020-01-15 | 2020-12-22 | 2020-01-15 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.1302
2184 | 109922 | Route 80 Shoulder Initiative | 0080 | Primary | Safety | VDOT | Russell County | LEBANON | Bristol | NonMPO:NonMPO | Infrastructure Investment Division | Jeffrey Buchanan | Jeff.Buchanan@vdot.virginia.gov | (276) 415-3440 | Jonathan A Henegar | Jonathan.Henegar@vdot.virginia.gov | (276) 206-0360 |  |  |  | 0 |  | 0 | FY2021 | 1665000 | 1745394 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 29 days early | Y | Project estimate is less than $5M and is up to 20% over budget | [5 empty] | 2017-10-27 | 2017-10-27 | 2017-10-27 | 2017-10-27 | G | 2017-10-30 | 2017-10-30 | 2018-08-17 | 2018-08-17 | G | [5 empty] | 2019-06-18 | 2019-06-18 | 2019-07-30 | 2019-07-30 | G | [5 empty] | 2020-01-15 | 2020-01-22 | 2020-05-08 | 2020-05-08 | G | [5 empty] | 2019-12-30 | 2019-12-17 | 2020-04-02 | 2019-12-17 | G | [5 empty] | 2020-06-09 | 2020-05-05 | 2020-06-09 | 2020-05-05 | G | 2020-07-30 | 2020-07-21 | 2020-08-19 | 2020-07-21 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.059543
2185 | 110824 | FYA CONVERSION OF 25 TRAFFIC SIGNALS | 9999 | Secondary | Safety | Locally | Fredericksburg | FREDERICKSBURG | Fredericksburg | Fredericksburg:Fredericksburg | Infrastructure Investment Division | Peter A Hedrich | Peter.Hedrich@vdot.virginia.gov | (540) 899-4540 | Anastasia Kapitan | Anastasia.Kapitan@vdot.virginia.gov | (540) 899-4292 | Erik Nelson | enelson@fredericksburgva.gov |  | 0 |  | 0 | FY2022 | 495000 | 485000 | ACTIVITY DATES SET | Y | Solicit Bids milestone is 33 days ahead of the expected completion date and there is a risk of missing this milestone date | G | Project is on budget | 2019-07-01 | 2019-07-01 | 2019-09-24 | 2019-09-19 | G | 2019-09-25 | 2019-09-01 | 2019-10-08 | 2019-09-20 | G | 2019-10-09 | 2019-09-23 | 2020-04-20 | 2020-04-07 | G | [35 empty] | 2020-12-29 |  | 2021-03-26 |  | Y | 2021-05-10 |  | 2021-10-28 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.15755
2186 | 111303 | #SGR18VB - BRIDGE-ONLY REHAB I-64 OVER I-95 (Fed 21441) | 0064 | Interstate | Bridge Rehab w/o Added Capacity | VDOT | Richmond | ASHLAND | Richmond | Richmond:Richmond | Infrastructure Investment/Asset Management Division | Evan Roberts | Evan.Roberts@vdot.virginia.gov | (804) 609-5427 | Evan Roberts | Evan.Roberts@vdot.virginia.gov | (804) 609-5427 |  |  |  | 0 |  | 1 | FY2022 | 4050000 | 4650000 | ACTIVITY DATES SET | Y | Solicit Bids milestone is 51 days ahead of the expected completion date and there is a risk of missing this milestone date | Y | Project estimate is less than $5M and is up to 20% over budget | [5 empty] | 2017-08-16 | 2017-08-16 | 2017-08-22 | 2017-08-22 | G | 2019-06-03 | 2019-06-03 | 2019-11-21 | 2019-11-18 | G | [5 empty] | 2020-05-27 | 2020-06-05 | 2020-06-09 | 2020-06-09 | G | 2020-07-23 | 2020-07-23 | 2020-07-23 | 2020-07-23 | G | 2020-08-20 | 2020-08-20 | 2020-08-20 | 2020-08-20 | G | 2020-07-23 | 2020-07-23 | 2020-07-23 | 2020-07-23 | G | 2020-06-11 | 2019-06-27 | 2020-10-02 | 2019-06-27 | G | [5 empty] | 2021-04-13 |  | 2021-04-13 |  | Y | 2021-09-20 |  | 2021-10-08 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.10672
2187 | 111452 | #SGR18LB - REPLACE SUPERSTRUCT & REPAIR SUBSTRUCT(29760 Fed) | 0000 | Miscellaneous | Bridge Rehab w/o Added Capacity | Locally | Buchanan County | LEBANON | Bristol | NonMPO:NonMPO | Infrastructure Investment Division | John W Bechtold | John.Bechtold@vdot.virginia.gov | (276) 696-3365 | Roger L Musser | Roger.Musser@VDOT.Virginia.gov | (276) 696-3260 | Marcus Stiltner | marcus.stiltner@buchanancounty-va.gov | (276) 935-4013 | 0 |  | 1 | FY2023 | 85000 | 85000 | NO DATES SET YET-PE OPEN | G | Start Development milestone finished 1273 days early | G | Project is on budget | 2021-07-01 | 2018-02-01 | 2021-09-24 | 2018-04-02 | G | 2021-09-27 | 2018-04-03 | 2021-09-29 | 2018-04-05 | G | 2021-09-30 |  | 2022-04-12 |  | G | [35 empty] | 2023-02-23 |  | 2023-03-22 |  | G | 2023-03-23 |  | 2023-05-02 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.10028
2188 | 111796 | #SMART18 - BARRACKS RD @ EMMET ST INTERSECTION | 0029 | Urban | Safety | Locally | Charlottesville | CHARLOTTESVILLE | Culpeper | Charlottesville:Charlottesville | Local Assistance Division | Ken Connors |  |  | Michael D Barnes | MichaelD.Barnes@vdot.virginia.gov | (434) 422-9861 | Kyle Kling | klingk@charlottesville.gov | (434) 970-3182 | 1 | 2018 | 0 | FY2026 | 8640866 | 8640866 | NO DATES SET YET-PE OPEN | G | Start Development milestone finished 1161 days early | G | Project is on budget | 2021-04-16 | 2017-12-14 | 2021-07-12 | 2018-05-08 | G | 2021-07-13 | 2018-05-09 | 2021-07-15 | 2018-05-11 | G | 2021-07-16 | 2018-05-14 | 2022-12-27 |  | G | [10 empty] | 2024-02-14 |  | 2024-03-06 |  | G | [5 empty] | 2024-03-08 |  | 2025-04-14 |  | G | [10 empty] | 2025-04-30 |  | 2025-05-28 |  | G | 2025-05-29 |  | 2025-07-09 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.17205
2189 | 113175 | MULTI-MODAL IMPROVEMENTS (CITYWIDE) | 9999 | Urban | Facilities for Pedestrians and Bicycles | Locally | Charlottesville | CHARLOTTESVILLE | Culpeper | NonMPO:NonMPO | Local Assistance Division | Ken Connors |  |  | Michael D Barnes | MichaelD.Barnes@vdot.virginia.gov | (434) 422-9861 | Tim Motsch/ Jeanette Janiczek | motscht@charlottesville.gov | (434) 970-3182 | 0 |  | 0 | FY2022 | 1800000 | 1800000 | ACTIVITY DATES SET | G | Start Purchasing Right-of-Way milestone finished on-time | G | Project is on budget | 2019-03-01 | 2019-03-01 | 2019-05-23 | 2019-04-11 | G | 2019-05-24 | 2019-04-12 | 2019-05-29 | 2019-04-16 | G | 2019-05-30 | 2019-04-17 | 2019-12-05 | 2019-12-19 | R | [10 empty] | 2020-12-22 | 2020-12-22 | 2021-01-13 | 2021-01-13 | G | [5 empty] | 2021-01-19 | 2021-01-19 | 2021-10-25 |  | G | 2019-10-22 | 2020-02-28 | 2020-06-26 | 2020-02-28 | G | [5 empty] | 2021-11-10 |  | 2021-12-10 |  | G | 2022-03-07 |  | 2022-03-07 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.13698
2190 | 107013 | OLD LEE HIGHWAY BIKEWAY & TRAIL | 6628 | Urban | Facilities for Pedestrians and Bicycles | Locally | Fairfax | FAIRFAX | Northern Virginia | Northern Virginia:Fairfax | Local Assistance Division | Amir Salahshoor | A.Salahshoor@VDOT.Virginia.gov | (703) 259-1957 | Christer P Carshult | Christer.Carshult@vdot.virginia.gov | (703) 259-1765 | Wendy Sanford | wendy.sanford@fairfaxva.gov | 70338578 | 0 |  | 0 | FY2023 | 26800000 | 26800000 | NO DATES SET YET-PE OPEN | R | Determine Requirements milestone is 844 days past the expected completion date | G | Project is on budget | 2015-07-01 | 2015-07-01 | 2015-08-07 | 2015-08-07 | G | 2015-07-01 | 2015-07-01 | 2015-08-07 | 2015-08-07 | G | 2015-10-09 | 2015-08-10 | 2018-10-31 |  | R | [10 empty] | 2019-06-17 |  | 2021-09-30 |  | G | [5 empty] | 2020-02-04 |  | 2022-05-12 |  | G | [10 empty] | 2021-10-04 |  | 2022-03-31 |  | G | 2022-04-01 |  | 2022-08-31 |  | G | Design plans are being revised | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.27353
2191 | 108501 | ROUTE 50 SIDEWALK FROM ANNANDALE ROAD TO CHERRY STREET | 0050 | Primary | Safety | Locally | Fairfax County | FAIRFAX | Northern Virginia | Northern Virginia:Fairfax County | Infrastructure Investment Division | Amir Salahshoor | A.Salahshoor@VDOT.Virginia.gov | (703) 259-1957 | Rita Hockman | Rita.Hockman@vdot.virginia.gov | (804) 824-7421 | Fasika Metafria | Fasika.Metafria@fairfaxcounty.gov | (703) 324-5085 | 0 |  | 0 | FY2020 | 575001 | 470000 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 425 days early | G | Project is on budget | 2014-12-30 | 2014-12-30 | 2015-03-27 | 2015-03-27 | G | 2015-03-30 | 2015-03-30 | 2015-04-01 | 2015-04-01 | G | 2015-04-02 | 2015-04-02 | 2015-10-05 | 2015-10-05 | G | [10 empty] | 2016-08-01 | 2016-08-01 | 2017-06-09 | 2017-06-09 | G | [5 empty] | 2017-06-13 | 2017-06-13 | 2019-12-31 | 2017-12-19 | G | [10 empty] | 2020-01-21 | 2018-06-05 | 2020-01-21 | 2018-09-21 | G | 2020-01-22 | 2018-09-21 | 2020-03-03 | 2019-01-03 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.076009
2192 | 108885 | #SMART18 - HOPKINS ROAD SIDEWALK (BONNIEBANK RD TO S MELODY) | 0637 | Secondary | Safety | Locally | Chesterfield County | CHESTERFIELD | Richmond | Richmond:Chesterfield County | Infrastructure Investment Division | Michael S Gray | Mike.Gray@vdot.virginia.gov | (804) 609-5347 | Michael S Gray | Mike.Gray@vdot.virginia.gov | (804) 609-5347 | Stan Newcomb | NewcombS@chesterfield.gov | (804) 748-1037 | 1 | 2018 | 0 | FY2022 | 967200 | 954849 | ACTIVITY DATES SET | G | Obtained Permits milestone finished 220 days early | G | Project is on budget | 2021-07-02 | 2018-08-01 | 2021-09-27 | 2018-11-05 | G | 2019-09-30 | 2018-11-26 | 2019-09-30 | 2018-11-30 | G | 2021-10-01 | 2018-12-03 | 2022-04-13 | 2020-01-16 | G | [5 empty] | 2020-02-06 | 2020-02-06 | 2020-03-24 | 2020-03-24 | G | 2020-03-25 | 2020-03-24 | 2020-04-15 | 2020-03-24 | G | 2021-02-01 | 2020-03-24 | 2021-07-30 | 2020-03-24 | G | 2020-06-30 | 2020-03-24 | 2021-01-29 | 2020-03-24 | G | 2020-12-28 | 2021-01-22 | 2021-08-30 | 2021-01-22 | G | [5 empty] | 2021-09-30 |  | 2021-09-30 |  | G | 2022-01-31 |  | 2022-01-31 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.18672
2193 | 109578 | #HB2.FY17 - RAPPAHANNOCK COMM. COLLEGE SITE ACCESS IMPROV | 0033 | Primary | Other | VDOT | Gloucester County | SALUDA | Fredericksburg | NonMPO:NonMPO | Infrastructure Investment Division | Gale Dickerson |  |  | Beau C Hoyt | Beau.Hoyt@vdot.virginia.gov | (804) 317-3326 |  |  |  | 1 | 2017 | 0 | FY2019 | 625000 | 625000 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 127 days early | G | Project is on budget | [5 empty] | 2017-06-21 | 2017-06-21 | 2017-07-05 | 2017-07-07 | R | 2017-07-06 | 2017-07-10 | 2018-05-29 | 2017-11-30 | G | [5 empty] | 2018-01-26 | 2018-01-23 | 2018-02-08 | 2018-01-23 | G | 2018-04-17 | 2018-02-27 | 2018-04-17 | 2018-03-01 | G | 2018-02-21 | 2018-01-31 | 2018-02-21 | 2018-01-31 | G | 2018-04-17 | 2018-02-27 | 2018-04-17 | 2018-02-27 | G | [10 empty] | 2018-07-10 | 2018-06-12 | 2018-07-10 | 2018-06-12 | G | 2018-10-19 | 2018-08-13 | 2018-12-18 | 2018-08-13 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.077688
2194 | 110001 | #SGR18VB - RT 240 CROZET AVE STR 589 OVER LICKINGHOLE CREEK | 0240 | Primary | Bridge Rehab w/o Added Capacity | VDOT | Albemarle County | CHARLOTTESVILLE | Culpeper | Charlottesville:Albemarle County | Infrastructure Investment/Asset Management Division | Ken Connors |  |  | Howard M Tomlinson | Howard.Tomlinson@VDOT.virginia.gov | (540) 829-7436 |  |  |  | 0 |  | 1 | FY2022 | 2210000 | 2210000 | ACTIVITY DATES SET | G | Complete Purchasing Right-of-Way milestone finished 321 days early | G | Project is on budget | [5 empty] | 2017-07-03 | 2017-03-14 | 2017-07-17 | 2017-03-20 | G | 2017-07-18 | 2017-03-21 | 2018-06-14 | 2019-04-15 | R | [5 empty] | 2020-01-23 | 2019-04-18 | 2020-02-05 | 2019-05-28 | G | 2021-04-07 | 2020-04-17 | 2021-04-20 |  | G | 2021-09-13 | 2020-12-30 | 2022-03-24 |  | G | 2021-05-05 | 2020-05-04 | 2021-11-08 | 2020-12-22 | G | 2020-10-23 | 2020-08-20 | 2021-06-30 |  | G | [5 empty] | 2022-04-12 |  | 2022-04-12 |  | G | 2022-06-02 |  | 2022-06-22 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 1 | 0.28281
2195 | 110844 | PHASE 2 - PEDESTRIAN SAFETY IMPROVEMENTS - CITYWIDE |  | Miscellaneous | Safety | Locally | Richmond | ASHLAND | Richmond | Richmond:Richmond | Infrastructure Investment Division | Evan Austin | Evan.Austin@vdot.virginia.gov | (804) 609-5384 | Evan Austin | Evan.Austin@vdot.virginia.gov | (804) 609-5384 | Michael Sawyer | michael.sawyer@richmondgov.com | (804) 646-3435 | 0 |  | 0 | FY2022 | 1845600 | 1845600 | NO DATES SET YET-PE OPEN | R | Determine Requirements milestone is 318 days past the expected completion date | G | Project is on budget | 2019-07-01 | 2019-02-19 | 2019-09-24 | 2019-07-09 | G | 2019-09-25 | 2019-07-17 | 2019-09-27 | 2019-07-23 | G | 2019-09-30 |  | 2020-04-09 |  | R | [35 empty] | 2021-04-28 |  | 2021-05-25 |  | G | 2021-05-26 |  | 2021-11-16 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.08137
2196 | 111396 | W. Main Steet Sidewalk Extension |  | Primary | Facilities for Pedestrians and Bicycles | Locally | Louisa | LOUISA | Culpeper | NonMPO:NonMPO | Local Assistance Division | Thomas Fitzpatrick | Thomas.Fitzpatrick@vdot.virginia.gov |  | Thomas Fitzpatrick | Thomas.Fitzpatrick@vdot.virginia.gov |  | Liz Nelson | lnelson@louisatown.org | (540) 967-1400 | 0 |  | 0 | FY2022 | 1481009 | 1481009 | ACTIVITY DATES SET | R | Determine Requirements milestone finished 338 days late | G | Project is on budget | 2017-10-02 | 2017-10-02 | 2017-11-16 | 2017-11-16 | G | 2018-01-02 | 2018-01-02 | 2018-01-09 | 2018-01-09 | G | 2018-01-03 | 2018-01-03 | 2020-01-13 | 2020-12-16 | R | [10 empty] | 2021-04-29 |  | 2021-06-03 |  | G | [5 empty] | 2021-06-18 |  | 2021-11-17 |  | G | [10 empty] | 2022-02-28 |  | 2022-04-08 |  | G | 2022-06-28 |  | 2022-06-28 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.15565
2197 | 111791 | #SMART18 - Route 171 Widening between Route 17 and Route 134 | 0171 | Primary | Reconstruction w/ Added Capacity | VDOT | York County | WILLIAMSBURG | Hampton Roads | Hampton Roads:Hampton Roads District-wide | Infrastructure Investment Division | Peter G Reilly | Peter.Reilly@vdot.virginia.gov | (757) 858-6748 | Andrew B Scott | Andrew.Scott@VDOT.Virginia.gov | (757) 956-3273 | Timothy Cross | tcross@yorkcounty.gov | (757) 890-3496 | 1 | 2018 | 0 | FY2024 | 4643259 | 4643259 | NO DATES SET YET-PE OPEN | G | Start Development milestone finished 596 days early | G | Project is on budget | [5 empty] | 2021-08-02 | 2019-12-18 | 2021-08-13 | 2019-12-26 | G | 2021-08-16 |  | 2022-04-22 |  | G | [5 empty] | 2021-04-22 |  | 2021-05-05 |  | G | 2022-04-18 |  | 2022-05-03 |  | G | 2022-09-26 |  | 2023-06-23 |  | G | 2022-05-19 |  | 2022-11-23 |  | G | 2021-11-08 |  | 2022-05-18 |  | G | [5 empty] | 2023-07-11 |  | 2023-07-11 |  | G | 2023-08-24 |  | 2023-10-20 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.14974
2198 | 113029 | #SGR19VB - RT 644 over Pope Swamp (Fed 10424) Replacement | 0644 | Secondary | Bridge Replacement w/o Added Capacity | VDOT | Isle of Wight County | FRANKLIN | Hampton Roads | Hampton Roads:Isle of Wight County | Infrastructure Investment/Asset Management Division | Mark Wagner |  |  | Matthew Shaver | Matthew.Shaver@vdot.virginia.gov | (757) 956-3222 |  |  |  | 0 |  | 1 | FY2023 | 4200000 | 4118288 | ACTIVITY DATES SET | R | Engage Public milestone finished 80 days late | G | Project is on budget | [5 empty] | 2018-09-04 | 2018-07-16 | 2018-09-17 | 2018-07-27 | G | 2018-09-18 | 2018-07-30 | 2019-08-15 | 2019-08-15 | G | [5 empty] | 2020-07-21 | 2020-07-21 | 2020-08-03 | 2020-10-22 | R | 2021-10-04 |  | 2021-10-15 |  | G | 2022-03-18 |  | 2022-09-20 |  | G | 2021-11-02 |  | 2022-05-12 |  | G | 2018-11-26 | 2018-11-26 | 2022-06-03 |  | G | [5 empty] | 2022-10-11 |  | 2022-10-11 |  | G | 2023-01-06 |  | 2023-01-06 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.15083
2199 | 113182 | UPPER KENT DRIVE RECONSTRUCTION AND IMPROVEMENTS | 9999 | Urban | Reconstruction w/o Added Capacity | Locally | Manassas Park | MANASSAS | Northern Virginia | Northern Virginia:Manassas Park | Local Assistance Division | Claudia H Llana | Claudia.Llana@VDOT.Virginia.gov | (703) 259-1768 | Robert J Strevell | Robert.Strevell@vdot.virginia.gov | (703) 259-1988 | Calvin O'Dell | c.odell@manassasparkva.gov | 703335001 | 0 |  | 0 | FY2020 | 564000 | 564000 | NO DATES SET YET-PE OPEN | R | Solicit Bids milestone is 663 days past the expected completion date | G | Project is on budget | 2018-12-14 | 2018-09-01 | 2019-05-30 | 2018-10-26 | G | 2019-07-01 | 2019-02-19 | 2019-08-30 | 2019-04-19 | G | 2018-12-14 |  | 2019-06-28 |  | R | [20 empty] | 2018-12-14 |  | 2019-09-30 |  | R | [10 empty] | 2018-12-31 |  | 2019-04-30 |  | R | 2019-07-19 |  | 2019-11-27 |  | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.15822
2200 | 113363 | Primary Extensions: E Washington Street Resurfacing |  | Urban | Resurfacing | VDOT | Petersburg | PETERSBURG | Richmond | Tri-Cities:Petersburg | Local Assistance Division | Dianna M Bryant | Dianna.Bryant@VDOT.Virginia.gov | (804) 863-4004 | Dianna M Bryant | Dianna.Bryant@VDOT.Virginia.gov | (804) 863-4004 | Bill Riggleman | briggleman@petersburg-va.org | (804) 733-2355 | 0 |  | 1 | FY2020 | 464254 | 464254 | AWARDED | G | Start Delivery milestone finished 233 days early | G | Project is on budget | [10 empty] | 2018-05-01 | 2018-10-25 | 2018-05-07 | 2018-12-19 | R | [25 empty] | 2018-11-29 | 2018-11-29 | 2019-03-28 | 2018-11-29 | G | [5 empty] | 2019-05-28 | 2018-12-18 | 2019-05-28 | 2018-12-18 | G | 2019-08-16 | 2018-12-26 | 2019-08-16 | 2018-12-26 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | WORK/TASK ORDER | 1 | 0 | 0.067523
2201 | 113430 | West Creek Trail |  | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Goochland County | ASHLAND | Richmond | Richmond:Goochland County | Local Assistance Division | Jorg Huckabee-Mayfield | Jorg.Huckabee-Mayfield@VDOT.Virginia.gov | (804) 609-5292 | Jorg Huckabee-Mayfield | Jorg.Huckabee-Mayfield@VDOT.Virginia.gov | (804) 609-5292 | Derek Stamey | dstamey@goochlandva.us | (804) 556-5855 | 0 |  | 0 | FY2023 | 800000 | 800000 | NO DATES SET YET-PE OPEN | R | Determine Requirements milestone is 205 days past the expected completion date | G | Project is on budget | 2018-12-31 | 2018-07-30 | 2019-03-28 | 2019-04-10 | R | 2019-03-29 | 2019-05-16 | 2019-04-25 | 2019-05-22 | R | 2019-04-26 |  | 2020-07-31 |  | R | [10 empty] | 2021-05-27 |  | 2021-06-17 |  | G | [5 empty] | 2021-06-21 |  | 2022-04-04 |  | G | 2019-12-10 |  | 2020-08-12 |  | R | [5 empty] | 2022-04-20 |  | 2022-05-17 |  | G | 2022-08-05 |  | 2022-08-05 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.38139
2202 | 113607 | OLD CAROLINA ROAD SIDEWALK IMPROVEMENTS | 0703 | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Prince William County | MANASSAS | Northern Virginia | Northern Virginia:Prince William County | Local Assistance Division | Amir Salahshoor | A.Salahshoor@VDOT.Virginia.gov | (703) 259-1957 | Saif-Ur Qargha | Saif.Qargha@vdot.virginia.gov | (703) 259-3223 | Javier Ibe | jibe@pwcgov.org | (703) 792-8164 | 0 |  | 0 | FY2024 | 884626 | 1012415 | ACTIVITY DATES SET | G | Determine Requirements milestone finished on-time | Y | Project estimate is less than $5M and is up to 20% over budget | 2019-03-01 | 2019-03-01 | 2019-09-30 | 2019-09-10 | G | 2019-10-01 | 2019-08-15 | 2019-10-31 | 2019-09-11 | G | 2019-11-01 | 2019-09-12 | 2020-08-31 | 2020-08-31 | G | [10 empty] | 2021-11-16 |  | 2021-12-16 |  | G | [5 empty] | 2021-12-17 |  | 2022-09-13 |  | G | 2021-01-05 |  | 2021-08-09 |  | G | [5 empty] | 2022-10-12 |  | 2023-04-13 |  | G | 2023-04-14 |  | 2023-10-11 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 1 | 0.412
2203 | 113766 | ST. PAUL-REPLACE AND CONSTRUCT NEW SIDEWALK VAR. ROUTES | 9999 | Miscellaneous | Facilities for Pedestrians and Bicycles | Locally | Saint Paul | WISE | Bristol | NonMPO:NonMPO | Infrastructure Investment Division | Tabitha H Crowder | Tabitha.Crowder@vdot.virginia.gov | (276) 696-3482 | Kenneth R Plummer | KR.Plummer@VDOT.Virginia.gov | (276) 696-3261 | Deborah Baca |  |  | 0 |  | 0 | FY2025 | 766875 | 766875 | NO DATES SET YET | G | Agreement with Locality milestone is 884 days ahead of the expected completion date | G | Project is on budget | 2023-05-01 |  | 2023-07-25 |  | G | 2023-07-26 |  | 2023-07-28 |  | G | 2023-07-31 |  | 2024-02-08 |  | G | [25 empty] | 2024-03-18 |  | 2024-11-15 |  | G | [5 empty] | 2025-02-27 |  | 2025-03-26 |  | G | 2025-06-13 |  | 2025-06-13 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.098077
2204 | 113864 | Resurface Statler Blvd (Rte. 261S) - Primary Extension | 0261 | Urban | Resurfacing | Locally | Staunton | HARRISONBURG | Staunton | SAW:Staunton | Local Assistance Division | Donald F Komara | Donald.Komara@VDOT.Virginia.gov | (540) 434-2587 | Michael S Fulcher | Michael.Fulcher@VDOT.Virginia.gov | (540) 332-2243 | Steve Yancey | yanceysc@ci.staunton.va.us | (540) 332-3892 | 0 |  | 1 | FY2020 | 240000 | 240000 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 412 days early | G | Project is on budget | 2018-12-31 | 2018-10-05 | 2019-03-28 | 2018-11-05 | G | 2019-03-29 | 2018-11-06 | 2019-04-02 | 2019-03-01 | G | 2019-04-03 | 2019-03-04 | 2019-10-04 | 2019-03-11 | G | [25 empty] | 2019-03-12 | 2019-03-10 | 2019-11-08 | 2019-03-12 | G | [5 empty] | 2020-01-21 | 2019-03-07 | 2020-02-18 | 2019-03-20 | G | 2020-05-06 | 2019-03-20 | 2020-05-06 | 2019-03-21 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.063288
2205 | 114200 | INSTALL SIDEWALK - DEER RUN ROAD - CHESTERFIELD | 4700 | Secondary | Safety | Locally | Chesterfield County | CHESTERFIELD | Richmond | Richmond:Chesterfield County | Infrastructure Investment Division | Michael S Gray | Mike.Gray@vdot.virginia.gov | (804) 609-5347 | Michael S Gray | Mike.Gray@vdot.virginia.gov | (804) 609-5347 | Nathan Mathis | MathisN@chesterfield.gov | 7481037 | 0 |  | 0 | FY2025 | 700000 | 700000 | NO DATES SET YET-PE OPEN | G | Obtained Permits milestone finished 1007 days early | G | Project is on budget | 2022-02-07 | 2020-03-30 | 2022-05-02 | 2020-07-22 | G | 2022-05-03 | 2020-07-23 | 2022-05-05 | 2020-08-04 | G | 2022-05-06 |  | 2022-11-09 |  | G | [10 empty] | 2023-11-09 |  | 2023-12-04 |  | G | [5 empty] | 2023-12-06 |  | 2024-09-13 |  | G | 2022-12-20 | 2020-11-19 | 2023-08-23 | 2020-11-19 | G | [5 empty] | 2024-10-01 |  | 2024-10-29 |  | G | 2025-01-24 |  | 2025-01-24 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.18598
2206 | 115360 | Route 165 (Cedar Rd) Repaving, Segment 2 | 0165 | Urban | Resurfacing | Locally | Chesapeake | NORFOLK | Hampton Roads | Hampton Roads:Chesapeake | Local Assistance Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Johndel A Alcaide | John.Alcaide@vdot.virginia.gov | (757) 956-3098 | Sam Sawan | ssawan@cityofchesapeake.net | (757) 382-8263 | 0 |  | 0 | FY2020 | 360000 | 360000 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 33 days early | G | Project is on budget | 2019-08-01 | 2019-08-01 | 2019-10-25 | 2019-09-24 | G | [5 empty] | 2019-08-01 | 2019-08-01 | 2019-08-14 | 2019-08-14 | G | [35 empty] | 2020-05-18 | 2020-04-21 | 2020-06-15 | 2020-05-15 | G | 2020-06-30 | 2020-05-28 | 2020-06-30 | 2020-05-28 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.07468
2207 | 115884 | RTE 8069 HUBERT LANE | 8069 | Secondary | Reconstruction w/o Added Capacity | Locally | Chesterfield County | CHESTERFIELD | Richmond | Richmond:Chesterfield County | Infrastructure Investment Division | Rebecca J Worley | Rebecca.Worley@vdot.virginia.gov | (804) 674-2775 | Rebecca J Worley | Rebecca.Worley@vdot.virginia.gov | (804) 674-2775 | Stan Newcomb | newcombs@chesterfield.gov | (804) 717-6662 | 0 |  | 0 | FY2027 | 150000 | 150000 | NO DATES SET YET | G | Determine Requirements milestone is 1972 days ahead of the expected completion date | G | Project is on budget | 2026-07-06 |  | 2026-09-28 |  | G | [5 empty] | 2026-07-06 |  | 2026-07-17 |  | G | [25 empty] | 2026-07-20 |  | 2026-10-12 |  | G | [5 empty] | 2026-10-14 |  | 2026-11-12 |  | G | 2027-02-08 |  | 2027-02-08 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.26225
2208 | 116625 | NOVA SYSTEMIC HIGH VISIBILITY BACKPLATES PH3 | 9999 | Miscellaneous | Safety | VDOT | Northern Virginia District-wide |  | Northern Virginia | Northern Virginia:Northern Virginia District-wide | Infrastructure Investment/Asset Management Division | Waqar A Siddiqui | Sid.Siddiqui@VDOT.Virginia.gov | (703) 259-3225 | Tienjung Ho | Tien-Jung.Ho@VDOT.Virginia.gov | (703) 259-2752 |  |  |  | 0 |  | 0 | FY2021 | 3550867 | 3550867 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 80 days early | G | Project is on budget | [5 empty] | 2020-10-30 | 2020-05-06 | 2020-11-05 | 2020-05-06 | G | 2020-11-06 | 2020-05-18 | 2020-12-22 | 2020-07-23 | G | [5 empty] | 2020-07-23 | 2020-07-23 | 2020-07-23 | 2020-07-23 | G | [25 empty] | 2020-10-20 | 2020-08-17 | 2020-11-02 | 2020-08-20 | G | 2020-11-03 | 2020-08-20 | 2020-11-09 | 2020-08-21 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | WORK/TASK ORDER | 1 | 0 | 0.06738
2209 | 116844 | TULIP POPLAR DRIVE, PHASE I, RURAL ADDITION |  | Secondary | Reconstruction w/o Added Capacity | Locally | Warren County | EDINBURG | Staunton | NonMPO:NonMPO | Local Assistance Division | Kimberly Cameron | Kim.Cameron@vdot.virginia.gov | (540) 332-7886 | Kimberly Cameron | Kim.Cameron@vdot.virginia.gov | (540) 332-7886 | Bob Childress | rchildress@warrencountyva.net | (540) 636-4600 | 0 |  | 0 | FY2025 | 350000 | 350000 | NO DATES SET YET | G | Agreement with Locality milestone is 107 days ahead of the expected completion date | G | Project is on budget | 2021-02-01 |  | 2021-06-08 |  | G | 2021-06-09 |  | 2021-06-29 |  | G | 2021-07-29 |  | 2021-11-22 |  | G | [25 empty] | 2023-12-28 |  | 2024-05-29 |  | G | [5 empty] | 2024-07-26 |  | 2024-08-22 |  | G | 2024-11-13 |  | 2024-11-13 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.2051
2210 | 113374 | #SGR19VB - I195 over Acca Yard - Major Rehab - Fed Id 9880 | 0195 | Interstate | Bridge Rehab w/o Added Capacity | VDOT | Henrico County | ASHLAND | Richmond | Richmond:Henrico County | Infrastructure Investment/Asset Management Division | Noyan F Erermis | Noyan.Erermis@vdot.virginia.gov | (804) 819-9653 | Noyan F Erermis | Noyan.Erermis@vdot.virginia.gov | (804) 819-9653 | TBD |  |  | 0 |  | 0 | FY2025 | 22591445 | 22591445 | NO DATES SET YET-PE OPEN | G | Start Development milestone finished 1 days early | G | Project is on budget | [5 empty] | 2020-09-01 | 2020-09-01 | 2020-09-15 | 2020-09-14 | G | 2020-09-16 |  | 2021-08-13 |  | G | [5 empty] | 2022-07-20 |  | 2022-08-02 |  | G | 2023-10-03 |  | 2023-10-17 |  | G | 2024-03-18 |  | 2024-09-18 |  | G | 2023-11-01 |  | 2024-05-10 |  | G | 2023-09-26 |  | 2024-06-03 |  | G | [5 empty] | 2024-10-08 |  | 2024-10-08 |  | G | 2025-01-03 |  | 2025-01-03 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.13648
2211 | 113504 | #SGR19VB - RT 638 TURKEY RIDGE RD STRUCT 9007 OVER SOUTH RV | 0638 | Secondary | Bridge Replacement w/o Added Capacity | VDOT | Greene County | CHARLOTTESVILLE | Culpeper | NonMPO:NonMPO | Infrastructure Investment/Asset Management Division | Braden C Chapman | Braden.Chapman@VDOT.Virginia.gov | (540) 829-7421 | Brian A Arnold | Brian.Arnold@VDOT.Virginia.gov | (540) 829-7557 |  |  |  | 0 |  | 0 | FY2024 | 3280000 | 3280000 | ACTIVITY DATES SET | G | Engage Public milestone finished 306 days early | G | Project is on budget | [5 empty] | 2018-07-17 | 2018-06-19 | 2018-07-30 | 2018-06-25 | G | 2018-07-31 | 2019-07-08 | 2019-06-27 | 2020-10-28 | R | [5 empty] | 2021-10-06 | 2020-12-18 | 2021-10-20 | 2020-12-18 | G | 2022-10-10 |  | 2022-10-24 |  | G | 2023-03-24 |  | 2023-09-26 |  | G | 2022-11-08 |  | 2023-05-18 |  | G | 2022-10-03 |  | 2023-06-09 |  | G | [5 empty] | 2023-10-10 |  | 2023-10-10 |  | G | 2024-01-05 |  | 2024-01-05 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.080995
2212 | 113633 | Route 171 (Victory Blvd.) Right Turn Lane Extension | 0171 | Primary | Safety | VDOT | York County | WILLIAMSBURG | Hampton Roads | Hampton Roads:York County | Infrastructure Investment Division | John G Harman | JohnG.Harman@vdot.virginia.gov | (757) 956-3269 | John G Harman | JohnG.Harman@vdot.virginia.gov | (757) 956-3269 |  |  |  | 0 |  | 0 | FY2025 | 454936 | 454936 | NO DATES SET YET | G | Start Development milestone is 617 days ahead of the expected completion date | G | Project is on budget | [5 empty] | 2022-10-18 |  | 2022-10-31 |  | G | 2022-11-01 |  | 2023-06-27 |  | G | [5 empty] | 2024-03-07 |  | 2024-04-17 |  | G | [5 empty] | 2024-08-01 |  | 2024-11-25 |  | G | [5 empty] | 2024-07-17 |  | 2024-10-16 |  | G | [5 empty] | 2024-12-10 |  | 2024-12-10 |  | G | 2025-03-06 |  | 2025-03-06 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.10382
2213 | 113811 | Systemic Sight Distance - Traffic Signals | 9999 | Urban | Safety | Locally | Richmond | ASHLAND | Richmond | Richmond:Richmond | Local Assistance Division | Olena Fecek | Olena.Fecek@vdot.virginia.gov | (804) 524-6368 | Olena Fecek | Olena.Fecek@vdot.virginia.gov | (804) 524-6368 | Enrique Burgos | Enrique.Burgos@richmondgov.com | (804) 646-6337 | 0 |  | 0 | FY2022 | 1418061 | 1417888 | ACTIVITY DATES SET | R | Solicit Bids milestone is 52 days past the expected completion date | G | Project is on budget | 2019-09-03 | 2019-04-15 | 2019-11-27 | 2019-07-09 | G | 2019-12-02 | 2019-07-15 | 2019-12-04 | 2019-07-22 | G | 2019-12-05 | 2019-07-23 | 2020-06-11 | 2020-06-05 | G | [35 empty] | 2020-12-31 |  | 2020-12-31 |  | R | 2021-08-31 |  | 2021-08-31 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.17749
2214 | 113871 | ROUte 693 - PIKE ROAD - RURAL RUSTIC | 0693 | Secondary | Reconstruction w/o Added Capacity | VDOT | Bedford County | BEDFORD | Salem | NonMPO:NonMPO | Infrastructure Investment Division | Todd K Daniel | Todd.Daniel@VDOT.Virginia.gov | (540) 682-7000 | Clyde Spencer | Clyde.Spencer@vdot.virginia.gov | (540) 682-7011 |  |  |  | 0 |  | 0 | FY2029 | 650000 | 650000 | NO DATES SET YET | G | Start Development milestone is 1331 days ahead of the expected completion date | G | Project is on budget | [5 empty] | 2024-10-01 |  | 2024-10-14 |  | G | 2024-10-15 |  | 2025-09-12 |  | G | [5 empty] | 2026-07-21 |  | 2026-08-03 |  | G | 2027-11-08 |  | 2027-11-22 |  | G | 2028-04-20 |  | 2028-10-24 |  | G | 2027-12-10 |  | 2028-06-16 |  | G | 2027-04-28 |  | 2027-11-01 |  | G | [5 empty] | 2028-11-14 |  | 2028-11-14 |  | G | 2029-02-09 |  | 2029-02-09 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | SAAP CONTRACT | 0 | 0 | 0.18779
2215 | 114869 | RTE 712-SURFACE TREAT NON-HARDSURFACED ROADWAY | 0712 | Secondary | Resurfacing | VDOT | Floyd County | CHRISTIANSBURG | Salem | NonMPO:NonMPO | Infrastructure Investment Division | Christopher L Price | Christopher.Price@VDOT.Virginia.gov | (540) 381-7182 | Jason L Patrick | Jason.Patrick@vdot.virginia.gov | (540) 381-7178 |  |  |  | 0 |  | 0 | FY2026 | 714568 | 714568 | NO DATES SET YET | G | Start Development milestone is 51 days ahead of the expected completion date | G | Project is on budget | [5 empty] | 2021-03-31 |  | 2021-04-13 |  | G | 2021-04-14 |  | 2022-03-14 |  | G | [5 empty] | 2023-01-18 |  | 2023-01-31 |  | G | 2024-05-06 |  | 2024-05-17 |  | G | 2024-10-10 |  | 2025-04-22 |  | G | 2024-06-05 |  | 2024-12-11 |  | G | 2023-10-19 |  | 2024-04-29 |  | G | [5 empty] | 2025-05-13 |  | 2025-05-13 |  | G | 2025-08-04 |  | 2025-08-04 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | SAAP CONTRACT | 0 | 0 | 0.072208
2217 | 115887 | SYSTEMIC CURVE DELINEATION - DISTRICTWIDE | 9999 | Miscellaneous | Safety | VDOT | Richmond District-wide |  | Richmond | Richmond:Richmond District-wide | Infrastructure Investment/Asset Management Division | Adam S Brooks | Adam.Brooks@VDOT.Virginia.gov | (804) 609-5274 | Adam S Brooks | Adam.Brooks@VDOT.Virginia.gov | (804) 609-5274 | N\A |  |  | 0 |  | 0 | FY2024 | 3001870 | 3001872 | ACTIVITY DATES SET | G | Determine Requirements milestone finished on-time | Y | Project estimate is less than $5M and is up to 20% over budget | [5 empty] | 2019-11-01 | 2019-10-24 | 2019-11-15 | 2019-10-24 | G | 2019-11-18 | 2019-10-25 | 2020-11-17 | 2020-11-17 | G | [35 empty] | 2023-05-09 |  | 2023-05-09 |  | G | 2023-08-25 |  | 2023-08-25 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.061865
2218 | 116721 | NOVA SYSTEMIC PEDESTRIAN CROSSINGS PH1 | 9999 | Miscellaneous | Safety | VDOT | Northern Virginia District-wide |  | Northern Virginia | Northern Virginia:Northern Virginia District-wide | Infrastructure Investment/Asset Management Division | Waqar A Siddiqui | Sid.Siddiqui@VDOT.Virginia.gov | (703) 259-3225 | Tienjung Ho | Tien-Jung.Ho@VDOT.Virginia.gov | (703) 259-2752 |  |  |  | 0 |  | 0 | FY2023 | 2000000 | 2000000 | ACTIVITY DATES SET | G | Determine Requirements milestone finished 13 days early | G | Project is on budget | [5 empty] | 2020-10-30 | 2020-03-25 | 2020-10-30 | 2020-04-02 | G | 2020-11-02 | 2020-04-03 | 2021-02-16 | 2021-02-03 | G | [5 empty] | 2022-10-06 |  | 2022-10-20 |  | G | [25 empty] | 2022-12-21 |  | 2022-12-28 |  | G | 2022-12-29 |  | 2023-01-05 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | WORK/TASK ORDER | 0 | 0 | 0.066234
2219 | 117096 | #REVSH21 RTE 501 (WILBORN AVE) - DRAINAGE IMPROVEMENTS | 0501 | Urban | Other | Locally | South Boston | HALIFAX | Lynchburg | NonMPO:NonMPO | Local Assistance Division | Gregg Allen | Gregg.Allen@vdot.virginia.gov | (434) 426-5575 | Gregg Allen | Gregg.Allen@vdot.virginia.gov | (434) 426-5575 | CW CROWDER | ccrowder@southbostonva.us | (434) 575-4261 | 0 |  | 0 | FY2025 | 730800 | 730800 | NO DATES SET YET | G | Agreement with Locality milestone is 106 days ahead of the expected completion date | G | Project is on budget | 2021-01-29 |  | 2021-06-07 |  | G | 2021-06-08 |  | 2021-06-28 |  | G | 2022-01-07 |  | 2022-05-03 |  | G | [10 empty] | 2023-08-22 |  | 2023-09-26 |  | G | [5 empty] | 2023-09-27 |  | 2024-03-04 |  | G | 2024-01-30 |  | 2024-06-26 |  | G | [5 empty] | 2024-06-05 |  | 2024-07-02 |  | G | 2024-09-20 |  | 2024-09-20 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.096114
2220 | 117159 | #SGR21LP City of Suffolk 1906 Franklin Bypass | 0058 | Urban | Resurfacing | Locally | Suffolk | NORFOLK | Hampton Roads | Hampton Roads:Suffolk | Infrastructure Investment/Asset Management Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Johndel A Alcaide | John.Alcaide@vdot.virginia.gov | (757) 956-3098 | Edward Heide | eheide@suffolkva.us | (757) 514-7615 | 0 |  | 1 | FY2022 | 333028 | 333028 | NO DATES SET YET | G | Agreement with Locality milestone is 80 days ahead of the expected completion date | G | Project is on budget | 2021-01-04 |  | 2021-05-12 |  | G | 2021-05-13 |  | 2021-06-03 |  | G | 2021-07-02 |  | 2021-08-04 |  | G | [25 empty] | 2021-07-08 |  | 2021-08-04 |  | G | [5 empty] | 2021-10-01 |  | 2021-10-29 |  | G | 2022-01-26 |  | 2022-01-26 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.06803
2221 | 118234 | SAGER AVENUE SIDEWALK |  | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Fairfax | FAIRFAX | Northern Virginia | Northern Virginia:Fairfax | Local Assistance Division | Amir Salahshoor | A.Salahshoor@VDOT.Virginia.gov | (703) 259-1957 | Marlene Pinedo Fortich | Sofia.Pinedo@vdot.virginia.gov | (703) 259-1724 | Wendy Sanford | wendy.sanford@fairfaxva.gov | (703) 385-7889 | 0 |  | 0 | FY2025 | 530000 | 530000 | NO DATES SET YET | G | Agreement with Locality milestone is 107 days ahead of the expected completion date | G | Project is on budget | 2021-02-01 |  | 2021-06-08 |  | G | 2021-06-09 |  | 2021-06-29 |  | G | 2021-07-29 |  | 2021-11-22 |  | G | [10 empty] | 2023-03-20 |  | 2023-04-21 |  | G | [5 empty] | 2023-04-24 |  | 2023-10-11 |  | G | 2023-09-14 |  | 2024-02-20 |  | G | [5 empty] | 2024-01-23 |  | 2024-05-14 |  | G | 2024-08-02 |  | 2024-11-26 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.33334
2222 | 80488 | RTE 42 - IMPROVE RTE. 42 (MAIN STREET) IN BRIDGEWATER | 0042 | Urban | Safety | Locally | Bridgewater | HARRISONBURG | Staunton | Harrisonburg:Bridgewater | Infrastructure Investment Division | Jerry VanLear |  |  | Michael S Fulcher | Michael.Fulcher@VDOT.Virginia.gov | (540) 332-2243 | Ken Flick |  |  | 0 |  | 0 | FY2021 | 2119526 | 2119526 | ACTIVITY DATES SET | Y | Solicit Bids milestone is 2 days ahead of the expected completion date and there is a risk of missing this milestone date | G | Project is on budget | [5 empty] | 2007-02-01 | 2006-12-13 | 2007-02-28 | 2006-12-13 | G | 2015-03-31 | 2015-03-31 | 2019-03-29 | 2019-03-28 | G | [10 empty] | 2018-04-27 | 2018-04-27 | 2019-03-08 | 2019-03-07 | G | [20 empty] | 2020-12-23 |  | 2021-02-23 |  | Y | 2021-02-24 |  | 2021-06-30 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.1014
2223 | 107275 | Corporate Park Drive Extension | 0930 | Secondary | New Construction Roadway | Locally | Bedford County | BEDFORD | Salem | Lynchburg:Bedford County | Local Assistance Division | James M Guy | james.guy@vdot.virginia.gov | (540) 387-5247 | Adam J Czesnowski | Adam.Czesnowski@vdot.virginia.gov | (540) 541-1216 | Kevin Leamy | k.leamy@bedfordcountyva.gov | (540) 586-7616 | 0 |  | 0 | FY2019 | 2194685 | 2194685 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 1 days early | G | Project is on budget | 2015-08-18 | 2015-08-18 | 2015-08-18 | 2015-08-18 | G | 2015-08-18 | 2015-08-18 | 2015-08-19 | 2015-08-19 | G | 2016-03-22 | 2016-03-22 | 2018-02-15 | 2018-02-02 | G | [10 empty] | 2018-04-09 | 2018-02-22 | 2018-04-20 | 2018-02-22 | G | [20 empty] | 2018-07-16 | 2018-11-12 | 2018-07-16 | 2018-12-02 | R | 2018-07-17 | 2018-12-03 | 2019-01-17 | 2019-01-16 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.25123
2224 | 108493 | ROUTE 50 EASTBOUND SIDEWALK FROM SOUTH STREET TO ASPEN LANE | 0050 | Primary | Safety | Locally | Fairfax County | FAIRFAX | Northern Virginia | Northern Virginia:Fairfax County | Infrastructure Investment Division | Amir Salahshoor | A.Salahshoor@VDOT.Virginia.gov | (703) 259-1957 | Rita Hockman | Rita.Hockman@vdot.virginia.gov | (804) 824-7421 | Bijan (Ben) Samiyi | Bijan.Samiyi@fairfaxcounty.gov | (703) 324-1892 | 0 |  | 0 | FY2021 | 850001 | 1022510 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 773 days early | Y | Project estimate is less than $5M and is up to 20% over budget | 2014-12-30 | 2014-12-30 | 2015-03-27 | 2015-03-27 | G | 2015-03-30 | 2015-04-01 | 2015-04-01 | 2015-04-01 | G | 2015-04-02 | 2015-04-01 | 2015-10-05 | 2015-04-02 | G | [10 empty] | 2016-08-01 | 2016-08-01 | 2016-08-05 | 2016-08-05 | G | [5 empty] | 2016-10-31 | 2016-10-31 | 2017-06-14 | 2017-06-14 | G | [10 empty] | 2019-12-04 | 2018-05-30 | 2020-06-30 | 2018-08-31 | G | 2020-07-01 | 2018-09-04 | 2020-11-30 | 2018-10-19 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.07657
2225 | 109325 | #HB2.FY17 Int. Route 11 S. Rte. 652 Right Turn Lane | 0011 | Primary | Reconstruction w/ Added Capacity | VDOT | Frederick County | EDINBURG | Staunton | Winchester:Frederick County | Infrastructure Investment Division | Ronald L Tabor | Ronald.Tabor@vdot.virginia.gov | (540) 332-7887 | Alfred Scott | [5 empty] | 1 | 2017 | 0 | FY2018 | 514704 | 583463 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 27 days early | Y | Project estimate is less than $5M and is up to 20% over budget | [5 empty] | 2016-09-16 | 2016-09-16 | 2016-09-16 | 2016-09-16 | G | 2016-09-14 | 2016-09-14 | 2017-08-17 | 2017-06-06 | G | [5 empty] | 2017-07-27 | 2017-07-24 | 2017-07-27 | 2017-07-24 | G | 2017-12-18 | 2017-11-13 | 2017-12-18 | 2017-11-13 | G | 2017-10-19 | 2017-10-19 | 2017-10-19 | 2017-10-19 | G | 2017-12-19 | 2017-11-14 | 2017-12-19 | 2017-11-14 | G | [10 empty] | 2018-03-13 | 2018-03-13 | 2018-03-13 | 2018-03-13 | G | 2018-04-26 | 2018-05-25 | 2018-06-21 | 2018-05-25 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.069779
2226 | 110873 | Euclid Ave. - Install Mast Arms and Pedestrian Signal Heads | 0011 | Urban | Safety | Locally | Bristol | ABINGDON | Bristol | Bristol:Bristol | Infrastructure Investment Division | John W Bechtold | John.Bechtold@vdot.virginia.gov | (276) 696-3365 | Kenneth R Plummer | KR.Plummer@VDOT.Virginia.gov | (276) 696-3261 | Wallace McCulloch | wallace.mcculloch@bristolva.org | (276) 642-2315 | 0 |  | 0 | FY2022 | 426198 | 426198 | ACTIVITY DATES SET | G | Determine Requirements milestone finished 13 days early | G | Project is on budget | 2017-10-24 | 2018-01-08 | 2019-10-07 | 2018-01-24 | G | 2018-05-21 | 2018-06-06 | 2018-06-15 | 2018-06-13 | G | 2018-06-18 | 2018-06-14 | 2020-04-22 | 2020-04-09 | G | [35 empty] | 2021-04-28 |  | 2021-05-25 |  | G | 2021-05-26 |  | 2021-07-07 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.098964
2227 | 111165 | ADA TRANSIT STOP IMPROVEMENTS |  | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Richmond | ASHLAND | Richmond | Richmond:Richmond | Local Assistance Division | Jorg Huckabee-Mayfield | Jorg.Huckabee-Mayfield@VDOT.Virginia.gov | (804) 609-5292 | Jorg Huckabee-Mayfield | Jorg.Huckabee-Mayfield@VDOT.Virginia.gov | (804) 609-5292 | Adrienne Tores | adriennetores@ridegrtc.com | (804) 474-9798 | 0 |  | 0 | FY2020 | 141675 | 139891 | AWARDED | R | Start Delivery milestone finished 406 days late | G | Project is on budget | 2017-10-02 | 2017-12-21 | 2017-12-29 | 2018-07-26 | R | 2018-01-02 | 2018-07-11 | 2018-01-04 | 2018-07-20 | R | 2018-01-05 | 2018-07-24 | 2018-07-12 | 2018-12-20 | R | [35 empty] | 2019-05-15 | 2019-05-15 | 2019-06-12 | 2019-09-02 | R | 2019-06-13 | 2019-09-03 | 2019-12-12 | 2021-01-21 | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.35104
2228 | 111430 | Pedestrian Improvements - Cityof Galax | 9999 | Urban | Facilities for Pedestrians and Bicycles | Locally | Galax | MARTINSVILLE | Salem | NonMPO:NonMPO | Infrastructure Investment Division | Jessie Nester | Jessie.Nester@vdot.virginia.gov | (540) 613-4115 | Jessie Nester | Jessie.Nester@vdot.virginia.gov | (540) 613-4115 | Edwin Ward |  |  | 0 |  | 0 | FY2021 | 395052 | 394933 | ADVERTISED | R | Start Delivery milestone is 174 days past the expected completion date | G | Project is on budget | 2017-07-03 | 2017-07-03 | 2017-10-19 | 2017-10-19 | G | 2017-09-25 | 2017-09-25 | 2017-09-25 | 2017-09-25 | G | 2017-09-26 | 2018-02-06 | 2018-11-01 | 2018-08-20 | G | [10 empty] | 2019-07-15 | 2019-05-16 | 2019-08-02 | 2019-05-17 | G | [5 empty] | 2019-08-06 | 2019-05-22 | 2020-02-26 | 2019-07-11 | G | [10 empty] | 2020-03-13 | 2020-01-31 | 2020-04-09 | 2020-03-09 | G | 2020-04-10 |  | 2020-08-31 |  | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.11743
2229 | 112181 | Angle Bridge Reconstruction - North Main Street | 0000 | Urban | Bridge Rehab w/o Added Capacity | Locally | Rocky Mount | BEDFORD | Salem | NonMPO:NonMPO | Infrastructure Investment Division | Jessie Nester | Jessie.Nester@vdot.virginia.gov | (540) 613-4115 | Jessie Nester | Jessie.Nester@vdot.virginia.gov | (540) 613-4115 | Jessica Heckman | jheckman@rockymountva.org | (540) 483-0907 | 0 |  | 0 | FY2020 | 877695 | 1271261 | CONSTRUCTION STARTED | R | Start Delivery milestone finished 20 days late | R | Project estimate is less than $5M and is 20% or more over budget | 2018-04-02 | 2018-04-02 | 2018-10-03 | 2018-05-07 | G | 2018-10-04 | 2018-07-24 | 2018-10-08 | 2018-07-26 | G | 2018-10-09 | 2018-07-27 | 2019-10-09 | 2018-10-30 | G | [35 empty] | 2019-10-04 | 2020-02-28 | 2019-11-18 | 2020-04-15 | R | 2019-11-19 | 2020-05-20 | 2020-05-19 | 2020-06-08 | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.37863
2230 | 117331 | RESURFACE NON-HARDSURFACED ROADWAY-ROUTE 680 | 0680 | Secondary | Resurfacing | VDOT | Floyd County | CHRISTIANSBURG | Salem | NonMPO:NonMPO | Infrastructure Investment Division | David D Clarke | David.Clarke@VDOT.Virginia.gov | (540) 381-7190 | Christopher L Price | Christopher.Price@VDOT.Virginia.gov | (540) 381-7182 |  |  |  | 0 |  | 0 | FY2026 | 669286 | 669286 | NO DATES SET YET | G | Start Development milestone is 823 days ahead of the expected completion date | G | Project is on budget | [5 empty] | 2023-05-05 |  | 2023-05-25 |  | G | 2023-05-26 |  | 2024-04-01 |  | G | [5 empty] | 2024-10-28 |  | 2024-11-25 |  | G | [5 empty] | 2025-07-22 |  | 2025-11-20 |  | G | [5 empty] | 2025-04-14 |  | 2025-09-10 |  | G | [5 empty] | 2025-12-09 |  | 2025-12-09 |  | G | 2026-03-04 |  | 2026-03-04 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | SAAP CONTRACT | 0 | 0 | 0.072161
2231 | 118294 | Wasena Bridge (Main Street - SR 221) Bridge Replacement | 0000 | Urban | Bridge Replacement w/ Added Capacity | Locally | Roanoke | SALEM | Salem | Roanoke:Roanoke City | Local Assistance Division | Cheryl B Becker | Cheryl.Becker@vdot.virginia.gov | (540) 492-2531 | Cheryl B Becker | Cheryl.Becker@vdot.virginia.gov | (540) 492-2531 | Luke Pugh | luke.pugh@roanokeva.gov | (540) 853-5208 | 0 |  | 0 | FY2028 | 8790000 | 8790000 | NO DATES SET YET | G | Agreement with Locality milestone is 1422 days ahead of the expected completion date | G | Project is on budget | 2024-08-30 |  | 2025-01-13 |  | G | 2025-01-14 |  | 2025-02-05 |  | G | 2025-08-12 |  | 2025-12-08 |  | G | [25 empty] | 2026-12-03 |  | 2027-05-05 |  | G | [5 empty] | 2027-07-02 |  | 2027-07-30 |  | G | 2027-10-20 |  | 2027-10-20 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.20992
2232 | 99194 | Branders Bridge Road and Route 1 - intersection improvement | 9026 | Urban | Resurfacing | Locally | Colonial Heights | CHESTERFIELD | Richmond | Tri-Cities:Colonial Heights | Infrastructure Investment Division | Evan Austin | Evan.Austin@vdot.virginia.gov | (804) 609-5384 | Evan Austin | Evan.Austin@vdot.virginia.gov | (804) 609-5384 | Keith A Chisolm | chisolmk@colonialheightsva.gov | (804) 641-9106 | 0 |  | 0 | FY2023 | 629328 | 629328 | NO DATES SET YET-PE OPEN | G | Start Development milestone finished 49 days early | G | Project is on budget | 2020-07-01 | 2020-04-29 | 2020-09-24 | 2020-07-29 | G | 2020-09-25 | 2020-08-05 | 2020-09-29 | 2020-08-11 | G | 2020-09-30 |  | 2021-04-12 |  | G | [10 empty] | 2022-04-14 |  | 2022-05-04 |  | G | [5 empty] | 2022-05-06 |  | 2023-02-17 |  | G | 2021-05-18 |  | 2022-01-25 |  | G | [5 empty] | 2023-03-08 |  | 2023-04-04 |  | G | 2023-06-22 |  | 2023-06-22 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.10107
2233 | 107852 | Rte. 634 over Lower Chippokes Ck (VA. Str. No. 6075) | 0634 | Secondary | Bridge Replacement w/o Added Capacity | VDOT | Surry County | WILLIAMSBURG | Hampton Roads | Hampton Roads:Surry County | Asset Management Division | Mohamed A Ali | Mohamed.Ali@VDOT.Virginia.gov | (757) 956-3206 | Miranda S Kidd | miranda.kidd@vdot.virginia.gov | (757) 956-3342 |  |  |  | 0 |  | 0 | FY2020 | 1115584 | 1352300 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 89 days early | Y | Project estimate is less than $5M and is up to 20% over budget | [5 empty] | 2015-07-31 | 2015-09-17 | 2015-08-13 | 2015-09-22 | R | 2015-07-31 | 2015-09-23 | 2016-06-28 | 2016-08-19 | R | [5 empty] | 2017-08-30 | 2017-08-30 | 2017-09-13 | 2017-09-13 | G | 2018-10-02 | 2017-07-05 | 2018-10-16 | 2017-07-19 | G | 2019-03-18 | 2017-05-25 | 2019-09-18 | 2017-05-25 | G | 2018-10-31 | 2017-07-24 | 2019-05-10 | 2018-03-23 | G | 2018-06-08 | 2018-02-01 | 2019-06-10 | 2018-11-01 | G | [5 empty] | 2019-10-08 | 2019-07-09 | 2019-10-08 | 2019-07-09 | G | 2019-12-03 | 2019-09-25 | 2019-12-23 | 2019-09-25 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.096831
2234 | 108495 | ROUTE 50 SIDEWALK FROM CHERRY STREET TO LINDEN LANE (NORTH) | 0050 | Primary | Safety | Locally | Fairfax County | FAIRFAX | Northern Virginia | Northern Virginia:Fairfax County | Infrastructure Investment Division | Amir Salahshoor | A.Salahshoor@VDOT.Virginia.gov | (703) 259-1957 | Rita Hockman | Rita.Hockman@vdot.virginia.gov | (804) 824-7421 | Fasika Metafria | Fasika.Metafria@fairfaxcounty.gov | (703) 324-5085 | 0 |  | 0 | FY2020 | 450001 | 543470 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 472 days early | Y | Project estimate is less than $5M and is up to 20% over budget | 2014-12-30 | 2014-12-30 | 2015-03-27 | 2015-03-31 | R | 2015-03-30 | 2015-04-01 | 2015-04-01 | 2015-04-01 | G | 2015-04-02 | 2015-07-24 | 2015-10-05 | 2015-10-05 | G | [10 empty] | 2016-08-08 | 2016-08-08 | 2016-08-19 | 2016-08-19 | G | [5 empty] | 2016-08-23 | 2016-08-23 | 2019-11-13 | 2017-06-15 | G | [10 empty] | 2019-12-04 | 2018-06-05 | 2020-01-02 | 2018-09-06 | G | 2020-01-03 | 2018-09-07 | 2020-02-14 | 2018-10-30 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.076006
2235 | 109468 | #HB2.FY17 -- PEDESTRIAN IMPROVEMENTS ON RTE 17 SB | 0017 | Primary | Facilities for Pedestrians and Bicycles | VDOT | Gloucester County | SALUDA | Fredericksburg | Hampton Roads:Gloucester County | Infrastructure Investment Division | Wesley Foor | Wesley.Foor@vdot.virginia.gov | (540) 604-1370 | Wesley Foor | Wesley.Foor@vdot.virginia.gov | (540) 604-1370 |  |  |  | 1 | 2017 | 0 | FY2021 | 800000 | 800000 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 21 days early | G | Project is on budget | [5 empty] | 2017-03-14 | 2017-03-14 | 2017-03-27 | 2017-03-14 | G | 2017-03-28 | 2017-03-14 | 2018-01-16 | 2017-12-21 | G | [5 empty] | 2018-06-18 | 2018-06-02 | 2018-06-29 | 2018-06-15 | G | 2018-12-14 | 2018-10-08 | 2018-12-28 | 2018-10-22 | G | 2019-07-17 | 2019-06-06 | 2020-01-16 | 2019-06-06 | G | 2019-01-16 | 2018-12-17 | 2019-07-16 | 2019-06-04 | G | 2018-09-14 | 2018-09-14 | 2019-07-05 | 2018-09-14 | G | [5 empty] | 2020-02-11 | 2020-02-11 | 2020-02-11 | 2020-02-11 | G | 2020-05-14 | 2020-05-07 | 2020-07-10 | 2020-06-19 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.082449
2236 | 110987 | #SMART18 - RTE 208/HOOD DRIVE INTERSECTION IMPROVEMENT | 0636 | Secondary | Safety | VDOT | Spotsylvania County | FREDERICKSBURG | Fredericksburg | Fredericksburg:Spotsylvania County | Infrastructure Investment Division | Catherine C Coffey | Catherine.Coffey@vdot.virginia.gov | (540) 899-4280 | Anastasia Kapitan | Anastasia.Kapitan@vdot.virginia.gov | (540) 899-4292 |  |  |  | 1 | 2018 | 0 | FY2024 | 5150000 | 6301485 | ACTIVITY DATES SET | G | Engage Public milestone finished on-time | R | Project estimate is between $5M and $10M and is a $1M or more over budget | [5 empty] | 2019-07-19 | 2019-07-01 | 2019-08-01 | 2019-08-05 | R | 2019-08-02 | 2019-08-02 | 2020-04-23 | 2020-04-23 | G | [5 empty] | 2020-09-02 | 2020-09-02 | 2020-10-20 | 2020-10-20 | G | 2021-05-07 |  | 2021-05-20 |  | G | 2021-12-14 |  | 2022-11-04 |  | G | 2021-06-08 |  | 2022-06-07 |  | G | 2021-02-25 |  | 2021-08-27 |  | G | [5 empty] | 2023-02-14 |  | 2023-02-14 |  | G | 2023-05-18 |  | 2023-07-14 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.072649
2237 | 111402 | W&OD TRAIL CROSSING IMPROVEMENTS |  | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Falls Church | FAIRFAX | Northern Virginia | Northern Virginia:Falls Church | Local Assistance Division | Amir Salahshoor | A.Salahshoor@VDOT.Virginia.gov | (703) 259-1957 | Saif-Ur Qargha | Saif.Qargha@vdot.virginia.gov | (703) 259-3223 | Jeffrey Sikes | jsikes@fallschurchva.gov | (703) 248-5296 | 0 |  | 0 | FY2022 | 622000 | 1525407 | ACTIVITY DATES SET | Y | Solicit Bids milestone is 38 days ahead of the expected completion date and there is a risk of missing this milestone date | R | Project estimate is less than $5M and is 20% or more over budget | 2017-10-02 | 2017-10-02 | 2017-11-13 | 2017-11-13 | G | 2017-11-14 | 2017-11-14 | 2017-11-20 | 2017-11-20 | G | 2017-11-21 | 2017-11-21 | 2018-12-31 | 2018-12-31 | G | [10 empty] | 2019-10-23 | 2019-10-23 | 2019-11-27 | 2019-10-23 | G | [5 empty] | 2019-12-03 | 2019-11-15 | 2020-09-30 | 2019-11-15 | G | [10 empty] | 2020-10-16 |  | 2021-03-31 |  | Y | 2021-04-01 |  | 2021-08-31 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.49045
2238 | 111435 | #SGR18LB - BRIDGE REPLACEMENT CAMPGROUND RD. - (29803 Fed) | 0000 | Miscellaneous | Bridge Replacement w/o Added Capacity | Locally | Buchanan County | LEBANON | Bristol | NonMPO:NonMPO | Infrastructure Investment Division | Tabitha H Crowder | Tabitha.Crowder@vdot.virginia.gov | (276) 696-3482 | Roger L Musser | Roger.Musser@VDOT.Virginia.gov | (276) 696-3260 | Marcus Stiltner | marcus.stiltner@buchanancounty-va.gov | (276) 935-4013 | 0 |  | 1 | FY2021 | 290000 | 290000 | CONSTRUCTION STARTED | G | Start Delivery milestone finished on-time | G | Project is on budget | 2018-05-10 | 2018-02-01 | 2018-08-03 | 2018-04-02 | G | 2018-08-06 | 2018-04-03 | 2018-08-08 | 2018-04-05 | G | 2018-08-09 | 2018-04-06 | 2019-02-20 | 2019-02-19 | G | [35 empty] | 2020-01-14 | 2020-01-14 | 2020-04-09 | 2020-04-07 | G | 2020-04-10 | 2020-04-10 | 2020-07-06 | 2020-07-06 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.043628
2239 | 112899 | ROUTE 7 - WIDEN SHOULDERS AND INSTALL RUMBLE STRIPS | 0007 | Primary | Safety | VDOT | Clarke County | EDINBURG | Staunton | NonMPO:NonMPO | Infrastructure Investment Division | Keith M Rider | Keith.Rider@VDOT.Virginia.gov | (434) 856-8145 | Kunal Kothawade | Kunal.Kothawade@vdot.virginia.gov | (540) 332-9259 |  |  |  | 0 |  | 0 | FY2023 | 1177000 | 1177000 | NO DATES SET YET | R | Start Development milestone is 100 days past the expected completion date | G | Project is on budget | [5 empty] | 2020-10-30 |  | 2020-11-13 |  | R | 2020-11-16 |  | 2021-07-12 |  | G | [5 empty] | 2022-03-22 |  | 2022-05-02 |  | G | [5 empty] | 2022-08-16 |  | 2022-12-12 |  | G | [5 empty] | 2022-08-01 |  | 2022-11-01 |  | G | [5 empty] | 2022-12-13 |  | 2022-12-13 |  | G | 2023-03-09 |  | 2023-03-09 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.061828
2240 | 113324 | Installation of Pedestrian Countdown Signal | 0000 | Urban | Safety | Locally | Roanoke | SALEM | Salem | Roanoke:Roanoke City | Local Assistance Division | Cheryl B Becker | Cheryl.Becker@vdot.virginia.gov | (540) 492-2531 | Cheryl B Becker | Cheryl.Becker@vdot.virginia.gov | (540) 492-2531 | Hong Liu | hong.liu@roanokeva.gov | (540) 853-2686 | 0 |  | 0 | FY2023 | 101984 | 101984 | NO DATES SET YET | R | Start Development milestone is 47 days past the expected completion date | G | Project is on budget | 2020-10-01 | 2020-10-01 | 2020-12-30 | 2020-12-29 | G | 2020-12-31 |  | 2021-01-05 |  | R | 2021-01-06 |  | 2021-08-02 |  | G | [25 empty] | 2021-11-30 |  | 2022-08-03 |  | G | [5 empty] | 2022-08-19 |  | 2022-09-16 |  | G | 2023-02-16 |  | 2023-02-16 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.21572
2241 | 113751 | Lake Taylor Sidewalk Improvements | 0165 | Urban | Facilities for Pedestrians and Bicycles | Locally | Norfolk | NORFOLK | Hampton Roads | Hampton Roads:Norfolk | Infrastructure Investment Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Derrick Williams | Derrick.Williams@vdot.virginia.gov | (757) 956-3097 | Robert Brown, P.E. | rob.brown@norfolk.gov | (757) 664-7305 | 0 |  | 0 | FY2024 | 610300 | 610300 | NO DATES SET YET | G | Agreement with Locality milestone is 283 days ahead of the expected completion date | Y | Estimate not current | 2021-09-02 |  | 2021-12-01 |  | G | 2021-12-02 |  | 2021-12-06 |  | G | 2021-12-07 |  | 2022-06-14 |  | G | [25 empty] | 2022-07-21 |  | 2023-03-29 |  | G | [5 empty] | 2023-04-26 |  | 2023-05-23 |  | G | 2023-08-11 |  | 2023-08-11 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.23169
2242 | 113998 | SYSTEMIC PEDESTRIAN CROSSING ACCOMMODATIONS - DISTRICTWIDE | 9999 | Miscellaneous | Safety | VDOT | Richmond District-wide |  | Richmond | Richmond:Richmond District-wide | Infrastructure Investment Division | Adam S Brooks | Adam.Brooks@VDOT.Virginia.gov | (804) 609-5274 | Adam S Brooks | Adam.Brooks@VDOT.Virginia.gov | (804) 609-5274 |  |  |  | 0 |  | 0 | FY2027 | 684000 | 684000 | NO DATES SET YET | G | Start Development milestone is 661 days ahead of the expected completion date | Y | Estimate not current | [5 empty] | 2022-12-01 |  | 2022-12-14 |  | G | 2022-12-15 |  | 2023-11-09 |  | G | [5 empty] | 2024-09-16 |  | 2024-09-27 |  | G | 2026-01-08 |  | 2026-01-23 |  | G | 2026-06-17 |  | 2026-12-23 |  | G | 2026-02-10 |  | 2026-08-13 |  | G | 2025-06-24 |  | 2025-12-31 |  | G | [5 empty] | 2027-01-12 |  | 2027-01-12 |  | G | 2027-04-06 |  | 2027-04-06 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.067794
2243 | 115242 | #SMART20 Hampton Roads Center Pkwy Bike & Pedestrian Access | 0000 | Urban | Facilities for Pedestrians and Bicycles | Locally | Hampton | WILLIAMSBURG | Hampton Roads | Hampton Roads:Hampton | Infrastructure Investment Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Derrick Williams | Derrick.Williams@vdot.virginia.gov | (757) 956-3097 | Lynne M. Keenan | lynne.keenan@hampton.gov | (757) 727-6859 | 1 | 2020 | 0 | FY2027 | 2163325 | 2163325 | NO DATES SET YET | G | Agreement with Locality milestone is 978 days ahead of the expected completion date | Y | Estimate not current | 2023-08-03 |  | 2023-10-27 |  | G | 2023-10-30 |  | 2023-11-13 |  | G | 2023-11-14 |  | 2024-10-29 |  | G | [10 empty] | 2025-10-31 |  | 2025-11-21 |  | G | [5 empty] | 2025-11-25 |  | 2026-10-08 |  | G | 2024-06-28 |  | 2025-03-07 |  | G | [5 empty] | 2026-10-27 |  | 2026-11-24 |  | G | 2027-02-19 |  | 2027-02-19 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 |  | 0 | 1 | 0.22698
2244 | 115708 | HERNDON MAINTENANCE RS - MILL AND OVERLAY | 9999 | Urban | Resurfacing | Locally | Herndon | FAIRFAX | Northern Virginia | Northern Virginia:Herndon | Local Assistance Division | Amir Salahshoor | A.Salahshoor@VDOT.Virginia.gov | (703) 259-1957 | Rita Hockman | Rita.Hockman@vdot.virginia.gov | (804) 824-7421 | John Irish | john.irish@herndon-va.gov | (703) 435-6800 | 0 |  | 0 | FY2021 |  |  | CONSTRUCTION COMPLETED | G | Determine Requirements milestone finished 166 days early | R | Critical information missing | 2019-11-01 | 2019-08-01 | 2020-05-29 | 2019-09-09 | G | [5 empty] | 2020-06-01 | 2020-04-17 | 2020-09-30 | 2020-04-17 | G | [35 empty] | 2020-07-02 | 2019-05-09 | 2020-09-14 | 2019-05-10 | G | 2020-12-07 | 2019-05-13 | 2021-02-15 | 2019-05-14 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.1737
2245 | 116624 | NOVA SYSTEMIC HIGH VISIBILITY BACKPLATES PH2 | 9999 | Miscellaneous | Safety | VDOT | Northern Virginia District-wide |  | Northern Virginia | Northern Virginia:Northern Virginia District-wide | Infrastructure Investment/Asset Management Division | Waqar A Siddiqui | Sid.Siddiqui@VDOT.Virginia.gov | (703) 259-3225 | Tienjung Ho | Tien-Jung.Ho@VDOT.Virginia.gov | (703) 259-2752 |  |  |  | 0 |  | 0 | FY2021 | 3600000 | 3600000 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 55 days early | G | Project is on budget | [5 empty] | 2020-10-30 | 2020-02-26 | 2020-11-05 | 2020-03-03 | G | 2020-11-06 | 2020-03-04 | 2020-12-22 | 2020-07-17 | G | [5 empty] | 2020-07-17 | 2020-07-17 | 2020-07-17 | 2020-07-17 | G | [25 empty] | 2020-09-18 | 2020-08-05 | 2020-09-29 | 2020-08-07 | G | 2020-09-30 | 2020-08-07 | 2020-10-01 | 2020-08-07 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | WORK/TASK ORDER | 1 | 0 | 0.067418
2246 | 116964 | #SGR21LP ROUTE 340 PRIMARY EXTENSION PAVING |  | Primary | Resurfacing | VDOT | Luray | HARRISONBURG | Staunton | NonMPO:NonMPO | Infrastructure Investment Division | Joel D Denunzio | Joel.DeNunzio@VDOT.virginia.gov | (540) 332-9093 | Mark W Hisey | Mark.Hisey@VDOT.Virginia.gov | (540) 280-4820 |  |  |  | 0 |  | 1 | FY2021 | 48521 | 48521 | ACTIVITY DATES SET | Y | Solicit Bids milestone is 51 days ahead of the expected completion date and there is a risk of missing this milestone date | G | Project is on budget | [5 empty] | 2021-01-11 | 2020-11-03 | 2021-02-02 | 2020-11-24 | G | 2021-02-03 | 2020-11-25 | 2021-12-03 | 2021-01-11 | G | [5 empty] | 2021-01-12 | 2021-01-12 | 2021-01-12 | 2021-01-12 | G | [5 empty] | 2020-12-28 | 2021-01-14 | 2021-04-12 | 2021-01-19 | G | [15 empty] | 2021-04-13 |  | 2021-04-13 |  | Y | 2021-06-30 |  | 2021-06-30 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.060459
2247 | 117899 | VCR TRAIL - TAP |  | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Spotsylvania County | FREDERICKSBURG | Fredericksburg | Fredericksburg:Spotsylvania County | Local Assistance Division | Catherine C Coffey | Catherine.Coffey@vdot.virginia.gov | (540) 899-4280 | Khalil Minhas | Khalil.Minhas@vdot.virginia.gov | (540) 374-3369 | Paul Agnello | pagnello@spotsylvania.va.us | (540) 507-7398 | 0 |  | 0 | FY2024 | 313286 | 313286 | NO DATES SET YET | G | Agreement with Locality milestone is 80 days ahead of the expected completion date | G | Project is on budget | 2021-01-04 |  | 2021-05-12 |  | G | 2021-05-13 |  | 2021-06-03 |  | G | 2021-12-13 |  | 2022-04-08 |  | G | [25 empty] | 2023-04-05 |  | 2023-08-31 |  | G | [5 empty] | 2023-10-31 |  | 2023-11-30 |  | G | 2024-02-23 |  | 2024-02-23 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.29829
2248 | 118494 | BIKESHARE EXPANSION - FAIRFAX COUNTY | 9999 | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Fairfax County | FAIRFAX | Northern Virginia | Northern Virginia:Fairfax County | Local Assistance Division | Andrew G Beacher | Andrew.Beacher@vdot.virginia.gov | (703) 259-2239 | Rhoderick M Undan | Rhoderick.Undan@vdot.virginia.gov | (703) 259-3347 | Nicole Wynands | nicole.wynands@fairfaxcounty.gov | (703) 877-5625 | 0 |  | 0 | FY2025 | 625000 | 625000 | NO DATES SET YET | G | Agreement with Locality milestone is 107 days ahead of the expected completion date | G | Project is on budget | 2021-02-01 |  | 2021-06-08 |  | G | 2021-06-09 |  | 2021-06-29 |  | G | 2021-07-29 |  | 2021-11-22 |  | G | [25 empty] | 2023-04-05 |  | 2023-08-31 |  | G | [5 empty] | 2023-06-20 |  | 2023-11-30 |  | G | 2024-02-23 |  | 2024-07-31 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.25458
2249 | 5462 | RTE 773 - SAFETY IMPROVEMENTS | 0773 | Secondary | Reconstruction w/o Added Capacity | VDOT | Patrick County | MARTINSVILLE | Salem | NonMPO:NonMPO | Infrastructure Investment Division | Lisa P Hughes | Lisa.Hughes@VDOT.Virginia.gov | (276) 629-2582 | Jason L Patrick | Jason.Patrick@vdot.virginia.gov | (540) 381-7178 |  |  |  | 0 |  | 0 | FY2022 | 1022032 | 1022032 | ACTIVITY DATES SET | G | Obtained Permits milestone finished 14 days early | G | Project is on budget | [5 empty] | 2007-07-16 | 2007-05-31 | 2007-08-17 | 2007-05-31 | G | 2019-01-03 | 2019-01-03 | 2019-05-28 | 2020-01-28 | R | [10 empty] | 2020-01-29 | 2020-01-29 | 2020-01-29 | 2020-01-29 | G | [10 empty] | 2020-08-26 | 2020-08-17 | 2020-10-28 | 2020-10-14 | G | [5 empty] | 2021-07-19 |  | 2021-07-19 |  | G | 2021-07-20 |  | 2022-01-12 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | SAAP CONTRACT | 0 | 0 | 0.092447
2250 | 113706 | #SGR19LP - Primary Extension RT 58 Westbound, Segment 1 | 0058 | Urban | Resurfacing | Locally | Suffolk | NORFOLK | Hampton Roads | Hampton Roads:Suffolk | Infrastructure Investment Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Johndel A Alcaide | John.Alcaide@vdot.virginia.gov | (757) 956-3098 | Ed Heide | eheide@suffolkva.us | (757) 514-7615 | 0 |  | 1 | FY2019 | 343000 | 343000 | WAITING FINANCIAL CLOSURE | G | Obtained Permits milestone finished 224 days early | G | Project is on budget | 2018-09-04 | 2018-09-24 | 2018-11-30 | 2018-10-04 | G | 2018-12-03 | 2018-10-05 | 2018-12-05 | 2018-10-05 | G | 2018-12-06 | 2018-10-08 | 2019-06-13 | 2018-10-11 | G | [25 empty] | 2019-05-28 | 2019-06-21 | 2020-02-03 | 2019-06-24 | G | [5 empty] | 2018-10-17 | 2018-10-17 | 2018-10-18 | 2018-10-18 | G | 2018-10-18 | 2018-10-18 | 2018-10-19 | 2018-10-19 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.096073
2251 | 113884 | Cummings Street Primary Extension Paving | 0075 | Urban | Resurfacing | Locally | Abingdon | ABINGDON | Bristol | Bristol:Abingdon | Local Assistance Division | Tabitha H Crowder | Tabitha.Crowder@vdot.virginia.gov | (276) 696-3482 | Tabitha H Crowder | Tabitha.Crowder@vdot.virginia.gov | (276) 696-3482 | Michael Surrett | msurrett@abingdon-va.gov | (276) 628-3167 | 0 |  | 0 | FY2019 | 231200 | 231200 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished on-time | G | Project is on budget | 2019-06-17 | 2018-08-01 | 2019-09-10 | 2018-09-10 | G | [5 empty] | 2019-06-17 | 2018-09-12 | 2019-06-28 | 2018-09-28 | G | [25 empty] | 2018-10-01 | 2018-10-01 | 2018-12-28 | 2018-10-22 | G | [5 empty] | 2018-11-05 | 2018-11-05 | 2018-11-05 | 2018-11-05 | G | 2018-12-03 | 2018-12-03 | 2018-12-03 | 2018-12-03 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.056866
2252 | 115195 | Atlee Station Rd Widening | 0637 | Secondary | Reconstruction w/ Added Capacity | Locally | Hanover County | ASHLAND | Richmond | Richmond:Hanover County | Infrastructure Investment Division | Cynthia Crouch | Cynthia.Crouch@vdot.virginia.gov | (804) 609-5313 | Cynthia Crouch | Cynthia.Crouch@vdot.virginia.gov | (804) 609-5313 | Joe Vidunas | jevidunas@co.hanover.va.us | (804) 365-6176 | 0 |  | 0 | FY2028 | 31529239 | 31529239 | NO DATES SET YET | G | Agreement with Locality milestone is 1380 days ahead of the expected completion date | G | Project is on budget | 2024-09-04 |  | 2024-12-02 |  | G | 2024-12-03 |  | 2024-12-05 |  | G | 2024-12-06 |  | 2025-12-08 |  | G | [10 empty] | 2026-12-21 |  | 2027-01-12 |  | G | [5 empty] | 2027-01-14 |  | 2027-10-22 |  | G | 2025-07-22 |  | 2026-03-30 |  | G | [5 empty] | 2027-11-09 |  | 2027-12-09 |  | G | 2028-03-03 |  | 2028-03-03 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.23544
2253 | 115409 | #SMART20 - Maury St Streetscape Phase II | 9999 | Urban | Facilities for Pedestrians and Bicycles | Locally | Richmond | ASHLAND | Richmond | Richmond:Richmond | Infrastructure Investment Division | Melinda G Baicy | Melinda.Baicy@vdot.virginia.gov | (804) 609-5390 | Melinda G Baicy | Melinda.Baicy@vdot.virginia.gov | (804) 609-5390 | Lamont Benjamin |  |  | 1 | 2020 | 0 | FY2027 | 4618000 | 4618000 | NO DATES SET YET | G | Agreement with Locality milestone is 1073 days ahead of the expected completion date | G | Project is on budget | 2023-10-30 |  | 2024-01-30 |  | G | 2024-01-31 |  | 2024-02-02 |  | G | 2024-02-05 |  | 2024-08-07 |  | G | [10 empty] | 2025-06-04 |  | 2025-06-24 |  | G | 2026-04-01 |  | 2026-09-30 |  | G | 2025-06-26 |  | 2026-04-09 |  | G | 2024-09-13 |  | 2025-05-21 |  | G | [5 empty] | 2026-04-27 |  | 2026-05-22 |  | G | 2026-08-12 |  | 2026-08-12 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.13957
2254 | 115717 | #SMART20 I-81 EXIT 313 BRIDGE CAPACITY IMPROVMENT | 0081 | Interstate | Bridge Replacement w/ Added Capacity | VDOT | Frederick County | EDINBURG | Staunton | Winchester:Frederick County | Infrastructure Investment Division | John-Allen L Ennis | JohnAllen.Ennis@VDOT.Virginia.gov | (540) 332-9118 | David Robinson | David.Robinson@vdot.virginia.gov | (540) 332-7758 |  |  |  | 1 | 2020 | 0 | FY2024 | 5264400 | 5264400 | NO DATES SET YET-PE OPEN | R | Determine Requirements milestone is 480 days past the expected completion date | G | Project is on budget | [5 empty] | 2019-03-01 | 2017-08-07 | 2019-03-14 | 2017-08-15 | G | 2019-03-15 | 2017-08-16 | 2019-10-30 |  | R | [5 empty] | 2020-12-17 |  | 2021-03-17 |  | Y | 2022-04-11 |  | 2022-04-29 |  | G | 2022-09-23 |  | 2023-07-06 |  | G | 2022-05-16 |  | 2023-04-26 |  | G | 2021-09-29 |  | 2023-03-01 |  | G | [5 empty] | 2023-07-11 |  | 2023-08-08 |  | G | 2023-11-30 |  | 2024-02-13 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.060614
2255 | 116890 | CAROLINE STREET - MILLING, PAVEMENT & RECONSTRUCTION | 0015 | Urban | Resurfacing | Locally | Orange | LOUISA | Culpeper | NonMPO:NonMPO | Local Assistance Division | Gregory J Cooley | Gregory.Cooley@vdot.virginia.gov | (434) 906-7979 | John P Price | John.Price@VDOT.Virginia.gov | (540) 347-6371 | John Cooley | townplanner@townoforangeva.org | (540) 672-6917 | 0 |  | 0 | FY2022 | 238048 | 238048 | NO DATES SET YET | R | Agreement with Locality milestone is 39 days past the expected completion date | G | Project is on budget | 2020-09-01 |  | 2021-01-13 |  | R | [5 empty] | 2021-01-14 |  | 2021-01-29 |  | R | [25 empty] | 2020-09-30 |  | 2021-03-08 |  | Y | [5 empty] | 2021-05-04 |  | 2021-06-01 |  | G | 2021-08-19 |  | 2021-08-19 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.048112
2256 | 117570 | ARLINGTON BLVD & WASHINGTON BLVD ACCELERATION RAMP #2 | 0027 | Primary | Safety | Locally | Arlington County | FAIRFAX | Northern Virginia | Northern Virginia:Arlington County | Local Assistance Division | Susie X Lue | Susie.Lue@vdot.virginia.gov | (703) 259-2918 | Susie X Lue | Susie.Lue@vdot.virginia.gov | (703) 259-2918 | Olivia Daniszewski | Odaniszewski@arlingtonva.us | 70348808 | 0 |  | 0 | FY2025 | 534000 | 534000 | NO DATES SET YET | Y | Agreement with Locality milestone is 5 days ahead of the expected completion date and there is a risk of missing this milestone date | G | Project is on budget | 2020-07-31 | 2020-07-08 | 2021-02-26 |  | Y | 2021-03-01 |  | 2021-03-31 |  | G | 2021-11-01 |  | 2022-07-29 |  | G | [5 empty] | 2022-09-01 |  | 2023-01-31 |  | G | 2023-08-01 |  | 2023-08-31 |  | G | [5 empty] | 2023-09-05 |  | 2024-06-28 |  | G | 2021-12-01 |  | 2022-07-29 |  | G | [5 empty] | 2024-08-01 |  | 2024-12-31 |  | G | 2025-01-02 |  | 2025-05-30 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.23214
2257 | 117951 | #81CIP DETOUR SIGNAL UPGRADES FOR BRISTOL & WYTHEVILLE | 9999 | Primary | Traffic Management/Engineering | VDOT | Bristol | ABINGDON | Bristol | NonMPO:NonMPO | Infrastructure Investment Division | Brian Holt | Brian.Holt@vdot.virginia.gov | (276) 696-3414 | Jeremy J Mullins | Jeremy.Mullins@vdot.virginia.gov | (276) 696-3259 |  |  |  | 0 |  | 0 | FY2024 | 3967047 | 3967047 | NO DATES SET YET-PE OPEN | G | Obtained Permits milestone finished 734 days early | G | Project is on budget | [5 empty] | 2020-10-01 | 2020-10-01 | 2020-10-22 | 2020-10-22 | G | 2020-10-23 | 2020-10-23 | 2021-08-26 |  | G | [5 empty] | 2022-04-01 |  | 2022-04-28 |  | G | [5 empty] | 2022-12-21 |  | 2023-04-25 |  | G | [5 empty] | 2022-09-08 | 2021-02-09 | 2023-02-13 | 2021-02-09 | G | [5 empty] | 2023-05-09 |  | 2023-05-09 |  | G | 2023-07-28 |  | 2023-07-28 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.095941
2258 | 118580 | HSIP Hampton Roads Unsignalized Int Pavement Markings | 9999 | Secondary | Safety | VDOT | Hampton Roads District-wide |  | Hampton Roads | Hampton Roads:Hampton Roads District-wide | Infrastructure Investment/Asset Management Division | Mark T Grass | Mark.Grass@VDOT.Virginia.gov | (757) 956-3165 | Jay Mohney | Jay.Mohney@vdot.virginia.gov | (757) 956-3168 |  |  |  | 0 |  | 0 | FY2022 | 150000 | 150000 | NO DATES SET YET | G | Determine Requirements milestone is 369 days ahead of the expected completion date | G | Project is on budget | [10 empty] | 2021-10-12 |  | 2022-02-25 |  | G | [35 empty] | 2022-03-01 |  | 2022-03-07 |  | G | 2022-03-08 |  | 2022-03-14 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | WORK/TASK ORDER | 0 | 0 | 0.098214
2259 | 13427 | RTE 172 - CITY OF POQUOSON - PHASE I | 0172 | Urban | Reconstruction w/ Added Capacity | VDOT | Poquoson | WILLIAMSBURG | Hampton Roads | Hampton Roads:Poquoson | Infrastructure Investment Division | Samba Secka | Samba.Secka@vdot.virginia.gov | (757) 956-3058 | Samba Secka | Samba.Secka@vdot.virginia.gov | (757) 956-3058 |  |  |  | 0 |  | 0 | FY2020 | 19822904 | 13918671 | ACTIVITY DATES SET | R | Solicit Bids milestone is 530 days past the expected completion date | G | Project is on budget | [5 empty] | 2001-07-16 | 2001-09-11 | 2001-07-31 | 2001-09-12 | R | 2006-07-03 | 2006-07-03 | 2016-05-31 | 2015-08-14 | G | [10 empty] | 2016-11-07 | 2016-11-07 | 2017-02-03 | 2017-02-03 | G | 2016-06-03 | 2019-01-30 | 2020-04-13 | 2020-11-20 | R | 2017-03-10 | 2017-03-10 | 2019-12-31 | 2019-01-23 | G | [10 empty] | 2019-09-10 |  | 2019-09-10 |  | R | 2019-10-24 |  | 2020-02-24 |  | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 1 | 0.27315
2260 | 15958 | COMMERCE ROAD - WIDENING |  | Urban | Reconstruction w/ Added Capacity | Locally | Richmond | CHESTERFIELD | Richmond | Richmond:Richmond | Infrastructure Investment Division | Evan Austin | Evan.Austin@vdot.virginia.gov | (804) 609-5384 | Evan Austin | Evan.Austin@vdot.virginia.gov | (804) 609-5384 | Tom Westbrook | Thomas.Westbrook@richmondgov.com | (804) 646-3421 | 0 |  | 0 | FY2019 | 14940100 | 20945000 | ACTIVITY DATES SET | R | Solicit Bids milestone is 877 days past the expected completion date | R | Project estimate is greater than $10M and is over budget by (a) 10% or more or (b) $5M or more | [5 empty] | 1996-08-01 | 1997-04-20 | 1996-08-31 | 1997-09-01 | R | 1995-09-01 | 1995-08-08 | 1997-08-29 | 1997-09-04 | R | [10 empty] | 2014-05-13 | 2014-05-13 | 2014-05-13 | 2014-05-13 | G | [20 empty] | 2018-09-04 |  | 2018-09-28 |  | R | 2018-12-03 |  | 2018-12-31 |  | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.22151
2261 | 104773 | Bridge Replacement Rte 609 over Little River (Fed ID 18548) | 0609 | Secondary | Bridge Replacement w/ Added Capacity | VDOT | Tazewell County | LEBANON | Bristol | NonMPO:NonMPO | Infrastructure Investment Division | Gary Lester |  |  | Shane C Morrison | Shane.Morrison@vdot.virginia.gov | (276) 696-3380 |  |  |  | 0 |  | 0 | FY2019 | 1752037 | 1708039 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished on-time | G | Project is on budget | [5 empty] | 2016-07-05 | 2016-07-05 | 2016-07-05 | 2016-07-05 | G | 2016-08-04 | 2013-11-26 | 2018-05-31 | 2018-06-29 | R | [35 empty] | 2018-10-09 | 2018-10-09 | 2018-10-09 | 2018-10-09 | G | 2018-10-10 | 2018-12-07 | 2018-12-07 | 2018-12-07 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.067484
2262 | 105286 | FAIRFAX COUNTY - SRTS - GRAHAM ROAD ES - CROSSING IMP. | 0000 | Secondary | Safety | Locally | Fairfax County | FAIRFAX | Northern Virginia | Northern Virginia:Fairfax County | Infrastructure Investment Division | John T Tasselli | Tom.Tasselli@vdot.virginia.gov | (703) 259-2430 | Rita Hockman | Rita.Hockman@vdot.virginia.gov | (804) 824-7421 | Francesco Lauretti | Francesco.Lauretti@fairfaxcounty.gov | (703) 877-5600 | 0 |  | 0 | FY2019 | 190000 | 186182 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 149 days early | G | Project is on budget | 2014-05-21 | 2014-05-21 | 2014-05-21 | 2014-05-21 | G | 2013-11-01 | 2014-08-05 | 2014-02-01 | 2014-08-11 | R | 2013-12-02 | 2018-01-16 | 2014-04-01 | 2018-01-17 | R | [5 empty] | 2018-01-08 | 2018-01-08 | 2018-01-25 | 2018-01-25 | G | [25 empty] | 2018-04-02 | 2018-05-14 | 2018-06-01 | 2018-06-01 | G | 2018-10-31 | 2018-10-31 | 2019-03-29 | 2018-10-31 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.13673
2263 | 105706 | Reconstruct Massanetta Springs Rd. | 0687 | Secondary | Reconstruction w/o Added Capacity | Locally | Rockingham County | HARRISONBURG | Staunton | Harrisonburg:Rockingham County | Local Assistance Division | Donald F Komara | Donald.Komara@VDOT.Virginia.gov | (540) 434-2587 | Michael S Fulcher | Michael.Fulcher@VDOT.Virginia.gov | (540) 332-2243 | Stephen King | sking@rockinghamcountyva.gov | (540) 578-1130 | 0 |  | 0 | FY2019 | 3500000 | 3500000 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 144 days early | G | Project is on budget | [5 empty] | 2016-03-30 | 2016-03-30 | 2016-03-30 | 2016-03-30 | G | 2016-04-29 | 2016-04-29 | 2018-03-30 | 2018-03-30 | G | [10 empty] | 2018-01-31 | 2018-01-31 | 2018-05-24 | 2018-05-24 | G | [20 empty] | 2018-10-01 | 2018-11-01 | 2018-12-31 | 2018-11-30 | G | 2019-01-02 | 2018-10-31 | 2019-05-31 | 2019-01-07 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.15759
2264 | 106701 | HRRR - Safety Improvements | 9999 | Secondary | Safety | VDOT | Bedford County | BEDFORD | Salem | NonMPO:NonMPO | Infrastructure Investment Division | Bernard S Grinnell | Sean.Grinnell@VDOT.Virginia.gov | (540) 375-0148 | Jason L Patrick | Jason.Patrick@vdot.virginia.gov | (540) 381-7178 |  |  |  | 0 |  | 0 | FY2022 | 1841763 | 2040050 | ACTIVITY DATES SET | Y | Complete Purchasing Right-of-Way milestone is 52 days ahead of the expected completion date and there is a risk of missing this milestone date | Y | Project estimate is less than $5M and is up to 20% over budget | [5 empty] | 2015-09-01 | 2015-10-29 | 2015-09-01 | 2015-11-30 | R | 2015-11-17 | 2016-01-22 | 2018-12-21 | 2018-12-05 | G | [5 empty] | 2020-10-20 | 2020-10-20 | 2020-10-20 | 2020-10-30 | R | 2020-11-20 | 2020-10-29 | 2020-11-20 | 2020-11-17 | G | 2021-04-02 |  | 2021-05-13 |  | G | 2020-11-16 |  | 2021-04-14 |  | Y | 2020-12-24 | 2019-03-06 | 2021-06-17 | 2019-03-06 | G | [5 empty] | 2021-09-14 |  | 2021-09-14 |  | G | 2021-10-28 |  | 2022-04-04 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.14977
2265 | 107020 | RTE 37 - SAFETY IMPROVEMENTS | 0037 | Primary | Safety | VDOT | Frederick County | EDINBURG | Staunton | Winchester:Frederick County | Infrastructure Investment Division | Keith M Rider | Keith.Rider@VDOT.Virginia.gov | (434) 856-8145 | Kunal Kothawade | Kunal.Kothawade@vdot.virginia.gov | (540) 332-9259 |  |  |  | 0 |  | 0 | FY2021 | 3750000 | 3750000 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 56 days early | G | Project is on budget | [5 empty] | 2017-07-11 | 2017-07-11 | 2017-08-08 | 2017-08-08 | G | 2017-08-09 | 2017-08-09 | 2018-07-26 | 2018-02-01 | G | [35 empty] | 2020-05-20 | 2020-03-10 | 2020-05-20 | 2020-03-10 | G | 2020-07-06 | 2020-05-29 | 2020-07-24 | 2020-05-29 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.064231
2266 | 107073 | US 23 Shoulder Initiative | 0023 | Primary | Safety | VDOT | Bristol District-wide |  | Bristol | NonMPO:NonMPO | Infrastructure Investment Division | Allan D Sumpter | Allan.Sumpter@VDOT.virginia.gov | (276) 525-6461 | Chase R Buchanan | Chase.Buchanan@VDOT.Virginia.gov | (276) 696-3251 |  |  |  | 0 |  | 0 | FY2020 | 2800000 | 3075480 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished on-time | Y | Project estimate is less than $5M and is up to 20% over budget | [5 empty] | 2017-09-12 | 2017-09-12 | 2017-09-13 | 2017-09-13 | G | 2017-07-17 | 2017-07-17 | 2019-02-08 | 2019-02-08 | G | [35 empty] | 2020-02-21 | 2020-02-11 | 2020-02-21 | 2020-02-11 | G | 2020-05-07 | 2020-05-07 | 2020-05-07 | 2020-05-07 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.070238
2267 | 108004 | RTE 95 - IMPROVE TRAFFIC OPERATIONS AND SOUND WALL DESIGN | 0095 | Interstate | Other | VDOT | Richmond District-wide | ASHLAND | Richmond | Richmond:Richmond District-wide | Infrastructure Investment Division | Lawrence Ramsey | Brian.Ramsey@VDOT.Virginia.gov | (804) 585-3579 | Lawrence Ramsey | Brian.Ramsey@VDOT.Virginia.gov | (804) 585-3579 |  |  |  | 0 |  | 0 | FY2019 | 3956888 | 3956888 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 168 days early | G | Project is on budget | [5 empty] | 2016-01-05 | 2016-01-05 | 2016-01-20 | 2016-01-20 | G | 2016-01-05 | 2016-01-05 | 2018-03-30 | 2018-03-29 | G | [5 empty] | 2018-03-30 | 2018-03-30 | 2018-04-23 | 2018-04-18 | G | 2018-04-23 | 2018-04-18 | 2018-04-23 | 2018-04-18 | G | [20 empty] | 2018-09-11 | 2018-10-09 | 2019-02-12 | 2018-10-09 | G | 2019-04-04 | 2018-12-27 | 2019-06-13 | 2018-12-27 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.066633
2268 | 109299 | #HB2.FY17 GOVERNMENT CENTER PARKWAY EXTENSION | 9999 | Urban | New Construction Roadway | Locally | Fairfax | FAIRFAX | Northern Virginia | Northern Virginia:Fairfax | Infrastructure Investment Division | Terry Yates | Terry.Yates@vdot.virginia.gov | (703) 259-2118 | Robert J Strevell | Robert.Strevell@vdot.virginia.gov | (703) 259-1988 | Wendy Block Sanford | wendyblock.sanford@fairfaxva.gov | (703) 385-7889 | 1 | 2017 | 0 | FY2020 | 3144181 | 7500181 | NO DATES SET YET-PE OPEN | R | Relocate Utilities milestone baseline missing | R | Project estimate is less than $5M and is 20% or more over budget | 2016-07-01 | 2016-06-22 | 2017-01-11 | 2016-10-24 | G | 2017-01-12 | 2016-10-25 | 2017-01-17 | 2016-10-26 | G | 2017-01-18 | 2017-04-03 | 2017-08-11 |  | R | [9 empty] | R | 2018-06-08 |  | 2018-06-28 |  | R |  |  |  |  | R | 2018-07-02 |  | 2019-04-15 |  | R | [10 empty] | 2019-05-01 |  | 2019-05-29 |  | R | 2019-05-30 |  | 2019-07-10 |  | R | Delay due to unforeseen issues with utilities, railroad coordination, or right-of-way acquisition | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.27098
2269 | 109466 | #HB2.FY17 - INTERSECTION IMPROVEMENTS ROUTE 30/360 | 0030 | Primary | Reconstruction w/o Added Capacity | VDOT | King William County | SALUDA | Fredericksburg | NonMPO:NonMPO | Infrastructure Investment Division | Wesley Foor | Wesley.Foor@vdot.virginia.gov | (540) 604-1370 | Wesley Foor | Wesley.Foor@vdot.virginia.gov | (540) 604-1370 |  |  |  | 1 | 2017 | 0 | FY2021 | 3000000 | 3000000 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 127 days early | G | Project is on budget | [5 empty] | 2017-02-06 | 2017-01-19 | 2017-02-06 | 2017-01-19 | G | 2017-07-06 | 2017-01-23 | 2018-02-15 | 2017-12-12 | G | [5 empty] | 2018-05-09 | 2018-06-04 | 2018-05-22 | 2018-06-11 | R | 2019-02-06 | 2019-01-22 | 2019-02-20 | 2019-02-07 | G | 2019-09-11 | 2019-10-09 | 2020-03-23 | 2020-03-19 | G | 2019-03-08 | 2019-02-21 | 2019-09-10 | 2019-09-09 | G | [10 empty] | 2020-04-14 | 2020-01-07 | 2020-04-14 | 2020-01-07 | G | 2020-07-17 | 2020-05-07 | 2020-09-11 | 2020-05-07 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.081063
2270 | 79923 | #HB2.FY17 RTE 81 - SAFETY IMPROVEMENTS, EXIT 213 | 0081 | Interstate | Safety | VDOT | Augusta County | HARRISONBURG | Staunton | NonMPO:NonMPO | Infrastructure Investment Division | Garrett Moore |  |  | Stephan M Ball | Stephan.Ball@VDOT.Virginia.gov | (540) 332-9047 |  |  |  | 1 | 2017 | 0 | FY2017 | 2688439 | 1565000 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 36 days early | G | Project is on budget | [5 empty] | 2006-12-01 | 2006-12-01 | 2006-12-29 | 2006-12-29 | G | 2007-09-01 | 2007-08-21 | 2013-12-20 | 2016-07-20 | R | [5 empty] | 2014-07-31 | 2016-07-20 | 2014-09-30 | 2016-07-26 | R | [15 empty] | 2016-10-25 | 2016-10-25 | 2016-10-28 | 2016-10-28 | G | [5 empty] | 2016-06-10 | 2016-12-13 | 2016-12-13 | 2016-12-13 | G | 2017-03-01 | 2017-02-22 | 2017-03-30 | 2017-02-22 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.06162
2271 | 104955 | #SGR17VB - BR REPLACE RT 92 OVER BUTCHERS CREEK (Fed 11943) | 0092 | Primary | Bridge Replacement w/o Added Capacity | VDOT | Mecklenburg County | SOUTH HILL | Richmond | NonMPO:NonMPO | Infrastructure Investment/Asset Management Division | Thomas Kendrick | Thomas.Kendrick@vdot.virginia.gov | (804) 609-5281 | Thomas Kendrick | Thomas.Kendrick@vdot.virginia.gov | (804) 609-5281 |  |  |  | 0 |  | 1 | FY2022 | 3020000 | 2000000 | ACTIVITY DATES SET | G | Determine Requirements milestone finished 2 days early | G | Project is on budget | [10 empty] | 2017-08-24 | 2017-10-11 | 2018-08-15 | 2018-08-13 | G | [35 empty] | 2021-11-09 |  | 2021-11-09 |  | G | 2022-03-30 |  | 2022-04-19 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.060315
2272 | 105608 | Chrisman Mill Rd -Realign N Side of Road at Crossing | 0000 | Urban | Rail/Highway Crossing | Locally | Christiansburg | CHRISTIANSBURG | Salem | New River Valley:Christiansburg | Infrastructure Investment Division | David D Clarke | David.Clarke@VDOT.Virginia.gov | (540) 381-7190 | Adam J Czesnowski | Adam.Czesnowski@vdot.virginia.gov | (540) 541-1216 | Wayne Nelson | wnelson@christiansburg.org | (540) 382-6120 | 0 |  | 0 | FY2020 | 747725 | 1269723 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 7 days early | R | Project estimate is less than $5M and is 20% or more over budget | [5 empty] | 2015-08-15 | 2015-06-25 | 2015-08-15 | 2015-11-13 | R | 2015-09-14 | 2016-02-02 | 2016-01-14 | 2017-01-23 | R | [10 empty] | 2018-04-16 | 2018-04-16 | 2018-04-18 | 2018-04-18 | G | [20 empty] | 2019-02-01 | 2019-06-06 | 2019-02-01 | 2019-06-09 | R | 2019-03-01 | 2019-07-08 | 2019-08-01 | 2019-07-25 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.10729
2273 | 106495 | CAPITAL BIKESHARE EXPANSION-GEORGE WASHINGTON MEMORIAL PKWY | 0400 | Miscellaneous | Facilities for Pedestrians and Bicycles | Locally | Arlington County | FAIRFAX | Northern Virginia | Northern Virginia:Arlington County | Infrastructure Investment Division | Amir Salahshoor | A.Salahshoor@VDOT.Virginia.gov | (703) 259-1957 | Rita Hockman | Rita.Hockman@vdot.virginia.gov | (804) 824-7421 | Paul DeMaio | paul@metrobike.net | (202) 684-8126 | 0 |  | 0 | FY2019 | 501000 | 417627 | CONSTRUCTION STARTED | R | Start Delivery milestone finished 103 days late | G | Project is on budget | 2016-06-01 | 2016-07-20 | 2016-08-31 | 2016-08-18 | G | [5 empty] | 2016-11-15 | 2016-11-15 | 2017-02-28 | 2017-04-03 | R | [25 empty] | 2017-06-19 | 2017-06-19 | 2017-06-29 | 2017-06-29 | G | [5 empty] | 2018-10-01 | 2019-08-15 | 2018-12-28 | 2019-08-15 | R | 2019-01-02 | 2019-08-19 | 2019-05-30 | 2019-09-10 | R | Delay due to changes in scope of work, project management, plan designs, or resolution of public comments | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.15314
2274 | 106927 | CHAIN BRIDGE ROAD WALKWAY | 3547 | Primary | Facilities for Pedestrians and Bicycles | Locally | Fairfax County | FAIRFAX | Northern Virginia | Northern Virginia:Fairfax County | Infrastructure Investment Division | Amir Salahshoor | A.Salahshoor@VDOT.Virginia.gov | (703) 259-1957 | Rita Hockman | Rita.Hockman@vdot.virginia.gov | (804) 824-7421 | Dennis Marsh | Dennis.Marsh@fairfaxcounty.gov | (703) 877-5746 | 0 |  | 0 | FY2021 | 1150000 | 150000 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 890 days early | G | Project is on budget | [10 empty] | 2015-04-01 | 2015-04-01 | 2015-04-01 | 2015-04-01 | G | [10 empty] | 2016-04-29 | 2016-04-29 | 2016-05-12 | 2016-04-29 | G | [20 empty] | 2018-10-03 | 2018-02-24 | 2020-11-04 | 2018-05-25 | G | 2020-12-22 | 2018-08-02 | 2021-01-13 | 2018-08-07 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.07827
2275 | 107037 | RTE 147 - INSTALL PEDESTRIAN LIGHTING - HUGUENOT BRIDGE | 0147 | Primary | Safety | VDOT | Henrico County | ASHLAND | Richmond | Richmond:Henrico County | Infrastructure Investment Division | Adam S Brooks | Adam.Brooks@VDOT.Virginia.gov | (804) 609-5274 | Adam S Brooks | Adam.Brooks@VDOT.Virginia.gov | (804) 609-5274 |  |  |  | 0 |  | 0 | FY2025 | 1277000 | 1277000 | NO DATES SET YET-PE OPEN | R | Determine Requirements milestone is 447 days past the expected completion date | G | Project is on budget | [5 empty] | 2018-10-19 | 2018-10-11 | 2018-11-01 | 2018-10-17 | G | 2018-11-02 | 2018-10-18 | 2019-12-02 |  | R | [5 empty] | 2020-10-05 |  | 2020-10-19 |  | R | 2022-06-07 |  | 2022-06-20 |  | G | 2024-01-03 |  | 2024-07-02 |  | G | 2022-07-06 |  | 2023-01-03 |  | G | 2021-10-21 | 2020-02-13 | 2022-10-05 | 2020-02-13 | G | [5 empty] | 2024-10-31 |  | 2024-10-31 |  | G | 2024-12-13 |  | 2025-01-02 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.071877
2276 | 107259 | Downtown Suffolk Drainage Improvements | 0000 | Urban | Other | Locally | Suffolk | NORFOLK | Hampton Roads | Hampton Roads:Suffolk | Local Assistance Division | Stephen Rowan | Steve.Rowan@vdot.virginia.gov | (757) 790-9925 | Johndel A Alcaide | John.Alcaide@vdot.virginia.gov | (757) 956-3098 | Robert Lewis | relewis@suffolkva.us | (757) 514-7621 | 0 |  | 0 | FY2021 | 1500000 | 2562649 | ACTIVITY DATES SET | Y | Solicit Bids milestone is 12 days ahead of the expected completion date and there is a risk of missing this milestone date | R | Project estimate is less than $5M and is 20% or more over budget | 2015-05-18 | 2015-05-18 | 2015-08-11 | 2015-08-11 | G | 2015-08-12 | 2015-08-12 | 2016-01-14 | 2016-01-14 | G | 2016-01-19 | 2016-01-19 | 2018-10-04 | 2019-06-28 | R | [10 empty] | 2020-04-06 | 2020-05-01 | 2020-05-01 | 2020-05-01 | G | [20 empty] | 2021-03-05 |  | 2021-03-05 |  | Y | 2021-03-08 |  | 2021-06-11 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.12131
2277 | 108205 | Stabilization and Restoration - Lighthouse Phase II |  | Enhancement | Restoration and Rehabilitation | Locally | Mathews County | SALUDA | Fredericksburg | NonMPO:NonMPO | Local Assistance Division | Michael T Coffey | MichaelT.Coffey@vdot.virginia.gov | (540) 899-4225 | Michael T Coffey | MichaelT.Coffey@vdot.virginia.gov | (540) 899-4225 | Mindy Moran | MMoran@co.mathews.va.us | (804) 725-4034 | 0 |  | 0 | FY2020 | 1625200 | 2137522 | AWARDED | R | Start Delivery milestone finished 180 days late | R | Project estimate is less than $5M and is 20% or more over budget | 2016-04-13 | 2016-04-13 | 2016-07-13 | 2016-07-13 | G | 2016-07-08 | 2016-07-08 | 2016-07-12 | 2016-07-12 | G | 2016-07-13 | 2016-07-13 | 2018-09-25 | 2018-09-25 | G | [35 empty] | 2019-03-13 | 2019-11-07 | 2019-06-05 | 2019-11-07 | R | 2019-06-06 | 2019-12-30 | 2019-10-11 | 2020-04-08 | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.34268
2279 | 109531 | #HB2.FY17 RTE 460 - INTERSECTION RECONSTRUCTION AT RTE 307 | 0460 | Primary | Safety | VDOT | Prince Edward County | DILLWYN | Lynchburg | NonMPO:NonMPO | Infrastructure Investment Division | Brian J Casto | Brian.Casto@VDOT.Virginia.gov | (434) 856-8276 | Gregory K Parsons | Gregory.Parsons@vdot.virginia.gov | (434) 856-8297 |  |  |  | 1 | 2017 | 0 | FY2020 | 2744657 | 2744657 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 22 days early | G | Project is on budget | [5 empty] | 2016-08-16 | 2016-08-16 | 2016-08-16 | 2016-08-16 | G | 2016-08-17 | 2016-08-17 | 2017-01-30 | 2017-01-25 | G | [5 empty] | 2017-12-06 | 2017-12-06 | 2017-12-19 | 2017-12-19 | G | 2018-11-02 | 2018-10-16 | 2018-11-16 | 2018-10-16 | G | 2019-05-31 | 2019-05-29 | 2019-11-20 | 2019-10-24 | G | 2018-12-06 | 2018-10-29 | 2019-05-30 | 2019-05-28 | G | [10 empty] | 2019-12-10 | 2019-12-10 | 2019-12-10 | 2019-12-10 | G | 2020-01-29 | 2020-03-03 | 2020-03-25 | 2020-03-03 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.095733
2280 | 110127 | RT 608 - ALTICE RD - RURAL RUSTIC | 0608 | Secondary | Resurfacing | VDOT | Bedford County | BEDFORD | Salem | NonMPO:NonMPO | Infrastructure Investment Division | Todd K Daniel | Todd.Daniel@VDOT.Virginia.gov | (540) 682-7000 | John JP Morris | John.Morris@vdot.virginia.gov | (540) 682-7010 |  |  |  | 0 |  | 0 | FY2019 | 447574 | 447574 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 346 days early | G | Project is on budget | [5 empty] | 2016-11-18 | 2016-11-29 | 2016-12-05 | 2016-12-06 | R | 2016-12-06 | 2016-12-07 | 2017-07-28 | 2018-01-30 | R | [5 empty] | 2018-06-26 | 2018-04-10 | 2018-07-02 | 2018-04-10 | G | [5 empty] | 2018-05-09 | 2018-04-19 | 2018-05-09 | 2018-04-19 | G | [5 empty] | 2018-04-04 | 2018-02-27 | 2018-07-26 | 2018-02-27 | G | [5 empty] | 2018-08-28 | 2018-04-24 | 2019-02-26 | 2018-04-24 | G | 2019-04-11 | 2018-06-25 | 2019-06-06 | 2018-06-25 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | SAAP CONTRACT | 1 | 0 | 0.12026
2281 | 111227 | #SMART18 - (St) INTERSECTION OF RTE 277 AND WARRIOR DR | 0277 | Primary | Reconstruction w/o Added Capacity | VDOT | Frederick County | EDINBURG | Staunton | Winchester:Frederick County | Infrastructure Investment Division | Matthew P Dana | Matt.Dana@VDOT.Virginia.gov | (540) 332-7786 | Ronald L Tabor | Ronald.Tabor@vdot.virginia.gov | (540) 332-7887 |  |  |  | 1 | 2018 | 0 | FY2025 | 476644 | 476644 | NO DATES SET YET | G | Start Development milestone is 173 days ahead of the expected completion date | G | Project is on budget | [5 empty] | 2021-08-02 |  | 2021-08-13 |  | G | 2021-08-16 |  | 2022-04-21 |  | G | [5 empty] | 2022-12-06 |  | 2022-12-19 |  | G | 2023-11-15 |  | 2023-11-30 |  | G | 2024-04-26 |  | 2024-10-08 |  | G | 2023-12-18 |  | 2024-06-24 |  | G | 2023-07-25 |  | 2024-02-02 |  | G | [5 empty] | 2024-11-12 |  | 2024-11-12 |  | G | 2024-12-31 |  | 2025-02-28 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.073709
2282 | 111636 | Route 607 Bland Co Replace Struct 6057 Fed ID 3068 | 0607 | Secondary | Bridge Replacement w/o Added Capacity | VDOT | Bland County | WYTHEVILLE | Bristol | NonMPO:NonMPO | Infrastructure Investment Division | Gary Lester |  |  | Shane C Morrison | Shane.Morrison@vdot.virginia.gov | (276) 696-3380 |  |  |  | 0 |  | 0 | FY2020 | 868665 | 875391 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 12 days early | Y | Project estimate is less than $5M and is up to 20% over budget | [5 empty] | 2017-08-25 | 2017-08-25 | 2017-08-25 | 2017-08-25 | G | 2017-08-28 | 2017-08-28 | 2018-04-20 | 2019-01-28 | R | [5 empty] | 2019-02-26 | 2019-02-26 | 2019-02-26 | 2019-02-26 | G | [5 empty] | 2019-03-01 | 2019-03-01 | 2019-03-01 | 2019-03-01 | G | [5 empty] | 2019-04-26 | 2019-03-26 | 2019-07-29 | 2019-04-01 | G | [5 empty] | 2019-08-13 | 2019-08-13 | 2019-08-13 | 2019-08-13 | G | 2019-09-27 | 2019-11-13 | 2019-11-25 | 2019-11-13 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.071884
2283 | 112553 | RANDOLPH AVE-RECONSTRUCTION | 9999 | Urban | Reconstruction w/o Added Capacity | Locally | South Boston | HALIFAX | Lynchburg | NonMPO:NonMPO | Infrastructure Investment Division | John E Neblett | John.Neblett@VDOT.Virginia.gov | (434) 856-8202 | John E Neblett | John.Neblett@VDOT.Virginia.gov | (434) 856-8202 | C. W. Crowder, Jr. | crowder@southboston.va.us | (434) 575-4261 | 0 |  | 0 | FY2020 | 280691 | 280691 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 599 days early | G | Project is on budget | 2018-01-08 | 2018-01-08 | 2018-04-04 | 2018-03-06 | G | 2018-04-05 | 2018-03-06 | 2018-04-09 | 2018-03-06 | G | 2018-04-10 | 2018-03-07 | 2018-10-11 | 2018-03-07 | G | [10 empty] | 2018-12-28 | 2018-04-11 | 2019-01-22 | 2018-04-11 | G | [5 empty] | 2019-01-24 | 2018-04-13 | 2019-10-30 | 2018-04-13 | G | [10 empty] | 2019-11-18 | 2018-04-18 | 2019-12-17 | 2018-04-18 | G | 2019-12-18 | 2018-06-11 | 2020-01-31 | 2018-06-11 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.078407
2284 | 112758 | Citywide Pedestrian Safety Improvements ??? Intersections | 0000 | Urban | Facilities for Pedestrians and Bicycles | Locally | Norfolk | NORFOLK | Hampton Roads | Hampton Roads:Norfolk | Infrastructure Investment Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Derrick Williams | Derrick.Williams@vdot.virginia.gov | (757) 956-3097 | L. Keith Darrow , P.E. | Keith.Darrow@norfolk.gov | (757) 664-7857 | 0 |  | 0 | FY2023 | 3000000 | 3000000 | ACTIVITY DATES SET | R | Start Purchasing Right-of-Way milestone is 25 days past the expected completion date | G | Project is on budget | 2018-05-03 | 2018-05-01 | 2018-07-27 | 2018-06-08 | G | 2018-07-30 | 2018-07-13 | 2018-08-10 | 2018-07-17 | G | 2018-08-13 | 2018-07-18 | 2019-08-13 | 2019-08-13 | G | [10 empty] | 2021-01-12 |  | 2021-01-27 |  | R | [5 empty] | 2021-06-07 |  | 2022-04-20 |  | G | [10 empty] | 2022-05-19 |  | 2022-06-30 |  | G | 2022-07-01 |  | 2022-12-23 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.24426
2285 | 113441 | RTE 144 (Temple Ave)Resurfacing (Conduit Rd to Limits) | 0144 | Urban | Resurfacing | Locally | Colonial Heights | CHESTERFIELD | Richmond | Tri-Cities:Colonial Heights | Local Assistance Division | Brian J Lokker | Brian.Lokker@VDOT.Virginia.gov | (804) 524-6010 | Brian J Lokker | Brian.Lokker@VDOT.Virginia.gov | (804) 524-6010 | Keith Chisolm | chisolmk@colonialheightsva.gov | (804) 520-9334 | 0 |  | 1 | FY2019 | 780000 | 780000 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 39 days early | G | Project is on budget | 2018-07-02 | 2018-07-01 | 2018-09-25 | 2018-08-14 | G | 2018-09-26 | 2018-08-15 | 2018-09-28 | 2018-08-28 | G | 2018-10-01 | 2018-09-04 | 2019-04-11 | 2018-10-24 | G | [35 empty] | 2018-12-03 | 2018-10-31 | 2018-12-31 | 2018-12-06 | G | 2019-03-25 | 2018-12-07 | 2019-04-01 | 2019-02-21 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.084978
2286 | 113594 | RTE 3 & 20 INT. IMPROVEMENT - PAVING WORK ORDER | 0003 | Primary | Resurfacing | VDOT | Orange County | LOUISA | Culpeper | NonMPO:NonMPO | Infrastructure Investment Division | Ken Connors |  |  | Bethel Kefyalew | Bethel.Kefyalew@vdot.virginia.gov | (540) 603-6015 |  |  |  | 0 |  | 0 | FY2019 | 156805 | 156805 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 39 days early | G | Project is on budget | [10 empty] | 2018-10-29 | 2018-05-29 | 2019-03-13 | 2019-03-13 | G | [35 empty] | 2019-05-03 | 2019-03-25 | 2019-05-03 | 2019-03-25 | G | 2019-05-03 | 2019-03-25 | 2019-05-03 | 2019-03-25 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | WORK/TASK ORDER | 1 | 0 | 0.06048
2287 | 113711 | #TAP19 RIVERWALK TRAIL EXTENSION | 9999 | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Danville | HALIFAX | Lynchburg | Danville:Danville | Local Assistance Division | Gregg Allen | Gregg.Allen@vdot.virginia.gov | (434) 426-5575 | Jay S Brown | Jay.Brown@VDOT.Virginia.gov | (434) 856-8246 | KAREN BLACK | blackka@danvilleva.gov | (434) 799-8919 | 0 |  | 0 | FY2022 | 205000 | 205000 | ACTIVITY DATES SET | G | Complete Purchasing Right-of-Way milestone finished on-time | G | Project is on budget | 2019-01-31 | 2018-12-27 | 2019-04-25 | 2018-12-27 | G | 2019-04-26 | 2018-12-28 | 2019-04-30 | 2019-02-08 | G | 2019-05-01 | 2019-05-01 | 2019-11-04 | 2020-10-28 | R | [10 empty] | 2020-11-06 | 2020-11-06 | 2020-11-06 | 2020-11-06 | G | [5 empty] | 2020-11-06 | 2020-11-09 | 2020-11-09 | 2020-11-09 | G | [10 empty] | 2021-12-01 |  | 2021-12-15 |  | G | 2022-06-09 |  | 2022-06-16 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.1884
2288 | 113735 | RTE 677 - RURAL RUSTIC RD (SURFACE TREAT NON-HARDSURFACE RD) | 0677 | Secondary | Reconstruction w/o Added Capacity | VDOT | Fluvanna County | LOUISA | Culpeper | NonMPO:NonMPO | Infrastructure Investment Division | Ken Connors |  |  | Bethel Kefyalew | Bethel.Kefyalew@vdot.virginia.gov | (540) 603-6015 |  |  |  | 0 |  | 0 | FY2026 | 136273 | 136273 | NO DATES SET YET | G | Start Development milestone is 964 days ahead of the expected completion date | G | Project is on budget | [5 empty] | 2023-10-02 |  | 2023-10-13 |  | G | 2023-10-17 |  | 2024-06-11 |  | G | [5 empty] | 2025-02-20 |  | 2025-04-02 |  | G | [5 empty] | 2025-07-17 |  | 2025-11-07 |  | G | [5 empty] | 2025-07-01 |  | 2025-10-01 |  | G | [5 empty] | 2025-11-10 |  | 2025-11-10 |  | G | 2026-02-06 |  | 2026-02-06 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | SAAP CONTRACT | 0 | 0 | 0.094069
2289 | 113882 | #SGR19LB??- MLK BLV over Beaver Crk Bristol VA 8002 Fed 2000 | 0000 | Urban | Bridge Rehab w/o Added Capacity | Locally | Bristol | ABINGDON | Bristol | Bristol:Bristol | Infrastructure Investment/Asset Management Division | John W Bechtold | John.Bechtold@vdot.virginia.gov | (276) 696-3365 | Kenneth R Plummer | KR.Plummer@VDOT.Virginia.gov | (276) 696-3261 | Wallace McCulloch | wallace.mcculloch@bristolva.org | (276) 642-2316 | 0 |  | 1 | FY2022 | 2150000 | 2150000 | NO DATES SET YET-PE OPEN | R | Determine Requirements milestone is 12 days past the expected completion date | G | Project is on budget | 2020-04-30 | 2019-10-17 | 2020-07-24 | 2020-01-13 | G | 2020-07-27 | 2020-01-14 | 2020-07-29 | 2020-01-15 | G | 2020-07-30 |  | 2021-02-09 |  | R | [25 empty] | 2021-03-18 |  | 2021-11-17 |  | G | [5 empty] | 2022-03-01 |  | 2022-03-28 |  | G | 2022-06-15 |  | 2022-06-15 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.11606
2290 | 110433 | #SGR17VB - HUNTER MILL RD OVER COLVIN RUN BRIDGE REPLACEMENT | 0674 | Secondary | Bridge Replacement w/ Added Capacity | VDOT | Fairfax County | FAIRFAX | Northern Virginia | Northern Virginia:Fairfax County | Infrastructure Investment/Asset Management Division | Gary Runco | Gary.Runco@vdot.virginia.gov | (703) 259-3341 | Vicente S Valeza | Vicente.Valeza@vdot.virginia.gov | (703) 259-3256 |  |  |  | 0 |  | 1 | FY2021 | 2273488 | 4789298 | ADVERTISED | G | Solicit Bids milestone finished on-time | R | Project estimate is less than $5M and is 20% or more over budget | [10 empty] | 2018-03-06 | 2017-01-27 | 2018-03-19 | 2017-12-21 | G | [35 empty] | 2021-02-09 | 2021-02-09 | 2021-02-09 | 2021-02-09 | G | 2021-04-01 |  | 2021-04-21 |  | G | Preliminary design and/or investigations are still underway | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.075061
2291 | 111366 | #SMART18 - Plantation Rd Bike/Ped/Streetscape Phase II | 0115 | Urban | Facilities for Pedestrians and Bicycles | Locally | Roanoke County | SALEM | Salem | Roanoke:Roanoke County | Infrastructure Investment Division | Adam J Czesnowski | Adam.Czesnowski@vdot.virginia.gov | (540) 541-1216 | Adam J Czesnowski | Adam.Czesnowski@vdot.virginia.gov | (540) 541-1216 | David Holladay | dholladay@roanokecountyva.org | (540) 772-2094 | 1 | 2018 | 0 | FY2021 | 1752213 | 2101020 | ADVERTISED | G | Solicit Bids milestone finished 83 days early | Y | Project estimate is less than $5M and is up to 20% over budget | 2018-07-17 | 2018-07-17 | 2018-10-09 | 2019-04-17 | R | 2018-10-10 | 2019-04-29 | 2018-10-12 | 2019-05-08 | R | 2018-10-16 | 2019-05-09 | 2019-03-14 | 2019-11-01 | R | [5 empty] | 2020-04-06 | 2020-03-06 | 2020-04-17 | 2020-03-06 | G | 2020-04-20 | 2020-03-17 | 2020-05-08 | 2020-03-26 | G | [5 empty] | 2020-05-12 | 2020-03-27 | 2020-12-16 | 2020-10-20 | G | [10 empty] | 2021-02-18 | 2020-12-29 | 2021-04-08 | 2021-01-15 | G | 2021-04-09 |  | 2021-06-30 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.2103
2292 | 112311 | BELMONT FERRY FARM TRAIL -- PHASE VI | 0097 | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Stafford County | FREDERICKSBURG | Fredericksburg | Fredericksburg:Stafford County | Local Assistance Division | Catherine C Coffey | Catherine.Coffey@vdot.virginia.gov | (540) 899-4280 | Jessica Graves | Jessica.Graves@vdot.virginia.gov | (540) 899-4267 | Jim Pickens | JPickens@staffordcountyva.gov | (540) 658-4506 | 0 |  | 0 | FY2022 | 2515944 | 2515944 | ACTIVITY DATES SET | R | Start Purchasing Right-of-Way milestone is 275 days past the expected completion date | G | Project is on budget | 2017-08-01 | 2017-08-01 | 2017-10-05 | 2017-10-05 | G | 2017-10-06 | 2017-10-06 | 2017-10-18 | 2017-10-18 | G | 2017-10-19 | 2017-10-19 | 2019-03-20 | 2019-03-20 | G | [10 empty] | 2020-05-04 |  | 2020-05-22 |  | R | [5 empty] | 2020-05-27 |  | 2021-05-26 |  | G | [10 empty] | 2021-09-22 |  | 2022-01-21 |  | G | 2022-03-08 |  | 2022-05-31 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.2848
2293 | 112655 | RECREATIONAL ACCESS TO WESTMORELAND RECREATION COMPLEX | 0000 | Secondary | New Construction Roadway | Locally | Westmoreland County | NORTHERN NECK | Fredericksburg | NonMPO:NonMPO | Local Assistance Division | William C White | Carter.White@VDOT.Virginia.gov | (804) 333-7942 | William C White | Carter.White@VDOT.Virginia.gov | (804) 333-7942 | Norm Risavi | nrisavi@westmoreland-county.org | (804) 493-0130 | 0 |  | 0 | FY2020 | 920000 | 920000 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 306 days early | Y | Estimate not current | 2018-09-04 | 2018-02-27 | 2018-11-30 | 2018-03-01 | G | 2018-12-03 | 2018-12-03 | 2018-12-05 | 2018-12-03 | G | 2018-12-06 | 2018-12-06 | 2019-06-13 | 2018-12-06 | G | [35 empty] | 2019-12-26 | 2019-02-08 | 2020-01-27 | 2019-02-08 | G | 2020-01-28 | 2019-02-08 | 2020-03-09 | 2019-05-08 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.1629
2294 | 113183 | COMMONWEALTH DRIVE / DOMINION DRIVE SIDEWALKS | 0852 | Secondary | Facilities for Pedestrians and Bicycles | Locally | Albemarle County | CHARLOTTESVILLE | Culpeper | Charlottesville:Albemarle County | Local Assistance Division | Ken Connors |  |  | Thomas Fitzpatrick | Thomas.Fitzpatrick@vdot.virginia.gov |  | JACK KELSEY |  |  | 0 |  | 0 | FY2023 | 3336224 | 3336224 | ACTIVITY DATES SET | R | Start Purchasing Right-of-Way milestone is 355 days past the expected completion date | G | Project is on budget | 2019-03-18 | 2018-08-01 | 2019-06-10 | 2018-08-21 | G | 2019-06-11 | 2018-11-01 | 2019-06-13 | 2018-11-27 | G | 2019-06-14 | 2018-11-01 | 2019-12-20 | 2018-11-30 | G | [10 empty] | 2019-12-04 |  | 2020-03-03 |  | R | [5 empty] | 2020-04-15 |  | 2022-01-21 |  | G | [10 empty] | 2022-03-22 |  | 2022-04-18 |  | G | 2022-07-07 |  | 2022-07-07 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.32312
2295 | 113462 | Euclid Road Sidewalk- Phase II | 0000 | Urban | Facilities for Pedestrians and Bicycles | Locally | Virginia Beach | NORFOLK | Hampton Roads | Hampton Roads:Virginia Beach | Local Assistance Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Marci Thompson | Marci.Thompson@vdot.virginia.gov | (757) 956-3093 | Katie Shannon | kshannon@vbgov.com | (757) 385-1514 | 0 |  | 0 | FY2022 | 398877 | 398877 | NO DATES SET YET-PE OPEN | R | Determine Requirements milestone is 591 days past the expected completion date | G | Project is on budget | 2018-10-01 | 2018-10-01 | 2018-12-28 | 2019-04-04 | R | 2018-12-31 | 2019-04-10 | 2019-01-03 | 2019-04-25 | R | 2019-01-04 | 2019-04-26 | 2019-07-11 |  | R | [10 empty] | 2020-05-06 |  | 2020-05-27 |  | R | [5 empty] | 2020-05-29 |  | 2021-03-12 |  | Y | 2019-08-16 |  | 2020-04-23 |  | R | [5 empty] | 2021-03-30 |  | 2021-04-26 |  | G | 2021-07-15 |  | 2021-07-15 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.094284
2296 | 113632 | Route 60 (Pocahontas Trail) Intersection Lighting | 0060 | Primary | Safety | VDOT | York County | WILLIAMSBURG | Hampton Roads | Hampton Roads:York County | Infrastructure Investment Division | Hayden Hill | Hayden.Hill@volkert.com | (703) 642-8100 | Mark S Winslow | Mark.Winslow@VDOT.Virginia.gov | (757) 925-1528 |  |  |  | 0 |  | 0 | FY2025 | 134695 | 134695 | NO DATES SET YET | G | Start Development milestone is 617 days ahead of the expected completion date | G | Project is on budget | [5 empty] | 2022-10-18 |  | 2022-10-31 |  | G | 2022-11-01 |  | 2023-06-27 |  | G | [5 empty] | 2024-03-07 |  | 2024-04-17 |  | G | [5 empty] | 2024-08-01 |  | 2024-11-25 |  | G | [5 empty] | 2024-07-17 |  | 2024-10-16 |  | G | [5 empty] | 2024-12-10 |  | 2024-12-10 |  | G | 2025-03-06 |  | 2025-03-06 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.10318
2297 | 113718 | #SGR19LP - Virginia Beach Blvd Eastbound Mill and Overlay | 0058 | Urban | Resurfacing | Locally | Virginia Beach | NORFOLK | Hampton Roads | Hampton Roads:Virginia Beach | Infrastructure Investment Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Marci Thompson | Marci.Thompson@vdot.virginia.gov | (757) 956-3093 | Katie Shannon, P.E. | kshannon@vbgov.com | (757) 385-1514 | 0 |  | 1 | FY2019 | 558000 | 558000 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 245 days early | G | Project is on budget | 2018-09-04 | 2018-09-04 | 2018-11-30 | 2018-10-23 | G | 2018-12-03 | 2018-10-24 | 2018-12-05 | 2018-10-25 | G | 2018-12-06 | 2018-10-25 | 2019-06-13 | 2018-10-25 | G | [35 empty] | 2019-04-10 | 2018-10-25 | 2019-05-07 | 2018-10-25 | G | 2019-06-28 | 2018-10-26 | 2019-06-28 | 2018-10-26 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.090661
2298 | 113807 | #SGR21VB - RT 1470 CULVERT REPLACE, ID 23928 | 1470 | Secondary | Bridge Replacement w/o Added Capacity | VDOT | Spotsylvania County | FREDERICKSBURG | Fredericksburg | Fredericksburg:Spotsylvania County | Infrastructure Investment Division | Annette F Adams | Annette.Adams@VDOT.Virginia.gov | (540) 372-3583 | Sylvester C Okpala | Sylvester.Okpala@VDOT.Virginia.gov | (540) 907-8174 | Paul Agnello | pagnello@spotsylvania.va.us | (540) 507-7398 | 0 |  | 0 | FY2021 | 2800000 | 1741000 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 11 days early | G | Project is on budget | [5 empty] | 2018-08-09 | 2018-08-09 | 2018-08-10 | 2018-08-10 | G | 2018-08-13 | 2018-09-25 | 2019-03-22 | 2019-02-27 | G | [5 empty] | 2019-02-25 | 2019-02-25 | 2019-03-04 | 2019-03-04 | G | 2019-04-19 | 2019-03-21 | 2019-05-02 | 2019-03-26 | G | 2019-11-15 | 2017-09-06 | 2020-03-30 | 2020-03-19 | G | 2019-05-17 | 2019-05-29 | 2019-11-14 | 2019-11-12 | G | [10 empty] | 2020-04-14 | 2020-04-07 | 2020-04-14 | 2020-04-07 | G | 2020-07-06 | 2020-06-25 | 2020-07-06 | 2020-06-25 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.059711
2299 | 115372 | Transportation Information and Decision Support System |  | Urban | Traffic Management/Engineering | Locally | Norfolk | NORFOLK | Hampton Roads | Hampton Roads:Norfolk | Infrastructure Investment Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Derrick Williams | Derrick.Williams@vdot.virginia.gov | (757) 956-3097 | Rob Brown | Robert.Brown@norfolk.gov | (757) 664-7305 | 0 |  | 0 | FY2027 | 800000 | 800000 | NO DATES SET YET | G | Agreement with Locality milestone is 1432 days ahead of the expected completion date | Y | Estimate not current | 2024-10-23 |  | 2025-01-23 |  | G | 2025-01-24 |  | 2025-01-28 |  | G | 2025-01-29 |  | 2025-08-01 |  | G | [25 empty] | 2025-09-09 |  | 2026-05-15 |  | G | [5 empty] | 2026-08-20 |  | 2026-09-17 |  | G | 2026-12-10 |  | 2026-12-10 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.40942
2300 | 115403 | #SMART20 - Roundabout for Darvills Rd at Military Rd | 0040 | Primary | Safety | VDOT | Nottoway County | PETERSBURG | Richmond | NonMPO:NonMPO | Infrastructure Investment Division | Roy Soto | Roy.Soto@vdot.virginia.gov | (804) 609-5239 | Roy Soto | Roy.Soto@vdot.virginia.gov | (804) 609-5239 |  |  |  | 1 | 2020 | 0 | FY2028 | 7267500 | 7267500 | NO DATES SET YET-PE OPEN | G | Start Development milestone finished 1093 days early | G | Project is on budget | [5 empty] | 2023-09-01 | 2020-09-14 | 2023-09-15 | 2020-09-17 | G | 2023-09-18 |  | 2024-08-14 |  | G | [5 empty] | 2025-06-20 |  | 2025-07-03 |  | G | 2026-10-08 |  | 2026-10-22 |  | G | 2027-03-24 |  | 2027-09-24 |  | G | 2026-11-09 |  | 2027-05-19 |  | G | 2026-03-31 |  | 2026-10-01 |  | G | [5 empty] | 2027-10-12 |  | 2027-10-12 |  | G | 2028-01-07 |  | 2028-01-07 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.05942
2301 | 116270 | #I81CIP NB EXIT 291 EXTEND ACCELERATION LANE (ID #46) | 0081 | Interstate | Reconstruction w/o Added Capacity | VDOT | Shenandoah County | EDINBURG | Staunton | NonMPO:NonMPO | Infrastructure Investment Division | John-Allen L Ennis | JohnAllen.Ennis@VDOT.Virginia.gov | (540) 332-9118 | Timothy Gregory | Tim.Gregory@vdot.virginia.gov | (540) 332-7891 |  |  |  | 0 |  | 0 | FY2022 | 3392569 | 1204133 | ADVERTISED | G | Solicit Bids milestone finished 91 days early | G | Project is on budget | [5 empty] | 2020-07-01 | 2020-01-21 | 2020-07-15 | 2020-02-03 | G | 2020-07-16 | 2020-02-04 | 2021-06-14 | 2020-05-15 | G | [5 empty] | 2020-05-18 | 2020-05-18 | 2020-07-14 | 2020-07-14 | G | 2020-10-30 | 2020-10-30 | 2020-10-30 | 2020-10-30 | G | 2020-09-03 | 2020-09-03 | 2020-09-03 | 2020-09-03 | G | 2020-10-30 | 2020-10-30 | 2020-10-30 | 2020-10-30 | G | 2020-10-09 | 2020-09-24 | 2021-02-09 | 2020-09-24 | G | [5 empty] | 2021-03-09 | 2020-12-08 | 2021-03-09 | 2020-12-08 | G | 2021-05-27 |  | 2021-07-09 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.064112
2302 | 117051 | N Parham Road Sidewalk | 7518 | Secondary | Facilities for Pedestrians and Bicycles | Locally | Henrico County | ASHLAND | Richmond | Richmond:Henrico County | Local Assistance Division | Cindy Crouch |  |  | Cynthia Crouch | Cynthia.Crouch@vdot.virginia.gov | (804) 609-5313 | TBD |  | TBD | 0 |  | 0 | FY2029 | 790050 | 790050 | NO DATES SET YET | G | Agreement with Locality milestone is 1543 days ahead of the expected completion date | G | Project is on budget | 2025-01-06 |  | 2025-05-14 |  | G | 2025-05-15 |  | 2025-06-05 |  | G | 2025-12-15 |  | 2026-04-10 |  | G | [10 empty] | 2027-07-30 |  | 2027-09-02 |  | G | [5 empty] | 2027-09-03 |  | 2028-02-09 |  | G | 2028-01-05 |  | 2028-06-05 |  | G | [5 empty] | 2028-05-12 |  | 2028-06-09 |  | G | 2028-08-29 |  | 2028-08-29 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.34909
2303 | 118306 | MOUNT VERNON AVENUE BRIDGE REPLACEMENT | 6591 | Urban | Bridge Replacement w/o Added Capacity | Locally | Multi-jurisdictional: Northern Virginia MPO |  | Northern Virginia | Northern Virginia:Multi-jurisdictional: Northern Virginia MPO | Local Assistance Division | Andrew G Beacher | Andrew.Beacher@vdot.virginia.gov | (703) 259-2239 | Robert J Strevell | Robert.Strevell@vdot.virginia.gov | (703) 259-1988 | Alan McDonald | amcdonald@arlingtonva.us | (703) 228-1861 | 0 |  | 0 | FY2027 | 30000000 | 30000000 | NO DATES SET YET | G | Agreement with Locality milestone is 190 days ahead of the expected completion date | G | Project is on budget | 2021-02-01 |  | 2021-08-30 |  | G | 2021-08-31 |  | 2021-09-21 |  | G | 2022-04-05 |  | 2022-12-07 |  | G | [10 empty] | 2025-03-12 |  | 2025-04-15 |  | G | [5 empty] | 2025-04-16 |  | 2025-11-03 |  | G | 2025-02-11 |  | 2025-10-10 |  | G | [5 empty] | 2026-02-12 |  | 2026-04-09 |  | G | 2026-06-29 |  | 2026-08-24 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.26977
2304 | 82892 | RTE 618 - RECONSTRUCTION | 0618 | Secondary | Reconstruction w/o Added Capacity | VDOT | Charles City County | ASHLAND | Richmond | Richmond:Charles City County | Infrastructure Investment Division | Thomas Kendrick | Thomas.Kendrick@vdot.virginia.gov | (804) 609-5281 | Lawrence Ramsey | Brian.Ramsey@VDOT.Virginia.gov | (804) 585-3579 |  |  |  | 0 |  | 0 | FY2021 | 1533062 | 1533062 | AWARDED | G | Start Delivery milestone finished 76 days early | G | Project is on budget | [5 empty] | 2011-04-01 | 2011-12-29 | 2012-03-31 | 2013-05-31 | R | 2014-11-03 | 2016-09-01 | 2018-03-16 | 2018-03-16 | G | [5 empty] | 2018-08-15 | 2018-05-22 | 2018-08-28 | 2018-08-08 | G | 2019-06-27 | 2019-05-23 | 2019-07-11 | 2019-06-24 | G | 2020-03-09 | 2019-11-07 | 2020-09-09 | 2019-11-07 | G | 2019-07-29 | 2019-07-19 | 2020-02-06 | 2019-11-05 | G | 2019-12-09 | 2019-04-10 | 2020-06-12 | 2019-04-10 | G | [5 empty] | 2020-09-08 | 2020-09-08 | 2020-09-08 | 2020-09-08 | G | 2020-12-02 | 2020-11-17 | 2021-02-01 | 2020-11-17 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.14451
2305 | 98957 | #SGR19VB - RT 696 Selma Lowmr Rd Over Karnes Ck Fed-1195 | 0696 | Secondary | Bridge Replacement w/o Added Capacity | VDOT | Alleghany County | LEXINGTON | Staunton | NonMPO:NonMPO | Infrastructure Investment/Asset Management Division | Rex L Pearce | Rex.Pearce@vdot.virginia.gov | (540) 332-9104 | James T Johnston | james.johnston@VDOT.virginia.gov | (540) 332-7795 |  |  |  | 0 |  | 0 | FY2020 | 3422113 | 4432220 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 50 days early | R | Project estimate is less than $5M and is 20% or more over budget | [5 empty] | 2012-07-02 | 2012-07-01 | 2012-07-02 | 2012-07-02 | G | 2013-01-15 | 2013-01-15 | 2017-11-14 | 2017-11-14 | G | [5 empty] | 2017-05-01 | 2017-05-01 | 2017-05-15 | 2017-05-15 | G | 2017-05-17 | 2017-05-17 | 2017-06-14 | 2017-06-14 | G | 2018-10-04 | 2018-09-26 | 2019-04-10 | 2019-04-02 | G | 2017-07-25 | 2017-07-25 | 2018-10-04 | 2018-10-02 | G | 2018-03-26 | 2018-03-26 | 2018-12-26 | 2018-09-12 | G | [5 empty] | 2019-07-11 | 2019-07-11 | 2019-08-13 | 2019-08-13 | G | 2019-10-17 | 2019-11-13 | 2020-01-02 | 2019-11-13 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.060771
2306 | 101495 | Route 671 over Nottoway River and Nottoway River ( Two Struc | 0671 | Secondary | Bridge Replacement w/o Added Capacity | VDOT | Southampton County | FRANKLIN | Hampton Roads | NonMPO:NonMPO | Infrastructure Investment Division | Christopher E Eggleston | Christopher.Eggleston@vdot.virginia.gov | (757) 857-8955 | Miranda S Kidd | miranda.kidd@vdot.virginia.gov | (757) 956-3342 |  |  |  | 0 |  | 0 | FY2020 | 12741664 | 9646619 | CONSTRUCTION STARTED | R | Relocate Utilities milestone is 632 days past the expected completion date | G | Project is on budget | [5 empty] | 2011-06-01 | 2011-10-19 | 2011-12-30 | 2011-10-19 | G | 2011-11-30 | 2011-10-25 | 2012-01-31 | 2012-01-31 | G | [10 empty] | 2018-01-16 | 2018-08-06 | 2018-06-29 | 2018-08-07 | R | 2018-12-06 |  | 2019-05-31 |  | R | 2018-07-05 | 2018-08-10 | 2018-12-05 | 2019-04-03 | R | 2018-01-23 | 2018-01-23 | 2018-06-21 | 2019-04-17 | R | [5 empty] | 2019-06-07 | 2020-06-09 | 2019-07-09 | 2020-06-09 | R | 2019-08-28 | 2020-09-16 | 2019-10-23 | 2020-09-16 | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.15616
2307 | 105623 | Rosemont Road | 0000 | Urban | Reconstruction w/ Added Capacity | Locally | Virginia Beach | NORFOLK | Hampton Roads | Hampton Roads:Virginia Beach | Local Assistance Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Marci Thompson | Marci.Thompson@vdot.virginia.gov | (757) 956-3093 | Katie Shannon | kshannon@vbgov.com | (757) 385-1514 | 0 |  | 0 | FY2021 | 18541000 | 18541000 | ACTIVITY DATES SET | R | Complete Purchasing Right-of-Way milestone baseline missing | G | Project is on budget | [5 empty] | 2014-06-26 | 2014-06-26 | 2014-07-08 | 2014-07-08 | G | 2015-08-25 | 2014-07-01 | 2019-02-28 | 2018-10-22 | G | [10 empty] | 2016-05-06 | 2016-05-06 | 2016-06-20 | 2016-06-20 | G | [9 empty] | R | [10 empty] | 2019-12-30 |  | 2020-01-31 |  | R | 2020-04-15 |  | 2020-08-20 |  | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.18642
2308 | 107462 | SCHOLASTIC WAY SIDEWALKS - C502 |  | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Augusta County | HARRISONBURG | Staunton | SAW:Augusta County | Local Assistance Division | Jeremy Mason |  |  | Michael S Fulcher | Michael.Fulcher@VDOT.Virginia.gov | (540) 332-2243 | Candy Hensley - Augusta County | chensley@co.augusta.va.us | (540) 245-5615 | 0 |  | 0 | FY2019 | 227905 | 262868 | CONSTRUCTION COMPLETED | R | Start Delivery milestone finished 154 days late | Y | Project estimate is less than $5M and is up to 20% over budget | 2015-05-01 | 2015-05-01 | 2015-07-27 | 2015-07-27 | G | 2015-07-28 | 2015-07-21 | 2015-08-10 | 2015-07-28 | G | 2015-08-11 | 2015-07-29 | 2016-04-08 | 2016-03-28 | G | [10 empty] | 2017-03-09 | 2017-03-09 | 2017-06-27 | 2017-06-27 | G | [20 empty] | 2018-02-28 | 2018-02-28 | 2018-07-05 | 2018-11-19 | R | 2018-07-06 | 2019-02-01 | 2018-09-28 | 2019-03-01 | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.35761
2309 | 109379 | #HB2.FY17 SOUTH MAIN ST & MLK WAY IMPROVEMENTS | 0000 | Urban | Reconstruction w/o Added Capacity | Locally | Harrisonburg | HARRISONBURG | Staunton | Harrisonburg:Harrisonburg | Infrastructure Investment Division | Michael S Fulcher | Michael.Fulcher@VDOT.Virginia.gov | (540) 332-2243 | Michael S Fulcher | Michael.Fulcher@VDOT.Virginia.gov | (540) 332-2243 | Tom Hartman | Tom.Hartman@harrisonburgva.gov | (540) 434-5928 | 1 | 2017 | 0 | FY2017 | 3174933 | 3692098 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 4 days early | Y | Project estimate is less than $5M and is up to 20% over budget | 2016-07-05 | 2016-07-05 | 2016-07-18 | 2016-07-18 | G | 2016-09-12 | 2016-09-12 | 2016-09-14 | 2016-09-14 | G | 2016-07-22 | 2016-07-22 | 2016-09-21 | 2016-09-21 | G | [10 empty] | 2016-11-01 | 2016-11-01 | 2016-11-01 | 2016-11-01 | G | [5 empty] | 2016-11-02 | 2016-11-02 | 2016-12-21 | 2016-12-21 | G | [10 empty] | 2016-12-23 | 2016-11-01 | 2016-12-30 | 2016-11-15 | G | 2017-01-03 | 2016-11-16 | 2017-02-14 | 2017-02-10 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.076684
2310 | 116005 | District-wide Flashing Yellow Arrows Installations | 9999 | Miscellaneous | Safety | VDOT | Culpeper District-wide |  | Culpeper | NonMPO:NonMPO | Infrastructure Investment/Asset Management Division | Gregory J Cooley | Gregory.Cooley@vdot.virginia.gov | (434) 906-7979 | Caroline Awua-Mensah | Caroline.Awua-Mensah@vdot.virginia.gov | (540) 829-7618 |  |  |  | 0 |  | 0 | FY2021 | 125664 | 125664 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 100 days early | G | Project is on budget | [5 empty] | 2020-06-04 | 2019-10-23 | 2020-06-04 | 2019-12-04 | G | 2020-06-05 | 2019-12-05 | 2020-09-14 | 2020-09-14 | G | [5 empty] | 2020-09-25 | 2020-09-25 | 2020-11-23 | 2020-11-23 | G | [25 empty] | 2021-02-03 | 2020-12-17 | 2021-03-24 | 2020-12-21 | G | 2021-03-25 | 2020-12-21 | 2021-03-31 | 2020-12-21 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | WORK/TASK ORDER | 1 | 0 | 0.10374
2311 | 116863 | UNIVERSITY BLVD EXTENSION |  | Urban | Reconstruction w/ Added Capacity | Locally | Harrisonburg | HARRISONBURG | Staunton | Harrisonburg:Harrisonburg | Local Assistance Division | Kimberly Cameron | Kim.Cameron@vdot.virginia.gov | (540) 332-7886 | Michael S Fulcher | Michael.Fulcher@VDOT.Virginia.gov | (540) 332-2243 | Tom Hartman | tom.hartman@harrisonburgva.gov | (540) 434-5928 | 0 |  | 0 | FY2025 | 9476558 | 9476558 | NO DATES SET YET | G | Agreement with Locality milestone is 107 days ahead of the expected completion date | G | Project is on budget | 2021-02-01 |  | 2021-06-08 |  | G | 2021-06-09 |  | 2021-06-29 |  | G | 2021-07-29 |  | 2021-11-22 |  | G | [10 empty] | 2023-03-20 |  | 2023-04-21 |  | G | [5 empty] | 2023-04-24 |  | 2023-09-20 |  | G | 2024-03-07 |  | 2024-08-02 |  | G | [5 empty] | 2024-07-12 |  | 2024-08-08 |  | G | 2024-10-29 |  | 2024-10-29 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.1144
2312 | 118065 | Lakeside Community Trail Phase 1 |  | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Henrico County | ASHLAND | Richmond | Richmond:Henrico County | Local Assistance Division | Jorg Huckabee-Mayfield | Jorg.Huckabee-Mayfield@VDOT.Virginia.gov | (804) 609-5292 | Jorg Huckabee-Mayfield | Jorg.Huckabee-Mayfield@VDOT.Virginia.gov | (804) 609-5292 | Michael Aust | aus019@henrico.us | (804) 501-4019 | 0 |  | 0 | FY2025 | 1823840 | 1823840 | NO DATES SET YET | G | Agreement with Locality milestone is 199 days ahead of the expected completion date | G | Project is on budget | 2021-05-03 |  | 2021-09-08 |  | G | 2021-09-09 |  | 2021-09-29 |  | G | 2022-04-13 |  | 2022-08-04 |  | G | [10 empty] | 2023-11-28 |  | 2024-01-03 |  | G | [5 empty] | 2024-01-04 |  | 2024-06-04 |  | G | 2024-05-01 |  | 2024-09-27 |  | G | [5 empty] | 2024-09-06 |  | 2024-10-03 |  | G | 2024-12-27 |  | 2024-12-27 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.4379
2313 | 51194 | RTE 768 - SURF TRT NON-HRDSURF RD | 0768 | Secondary | Reconstruction w/o Added Capacity | VDOT | Floyd County | CHRISTIANSBURG | Salem | NonMPO:NonMPO | Infrastructure Investment Division | Robert P Williams | Robbie.Williams@VDOT.Virginia.gov | (276) 229-9954 | Audra Parson | Audra.Parson@vdot.virginia.gov | (540) 951-3727 |  |  |  | 0 |  | 0 | FY2023 | 1176925 | 1176925 | NO DATES SET YET-PE OPEN | G | Start Development milestone finished 863 days early | G | Project is on budget | [5 empty] | 2021-04-13 | 2019-05-01 | 2021-10-13 | 2019-06-03 | G | 2021-10-19 | 2019-06-06 | 2021-11-30 |  | G | [10 empty] | 2022-04-01 |  | 2022-04-01 |  | G | [20 empty] | 2022-12-19 |  | 2022-12-19 |  | G | 2022-12-20 |  | 2023-06-28 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | SAAP CONTRACT | 0 | 0 | 0.10725
2314 | 97708 | RTE 684 OVER GOOSE CREEK (STR 2808) - BRIDGE REPL | 0684 | Secondary | Bridge Replacement w/o Added Capacity | VDOT | Bedford County | BEDFORD | Salem | NonMPO:NonMPO | Infrastructure Investment Division | Anthony T Marshall | Todd.Marshall@VDOT.Virginia.gov | (540) 387-5460 | Anthony L Handy | Tony.Handy@VDOT.Virginia.gov | (540) 352-9050 |  |  |  | 0 |  | 0 | FY2019 | 4110813 | 2700736 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 87 days early | G | Project is on budget | [5 empty] | 2010-07-20 | 2010-08-26 | 2010-08-20 | 2010-08-26 | R | 2014-12-01 | 2014-11-28 | 2017-05-05 | 2017-05-05 | G | [5 empty] | 2015-10-12 | 2015-10-12 | 2015-11-12 | 2015-11-12 | G | 2016-08-31 | 2016-08-31 | 2016-09-16 | 2016-09-16 | G | 2017-07-31 | 2017-07-07 | 2018-07-10 | 2018-07-06 | G | 2016-12-23 | 2016-12-23 | 2017-06-07 | 2017-06-07 | G | 2017-03-22 | 2017-03-22 | 2018-07-10 | 2018-03-14 | G | [5 empty] | 2018-06-14 | 2018-07-10 | 2018-07-10 | 2018-07-10 | G | 2018-08-01 | 2018-09-07 | 2018-12-03 | 2018-09-07 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.099556
2315 | 99478 | #HB2.FY17 RTE 7 CORRIDOR IMPROVEMENTS - PHASE 1 and PHASE 2 | 0007 | Primary | Reconstruction w/ Added Capacity | VDOT | Fairfax County | FAIRFAX | Northern Virginia | Northern Virginia:Fairfax County | Infrastructure Investment Division | Terry Yates | Terry.Yates@vdot.virginia.gov | (703) 259-2118 | Md A Rahman | MD.Rahman@VDOT.Virginia.gov | (703) 259-1940 | Tom Biesiadny | Tom.Biesiadny@fairfaxcounty.go | (703) 877-5663 | 1 | 2017 | 0 | FY2019 | 135871738 | 135871738 | CONSTRUCTION STARTED | G | Engage Public milestone finished on-time | G | Project is on budget | 2016-11-01 | 2016-11-01 | 2017-02-28 | 2017-02-27 | G | 2016-09-30 | 2016-09-23 | 2016-09-30 | 2016-09-23 | G | 2016-09-26 | 2016-09-26 | 2017-07-13 | 2017-10-24 | R | [5 empty] | 2018-07-18 | 2018-07-18 | 2018-11-15 | 2018-11-15 | G | 2017-11-21 | 2017-11-21 | 2017-11-21 | 2017-11-21 | G | [20 empty] | 2017-11-21 | 2017-11-21 | 2017-11-21 | 2017-11-21 | G | 2017-11-21 | 2017-11-21 | 2018-07-18 | 2018-07-18 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | DESIGN BUILD/PPTA | 1 | 1 | 0.20064
2316 | 104944 | #SGR17VB - RT 29-REPL BR & APPR / STA RV. & NSRR(Fed 30097) | 0029 | Primary | Bridge Replacement w/o Added Capacity | VDOT | Altavista | APPOMATTOX | Lynchburg | NonMPO:NonMPO | Infrastructure Investment/Asset Management Division | Brian J Casto | Brian.Casto@VDOT.Virginia.gov | (434) 856-8276 | Lindsey S Hodges | Lindsey.Hodges@vdot.virginia.gov | (434) 856-8143 |  |  |  | 0 |  | 1 | FY2019 | 28388031 | 28171346 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 77 days early | G | Project is on budget | [5 empty] | 2015-07-01 | 2013-07-09 | 2015-07-01 | 2013-07-09 | G | 2013-07-31 | 2013-07-31 | 2015-06-12 | 2015-06-12 | G | [5 empty] | 2016-06-01 | 2016-06-01 | 2016-09-20 | 2016-09-20 | G | 2017-07-05 | 2017-07-05 | 2017-07-05 | 2017-07-05 | G | 2018-04-06 | 2018-04-06 | 2018-08-06 | 2018-08-01 | G | 2017-07-13 | 2017-07-13 | 2018-01-25 | 2018-01-25 | G | 2017-03-21 | 2017-03-21 | 2018-03-01 | 2018-03-01 | G | [5 empty] | 2018-08-20 | 2018-09-11 | 2018-09-11 | 2018-09-11 | G | 2018-12-20 | 2018-12-05 | 2019-02-20 | 2018-12-05 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.08263
2317 | 107187 | RICHMOND HIGHWAY CORRIDOR IMPROVEMENTS | 0001 | Primary | Reconstruction w/ Added Capacity | VDOT | Fairfax County | FAIRFAX | Northern Virginia | Northern Virginia:Fairfax County | Infrastructure Investment Division | Terry Yates | Terry.Yates@vdot.virginia.gov | (703) 259-2118 | E Daniel Reinhard | Dan.Reinhard@vdot.virginia.gov | (703) 259-2599 | Ajmal Hamidi | Ajmal.Hamidi@fairfaxcounty.gov | (703) 877-5828 | 0 |  | 0 | FY2022 | 414924741 | 414924741 | NO DATES SET YET-PE OPEN | R | Determine Requirements milestone is 1637 days past the expected completion date | G | Project is on budget | [5 empty] | 2015-07-15 | 2015-08-18 | 2015-07-28 | 2015-08-18 | R | 2015-07-29 | 2016-06-22 | 2016-08-29 |  | R | [5 empty] | 2017-08-11 | 2019-03-27 | 2017-08-24 | 2020-05-07 | R | 2019-07-10 |  | 2019-07-23 |  | R | 2020-09-22 |  | 2021-03-29 |  | G | 2019-08-08 |  | 2020-02-19 |  | R | 2018-11-09 | 2016-01-19 | 2019-11-12 | 2016-01-20 | G | [5 empty] | 2021-07-28 |  | 2021-07-28 |  | G | 2021-09-09 |  | 2021-09-29 |  | G | Preliminary design and/or investigations are still underway | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.1295
2318 | 108460 | NEW TRAFFIC SIGNALS III | 9999 | Urban | Traffic Management/Engineering | Locally | Falls Church | FAIRFAX | Northern Virginia | Northern Virginia:Falls Church | Local Assistance Division | Terry Yates | Terry.Yates@vdot.virginia.gov | (703) 259-2118 | Rita Hockman | Rita.Hockman@vdot.virginia.gov | (804) 824-7421 | Tara Puzin, P.E. | tpuzin@fallschurchva.gov | (703) 405-0175 | 0 |  | 0 | FY2019 | 750000 | 989162 | CONSTRUCTION STARTED | R | Start Delivery milestone finished 199 days late | R | Project estimate is less than $5M and is 20% or more over budget | 2016-08-01 | 2016-08-01 | 2016-10-25 | 2016-10-25 | G | 2016-10-26 | 2016-10-26 | 2016-10-28 | 2016-10-28 | G | 2016-10-31 | 2016-10-31 | 2017-05-10 | 2017-05-25 | R | [10 empty] | 2018-03-08 | 2018-03-08 | 2018-03-28 | 2018-03-28 | G | [5 empty] | 2018-03-30 | 2018-03-30 | 2019-01-09 | 2019-01-02 | G | [10 empty] | 2019-01-29 | 2019-01-22 | 2019-02-26 | 2019-02-26 | G | 2019-02-27 | 2019-02-27 | 2019-04-08 | 2019-10-24 | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.41684
2319 | 109816 | BICYCLE SHARING INITIATIVE- PURCHASE/INSTALL BIKE STATIONS | 9999 | Urban | Facilities for Pedestrians and Bicycles | Locally | Alexandria | FAIRFAX | Northern Virginia | Northern Virginia:Alexandria | Infrastructure Investment Division | Terry Yates | Terry.Yates@vdot.virginia.gov | (703) 259-2118 | Rhoderick M Undan | Rhoderick.Undan@vdot.virginia.gov | (703) 259-3347 | Vicki Caudullo | victoria.caudullo@alexandriava.gov | (703) 746-4160 | 0 |  | 0 | FY2021 | 699345 | 1636356 | ACTIVITY DATES SET | R | Solicit Bids milestone is 387 days past the expected completion date | R | Project estimate is less than $5M and is 20% or more over budget | 2017-07-17 | 2017-07-17 | 2017-12-28 | 2017-12-28 | G | 2018-01-03 | 2018-01-03 | 2018-01-05 | 2018-01-05 | G | 2018-01-08 | 2018-01-08 | 2019-03-29 | 2019-03-29 | G | [35 empty] | 2019-08-20 |  | 2020-01-31 |  | R | 2020-02-03 |  | 2020-07-31 |  | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.21844
2320 | 109995 | Whites Mill Renovation | 9999 | Primary | Facilities for Pedestrians and Bicycles | Locally | Washington County | ABINGDON | Bristol | NonMPO:NonMPO | Local Assistance Division | Tabitha H Crowder | Tabitha.Crowder@vdot.virginia.gov | (276) 696-3482 | Tabitha H Crowder | Tabitha.Crowder@vdot.virginia.gov | (276) 696-3482 | Scott McCoy | smccoy@mrpdc.org | (276) 783-5103 | 0 |  | 0 | FY2019 | 31094 | 28576 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 46 days early | G | Project is on budget | 2016-09-13 | 2016-09-13 | 2016-12-09 | 2016-12-09 | G | [5 empty] | 2016-09-13 | 2016-09-13 | 2016-09-26 | 2016-09-26 | G | [35 empty] | 2017-04-11 | 2019-02-28 | 2017-05-08 | 2019-03-15 | R | 2019-04-15 | 2019-03-18 | 2019-06-10 | 2019-04-25 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.13856
2322 | 111164 | BROAD ST PEDESTRIAN HYBRID BEACON |  | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Richmond | ASHLAND | Richmond | Richmond:Richmond | Local Assistance Division | Jorg Huckabee-Mayfield | Jorg.Huckabee-Mayfield@VDOT.Virginia.gov | (804) 609-5292 | Jorg Huckabee-Mayfield | Jorg.Huckabee-Mayfield@VDOT.Virginia.gov | (804) 609-5292 | Jian Xu | jian.xu@richmondgov.com | (804) 646-5402 | 0 |  | 0 | FY2022 | 200558 | 200558 | ACTIVITY DATES SET | R | Solicit Bids milestone is 23 days past the expected completion date | G | Project is on budget | 2017-10-02 | 2017-10-02 | 2017-12-29 | 2017-10-02 | G | 2018-01-02 | 2018-07-16 | 2018-01-04 | 2018-07-25 | R | 2018-01-05 | 2020-03-12 | 2018-07-12 | 2020-04-16 | R | [10 empty] | 2020-05-18 | 2020-05-15 | 2020-06-03 | 2020-05-15 | G | [5 empty] | 2020-06-05 | 2020-05-15 | 2020-06-05 | 2020-05-15 | G | 2020-05-18 | 2020-05-29 | 2020-12-18 | 2020-05-29 | G | [5 empty] | 2021-01-29 |  | 2021-01-29 |  | R | 2021-02-01 |  | 2021-07-28 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.35132
2323 | 111695 | Route 460 and Route 226 Intersection improvement | 0460 | Primary | Reconstruction w/o Added Capacity | VDOT | Dinwiddie County | PETERSBURG | Richmond | Tri-Cities:Dinwiddie County | Infrastructure Investment Division | Dianna M Bryant | Dianna.Bryant@VDOT.Virginia.gov | (804) 863-4004 | Dianna M Bryant | Dianna.Bryant@VDOT.Virginia.gov | (804) 863-4004 |  |  |  | 0 |  | 0 | FY2029 | 1800000 | 1800000 | NO DATES SET YET | G | Start Development milestone is 1251 days ahead of the expected completion date | Y | Estimate not current | [5 empty] | 2024-07-15 |  | 2024-07-26 |  | G | 2024-07-29 |  | 2025-06-25 |  | G | [5 empty] | 2026-05-01 |  | 2026-05-14 |  | G | 2027-08-19 |  | 2027-09-01 |  | G | 2028-02-02 |  | 2028-08-04 |  | G | 2027-09-20 |  | 2028-03-30 |  | G | 2027-02-09 |  | 2027-08-12 |  | G | [5 empty] | 2028-08-08 |  | 2028-08-08 |  | G | 2028-11-13 |  | 2029-01-11 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.077924
2324 | 111714 | #SMART18 - Cogbill/Hopkins/Chippenham - Park and Ride Lot | 0638 | Secondary | Other | Locally | Chesterfield County | CHESTERFIELD | Richmond | Richmond:Chesterfield County | Infrastructure Investment Division | Michael S Gray | Mike.Gray@vdot.virginia.gov | (804) 609-5347 | Michael S Gray | Mike.Gray@vdot.virginia.gov | (804) 609-5347 | Chessa Faulkner | faulknerc@chesterfield.gov | 7481037 | 1 | 2018 | 0 | FY2023 | 2945000 | 2945000 | ACTIVITY DATES SET | Y | Start Purchasing Right-of-Way milestone is 8 days ahead of the expected completion date and there is a risk of missing this milestone date | G | Project is on budget | 2019-07-01 | 2018-09-28 | 2019-09-24 | 2018-10-23 | G | 2019-09-25 | 2018-11-22 | 2021-09-30 | 2018-11-28 | G | 2019-09-30 | 2018-11-29 | 2020-04-09 | 2020-04-06 | G | [5 empty] | 2021-01-19 | 2021-01-15 | 2021-01-19 | 2021-01-15 | G | 2021-01-20 |  | 2021-03-01 |  | Y | 2021-10-01 |  | 2022-03-30 |  | G | 2021-03-16 |  | 2021-09-30 |  | G | 2021-10-01 |  | 2022-03-04 |  | G | [5 empty] | 2022-04-22 |  | 2022-05-31 |  | G | 2022-07-14 |  | 2022-09-30 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.24386
2325 | 113130 | FY19 RS - Reconstruct Curb, Gutter and Sidewalks | 0000 | Urban | Reconstruction w/o Added Capacity | Locally | Blacksburg | CHRISTIANSBURG | Salem | New River Valley:Blacksburg | Local Assistance Division | Adam J Czesnowski | Adam.Czesnowski@vdot.virginia.gov | (540) 541-1216 | Adam J Czesnowski | Adam.Czesnowski@vdot.virginia.gov | (540) 541-1216 | Randy Formica | rformica@blacksburg.gov | (540) 961-1121 | 0 |  | 0 | FY2020 | 120000 | 120000 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 399 days early | G | Project is on budget | 2018-08-01 | 2018-08-01 | 2018-10-25 | 2018-08-21 | G | 2018-10-26 | 2018-08-30 | 2018-10-30 | 2018-08-30 | G | 2018-10-31 | 2018-09-27 | 2019-08-01 | 2018-09-27 | G | [35 empty] | 2019-06-04 | 2018-10-03 | 2019-07-01 | 2018-10-03 | G | 2019-11-25 | 2018-10-04 | 2019-11-25 | 2018-10-22 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.15848
2326 | 113333 | Blue Ridge Road Path Phase 2B - Glasgow | 0684 | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Glasgow | LEXINGTON | Staunton | NonMPO:NonMPO | Infrastructure Investment Division | David C Morris | David.Morris2@VDOT.Virginia.gov | (540) 332-8607 | Michael S Fulcher | Michael.Fulcher@VDOT.Virginia.gov | (540) 332-2243 | Heather Ryan | hryan@glasgowvirginia.org | (540) 258-2246 | 0 |  | 0 | FY2020 | 257009 | 284609 | CONSTRUCTION STARTED | R | Start Delivery milestone finished 103 days late | Y | Project estimate is less than $5M and is up to 20% over budget | 2018-10-31 | 2018-10-31 | 2019-01-31 | 2019-05-24 | R | [5 empty] | 2018-10-31 | 2018-10-31 | 2019-05-10 | 2019-05-10 | G | [35 empty] | 2019-10-01 | 2019-10-01 | 2020-01-14 | 2019-10-30 | G | 2020-04-06 | 2020-07-31 | 2020-05-22 | 2020-09-02 | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.34409
2327 | 113442 | Route 36 Resurfacing, City of Petersburg | 0036 | Urban | Resurfacing | VDOT | Petersburg | PETERSBURG | Richmond | Tri-Cities:Petersburg | Local Assistance Division | James Shepherd | James.Shepherd@vdot.virginia.gov | (804) 609-5305 | James Shepherd | James.Shepherd@vdot.virginia.gov | (804) 609-5305 | Bill Riggleman | bill@petersburg-va.org | (804) 993-1927 | 0 |  | 1 | FY2019 | 537004 | 537004 | AWARDED | G | Start Delivery milestone finished 34 days early | G | Project is on budget | [10 empty] | 2019-01-02 | 2018-12-10 | 2019-01-08 | 2019-01-02 | G | [35 empty] | 2019-05-15 | 2019-03-12 | 2019-05-15 | 2019-03-12 | G | 2019-05-16 | 2019-03-13 | 2019-05-28 | 2019-04-24 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.067605
2328 | 113818 | Regional EVP (Opticom) Project - Virginia Beach | 9999 | Urban | Traffic Management/Engineering | Locally | Virginia Beach | NORFOLK | Hampton Roads | Hampton Roads:Virginia Beach | Infrastructure Investment Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Marci Thompson | Marci.Thompson@vdot.virginia.gov | (757) 956-3093 | Katie Shannon, PE | kshannon@vbgov.com |  | 0 |  | 0 | FY2021 | 204000 | 204000 | NO DATES SET YET-PE OPEN | R | Determine Requirements milestone is 591 days past the expected completion date | G | Project is on budget | 2018-10-01 | 2018-12-01 | 2018-12-28 | 2019-04-02 | R | 2018-12-31 | 2019-04-10 | 2019-01-03 | 2019-04-16 | R | 2019-01-04 | 2019-04-17 | 2019-07-11 |  | R | [25 empty] | 2019-07-12 | 2020-04-21 | 2020-03-19 | 2020-04-21 | R | [5 empty] | 2020-05-21 |  | 2020-06-18 |  | R | 2020-09-08 |  | 2020-09-08 |  | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.24172
2329 | 113992 | CONSTRUCT SIDEWALKS ON SPOTSWOOD FURNACE ROAD | 0620 | Secondary | Safety | VDOT | Spotsylvania County | FREDERICKSBURG | Fredericksburg | Fredericksburg:Spotsylvania County | Infrastructure Investment Division | Peter A Hedrich | Peter.Hedrich@vdot.virginia.gov | (540) 899-4540 | Khalil Minhas | Khalil.Minhas@vdot.virginia.gov | (540) 374-3369 |  |  |  | 0 |  | 0 | FY2028 | 950000 | 950000 | NO DATES SET YET | G | Start Development milestone is 955 days ahead of the expected completion date | G | Project is on budget | [5 empty] | 2023-09-21 |  | 2023-10-04 |  | G | 2023-10-05 |  | 2024-05-14 |  | G | [5 empty] | 2025-01-23 |  | 2025-02-05 |  | G | 2026-01-23 |  | 2026-02-05 |  | G | 2026-08-26 |  | 2027-03-09 |  | G | 2026-02-24 |  | 2026-08-26 |  | G | 2025-07-18 |  | 2026-01-28 |  | G | [5 empty] | 2027-04-13 |  | 2027-04-13 |  | G | 2027-07-02 |  | 2027-07-02 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.068673
2330 | 110011 | #SGR17VB - RT 682 Str 6487 over Copper Creek Fed 16840 | 0682 | Secondary | Bridge Rehab w/ Added Capacity | VDOT | Scott County | WISE | Bristol | NonMPO:NonMPO | Infrastructure Investment/Asset Management Division | Gary Lester |  |  | John E Sproles | John.Sproles@VDOT.Virginia.gov | (276) 696-3391 |  |  |  | 0 |  | 1 | FY2021 | 1255547 | 1255510 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 637 days early | G | Project is on budget | [5 empty] | 2016-09-01 | 2016-12-16 | 2016-09-15 | 2016-12-30 | R | 2016-09-16 | 2017-01-03 | 2017-08-15 | 2017-12-14 | R | [5 empty] | 2019-01-17 | 2018-10-18 | 2019-02-01 | 2018-10-18 | G | 2020-04-03 | 2018-11-16 | 2020-04-16 | 2018-11-16 | G | 2020-09-09 | 2018-09-20 | 2021-03-22 | 2018-09-20 | G | 2020-05-01 | 2018-11-16 | 2020-11-04 | 2018-11-16 | G | 2019-10-22 | 2018-01-25 | 2020-06-26 | 2018-01-25 | G | [5 empty] | 2021-04-13 | 2019-07-09 | 2021-04-13 | 2019-07-09 | G | 2021-06-03 | 2019-09-25 | 2021-06-23 | 2019-09-25 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.086699
2332 | 111437 | #SGR18LB - BRIDGE REPLACEMENT GRANNY CREEK (29696 Fed) | 0000 | Miscellaneous | Bridge Replacement w/o Added Capacity | Locally | Buchanan County | LEBANON | Bristol | NonMPO:NonMPO | Infrastructure Investment Division | John W Bechtold | John.Bechtold@vdot.virginia.gov | (276) 696-3365 | Roger L Musser | Roger.Musser@VDOT.Virginia.gov | (276) 696-3260 | Marcus Stiltner | marcus.stiltner@buchanancounty-va.gov | (276) 935-4013 | 0 |  | 1 | FY2021 | 180000 | 180000 | CONSTRUCTION STARTED | G | Start Delivery milestone finished on-time | G | Project is on budget | 2018-05-10 | 2018-02-01 | 2018-08-03 | 2018-04-02 | G | 2018-08-06 | 2018-04-03 | 2018-08-08 | 2018-04-05 | G | 2018-08-09 | 2018-04-06 | 2019-02-20 | 2019-02-19 | G | [35 empty] | 2020-01-14 | 2020-01-14 | 2020-04-09 | 2020-04-07 | G | 2020-04-10 | 2020-04-10 | 2020-07-06 | 2020-07-06 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.043537
2333 | 111709 | #SMART18 - Route 13 & Route 175 Chincoteague Road | 0013 | Primary | Safety | VDOT | Accomack County | ACCOMAC | Hampton Roads | NonMPO:NonMPO | Infrastructure Investment Division | Todd M Halacy | Todd.Halacy@VDOT.Virginia.gov | (757) 956-3010 | John K Arms | John.Arms@vdot.virginia.gov | (757) 995-5156 | Rich Morrison | 7sapper0@gmail.com | (757) 787-5726 | 1 | 2018 | 0 | FY2021 | 779156 | 780854 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 84 days early | Y | Project estimate is less than $5M and is up to 20% over budget | [5 empty] | 2017-09-01 | 2017-08-25 | 2017-09-15 | 2017-08-25 | G | 2017-09-18 | 2017-09-18 | 2018-01-17 | 2018-01-17 | G | [5 empty] | 2018-07-10 | 2018-07-10 | 2018-07-23 | 2018-07-12 | G | 2019-04-15 | 2019-03-13 | 2019-04-26 | 2019-03-19 | G | 2019-08-07 | 2019-08-07 | 2020-04-28 | 2020-04-20 | G | 2019-05-14 | 2019-04-03 | 2019-11-01 | 2019-10-18 | G | 2018-10-12 | 2018-10-12 | 2019-04-24 | 2018-10-12 | G | [5 empty] | 2020-05-12 | 2020-02-11 | 2020-05-12 | 2020-02-11 | G | 2020-06-26 | 2020-05-29 | 2020-08-21 | 2020-05-29 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.093103
2334 | 112463 | PRINCE WILLIAM PARKWAY SIDEWALK | 0294 | Secondary | Facilities for Pedestrians and Bicycles | Locally | Prince William County | MANASSAS | Northern Virginia | Northern Virginia:Prince William County | Infrastructure Investment Division | Amir Salahshoor | A.Salahshoor@VDOT.Virginia.gov | (703) 259-1957 | Marlene Pinedo Fortich | Sofia.Pinedo@vdot.virginia.gov | (703) 259-1724 | TBD |  |  | 0 |  | 0 | FY2027 | 1100000 | 1100000 | NO DATES SET YET | G | Agreement with Locality milestone is 796 days ahead of the expected completion date | Y | Estimate not current | 2022-10-03 |  | 2023-04-28 |  | G | 2023-05-01 |  | 2023-05-31 |  | G | 2023-06-01 |  | 2023-12-29 |  | G | [10 empty] | 2025-01-02 |  | 2025-01-31 |  | G | [5 empty] | 2025-02-04 |  | 2025-11-26 |  | G | [10 empty] | 2025-12-30 |  | 2026-06-30 |  | G | 2026-07-01 |  | 2026-11-30 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.34328
2335 | 113185 | SOUTH MAPLE AND W ANNANDALE RD INTERSECTION IMPROVEMENTS | 6609 | Urban | Safety | Locally | Falls Church | FAIRFAX | Northern Virginia | Northern Virginia:Falls Church | Local Assistance Division | Andrew G Beacher | Andrew.Beacher@vdot.virginia.gov | (703) 259-2239 | Marlene Pinedo Fortich | Sofia.Pinedo@vdot.virginia.gov | (703) 259-1724 | Ali Khavari | akhavari@fallschurchva.gov | (703) 248-5394 | 0 |  | 0 | FY2023 | 1710000 | 1710000 | NO DATES SET YET-PE OPEN | R | Start Development milestone baseline missing | G | Project is on budget | 2018-10-31 | 2018-07-01 | 2019-03-29 | 2018-08-13 | G |  | 2018-08-14 |  | 2018-09-04 | R | 2019-11-01 | 2020-12-04 | 2020-10-30 |  | R | [10 empty] | 2021-09-01 |  | 2021-09-30 |  | G | [5 empty] | 2021-10-01 |  | 2022-07-29 |  | G | 2019-12-02 |  | 2020-08-31 |  | R | [5 empty] | 2022-09-01 |  | 2023-01-31 |  | G | 2023-02-01 |  | 2023-06-30 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.42186
2336 | 113440 | Clover Hill Area School Ped Improvements |  | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Chesterfield County | CHESTERFIELD | Richmond | Richmond:Chesterfield County | Local Assistance Division | Jorg Huckabee-Mayfield | Jorg.Huckabee-Mayfield@VDOT.Virginia.gov | (804) 609-5292 | Jorg Huckabee-Mayfield | Jorg.Huckabee-Mayfield@VDOT.Virginia.gov | (804) 609-5292 | Nate Mathis | MathisN@chesterfield.gov | (804) 748-1037 | 0 |  | 0 | FY2022 | 1200000 | 1200000 | ACTIVITY DATES SET | G | Complete Purchasing Right-of-Way milestone finished on-time | G | Project is on budget | 2018-11-30 | 2018-11-03 | 2019-02-28 | 2019-04-02 | R | 2019-03-01 | 2019-04-03 | 2019-03-05 | 2019-05-06 | R | 2019-03-06 | 2019-05-07 | 2020-05-29 | 2020-05-26 | G | [10 empty] | 2020-10-01 | 2020-10-01 | 2020-10-01 | 2020-10-01 | G | [5 empty] | 2020-10-05 | 2020-10-05 | 2020-10-05 | 2020-10-05 | G | 2020-08-18 | 2020-06-04 | 2021-04-02 | 2020-06-04 | G | [5 empty] | 2021-07-01 |  | 2021-07-01 |  | G | 2021-07-02 |  | 2021-11-09 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.3554
2337 | 113743 | RTE 648-RURAL RUSTIC RD (SURFACE TREAT NON-HARD SURFACE RD) | 0648 | Secondary | Reconstruction w/o Added Capacity | VDOT | Fauquier County | WARRENTON | Culpeper | NonMPO:NonMPO | Infrastructure Investment Division | Ken Connors |  |  | Benjamin Davison | Ben.Davison@vdot.virginia.gov | (540) 347-6446 |  |  |  | 0 |  | 0 | FY2025 | 540000 | 540000 | NO DATES SET YET | G | Start Development milestone is 600 days ahead of the expected completion date | Y | Estimate not current | [5 empty] | 2022-10-03 |  | 2022-10-14 |  | G | 2022-10-18 |  | 2023-06-13 |  | G | [5 empty] | 2024-02-22 |  | 2024-04-03 |  | G | [5 empty] | 2024-07-18 |  | 2024-11-08 |  | G | [5 empty] | 2024-07-02 |  | 2024-10-02 |  | G | [5 empty] | 2024-11-12 |  | 2024-11-12 |  | G | 2025-02-07 |  | 2025-02-07 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | SAAP CONTRACT | 0 | 0 | 0.10392
2338 | 113872 | ROUTE 630 - CARTERS MILL ROAD - RURAL RUSTIC | 0630 | Secondary | Reconstruction w/o Added Capacity | VDOT | Bedford County | BEDFORD | Salem | NonMPO:NonMPO | Infrastructure Investment Division | Todd K Daniel | Todd.Daniel@VDOT.Virginia.gov | (540) 682-7000 | Clyde Spencer | Clyde.Spencer@vdot.virginia.gov | (540) 682-7011 |  |  |  | 0 |  | 0 | FY2029 | 1138500 | 1138500 | NO DATES SET YET | G | Start Development milestone is 1331 days ahead of the expected completion date | G | Project is on budget | [5 empty] | 2024-10-01 |  | 2024-10-14 |  | G | 2024-10-15 |  | 2025-09-12 |  | G | [5 empty] | 2026-07-21 |  | 2026-08-03 |  | G | 2027-11-08 |  | 2027-11-22 |  | G | 2028-04-20 |  | 2028-10-24 |  | G | 2027-12-10 |  | 2028-06-16 |  | G | 2027-04-28 |  | 2027-11-01 |  | G | [5 empty] | 2028-11-14 |  | 2028-11-14 |  | G | 2029-02-09 |  | 2029-02-09 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | SAAP CONTRACT | 0 | 0 | 0.18935
2339 | 114899 | RTE 624 - MORGAN'S FORD APPROACH WORK | 0624 | Secondary | Reconstruction w/o Added Capacity | VDOT | Warren County | EDINBURG | Staunton | NonMPO:NonMPO | Infrastructure Investment Division | Randolph S Kiser | Randy.Kiser@VDOT.Virginia.gov | (540) 332-9092 | Michael S Sensabaugh | M.Sensabaugh@VDOT.Virginia.gov | (540) 332-9103 |  |  |  | 0 |  | 0 | FY2020 | 593133 | 600045 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 14 days early | Y | Project estimate is less than $5M and is up to 20% over budget | [10 empty] | 2019-06-03 | 2019-06-03 | 2019-06-07 | 2019-06-07 | G | [25 empty] | 2019-03-21 | 2019-03-21 | 2019-09-23 | 2019-05-15 | G | [5 empty] | 2019-05-21 | 2019-05-21 | 2019-05-21 | 2019-05-21 | G | 2019-08-12 | 2019-07-29 | 2019-08-12 | 2019-07-29 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.08168
2340 | 115099 | Lee Highway Primary Extension Paving | 0011 | Urban | Resurfacing | Locally | Bristol | ABINGDON | Bristol | Bristol:Bristol | Local Assistance Division | John W Bechtold | John.Bechtold@vdot.virginia.gov | (276) 696-3365 | John W Bechtold | John.Bechtold@vdot.virginia.gov | (276) 696-3365 | Wallace McCulloch | wallacemcculloch@bristolva.org | (276) 642-2316 | 0 |  | 0 | FY2020 | 224000 | 224000 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 5 days early | G | Project is on budget | 2019-07-01 | 2019-07-01 | 2019-09-24 | 2019-09-24 | G | [5 empty] | 2019-07-01 | 2019-07-01 | 2019-07-15 | 2019-07-15 | G | [25 empty] | 2019-07-16 | 2019-07-15 | 2019-10-08 | 2019-07-15 | G | [5 empty] | 2019-10-10 | 2019-10-10 | 2019-11-07 | 2019-11-04 | G | 2020-02-04 | 2020-01-30 | 2020-02-04 | 2020-01-30 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.060616
2342 | 115606 | ROUTE 659-SURFACE TREAT NON-HARSURFACED ROADWAY | 0659 | Secondary | Resurfacing | VDOT | Giles County | CHRISTIANSBURG | Salem | NonMPO:NonMPO | Infrastructure Investment Division | Christopher L Price | Christopher.Price@VDOT.Virginia.gov | (540) 381-7182 | Christopher L Price | Christopher.Price@VDOT.Virginia.gov | (540) 381-7182 |  |  |  | 0 |  | 0 | FY2027 | 875000 | 875000 | NO DATES SET YET | G | Start Development milestone is 1209 days ahead of the expected completion date | G | Project is on budget | [5 empty] | 2024-06-03 |  | 2024-06-14 |  | G | 2024-06-17 |  | 2025-02-11 |  | G | [5 empty] | 2025-10-14 |  | 2025-11-26 |  | G | [5 empty] | 2026-03-19 |  | 2026-07-10 |  | G | [5 empty] | 2026-03-04 |  | 2026-06-03 |  | G | [5 empty] | 2026-07-14 |  | 2026-07-14 |  | G | 2026-10-02 |  | 2026-10-02 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | SAAP CONTRACT | 0 | 0 | 0.072377
2343 | 116961 | #SGR21VP F21 SGR Plant Mix Interstate PM4S-964-F21 |  | Interstate | Resurfacing | VDOT | Richmond District-wide |  | Richmond | Tri-Cities:Prince George County | Infrastructure Investment/Asset Management Division | Shahriar Najafi | Shahriar.Najafi@vdot.virginia.gov | (804) 609-5242 | Shahriar Najafi | Shahriar.Najafi@vdot.virginia.gov | (804) 609-5242 |  |  |  | 0 |  | 1 | FY2022 | 6326055 | 6326055 | ADVERTISED | G | Solicit Bids milestone finished 42 days early | G | Project is on budget | [10 empty] | 2021-01-14 | 2020-06-30 | 2021-01-22 | 2020-10-29 | G | [35 empty] | 2020-10-30 | 2021-01-12 | 2021-02-23 | 2021-01-12 | G | 2021-06-24 |  | 2021-08-05 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.071117
2344 | 117222 | FY21 ITTF Transportation Data Analytics | 9999 | Interstate | Safety | VDOT | Statewide |  | Statewide | Multiple MPOs:Statewide | Infrastructure Investment Division | Catherine C Mcghee | Cathy.McGhee@VDOT.Virginia.gov | (434) 293-1973 | Beverly Quinlan | Beverly.Quinlan@oipi.virginia.gov | (804) 786-2356 |  |  |  | 0 |  | 0 | FY2021 | 3000000 | 3000000 | NO DATES SET YET | R | Determine Requirements milestone is 131 days past the expected completion date | G | Project is on budget | [10 empty] | 2020-09-30 |  | 2020-10-13 |  | R | [25 empty] | 2020-09-30 |  | 2021-03-08 |  | Y | [5 empty] | 2021-01-12 |  | 2021-01-12 |  | R | 2021-04-05 |  | 2021-04-05 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | ADMINISTRATIVE SERVICES | 0 | 1 | 0.30984
2345 | 117997 | N. Franklin/Wades Ped. Improvements |  | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Christiansburg | CHRISTIANSBURG | Salem | New River Valley:Christiansburg | Local Assistance Division | Adam J Czesnowski | Adam.Czesnowski@vdot.virginia.gov | (540) 541-1216 | Adam J Czesnowski | Adam.Czesnowski@vdot.virginia.gov | (540) 541-1216 | Justin St. Clair | jstclair@christiansburg.org | (540) 382-6120 | 0 |  | 0 | FY2025 | 209716 | 209716 | NO DATES SET YET | G | Agreement with Locality milestone is 50 days ahead of the expected completion date | G | Project is on budget | 2020-12-01 |  | 2021-04-12 |  | G | 2021-04-13 |  | 2021-05-03 |  | G | 2021-11-08 |  | 2022-03-09 |  | G | [10 empty] | 2023-06-27 |  | 2023-08-01 |  | G | [5 empty] | 2023-08-02 |  | 2024-01-04 |  | G | 2023-11-30 |  | 2024-05-01 |  | G | [5 empty] | 2024-04-10 |  | 2024-05-07 |  | G | 2024-07-26 |  | 2024-07-26 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.24501
2346 | 118160 | North Franklin Sidewalk - Elm to Mill | 0000 | Urban | Facilities for Pedestrians and Bicycles | Locally | Christiansburg | CHRISTIANSBURG | Salem | New River Valley:Christiansburg | Local Assistance Division | Adam J Czesnowski | Adam.Czesnowski@vdot.virginia.gov | (540) 541-1216 | Adam J Czesnowski | Adam.Czesnowski@vdot.virginia.gov | (540) 541-1216 | Wayne Nelson | wnelson@christiansburg.org | (540) 382-9120 | 0 |  | 0 | FY2028 | 2119000 | 2119000 | NO DATES SET YET | G | Agreement with Locality milestone is 1422 days ahead of the expected completion date | G | Project is on budget | 2024-08-30 |  | 2025-01-13 |  | G | 2025-01-14 |  | 2025-02-05 |  | G | 2025-08-12 |  | 2025-12-08 |  | G | [10 empty] | 2027-04-01 |  | 2027-05-05 |  | G | [5 empty] | 2027-05-06 |  | 2027-10-04 |  | G | 2027-08-31 |  | 2028-02-04 |  | G | [5 empty] | 2028-01-12 |  | 2028-02-10 |  | G | 2028-05-01 |  | 2028-05-01 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.10001
2347 | 50529 | RTE 9999 (THREE CHOPT ROAD) WIDEN TO 4 LANES | 9999 | Secondary | Reconstruction w/ Added Capacity | Locally | Henrico County | ASHLAND | Richmond | Richmond:Henrico County | Infrastructure Investment Division | Douglas L Orcutt | Doug.Orcutt@vdot.virginia.gov | (804) 609-5428 | Douglas L Orcutt | Doug.Orcutt@vdot.virginia.gov | (804) 609-5428 | Todd Eure | tie@co.henrico.va.us | (804) 501-5985 | 0 |  | 0 | FY2020 | 6163250 | 30818528 | ACTIVITY DATES SET | R | Complete Purchasing Right-of-Way milestone is 587 days past the expected completion date | R | Project estimate is between $5M and $10M and is a $1M or more over budget | 2015-05-01 | 1999-11-15 | 2015-05-30 | 1999-11-30 | G | [5 empty] | 2015-06-01 | 2014-08-14 | 2015-10-01 | 2014-08-19 | G | [10 empty] | 2014-09-18 | 2014-09-18 | 2014-09-23 | 2014-09-23 | G | 2019-01-30 |  | 2019-08-01 |  | R | 2018-01-08 |  | 2019-07-15 |  | R | [10 empty] | 2019-11-30 |  | 2019-11-30 |  | R | 2019-12-31 |  | 2020-03-31 |  | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.3397
2348 | 102951 | Main Street Pedestrian Improvements | 0258 | Primary | Facilities for Pedestrians and Bicycles | Locally | Isle of Wight County | FRANKLIN | Hampton Roads | Hampton Roads:Isle of Wight County | Infrastructure Investment Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Keisha Wilkins | Keisha.Wilkins@vdot.virginia.gov | (757) 956-3110 | Jamie Oliver | joliver@isleofwightus.net | (757) 365-1653 | 0 |  | 0 | FY2022 | 1430000 | 1430000 | NO DATES SET YET-PE OPEN | R | Determine Requirements milestone is 410 days past the expected completion date | G | Project is on budget | 2018-10-01 | 2017-10-19 | 2019-02-13 | 2017-10-19 | G | 2019-02-14 | 2018-10-01 | 2019-03-07 | 2019-01-24 | G | 2019-09-11 |  | 2020-01-08 |  | R | [25 empty] | 2021-01-04 |  | 2021-06-03 |  | G | [5 empty] | 2021-08-02 |  | 2021-08-27 |  | G | 2021-11-18 |  | 2021-11-18 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.19991
2349 | 104328 | HERNDON METRORAIL INTERMODAL ACCESS IMPROVEMENTS |  | Urban | Transit | Locally | Herndon | FAIRFAX | Northern Virginia | Northern Virginia:Herndon | Infrastructure Investment Division | Terry Yates | Terry.Yates@vdot.virginia.gov | (703) 259-2118 | Susie X Lue | Susie.Lue@vdot.virginia.gov | (703) 259-2918 | Zeljko Spasojevic | zeljko.spasojevic@herndon-va.gov | (703) 435-6800 | 0 |  | 0 | FY2022 | 2609701 | 6071151 | ACTIVITY DATES SET | R | Relocate Utilities milestone is 53 days past the expected completion date | R | Project estimate is less than $5M and is 20% or more over budget | 2013-05-01 | 2013-05-01 | 2013-12-26 | 2013-08-13 | G | 2013-12-27 | 2013-12-27 | 2014-08-28 | 2014-07-29 | G | 2014-12-26 | 2014-12-26 | 2018-12-28 | 2017-12-18 | G | [10 empty] | 2017-12-01 | 2017-12-01 | 2018-05-22 | 2018-05-22 | G | 2019-06-25 | 2019-06-25 | 2020-12-30 |  | R | 2018-05-23 | 2018-05-23 | 2020-04-27 | 2020-04-27 | G | 2016-12-30 | 2016-12-30 | 2017-11-01 | 2017-11-01 | G | [5 empty] | 2021-04-28 |  | 2021-08-19 |  | G | 2021-08-20 |  | 2021-12-23 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.21635
2350 | 115133 | #SMART20 East Main Street |  | Primary | Reconstruction w/o Added Capacity | Locally | Waynesboro | HARRISONBURG | Staunton | SAW:Waynesboro | Infrastructure Investment Division | Randolph S Kiser | Randy.Kiser@VDOT.Virginia.gov | (540) 332-9092 | Michael S Fulcher | Michael.Fulcher@VDOT.Virginia.gov | (540) 332-2243 | City of Waynesboro | judaylj@ci.waynesboro.va.us | (540) 942-6604 | 1 | 2020 | 0 | FY2026 | 2249987 | 2249987 | NO DATES SET YET | G | Agreement with Locality milestone is 976 days ahead of the expected completion date | G | Project is on budget | 2023-08-01 |  | 2023-10-25 |  | G | 2023-10-26 |  | 2023-10-30 |  | G | 2023-10-31 |  | 2024-05-09 |  | G | [10 empty] | 2025-03-07 |  | 2025-03-27 |  | G | [5 empty] | 2025-03-31 |  | 2026-01-08 |  | G | 2024-06-17 |  | 2025-02-24 |  | G | [5 empty] | 2026-01-28 |  | 2026-02-25 |  | G | 2026-05-14 |  | 2026-05-14 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.1157
2351 | 115350 | #SMART20 Battlefield Blvd/Volvo Pkwy Intersection Improvemnt |  | Urban | Reconstruction w/ Added Capacity | Locally | Chesapeake | NORFOLK | Hampton Roads | Hampton Roads:Chesapeake | Infrastructure Investment Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Johndel A Alcaide | John.Alcaide@vdot.virginia.gov | (757) 956-3098 | Troy Eisenberger | teisenberger@cityofchesapeake.net | (757) 382-6383 | 1 | 2020 | 0 | FY2027 | 1475129 | 1475129 | NO DATES SET YET | G | Agreement with Locality milestone is 929 days ahead of the expected completion date | Y | Estimate not current | 2023-06-15 |  | 2023-09-08 |  | G | 2023-09-11 |  | 2023-09-22 |  | G | 2023-09-25 |  | 2024-09-10 |  | G | [10 empty] | 2025-09-12 |  | 2025-10-02 |  | G | [5 empty] | 2025-10-06 |  | 2026-07-20 |  | G | 2024-05-10 |  | 2025-01-15 |  | G | [5 empty] | 2026-08-05 |  | 2026-09-01 |  | G | 2026-11-23 |  | 2026-11-23 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.24809
2352 | 116865 | JUBAL EARLY DRIVE TRAFFIC IMPROVEMENTS |  | Urban | Reconstruction w/ Added Capacity | Locally | Winchester | EDINBURG | Staunton | Winchester:Winchester | Local Assistance Division | Kimberly Cameron | Kim.Cameron@vdot.virginia.gov | (540) 332-7886 | Kimberly Cameron | Kim.Cameron@vdot.virginia.gov | (540) 332-7886 | Perry Eisenach | perry.eisenach@winchesterva.gov | (540) 667-1815 | 0 |  | 0 | FY2025 | 2500000 | 2500000 | NO DATES SET YET | G | Agreement with Locality milestone is 107 days ahead of the expected completion date | G | Project is on budget | 2021-02-01 |  | 2021-06-08 |  | G | 2021-06-09 |  | 2021-06-29 |  | G | 2021-07-29 |  | 2021-11-22 |  | G | [10 empty] | 2023-03-20 |  | 2023-04-21 |  | G | [5 empty] | 2023-04-24 |  | 2023-09-20 |  | G | 2024-03-27 |  | 2024-08-22 |  | G | [5 empty] | 2024-08-01 |  | 2024-08-28 |  | G | 2024-11-19 |  | 2024-11-19 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.17476
2353 | 117118 | Sandbridge Road Sidewalk |  | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Virginia Beach | NORFOLK | Hampton Roads | Hampton Roads:Virginia Beach | Local Assistance Division | Susan Wilson | Susan.Wilson@vdot.virginia.gov | (757) 956-3099 | Marci Thompson | Marci.Thompson@vdot.virginia.gov | (757) 956-3093 | Katie Shannon | kshannon@vbgov.com | (757) 385-1514 | 0 |  | 0 | FY2023 | 787603 | 787603 | NO DATES SET YET | G | Agreement with Locality milestone is 80 days ahead of the expected completion date | G | Project is on budget | 2021-01-04 |  | 2021-05-12 |  | G | 2021-05-13 |  | 2021-06-03 |  | G | 2021-12-13 |  | 2022-04-08 |  | G | [10 empty] | 2022-05-09 |  | 2022-06-13 |  | G | [5 empty] | 2022-06-14 |  | 2022-11-10 |  | G | 2022-10-07 |  | 2023-03-15 |  | G | [5 empty] | 2023-02-22 |  | 2023-03-21 |  | G | 2023-06-08 |  | 2023-06-08 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.2761
2354 | 117941 | #TAP21 BUS 29 (MAIN STREET) - CONSTRUCT SIDEWALK | 9999 | Enhancement | Facilities for Pedestrians and Bicycles | VDOT | Altavista | APPOMATTOX | Lynchburg | NonMPO:NonMPO | Local Assistance Division | Brian J Casto | Brian.Casto@VDOT.Virginia.gov | (434) 856-8276 | Brian J Casto | Brian.Casto@VDOT.Virginia.gov | (434) 856-8276 | JW COGGSDALE | jwcoggsdale@altavistava.gov | (434) 369-5001 | 0 |  | 0 | FY2024 | 935790 | 935790 | NO DATES SET YET | R | Start Development milestone is 3 days past the expected completion date | G | Project is on budget | [5 empty] | 2021-01-29 |  | 2021-02-18 |  | R | 2021-02-19 |  | 2021-12-21 |  | G | [5 empty] | 2022-07-22 |  | 2022-08-18 |  | G | 2023-04-14 |  | 2023-05-18 |  | G | 2023-10-18 |  | 2024-02-23 |  | G | 2023-06-05 |  | 2023-11-01 |  | G | 2023-07-12 |  | 2023-12-12 |  | G | [5 empty] | 2024-03-12 |  | 2024-03-12 |  | G | 2024-05-30 |  | 2024-05-30 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 1 | 0.23586
2355 | 118146 | Route 1 (Holiday Lane - Willis Road) Shared-Use Path | 0001 | Primary | Safety and Education of Pedestrians /Bicyclisits | Locally | Chesterfield County | CHESTERFIELD | Richmond | Richmond:Chesterfield County | Infrastructure Investment Division | Michael S Gray | Mike.Gray@vdot.virginia.gov | (804) 609-5347 | Michael S Gray | Mike.Gray@vdot.virginia.gov | (804) 609-5347 | Barb Smith | smithbk@chesterfield.gov | (804) 748-1037 | 0 |  | 0 | FY2028 | 4370000 | 4370000 | NO DATES SET YET | G | Agreement with Locality milestone is 1179 days ahead of the expected completion date | G | Project is on budget | 2024-01-08 |  | 2024-05-15 |  | G | 2024-05-16 |  | 2024-06-06 |  | G | 2024-12-16 |  | 2025-04-11 |  | G | [10 empty] | 2026-07-31 |  | 2026-09-03 |  | G | [5 empty] | 2026-09-04 |  | 2027-02-10 |  | G | 2027-01-06 |  | 2027-06-07 |  | G | [5 empty] | 2027-05-14 |  | 2027-06-11 |  | G | 2027-08-31 |  | 2027-08-31 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.12023
2356 | 17536 | RTE 58 - CORRIDOR DEVELPMENT PROG - 4 LANES (Lovers Leap) | 0058 | Primary | Reconstruction w/ Added Capacity | VDOT | Patrick County | MARTINSVILLE | Salem | NonMPO:NonMPO | Infrastructure Investment Division | Robert A Griffith | Rob.Griffith@VDOT.Virginia.gov | (540) 387-5346 | Anthony L Handy | Tony.Handy@VDOT.Virginia.gov | (540) 352-9050 |  |  |  | 0 |  | 0 | FY2021 | 10783000 | 310900000 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 172 days early | R | Project estimate is greater than $10M and is over budget by (a) 10% or more or (b) $5M or more | [5 empty] | 1997-07-01 | 1997-07-07 | 1997-07-31 | 1997-07-08 | G | 1997-08-01 | 1997-01-28 | 1998-01-30 | 1997-04-26 | G | [5 empty] | 1998-12-02 | 1998-12-02 | 1998-12-17 | 1998-12-17 | G | 1999-06-17 | 1999-06-17 | 1999-06-25 | 1999-06-25 | G | [20 empty] | 2020-11-09 | 2020-09-11 | 2020-11-09 | 2020-09-15 | G | 2020-11-23 | 2020-11-30 | 2021-05-21 | 2020-11-30 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | DESIGN BUILD/PPTA | 1 | 0 | 0.085029
2357 | 89889 | HERNDON PARKWAY INTERSECTION AT VAN BUREN STREET | 0606 | Urban | Preliminary Engineering | Locally | Herndon | FAIRFAX | Northern Virginia | Northern Virginia:Herndon | Infrastructure Investment Division | Terry Yates | Terry.Yates@vdot.virginia.gov | (703) 259-2118 | Christer P Carshult | Christer.Carshult@vdot.virginia.gov | (703) 259-1765 | Richard Smith | richard.smith@herndon-va.gov | (703) 435-6853 | 0 |  | 0 | FY2021 | 100000 | 3075084 | ACTIVITY DATES SET | R | Solicit Bids milestone is 52 days past the expected completion date | R | Project estimate is less than $5M and is 20% or more over budget | 2009-09-01 | 2009-09-01 | 2009-09-01 | 2009-09-01 | G | 2009-10-01 | 2010-03-23 | 2009-10-31 | 2010-03-23 | R | 2010-02-01 | 2010-01-25 | 2010-05-31 | 2010-05-28 | G | [10 empty] | 2017-03-16 | 2017-03-16 | 2017-06-30 | 2017-06-30 | G | [20 empty] | 2019-11-22 |  | 2020-12-31 |  | R | 2021-01-04 |  | 2021-05-28 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.22159
2358 | 103285 | SUNRISE VALLEY DRIVE SIDEWALK NORTH - ASSOCIATION TO PRESTON | 9999 | Primary | Reconstruction w/o Added Capacity | Locally | Fairfax County | FAIRFAX | Northern Virginia | Northern Virginia:Fairfax County | Infrastructure Investment Division | Amir Salahshoor | A.Salahshoor@VDOT.Virginia.gov | (703) 259-1957 | Rita Hockman | Rita.Hockman@vdot.virginia.gov | (804) 824-7421 | Todd Minnix | Wesley.minnix@fairfaxcounty.gov | (703) 877-5749 | 0 |  | 0 | FY2020 | 1554485 | 1571180 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 17 days early | Y | Project estimate is less than $5M and is up to 20% over budget | [5 empty] | 2014-06-23 | 2014-06-23 | 2014-06-23 | 2014-06-23 | G | 2013-07-31 | 2014-06-24 | 2013-11-30 | 2014-09-24 | R | [10 empty] | 2016-03-23 | 2016-03-23 | 2016-06-28 | 2016-06-28 | G | [5 empty] | 2016-07-07 | 2016-07-07 | 2019-05-01 | 2019-04-30 | G | [10 empty] | 2019-05-01 | 2019-05-01 | 2019-05-01 | 2019-05-01 | G | 2019-05-01 | 2019-08-12 | 2019-08-30 | 2019-08-13 | G | Delay due to unforeseen issues with utilities, railroad coordination, or right-of-way acquisition | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.090844
2359 | 105525 | NEW TRAFFIC SIGNALS | 9999 | Urban | Traffic Management/Engineering | Locally | Falls Church | FAIRFAX | Northern Virginia | Northern Virginia:Falls Church | Local Assistance Division | Terry Yates | Terry.Yates@vdot.virginia.gov | (703) 259-2118 | Rita Hockman | Rita.Hockman@vdot.virginia.gov | (804) 824-7421 | Al Astorga | aastorga@fallschurchva.gov | (571) 835-6795 | 0 |  | 0 | FY2020 | 825000 | 950000 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 415 days early | Y | Project estimate is less than $5M and is up to 20% over budget | 2014-03-20 | 2014-03-20 | 2014-09-29 | 2014-06-20 | G | 2014-09-30 | 2014-09-30 | 2014-09-30 | 2014-09-30 | G | 2015-07-01 | 2015-07-01 | 2017-08-24 | 2017-06-24 | G | [10 empty] | 2016-11-01 | 2016-11-01 | 2016-12-15 | 2016-12-15 | G | 2016-12-16 | 2016-12-16 | 2017-09-15 | 2017-09-15 | G | 2016-12-16 | 2016-12-16 | 2018-03-25 | 2018-03-25 | G | [10 empty] | 2018-03-01 | 2018-03-01 | 2018-03-27 | 2018-03-27 | G | 2019-04-01 | 2018-07-11 | 2019-08-30 | 2018-07-11 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.41688
2360 | 106197 | RTE 637 - CONSTRUCT ROUNDABOUT | 0637 | Secondary | Safety | VDOT | Chesterfield County | CHESTERFIELD | Richmond | Richmond:Chesterfield County | Infrastructure Investment Division | William Wheeler | William.Wheeler@vdot.virginia.gov | (804) 609-5280 | William Wheeler | William.Wheeler@vdot.virginia.gov | (804) 609-5280 |  |  |  | 0 |  | 0 | FY2021 | 3400000 | 3994702 | ADVERTISED | R | Relocate Utilities milestone is 17 days past the expected completion date | Y | Project estimate is less than $5M and is up to 20% over budget | [5 empty] | 2015-07-01 | 2015-07-24 | 2015-07-01 | 2015-07-29 | R | 2015-07-31 | 2015-07-31 | 2018-06-29 | 2018-06-26 | G | [5 empty] | 2018-12-10 | 2018-10-18 | 2019-01-08 | 2018-12-17 | G | 2019-11-06 | 2020-01-07 | 2019-11-27 | 2020-01-14 | R | 2020-07-30 | 2020-09-01 | 2021-02-04 |  | R | 2019-12-24 | 2020-02-20 | 2020-06-30 | 2020-08-18 | R | 2019-01-10 | 2019-01-07 | 2019-08-14 | 2019-01-07 | G | [5 empty] | 2021-02-09 | 2021-02-09 | 2021-02-09 | 2021-02-09 | G | 2021-02-10 |  | 2021-05-04 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.16161
2361 | 109082 | RTE 654 (BAILEY BRIDGE ROAD) SIDEWALK | 0654 | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Chesterfield County | CHESTERFIELD | Richmond | Richmond:Chesterfield County | Local Assistance Division | Brian J Lokker | Brian.Lokker@VDOT.Virginia.gov | (804) 524-6010 | Brian J Lokker | Brian.Lokker@VDOT.Virginia.gov | (804) 524-6010 | Nate Mathis | mathisn@chesterfield.gov | (804) 748-1037 | 0 |  | 0 | FY2020 | 900000 | 900000 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 335 days early | G | Project is on budget | 2016-10-03 | 2016-08-23 | 2016-12-30 | 2016-08-23 | G | 2017-01-03 | 2016-09-23 | 2017-01-05 | 2016-09-23 | G | 2017-01-06 | 2016-09-26 | 2017-07-13 | 2017-10-10 | R | [10 empty] | 2018-05-09 | 2017-11-15 | 2018-05-30 | 2017-11-21 | G | [5 empty] | 2018-06-01 | 2018-01-10 | 2019-03-15 | 2018-02-21 | G | [10 empty] | 2019-04-02 | 2018-06-25 | 2019-04-29 | 2018-06-25 | G | 2019-04-23 | 2018-08-30 | 2019-07-31 | 2018-08-30 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.354
2362 | 109535 | #HB2.FY17 RTE 15 - LEFT & RIGHT TURN LANES AT RTE 665 | 0015 | Primary | Safety | VDOT | Prince Edward County | DILLWYN | Lynchburg | NonMPO:NonMPO | Infrastructure Investment Division | Laura J Walton | Laura.Walton@VDOT.Virginia.gov | (434) 856-8286 | Laura J Walton | Laura.Walton@VDOT.Virginia.gov | (434) 856-8286 |  |  |  | 1 | 2017 | 0 | FY2021 | 4989509 | 3092089 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 35 days early | G | Project is on budget | [5 empty] | 2017-01-17 | 2017-01-17 | 2017-01-30 | 2017-01-30 | G | 2017-01-31 | 2017-01-30 | 2017-12-26 | 2017-05-24 | G | [5 empty] | 2018-04-02 | 2018-04-02 | 2018-04-13 | 2018-04-13 | G | 2019-03-29 | 2019-03-29 | 2019-04-11 | 2019-04-03 | G | 2020-01-30 | 2020-02-13 | 2020-07-29 | 2020-07-27 | G | 2019-04-29 | 2019-04-04 | 2020-01-29 | 2020-01-27 | G | 2018-08-24 | 2018-07-27 | 2019-08-26 | 2018-07-27 | G | [5 empty] | 2020-09-08 | 2020-09-08 | 2020-09-08 | 2020-09-08 | G | 2020-10-23 | 2020-11-17 | 2020-12-22 | 2020-11-17 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.096856
2363 | 110128 | RTE 628 MENTOW DR RURAL RUSTIC | 0628 | Secondary | Resurfacing | VDOT | Bedford County | BEDFORD | Salem | NonMPO:NonMPO | Infrastructure Investment Division | Todd K Daniel | Todd.Daniel@VDOT.Virginia.gov | (540) 682-7000 | Jason L Patrick | Jason.Patrick@vdot.virginia.gov | (540) 381-7178 |  |  |  | 0 |  | 0 | FY2025 | 1317000 | 1317000 | NO DATES SET YET-PE OPEN | G | Start Development milestone finished 68 days early | G | Project is on budget | [5 empty] | 2020-07-01 | 2020-05-06 | 2020-07-15 | 2020-05-08 | G | 2020-07-16 | 2020-05-11 | 2021-06-07 |  | G | [5 empty] | 2022-03-29 |  | 2022-04-11 |  | G | 2023-06-27 |  | 2023-07-10 |  | G | 2023-11-28 |  | 2024-05-27 |  | G | 2023-07-26 |  | 2024-01-23 |  | G | 2022-12-21 |  | 2023-08-15 |  | G | [5 empty] | 2024-06-11 |  | 2024-06-11 |  | G | 2024-07-31 |  | 2024-08-20 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | SAAP CONTRACT | 0 | 0 | 0.12193
2364 | 110629 | I-66 EB INSIDE BELTWAY - TMP - WFC METRO ACCESS | 0066 | Interstate | Reconstruction w/o Added Capacity | VDOT | Northern Virginia District-wide |  | Northern Virginia | Northern Virginia:Northern Virginia District-wide | Infrastructure Investment Division | Mark A Gibney | Mark.Gibney@VDOT.Virginia.gov | (703) 259-2734 | Mark A Gibney | Mark.Gibney@VDOT.Virginia.gov | (703) 259-2734 |  |  |  | 0 |  | 0 | FY2019 | 3300000 | 4800000 | CONSTRUCTION STARTED | G | Engage Public milestone finished 85 days early | R | Project estimate is less than $5M and is 20% or more over budget | [5 empty] | 2017-03-02 | 2016-04-20 | 2017-03-15 | 2016-04-20 | G | 2017-03-16 | 2016-04-21 | 2017-11-02 | 2017-09-25 | G | [5 empty] | 2018-06-05 | 2018-04-23 | 2018-07-17 | 2018-04-23 | G | [5 empty] | 2018-10-30 | 2018-09-14 | 2019-02-28 | 2019-01-11 | G | [5 empty] | 2017-03-05 | 2017-03-05 | 2017-03-06 | 2017-03-06 | G | [5 empty] | 2019-03-12 | 2017-04-07 | 2019-03-13 | 2017-04-07 | G | 2019-05-02 | 2017-12-06 | 2019-05-22 | 2017-12-06 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | DESIGN BUILD/PPTA | 1 | 0 | 0.097835
2366 | 111874 | SUDLEY MANOR DRIVE & SEYMOUR ROAD TRAFFIC SIGNAL | 1566 | Secondary | Safety | VDOT | Prince William County | MANASSAS | Northern Virginia | Northern Virginia:Prince William County | Infrastructure Investment Division | Ivan M Horodyskyj | Ivan.Horodyskyj@VDOT.Virginia.gov | (703) 259-2330 | Jessica Paris | Jessica.Paris@vdot.virginia.gov | (703) 259-2409 |  |  |  | 0 |  | 0 | FY2022 | 660000 | 660000 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 356 days early | G | Project is on budget | [5 empty] | 2017-10-02 | 2017-09-14 | 2017-10-13 | 2017-09-18 | G | 2017-10-17 | 2017-09-19 | 2018-09-13 | 2018-12-26 | R | [5 empty] | 2019-10-29 | 2018-12-12 | 2019-11-12 | 2019-03-07 | G | 2020-08-05 | 2019-10-18 | 2020-08-18 | 2019-10-18 | G | 2020-12-31 | 2019-11-15 | 2021-07-08 | 2019-11-15 | G | 2020-08-21 | 2019-11-15 | 2021-03-04 | 2020-08-12 | G | [10 empty] | 2021-07-13 | 2020-12-23 | 2021-07-13 | 2020-12-23 | G | 2021-10-14 | 2020-12-23 | 2021-12-14 | 2020-12-23 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | WORK/TASK ORDER | 1 | 0 | 0.14386
2367 | 113278 | Sidewalks(Phs 1) GWashington Mem. Hwy, Hptn Hwy, Hubbard La | 9999 | Primary | Safety | Locally | York County | WILLIAMSBURG | Hampton Roads | Hampton Roads:York County | Local Assistance Division | Christopher R Carroll | C.Carroll@VDOT.Virginia.gov | (757) 253-5140 | Keisha Wilkins | Keisha.Wilkins@vdot.virginia.gov | (757) 956-3110 | Tim Cross | tcross@yorkcounty.gov | (757) 890-3496 | 0 |  | 0 | FY2022 | 572226 | 572226 | ACTIVITY DATES SET | R | Determine Requirements milestone finished 282 days late | G | Project is on budget | 2018-12-03 | 2018-09-12 | 2019-03-01 | 2018-09-12 | G | 2019-03-04 | 2018-09-13 | 2019-03-06 | 2018-09-14 | G | 2019-03-07 | 2019-10-01 | 2019-09-09 | 2020-06-17 | R | [35 empty] | 2021-07-21 |  | 2021-08-31 |  | G | 2021-11-22 |  | 2021-11-22 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.15903
2368 | 113750 | Int. Imprv. upgrad traffic signal & ped facilities | 9999 | Primary | Safety | Locally | Norfolk | NORFOLK | Hampton Roads | Hampton Roads:Norfolk | Infrastructure Investment Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Derrick Williams | Derrick.Williams@vdot.virginia.gov | (757) 956-3097 | Robert Brown, P.E. | rob.brown@norfolk.gov | (757) 664-7305 | 0 |  | 0 | FY2024 | 871300 | 871300 | NO DATES SET YET | G | Agreement with Locality milestone is 292 days ahead of the expected completion date | Y | Estimate not current | 2021-09-14 |  | 2021-12-10 |  | G | 2021-12-13 |  | 2021-12-15 |  | G | 2021-12-16 |  | 2022-06-23 |  | G | [25 empty] | 2022-08-01 |  | 2023-04-07 |  | G | [5 empty] | 2023-05-05 |  | 2023-06-02 |  | G | 2023-08-22 |  | 2023-08-22 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.2097
2369 | 113876 | #SGR19LB??- Fairground Rd RT 16 Clin Rv Taz VA 1802 Fed 2254 | 0016 | Primary | Bridge Replacement w/o Added Capacity | VDOT | Tazewell | LEBANON | Bristol | NonMPO:NonMPO | Infrastructure Investment/Asset Management Division | Gary Lester |  |  | Shane C Morrison | Shane.Morrison@vdot.virginia.gov | (276) 696-3380 |  |  |  | 0 |  | 0 | FY2022 | 2300000 | 2300000 | NO DATES SET YET | Y | Start Development milestone is 8 days ahead of the expected completion date and there is a risk of missing this milestone date | G | Project is on budget | [5 empty] | 2021-02-15 |  | 2021-03-01 |  | Y | 2021-03-02 |  | 2021-04-26 |  | G | [35 empty] | 2021-12-14 |  | 2021-12-14 |  | G | 2022-03-10 |  | 2022-03-10 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.060278
2370 | 108669 | SIGNALIZED PEDESTRIAN ACCOMMODATIONS - DW | 9999 | Primary | Safety | VDOT | Richmond District-wide |  | Richmond | Richmond:Richmond District-wide | Infrastructure Investment Division | Evan Roberts | Evan.Roberts@vdot.virginia.gov | (804) 609-5427 | Evan Roberts | Evan.Roberts@vdot.virginia.gov | (804) 609-5427 |  |  |  | 0 |  | 0 | FY2022 | 2400000 | 2400000 | ACTIVITY DATES SET | R | Complete Purchasing Right-of-Way milestone is 54 days past the expected completion date | G | Project is on budget | [5 empty] | 2017-10-11 | 2017-10-11 | 2017-10-18 | 2017-10-18 | G | 2017-10-19 | 2017-10-19 | 2018-11-09 | 2018-11-09 | G | [5 empty] | 2019-05-03 | 2019-06-18 | 2019-06-18 | 2019-06-18 | G | 2020-02-25 | 2020-06-10 | 2020-03-09 | 2020-08-24 | R | 2021-02-01 |  | 2021-04-26 |  | G | 2020-03-25 | 2020-09-10 | 2020-12-29 |  | R | [10 empty] | 2021-06-08 |  | 2021-06-08 |  | G | 2021-07-23 |  | 2021-09-17 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.067429
2371 | 109229 | LAKEVIEW RD AND BRANDERS BRIDGE RD INTERSECTION IMPROVEMENTS | 0625 | Secondary | Safety | Locally | Chesterfield County | CHESTERFIELD | Richmond | Tri-Cities:Chesterfield County | Infrastructure Investment Division | Michael S Gray | Mike.Gray@vdot.virginia.gov | (804) 609-5347 | Michael S Gray | Mike.Gray@vdot.virginia.gov | (804) 609-5347 | Chessa Faulkner | FaulknerC@Chesterfield.gov | 7481037 | 0 |  | 0 | FY2024 | 4009990 | 4009990 | ACTIVITY DATES SET | G | Determine Requirements milestone finished 1 days early | G | Project is on budget | 2019-10-01 | 2019-10-01 | 2019-12-30 | 2019-12-18 | G | 2019-12-31 | 2019-12-19 | 2020-01-03 | 2019-12-26 | G | 2020-01-06 | 2019-12-27 | 2020-07-10 | 2020-07-09 | G | [5 empty] | 2021-05-03 |  | 2021-06-02 |  | G | 2021-10-04 |  | 2021-10-25 |  | G | 2022-08-31 |  | 2023-05-30 |  | G | 2021-12-02 |  | 2022-08-30 |  | G | 2022-10-04 |  | 2023-06-12 |  | G | [5 empty] | 2023-06-27 |  | 2023-06-27 |  | G | 2023-09-15 |  | 2023-09-15 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 1 | 0.2443
2372 | 109565 | Pedestrian improvements at E.Virginia Beach Blvd and Newtown | 0000 | Urban | Facilities for Pedestrians and Bicycles | Locally | Norfolk | NORFOLK | Hampton Roads | Hampton Roads:Norfolk | Infrastructure Investment Division | Stephen Rowan | Steve.Rowan@vdot.virginia.gov | (757) 790-9925 | Joshua D Negovan | Joshua.Negovan@vdot.virginia.gov | (757) 956-3347 | Keith Darrow, P.E. | Keith.darrow@norfolk.gov | (757) 664-7305 | 0 |  | 0 | FY2020 | 370300 | 1955853 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 36 days early | R | Project estimate is less than $5M and is 20% or more over budget | 2017-02-28 | 2017-01-28 | 2017-05-22 | 2017-03-16 | G | 2017-05-23 | 2017-03-17 | 2017-05-25 | 2017-03-22 | G | 2017-05-26 | 2017-03-17 | 2017-12-04 | 2018-02-06 | R | [10 empty] | 2019-07-10 | 2019-05-09 | 2019-07-10 | 2019-05-09 | G | [5 empty] | 2019-07-12 | 2019-05-09 | 2019-07-12 | 2019-05-09 | G | 2018-12-06 | 2018-12-03 | 2019-08-09 | 2018-12-03 | G | [5 empty] | 2019-09-10 | 2019-05-10 | 2019-10-22 | 2019-09-08 | G | 2020-01-15 | 2019-11-27 | 2020-04-10 | 2020-03-05 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.23542
2373 | 110133 | RT 644 OLD CIFAX RD - RURAL RUSTIC | 0644 | Secondary | Resurfacing | VDOT | Bedford County | BEDFORD | Salem | NonMPO:NonMPO | Infrastructure Investment Division | Todd K Daniel | Todd.Daniel@VDOT.Virginia.gov | (540) 682-7000 | Jason L Patrick | Jason.Patrick@vdot.virginia.gov | (540) 381-7178 |  |  |  | 0 |  | 0 | FY2023 | 584000 | 882537 | AWARDED | G | Start Delivery milestone finished 647 days early | R | Project estimate is less than $5M and is 20% or more over budget | [5 empty] | 2018-04-03 | 2018-03-30 | 2018-04-16 | 2018-04-04 | G | 2018-04-17 | 2018-04-05 | 2019-03-15 | 2019-03-15 | G | [5 empty] | 2019-12-18 | 2019-12-17 | 2020-01-02 | 2019-12-31 | G | 2021-04-09 |  | 2021-04-22 |  | G | 2021-09-15 | 2019-12-26 | 2022-03-28 | 2019-12-26 | G | 2021-05-10 | 2020-02-26 | 2021-11-12 |  | G | 2021-01-13 | 2020-01-16 | 2022-01-28 | 2020-01-16 | G | [5 empty] | 2022-05-10 | 2020-10-20 | 2022-05-10 | 2020-10-20 | G | 2022-06-30 | 2020-12-15 | 2022-09-23 | 2020-12-15 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | SAAP CONTRACT | 1 | 0 | 0.12087
2374 | 110797 | #SMART18 - US 11 at Railroad Drive Inter. Improvement | 0011 | Primary | Reconstruction w/ Added Capacity | VDOT | Smyth County | ABINGDON | Bristol | NonMPO:NonMPO | Infrastructure Investment Division | Allan D Sumpter | Allan.Sumpter@VDOT.virginia.gov | (276) 525-6461 | James R Jones | jamesr.jones@vdot.virginia.gov | (276) 696-3257 |  |  |  | 1 | 2018 | 0 | FY2022 | 2783000 | 2782705 | ACTIVITY DATES SET | G | Complete Purchasing Right-of-Way milestone finished 112 days early | G | Project is on budget | [5 empty] | 2017-07-14 | 2017-07-14 | 2017-07-27 | 2017-07-26 | G | 2017-07-28 | 2017-07-19 | 2018-05-17 | 2018-05-16 | G | [5 empty] | 2019-02-14 | 2019-02-14 | 2019-02-28 | 2019-02-27 | G | 2020-04-21 | 2020-03-10 | 2020-05-04 | 2020-03-26 | G | 2020-09-25 | 2020-10-21 | 2021-04-07 |  | G | 2020-05-20 | 2020-04-20 | 2021-03-11 | 2020-11-19 | G | 2019-10-03 | 2020-01-21 | 2020-04-14 | 2020-04-14 | G | [5 empty] | 2021-06-08 |  | 2021-06-08 |  | G | 2021-07-26 |  | 2021-09-20 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.079392
2375 | 111740 | #SMART18 - RTE 208-522 ROUNDABOUT AT WARES CROSSROADS | 0522 | Primary | Safety | VDOT | Louisa County | LOUISA | Culpeper | NonMPO:NonMPO | Infrastructure Investment Division | Gregory J Cooley | Gregory.Cooley@vdot.virginia.gov | (434) 906-7979 | Justin Warfield | Justin.Warfield@vdot.virginia.gov | (540) 829-7599 |  |  |  | 1 | 2018 | 0 | FY2022 | 5400000 | 5400000 | NO DATES SET YET-PE OPEN | R | Determine Requirements milestone is 954 days past the expected completion date | G | Project is on budget | [5 empty] | 2017-08-01 | 2018-08-14 | 2017-08-14 | 2018-08-14 | R | 2017-08-15 | 2019-01-17 | 2018-07-13 |  | R | [5 empty] | 2019-05-20 |  | 2019-06-03 |  | R | 2020-09-04 |  | 2020-09-18 |  | R | 2021-02-18 |  | 2021-08-23 |  | G | 2020-10-06 |  | 2021-04-16 |  | Y | 2020-02-27 | 2019-04-11 | 2020-08-28 | 2019-04-11 | G | [5 empty] | 2021-09-14 |  | 2021-09-14 |  | G | 2021-10-29 |  | 2021-12-29 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.07717
2376 | 112945 | Rt. 658/Rockland Rd. NS Railway Bridge - Warren County | 0658 | Secondary | Bridge, New Construction | VDOT | Warren County | EDINBURG | Staunton | NonMPO:NonMPO | Local Assistance Division | Steven K Damron | Steven.Damron@VDOT.Virginia.gov | (804) 786-1172 | Elizabeth G Jordan | Elizabeth.Jordan@VDOT.Virginia.gov | (540) 332-7880 |  |  | (540) 636-4600 | 0 |  | 0 | FY2025 | 21773353 | 21773353 | NO DATES SET YET-PE OPEN | R | Determine Requirements milestone is 55 days past the expected completion date | G | Project is on budget | [5 empty] | 2019-10-31 | 2019-10-31 | 2019-11-14 | 2019-11-14 | G | 2019-11-15 |  | 2020-12-28 |  | R | [5 empty] | 2021-12-27 |  | 2022-01-10 |  | G | 2023-04-07 |  | 2023-04-20 |  | G | 2023-09-14 |  | 2024-03-26 |  | G | 2023-05-08 |  | 2023-11-09 |  | G | 2022-09-20 |  | 2023-05-26 |  | G | [5 empty] | 2024-04-09 |  | 2024-04-09 |  | G | 2024-07-29 |  | 2024-07-29 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.17694
2377 | 113389 | #SGR19VB - BRIDGE MAJOR REHAB RT 1 OVER CSX RW | 0001 | Primary | Bridge Rehab w/o Added Capacity | VDOT | Brunswick County | SOUTH HILL | Richmond | NonMPO:NonMPO | Infrastructure Investment/Asset Management Division | Anthony S Haverly | Anthony.Haverly@vdot.virginia.gov | (804) 609-5225 | Anthony S Haverly | Anthony.Haverly@vdot.virginia.gov | (804) 609-5225 |  |  |  | 0 |  | 1 | FY2022 | 2940000 | 2940000 | ACTIVITY DATES SET | G | Complete Purchasing Right-of-Way milestone finished 67 days early | G | Project is on budget | [5 empty] | 2018-09-04 | 2018-08-22 | 2018-09-17 | 2018-08-27 | G | 2018-09-18 | 2019-03-28 | 2019-08-15 | 2019-08-14 | G | [5 empty] | 2020-05-01 | 2020-04-17 | 2020-06-02 | 2020-06-01 | G | 2020-12-18 | 2020-12-11 | 2021-01-19 | 2020-12-11 | G | 2021-02-17 | 2020-12-11 | 2021-08-20 | 2020-12-11 | G | 2021-02-16 | 2020-12-11 | 2021-02-16 | 2020-12-11 | G | 2020-06-04 | 2019-06-05 | 2021-03-25 | 2019-06-05 | G | [5 empty] | 2021-09-14 |  | 2021-09-14 |  | G | 2021-12-08 |  | 2022-03-08 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.13983
2378 | 113767 | NORTON ROAD - CONSTRUCT NEW SIDEWALK-PHASE 2 AND PHASE 3 | 0000 | Urban | Facilities for Pedestrians and Bicycles | Locally | Wise | WISE | Bristol | NonMPO:NonMPO | Infrastructure Investment Division | Allan D Sumpter | Allan.Sumpter@VDOT.virginia.gov | (276) 525-6461 | Roger L Musser | Roger.Musser@VDOT.Virginia.gov | (276) 696-3260 | Laura Mullins |  |  | 0 |  | 0 | FY2023 | 717550 | 717550 | NO DATES SET YET-PE OPEN | G | Start Development milestone finished 387 days early | G | Project is on budget | 2021-05-03 |  | 2021-07-27 |  | G | 2021-07-28 | 2020-07-01 | 2021-07-30 | 2020-07-08 | G | 2021-08-02 |  | 2022-02-10 |  | G | [25 empty] | 2022-03-21 |  | 2022-11-18 |  | G | [5 empty] | 2023-03-02 |  | 2023-03-29 |  | G | 2023-06-16 |  | 2023-06-16 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.10507
2379 | 113920 | FRED. DIST. - TRAFFIC SIGNAL MUTCD UPGRADES (CN ONLY) | 9999 | Miscellaneous | Safety | VDOT | Fredericksburg District-wide |  | Fredericksburg | Fredericksburg:Fredericksburg District-wide | Infrastructure Investment Division | Emmett T Newton | Tommy.Newton@VDOT.Virginia.gov | (540) 899-4541 | Benjamin Ernst | Benjamin.Ernst@vdot.virginia.gov | (571) 585-0902 |  |  |  | 0 |  | 0 | FY2020 | 1085310 | 20793 | CONSTRUCTION STARTED | G | Start Delivery milestone finished on-time | G | Project is on budget | [10 empty] | 2019-10-01 | 2019-11-13 | 2020-02-13 | 2019-11-13 | G | [35 empty] | 2020-01-31 | 2020-01-31 | 2020-01-31 | 2020-01-31 | G | 2020-01-31 | 2020-01-31 | 2020-01-31 | 2020-01-31 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | WORK/TASK ORDER | 1 | 0 | 0.070178
2380 | 115131 | #SMART20 Intersection Improvements US 211/340 Big Oak Road | 0211 | Primary | Safety | VDOT | Page County | HARRISONBURG | Staunton | NonMPO:NonMPO | Infrastructure Investment Division | Randolph S Kiser | Randy.Kiser@VDOT.Virginia.gov | (540) 332-9092 | Ronald L Tabor | Ronald.Tabor@vdot.virginia.gov | (540) 332-7887 |  |  |  | 1 | 2020 | 0 | FY2025 | 3310977 | 3310977 | NO DATES SET YET-PE OPEN | Y | Determine Requirements milestone is 24 days ahead of the expected completion date and there is a risk of missing this milestone date | G | Project is on budget | [5 empty] | 2020-03-03 | 2019-12-02 | 2020-03-16 | 2019-12-27 | G | 2020-03-17 |  | 2021-03-17 |  | Y | [5 empty] | 2022-01-21 |  | 2022-02-03 |  | G | 2023-05-10 |  | 2023-05-23 |  | G | 2023-10-17 |  | 2024-04-25 |  | G | 2023-06-09 |  | 2023-12-15 |  | G | 2022-10-24 |  | 2023-05-03 |  | G | [5 empty] | 2024-05-14 |  | 2024-05-14 |  | G | 2024-08-05 |  | 2024-12-30 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.068395
2381 | 116280 | #I81CIP NB & SB MM 242 TO 248, 3-LANE WIDENING (ID #62) | 0081 | Interstate | Reconstruction w/ Added Capacity | VDOT | Harrisonburg | HARRISONBURG | Staunton | Harrisonburg:Harrisonburg | Infrastructure Investment Division | John-Allen L Ennis | JohnAllen.Ennis@VDOT.Virginia.gov | (540) 332-9118 | Scott A Alexander | Scott.Alexander@VDOT.Virginia.gov | (540) 332-9030 |  |  |  | 0 |  | 0 | FY2025 | 271786995 | 271786995 | NO DATES SET YET-PE OPEN | G | Start Development milestone finished 159 days early | G | Project is on budget | [5 empty] | 2020-07-01 | 2020-01-27 | 2020-07-15 | 2020-02-07 | G | 2020-07-16 | 2020-07-16 | 2021-08-24 |  | G | [5 empty] | 2022-08-23 |  | 2022-09-06 |  | G | 2023-12-05 |  | 2023-12-18 |  | G | 2024-05-15 |  | 2024-11-19 |  | G | 2024-01-05 |  | 2024-07-11 |  | G | 2023-05-22 |  | 2024-01-29 |  | G | [5 empty] | 2024-12-10 |  | 2024-12-10 |  | G | 2025-04-03 |  | 2025-04-03 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.13408
2382 | 117114 | #SGR21LP - CITY OF FREDERICKSBURG PLANK RD 3 E | 0003 | Primary | Resurfacing | VDOT | Fredericksburg | FREDERICKSBURG | Fredericksburg | Fredericksburg:Fredericksburg | Local Assistance Division | Anastasia Kapitan | Anastasia.Kapitan@vdot.virginia.gov | (540) 899-4292 | Richard A Spurlock | Richard.Spurlock@VDOT.Virginia.gov | (540) 899-4302 | Erik Nelson | enelson@fredericksburgva.gov | (540) 937-0572 | 0 |  | 1 | FY2023 | 400000 | 400000 | ACTIVITY DATES SET | G | Obtained Permits milestone finished 357 days early | G | Project is on budget | [10 empty] | 2020-07-31 | 2020-07-31 | 2020-08-13 | 2021-01-27 | R | [25 empty] | 2021-01-28 | 2021-01-28 | 2022-01-28 | 2021-02-05 | G | [5 empty] | 2023-04-11 |  | 2023-04-11 |  | G | 2023-06-29 |  | 2023-06-29 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.14372
2383 | 117139 | Twin Pines Road Widening- Swanonoa to Sunset | 0949 | Urban | Reconstruction w/o Added Capacity | Locally | Portsmouth | NORFOLK | Hampton Roads | Hampton Roads:Portsmouth | Local Assistance Division | Susan Wilson | Susan.Wilson@vdot.virginia.gov | (757) 956-3099 | Marci Thompson | Marci.Thompson@vdot.virginia.gov | (757) 956-3093 | James Wright | wrightj@portsmouthva.gov | (757) 393-8592 | 0 |  | 0 | FY2024 | 1800000 | 1800000 | NO DATES SET YET | R | Agreement with Locality milestone is 72 days past the expected completion date | G | Project is on budget | 2020-08-03 |  | 2020-12-11 |  | R | 2020-12-14 |  | 2021-01-05 |  | R | 2021-07-14 |  | 2021-11-04 |  | G | [25 empty] | 2022-11-01 |  | 2023-04-06 |  | G | [5 empty] | 2023-06-05 |  | 2023-06-30 |  | G | 2023-09-20 |  | 2023-09-20 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.11258
2384 | 57048 | #SMART18 - RTE 264 INTERCHNG IMPROVEMENTS 64WB RAMP TO 264EB | 0264 | Interstate | Reconstruction w/o Added Capacity | VDOT | Norfolk | NORFOLK | Hampton Roads | Hampton Roads:Norfolk | Infrastructure Investment Division | James A Klotz | James.Klotz@vdot.virginia.gov | (757) 274-2552 | James A Klotz | James.Klotz@vdot.virginia.gov | (757) 274-2552 |  |  |  | 1 | 2018 | 0 | FY2017 | 6635307 |  | CONSTRUCTION STARTED | G | Start Delivery milestone finished on-time | R | Critical information missing | [5 empty] | 2001-01-02 | 2001-02-12 | 2001-01-31 | 2001-02-28 | R | 2001-06-01 | 2000-08-25 | 2001-08-31 | 2000-12-04 | G | [5 empty] | 2011-07-14 | 2011-07-14 | 2014-10-22 | 2014-10-22 | G | 2015-02-02 | 2015-02-02 | 2015-04-30 | 2015-04-30 | G | 2016-03-15 | 2016-03-15 | 2017-06-29 | 2017-06-29 | G | 2015-09-03 | 2015-09-03 | 2016-10-05 | 2016-10-05 | G | 2001-08-30 | 2001-08-30 | 2016-05-27 | 2016-05-27 | G | [5 empty] | 2016-04-26 | 2016-04-26 | 2016-04-26 | 2016-04-26 | G | 2016-09-21 | 2016-09-21 | 2016-09-21 | 2016-09-21 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 1 | 0.20302
2385 | 104848 | RT 629 STRUCTURE OVER MIDDLE FORK KENT BRANCH | 0629 | Secondary | Bridge Replacement w/ Added Capacity | VDOT | Fluvanna County | LOUISA | Culpeper | NonMPO:NonMPO | Infrastructure Investment Division | Dewitt D Sprinkel | Brent.Sprinkel@VDOT.Virginia.gov | (540) 829-7552 | Bobby J Jenkins | Bobby.JenkinsJr@VDOT.Virginia.gov | (540) 829-7694 |  |  |  | 0 |  | 0 | FY2019 | 2457000 | 2457000 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 62 days early | G | Project is on budget | [5 empty] | 2013-07-01 | 2013-07-01 | 2013-07-01 | 2013-07-01 | G | 2017-09-15 | 2017-09-15 | 2017-12-01 | 2017-12-01 | G | [5 empty] | 2017-12-13 | 2017-12-13 | 2017-12-28 | 2017-12-28 | G | 2018-05-01 | 2018-03-06 | 2018-05-15 | 2018-03-26 | G | [5 empty] | 2018-06-01 | 2018-04-04 | 2018-12-11 | 2018-10-02 | G | [10 empty] | 2018-11-01 | 2018-09-10 | 2018-12-11 | 2018-10-09 | G | 2019-02-20 | 2018-12-27 | 2019-02-27 | 2018-12-27 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.072361
2386 | 106978 | OPEN CONTAINER - DISTRICTWIDE PRIMARY SHOULDER RUMBLE STRIPS | 9999 | Primary | Safety | VDOT | Rappahannock County | WARRENTON | Culpeper | NonMPO:NonMPO | Infrastructure Investment Division | Nathan Umberger |  |  | Caroline Awua-Mensah | Caroline.Awua-Mensah@vdot.virginia.gov | (540) 829-7618 |  |  |  | 0 |  | 0 | FY2019 | 3000000 | 3000000 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 482 days early | Y | Estimate not current | [5 empty] | 2016-07-01 | 2015-09-03 | 2016-07-15 | 2015-09-11 | G | 2016-07-18 | 2015-09-03 | 2016-08-12 | 2016-05-18 | G | [35 empty] | 2018-07-20 | 2017-04-26 | 2018-07-20 | 2017-04-26 | G | 2018-09-04 | 2017-05-30 | 2018-09-24 | 2017-05-30 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | WORK/TASK ORDER | 1 | 0 | 0.082963
2387 | 107529 | Rte 627 - Widen Road, Improve Ditches and Straighten Curve | 0627 | Secondary | Reconstruction w/o Added Capacity | VDOT | Surry County | WILLIAMSBURG | Hampton Roads |  | Infrastructure Investment Division | Christopher R Carroll | C.Carroll@VDOT.Virginia.gov | (757) 253-5140 | Kenneth D Mckinna | Kenneth.McKinna@VDOT.Virginia.gov | (757) 956-3271 |  |  |  | 0 |  | 0 | FY2029 | 2471222 | 2471222 | NO DATES SET YET | G | Start Development milestone is 1270 days ahead of the expected completion date | Y | Estimate not current | [5 empty] | 2024-08-01 |  | 2024-08-14 |  | G | 2024-08-15 |  | 2025-07-15 |  | G | [5 empty] | 2026-05-20 |  | 2026-06-03 |  | G | 2027-09-08 |  | 2027-09-21 |  | G | 2028-02-22 |  | 2028-08-23 |  | G | 2027-10-07 |  | 2028-04-18 |  | G | 2027-03-01 |  | 2027-08-31 |  | G | [5 empty] | 2028-09-12 |  | 2028-09-12 |  | G | 2028-10-27 |  | 2028-12-27 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 1 | 0.2221
2388 | 109070 | SYSTEMIC ROAD DEPARTURE COUNTERMEASURES WITH RUMBLE STRIPS | 9999 | Primary | Safety | VDOT | Staunton District-wide |  | Staunton | NonMPO:NonMPO | Infrastructure Investment Division | Keith M Rider | Keith.Rider@VDOT.Virginia.gov | (434) 856-8145 | Kunal Kothawade | Kunal.Kothawade@vdot.virginia.gov | (540) 332-9259 |  |  |  | 0 |  | 0 | FY2019 | 1499000 | 1499000 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 111 days early | G | Project is on budget | [5 empty] | 2016-11-30 | 2016-09-08 | 2016-12-13 | 2016-09-21 | G | 2016-12-14 | 2016-09-22 | 2017-08-07 | 2016-10-06 | G | [5 empty] | 2017-06-26 | 2017-06-22 | 2017-08-07 | 2017-06-22 | G | [5 empty] | 2017-06-29 | 2017-05-15 | 2017-06-29 | 2017-05-15 | G | [15 empty] | 2018-10-09 | 2018-08-14 | 2018-10-09 | 2018-08-14 | G | 2018-12-04 | 2018-09-04 | 2018-12-24 | 2018-09-04 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | WORK/TASK ORDER | 1 | 0 | 0.068698
2389 | 109951 | Henrico County Automated Traffic Management System (ATMS) | 0000 | Secondary | Safety | Locally | Henrico County | ASHLAND | Richmond | Richmond:Henrico County | Local Assistance Division | Douglas L Orcutt | Doug.Orcutt@vdot.virginia.gov | (804) 609-5428 | Douglas L Orcutt | Doug.Orcutt@vdot.virginia.gov | (804) 609-5428 | Sharon Smidler | smi20@henrico.us | (804) 501-4617 | 0 |  | 0 | FY2022 | 9805731 | 9805731 | NO DATES SET YET-PE OPEN | R | Determine Requirements milestone is 447 days past the expected completion date | G | Project is on budget | 2018-04-17 | 2018-04-17 | 2018-04-17 | 2018-04-17 | G | 2018-08-31 | 2019-02-18 | 2019-04-01 | 2019-02-22 | G | 2019-04-02 |  | 2019-12-02 |  | R | [35 empty] | 2020-11-18 |  | 2021-01-04 |  | R | 2021-01-05 |  | 2021-07-01 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.33726
2390 | 115917 | PEDESTRIAN CROSSINGS - BRISTOL DISTRICTWIDE | 9999 | Primary | Safety | VDOT | Bristol District-wide |  | Bristol | NonMPO:NonMPO | Infrastructure Investment/Asset Management Division | Brian Holt | Brian.Holt@vdot.virginia.gov | (276) 696-3414 | Jeremy J Mullins | Jeremy.Mullins@vdot.virginia.gov | (276) 696-3259 |  |  |  | 0 |  | 0 | FY2025 | 310968 | 310968 | NO DATES SET YET | Y | Start Development milestone is 9 days ahead of the expected completion date and there is a risk of missing this milestone date | Y | Estimate not current | [5 empty] | 2021-01-19 |  | 2021-03-02 |  | Y | 2021-03-03 |  | 2022-05-12 |  | G | [35 empty] | 2024-07-09 |  | 2024-07-09 |  | G | 2024-09-27 |  | 2024-09-27 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.079465
2391 | 116592 | DISTRICT-WIDE SYSTEMIC UNSIGNALIZED INTER (FY23-FY25) | 9999 | Miscellaneous | Safety | VDOT | Fredericksburg District-wide |  | Fredericksburg | Fredericksburg:Fredericksburg District-wide | Infrastructure Investment Division | Peter A Hedrich | Peter.Hedrich@vdot.virginia.gov | (540) 899-4540 | Jessica Graves | Jessica.Graves@vdot.virginia.gov | (540) 899-4267 |  |  |  | 0 |  | 0 | FY2023 | 222222 | 222222 | NO DATES SET YET | G | Start Development milestone is 596 days ahead of the expected completion date | G | Project is on budget | [5 empty] | 2022-10-10 |  | 2022-10-10 |  | G | 2022-10-11 |  | 2023-01-26 |  | G | [5 empty] | 2023-02-08 |  | 2023-02-22 |  | G | [25 empty] | 2023-03-10 |  | 2023-03-16 |  | G | 2023-03-17 |  | 2023-03-23 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | WORK/TASK ORDER | 0 | 0 | 0.070056
2392 | 117115 | Grant Street New Roadway | 0134 | Urban | New Construction Roadway | Locally | Hampton | WILLIAMSBURG | Hampton Roads | Hampton Roads:Hampton | Local Assistance Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Derrick Williams | Derrick.Williams@vdot.virginia.gov | (757) 956-3097 | Sandon Rogers | Sandon.rogers@hampton.gov | (757) 727-6786 | 0 |  | 0 | FY2024 | 5784000 | 5784000 | NO DATES SET YET | R | Agreement with Locality milestone is 72 days past the expected completion date | G | Project is on budget | 2020-08-03 |  | 2020-12-11 |  | R | 2020-12-14 |  | 2021-01-05 |  | R | 2021-07-14 |  | 2021-11-04 |  | G | [10 empty] | 2023-03-03 |  | 2023-04-06 |  | G | [5 empty] | 2023-04-07 |  | 2023-09-05 |  | G | 2023-08-02 |  | 2024-01-04 |  | G | [5 empty] | 2023-12-12 |  | 2024-01-10 |  | G | 2024-04-02 |  | 2024-04-02 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.20548
2393 | 117142 | #SGR21LP - CITY OF FREDERICKSBURG PLANK RD 3 E (291) | 0003 | Primary | Resurfacing | VDOT | Fredericksburg | FREDERICKSBURG | Fredericksburg | Fredericksburg:Fredericksburg | Local Assistance Division | Jessica Graves | Jessica.Graves@vdot.virginia.gov | (540) 899-4267 | Jessica Graves | Jessica.Graves@vdot.virginia.gov | (540) 899-4267 | Erik Nelson | enelson@fredericksburgva.gov | (540) 937-0572 | 0 |  | 1 | FY2022 | 400000 | 272869 | ACTIVITY DATES SET | Y | Solicit Bids milestone is 51 days ahead of the expected completion date and there is a risk of missing this milestone date | G | Project is on budget | [10 empty] | 2021-07-30 | 2020-12-01 | 2021-08-12 | 2020-12-21 | G | [35 empty] | 2021-04-13 |  | 2021-04-13 |  | Y | 2021-07-01 |  | 2021-07-01 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.14359
2394 | 86316 | #SGR17VB - BR Repl RT 723 over Opequon Creek Va STR 6904 | 0723 | Secondary | Bridge Replacement w/ Added Capacity | VDOT | Frederick County | EDINBURG | Staunton | Winchester:Frederick County | Infrastructure Investment/Asset Management Division | Jerry Copp |  |  | Jean Uhl | Jean.Uhl@vdot.virginia.gov | (540) 332-9267 |  |  |  | 0 |  | 1 | FY2021 | 1745365 | 2386299 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 666 days early | R | Project estimate is less than $5M and is 20% or more over budget | [5 empty] | 2010-07-01 | 2010-07-19 | 2010-07-01 | 2010-07-19 | R | 2010-10-04 | 2010-10-04 | 2011-01-31 | 2011-04-14 | R | [10 empty] | 2015-09-03 | 2015-09-03 | 2015-09-28 | 2015-09-28 | G | [5 empty] | 2017-07-24 | 2017-07-24 | 2017-10-30 | 2017-10-30 | G | 2017-07-05 | 2017-07-05 | 2018-06-07 | 2018-06-07 | G | [5 empty] | 2017-10-10 | 2017-10-10 | 2020-11-10 | 2018-11-06 | G | 2018-09-20 | 2019-01-23 | 2020-11-19 | 2019-01-23 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.071542
2395 | 105786 | ADD ADA COMPLIANT SIDEWALK & RETAINING WALL TO 18TH ST | 0120 | Primary | Facilities for Pedestrians and Bicycles | Locally | Arlington County | FAIRFAX | Northern Virginia | Northern Virginia:Arlington County | Local Assistance Division | Bud Siegel |  |  | Rita Hockman | Rita.Hockman@vdot.virginia.gov | (804) 824-7421 | Ravinder K. Singh, PE | rksingh@arlingtonva.us | (571) 220-1882 | 0 |  | 0 | FY2020 | 375000 | 1734372 | CONSTRUCTION STARTED | R | Start Delivery milestone finished 337 days late | R | Project estimate is less than $5M and is 20% or more over budget | 2015-06-01 | 2015-05-27 | 2015-08-31 | 2015-06-10 | G | 2015-10-01 | 2015-09-01 | 2015-10-01 | 2015-09-01 | G | 2015-11-02 | 2015-11-02 | 2016-08-01 | 2016-06-01 | G | [35 empty] | 2019-06-01 | 2020-05-08 | 2019-06-01 | 2020-07-10 | R | 2019-09-03 | 2020-07-13 | 2020-01-02 | 2020-12-04 | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.2098
2396 | 107123 | Route 58 Grayson Co Shoulder & Rumble Strips | 0058 | Primary | Safety | VDOT | Grayson County | WYTHEVILLE | Bristol | NonMPO:NonMPO | Infrastructure Investment Division | John W Bechtold | John.Bechtold@vdot.virginia.gov | (276) 696-3365 | Brandi Halloway | Brandi.Halloway@vdot.virginia.gov | (276) 696-3254 |  |  |  | 0 |  | 0 | FY2019 | 670000 | 1474359 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished on-time | R | Project estimate is less than $5M and is 20% or more over budget | [5 empty] | 2017-07-05 | 2017-07-05 | 2017-07-18 | 2017-07-13 | G | 2017-07-19 | 2017-07-18 | 2017-08-15 | 2018-02-02 | R | [35 empty] | 2018-05-22 | 2018-05-22 | 2018-05-22 | 2018-05-22 | G | 2018-07-16 | 2018-07-16 | 2018-07-16 | 2018-07-16 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.066355
2397 | 108868 | Roanoke Street Sidewalk Construction | 0460 | Urban | Facilities for Pedestrians and Bicycles | Locally | Christiansburg | CHRISTIANSBURG | Salem | New River Valley:Christiansburg | Local Assistance Division | Adam J Czesnowski | Adam.Czesnowski@vdot.virginia.gov | (540) 541-1216 | Adam J Czesnowski | Adam.Czesnowski@vdot.virginia.gov | (540) 541-1216 | Wayne Nelson | wnelson@christiansburg.org | (540) 382-6120 | 0 |  | 0 | FY2019 | 374590 | 374590 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 15 days early | G | Project is on budget | 2016-07-01 | 2016-07-01 | 2016-09-26 | 2016-08-29 | G | 2016-09-27 | 2016-10-05 | 2016-09-29 | 2016-10-12 | R | 2016-09-30 | 2016-08-29 | 2017-04-12 | 2017-05-05 | R | [10 empty] | 2018-03-21 | 2018-04-10 | 2018-04-10 | 2018-04-10 | G | [5 empty] | 2018-04-12 | 2018-04-10 | 2018-05-17 | 2018-04-10 | G | [10 empty] | 2018-06-05 | 2018-06-29 | 2018-07-02 | 2018-07-01 | G | 2018-07-03 | 2018-12-18 | 2019-01-02 | 2018-12-18 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.095989
2398 | 109594 | TOWN OF LEESBURG - BATTLEFIELD PKWY SHARED USE PATH @ RTE 15 |  | Urban | Safety | Locally | Leesburg | LEESBURG | Northern Virginia | Northern Virginia:Leesburg | Local Assistance Division | Kimberly Mccool | Kimberly.McCool@vdot.virginia.gov | (703) 259-3220 | Veljibhai M Desai | Veljibhai.Desai@vdot.virginia.gov | (703) 259-2927 | Ann Geiger, TOWN OF LEESBURG CIP MANAGER | ageiger@leesburgva.gov | (703) 771-2742 | 0 |  | 0 | FY2020 | 726000 | 717078 | CONSTRUCTION COMPLETED | R | Start Delivery milestone finished 33 days late | G | Project is on budget | 2016-07-01 | 2016-08-30 | 2016-09-26 | 2016-10-13 | R | 2016-09-27 | 2016-09-14 | 2016-09-29 | 2016-09-14 | G | 2016-09-30 | 2017-07-01 | 2017-04-12 | 2018-04-17 | R | [10 empty] | 2018-12-31 | 2018-12-10 | 2019-01-23 | 2019-01-03 | G | [5 empty] | 2019-01-25 | 2019-01-07 | 2019-07-30 | 2019-04-08 | G | [10 empty] | 2019-08-15 | 2019-06-25 | 2019-09-12 | 2019-08-28 | G | 2019-09-13 | 2019-10-29 | 2019-10-24 | 2019-11-26 | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.35984
2399 | 110155 | Roanoke River Greenway - Blue Ridge Pkwy to Explore Park |  | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Roanoke County | SALEM | Salem | Roanoke:Roanoke County | Local Assistance Division | Cheryl B Becker | Cheryl.Becker@vdot.virginia.gov | (540) 492-2531 | Cheryl B Becker | Cheryl.Becker@vdot.virginia.gov | (540) 492-2531 | Roanoke County | dblount@roanokecountyva.gov | (540) 777-6321 | 0 |  | 0 | FY2021 | 1733750 | 1733750 | ACTIVITY DATES SET | R | Solicit Bids milestone is 223 days past the expected completion date | G | Project is on budget | 2017-06-05 | 2017-06-05 | 2017-11-21 | 2017-11-21 | G | 2017-12-08 | 2017-12-08 | 2017-12-14 | 2017-12-14 | G | 2017-12-29 | 2017-12-29 | 2018-07-20 | 2018-06-28 | G | [10 empty] | 2019-07-24 | 2019-08-13 | 2019-08-13 | 2019-08-13 | G | [5 empty] | 2019-08-15 | 2019-08-15 | 2020-05-28 | 2020-05-28 | G | [10 empty] | 2020-06-15 |  | 2020-07-13 |  | R | 2020-07-14 |  | 2020-12-07 |  | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.34155
2400 | 110893 | #SGR18LB - BRIDGE REPAIR RT 250 BYPASS OVER NS RAILROAD | 0250 | Urban | Bridge Rehab w/o Added Capacity | Locally | Charlottesville | CHARLOTTESVILLE | Culpeper | Charlottesville:Charlottesville | Infrastructure Investment Division | Ken Connors |  |  | Michael D Barnes | MichaelD.Barnes@vdot.virginia.gov | (434) 422-9861 | Kyle Kling | klingk@charlottesville.gov | (434) 970-3182 | 0 |  | 1 | FY2021 | 1303496 | 1226832 | CONSTRUCTION STARTED | G | Start Delivery milestone finished on-time | G | Project is on budget | 2018-01-02 | 2018-01-02 | 2018-03-29 | 2018-03-19 | G | 2018-03-30 | 2018-03-30 | 2018-04-03 | 2018-04-03 | G | 2018-04-04 | 2018-04-04 | 2018-10-05 | 2018-10-05 | G | [10 empty] | 2019-10-09 | 2019-10-09 | 2019-10-30 | 2019-10-17 | G | [5 empty] | 2019-11-01 | 2019-10-18 | 2020-08-13 | 2020-06-08 | G | [10 empty] | 2020-08-31 | 2020-08-24 | 2020-09-28 | 2020-09-11 | G | 2020-09-29 | 2020-09-14 | 2020-11-09 | 2020-11-09 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.20642
2401 | 111093 | RTE 58 EB - SHOULDER WIDENING / RUMBLE STRIPS / GR UPGRADES | 0058 | Primary | Safety | VDOT | Pittsylvania County | HALIFAX | Lynchburg | NonMPO:NonMPO | Infrastructure Investment Division | Veljibhai M Desai | Veljibhai.Desai@vdot.virginia.gov | (703) 259-2927 | Lindsey S Hodges | Lindsey.Hodges@vdot.virginia.gov | (434) 856-8143 |  |  |  | 0 |  | 0 | FY2019 | 3404322 | 3340068 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 25 days early | G | Project is on budget | [5 empty] | 2017-06-21 | 2017-06-29 | 2017-07-05 | 2017-06-29 | G | 2017-07-06 | 2018-03-21 | 2018-06-04 | 2018-06-27 | R | [5 empty] | 2018-06-27 | 2018-06-27 | 2018-06-27 | 2018-06-27 | G | 2018-08-16 | 2018-08-16 | 2018-08-16 | 2018-08-16 | G | 2018-06-21 | 2018-06-21 | 2018-06-21 | 2018-06-21 | G | 2018-08-16 | 2018-08-16 | 2018-08-16 | 2018-08-16 | G | [10 empty] | 2018-12-11 | 2018-12-04 | 2018-12-11 | 2018-12-04 | G | 2019-02-05 | 2019-02-22 | 2019-03-19 | 2019-02-22 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.080577
2402 | 111712 | #SMART18 - Route 1 (Marina Dr. to Merriewood Rd.) Sidewalk | 0001 | Primary | Safety | Locally | Chesterfield County | CHESTERFIELD | Richmond | Richmond:Chesterfield County | Infrastructure Investment Division | Michael S Gray | Mike.Gray@vdot.virginia.gov | (804) 609-5347 | Michael S Gray | Mike.Gray@vdot.virginia.gov | (804) 609-5347 | Barb Smith | smithbk@chesterfield.gov | 7481037 | 1 | 2018 | 0 | FY2022 | 2082640 | 3299000 | NO DATES SET YET-PE OPEN | R | Determine Requirements milestone is 318 days past the expected completion date | R | Project estimate is less than $5M and is 20% or more over budget | 2019-07-01 | 2018-07-10 | 2019-09-24 | 2018-10-23 | G | 2019-09-25 | 2018-11-13 | 2021-09-30 | 2018-11-15 | G | 2019-09-30 | 2018-11-16 | 2020-04-09 |  | R | [5 empty] | 2020-11-30 |  | 2020-11-30 |  | R | 2021-02-04 |  | 2021-02-25 |  | Y | 2022-04-01 |  | 2023-03-31 |  | G | 2021-03-01 |  | 2021-12-07 |  | G | 2022-12-30 | 2020-11-30 | 2023-04-28 |  | G | [5 empty] | 2021-12-23 |  | 2022-01-25 |  | G | 2022-01-26 |  | 2022-03-08 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.10239
2403 | 113222 | CHURCH ST NE - SIDEWALK, CURB AND GUTTER | 6933 | Urban | Facilities for Pedestrians and Bicycles | Locally | Vienna | FAIRFAX | Northern Virginia | Northern Virginia:Vienna | Local Assistance Division | Andrew G Beacher | Andrew.Beacher@vdot.virginia.gov | (703) 259-2239 | Rita Hockman | Rita.Hockman@vdot.virginia.gov | (804) 824-7421 | Michael Gallagher | Michael.Gallagher@viennava.gov | (703) 255-6389 | 0 |  | 0 | FY2019 | 660000 | 660000 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 111 days early | G | Project is on budget | 2018-10-31 | 2018-09-01 | 2019-03-29 | 2018-10-26 | G | 2019-06-21 | 2018-10-29 | 2019-07-31 | 2018-10-30 | G | 2018-10-31 | 2018-11-15 | 2019-05-30 | 2018-12-14 | G | [10 empty] | 2018-09-04 | 2018-09-04 | 2019-01-23 | 2019-01-23 | G | [5 empty] | 2019-01-02 | 2019-01-02 | 2019-01-15 | 2019-01-15 | G | [10 empty] | 2019-01-24 | 2019-01-24 | 2019-01-24 | 2019-01-24 | G | 2019-01-25 | 2019-01-25 | 2019-05-16 | 2019-01-25 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.17239
2404 | 113479 | #SGR19LB??- Lakeside Ave over N. Run - Rep Br (Fed ID 9657) | 0161 | Urban | Bridge Replacement w/o Added Capacity | Locally | Henrico County | ASHLAND | Richmond | Richmond:Henrico County | Local Assistance Division | Cynthia Crouch | Cynthia.Crouch@vdot.virginia.gov | (804) 609-5313 | Cynthia Crouch | Cynthia.Crouch@vdot.virginia.gov | (804) 609-5313 | Robin Wilder | wil47@henrico.us | (804) 727-8252 | 0 |  | 1 | FY2023 | 6882446 | 6882446 | NO DATES SET YET | R | Agreement with Locality milestone is 124 days past the expected completion date | G | Project is on budget | 2020-07-27 | 2020-07-10 | 2020-10-20 |  | R | 2020-10-21 |  | 2020-11-20 |  | R | 2020-11-23 |  | 2021-06-02 |  | G | [5 empty] | 2021-11-30 |  | 2022-01-12 |  | G | 2022-03-30 |  | 2022-04-19 |  | G | 2022-12-23 |  | 2023-08-31 |  | G | 2022-04-21 |  | 2023-02-02 |  | G | 2021-07-09 |  | 2022-03-17 |  | G | [5 empty] | 2023-02-21 |  | 2023-03-20 |  | G | 2023-06-07 |  | 2023-06-07 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.19546
2405 | 113609 | GEMINI WAY PEDESTRIAN IMPROVEMENTS | 2491 | Secondary | Facilities for Pedestrians and Bicycles | Locally | Prince William County | MANASSAS | Northern Virginia | Northern Virginia:Prince William County | Local Assistance Division | Claudia H Llana | Claudia.Llana@VDOT.Virginia.gov | (703) 259-1768 | Jeffrey S Daily | Jeff.Daily@VDOT.Virginia.gov | (703) 259-2993 | Javier Ibe | jibe@pwcgov.org | (703) 792-8164 | 0 |  | 0 | FY2023 | 1090265 | 1140265 | ACTIVITY DATES SET | G | Relocate Utilities milestone finished on-time | Y | Project estimate is less than $5M and is up to 20% over budget | 2018-04-17 | 2018-04-17 | 2018-11-14 | 2018-11-14 | G | 2018-11-14 | 2018-11-14 | 2019-01-03 | 2019-01-03 | G | 2018-12-31 | 2018-12-31 | 2019-01-08 | 2020-02-20 | R | [10 empty] | 2020-02-18 | 2020-02-18 | 2020-02-19 | 2020-02-19 | G | 2020-02-21 | 2020-02-21 | 2020-02-21 | 2020-02-21 | G | 2020-02-20 | 2020-02-20 | 2020-02-20 | 2020-02-20 | G | [10 empty] | 2020-12-09 |  | 2022-07-26 |  | G | 2022-10-13 |  | 2023-03-29 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.30866
2406 | 113867 | WRONG WAY MITIGATION AT RAMPS - DISTRICTWIDE | 9999 | Miscellaneous | Safety | VDOT | Richmond District-wide |  | Richmond | Richmond:Richmond District-wide | Infrastructure Investment Division | Adam S Brooks | Adam.Brooks@VDOT.Virginia.gov | (804) 609-5274 | Adam S Brooks | Adam.Brooks@VDOT.Virginia.gov | (804) 609-5274 |  |  |  | 0 |  | 0 | FY2025 | 373024 | 373024 | NO DATES SET YET-PE OPEN | G | Obtained Permits milestone finished 2072 days early | G | Project is on budget | [5 empty] | 2022-12-01 | 2018-09-05 | 2022-12-14 | 2018-09-10 | G | 2022-12-15 | 2018-09-11 | 2023-08-08 |  | G | [5 empty] | 2024-04-17 |  | 2024-05-29 |  | G | [5 empty] | 2024-09-12 |  | 2025-01-09 |  | G | [5 empty] | 2024-08-27 | 2019-04-01 | 2024-12-02 | 2019-04-01 | G | [5 empty] | 2025-01-14 |  | 2025-01-14 |  | G | 2025-04-08 |  | 2025-04-08 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.067604
2407 | 114661 | ARC -Floyd Regional Commerce Road construction | 0000 | Secondary | New Construction Roadway | Locally | Floyd County | CHRISTIANSBURG | Salem | NonMPO:NonMPO | Local Assistance Division | Adam J Czesnowski | Adam.Czesnowski@vdot.virginia.gov | (540) 541-1216 | Adam J Czesnowski | Adam.Czesnowski@vdot.virginia.gov | (540) 541-1216 | Lydeana Martin | lmartin@floydcova.org | (540) 745-9300 | 0 |  | 0 | FY2021 | 2552593 | 2552593 | ACTIVITY DATES SET | R | Engage Public milestone baseline missing | G | Project is on budget | 2019-02-01 | 2019-02-01 | 2019-04-26 | 2019-04-02 | G | 2019-04-29 | 2019-04-05 | 2019-05-01 | 2019-05-10 | R | 2019-05-02 | 2020-06-12 | 2019-11-05 | 2021-02-08 | R |  |  |  |  | R | [20 empty] | 2019-12-16 |  | 2020-08-18 |  | R | [5 empty] | 2020-11-24 |  | 2020-12-23 |  | R | 2021-03-18 |  | 2021-03-18 |  | Y |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.15849
2408 | 115115 | RICHMOND AVENUE- Primary Extension Paving |  | Urban | Resurfacing | Locally | Staunton | HARRISONBURG | Staunton | SAW:Staunton | Local Assistance Division | Donald F Komara | Donald.Komara@VDOT.Virginia.gov | (540) 434-2587 | Michael S Fulcher | Michael.Fulcher@VDOT.Virginia.gov | (540) 332-2243 | City of Staunton | yanceysc@ci.staunton.va.us | (540) 332-3892 | 0 |  | 0 | FY2020 | 134862 | 134862 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 89 days early | G | Project is on budget | 2019-08-01 | 2019-08-01 | 2019-10-25 | 2019-12-17 | R | [5 empty] | 2019-08-01 | 2019-08-01 | 2019-08-14 | 2019-08-14 | G | [25 empty] | 2019-08-15 | 2019-12-18 | 2019-12-30 | 2019-12-18 | G | [5 empty] | 2019-12-31 | 2020-01-06 | 2020-03-31 | 2020-03-31 | G | 2020-06-18 | 2020-04-01 | 2020-06-30 | 2020-04-02 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.063125
2409 | 115251 | Rte 60 W Roanoke St _ Resurfacing | 0060 | Urban | Resurfacing | Locally | Richmond | ASHLAND | Richmond | Richmond:Richmond | Local Assistance Division | Brian J Lokker | Brian.Lokker@VDOT.Virginia.gov | (804) 524-6010 | Brian J Lokker | Brian.Lokker@VDOT.Virginia.gov | (804) 524-6010 | Kenny Horak | Kenneth.horak@richmondgov.com | (804) 646-4781 | 0 |  | 0 | FY2020 | 172943 | 172943 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 5 days early | G | Project is on budget | 2019-07-01 | 2019-04-16 | 2019-09-24 | 2020-01-30 | R | [5 empty] | 2019-09-25 | 2020-01-30 | 2019-11-27 | 2020-02-13 | R | [25 empty] | 2020-02-10 | 2020-03-04 | 2020-04-29 | 2020-03-04 | G | [5 empty] | 2020-05-01 | 2020-03-19 | 2020-05-01 | 2020-03-19 | G | 2020-06-30 | 2020-06-25 | 2020-06-30 | 2020-06-25 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 |  | 1 | 0 | 0.081816
2410 | 111043 | #SGR18LB - Badger Road over Washington Ditch | 0674 | Urban | Bridge Replacement w/o Added Capacity | Locally | Suffolk | NORFOLK | Hampton Roads | Hampton Roads:Suffolk | Infrastructure Investment Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Johndel A Alcaide | John.Alcaide@vdot.virginia.gov | (757) 956-3098 | L Hansen | lhansen@suffolkva.us | (757) 514-7687 | 0 |  | 1 | FY2019 | 748326 | 748326 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 189 days early | G | Project is on budget | 2017-07-14 | 2017-07-14 | 2017-11-21 | 2017-10-05 | G | 2017-11-22 | 2017-11-22 | 2017-12-22 | 2017-12-21 | G | 2017-12-26 | 2017-12-22 | 2018-04-20 | 2018-03-16 | G | [25 empty] | 2018-04-03 | 2018-04-03 | 2018-05-29 | 2018-05-24 | G | [5 empty] | 2018-06-19 | 2018-03-30 | 2018-06-19 | 2018-04-01 | G | 2018-09-07 | 2018-05-30 | 2018-12-05 | 2018-05-30 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.10878
2411 | 111649 | Walnut Ave Bike/Ped Accommodations (5th St to Town limit) | 9999 | Miscellaneous | Facilities for Pedestrians and Bicycles | Locally | Vinton | SALEM | Salem | Roanoke:Vinton | Infrastructure Investment Division | Michael W Gray | Michael.Gray@VDOT.Virginia.gov | (540) 494-8288 | Jessie Nester | Jessie.Nester@vdot.virginia.gov | (540) 613-4115 | Anita McMillan |  | (540) 983-0607 | 0 |  | 0 | FY2022 | 1684030 | 1578639 | ACTIVITY DATES SET | G | Determine Requirements milestone finished on-time | G | Project is on budget | 2018-02-28 | 2018-02-28 | 2018-10-02 | 2018-11-16 | R | 2018-10-03 | 2018-11-30 | 2018-10-05 | 2018-11-30 | R | 2018-10-08 | 2019-07-16 | 2019-10-08 | 2019-10-08 | G | [35 empty] | 2021-09-30 |  | 2021-10-28 |  | G | 2021-11-22 |  | 2022-04-19 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.21019
2413 | 113387 | #SGR19VB - RT 33 over I64 - Super Repl - FED ID 12630 | 0033 | Primary | Bridge Replacement w/o Added Capacity | VDOT | New Kent County | ASHLAND | Richmond | Richmond:New Kent County | Infrastructure Investment/Asset Management Division | Noyan F Erermis | Noyan.Erermis@vdot.virginia.gov | (804) 819-9653 | Noyan F Erermis | Noyan.Erermis@vdot.virginia.gov | (804) 819-9653 | TBD |  |  | 0 |  | 0 | FY2025 | 9500000 | 9500000 | NO DATES SET YET-PE OPEN | G | Start Development milestone finished on-time | G | Project is on budget | [5 empty] | 2020-09-01 | 2020-09-01 | 2020-09-15 | 2020-09-15 | G | 2020-09-16 |  | 2021-08-13 |  | G | [5 empty] | 2022-07-20 |  | 2022-08-02 |  | G | 2023-10-03 |  | 2023-10-17 |  | G | 2024-03-18 |  | 2024-09-18 |  | G | 2023-11-01 |  | 2024-05-10 |  | G | 2023-09-26 |  | 2024-06-03 |  | G | [5 empty] | 2024-10-08 |  | 2024-10-08 |  | G | 2025-01-03 |  | 2025-01-03 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.084158
2414 | 113581 | RECONSTRUCTION - 312 LAFAYETTE BLVD | 0001 | Urban | Reconstruction w/o Added Capacity | Locally | Fredericksburg | FREDERICKSBURG | Fredericksburg | NonMPO:NonMPO | Infrastructure Investment Division | Richard A Spurlock | Richard.Spurlock@VDOT.Virginia.gov | (540) 899-4302 | Richard A Spurlock | Richard.Spurlock@VDOT.Virginia.gov | (540) 899-4302 | Erik Nelson | enelson@fredericksburgva.gov | (540) 937-0572 | 0 |  | 1 | FY2019 | 54742 | 54742 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 94 days early | G | Project is on budget | 2019-03-06 | 2018-07-30 | 2019-05-29 | 2018-10-23 | G | [5 empty] | 2019-03-06 | 2019-02-26 | 2019-03-19 | 2019-02-28 | G | [25 empty] | 2019-03-01 | 2019-02-28 | 2019-05-23 | 2019-02-28 | G | [5 empty] | 2019-05-24 | 2019-01-07 | 2019-06-21 | 2019-03-01 | G | 2019-06-24 | 2019-03-12 | 2019-06-24 | 2019-03-22 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.078928
2415 | 113833 | Three Chopt Rd Sidewalk Impr. (Dinwiddie Ave to Bexhill Rd) | 7645 | Secondary | Facilities for Pedestrians and Bicycles | Locally | Henrico County | ASHLAND | Richmond | Richmond:Henrico County | Infrastructure Investment Division | Cynthia Crouch | Cynthia.Crouch@vdot.virginia.gov | (804) 609-5313 | Cynthia Crouch | Cynthia.Crouch@vdot.virginia.gov | (804) 609-5313 | Kevin Newcomb | NEW038@henrico.us | (804) 501-5532 | 0 |  | 0 | FY2023 | 2165000 | 2165000 | ACTIVITY DATES SET | G | Obtained Permits milestone finished 575 days early | G | Project is on budget | 2018-07-02 | 2018-07-02 | 2018-09-25 | 2019-02-05 | R | 2018-09-26 | 2019-02-06 | 2018-09-28 | 2019-02-12 | R | 2018-10-01 | 2019-02-13 | 2019-04-11 | 2019-04-10 | G | [10 empty] | 2021-05-14 |  | 2021-06-07 |  | G | 2022-02-01 |  | 2022-07-08 |  | G | 2021-06-09 |  | 2022-01-31 |  | G | 2021-11-22 | 2020-12-30 | 2022-07-28 | 2020-12-30 | G | [5 empty] | 2022-08-01 |  | 2022-08-31 |  | G | 2022-12-30 |  | 2022-12-30 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.26528
2416 | 113932 | #SGR19LB??- 2nd St RT 67 Clinch Rv Richland VA 1804 Fed 2246 | 0067 | Primary | Bridge Rehab w/o Added Capacity | VDOT | Richlands | LEBANON | Bristol | NonMPO:NonMPO | Infrastructure Investment/Asset Management Division | Gary Lester |  |  | Jason A Graham | Jason.Graham@vdot.virginia.gov | (276) 696-3383 |  |  |  | 0 |  | 1 | FY2022 | 1650000 | 1650000 | NO DATES SET YET-PE OPEN | R | Determine Requirements milestone is 24 days past the expected completion date | G | Project is on budget | [5 empty] | 2020-09-15 | 2018-10-01 | 2020-09-28 | 2018-10-12 | G | 2020-09-29 |  | 2021-01-28 |  | R | [35 empty] | 2021-11-09 |  | 2021-11-09 |  | G | 2022-02-07 |  | 2022-02-07 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.1429
2418 | 115199 | BUS ON SHOULDER AND TRANSIT ZONE | 9999 | Public Transportation | Transit | VDOT | Fairfax County | FAIRFAX | Northern Virginia | Northern Virginia:Fairfax County | Infrastructure Investment Division | Kamal S Suliman | Kamal.Suliman@VDOT.Virginia.gov | (703) 259-2231 | Marc A Cioffi | marc.cioffi@vdot.virginia.gov | (703) 259-2329 |  |  |  | 0 |  | 0 | FY2019 | 100000 | 100000 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 19 days early | G | Project is on budget | [5 empty] | 2019-02-15 | 2019-02-15 | 2019-02-15 | 2019-02-15 | G | 2019-02-19 | 2019-02-19 | 2019-05-28 | 2019-05-13 | G | [5 empty] | 2019-03-25 | 2019-03-25 | 2019-05-13 | 2019-05-13 | G | [25 empty] | 2019-05-30 | 2019-05-13 | 2019-06-05 | 2019-05-17 | G | 2019-06-06 | 2019-05-20 | 2019-06-12 | 2019-05-24 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | WORK/TASK ORDER | 1 | 0 | 0.074912
2420 | 115555 | #SMART20 - Scott's Add BRT Station Ped Safety/Streetscape | 9999 | Primary | Facilities for Pedestrians and Bicycles | Locally | Richmond | ASHLAND | Richmond | Richmond:Richmond | Infrastructure Investment Division | Melinda G Baicy | Melinda.Baicy@vdot.virginia.gov | (804) 609-5390 | Melinda G Baicy | Melinda.Baicy@vdot.virginia.gov | (804) 609-5390 | Lamont Benjamin |  |  | 1 | 2020 | 0 | FY2026 | 1612000 | 1612000 | NO DATES SET YET | G | Agreement with Locality milestone is 1041 days ahead of the expected completion date | G | Project is on budget | 2023-10-02 |  | 2023-12-29 |  | G | 2024-01-02 |  | 2024-01-04 |  | G | 2024-01-05 |  | 2024-07-11 |  | G | [25 empty] | 2024-08-16 |  | 2025-04-24 |  | G | [5 empty] | 2025-07-30 |  | 2025-08-26 |  | G | 2025-11-17 |  | 2025-11-17 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.12069
2421 | 115785 | Woodpecker Rd Safety Improvements Cattail Rd to Matoaca Rd | 0626 | Secondary | Safety | VDOT | Chesterfield County | CHESTERFIELD | Richmond | Tri-Cities:Chesterfield County | Infrastructure Investment Division | Evan Roberts | Evan.Roberts@vdot.virginia.gov | (804) 609-5427 | Evan Roberts | Evan.Roberts@vdot.virginia.gov | (804) 609-5427 |  |  |  | 0 |  | 0 | FY2021 | 387000 | 387000 | NO DATES SET YET-PE OPEN | R | Determine Requirements milestone is 226 days past the expected completion date | G | Project is on budget | [5 empty] | 2020-04-01 | 2020-03-10 | 2020-04-01 | 2020-03-17 | G | 2020-04-02 |  | 2020-07-10 |  | R | [5 empty] | 2020-07-23 |  | 2020-08-05 |  | R | [25 empty] | 2020-08-21 |  | 2020-08-27 |  | R | 2020-08-28 |  | 2020-09-03 |  | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | WORK/TASK ORDER | 0 | 1 | 0.21223
2422 | 115870 | #I81CIP NB EXIT 302 EXTEND DECELERATION LANE ( ID #48) | 0081 | Interstate | Reconstruction w/o Added Capacity | VDOT | Frederick County | EDINBURG | Staunton | NonMPO:NonMPO | Infrastructure Investment Division | John-Allen L Ennis | JohnAllen.Ennis@VDOT.Virginia.gov | (540) 332-9118 | Alexander Alvarado | Alexander.Alvarado@vdot.virginia.gov | (540) 332-7372 |  |  |  | 0 |  | 0 | FY2020 | 1047000 | 424766 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished on-time | G | Project is on budget | [5 empty] | 2019-09-06 | 2019-09-06 | 2019-09-19 | 2019-09-10 | G | 2019-09-20 | 2019-06-19 | 2020-05-15 | 2019-06-26 | G | [5 empty] | 2019-10-17 | 2019-10-17 | 2019-10-17 | 2019-10-17 | G | [5 empty] | 2019-08-23 | 2019-08-23 | 2019-08-23 | 2019-08-23 | G | [15 empty] | 2020-01-07 | 2020-01-07 | 2020-01-07 | 2020-01-07 | G | 2020-03-30 | 2020-03-30 | 2020-03-30 | 2020-03-30 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | SAAP CONTRACT | 1 | 0 | 0.063092
2423 | 116917 | SRTS: GORDON-BARBOUR ACCESS IMPROVEMENTS |  | Primary | Facilities for Pedestrians and Bicycles | VDOT | Gordonsville | LOUISA | Culpeper | NonMPO:NonMPO | Local Assistance Division | Gregory J Cooley | Gregory.Cooley@vdot.virginia.gov | (434) 906-7979 | Michael Jacobs | Mike.Jacobs@VDOT.Virginia.gov | (540) 829-7502 | Deborah Kendall | dkendall@gordonsville.org | 54083222 | 0 |  | 0 | FY2024 | 563980 | 563980 | NO DATES SET YET | R | Start Development milestone is 122 days past the expected completion date | G | Project is on budget | [5 empty] | 2020-10-01 |  | 2020-10-22 |  | R | 2020-10-23 |  | 2021-08-26 |  | G | [5 empty] | 2022-04-01 |  | 2022-04-28 |  | G | 2022-12-20 |  | 2023-01-27 |  | G | 2023-06-27 |  | 2023-10-26 |  | G | 2023-02-13 |  | 2023-07-12 |  | G | 2023-03-22 |  | 2023-08-17 |  | G | [5 empty] | 2023-11-14 |  | 2023-11-14 |  | G | 2024-02-08 |  | 2024-02-08 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.12896
2424 | 117152 | #SGR21LP City of Suffolk 1861 Whaleyville Blvd | 0013 | Urban | Resurfacing | Locally | Suffolk | NORFOLK | Hampton Roads | Hampton Roads:Suffolk | Infrastructure Investment/Asset Management Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Johndel A Alcaide | John.Alcaide@vdot.virginia.gov | (757) 956-3098 | Edward Heide | eheide@suffolkva.us | (757) 514-7615 | 0 |  | 1 | FY2022 | 243545 | 243545 | NO DATES SET YET | G | Agreement with Locality milestone is 80 days ahead of the expected completion date | G | Project is on budget | 2021-01-04 |  | 2021-05-12 |  | G | 2021-05-13 |  | 2021-06-03 |  | G | 2021-07-02 |  | 2021-08-04 |  | G | [25 empty] | 2021-07-08 |  | 2021-08-04 |  | G | [5 empty] | 2021-10-01 |  | 2021-10-29 |  | G | 2022-01-26 |  | 2022-01-26 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.067886
2425 | 117940 | #TAP21 RTE 47 - CONSTRUCT SIDEWALK | 0047 | Enhancement | Facilities for Pedestrians and Bicycles | VDOT | Charlotte C.H. | HALIFAX | Lynchburg | NonMPO:NonMPO | Local Assistance Division | Brian J Casto | Brian.Casto@VDOT.Virginia.gov | (434) 856-8276 | Brian J Casto | Brian.Casto@VDOT.Virginia.gov | (434) 856-8276 | KAREN PRICE | clerk@towncch.com | (434) 542-5781 | 0 |  | 0 | FY2024 | 454765 | 454765 | NO DATES SET YET | R | Start Development milestone is 3 days past the expected completion date | G | Project is on budget | [5 empty] | 2021-01-29 |  | 2021-02-18 |  | R | 2021-02-19 |  | 2021-12-21 |  | G | [5 empty] | 2022-07-22 |  | 2022-08-18 |  | G | 2023-04-14 |  | 2023-05-18 |  | G | 2023-10-18 |  | 2024-02-23 |  | G | 2023-06-05 |  | 2023-11-01 |  | G | 2023-07-12 |  | 2023-12-12 |  | G | [5 empty] | 2024-03-12 |  | 2024-03-12 |  | G | 2024-05-30 |  | 2024-05-30 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 1 | 0.21114
2426 | 118181 | Downtown - Rorer Avenue Drainage Improvement | 0000 | Urban | Mitigation of Water Pollution Due to Highway Runof | Locally | Roanoke | SALEM | Salem | Roanoke:Roanoke City | Local Assistance Division | Cheryl B Becker | Cheryl.Becker@vdot.virginia.gov | (540) 492-2531 | Cheryl B Becker | Cheryl.Becker@vdot.virginia.gov | (540) 492-2531 | Joseph Arthur | Joseph.Arthur@roanokeva.gov | (540) 853-5901 | 0 |  | 0 | FY2028 | 160000 | 160000 | NO DATES SET YET | G | Agreement with Locality milestone is 1422 days ahead of the expected completion date | G | Project is on budget | 2024-08-30 |  | 2025-01-13 |  | G | 2025-01-14 |  | 2025-02-05 |  | G | 2025-08-12 |  | 2025-12-08 |  | G | [10 empty] | 2027-04-01 |  | 2027-05-05 |  | G | [5 empty] | 2027-05-06 |  | 2027-10-04 |  | G | 2027-08-31 |  | 2028-02-04 |  | G | [5 empty] | 2028-01-12 |  | 2028-02-10 |  | G | 2028-05-01 |  | 2028-05-01 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.20246
2427 | 76402 | CONSTRUCT NEW 2 LANE CONNECTOR - PHASE 1 |  | Urban | New Construction Roadway | Locally | Radford | CHRISTIANSBURG | Salem | NonMPO:NonMPO | Infrastructure Investment Division | Adam J Czesnowski | Adam.Czesnowski@vdot.virginia.gov | (540) 541-1216 | Adam J Czesnowski | Adam.Czesnowski@vdot.virginia.gov | (540) 541-1216 | David Ridpath | David.Ridpath@radfordva.gov | (540) 731-3603 | 0 |  | 0 | FY2023 | 5627990 | 5627990 | ACTIVITY DATES SET | R | Determine Requirements milestone finished 278 days late | Y | Estimate not current | 2017-12-15 | 2017-12-15 | 2018-10-01 | 2018-06-26 | G | 2006-11-27 | 2006-11-27 | 2006-11-27 | 2006-11-27 | G | 2018-10-02 | 2019-07-09 | 2019-05-10 | 2020-02-12 | R | [10 empty] | 2021-06-01 |  | 2021-06-21 |  | G | [5 empty] | 2021-07-06 |  | 2022-05-12 |  | G | [10 empty] | 2022-07-13 |  | 2022-08-23 |  | G | 2022-08-24 |  | 2023-02-28 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.13976
2428 | 92999 | RTE 1 - FULLER HEIGHTS ROAD-FULLER ROAD RELOCATION PROJECT | 0001 | Primary | Reconstruction w/o Added Capacity | Locally | Prince William County | MANASSAS | Northern Virginia | Northern Virginia:Prince William County | Infrastructure Investment Division | Claudia H Llana | Claudia.Llana@VDOT.Virginia.gov | (703) 259-1768 | Jeffrey S Daily | Jeff.Daily@VDOT.Virginia.gov | (703) 259-2993 | Khattab Shammout | KShammout@pwcgov.org | (703) 792-6826 | 0 |  | 0 | FY2022 | 6603825 | 8042785 | ACTIVITY DATES SET | R | Complete Purchasing Right-of-Way milestone is 338 days past the expected completion date | R | Project estimate is between $5M and $10M and is a $1M or more over budget | [5 empty] | 2009-09-01 | 2009-09-09 | 2009-10-15 | 2009-09-09 | G | 2009-08-14 | 2011-08-08 | 2009-12-14 | 2011-08-08 | R | [5 empty] | 2012-03-01 | 2012-03-01 | 2012-04-04 | 2012-04-04 | G | 2012-07-16 | 2012-07-16 | 2012-07-23 | 2012-07-23 | G | [5 empty] | 2012-08-16 | 2012-08-16 | 2020-03-20 |  | R | [10 empty] | 2021-12-01 |  | 2021-12-01 |  | G | 2022-01-30 |  | 2022-01-30 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.25925
2429 | 98304 | TAZEWELL COUNTY FY 11 REVENUE SHARING LOCALLY ADMINISTERED | 9999 | Secondary | Reconstruction w/o Added Capacity | Locally | Tazewell County | LEBANON | Bristol | NonMPO:NonMPO | Local Assistance Division | Tabitha H Crowder | Tabitha.Crowder@vdot.virginia.gov | (276) 696-3482 | Tabitha H Crowder | Tabitha.Crowder@vdot.virginia.gov | (276) 696-3482 | Kenneth Dunford | kdunford@tazewellcounty.org | (276) 385-1217 | 0 |  | 0 | FY2019 | 405596 | 763000 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 108 days early | R | Project estimate is less than $5M and is 20% or more over budget | [5 empty] | 2010-11-15 | 2010-09-19 | 2013-09-01 | 2013-09-01 | G | 2014-05-01 | 2013-07-01 | 2014-09-01 | 2013-07-01 | G | [35 empty] | 2018-11-01 | 2018-08-01 | 2018-11-30 | 2018-08-31 | G | 2018-12-03 | 2018-09-03 | 2018-12-31 | 2018-09-14 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.10157
2430 | 115718 | #SMART20 US 33 (MARKET STREET) AND I-81 IMPROVEMENTS | 0033 | Primary | Bridge Replacement w/ Added Capacity | VDOT | Harrisonburg | HARRISONBURG | Staunton | Harrisonburg:Harrisonburg | Infrastructure Investment Division | John-Allen L Ennis | JohnAllen.Ennis@VDOT.Virginia.gov | (540) 332-9118 | John-Allen L Ennis | JohnAllen.Ennis@VDOT.Virginia.gov | (540) 332-9118 |  |  |  | 1 | 2020 | 0 | FY2023 | 7634231 | 7634231 | ACTIVITY DATES SET | R | Start Purchasing Right-of-Way milestone is 27 days past the expected completion date | G | Project is on budget | [5 empty] | 2019-10-30 | 2019-11-18 | 2019-11-13 | 2019-11-22 | R | 2019-11-14 | 2019-11-18 | 2020-02-13 | 2019-12-09 | G | [5 empty] | 2020-02-12 | 2020-02-12 | 2020-04-07 | 2020-03-26 | G | 2021-01-08 |  | 2021-01-25 |  | R | 2021-08-16 |  | 2022-10-11 |  | G | 2021-02-10 |  | 2021-10-11 |  | G | 2020-10-01 | 2020-10-01 | 2022-04-21 | 2020-10-01 | G | [5 empty] | 2022-11-08 |  | 2022-11-08 |  | G | 2022-11-09 |  | 2023-06-15 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.060371
2431 | 115832 | ITTF FY20 PERFORMANCE PARKING -COMMERCIAL CORRIDORS | 9999 | Miscellaneous | Traffic Management/Engineering | Locally | Arlington County | FAIRFAX | Northern Virginia | Northern Virginia:Arlington County | Infrastructure Investment Division | Catherine C Mcghee | Cathy.McGhee@VDOT.Virginia.gov | (434) 293-1973 | Susie X Lue | Susie.Lue@vdot.virginia.gov | (703) 259-2918 | Stephen Crim | scrim@arlingtonva.us | (703) 228-7494 | 0 |  | 0 | FY2023 | 0 | 0 | NO DATES SET YET | G | Agreement with Locality milestone is 123 days ahead of the expected completion date | R | Critical information missing | 2021-04-01 | 2020-07-15 | 2021-06-24 |  | G | 2021-06-25 |  | 2021-06-29 |  | G | 2021-06-30 |  | 2022-01-07 |  | G | [25 empty] | 2022-02-16 |  | 2022-10-18 |  | G | [5 empty] | 2023-01-30 |  | 2023-02-27 |  | G | 2023-05-16 |  | 2023-05-16 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.2069
2432 | 116843 | LAKE DRIVE, PHASE I RURAL ADDITION |  | Secondary | Reconstruction w/o Added Capacity | Locally | Warren County | EDINBURG | Staunton | NonMPO:NonMPO | Local Assistance Division | Kimberly Cameron | Kim.Cameron@vdot.virginia.gov | (540) 332-7886 | Kimberly Cameron | Kim.Cameron@vdot.virginia.gov | (540) 332-7886 | Bob Childerss | rchildress@warrencountyva.net | (540) 636-4600 | 0 |  | 0 | FY2025 | 475000 | 475000 | NO DATES SET YET | G | Agreement with Locality milestone is 107 days ahead of the expected completion date | G | Project is on budget | 2021-02-01 |  | 2021-06-08 |  | G | 2021-06-09 |  | 2021-06-29 |  | G | 2021-07-29 |  | 2021-11-22 |  | G | [25 empty] | 2023-12-28 |  | 2024-05-29 |  | G | [5 empty] | 2024-07-26 |  | 2024-08-22 |  | G | 2024-11-13 |  | 2024-11-13 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.20573
2433 | 117102 | Old Buckroe Rd Pedestrian Improvements |  | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Hampton | WILLIAMSBURG | Hampton Roads | Hampton Roads:Hampton | Local Assistance Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Derrick Williams | Derrick.Williams@vdot.virginia.gov | (757) 956-3097 | Sandon Rogers, P.E. | Sandon.Rogers@hampton.gov | (757) 727-6786 | 0 |  | 0 | FY2024 | 1050251 | 1050251 | NO DATES SET YET | G | Agreement with Locality milestone is 81 days ahead of the expected completion date | G | Project is on budget | 2021-01-05 |  | 2021-05-13 |  | G | 2021-05-14 |  | 2021-06-04 |  | G | 2021-11-02 |  | 2022-03-03 |  | G | [10 empty] | 2023-04-11 |  | 2023-05-08 |  | G | [5 empty] | 2023-05-09 |  | 2023-10-05 |  | G | 2023-09-07 |  | 2024-02-07 |  | G | [5 empty] | 2023-11-22 |  | 2024-02-13 |  | G | 2024-05-02 |  | 2024-05-02 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.36751
2434 | 117569 | #81 CIP DETOUR IMPROVEMENTS - EXIT 240 AND EXIT 323 | 9999 | Primary | Other | VDOT | Staunton District-wide |  | Staunton | NonMPO:NonMPO | Infrastructure Investment Division | Keith M Rider | Keith.Rider@VDOT.Virginia.gov | (434) 856-8145 | Kunal Kothawade | Kunal.Kothawade@vdot.virginia.gov | (540) 332-9259 |  |  |  | 0 |  | 0 | FY2023 | 1800000 | 1800000 | NO DATES SET YET-PE OPEN | G | Start Development milestone finished 14 days early | G | Project is on budget | [5 empty] | 2020-08-03 | 2020-08-03 | 2020-08-21 | 2020-08-07 | G | 2020-08-24 | 2020-08-10 | 2021-06-28 |  | G | [5 empty] | 2022-02-01 |  | 2022-03-01 |  | G | [5 empty] | 2022-10-19 |  | 2023-02-24 |  | G | [5 empty] | 2022-07-13 |  | 2022-12-13 |  | G | [5 empty] | 2023-03-14 |  | 2023-03-14 |  | G | 2023-06-01 |  | 2023-06-01 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.089161
2435 | 118089 | SPERRYVILLE PIKE SIDEWALK EXTENSION | 0522 | Primary | Facilities for Pedestrians and Bicycles | Locally | Culpeper | WARRENTON | Culpeper | NonMPO:NonMPO | Local Assistance Division | Gregory J Cooley | Gregory.Cooley@vdot.virginia.gov | (434) 906-7979 | John P Price | John.Price@VDOT.Virginia.gov | (540) 347-6371 | BEN HOLT | BHOLT@CULPEPERVA.GOV | (540) 829-8260 | 0 |  | 0 | FY2024 | 796891 | 796891 | NO DATES SET YET | G | Agreement with Locality milestone is 163 days ahead of the expected completion date | G | Project is on budget | 2021-03-29 |  | 2021-08-03 |  | G | 2021-08-04 |  | 2021-08-24 |  | G | 2022-03-09 |  | 2022-06-29 |  | G | [25 empty] | 2023-06-26 |  | 2023-11-27 |  | G | [5 empty] | 2024-01-29 |  | 2024-02-26 |  | G | 2024-05-14 |  | 2024-05-14 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.19921
2436 | 76401 | SAFETY IMPRV -- RTE 122 BURKS HILL RD @ TIGER TRL | 0122 | Urban | Safety | VDOT | Bedford | BEDFORD | Salem | NonMPO:NonMPO | Infrastructure Investment Division | Thomas W Digiulian | Thomas.DiGiulian@VDOT.Virginia.gov | (540) 387-5356 | Anthony L Handy | Tony.Handy@VDOT.Virginia.gov | (540) 352-9050 |  |  |  | 0 |  | 0 | FY2019 | 440813 | 450093 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 259 days early | Y | Project estimate is less than $5M and is up to 20% over budget | [5 empty] | 2006-08-01 | 2006-07-13 | 2006-08-31 | 2006-07-14 | G | 2005-12-02 | 2005-12-02 | 2017-07-03 | 2017-08-10 | R | 2017-05-03 | 2017-05-03 | 2017-08-07 | 2017-08-07 | G | [30 empty] | 2018-04-10 | 2018-04-10 | 2018-04-10 | 2018-04-10 | G | 2018-11-08 | 2018-06-25 | 2019-03-11 | 2018-06-25 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.17396
2437 | 90178 | #SGR17VB - RT 703 Over Eidson Creek VA Str. 6100 | 0703 | Secondary | Bridge Replacement w/o Added Capacity | VDOT | Augusta County | HARRISONBURG | Staunton | NonMPO:NonMPO | Infrastructure Investment/Asset Management Division | Ashraf A Antonius | Ashraf.Antonius@vdot.virginia.gov | (540) 332-9107 | Ashraf A Antonius | Ashraf.Antonius@vdot.virginia.gov | (540) 332-9107 |  |  |  | 0 |  | 1 | FY2021 | 2291800 | 2700000 | AWARDED | G | Start Delivery milestone finished 50 days early | Y | Project estimate is less than $5M and is up to 20% over budget | [5 empty] | 2013-10-15 | 2013-07-15 | 2013-10-15 | 2013-07-15 | G | 2013-11-15 | 2013-11-01 | 2014-03-18 | 2014-03-18 | G | [10 empty] | 2019-06-03 | 2019-05-29 | 2019-07-30 | 2019-06-11 | G | [5 empty] | 2019-06-13 | 2019-06-13 | 2020-07-27 | 2020-06-23 | G | 2018-04-18 | 2019-02-27 | 2019-03-14 | 2019-08-21 | R | [5 empty] | 2020-09-15 | 2020-11-04 | 2020-11-10 | 2020-11-04 | G | 2021-03-10 | 2021-01-26 | 2021-03-17 | 2021-01-26 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.061254
2438 | 95635 | RTE 211(WBL) BRIDGE REPLACEMENT OVER SF SHEN RIVER (PE Only) | 0211 | Primary | Bridge Replacement w/ Added Capacity | VDOT | Page County | HARRISONBURG | Staunton | NonMPO:NonMPO | Asset Management Division | Keith P Weakley | Keith.Weakley@VDOT.Virginia.gov | (703) 298-8428 | Michael L Branscome | Michael.Branscome@VDOT.Virginia.gov | (540) 332-2377 |  |  |  | 0 |  | 0 | FY2021 | 940000 | 1200000 | STUDY ONLY | G | Start Delivery milestone finished on-time | R | Project estimate is less than $5M and is 20% or more over budget | [5 empty] | 2010-07-16 | 2010-07-07 | 2010-09-01 | 2010-07-07 | G | 2013-01-02 | 2013-01-01 | 2013-02-19 | 2013-02-19 | G | [40 empty] | 2020-07-28 | 2020-07-21 | 2020-08-27 | 2020-08-27 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.069555
2439 | 105309 | #HB2.FY17 Widen Rte. 11 & I-81 south bound on & off ramps | 0011 | Urban | Reconstruction w/ Added Capacity | Locally | Bristol | ABINGDON | Bristol | Bristol:Bristol | Infrastructure Investment Division | John W Bechtold | John.Bechtold@vdot.virginia.gov | (276) 696-3365 | John W Bechtold | John.Bechtold@vdot.virginia.gov | (276) 696-3365 | Wallace McCulloch | wallace.mcculloch@bristolva.org | (276) 642-2316 | 1 | 2017 | 0 | FY2021 | 5850000 | 5850000 | ACTIVITY DATES SET | R | Solicit Bids milestone is 33 days past the expected completion date | G | Project is on budget | 2016-11-01 | 2013-10-11 | 2017-01-03 | 2014-01-10 | G | 2016-08-01 | 2014-01-13 | 2016-08-01 | 2015-12-22 | G | 2016-08-01 | 2016-10-31 | 2017-09-08 | 2017-05-10 | G | [10 empty] | 2019-02-06 | 2019-02-06 | 2019-07-31 | 2019-07-31 | G | [5 empty] | 2019-08-02 | 2019-08-02 | 2020-09-01 | 2021-01-04 | R | 2017-06-16 | 2017-06-16 | 2018-02-23 | 2018-02-23 | G | [5 empty] | 2020-10-16 |  | 2021-01-19 |  | R | 2021-04-08 |  | 2021-05-19 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.13028
2440 | 106692 | #SMART18 - I-64 Southside Widening and High-Rise Bridge Ph 1 | 0064 | Interstate | Reconstruction w/ Added Capacity | VDOT | Chesapeake | NORFOLK | Hampton Roads | Hampton Roads:Chesapeake | Infrastructure Investment Division | Dawn Odom | Dawn.Odom@vdot.virginia.gov | (000) 000-0000 | Ricardo Correa | Ricardo.Correa@vdot.virginia.gov | (757) 956-3106 |  |  |  | 1 | 2018 | 0 | FY2017 | 500000000 |  | CONSTRUCTION STARTED | R | Start Delivery milestone finished 280 days late | R | Critical information missing | [5 empty] | 2015-02-02 | 2015-02-02 | 2015-02-02 | 2015-02-02 | G | 2016-02-19 | 2016-02-19 | 2016-06-28 | 2016-06-28 | G | [5 empty] | 2016-10-31 | 2016-12-06 | 2016-11-14 | 2016-12-13 | R | 2016-12-06 | 2016-12-12 | 2016-12-12 | 2016-12-12 | G | [20 empty] | 2016-12-13 | 2016-12-14 | 2016-12-14 | 2016-12-14 | G | 2017-01-17 | 2017-10-24 | 2017-01-17 | 2017-10-24 | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NOT APPLICABLE | 1 | 1 | 0.36031
2441 | 107340 | N. King Street Improvements - Phase IV | 0278 | Urban | Reconstruction w/o Added Capacity | Locally | Hampton | WILLIAMSBURG | Hampton Roads | Hampton Roads:Hampton | Local Assistance Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Derrick Williams | Derrick.Williams@vdot.virginia.gov | (757) 956-3097 | Philippe Fenouil, P.E. | philippe.fenouli@hampton.gov | (757) 727-6197 | 0 |  | 0 | FY2019 | 865370 | 3012203 | ACTIVITY DATES SET | R | Solicit Bids milestone is 1167 days past the expected completion date | R | Project estimate is less than $5M and is 20% or more over budget | 2015-09-01 | 2015-07-02 | 2015-11-30 | 2015-07-02 | G | 2015-12-01 | 2015-07-24 | 2015-12-14 | 2015-08-04 | G | 2015-12-15 | 2015-08-07 | 2016-08-09 | 2016-11-01 | R | [10 empty] | 2017-06-29 | 2017-12-05 | 2017-07-13 | 2019-08-19 | R | [20 empty] | 2017-08-16 |  | 2017-12-12 |  | R | 2018-03-12 |  | 2018-08-28 |  | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.15842
2442 | 108774 | EDMUNDS STREET - DRAINAGE IMPROVEMENTS | 9999 | Urban | Restoration and Rehabilitation | Locally | South Boston | HALIFAX | Lynchburg | NonMPO:NonMPO | Local Assistance Division | John E Neblett | John.Neblett@VDOT.Virginia.gov | (434) 856-8202 | Gregg Allen | Gregg.Allen@vdot.virginia.gov | (434) 426-5575 | C.W. Crowder, Jr. | ccrowder@southboston.va.us | (434) 575-4261 | 0 |  | 0 | FY2020 | 493022 | 493022 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 325 days early | G | Project is on budget | 2016-10-03 | 2016-07-01 | 2016-12-30 | 2016-08-24 | G | 2017-01-03 | 2016-08-25 | 2017-01-05 | 2017-10-02 | R | 2017-01-06 | 2017-10-03 | 2017-07-13 | 2017-10-17 | R | [35 empty] | 2018-08-28 | 2018-08-13 | 2018-09-25 | 2018-08-13 | G | 2019-01-23 | 2018-10-02 | 2019-08-23 | 2018-10-02 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.074102
2443 | 109059 | Washington Ave Streetscape and Pedestrian Improvements |  | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Newport News | WILLIAMSBURG | Hampton Roads | Hampton Roads:Newport News | Local Assistance Division | Stephen Rowan | Steve.Rowan@vdot.virginia.gov | (757) 790-9925 | Chessica Villaflores | Chessica.Villaflores@vdot.virginia.gov | (757) 956-3094 | City of Newport News | dmcbride@nnva.gov | (757) 926-8715 | 0 |  | 0 | FY2022 | 1490000 | 1490000 | ACTIVITY DATES SET | G | Complete Purchasing Right-of-Way milestone finished 195 days early | G | Project is on budget | 2017-03-06 | 2017-03-06 | 2017-03-06 | 2017-03-06 | G | 2016-11-09 | 2016-11-09 | 2016-11-09 | 2016-11-09 | G | 2016-11-10 | 2016-11-10 | 2019-01-31 | 2019-09-13 | R | [10 empty] | 2020-09-30 | 2020-09-30 | 2020-10-06 | 2020-09-30 | G | [5 empty] | 2020-10-08 | 2020-09-30 | 2021-04-13 | 2020-09-30 | G | [10 empty] | 2021-04-29 |  | 2021-06-24 |  | G | 2021-06-25 |  | 2021-12-17 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.44163
2445 | 109604 | HORNER ROAD SIDEWALKS | 0639 | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Prince William County | MANASSAS | Northern Virginia | Northern Virginia:Prince William County | Local Assistance Division | Bud Siegel |  |  | Rita Hockman | Rita.Hockman@vdot.virginia.gov | (804) 824-7421 | Paul Sweeney | psweeney@pwcgov.org | (703) 906-4741 | 0 |  | 0 | FY2019 | 594640 | 457382 | WAITING FINANCIAL CLOSURE | R | Start Delivery milestone finished 71 days late | G | Project is on budget | 2016-10-03 | 2016-10-03 | 2016-12-30 | 2017-01-12 | R | 2017-01-03 | 2017-01-13 | 2017-01-05 | 2017-02-17 | R | 2017-01-06 | 2017-02-20 | 2017-07-13 | 2017-07-13 | G | [10 empty] | 2018-05-09 | 2019-01-28 | 2018-05-30 | 2019-02-08 | R | [5 empty] | 2018-06-01 | 2019-02-11 | 2019-03-15 | 2019-05-08 | R | [10 empty] | 2019-04-02 | 2019-05-13 | 2019-04-29 | 2019-07-15 | R | 2019-04-30 | 2019-08-20 | 2019-06-10 | 2019-08-20 | R | Delay due to unforeseen issues with utilities, railroad coordination, or right-of-way acquisition | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.40961
2446 | 110828 | RTE 11 SHOULDER WIDENING & RUMBLE STRIPS | 0011 | Primary | Safety | VDOT | Rockbridge County | LEXINGTON | Staunton | NonMPO:NonMPO | Infrastructure Investment/Asset Management Division | Matthew Bond | Matthew.Bond@vdot.virginia.gov | (540) 332-9275 | Michael L Surratt | Michael.Surratt@VDOT.Virginia.gov | (540) 332-9325 |  |  |  | 0 |  | 0 | FY2023 | 1690000 | 1690000 | NO DATES SET YET | G | Start Development milestone is 444 days ahead of the expected completion date | G | Project is on budget | [5 empty] | 2022-04-28 |  | 2022-05-11 |  | G | 2022-05-12 |  | 2022-06-09 |  | G | [35 empty] | 2023-01-10 |  | 2023-01-10 |  | G | 2023-02-27 |  | 2023-03-17 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.097826
2447 | 111229 | #SMART18 - (St) WILSON COMPLEX ROUNDABOUT | 0358 | Miscellaneous | Reconstruction w/ Added Capacity | VDOT | Augusta County | HARRISONBURG | Staunton | SAW:Augusta County | Infrastructure Investment Division | Matthew P Dana | Matt.Dana@VDOT.Virginia.gov | (540) 332-7786 | Anthony E Pelina | Anthony.Pelina@vdot.virginia.gov | (540) 332-9575 |  |  |  | 1 | 2018 | 0 | FY2025 | 1727222 | 1727222 | NO DATES SET YET | G | Start Development milestone is 173 days ahead of the expected completion date | G | Project is on budget | [5 empty] | 2021-08-02 |  | 2021-08-13 |  | G | 2021-08-16 |  | 2022-08-16 |  | G | [5 empty] | 2023-02-07 |  | 2023-02-21 |  | G | 2023-11-15 |  | 2023-11-30 |  | G | 2024-04-26 |  | 2024-09-03 |  | G | 2023-12-18 |  | 2024-09-18 |  | G | 2023-07-31 |  | 2024-02-08 |  | G | [5 empty] | 2024-11-12 |  | 2024-11-14 |  | G | 2025-01-03 |  | 2025-03-04 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.082718
2448 | 111360 | Franklin Road Sidewalk Improvements- Rt. 220 B- Roanoke City | 0220 | Urban | Facilities for Pedestrians and Bicycles | Locally | Roanoke | SALEM | Salem | Roanoke:Roanoke City | Infrastructure Investment Division | Cheryl B Becker | Cheryl.Becker@vdot.virginia.gov | (540) 492-2531 | Cheryl B Becker | Cheryl.Becker@vdot.virginia.gov | (540) 492-2531 | James Nuckles | james.nuckles@roanokeva.gov | (540) 853-2953 | 0 |  | 0 | FY2021 | 1704013 | 1011897 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 360 days early | G | Project is on budget | 2017-06-29 | 2017-06-29 | 2017-11-15 | 2017-11-15 | G | 2017-07-26 | 2017-07-26 | 2017-08-02 | 2017-08-02 | G | 2017-12-12 | 2017-12-12 | 2018-08-01 | 2018-07-25 | G | [35 empty] | 2020-06-09 | 2019-08-15 | 2020-07-07 | 2019-09-15 | G | 2020-07-08 | 2019-09-16 | 2020-10-29 | 2019-11-04 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.32312
2449 | 111461 | RTE 1 - RECONSTRUCTION RT 1 / Jefferson Davis Highway | 0001 | Urban | Reconstruction w/o Added Capacity | Locally | Fredericksburg | FREDERICKSBURG | Fredericksburg | NonMPO:NonMPO | Infrastructure Investment Division | Richard A Spurlock | Richard.Spurlock@VDOT.Virginia.gov | (540) 899-4302 | Richard A Spurlock | Richard.Spurlock@VDOT.Virginia.gov | (540) 899-4302 | Erik Nelson | enelson@fredericksburgva.gov | (540) 372-1080 | 0 |  | 0 | FY2019 | 315489 | 315489 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 289 days early | G | Project is on budget | 2017-08-04 | 2017-06-02 | 2017-10-30 | 2017-07-21 | G | [5 empty] | 2017-08-04 | 2017-06-02 | 2017-08-17 | 2017-09-18 | R | [35 empty] | 2017-09-19 | 2018-03-06 | 2018-12-04 | 2018-03-06 | G | 2018-12-05 | 2018-04-02 | 2019-01-16 | 2018-04-02 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.079336
2450 | 107093 | MALLARD DR - RECONSTRUCTION | 0000 | Urban | Reconstruction w/o Added Capacity | Locally | Colonial Heights | CHESTERFIELD | Richmond | Tri-Cities:Colonial Heights | Local Assistance Division | Brian J Lokker | Brian.Lokker@VDOT.Virginia.gov | (804) 524-6010 | Brian J Lokker | Brian.Lokker@VDOT.Virginia.gov | (804) 524-6010 | SCOTT THORNTON |  | (804) 520-9215 | 0 |  | 0 | FY2019 | 140000 | 140000 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 264 days early | G | Project is on budget | 2015-07-01 | 2016-07-05 | 2015-09-24 | 2016-07-05 | R | 2015-09-25 | 2017-02-16 | 2015-10-08 | 2017-02-16 | R | 2015-10-09 | 2017-07-07 | 2016-06-08 | 2017-07-07 | R | [10 empty] | 2018-07-03 | 2015-07-01 | 2018-07-03 | 2015-07-01 | G | [20 empty] | 2018-08-03 | 2017-10-18 | 2018-08-03 | 2017-10-18 | G | 2018-08-07 | 2017-10-19 | 2018-08-07 | 2017-11-16 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.16248
2451 | 108639 | #SMART18 - ELKHARDT RD - ROADWAY, PEDESTRIAN, & BIKE IMPROVE | 0663 | Secondary | Facilities for Pedestrians and Bicycles | Locally | Chesterfield County | CHESTERFIELD | Richmond | Richmond:Chesterfield County | Local Assistance Division | Michael S Gray | Mike.Gray@vdot.virginia.gov | (804) 609-5347 | Michael S Gray | Mike.Gray@vdot.virginia.gov | (804) 609-5347 | Bill Arel | arelb@chesterfield.gov | (804) 748-1037 | 1 | 2018 | 0 | FY2022 | 4110000 | 5740814 | ACTIVITY DATES SET | Y | Relocate Utilities milestone is 8 days ahead of the expected completion date and there is a risk of missing this milestone date | R | Project estimate is less than $5M and is 20% or more over budget | 2017-01-31 | 2016-10-06 | 2017-04-25 | 2016-10-06 | G | 2017-04-26 | 2016-12-08 | 2017-04-28 | 2016-12-08 | G | 2017-05-01 | 2017-05-01 | 2017-11-02 | 2017-10-13 | G | [5 empty] | 2018-05-22 | 2018-05-22 | 2018-06-11 | 2019-01-03 | R | 2018-06-11 | 2019-03-19 | 2018-06-29 | 2019-03-25 | R | 2020-02-18 | 2020-02-13 | 2021-03-01 |  | Y | 2018-08-14 | 2019-04-12 | 2021-04-22 | 2020-02-12 | G | [10 empty] | 2021-05-10 |  | 2021-06-07 |  | G | 2021-06-08 |  | 2021-07-19 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.29361
2452 | 108790 | Chesapeake Expressway Guardrail Improvements | 0168 | Urban | Safety | Locally | Chesapeake | NORFOLK | Hampton Roads | Hampton Roads:Chesapeake | Infrastructure Investment Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Johndel A Alcaide | John.Alcaide@vdot.virginia.gov | (757) 956-3098 | Scott Frechem | sfrechem@cityofchesapeake.net | (757) 382-6319 | 0 |  | 0 | FY2019 | 816050 | 678628 | WAITING FINANCIAL CLOSURE | R | Start Delivery milestone finished 168 days late | G | Project is on budget | 2016-07-01 | 2016-07-01 | 2016-09-26 | 2017-03-29 | R | 2016-09-27 | 2016-09-07 | 2016-09-29 | 2016-09-07 | G | 2016-09-30 | 2016-09-08 | 2017-04-12 | 2017-05-30 | R | [35 empty] | 2018-02-23 | 2018-11-09 | 2018-03-22 | 2018-12-16 | R | 2018-08-24 | 2018-12-17 | 2018-11-20 | 2019-05-07 | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.20642
2453 | 109287 | #HB2.FY17 Rte 122 & Rte 636 Intersection Safety Improvements | 0122 | Primary | Reconstruction w/o Added Capacity | VDOT | Franklin County | BEDFORD | Salem | NonMPO:NonMPO | Infrastructure Investment Division | Alex H Price | Alex.Price@VDOT.Virginia.gov | (540) 378-5053 | Brian H Becker | Brian.Becker@VDOT.Virginia.gov | (540) 204-7959 | Lisa Cooper | lisa.cooper@franklincountyva.gov | (540) 483-6642 | 1 | 2017 | 0 | FY2020 | 2718576 | 4308184 | ACTIVITY DATES SET | R | Relocate Utilities milestone is 452 days past the expected completion date | R | Project estimate is less than $5M and is 20% or more over budget | [5 empty] | 2016-07-06 | 2016-07-06 | 2016-08-10 | 2016-08-10 | G | 2016-08-16 | 2016-08-16 | 2017-07-14 | 2017-06-13 | G | [5 empty] | 2018-01-10 | 2017-11-20 | 2018-01-25 | 2017-11-27 | G | 2018-10-29 | 2018-10-18 | 2018-11-09 | 2018-11-05 | G | 2019-04-11 | 2020-09-22 | 2019-11-27 |  | R | 2018-11-30 | 2018-11-16 | 2019-08-26 | 2019-06-19 | G | [10 empty] | 2019-12-10 |  | 2019-12-10 |  | R | 2020-02-04 |  | 2020-04-28 |  | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 1 | 0.24034
2454 | 109601 | #SGR17VB - RT 726 - REPLACE BRIDGE STR. 6094 | 0726 | Secondary | Bridge Replacement w/ Added Capacity | VDOT | Albemarle County | CHARLOTTESVILLE | Culpeper | NonMPO:NonMPO | Infrastructure Investment/Asset Management Division | Braden C Chapman | Braden.Chapman@VDOT.Virginia.gov | (540) 829-7421 | Brian A Arnold | Brian.Arnold@VDOT.Virginia.gov | (540) 829-7557 |  |  |  | 0 |  | 1 | FY2023 | 3020000 | 3020000 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 825 days early | G | Project is on budget | [5 empty] | 2018-04-10 | 2017-03-27 | 2018-04-23 | 2017-03-27 | G | 2018-04-24 | 2017-03-28 | 2019-03-22 | 2018-08-01 | G | [5 empty] | 2018-08-24 | 2018-08-24 | 2018-08-29 | 2018-08-29 | G | 2021-05-04 | 2019-03-25 | 2021-05-17 | 2019-03-25 | G | 2021-09-10 | 2020-01-06 | 2022-03-23 | 2020-01-23 | G | 2021-06-02 | 2019-04-16 | 2021-11-12 | 2020-02-25 | G | 2020-09-17 | 2019-08-16 | 2021-09-17 | 2019-11-04 | G | [5 empty] | 2022-04-12 | 2020-03-10 | 2022-04-12 | 2020-03-10 | G | 2022-08-12 | 2020-05-29 | 2022-09-01 | 2020-05-29 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.095981
2455 | 110798 | #SMART18 - US 11 at SR 16 Int. -Improve turning movement | 0011 | Primary | Reconstruction w/o Added Capacity | VDOT | Marion | ABINGDON | Bristol | NonMPO:NonMPO | Infrastructure Investment Division | Tamara D Pritchard | Tamara.Pritchard@VDOT.Virginia.gov | (276) 696-3249 | James M Bullins | James.Bullins@VDOT.Virginia.gov | (276) 696-3349 |  |  |  | 1 | 2018 | 0 | FY2024 | 942000 | 942000 | ACTIVITY DATES SET | G | Determine Requirements milestone finished 442 days early | G | Project is on budget | [5 empty] | 2021-07-16 | 2020-05-01 | 2021-07-29 | 2020-05-14 | G | 2021-07-30 | 2020-05-15 | 2022-03-31 | 2021-01-13 | G | [5 empty] | 2021-09-10 |  | 2021-09-23 |  | G | 2022-11-14 |  | 2022-11-29 |  | G | 2023-04-26 |  | 2023-10-30 |  | G | 2022-12-15 |  | 2023-06-22 |  | G | 2022-05-03 |  | 2022-11-04 |  | G | [5 empty] | 2023-11-14 |  | 2023-11-14 |  | G | 2024-02-15 |  | 2024-02-22 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.077547
2457 | 111279 | #SGR18VB - RT 29 SBL - BRIDGE & APPR OVER NSRR (Fed 20579) | 0029 | Urban | Bridge Replacement w/o Added Capacity | VDOT | Lynchburg | APPOMATTOX | Lynchburg | Lynchburg:Lynchburg | Infrastructure Investment/Asset Management Division | Laura J Walton | Laura.Walton@VDOT.Virginia.gov | (434) 856-8286 | Lindsey S Hodges | Lindsey.Hodges@vdot.virginia.gov | (434) 856-8143 |  |  |  | 0 |  | 1 | FY2020 | 6842565 | 6842565 | CONSTRUCTION STARTED | G | Start Delivery milestone finished on-time | G | Project is on budget | [10 empty] | 2019-09-16 | 2019-08-21 | 2019-09-16 | 2019-08-21 | G | [35 empty] | 2020-01-14 | 2020-01-13 | 2020-01-14 | 2020-01-13 | G | 2020-05-20 | 2020-05-20 | 2020-05-20 | 2020-05-20 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.07545
2458 | 111457 | #SGR19LP - RT 3 - RECONSTRUCTION (BLUE & GRAY PARKWAY) | 0003 | Urban | Reconstruction w/o Added Capacity | Locally | Fredericksburg | FREDERICKSBURG | Fredericksburg | NonMPO:NonMPO | Infrastructure Investment Division | Richard A Spurlock | Richard.Spurlock@VDOT.Virginia.gov | (540) 899-4302 | Richard A Spurlock | Richard.Spurlock@VDOT.Virginia.gov | (540) 899-4302 | Erik Nelson | enelson@fredericksburgva.gov | (540) 372-1080 | 0 |  | 1 | FY2019 | 368182 | 368182 | WAITING FINANCIAL CLOSURE | G | Solicit Bids milestone finished 249 days early | G | Project is on budget | 2017-08-01 | 2017-06-02 | 2017-10-25 | 2017-07-21 | G | [5 empty] | 2017-08-01 | 2017-06-02 | 2017-08-14 | 2017-09-18 | R | [35 empty] | 2017-09-19 | 2018-03-30 | 2018-12-04 | 2018-03-30 | G | 2018-12-05 | 2018-03-06 | 2019-01-16 | 2018-03-06 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.079419
2459 | 111647 | #SMART18 - BROADVIEW AVENUE ACCESS MANAGEMENT IMPROVEMENTS | 0017 | Urban | Safety | VDOT | Warrenton | WARRENTON | Culpeper | Northern Virginia:Warrenton | Infrastructure Investment Division | Gregory J Cooley | Gregory.Cooley@vdot.virginia.gov | (434) 906-7979 | James D Cubbage | David.Cubbage@VDOT.Virginia.gov | (540) 727-7129 |  |  |  | 1 | 2018 | 0 | FY2022 | 4231877 | 4881877 | ACTIVITY DATES SET | R | Start Purchasing Right-of-Way milestone is 192 days past the expected completion date | Y | Project estimate is less than $5M and is up to 20% over budget | [5 empty] | 2017-11-01 | 2017-09-08 | 2017-11-15 | 2017-09-21 | G | 2017-11-16 | 2017-09-22 | 2018-08-07 | 2019-09-13 | R | [5 empty] | 2019-10-22 | 2019-10-11 | 2020-01-22 | 2020-01-21 | G | 2020-07-28 |  | 2020-08-13 |  | R | 2021-06-07 |  | 2021-12-13 |  | G | 2020-08-31 |  | 2021-08-31 |  | G | [10 empty] | 2021-12-14 |  | 2021-12-14 |  | G | 2022-03-31 |  | 2022-05-25 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.14176
2460 | 111686 | #SGR18VB - CHAIN BRIDGE RD OVER LEESBURG PIKE (Fed 6465) | 0123 | Primary | Bridge Rehab w/o Added Capacity | VDOT | Fairfax County | FAIRFAX | Northern Virginia | Northern Virginia:Fairfax County | Infrastructure Investment/Asset Management Division | Gary Runco | Gary.Runco@vdot.virginia.gov | (703) 259-3341 | Yusaf M Masud | Yusaf.Masud@vdot.virginia.gov | (703) 259-2973 |  |  |  | 0 |  | 1 | FY2020 | 1227822 | 1227822 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 26 days early | G | Project is on budget | [5 empty] | 2018-03-06 | 2018-03-17 | 2018-03-19 | 2018-03-17 | G | 2018-03-20 | 2018-03-01 | 2018-04-16 | 2018-03-30 | G | [35 empty] | 2019-08-23 | 2019-08-13 | 2019-08-23 | 2019-08-13 | G | 2019-10-09 | 2019-11-13 | 2019-12-09 | 2019-11-13 | G | Final design is still underway | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.079376
2461 | 111821 | #SMART18 - Summit View Business Park Phase 1 - EDA | 0220 | Primary | New Construction Roadway | Locally | Franklin County | BEDFORD | Salem | NonMPO:NonMPO | Local Assistance Division | Todd K Daniel | Todd.Daniel@VDOT.Virginia.gov | (540) 682-7000 | Cheryl B Becker | Cheryl.Becker@vdot.virginia.gov | (540) 492-2531 | Lisa Cooper | lisa.cooper@franklincountyva.gov | (540) 483-6642 | 1 | 2018 | 0 | FY2019 | 1959173 | 1959173 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 449 days early | G | Project is on budget | 2017-08-01 | 2017-07-20 | 2017-10-25 | 2017-11-06 | R | 2017-10-26 | 2017-11-07 | 2017-10-30 | 2018-01-30 | R | 2017-10-31 | 2017-08-01 | 2018-05-10 | 2018-01-31 | G | [35 empty] | 2018-12-10 | 2018-01-10 | 2019-01-08 | 2018-01-31 | G | 2019-01-09 | 2018-01-31 | 2019-04-26 | 2018-02-01 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.30904
2462 | 112478 | CITYWIDE MULTIMODAL TRANSPORTATION IMPROVEMENTS - FAIRFAX | 0029 | Urban | Facilities for Pedestrians and Bicycles | Locally | Fairfax | FAIRFAX | Northern Virginia | Northern Virginia:Fairfax | Infrastructure Investment Division | Amir Salahshoor | A.Salahshoor@VDOT.Virginia.gov | (703) 259-1957 | Robert J Strevell | Robert.Strevell@vdot.virginia.gov | (703) 259-1988 | Wendy Sanford | wendy.sanford@fairfaxva.gov | (703) 385-7889 | 0 |  | 0 | FY2027 | 755462 | 755462 | NO DATES SET YET | G | Agreement with Locality milestone is 768 days ahead of the expected completion date | G | Project is on budget | 2022-09-01 |  | 2023-03-31 |  | G | 2023-04-03 |  | 2023-04-28 |  | G | 2023-05-01 |  | 2023-12-29 |  | G | [10 empty] | 2025-01-02 |  | 2025-01-31 |  | G | [5 empty] | 2025-02-04 |  | 2025-11-26 |  | G | [10 empty] | 2025-12-15 |  | 2026-05-29 |  | G | 2026-06-01 |  | 2026-10-30 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.18971
2463 | 112877 | #SGR19VB - RT 311 OVER MEADOW CREEK (STR 5471) - BR REPLACE | 0311 | Primary | Bridge Replacement w/o Added Capacity | VDOT | Craig County | SALEM | Salem | NonMPO:NonMPO | Infrastructure Investment/Asset Management Division | Anthony T Marshall | Todd.Marshall@VDOT.Virginia.gov | (540) 387-5460 | Wendy Hungate | Wendy.Hungate@vdot.virginia.gov | (540) 387-5470 |  |  |  | 0 |  | 1 | FY2023 | 3150000 | 3150000 | ACTIVITY DATES SET | G | Obtained Permits milestone finished 685 days early | G | Project is on budget | [10 empty] | 2020-03-24 | 2019-01-14 | 2020-03-30 | 2019-01-22 | G | [25 empty] | 2020-03-24 | 2020-07-21 | 2022-06-06 | 2020-07-21 | G | [5 empty] | 2022-07-12 |  | 2022-07-12 |  | G | 2022-10-13 |  | 2023-01-24 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.097775
2464 | 112946 | Old Oak Ln., Phase V Rural Addition - Warren County | 0709 | Secondary | Reconstruction w/o Added Capacity | Locally | Warren County | EDINBURG | Staunton | NonMPO:NonMPO | Local Assistance Division | Kimberly Cameron | Kim.Cameron@vdot.virginia.gov | (540) 332-7886 | Kimberly Cameron | Kim.Cameron@vdot.virginia.gov | (540) 332-7886 | Mike Berry | mberry@warrencountyva.net | (540) 636-1543 | 0 |  | 0 | FY2022 | 1077903 | 1077903 | NO DATES SET YET-PE OPEN | R | Determine Requirements milestone is 195 days past the expected completion date | G | Project is on budget | 2019-10-31 | 2019-10-31 | 2020-01-31 | 2020-01-13 | G | 2020-02-03 | 2020-01-13 | 2020-02-05 | 2020-01-14 | G | 2020-02-06 |  | 2020-08-10 |  | R | [25 empty] | 2020-08-11 |  | 2021-04-19 |  | Y | [5 empty] | 2021-06-22 |  | 2021-07-20 |  | G | 2021-10-07 |  | 2021-10-07 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.20876
2465 | 113192 | DUMFRIES ROAD SHARED USE PATH | 0234 | Urban | Facilities for Pedestrians and Bicycles | Locally | Manassas | MANASSAS | Northern Virginia | Northern Virginia:Manassas | Local Assistance Division | Claudia H Llana | Claudia.Llana@VDOT.Virginia.gov | (703) 259-1768 | Marlene Pinedo Fortich | Sofia.Pinedo@vdot.virginia.gov | (703) 259-1724 | Sung Jin Chung | schung@ci.manassas.va.us | (703) 257-8339 | 0 |  | 0 | FY2023 | 862786 | 1097977 | ACTIVITY DATES SET | G | Determine Requirements milestone finished on-time | R | Project estimate is less than $5M and is 20% or more over budget | 2018-11-15 | 2018-04-05 | 2019-04-30 | 2018-09-12 | G | [5 empty] | 2019-09-03 | 2019-09-03 | 2020-03-31 | 2020-03-31 | G | [20 empty] | 2021-02-01 | 2020-12-21 | 2021-11-30 |  | G | [10 empty] | 2022-01-03 |  | 2022-04-29 |  | G | 2022-07-20 |  | 2022-11-30 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.13334
2466 | 113285 | STEWART AVE - RECONSTRUCTION |  | Urban | Reconstruction w/o Added Capacity | Locally | Hopewell | PETERSBURG | Richmond | Tri-Cities:Hopewell | Local Assistance Division | James Shepherd | James.Shepherd@vdot.virginia.gov | (804) 609-5305 | Brian J Lokker | Brian.Lokker@VDOT.Virginia.gov | (804) 524-6010 | Austin Anderson | AANDERSON@HOPWELLVA.GOV | (804) 541-2319 | 0 |  | 0 | FY2020 | 239261 | 239261 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 41 days early | G | Project is on budget | 2018-09-14 | 2018-08-13 | 2018-12-12 | 2018-08-14 | G | 2018-12-13 | 2018-11-07 | 2019-02-05 | 2018-11-14 | G | 2019-02-06 | 2018-12-14 | 2019-04-17 | 2019-04-09 | G | [25 empty] | 2019-05-13 | 2019-09-06 | 2019-10-31 | 2019-09-06 | G | [5 empty] | 2019-10-01 | 2019-09-23 | 2019-10-29 | 2019-10-29 | G | 2019-10-30 | 2019-10-30 | 2020-02-26 | 2020-01-16 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 |  | 1 | 0 | 0.071052
2467 | 113535 | #SGR19VB - RT 17/50/522 MILLWOOD PIKE BRIDGE OVER I-81 | 0017 | Interstate | Bridge Replacement w/o Added Capacity | VDOT | Frederick County | EDINBURG | Staunton | Winchester:Frederick County | Infrastructure Investment/Asset Management Division | Randolph S Kiser | Randy.Kiser@VDOT.Virginia.gov | (540) 332-9092 | David Robinson | David.Robinson@vdot.virginia.gov | (540) 332-7758 |  |  |  | 0 |  | 0 | FY2022 | 31328926 | 31328926 | NO DATES SET YET | R | Determine Requirements milestone is 261 days past the expected completion date | G | Project is on budget | [10 empty] | 2020-06-01 |  | 2020-06-05 |  | R | [10 empty] | 2020-12-08 |  | 2020-12-21 |  | R | 2021-05-19 |  | 2021-11-23 |  | G | 2020-12-24 |  | 2021-07-01 |  | G | 2020-07-16 |  | 2021-03-24 |  | Y | [5 empty] | 2021-12-14 |  | 2021-12-14 |  | G | 2022-04-07 |  | 2022-04-07 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.083938
2468 | 113614 | JUDICIAL TRAIL CONNECTION |  | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Fairfax | FAIRFAX | Northern Virginia | Northern Virginia:Fairfax | Local Assistance Division | Amir Salahshoor | A.Salahshoor@VDOT.Virginia.gov | (703) 259-1957 | Christer P Carshult | Christer.Carshult@vdot.virginia.gov | (703) 259-1765 | Wendy Sanford | wendy.sanford@fairfaxva.gov | (703) 385-7889 | 0 |  | 0 | FY2025 | 436000 | 436000 | ACTIVITY DATES SET | G | Determine Requirements milestone finished on-time | G | Project is on budget | 2019-07-01 | 2018-08-01 | 2020-01-31 | 2018-10-16 | G | 2020-02-03 | 2019-01-08 | 2020-02-28 | 2019-02-08 | G | 2020-03-02 | 2019-09-13 | 2020-12-31 | 2020-12-31 | G | [10 empty] | 2022-12-19 |  | 2023-01-18 |  | G | [5 empty] | 2023-01-19 |  | 2023-10-18 |  | G | [10 empty] | 2023-12-28 |  | 2024-06-18 |  | G | 2024-06-19 |  | 2024-12-16 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.33291
2469 | 113741 | RTE 721 - RURAL RUSTIC (SURFACE TREAT NON-HARDSURFACE ROAD) | 0721 | Secondary | Reconstruction w/o Added Capacity | VDOT | Culpeper County | WARRENTON | Culpeper | NonMPO:NonMPO | Infrastructure Investment Division | Ken Connors |  |  | Benjamin Davison | Ben.Davison@vdot.virginia.gov | (540) 347-6446 |  |  |  | 0 |  | 0 | FY2025 | 495000 | 495000 | NO DATES SET YET | G | Start Development milestone is 600 days ahead of the expected completion date | Y | Estimate not current | [5 empty] | 2022-10-03 |  | 2022-10-14 |  | G | 2022-10-18 |  | 2023-06-13 |  | G | [5 empty] | 2024-02-22 |  | 2024-04-03 |  | G | [5 empty] | 2024-07-18 |  | 2024-11-08 |  | G | [5 empty] | 2024-07-02 |  | 2024-10-02 |  | G | [5 empty] | 2024-11-12 |  | 2024-11-12 |  | G | 2025-02-07 |  | 2025-02-07 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | SAAP CONTRACT | 0 | 0 | 0.10385
2470 | 111735 | #SGR19LB??- University Blvd/Appomattox River Canal | 0036 | Urban | Bridge Replacement w/o Added Capacity | VDOT | Petersburg | PETERSBURG | Richmond | Tri-Cities:Petersburg | Infrastructure Investment Division | Thomas Kendrick | Thomas.Kendrick@vdot.virginia.gov | (804) 609-5281 | Thomas Kendrick | Thomas.Kendrick@vdot.virginia.gov | (804) 609-5281 | Bill Riggleman | bill@petersburg-va.org | (804) 733-2353 | 0 |  | 1 | FY2023 | 2025000 | 2025000 | ACTIVITY DATES SET | R | Engage Public milestone is 395 days past the expected completion date | G | Project is on budget | [5 empty] | 2018-06-01 | 2018-06-12 | 2018-06-14 | 2018-06-14 | G | 2018-06-15 | 2018-06-15 | 2019-05-14 | 2019-05-09 | G | [5 empty] | 2019-12-06 |  | 2020-01-23 |  | R | 2020-11-20 | 2020-12-07 | 2020-12-07 | 2020-12-07 | G | 2021-08-05 |  | 2022-08-05 |  | G | 2021-01-07 |  | 2021-07-07 |  | G | 2020-11-13 | 2020-11-16 | 2022-02-01 | 2020-11-16 | G | [5 empty] | 2022-09-13 |  | 2022-10-11 |  | G | 2023-01-31 |  | 2023-03-28 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.07011
2471 | 112211 | Signal Replacement N. Loudoun St / Brick Kiln Rd / Brooke Rd | 0011 | Urban | Reconstruction w/o Added Capacity | Locally | Winchester | EDINBURG | Staunton | Winchester:Winchester | Infrastructure Investment Division | Kimberly Cameron | Kim.Cameron@vdot.virginia.gov | (540) 332-7886 | Kimberly Cameron | Kim.Cameron@vdot.virginia.gov | (540) 332-7886 | Perry Eisenach | Perry.Eisenach@winchesterva.gov | (540) 667-1815 | 0 |  | 0 | FY2023 | 600000 | 600000 | ACTIVITY DATES SET | G | Determine Requirements milestone finished on-time | G | Project is on budget | 2020-01-15 | 2020-01-15 | 2020-02-20 | 2020-02-20 | G | 2020-02-21 | 2020-02-20 | 2020-04-02 | 2020-03-03 | G | 2020-04-03 | 2020-03-03 | 2021-02-01 | 2021-02-01 | G | [35 empty] | 2022-06-30 |  | 2022-09-23 |  | G | 2022-09-26 |  | 2022-12-22 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.1218
2472 | 112778 | I-66 MEDIAN WIDENING FOR WMATA ORANGE LINE ACCOMODATION | 0066 | Interstate | Reconstruction w/o Added Capacity | VDOT | Fairfax County | FAIRFAX | Northern Virginia | Northern Virginia:Fairfax County | Infrastructure Investment Division | Susan N Shaw | Susan.Shaw@VDOT.Virginia.gov | (703) 259-1995 | Harinderbir S Warraich | HS.Warraich@VDOT.Virginia.gov | (571) 459-2362 |  |  |  | 0 |  | 0 | FY2019 | 40000000 | 40000000 | AWARDED | G | Start Delivery milestone finished on-time | G | Project is on budget | [10 empty] | 2018-02-22 | 2018-02-22 | 2018-06-28 | 2018-06-28 | G | [35 empty] | 2018-07-02 | 2018-07-02 | 2018-07-09 | 2018-07-09 | G | 2018-07-10 | 2018-07-10 | 2018-07-18 | 2018-07-18 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | WORK/TASK ORDER | 1 | 0 | 0.12625
2473 | 112918 | District Signal Upgrades_FYA | 9999 | Miscellaneous | Safety | VDOT | Culpeper District-wide |  | Culpeper | NonMPO:NonMPO | Infrastructure Investment Division | Ken Connors |  |  | Caroline Awua-Mensah | Caroline.Awua-Mensah@vdot.virginia.gov | (540) 829-7618 |  |  |  | 0 |  | 0 | FY2019 | 312270 | 331737 | CONSTRUCTION STARTED | R | Start Delivery milestone finished 70 days late | Y | Project estimate is less than $5M and is up to 20% over budget | [5 empty] | 2018-09-04 | 2018-08-17 | 2018-09-04 | 2018-08-17 | G | 2018-09-05 | 2018-08-20 | 2018-12-17 | 2018-09-10 | G | [5 empty] | 2018-09-27 | 2018-08-26 | 2018-10-10 | 2018-10-02 | G | [25 empty] | 2018-10-26 | 2018-12-21 | 2018-11-01 | 2018-12-21 | R | 2018-11-02 | 2019-01-17 | 2018-11-08 | 2019-01-17 | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | WORK/TASK ORDER | 1 | 0 | 0.12772
2474 | 112980 | MADDOX DRIVE - MILLING, PAVING & RECONSTRUCTION |  | Urban | Resurfacing | Locally | Orange | LOUISA | Culpeper | NonMPO:NonMPO | Local Assistance Division | Ken Connors |  |  | Bobby J Jenkins | Bobby.JenkinsJr@VDOT.Virginia.gov | (540) 829-7694 | JOHN COOLEY | townplanner@townoforangeva.org | (540) 672-6917 | 0 |  | 0 | FY2020 | 49580 | 49580 | WAITING FINANCIAL CLOSURE | G | Obtained Permits milestone finished 36 days early | G | Project is on budget | 2019-02-21 | 2018-07-01 | 2019-05-15 | 2018-07-09 | G | [5 empty] | 2019-02-21 | 2018-10-01 | 2019-03-06 | 2018-10-01 | G | [25 empty] | 2019-03-01 | 2019-04-17 | 2019-05-23 | 2019-04-17 | G | [5 empty] | 2019-05-24 | 2018-12-06 | 2019-06-21 | 2019-01-15 | G | 2019-09-11 | 2019-01-15 | 2019-09-11 | 2019-02-01 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.047883
2475 | 113196 | Sandbridge Road - Nimmo Parkway Phase VIIA | 9999 | Urban | Reconstruction w/o Added Capacity | Locally | Virginia Beach | NORFOLK | Hampton Roads | Hampton Roads:Virginia Beach | Local Assistance Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Marci Thompson | Marci.Thompson@vdot.virginia.gov | (757) 956-3093 | Katie Shannon, PE | kshannon@vbgov.com |  | 0 |  | 0 | FY2023 | 20657581 | 20657581 | NO DATES SET YET-PE OPEN | R | Determine Requirements milestone is 4 days past the expected completion date | G | Project is on budget | [10 empty] | 2020-02-19 |  | 2021-02-17 |  | R | [10 empty] | 2022-03-03 |  | 2022-03-23 |  | G | [5 empty] | 2022-03-25 |  | 2023-01-04 |  | G | [10 empty] | 2023-01-24 |  | 2023-02-21 |  | G | 2023-05-10 |  | 2023-05-10 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.1547
2476 | 113509 | Granby Street Bike Bypass at Riverview | 0460 | Urban | Facilities for Pedestrians and Bicycles | Locally | Norfolk | NORFOLK | Hampton Roads | Hampton Roads:Norfolk | Infrastructure Investment Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Derrick Williams | Derrick.Williams@vdot.virginia.gov | (757) 956-3097 | Deborah.Mangiaracina, P.E. | Deborah.Mangiaracina@norfolk.gov' | (757) 664-7459 | 0 |  | 0 | FY2021 | 578600 | 709162 | ADVERTISED | R | Start Delivery milestone is 108 days past the expected completion date | Y | Project estimate is less than $5M and is up to 20% over budget | 2018-10-09 | 2018-10-09 | 2019-01-08 | 2018-12-26 | G | 2019-01-09 | 2018-12-27 | 2019-01-11 | 2019-01-07 | G | 2019-01-14 | 2019-04-03 | 2019-07-19 | 2019-10-04 | R | [35 empty] | 2020-07-07 | 2020-08-04 | 2020-08-17 | 2020-09-15 | R | 2020-11-05 |  | 2020-11-05 |  | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.23193
2477 | 113567 | Roanoke River Greenway through Explore Park | 9999 | Miscellaneous | Facilities for Pedestrians and Bicycles | Locally | Roanoke County | SALEM | Salem | Roanoke:Roanoke County | Infrastructure Investment Division | Cheryl B Becker | Cheryl.Becker@vdot.virginia.gov | (540) 492-2531 | Cheryl B Becker | Cheryl.Becker@vdot.virginia.gov | (540) 492-2531 | David Henderson | DHenderson@roanokecountyva.gov | (540) 772-2083 | 0 |  | 0 | FY2022 | 3020308 | 3020308 | NO DATES SET YET-PE OPEN | R | Determine Requirements milestone is 202 days past the expected completion date | G | Project is on budget | 2019-10-01 | 2019-08-01 | 2019-12-30 | 2020-05-10 | R | 2019-12-31 | 2020-05-29 | 2020-01-03 | 2020-05-29 | R | 2020-01-06 |  | 2020-08-03 |  | R | [25 empty] | 2020-12-01 |  | 2021-08-04 |  | G | [5 empty] | 2021-08-20 |  | 2021-09-17 |  | G | 2022-02-17 |  | 2022-02-17 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.1663
2478 | 113703 | #SGR19LP - Primary Extension RT 58 Eastbound | 0058 | Urban | Resurfacing | Locally | Suffolk | NORFOLK | Hampton Roads | Hampton Roads:Suffolk | Infrastructure Investment Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Johndel A Alcaide | John.Alcaide@vdot.virginia.gov | (757) 956-3098 | Edward Heide | eheide@suffolkva.us | (757) 514-7615 | 0 |  | 1 | FY2019 | 213000 | 213000 | WAITING FINANCIAL CLOSURE | G | Obtained Permits milestone finished 224 days early | G | Project is on budget | 2018-09-04 | 2018-09-24 | 2018-11-30 | 2018-10-04 | G | 2018-12-03 | 2018-10-05 | 2018-12-05 | 2018-10-08 | G | 2018-12-06 | 2018-10-08 | 2019-06-13 | 2018-10-11 | G | [25 empty] | 2019-05-28 | 2019-06-21 | 2020-02-03 | 2019-06-24 | G | [5 empty] | 2018-10-16 | 2018-10-16 | 2018-10-18 | 2018-10-18 | G | 2018-10-18 | 2018-10-18 | 2018-10-19 | 2018-10-19 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.095765
2479 | 113806 | RTE 3 LICK RUN, BRIDGE REPLACE, NON-NBI, ID 17921 | 0003 | Primary | Bridge Replacement w/o Added Capacity | VDOT | Spotsylvania County | FREDERICKSBURG | Fredericksburg | Fredericksburg:Spotsylvania County | Infrastructure Investment Division | Annette F Adams | Annette.Adams@VDOT.Virginia.gov | (540) 372-3583 | Khalil Minhas | Khalil.Minhas@vdot.virginia.gov | (540) 374-3369 | Paul Agnello | pagnello@spotsylvania.va.us | (540) 507-7398 | 0 |  | 0 | FY2024 | 4799587 | 4799587 | ACTIVITY DATES SET | G | Engage Public milestone finished 5 days early | G | Project is on budget | [5 empty] | 2018-10-08 | 2018-08-23 | 2018-10-22 | 2018-08-23 | G | 2018-10-23 | 2018-08-24 | 2019-05-31 | 2019-05-31 | G | [5 empty] | 2020-06-30 | 2020-06-30 | 2020-08-11 | 2020-08-06 | G | 2021-11-04 |  | 2022-01-05 |  | G | 2023-08-28 |  | 2024-03-01 |  | G | 2022-01-24 |  | 2023-08-25 |  | G | 2022-01-21 |  | 2022-09-21 |  | G | [5 empty] | 2024-03-12 |  | 2024-03-12 |  | G | 2024-06-21 |  | 2024-06-21 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.052134
2481 | 115300 | PRIMARY EXTENSION PAVING FY20 - HILLWOOD AVENUE - 264 | 0338 | Urban | Resurfacing | Locally | Falls Church | FAIRFAX | Northern Virginia | Northern Virginia:Falls Church | Local Assistance Division | Andrew G Beacher | Andrew.Beacher@vdot.virginia.gov | (703) 259-2239 | Rita Hockman | Rita.Hockman@vdot.virginia.gov | (804) 824-7421 | Tara Puzin | tpuzin@fallschurchva.gov | (703) 405-0175 | 0 |  | 1 | FY2020 | 788190 | 788190 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 121 days early | G | Project is on budget | 2019-07-01 | 2019-07-01 | 2019-09-30 | 2019-08-23 | G | [5 empty] | 2019-10-01 | 2019-09-11 | 2019-10-31 | 2019-09-11 | G | [25 empty] | 2019-08-26 | 2019-09-15 | 2019-11-27 | 2019-09-15 | G | [5 empty] | 2019-10-23 | 2019-09-20 | 2019-12-19 | 2019-09-20 | G | 2019-12-20 | 2019-10-21 | 2020-02-19 | 2019-10-21 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.3651
2482 | 115402 | #SMART20 - Lower Appomattox River Trail | 0010 | Urban |  | Locally | Prince George County | PETERSBURG | Richmond | Tri-Cities:Prince George County | Infrastructure Investment Division | James Shepherd | James.Shepherd@vdot.virginia.gov | (804) 609-5305 | James Shepherd | James.Shepherd@vdot.virginia.gov | (804) 609-5305 | Horace Wade |  |  | 1 | 2020 | 0 | FY2025 | 44000 | 44000 | NO DATES SET YET | G | Determine Requirements milestone is 1026 days ahead of the expected completion date | G | Project is on budget | 2023-12-01 |  | 2024-02-29 |  | G | [5 empty] | 2023-12-01 |  | 2023-12-14 |  | G | [25 empty] | 2023-12-15 |  | 2024-03-14 |  | G | [5 empty] | 2024-03-18 |  | 2024-04-12 |  | G | 2024-07-02 |  | 2024-07-02 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.10415
2483 | 115873 | GUARDRAIL INSTALLATION | 0723 | Secondary | Safety | VDOT | Nottoway County | PETERSBURG | Richmond | NonMPO:NonMPO | Infrastructure Investment Division | Dianna M Bryant | Dianna.Bryant@VDOT.Virginia.gov | (804) 863-4004 | Adam S Brooks | Adam.Brooks@VDOT.Virginia.gov | (804) 609-5274 |  |  |  | 0 |  | 0 | FY2024 | 299399 | 299399 | NO DATES SET YET | G | Start Development milestone is 743 days ahead of the expected completion date | G | Project is on budget | [5 empty] | 2023-03-06 |  | 2023-03-06 |  | G | 2023-03-07 |  | 2023-06-13 |  | G | [5 empty] | 2023-06-26 |  | 2023-07-10 |  | G | [25 empty] | 2023-07-26 |  | 2023-08-01 |  | G | 2023-08-02 |  | 2023-08-08 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | WORK/TASK ORDER | 0 | 0 | 0.069382
2484 | 116557 | SYSTEMIC UNSIGNALIZED INTERSECTION TREATMENTS - DISTRICTWIDE | 9999 | Miscellaneous | Safety | VDOT | Richmond District-wide |  | Richmond | Richmond:Richmond District-wide | Infrastructure Investment Division | Rebecca J Worley | Rebecca.Worley@vdot.virginia.gov | (804) 674-2775 | Rebecca J Worley | Rebecca.Worley@vdot.virginia.gov | (804) 674-2775 | N\A |  |  | 0 |  | 0 | FY2021 | 190000 | 190000 | AWARDED | G | Start Delivery milestone finished 29 days early | G | Project is on budget | [10 empty] | 2020-03-13 | 2020-03-13 | 2020-07-20 | 2020-05-21 | G | [35 empty] | 2020-08-05 | 2020-07-20 | 2020-08-11 | 2020-07-20 | G | 2020-08-12 | 2020-07-20 | 2020-08-18 | 2020-07-20 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | WORK/TASK ORDER | 1 | 0 | 0.067494
2485 | 116836 | Rte. 619 - High Knob Access Enhancements | 0018 | Miscellaneous | Facilities for Pedestrians and Bicycles | Locally | Norton | WISE | Bristol | NonMPO:NonMPO | Local Assistance Division | Kenneth R Plummer | KR.Plummer@VDOT.Virginia.gov | (276) 696-3261 | Kenneth R Plummer | KR.Plummer@VDOT.Virginia.gov | (276) 696-3261 | Fred Ramey | fredr@nortonva.org | (276) 679-1160 | 0 |  | 0 | FY2023 | 461000 | 461000 | NO DATES SET YET-PE OPEN | G | Start Development milestone finished 99 days early | G | Project is on budget | 2020-04-29 | 2020-04-29 | 2020-09-03 | 2020-04-29 | G | 2020-09-04 | 2020-05-21 | 2020-09-25 | 2020-06-18 | G | 2021-04-09 |  | 2021-08-02 |  | G | [25 empty] | 2022-07-28 |  | 2022-12-29 |  | G | [5 empty] | 2023-03-02 |  | 2023-03-29 |  | G | 2023-06-16 |  | 2023-06-16 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.12872
2486 | 117047 | Pedestrian Accommodations at Spring Park | 0161 | Secondary | Facilities for Pedestrians and Bicycles | Locally | Henrico County | ASHLAND | Richmond | Richmond:Henrico County | Local Assistance Division | Cynthia Crouch | Cynthia.Crouch@vdot.virginia.gov | (804) 609-5313 | Cynthia Crouch | Cynthia.Crouch@vdot.virginia.gov | (804) 609-5313 | TBD |  | TBD | 0 |  | 0 | FY2029 | 533900 | 533900 | NO DATES SET YET | G | Agreement with Locality milestone is 1543 days ahead of the expected completion date | G | Project is on budget | 2025-01-06 |  | 2025-05-14 |  | G | 2025-05-15 |  | 2025-06-05 |  | G | 2025-12-15 |  | 2026-04-10 |  | G | [10 empty] | 2027-07-30 |  | 2027-09-02 |  | G | [5 empty] | 2027-09-03 |  | 2028-02-09 |  | G | 2028-01-05 |  | 2028-06-05 |  | G | [5 empty] | 2028-05-12 |  | 2028-06-09 |  | G | 2028-08-29 |  | 2028-08-29 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.34771
2487 | 69050 | #HB2.FY17 Bridge Rd & Shoulders Hill Rd Intersection Imps | 0626 | Urban | Reconstruction w/o Added Capacity | Locally | Suffolk | NORFOLK | Hampton Roads | Hampton Roads:Suffolk | Infrastructure Investment Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Johndel A Alcaide | John.Alcaide@vdot.virginia.gov | (757) 956-3098 | Robert Lewis | relewis@suffolkva.us | (757) 514-7621 | 1 | 2017 | 0 | FY2022 | 17078876 | 24099362 | ACTIVITY DATES SET | R | Start Purchasing Right-of-Way milestone finished 141 days late | R | Project estimate is greater than $10M and is over budget by (a) 10% or more or (b) $5M or more | [5 empty] | 2003-09-16 | 2003-09-23 | 2003-09-30 | 2003-09-24 | G | 2010-10-01 | 2003-10-01 | 2017-07-03 | 2017-06-30 | G | [10 empty] | 2019-03-18 | 2019-03-18 | 2019-04-01 | 2019-08-20 | R | [20 empty] | 2021-11-15 |  | 2021-12-15 |  | G | 2021-12-16 |  | 2022-03-15 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.22255
2488 | 103611 | Town of Glade Spring, Salt Trail Extension |  | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Glade Spring | ABINGDON | Bristol | NonMPO:NonMPO | Local Assistance Division | Chase R Buchanan | Chase.Buchanan@VDOT.Virginia.gov | (276) 696-3251 | Roger L Musser | Roger.Musser@VDOT.Virginia.gov | (276) 696-3260 | Town of Glade Spring |  |  | 0 |  | 0 | FY2024 | 427440 | 427440 | ACTIVITY DATES SET | G | Determine Requirements milestone finished on-time | G | Project is on budget | [5 empty] | 2012-10-01 | 2013-04-17 | 2012-10-01 | 2013-04-18 | R | 2016-09-22 | 2016-09-22 | 2017-02-22 | 2017-02-22 | G | [10 empty] | 2021-10-13 |  | 2021-10-29 |  | G | [20 empty] | 2023-11-01 |  | 2023-12-15 |  | G | 2024-01-02 |  | 2024-02-28 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.24756
2489 | 107769 | RTE 95 - UPGRADE SIGNS | 0095 | Interstate | Safety | VDOT | Richmond District-wide | ASHLAND | Richmond | Richmond:Richmond District-wide | Infrastructure Investment Division | Lawrence Ramsey | Brian.Ramsey@VDOT.Virginia.gov | (804) 585-3579 | Lawrence Ramsey | Brian.Ramsey@VDOT.Virginia.gov | (804) 585-3579 |  |  |  | 0 |  | 0 | FY2019 | 6758000 | 6758000 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 17 days early | G | Project is on budget | [5 empty] | 2015-08-19 | 2015-08-05 | 2015-09-01 | 2016-10-19 | R | 2015-09-02 | 2016-10-20 | 2016-04-28 | 2017-12-04 | R | [5 empty] | 2017-03-29 | 2018-01-24 | 2017-04-26 | 2018-01-24 | R | [5 empty] | 2016-07-29 | 2016-07-29 | 2016-07-29 | 2016-07-29 | G | [15 empty] | 2017-12-12 | 2018-03-13 | 2018-03-13 | 2018-03-13 | G | 2018-05-02 | 2018-06-25 | 2018-07-12 | 2018-06-25 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.063138
2491 | 115344 | #I81CIP CAMERA INSTALLATION | 0081 | Interstate | Safety | VDOT | Statewide |  | Statewide | Multiple MPOs:Statewide | Infrastructure Investment Division | Bernard S Grinnell | Sean.Grinnell@VDOT.Virginia.gov | (540) 375-0148 | Bernard S Grinnell | Sean.Grinnell@VDOT.Virginia.gov | (540) 375-0148 |  |  |  | 0 |  | 0 | FY2020 |  |  | NO DATES SET YET | R | Determine Requirements milestone is 508 days past the expected completion date | R | Critical information missing | [10 empty] | 2019-05-28 |  | 2019-10-02 |  | R | [35 empty] | 2019-10-04 | 2019-10-03 | 2019-10-10 | 2019-10-09 | G | 2019-10-11 | 2019-10-10 | 2019-10-17 | 2019-10-16 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | WORK/TASK ORDER | 1 | 1 | 0.3063
2492 | 115508 | #SMART20 Wakefield 460 Eastbound Turnlane | 0460 | Primary | Safety | VDOT | Sussex County | FRANKLIN | Hampton Roads | NonMPO:NonMPO | Infrastructure Investment Division | Hayden Hill | Hayden.Hill@volkert.com | (703) 642-8100 | Hayden Hill | Hayden.Hill@volkert.com | (703) 642-8100 | Andre Greene | amgreene@sussexcountyva.gov | (434) 246-1043 | 1 | 2020 | 0 | FY2028 | 994846 | 994846 | NO DATES SET YET | G | Start Development milestone is 968 days ahead of the expected completion date | Y | Estimate not current | [5 empty] | 2023-08-15 |  | 2023-10-17 |  | G | 2023-10-18 |  | 2024-10-18 |  | G | [5 empty] | 2025-08-26 |  | 2025-09-09 |  | G | 2026-12-17 |  | 2026-12-31 |  | G | 2027-05-27 |  | 2027-12-03 |  | G | 2027-01-21 |  | 2027-07-26 |  | G | 2026-06-04 |  | 2026-12-10 |  | G | [5 empty] | 2027-12-14 |  | 2027-12-14 |  | G | 2028-03-09 |  | 2028-03-09 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.11007
2493 | 115923 | HSIP HR CL Rumbles Primaries | 9999 | Miscellaneous | Safety | VDOT | Hampton Roads District-wide |  | Hampton Roads | Hampton Roads:Hampton Roads District-wide | Infrastructure Investment/Asset Management Division | Todd M Halacy | Todd.Halacy@VDOT.Virginia.gov | (757) 956-3010 | Jesse Alan Williams | Alan.Williams@vdot.virginia.gov | (757) 925-1574 |  |  |  | 0 |  | 0 | FY2021 | 102201 | 114718 | ACTIVITY DATES SET | G | Determine Requirements milestone finished 17 days early | Y | Project estimate is less than $5M and is up to 20% over budget | [5 empty] | 2020-01-14 | 2020-01-14 | 2020-03-12 | 2020-02-28 | G | 2020-03-13 | 2020-03-02 | 2020-04-23 | 2020-04-06 | G | [5 empty] | 2020-05-15 |  | 2021-05-17 |  | G | [25 empty] | 2021-06-08 |  | 2021-06-08 |  | G | 2021-06-09 |  | 2021-06-15 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | WORK/TASK ORDER | 0 | 0 | 0.076148
2494 | 116683 | STAUNTON DISTRICT ENHANCED CURVE SIGNING AND DELINEATION | 9999 | Miscellaneous | Safety | VDOT | Staunton District-wide |  | Staunton | NonMPO:NonMPO | Infrastructure Investment/Asset Management Division | Matthew Bond | Matthew.Bond@vdot.virginia.gov | (540) 332-9275 | Michael L Surratt | Michael.Surratt@VDOT.Virginia.gov | (540) 332-9325 |  |  |  | 0 |  | 0 | FY2021 | 5231661 | 5231661 | NO DATES SET YET | R | Start Development milestone is 389 days past the expected completion date | G | Project is on budget | [5 empty] | 2020-01-14 |  | 2020-01-29 |  | R | 2020-01-30 |  | 2020-02-27 |  | R | [35 empty] | 2020-09-08 |  | 2020-09-08 |  | R | 2020-12-02 |  | 2020-12-02 |  | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NOT APPLICABLE | 0 | 0 | 0.073348
2495 | 116993 | #SGR21VP PM7E-967-F21,P401 Primary Plant Mix | 9999 | Primary | Resurfacing | VDOT | Culpeper District-wide |  | Culpeper | NonMPO:NonMPO | Infrastructure Investment/Asset Management Division | Donald R Schoch | Donald.Schoch@vdot.virginia.gov | (540) 829-7500 | Donald R Schoch | Donald.Schoch@vdot.virginia.gov | (540) 829-7500 |  |  |  | 0 |  | 1 | FY2021 | 993986 | 993986 | ADVERTISED | G | Solicit Bids milestone finished on-time | G | Project is on budget | [10 empty] | 2021-03-01 | 2020-11-24 | 2021-03-05 | 2021-01-12 | G | [35 empty] | 2021-01-12 | 2021-01-12 | 2021-01-12 | 2021-01-12 | G | 2021-04-06 |  | 2021-04-06 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.10584
2496 | 117648 | ORANGE TRANSPORTATION CENTER - SIGNAL - PHASE 4 | 0015 | Primary | Facilities for Pedestrians and Bicycles | VDOT | Orange | LOUISA | Culpeper | NonMPO:NonMPO | Local Assistance Division | Gregory J Cooley | Gregory.Cooley@vdot.virginia.gov | (434) 906-7979 | John P Price | John.Price@VDOT.Virginia.gov | (540) 347-6371 | JOHN COOLEY | townplanner@townoforangeva.org | (540) 672-6917 | 0 |  | 0 | FY2021 | 42756 | 51810 | AWARDED | G | Start Delivery milestone finished on-time | Y | Project estimate is less than $5M and is up to 20% over budget | [10 empty] | 2020-09-08 | 2020-09-08 | 2020-10-05 | 2020-09-28 | G | [35 empty] | 2020-10-02 | 2020-09-28 | 2020-10-08 | 2020-10-01 | G | 2020-11-09 | 2020-10-01 | 2020-11-16 | 2020-11-16 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | WORK/TASK ORDER | 1 | 0 | 0.12794
2497 | 100550 | CFX - DOE BRANCH - VDOT FINAL GRADING AND PAVING | 0121 | Primary | New Construction Roadway | VDOT | Buchanan County | LEBANON | Bristol | NonMPO:NonMPO | Infrastructure Investment Division | Marty R Halloway | Marty.Halloway@VDOT.Virginia.gov | (276) 696-3367 | Robert C Leonard | Robert.Leonard@VDOT.Virginia.gov | (276) 696-3258 |  |  |  | 0 |  | 0 | FY2031 | 25500000 | 25500000 | NO DATES SET YET | G | Start Development milestone is 3062 days ahead of the expected completion date | G | Project is on budget | [5 empty] | 2029-07-11 |  | 2029-07-11 |  | G | 2029-07-31 |  | 2029-09-30 |  | G | [35 empty] | 2030-06-03 |  | 2030-06-03 |  | G | 2030-12-30 |  | 2031-01-15 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | DESIGN BUILD/PPTA | 0 | 0 | 0.11001
2498 | 105733 | RTE 623 - IMPROVE INTERSECTION | 0623 | Secondary | Safety | Locally | Goochland County | ASHLAND | Richmond | Richmond:Goochland County | Infrastructure Investment Division | Raymond Chapman | Scott.Chapman@vdot.virginia.gov | (804) 609-5277 | Raymond Chapman | Scott.Chapman@vdot.virginia.gov | (804) 609-5277 | TBD, Goochland County |  |  | 0 |  | 0 | FY2027 | 5476000 | 5476000 | NO DATES SET YET | G | Agreement with Locality milestone is 617 days ahead of the expected completion date | G | Project is on budget | 2022-08-31 |  | 2022-10-31 |  | G | 2022-11-01 |  | 2022-11-30 |  | G | 2023-12-29 |  | 2023-12-29 |  | G | [5 empty] | 2025-08-29 |  | 2025-09-30 |  | G | 2025-11-03 |  | 2025-11-03 |  | G | [5 empty] | 2025-11-17 |  | 2026-09-30 |  | G | [10 empty] | 2026-11-02 |  | 2026-11-02 |  | G | 2027-01-20 |  | 2027-02-16 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.17889
2499 | 109250 | ROUTE 16 (BACK OF THE DRAGON) SCENIC OVERLOOK IMPROVEMENTS | 0016 | Enhancement | Scenic or Historic Highway Programs | Locally | Smyth County | ABINGDON | Bristol | NonMPO:NonMPO | Local Assistance Division | John W Bechtold | John.Bechtold@vdot.virginia.gov | (276) 696-3365 | Roger L Musser | Roger.Musser@VDOT.Virginia.gov | (276) 696-3260 | Aaron Sizemore | asizemore@mrpdc.org | (276) 783-5103 | 0 |  | 0 | FY2021 | 935000 | 959677 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 120 days early | Y | Project estimate is less than $5M and is up to 20% over budget | 2016-10-03 | 2016-09-17 | 2016-12-30 | 2016-10-14 | G | 2017-01-03 | 2016-10-18 | 2017-01-05 | 2016-10-20 | G | 2017-01-06 | 2016-10-21 | 2017-07-13 | 2017-06-28 | G | [10 empty] | 2019-07-18 | 2018-12-17 | 2019-12-03 | 2019-01-31 | G | [5 empty] | 2019-12-05 | 2019-02-05 | 2019-12-11 | 2019-10-11 | G | 2016-11-01 | 2016-11-01 | 2017-07-10 | 2017-08-07 | R | [5 empty] | 2020-03-13 | 2020-01-15 | 2020-05-07 | 2020-03-13 | G | 2020-07-28 | 2020-03-30 | 2020-07-28 | 2020-03-30 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.17837
2500 | 109484 | #HB2.FY17 FONTAINE AVENUE STREETSCAPE IMPROVEMENTS | 0000 | Urban | Reconstruction w/o Added Capacity | Locally | Charlottesville | CHARLOTTESVILLE | Culpeper | Charlottesville:Charlottesville | Infrastructure Investment Division | Ken Connors |  |  | Michael D Barnes | MichaelD.Barnes@vdot.virginia.gov | (434) 422-9861 | Kyle Kling | klingk@charlottesville.gov | (434) 970-3993 | 1 | 2017 | 0 | FY2023 | 11700000 | 12645431 | ACTIVITY DATES SET | R | Start Purchasing Right-of-Way milestone is 44 days past the expected completion date | Y | Project estimate is greater than $10M and is over budget by (a) up to 10% or (b) up to $5M | 2016-09-28 | 2016-09-28 | 2016-10-24 | 2016-10-24 | G | 2016-10-25 | 2016-10-25 | 2016-10-31 | 2016-10-31 | G | 2016-11-15 | 2016-11-15 | 2018-01-08 | 2020-02-03 | R | [10 empty] | 2020-12-17 |  | 2021-01-08 |  | R | [5 empty] | 2021-01-12 |  | 2021-10-15 |  | G | [10 empty] | 2022-04-15 |  | 2022-06-24 |  | G | 2022-06-27 |  | 2022-08-29 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.1746
2501 | 112638 | Route 646 - Improve Curve Safety | 0646 | Secondary | Reconstruction w/o Added Capacity | VDOT | Southampton County | FRANKLIN | Hampton Roads | NonMPO:NonMPO | Infrastructure Investment Division | John G Harman | JohnG.Harman@vdot.virginia.gov | (757) 956-3269 | Jeanette W Driscoll | Jeanette.Driscoll@VDOT.Virginia.gov | (757) 956-3263 |  |  |  | 0 |  | 0 | FY2022 | 1282802 | 1270750 | ACTIVITY DATES SET | G | Complete Purchasing Right-of-Way milestone finished 16 days early | G | Project is on budget | [5 empty] | 2018-07-02 | 2018-10-15 | 2018-07-16 | 2018-10-17 | R | 2018-07-17 | 2018-10-18 | 2019-06-13 | 2019-05-03 | G | [5 empty] | 2019-12-18 | 2019-08-05 | 2020-02-18 | 2019-11-06 | G | 2020-06-10 | 2020-05-28 | 2020-06-30 | 2020-05-28 | G | 2021-02-26 |  | 2021-08-30 |  | G | 2020-07-17 | 2020-06-04 | 2021-02-10 | 2021-01-25 | G | 2019-11-26 | 2020-10-21 | 2021-02-11 | 2021-01-14 | G | [5 empty] | 2021-11-09 |  | 2021-11-09 |  | G | 2021-12-29 |  | 2022-03-28 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.18831
2502 | 113191 | GODWIN DRIVE SHARED USE PATH | 9999 | Urban | Facilities for Pedestrians and Bicycles | Locally | Manassas | MANASSAS | Northern Virginia | Northern Virginia:Manassas | Local Assistance Division | Claudia H Llana | Claudia.Llana@VDOT.Virginia.gov | (703) 259-1768 | Saif-Ur Qargha | Saif.Qargha@vdot.virginia.gov | (703) 259-3223 | Sung Jin Chung | schung@ci.manassas.va.us | (703) 257-8339 | 0 |  | 0 | FY2023 | 1506746 | 1668993 | ACTIVITY DATES SET | R | Obtained Permits milestone is 292 days past the expected completion date | Y | Project estimate is less than $5M and is up to 20% over budget | 2018-10-31 | 2018-08-15 | 2019-03-29 | 2018-09-12 | G | [5 empty] | 2019-09-03 | 2019-08-01 | 2020-03-31 | 2020-02-28 | G | [10 empty] | 2020-12-28 |  | 2021-03-11 |  | Y | [5 empty] | 2021-03-12 |  | 2022-01-13 |  | G | 2019-08-01 |  | 2020-05-05 |  | R | [5 empty] | 2022-02-14 |  | 2022-06-13 |  | G | 2022-06-14 |  | 2022-11-14 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.1352
2503 | 113461 | Three Oaks Elementary Multi Use Path | 0000 | Urban | Facilities for Pedestrians and Bicycles | Locally | Virginia Beach | NORFOLK | Hampton Roads | Hampton Roads:Virginia Beach | Local Assistance Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Marci Thompson | Marci.Thompson@vdot.virginia.gov | (757) 956-3093 | Katie Shannon | kshannon@vbgov.com | (757) 385-1514 | 0 |  | 0 | FY2022 | 537206 | 537206 | ACTIVITY DATES SET | R | Determine Requirements milestone finished 545 days late | G | Project is on budget | 2018-10-01 | 2018-10-01 | 2018-12-28 | 2019-04-04 | R | 2018-12-31 | 2019-04-14 | 2019-01-03 | 2019-04-25 | R | 2019-01-04 | 2019-04-26 | 2019-07-11 | 2021-01-06 | R | [25 empty] | 2021-06-09 |  | 2021-10-14 |  | G | [5 empty] | 2022-02-02 |  | 2022-03-02 |  | G | 2022-05-19 |  | 2022-06-30 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.094644
2504 | 113499 | Russell County - Dante Depot Restoration | 9999 | Enhancement | Rehabilitation of Historic Bldgs/Facilities | Locally | Russell County | LEBANON | Bristol | NonMPO:NonMPO | Local Assistance Division | Tabitha H Crowder | Tabitha.Crowder@vdot.virginia.gov | (276) 696-3482 | Roger L Musser | Roger.Musser@VDOT.Virginia.gov | (276) 696-3260 | Lonzo Lester | lonzo.lester@russellcountyva.us | (276) 889-8000 | 0 |  | 0 | FY2021 | 253904 | 253904 | NO DATES SET YET-PE OPEN | R | Determine Requirements milestone is 380 days past the expected completion date | G | Project is on budget | 2019-04-30 | 2018-11-01 | 2019-07-24 | 2019-07-24 | G | 2019-07-25 | 2019-07-25 | 2019-07-29 | 2019-07-29 | G | 2019-07-30 |  | 2020-02-07 |  | R | [25 empty] | 2020-03-17 | 2020-03-17 | 2020-11-16 | 2020-11-16 | G | [5 empty] | 2020-12-16 |  | 2021-01-14 |  | R | 2021-04-07 |  | 2021-04-07 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.18968
2505 | 113635 | HILLSBORO GAVER MILL SHARED-USE PATH | 0812 | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Hillsboro | LEESBURG | Northern Virginia | Northern Virginia:Loudoun County | Local Assistance Division | Amir Salahshoor | A.Salahshoor@VDOT.Virginia.gov | (703) 259-1957 | Christer P Carshult | Christer.Carshult@vdot.virginia.gov | (703) 259-1765 | Roger Vance | MayorVance@gmail.com | (703) 431-3031 | 0 |  | 0 | FY2024 | 581903 | 581903 | ACTIVITY DATES SET | G | Determine Requirements milestone finished on-time | G | Project is on budget | 2019-06-21 | 2018-08-01 | 2020-01-31 | 2018-08-30 | G | 2020-02-03 | 2018-08-31 | 2020-03-30 | 2018-09-13 | G | 2020-03-31 | 2018-09-14 | 2020-12-31 | 2020-12-31 | G | [10 empty] | 2021-10-25 |  | 2021-11-30 |  | G | 2022-02-01 |  | 2022-07-21 |  | G | 2021-12-02 |  | 2022-09-30 |  | G | [10 empty] | 2022-10-19 |  | 2023-05-31 |  | G | 2023-08-18 |  | 2024-03-29 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.48707
2506 | 113722 | Primary Extension Paving - Hampton Blvd/ 39th St. | 0337 | Urban | Resurfacing | Locally | Norfolk | NORFOLK | Hampton Roads | Hampton Roads:Norfolk | Infrastructure Investment Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Derrick Williams | Derrick.Williams@vdot.virginia.gov | (757) 956-3097 | Deborah Mangiaracina, P. E. | Deborah.Mangiaracina@norfolk.gov | (757) 664-7459 | 0 |  | 1 | FY2019 | 268807 | 268807 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 83 days early | G | Project is on budget | 2018-09-04 | 2018-09-04 | 2018-11-30 | 2019-01-07 | R | 2018-12-03 | 2019-01-08 | 2018-12-05 | 2019-01-16 | R | 2018-12-06 | 2018-07-10 | 2019-06-13 | 2019-01-16 | G | [25 empty] | 2018-05-11 | 2019-01-16 | 2019-01-16 | 2019-01-16 | G | [5 empty] | 2018-12-18 | 2018-12-18 | 2019-01-16 | 2019-01-16 | G | 2019-04-09 | 2019-01-16 | 2019-04-09 | 2019-01-16 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.15124
2507 | 113824 | Providence Road & Mount Pleasant Road FYA | 0409 | Urban | Safety | Locally | Chesapeake | NORFOLK | Hampton Roads | Hampton Roads:Chesapeake | Infrastructure Investment Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Johndel A Alcaide | John.Alcaide@vdot.virginia.gov | (757) 956-3098 | Sam Sawan, PE | sawan@cityofchesapeake.net | (757) 382-8263 | 0 |  | 0 | FY2023 | 467000 | 467000 | NO DATES SET YET-PE OPEN | G | Obtained Permits milestone finished 659 days early | G | Project is on budget | 2020-06-01 | 2020-07-15 | 2020-10-06 | 2020-08-26 | G | 2020-10-07 | 2020-08-28 | 2020-10-28 | 2020-09-17 | G | 2020-12-01 |  | 2021-03-29 |  | G | [25 empty] | 2022-03-24 | 2020-10-29 | 2022-08-19 | 2020-10-29 | G | [5 empty] | 2022-10-19 |  | 2022-11-16 |  | G | 2023-02-10 |  | 2023-02-10 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.20528
2508 | 115513 | #SMART20 Carrollton Boulevard (Rte 17) Crosswalks | 0017 | Urban | Safety and Education of Pedestrians /Bicyclisits | VDOT | Isle of Wight County | FRANKLIN | Hampton Roads | Hampton Roads:Isle of Wight County | Infrastructure Investment Division | Emmanuel Eod Ofori-Darko | Emmanuel.Darko@VDOT.Virginia.gov | (757) 956-3261 | Jesse Alan Williams | Alan.Williams@vdot.virginia.gov | (757) 925-1574 | Jamie Oliver | joliver@isleofwightus.net | (757) 846-8600 | 1 | 2020 | 0 | FY2020 | 212000 | 212000 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished on-time | G | Project is on budget | [5 empty] | 2019-12-02 | 2019-11-19 | 2019-12-02 | 2019-12-02 | G | 2019-12-03 | 2019-12-02 | 2020-03-16 | 2020-03-16 | G | [5 empty] | 2020-05-05 | 2020-05-05 | 2020-05-18 | 2020-05-18 | G | [25 empty] | 2020-06-04 | 2020-06-04 | 2020-06-04 | 2020-06-04 | G | 2020-06-05 | 2020-06-05 | 2020-06-11 | 2020-06-11 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | WORK/TASK ORDER | 1 | 0 | 0.15606
2509 | 115559 | Denbigh Fringe Park & Ride Improvements | 0060 | Primary | Restoration and Rehabilitation | VDOT | Newport News | WILLIAMSBURG | Hampton Roads | Hampton Roads:Newport News | Infrastructure Investment Division | Christopher R Carroll | C.Carroll@VDOT.Virginia.gov | (757) 253-5140 | Keith R Snead | Keith.Snead@vdot.virginia.gov | (757) 866-0418 |  |  |  | 0 |  | 0 | FY2028 | 200365 | 200365 | NO DATES SET YET | G | Start Development milestone is 1605 days ahead of the expected completion date | Y | Estimate not current | [5 empty] | 2025-07-01 |  | 2025-07-15 |  | G | 2025-07-16 |  | 2026-03-12 |  | G | [5 empty] | 2026-11-13 |  | 2026-12-29 |  | G | [5 empty] | 2027-04-16 |  | 2027-08-09 |  | G | [5 empty] | 2027-04-01 |  | 2027-07-01 |  | G | [5 empty] | 2027-08-10 |  | 2027-08-10 |  | G | 2027-11-01 |  | 2027-11-01 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.13851
2510 | 111339 | #SGR18VB - RT 692 over Champion Swamp (Fed 10445) REPLACE | 0692 | Secondary | Bridge Replacement w/o Added Capacity | VDOT | Isle of Wight County | FRANKLIN | Hampton Roads | Hampton Roads:Isle of Wight County | Infrastructure Investment Division | Mohamed A Ali | Mohamed.Ali@VDOT.Virginia.gov | (757) 956-3206 | Nancy R Marshall | Nancy.Marshall@VDOT.Virginia.gov | (757) 956-3266 |  |  |  | 0 |  | 1 | FY2023 | 2060506 | 2060506 | ACTIVITY DATES SET | R | Determine Requirements milestone finished 99 days late | G | Project is on budget | [10 empty] | 2020-10-01 | 2020-10-01 | 2020-10-07 | 2021-01-14 | R | [5 empty] | 2021-03-17 |  | 2021-07-02 |  | G | [25 empty] | 2023-01-10 |  | 2023-01-10 |  | G | 2023-04-17 |  | 2023-06-12 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.1675
2512 | 113355 | Town of Blacksburg - Main Street Pedestrian Improvements | 0000 | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Blacksburg | CHRISTIANSBURG | Salem | New River Valley:Blacksburg | Local Assistance Division | Adam J Czesnowski | Adam.Czesnowski@vdot.virginia.gov | (540) 541-1216 | Adam J Czesnowski | Adam.Czesnowski@vdot.virginia.gov | (540) 541-1216 | Randy Formica | rformica@blacksburg.gov | (540) 961-1121 | 0 |  | 0 | FY2023 | 850994 | 850994 | ACTIVITY DATES SET | R | Determine Requirements milestone finished 522 days late | G | Project is on budget | 2018-10-01 | 2018-10-01 | 2018-12-28 | 2018-11-21 | G | 2018-12-31 | 2018-12-04 | 2019-01-03 | 2018-12-10 | G | 2019-01-04 | 2019-09-23 | 2019-08-01 | 2021-01-04 | R | [10 empty] | 2022-03-10 |  | 2022-03-30 |  | G | [5 empty] | 2022-04-01 |  | 2022-09-30 |  | G | 2022-04-01 |  | 2022-09-30 |  | G | [5 empty] | 2022-11-17 |  | 2022-11-17 |  | G | 2022-12-13 |  | 2023-02-27 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.35969
2513 | 113475 | ROAD & STORM SEWER IMPROVEMENTS (MAIN & MILL STREETS) |  | Urban | Other | Locally | Dayton | HARRISONBURG | Staunton | NonMPO:NonMPO | Local Assistance Division | Donald F Komara | Donald.Komara@VDOT.Virginia.gov | (540) 434-2587 | Michael S Fulcher | Michael.Fulcher@VDOT.Virginia.gov | (540) 332-2243 | Angela Lawrence | alawrence@daytonva.us | (540) 879-2241 | 0 |  | 0 | FY2021 | 400000 | 400000 | AWARDED | G | Start Delivery milestone finished 177 days early | G | Project is on budget | 2018-10-01 | 2018-11-27 | 2018-12-28 | 2018-12-27 | G | 2018-12-31 | 2018-12-28 | 2019-01-03 | 2019-01-03 | G | 2019-01-04 | 2019-01-04 | 2019-07-11 | 2020-05-27 | R | [10 empty] | 2020-08-07 | 2020-06-01 | 2020-08-27 | 2020-06-01 | G | [5 empty] | 2020-08-31 | 2020-06-29 | 2021-01-28 | 2020-06-29 | G | 2019-12-13 | 2020-07-28 | 2020-08-24 | 2020-07-28 | G | [5 empty] | 2021-02-15 | 2020-06-30 | 2021-03-15 | 2020-06-30 | G | 2021-06-02 | 2020-06-30 | 2021-06-02 | 2020-12-07 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.11338
2514 | 113591 | TIMBER FENCE TRAIL - SEGMENT 1 | 0678 | Urban | Facilities for Pedestrians and Bicycles | Locally | Warrenton | WARRENTON | Culpeper | Northern Virginia:Warrenton | Local Assistance Division | Ken Connors |  |  | John P Price | John.Price@VDOT.Virginia.gov | (540) 347-6371 | Margaret Rice |  |  | 0 |  | 0 | FY2021 | 451409 | 451409 | ACTIVITY DATES SET | R | Solicit Bids milestone is 192 days past the expected completion date | G | Project is on budget | 2018-11-01 | 2018-06-11 | 2019-02-01 | 2018-10-02 | G | 2019-02-04 | 2018-10-18 | 2019-02-06 | 2018-10-22 | G | 2019-02-07 | 2018-12-21 | 2019-08-12 | 2019-06-28 | G | [35 empty] | 2020-07-17 | 2020-12-01 | 2020-08-13 |  | R | 2020-11-03 |  | 2020-11-03 |  | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.13167
2516 | 113812 | Traffic Control Signals | 9999 | Urban | Safety | Locally | Richmond | ASHLAND | Richmond | Richmond:Richmond | Local Assistance Division | Olena Fecek | Olena.Fecek@vdot.virginia.gov | (804) 524-6368 | Olena Fecek | Olena.Fecek@vdot.virginia.gov | (804) 524-6368 | Enrique Burgos | Enrique.Burgos@richmondgov.com | (804) 646-6337 | 0 |  | 0 | FY2023 | 1444200 | 1444200 | NO DATES SET YET-PE OPEN | G | Start Development milestone finished 107 days early | G | Project is on budget | 2020-09-01 | 2019-02-19 | 2020-11-30 | 2019-07-10 | G | 2020-12-01 | 2020-07-22 | 2020-12-03 | 2020-08-18 | G | 2020-12-04 |  | 2021-06-11 |  | G | [25 empty] | 2021-07-20 |  | 2022-03-28 |  | G | [5 empty] | 2022-06-30 |  | 2022-07-28 |  | G | 2022-10-18 |  | 2022-10-18 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.17759
2517 | 115424 | Southside Bike Lane Network |  | Urban | Facilities for Pedestrians and Bicycles | Locally | Norfolk | NORFOLK | Hampton Roads | Hampton Roads:Norfolk | Infrastructure Investment Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Derrick Williams | Derrick.Williams@vdot.virginia.gov | (757) 956-3097 | Rob Brown | Robert.Brown@norfolk.gov | (757) 664-7305 | 0 |  | 0 | FY2027 | 1015900 | 1015900 | NO DATES SET YET | G | Agreement with Locality milestone is 1342 days ahead of the expected completion date | Y | Estimate not current | 2024-08-01 |  | 2024-10-25 |  | G | 2024-10-28 |  | 2024-10-30 |  | G | 2024-10-31 |  | 2025-05-12 |  | G | [25 empty] | 2025-06-18 |  | 2026-02-25 |  | G | [5 empty] | 2026-06-01 |  | 2026-06-26 |  | G | 2026-09-16 |  | 2026-09-16 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.23382
2518 | 115539 | BERMAN PARK GREENWAY | 9999 | Urban | Safety | Locally | Falls Church | FAIRFAX | Northern Virginia | Northern Virginia:Falls Church | Local Assistance Division | Amir Salahshoor | A.Salahshoor@VDOT.Virginia.gov | (703) 259-1957 | Christer P Carshult | Christer.Carshult@vdot.virginia.gov | (703) 259-1765 | Jeff Sikes | jsikes@fallschurchva.gov | (703) 248-5296 | 0 |  | 0 | FY2025 | 600000 | 600000 | NO DATES SET YET-PE OPEN | G | Start Development milestone finished 393 days early | Y | Estimate not current | 2020-07-31 | 2019-12-01 | 2021-02-26 | 2020-02-20 | G | 2021-03-01 | 2019-12-01 | 2021-03-31 | 2020-03-03 | G | 2022-01-03 |  | 2022-09-30 |  | G | [10 empty] | 2023-08-01 |  | 2023-08-31 |  | G | [5 empty] | 2023-09-05 |  | 2024-07-31 |  | G | 2023-08-01 |  | 2024-06-28 |  | G | [5 empty] | 2024-08-01 |  | 2025-01-31 |  | G | 2025-02-03 |  | 2025-06-30 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.41525
2519 | 115605 | RTE 709 SURFACE TREAT NON-HARDSURFACED ROADWAY | 0709 | Secondary | Resurfacing | VDOT | Pulaski County | CHRISTIANSBURG | Salem | NonMPO:NonMPO | Infrastructure Investment Division | Thomas W Digiulian | Thomas.DiGiulian@VDOT.Virginia.gov | (540) 387-5356 | Christopher L Price | Christopher.Price@VDOT.Virginia.gov | (540) 381-7182 |  |  |  | 0 |  | 0 | FY2026 | 961568 | 961568 | NO DATES SET YET-PE OPEN | G | Start Development milestone finished 1221 days early | G | Project is on budget | [5 empty] | 2023-07-31 | 2020-03-25 | 2023-08-11 | 2020-04-07 | G | 2023-08-14 |  | 2024-04-09 |  | G | [5 empty] | 2024-12-13 |  | 2025-01-29 |  | G | [5 empty] | 2025-05-14 |  | 2025-09-05 |  | G | [5 empty] | 2025-04-29 |  | 2025-07-30 |  | G | [5 empty] | 2025-09-09 |  | 2025-09-09 |  | G | 2025-12-03 |  | 2025-12-03 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | SAAP CONTRACT | 0 | 0 | 0.072468
2520 | 115724 | #SGR20LP - RT 3 -- BLUE & GRAY PARKWAY | 0003 | Urban | Reconstruction w/o Added Capacity | Locally | Fredericksburg | FREDERICKSBURG | Fredericksburg | Fredericksburg:Fredericksburg | Infrastructure Investment Division | Richard A Spurlock | Richard.Spurlock@VDOT.Virginia.gov | (540) 899-4302 | Richard A Spurlock | Richard.Spurlock@VDOT.Virginia.gov | (540) 899-4302 | Erik Nelson | enelson@fredericksburgva.gov | (540) 372-1080 | 0 |  | 1 | FY2021 | 120000 | 120000 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 30 days early | G | Project is on budget | 2019-07-15 | 2018-08-15 | 2019-10-07 | 2018-10-23 | G | [5 empty] | 2019-07-15 | 2019-07-15 | 2019-07-26 | 2019-07-26 | G | [25 empty] | 2019-07-29 | 2019-07-29 | 2019-10-22 | 2019-07-29 | G | [5 empty] | 2020-04-08 | 2020-04-08 | 2020-05-05 | 2020-04-08 | G | 2020-07-24 | 2020-06-24 | 2020-07-24 | 2020-06-24 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.12063
2521 | 116245 | #I81CIP SB EXIT 205 EXTEND ACCELERATION LANE (ID #59) | 0081 | Interstate | Reconstruction w/o Added Capacity | VDOT | Rockbridge County | LEXINGTON | Staunton | NonMPO:NonMPO | Infrastructure Investment Division | John-Allen L Ennis | JohnAllen.Ennis@VDOT.Virginia.gov | (540) 332-9118 | Timothy Gregory | Tim.Gregory@vdot.virginia.gov | (540) 332-7891 |  |  |  | 0 |  | 0 | FY2025 | 3483323 | 3483323 | NO DATES SET YET-PE OPEN | G | Obtained Permits milestone finished 1174 days early | Y | Estimate not current | [5 empty] | 2020-07-01 | 2019-11-12 | 2020-07-15 | 2020-01-14 | G | 2020-07-16 |  | 2021-06-14 |  | G | [5 empty] | 2022-04-20 |  | 2022-05-03 |  | G | 2023-08-08 |  | 2023-08-21 |  | G | 2024-01-22 |  | 2024-07-24 |  | G | 2023-09-07 |  | 2024-03-19 |  | G | 2023-01-27 | 2020-05-14 | 2023-08-01 | 2020-05-14 | G | [5 empty] | 2024-08-13 |  | 2024-08-13 |  | G | 2024-11-04 |  | 2024-11-04 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.07226
2522 | 116318 | Citywide Traffic Signal Upgrades Phase IV - CN only | 0064 | Urban | Traffic Management/Engineering | Locally | Hampton | WILLIAMSBURG | Hampton Roads | Hampton Roads:Hampton | Infrastructure Investment/Asset Management Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Derrick Williams | Derrick.Williams@vdot.virginia.gov | (757) 956-3097 | Sandon Rogers, P.E. | sandon.rogers@hampton.gov | (757) 727-6786 | 0 |  | 0 | FY2021 | 1647000 | 1826190 | ACTIVITY DATES SET | Y | Solicit Bids milestone is 33 days ahead of the expected completion date and there is a risk of missing this milestone date | Y | Project estimate is less than $5M and is up to 20% over budget | 2021-01-04 | 2020-09-04 | 2021-03-31 | 2020-09-04 | G | [5 empty] | 2021-01-04 | 2020-09-05 | 2021-01-19 | 2020-09-05 | G | [25 empty] | 2020-09-08 | 2020-12-09 | 2021-03-05 | 2020-12-09 | G | [5 empty] | 2021-03-08 |  | 2021-03-26 |  | Y | 2021-06-15 |  | 2021-06-15 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.19202
2523 | 116731 | NOVA ON-CALL INSTALL SIGNING AND PAVEMENT MARKING FY21-23 | 9999 | Miscellaneous | Safety | VDOT | Northern Virginia District-wide |  | Northern Virginia | Northern Virginia:Northern Virginia District-wide | Infrastructure Investment/Asset Management Division | Nikolaos Dais | Nick.Dais@vdot.virginia.gov | (703) 259-2237 | Anwar A Ansari | Anwar.Ansari@VDOT.Virginia.gov | (703) 334-0204 |  |  |  | 0 |  | 0 | FY2021 | 884361 | 884361 | ADVERTISED | R | Solicit Bids milestone finished 119 days late | G | Project is on budget | [10 empty] | 2020-03-16 | 2020-03-16 | 2020-07-21 | 2020-07-21 | G | [35 empty] | 2020-08-11 | 2020-12-08 | 2020-08-11 | 2020-12-08 | R | 2020-11-02 |  | 2021-04-28 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | REGIONAL ON-CALL CONTRACT | 0 | 0 | 0.065463
2524 | 117109 | #SGR21VB (FED ID 19295) Bri Rehab/Rte 58 over NS Railway | 0058 | Primary | Bridge Rehab w/o Added Capacity | VDOT | Wise County | WISE | Bristol | NonMPO:NonMPO | Infrastructure Investment/Asset Management Division | Jeffrey B Powell | Jeffrey.Powell@VDOT.Virginia.gov | (276) 696-3389 | David L Lively | David.Lively@VDOT.Virginia.gov | (276) 696-3388 |  |  |  | 0 |  | 1 | FY2025 | 10724533 | 10724533 | NO DATES SET YET | G | Start Development milestone is 243 days ahead of the expected completion date | G | Project is on budget | [5 empty] | 2021-10-01 |  | 2021-10-22 |  | G | 2021-10-25 |  | 2022-08-26 |  | G | [5 empty] | 2023-04-03 |  | 2023-04-28 |  | G | 2023-12-20 |  | 2024-01-29 |  | G | 2024-06-26 |  | 2024-10-25 |  | G | 2024-02-13 |  | 2024-07-11 |  | G | 2024-03-20 |  | 2024-08-15 |  | G | [5 empty] | 2024-11-12 |  | 2024-11-12 |  | G | 2025-02-06 |  | 2025-02-06 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.18096
2525 | 117213 | FY 21 Unsignalized Intersections | 9999 | Primary | Safety | VDOT | Salem District-wide |  | Salem | Roanoke:Salem District-wide | Infrastructure Investment/Asset Management Division | Bernard S Grinnell | Sean.Grinnell@VDOT.Virginia.gov | (540) 375-0148 | Jason W Knight | Jay.Knight@vdot.virginia.gov | (540) 375-0152 |  |  |  | 0 |  | 0 | FY2022 | 705557 | 705557 | ACTIVITY DATES SET | G | Determine Requirements milestone finished 217 days early | G | Project is on budget | [5 empty] | 2020-11-16 | 2020-05-12 | 2020-12-01 | 2020-05-13 | G | 2020-12-02 | 2020-05-19 | 2021-02-15 | 2020-07-13 | G | [35 empty] | 2021-12-14 |  | 2021-12-14 |  | G | 2022-05-18 |  | 2022-05-18 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.12193
2526 | 118470 | W Broad St Pedestrian and Transit Improvements - Glenside Dr | 0250 | Primary | Safety and Education of Pedestrians /Bicyclisits | VDOT | Henrico County | ASHLAND | Richmond | Richmond:Henrico County | Infrastructure Investment Division | Raymond Chapman | Scott.Chapman@vdot.virginia.gov | (804) 609-5277 | Raymond Chapman | Scott.Chapman@vdot.virginia.gov | (804) 609-5277 |  |  |  | 0 |  | 0 | FY2027 | 11272000 | 11272000 | NO DATES SET YET | G | Start Development milestone is 946 days ahead of the expected completion date | G | Project is on budget | [5 empty] | 2023-09-05 |  | 2023-09-25 |  | G | 2023-09-26 |  | 2024-07-30 |  | G | [5 empty] | 2025-03-05 |  | 2025-04-01 |  | G | 2025-11-19 |  | 2025-12-26 |  | G | 2026-05-29 |  | 2026-09-28 |  | G | 2026-01-13 |  | 2026-06-12 |  | G | 2026-02-20 |  | 2026-07-20 |  | G | [5 empty] | 2026-10-13 |  | 2026-10-13 |  | G | 2027-01-07 |  | 2027-01-07 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.09646
2527 | 83254 | MARINER'S MUSEUM MULTI-PURPOSE TRAIL |  | Urban | Reconstruction w/ Added Capacity | Locally | Newport News | WILLIAMSBURG | Hampton Roads | Hampton Roads:Newport News | Infrastructure Investment Division | Tan Young |  |  | Chessica Villaflores | Chessica.Villaflores@vdot.virginia.gov | (757) 956-3094 | Vincent Urbano P.E. | tyoung@nngov.com | (757) 926-3677 | 0 |  | 0 | FY2019 | 920399 | 2339611 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 126 days early | R | Project estimate is less than $5M and is 20% or more over budget | [5 empty] | 2007-12-03 | 2007-10-04 | 2007-12-31 | 2007-10-04 | G | 2008-01-02 | 2007-12-20 | 2009-02-20 | 2009-02-17 | G | [35 empty] | 2014-12-18 | 2014-12-01 | 2015-02-25 | 2015-03-23 | R | 2018-08-01 | 2018-06-28 | 2018-11-01 | 2018-06-28 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.33604
2528 | 104353 | RESURFACING STREETS IN CITY OF FAIRFAX | 0000 | Urban | Resurfacing | Locally | Fairfax | FAIRFAX | Northern Virginia | Northern Virginia:Fairfax | Infrastructure Investment Division | Terry Yates | Terry.Yates@vdot.virginia.gov | (703) 259-2118 | Rita Hockman | Rita.Hockman@vdot.virginia.gov | (804) 824-7421 | Peter Millard | peter.millard@fairfaxva.gov | (703) 246-6330 | 0 |  | 0 | FY2020 | 280560 | 280560 | CONSTRUCTION STARTED | R | Start Delivery milestone finished 48 days late | G | Project is on budget | 2018-11-05 | 2018-11-05 | 2018-12-07 | 2018-12-07 | G | 2018-11-15 | 2018-12-07 | 2018-11-15 | 2018-12-17 | R | 2018-12-17 | 2018-12-31 | 2019-04-15 | 2019-02-15 | G | [35 empty] | 2019-06-03 | 2019-04-15 | 2019-09-30 | 2019-09-27 | G | 2019-12-31 | 2019-12-30 | 2020-04-23 | 2020-06-10 | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.20081
2529 | 107291 | Signalized Intersection at Roanoke St & Falling Branch Rd | 0011 | Urban | Traffic Management/Engineering | Locally | Christiansburg | CHRISTIANSBURG | Salem | New River Valley:Christiansburg | Local Assistance Division | James M Guy | james.guy@vdot.virginia.gov | (540) 387-5247 | Adam J Czesnowski | Adam.Czesnowski@vdot.virginia.gov | (540) 541-1216 | Wayne Nelson | wnelson@christiansburg.org | (540) 382-6120 | 0 |  | 0 | FY2019 | 2337083 | 2337083 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 16 days early | G | Project is on budget | 2015-07-01 | 2015-07-01 | 2015-07-30 | 2015-07-30 | G | 2015-07-31 | 2016-02-18 | 2016-02-17 | 2016-03-09 | R | 2016-06-03 | 2016-06-03 | 2018-02-14 | 2018-02-02 | G | [10 empty] | 2018-04-20 | 2018-04-19 | 2018-05-03 | 2018-04-19 | G | [20 empty] | 2018-07-02 | 2018-06-29 | 2018-07-02 | 2018-07-01 | G | 2018-07-03 | 2018-12-18 | 2019-01-03 | 2018-12-18 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.1086
2530 | 116208 | DISTRICT-WIDE SYSTEMIC PEDESTRIAN CROSSING | 9999 | Miscellaneous | Safety | VDOT | Fredericksburg District-wide |  | Fredericksburg | Fredericksburg:Fredericksburg District-wide | Infrastructure Investment/Asset Management Division | Peter A Hedrich | Peter.Hedrich@vdot.virginia.gov | (540) 899-4540 | Jessica Graves | Jessica.Graves@vdot.virginia.gov | (540) 899-4267 |  |  |  | 0 |  | 0 | FY2023 | 310968 | 310968 | ACTIVITY DATES SET | G | Determine Requirements milestone finished 1 days early | G | Project is on budget | [5 empty] | 2019-11-12 | 2019-10-29 | 2019-11-12 | 2019-11-06 | G | 2019-11-13 | 2019-11-07 | 2020-02-27 | 2020-02-26 | G | [5 empty] | 2022-08-10 |  | 2022-08-23 |  | G | [25 empty] | 2022-09-09 |  | 2022-09-15 |  | G | 2022-09-16 |  | 2022-12-14 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | WORK/TASK ORDER | 0 | 0 | 0.062201
2531 | 116277 | #I81CIP NB MM 233 TO 237, WEYERS CAVE TCL (ID #44) | 0081 | Interstate | Bridge Replacement w/ Added Capacity | VDOT | Augusta County | HARRISONBURG | Staunton | NonMPO:NonMPO | Infrastructure Investment Division | John-Allen L Ennis | JohnAllen.Ennis@VDOT.Virginia.gov | (540) 332-9118 | Jennifer Hoover | Jennifer.Hoover@vdot.virginia.gov | (540) 332-2264 |  |  |  | 0 |  | 0 | FY2025 | 100798170 | 100798170 | NO DATES SET YET-PE OPEN | G | Start Development milestone finished 159 days early | G | Project is on budget | [5 empty] | 2020-07-01 | 2020-01-27 | 2020-07-15 | 2020-02-07 | G | 2020-07-16 |  | 2021-08-24 |  | G | [5 empty] | 2022-08-23 |  | 2022-09-06 |  | G | 2023-12-05 |  | 2023-12-18 |  | G | 2024-05-15 |  | 2024-11-19 |  | G | 2024-01-05 |  | 2024-07-11 |  | G | 2023-05-22 |  | 2024-01-29 |  | G | [5 empty] | 2024-12-10 |  | 2024-12-10 |  | G | 2025-04-03 |  | 2025-04-03 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.14657
2532 | 116697 | Victoria St & Caldwell St Drainage Improvements | 0000 | Urban | Mitigation of Water Pollution Due to Highway Runof | Locally | Roanoke | SALEM | Salem | Roanoke:Roanoke City | Local Assistance Division | Cheryl B Becker | Cheryl.Becker@vdot.virginia.gov | (540) 492-2531 | Cheryl B Becker | Cheryl.Becker@vdot.virginia.gov | (540) 492-2531 | Joseph Arthur | Joseph.Arthur@roanokeva.gov | (540) 853-5901 | 0 |  | 0 | FY2022 | 440000 | 440000 | NO DATES SET YET-PE OPEN | G | Start Development milestone finished 104 days early | G | Project is on budget | 2020-07-06 | 2020-06-01 | 2020-09-28 | 2020-06-18 | G | 2020-09-29 | 2020-06-19 | 2020-10-01 | 2020-06-19 | G | 2020-10-02 |  | 2021-04-14 |  | G | [25 empty] | 2021-05-20 |  | 2022-01-27 |  | G | [5 empty] | 2022-02-25 |  | 2022-03-24 |  | G | 2022-06-13 |  | 2022-06-13 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.20379
2533 | 116853 | MOSBY BOULEVARD SIDEWALK CONNECTIVITY |  | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Berryville | EDINBURG | Staunton | NonMPO:NonMPO | Local Assistance Division | Kimberly Cameron | Kim.Cameron@vdot.virginia.gov | (540) 332-7886 | Jeffery A Lineberry | Jeff.Lineberry@VDOT.Virginia.gov | (540) 332-2265 | Christy Dunkle | planner@berryvilleva.gov | (540) 955-4081 | 0 |  | 0 | FY2025 | 154191 | 154191 | NO DATES SET YET | G | Agreement with Locality milestone is 57 days ahead of the expected completion date | G | Project is on budget | 2020-12-08 |  | 2021-04-19 |  | G | 2021-04-20 |  | 2021-05-10 |  | G | 2021-11-16 |  | 2022-03-16 |  | G | [10 empty] | 2023-07-05 |  | 2023-08-08 |  | G | [5 empty] | 2023-08-09 |  | 2024-01-11 |  | G | 2023-09-14 |  | 2024-02-20 |  | G | [5 empty] | 2024-04-17 |  | 2024-05-14 |  | G | 2024-08-02 |  | 2024-08-02 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.42606
2534 | 117146 | #SGR21LP 114-City of Hampton 425 Power Plant Parkway | 0415 | Urban | Resurfacing | Locally | Hampton | WILLIAMSBURG | Hampton Roads | Hampton Roads:Hampton | Infrastructure Investment/Asset Management Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Derrick Williams | Derrick.Williams@vdot.virginia.gov | (757) 956-3097 | Sandon Rogers, P.E. | Sandon.rogers@hampton.gov | (757) 727-6786 | 0 |  | 1 | FY2022 | 482000 | 482000 | NO DATES SET YET | G | Agreement with Locality milestone is 80 days ahead of the expected completion date | G | Project is on budget | 2021-01-04 |  | 2021-05-12 |  | G | 2021-05-13 |  | 2021-06-03 |  | G | 2021-07-02 |  | 2021-07-30 |  | G | [25 empty] | 2021-07-02 |  | 2021-07-30 |  | G | [5 empty] | 2021-09-28 |  | 2021-10-26 |  | G | 2022-01-21 |  | 2022-01-21 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.097052
2535 | 117733 | ITTF HIGH SPEED COMMUNICATIONS ARTERIALS - NORTHWEST #2 | 9999 | Miscellaneous | Traffic Management/Engineering | VDOT | Statewide |  | Statewide | NonMPO:NonMPO | Infrastructure Investment/Asset Management Division | Catherine C Mcghee | Cathy.McGhee@VDOT.Virginia.gov | (434) 293-1973 | Steven K Damron | Steven.Damron@VDOT.Virginia.gov | (804) 786-1172 |  |  |  | 0 |  | 0 | FY2021 | 260000 | 260000 | ACTIVITY DATES SET | R | Solicit Bids milestone is 96 days past the expected completion date | G | Project is on budget | [10 empty] | 2020-07-01 | 2020-11-16 | 2020-11-06 | 2021-02-04 | R | [35 empty] | 2020-11-10 |  | 2020-11-17 |  | R | 2020-11-18 |  | 2020-11-24 |  | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | WORK/TASK ORDER | 0 | 1 | 0.19609
2536 | 118479 | #SGR21LP - City of Petersburg 1064 S Crater Rd | 0301 | Urban | Resurfacing | VDOT | Petersburg | PETERSBURG | Richmond | Tri-Cities:Petersburg | Infrastructure Investment/Asset Management Division | Raymond Chapman | Scott.Chapman@vdot.virginia.gov | (804) 609-5277 | Raymond Chapman | Scott.Chapman@vdot.virginia.gov | (804) 609-5277 |  |  |  | 0 |  | 1 | FY2023 | 565758 | 565758 | NO DATES SET YET | G | Start Development milestone is 190 days ahead of the expected completion date | G | Project is on budget | [5 empty] | 2021-08-17 |  | 2021-08-30 |  | G | 2021-08-31 |  | 2021-11-10 |  | G | [35 empty] | 2022-06-14 |  | 2022-06-14 |  | G | 2022-09-02 |  | 2022-09-02 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.060718
2537 | 97225 | RTE 43 OVER STONEY CREEK (STR. 02595) - BRIDGE REPLACEMENT | 0043 | Primary | Bridge Replacement w/o Added Capacity | VDOT | Bedford County | BEDFORD | Salem | NonMPO:NonMPO | Infrastructure Investment Division | Anthony T Marshall | Todd.Marshall@VDOT.Virginia.gov | (540) 387-5460 | Anthony L Handy | Tony.Handy@VDOT.Virginia.gov | (540) 352-9050 |  |  |  | 0 |  | 0 | FY2019 | 8492844 | 4246422 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished on-time | G | Project is on budget | [5 empty] | 2010-06-01 | 2011-02-01 | 2010-07-01 | 2011-02-01 | R | 2014-11-25 | 2014-11-25 | 2016-04-04 | 2016-03-30 | G | [5 empty] | 2016-02-26 | 2016-02-26 | 2016-03-30 | 2016-03-30 | G | 2017-03-01 | 2017-03-01 | 2017-03-14 | 2017-03-14 | G | 2017-08-18 | 2017-08-18 | 2018-03-19 | 2018-03-19 | G | 2017-03-17 | 2017-03-17 | 2017-08-23 | 2017-08-23 | G | 2017-03-21 | 2017-03-21 | 2018-03-13 | 2018-05-24 | R | [5 empty] | 2018-02-23 | 2018-06-26 | 2018-03-13 | 2018-06-26 | R | 2018-04-13 | 2018-08-13 | 2018-08-13 | 2018-08-13 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.12229
2538 | 104880 | RIDGEFIELD PKWY - CONSTRUCT SIDEWALK | 9999 | Secondary | Facilities for Pedestrians and Bicycles | Locally | Henrico County | ASHLAND | Richmond | Richmond:Henrico County | Infrastructure Investment Division | Cynthia Crouch | Cynthia.Crouch@vdot.virginia.gov | (804) 609-5313 | Cynthia Crouch | Cynthia.Crouch@vdot.virginia.gov | (804) 609-5313 | Michael Aust | AUS019@henrico.us | (804) 501-4019 | 0 |  | 0 | FY2019 | 1172010 | 1172000 | AWARDED | R | Start Delivery milestone finished 621 days late | G | Project is on budget | 2014-06-30 | 2014-06-11 | 2014-06-30 | 2014-06-11 | G | 2014-03-31 | 2014-07-16 | 2014-03-31 | 2014-07-16 | R | 2015-12-31 | 2015-12-01 | 2017-10-30 | 2017-12-21 | R | [5 empty] | 2016-10-03 | 2018-03-12 | 2016-10-28 | 2018-03-21 | R | 2017-01-10 | 2016-11-08 | 2017-01-19 | 2016-11-08 | G | [5 empty] | 2017-12-05 | 2018-12-05 | 2018-08-07 | 2019-10-04 | R | [10 empty] | 2018-11-30 | 2020-08-21 | 2018-12-28 | 2020-08-21 | R | 2019-01-30 | 2020-08-24 | 2019-02-28 | 2020-11-10 | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.2615
2539 | 107533 | TAP - APPOMATTOX RIVER TRAIL - Phase 5 |  | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Colonial Heights | CHESTERFIELD | Richmond | Tri-Cities:Colonial Heights | Local Assistance Division | Evan Austin | Evan.Austin@vdot.virginia.gov | (804) 609-5384 | Evan Austin | Evan.Austin@vdot.virginia.gov | (804) 609-5384 | Keith A Chisolm | chisolmk@colonialheightsva.gov | (804) 520-9215 | 0 |  | 0 | FY2022 | 645500 | 1244816 | ACTIVITY DATES SET | R | Start Purchasing Right-of-Way milestone is 235 days past the expected completion date | R | Project estimate is less than $5M and is 20% or more over budget | 2016-05-01 | 2016-05-01 | 2016-06-13 | 2016-06-13 | G | 2016-08-01 | 2016-08-01 | 2016-09-19 | 2016-09-19 | G | 2016-09-20 | 2019-03-12 | 2019-05-31 | 2019-05-31 | G | [5 empty] | 2020-04-20 | 2020-04-20 | 2020-05-01 | 2020-04-30 | G | 2020-03-27 |  | 2020-07-01 |  | R | [5 empty] | 2020-07-06 |  | 2021-07-01 |  | G | 2020-12-30 |  | 2021-09-01 |  | G | [5 empty] | 2021-07-20 |  | 2021-11-01 |  | G | 2021-11-02 |  | 2022-03-01 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.31946
2540 | 108909 | #HB2.FY17 Route 460 at Franklin Street EB Ramp Construction | 0460 | Primary | New Construction Roadway | VDOT | Christiansburg | CHRISTIANSBURG | Salem | New River Valley:Christiansburg | Infrastructure Investment Division | Marvin D Mann | M.Mann@VDOT.Virginia.gov | (540) 378-5055 | Marvin D Mann | M.Mann@VDOT.Virginia.gov | (540) 378-5055 | Dan Brugh | brughjd@montgomerycountyva.gov | (540) 394-2145 | 1 | 2017 | 0 | FY2019 | 2124395 | 2124395 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 214 days early | G | Project is on budget | [5 empty] | 2016-08-12 | 2016-08-12 | 2016-08-25 | 2016-08-25 | G | 2016-03-17 | 2016-03-17 | 2018-10-09 | 2017-06-19 | G | [5 empty] | 2017-12-28 | 2017-08-16 | 2018-01-11 | 2017-08-16 | G | [5 empty] | 2016-05-24 | 2016-05-24 | 2016-05-24 | 2016-05-24 | G | [15 empty] | 2018-06-15 | 2018-02-13 | 2018-07-10 | 2018-02-13 | G | 2018-08-29 | 2018-04-27 | 2018-11-27 | 2018-04-27 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.090029
2542 | 111364 | #SMART18 - Safety Improvements to Rte 670 & Rte 834 | 0834 | Secondary | Reconstruction w/o Added Capacity | VDOT | Franklin County | BEDFORD | Salem | NonMPO:NonMPO | Infrastructure Investment Division | Alex H Price | Alex.Price@VDOT.Virginia.gov | (540) 378-5053 | C E Cumbie | C.Cumbie@VDOT.Virginia.gov | (540) 387-5561 | Lisa Cooper | lisa.cooper@franklincountyva.gov | (540) 483-6642 | 1 | 2018 | 0 | FY2022 | 3940161 | 3940161 | ACTIVITY DATES SET | G | Start Purchasing Right-of-Way milestone finished 109 days early | G | Project is on budget | [5 empty] | 2018-07-02 | 2018-06-21 | 2018-07-16 | 2018-06-21 | G | 2018-07-17 | 2018-11-01 | 2019-02-04 | 2018-12-21 | G | [5 empty] | 2019-10-25 | 2019-09-18 | 2019-11-07 | 2019-10-29 | G | 2021-02-19 | 2020-10-12 | 2021-03-05 | 2020-11-16 | G | 2021-07-28 | 2021-01-20 | 2022-02-07 |  | G | 2021-03-23 | 2020-11-25 | 2021-09-23 |  | G | 2020-08-04 | 2019-02-15 | 2021-02-12 | 2019-02-15 | G | [5 empty] | 2022-02-08 |  | 2022-02-08 |  | G | 2022-04-29 |  | 2022-05-12 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 1 | 0.19833
2543 | 111545 | #SGR19LP - ALEXANDRIA PRIMARY EXTENSION PAVING FY18 - RT 1 | 0001 | Urban | Resurfacing | Locally | Alexandria | FAIRFAX | Northern Virginia | Northern Virginia:Alexandria | Local Assistance Division | Amir Salahshoor | A.Salahshoor@VDOT.Virginia.gov | (703) 259-1957 | Rita Hockman | Rita.Hockman@vdot.virginia.gov | (804) 824-7421 | TBD |  |  | 0 |  | 0 | FY2019 |  |  | PROJECT CLOSEOUT COMPLETE | R | Determine Requirements milestone finished 148 days late | R | Critical information missing | 2017-07-03 | 2017-07-03 | 2017-10-25 | 2017-07-03 | G | [5 empty] | 2017-07-03 | 2017-11-12 | 2017-07-17 | 2017-12-12 | R | [35 empty] | 2018-05-30 | 2017-09-18 | 2018-06-26 | 2017-09-18 | G | 2018-06-27 | 2017-09-19 | 2018-08-07 | 2017-09-19 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.19956
2544 | 112817 | MONUMENT DRIVE COMMUTER PARKING GARAGE AND TRANSIT CENTER | 7436 | Secondary | Other | Locally | Fairfax County | FAIRFAX | Northern Virginia | Northern Virginia:Fairfax County | Infrastructure Investment Division | Amir Salahshoor | A.Salahshoor@VDOT.Virginia.gov | (703) 259-1957 | Robert J Strevell | Robert.Strevell@vdot.virginia.gov | (703) 259-1988 | Ipek Aktuglu | Ipek.Aktuglu@fairfaxcounty.gov | (703) 324-1751 | 0 |  | 0 | FY2022 | 43400000 | 43400000 | ACTIVITY DATES SET | G | Complete Purchasing Right-of-Way milestone finished on-time | G | Project is on budget | 2018-04-02 | 2018-04-02 | 2018-06-25 | 2018-10-23 | R | 2018-06-26 | 2018-11-01 | 2018-06-28 | 2018-11-21 | R | 2018-06-29 | 2018-11-26 | 2019-07-01 | 2020-12-31 | R | [10 empty] | 2021-01-04 | 2021-01-04 | 2021-01-04 | 2021-01-04 | G | [5 empty] | 2021-01-07 | 2021-01-07 | 2021-01-07 | 2021-01-07 | G | [10 empty] | 2021-01-27 |  | 2021-04-30 |  | G | 2021-05-03 |  | 2021-09-30 |  | G | Preliminary design and/or investigations are still underway | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.28794
2545 | 113748 | Systemic Flashing Yellow Arrow Improvements Phase 2 | 9999 | Urban | Traffic Management/Engineering | Locally | Norfolk | NORFOLK | Hampton Roads | Hampton Roads:Norfolk | Infrastructure Investment Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Derrick Williams | Derrick.Williams@vdot.virginia.gov | (757) 956-3097 | Olga Beltsar, P.E. | olga.beltstar@norfolk.gov | (757) 664-7336 | 0 |  | 0 | FY2021 | 636141 | 636141 | NO DATES SET YET-PE OPEN | R | Determine Requirements milestone is 342 days past the expected completion date | G | Project is on budget | 2019-06-05 | 2019-01-11 | 2019-08-28 | 2020-03-09 | R | 2019-08-29 | 2020-03-09 | 2019-09-03 | 2020-04-02 | R | 2019-09-04 | 2020-04-03 | 2020-03-16 |  | R | [25 empty] | 2020-04-21 | 2020-06-18 | 2020-12-23 |  | R | [5 empty] | 2021-01-26 |  | 2021-02-23 |  | Y | 2021-05-12 |  | 2021-05-12 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.40816
2546 | 115528 | #SMART20 U.S. Route 460 at U.S. Route 258 Turn Lane Improve | 0460 | Urban | Reconstruction w/o Added Capacity | Locally | Isle of Wight County | FRANKLIN | Hampton Roads | Hampton Roads:Isle of Wight County | Infrastructure Investment Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Bryant H Porter | Bryant.Porter@VDOT.Virginia.gov | (757) 956-3092 | Jamie Oliver | joliver@isleofwightus.net | (757) 846-8600 | 1 | 2020 | 0 | FY2026 | 3234936 | 3234936 | NO DATES SET YET | G | Agreement with Locality milestone is 914 days ahead of the expected completion date | Y | Estimate not current | 2023-06-01 |  | 2023-08-24 |  | G | 2023-08-25 |  | 2023-08-29 |  | G | 2023-08-30 |  | 2024-03-12 |  | G | [10 empty] | 2025-03-14 |  | 2025-04-03 |  | G | [5 empty] | 2025-04-07 |  | 2026-01-15 |  | G | 2024-04-17 |  | 2024-12-19 |  | G | [5 empty] | 2026-02-04 |  | 2026-03-04 |  | G | 2026-05-21 |  | 2026-05-21 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.20679
2547 | 116083 | WALNEY RD AND BRADDOCK RD- SHARED USE PATHS | 9999 | Secondary | Facilities for Pedestrians and Bicycles | VDOT | Fairfax County | FAIRFAX | Northern Virginia | Northern Virginia:Fairfax County | Infrastructure Investment Division | Susan N Shaw | Susan.Shaw@VDOT.Virginia.gov | (703) 259-1995 | Harinderbir S Warraich | HS.Warraich@VDOT.Virginia.gov | (571) 459-2362 | Lauren Delmare | lauren.delmare@fairfaxcounty.gov | (703) 877-5781 | 0 |  | 0 | FY2020 | 4150000 | 4150000 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 97 days early | G | Project is on budget | 2019-10-01 | 2019-10-01 | 2019-10-10 | 2019-10-10 | G | 2019-10-01 | 2019-10-28 | 2020-01-30 | 2019-10-28 | G | 2020-01-31 | 2019-10-29 | 2021-02-01 | 2019-10-30 | G | [5 empty] | 2019-10-31 | 2019-10-31 | 2019-11-05 | 2019-11-05 | G | [25 empty] | 2019-11-07 | 2019-11-20 | 2020-03-09 | 2019-11-20 | G | 2019-10-01 | 2019-11-21 | 2020-02-26 | 2019-11-21 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | WORK/TASK ORDER | 1 | 0 | 0.081474
2548 | 116734 | TRAFFIC CALMING |  | Urban | Facilities for Pedestrians and Bicycles | Locally | Richmond | ASHLAND | Richmond | Richmond:Richmond | Local Assistance Division | Olena Fecek | Olena.Fecek@vdot.virginia.gov | (804) 524-6368 | Olena Fecek | Olena.Fecek@vdot.virginia.gov | (804) 524-6368 | Yongping Wang, P.E. | Yongping.Wang@richmondgov.com | (804) 646-2467 | 0 |  | 0 | FY2024 | 553000 | 553000 | NO DATES SET YET-PE OPEN | G | Start Development milestone finished 115 days early | G | Project is on budget | 2020-11-05 | 2020-10-07 | 2021-03-22 | 2020-11-10 | G | 2021-03-23 | 2020-12-08 | 2021-04-12 | 2020-12-18 | G | 2021-05-11 |  | 2021-09-01 |  | G | [25 empty] | 2022-08-29 |  | 2023-02-02 |  | G | [5 empty] | 2023-04-03 |  | 2023-04-28 |  | G | 2023-07-19 |  | 2023-07-19 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.16714
2549 | 117021 | #SGR21VB ROUTE 640 BRIDGE AND APPROACHES |  | Secondary | Bridge Replacement w/o Added Capacity | VDOT | Highland County | LEXINGTON | Staunton | NonMPO:NonMPO | Infrastructure Investment Division | Eulogio A Javier | Eulogio.Javier@VDOT.Virginia.gov | (540) 332-9105 | Amedebrhan Asfaw | Amedebrhan.Asfaw@vdot.virginia.gov | (540) 332-9541 |  |  |  | 0 |  | 1 | FY2024 | 4630089 | 4630089 | NO DATES SET YET-PE OPEN | G | Start Development milestone finished 18 days early | G | Project is on budget | [5 empty] | 2020-08-17 | 2020-08-17 | 2020-09-04 | 2020-08-17 | G | 2020-09-08 |  | 2021-07-13 |  | G | [5 empty] | 2022-02-15 |  | 2022-03-15 |  | G | 2022-11-01 |  | 2022-12-08 |  | G | 2023-05-11 |  | 2023-09-11 |  | G | 2022-12-23 |  | 2023-05-25 |  | G | 2023-01-19 |  | 2023-06-16 |  | G | [5 empty] | 2023-09-12 |  | 2023-09-12 |  | G | 2023-12-05 |  | 2023-12-05 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.060021
2550 | 109074 | Monticello Avenue Multi-Use Trail | 0321 | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Williamsburg | WILLIAMSBURG | Hampton Roads | Hampton Roads:Williamsburg | Local Assistance Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Chessica Villaflores | Chessica.Villaflores@vdot.virginia.gov | (757) 956-3094 | Aaron Small | asmall@williamsburgva.gov | (757) 220-6140 | 0 |  | 0 | FY2021 | 1323900 | 1249742 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 594 days early | G | Project is on budget | 2016-08-19 | 2016-08-19 | 2016-09-29 | 2016-09-29 | G | 2016-09-30 | 2016-09-30 | 2016-10-19 | 2016-10-19 | G | 2016-10-20 | 2016-10-20 | 2019-01-08 | 2019-01-08 | G | [10 empty] | 2019-10-30 | 2019-08-13 | 2019-11-20 | 2019-08-13 | G | [5 empty] | 2019-11-22 | 2019-07-01 | 2020-09-02 | 2019-07-01 | G | [10 empty] | 2020-09-21 | 2019-07-26 | 2020-10-16 | 2019-08-13 | G | 2020-10-20 | 2019-09-24 | 2021-05-27 | 2019-10-11 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.41084
2552 | 111415 | Smith Creek Trail Pedestrian Bridge |  | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Clifton Forge | LEXINGTON | Staunton | NonMPO:NonMPO | Local Assistance Division | Michael L Branscome | Michael.Branscome@VDOT.Virginia.gov | (540) 332-2377 | Jamison Brown | Jamison.Brown@vdot.virginia.gov | (540) 332-7389 | Ricky Bourne | rbourne@cliftonforgeva.gov | (540) 863-2500 | 0 |  | 0 | FY2021 | 409812 | 406860 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 320 days early | G | Project is on budget | 2018-03-01 | 2017-10-16 | 2018-05-23 | 2017-11-21 | G | 2018-05-24 | 2017-11-22 | 2018-05-29 | 2018-01-09 | G | 2018-05-30 | 2019-06-19 | 2019-06-13 | 2019-09-13 | R | [35 empty] | 2020-09-17 | 2020-03-27 | 2020-12-15 | 2020-05-12 | G | 2021-01-20 | 2020-05-12 | 2021-04-14 | 2020-05-29 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.38886
2553 | 111720 | TOBACCO HERITAGE TRAIL - HALIFAX COUNTY EXTENSION |  | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Halifax County | HALIFAX | Lynchburg | NonMPO:NonMPO | Local Assistance Division | Sharon S White | Sharon.White@VDOT.Virginia.gov | (434) 856-8220 | Sharon S White | Sharon.White@VDOT.Virginia.gov | (434) 856-8220 | Robin Tuck | rtuck@southsidepdc.org | (434) 447-7101 | 0 |  | 0 | FY2020 | 428000 | 945000 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 40 days early | R | Project estimate is less than $5M and is 20% or more over budget | 2007-09-11 | 2017-09-11 | 2017-09-29 | 2017-10-04 | R | 2017-11-07 | 2017-11-07 | 2017-11-07 | 2017-11-07 | G | 2017-11-08 | 2017-11-08 | 2018-07-17 | 2018-07-10 | G | [35 empty] | 2019-12-27 | 2019-08-27 | 2020-01-28 | 2019-08-27 | G | 2020-01-29 | 2020-01-28 | 2020-03-10 | 2020-01-30 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.26066
2554 | 113693 | #SGR19LB -??Rotunda Avenue over Tributary Goose Creek | 9999 | Urban | Bridge Replacement w/o Added Capacity | Locally | Chesapeake | NORFOLK | Hampton Roads | Hampton Roads:Chesapeake | Infrastructure Investment Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Johndel A Alcaide | John.Alcaide@vdot.virginia.gov | (757) 956-3098 | Sam Sawan | sawan@cityofchesapeake.net | (757) 382-8263 | 0 |  | 1 | FY2024 | 1195000 | 1195000 | NO DATES SET YET | G | Agreement with Locality milestone is 295 days ahead of the expected completion date | Y | Estimate not current | 2021-09-15 |  | 2021-12-13 |  | G | 2021-12-14 |  | 2021-12-16 |  | G | 2021-12-17 |  | 2022-06-24 |  | G | [10 empty] | 2023-04-21 |  | 2023-05-11 |  | G | [5 empty] | 2023-05-15 |  | 2024-02-27 |  | G | 2022-08-02 |  | 2023-04-10 |  | G | [5 empty] | 2024-03-14 |  | 2024-04-10 |  | G | 2024-06-28 |  | 2024-06-28 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.13661
2555 | 114055 | RTE 630 -RURAL RUSTIC ROAD (SURFACE TREAT NON-HARDSURFACE RD | 0630 | Secondary | Reconstruction w/o Added Capacity | VDOT | Orange County | LOUISA | Culpeper | NonMPO:NonMPO | Infrastructure Investment Division | Ken Connors |  |  | Bethel Kefyalew | Bethel.Kefyalew@vdot.virginia.gov | (540) 603-6015 |  |  |  | 0 |  | 0 | FY2024 | 201500 | 201500 | NO DATES SET YET | R | Start Development milestone is 122 days past the expected completion date | Y | Estimate not current | [5 empty] | 2020-10-01 |  | 2020-10-22 |  | R | 2020-10-23 |  | 2021-08-26 |  | G | [5 empty] | 2022-04-01 |  | 2022-04-28 |  | G | [5 empty] | 2022-12-21 |  | 2023-04-25 |  | G | [5 empty] | 2022-09-08 |  | 2023-02-13 |  | G | [5 empty] | 2023-05-09 |  | 2023-05-09 |  | G | 2023-07-28 |  | 2023-07-28 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | SAAP CONTRACT | 0 | 0 | 0.094166
2556 | 115530 | #SMART20 - ACCESS IMPROVEMENTS TO THE LANDMARK TRANSIT HUB | 9999 | Urban | Facilities for Pedestrians and Bicycles | Locally | Alexandria | FAIRFAX | Northern Virginia | Northern Virginia:Alexandria | Infrastructure Investment Division | Nassre Y Obeed | Nassre.Obeed@VDOT.Virginia.gov | (703) 259-1723 | Marlene Pinedo Fortich | Sofia.Pinedo@vdot.virginia.gov | (703) 259-1724 | Ramiro RIos | Ramiro.Rios@alexandriava.gov | (704) 746-4007 | 1 | 2020 | 0 | FY2028 | 6334630 | 6334630 | NO DATES SET YET | G | Agreement with Locality milestone is 1103 days ahead of the expected completion date | G | Project is on budget | 2023-08-01 |  | 2024-02-29 |  | G | 2024-03-01 |  | 2024-03-29 |  | G | 2024-11-01 |  | 2025-05-30 |  | G | [10 empty] | 2026-06-01 |  | 2026-06-30 |  | G | [5 empty] | 2026-07-02 |  | 2027-04-29 |  | G | 2026-06-01 |  | 2027-04-30 |  | G | [5 empty] | 2027-06-01 |  | 2027-09-30 |  | G | 2027-12-23 |  | 2028-04-28 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.23682
2557 | 116269 | #I81CIP NB & SB MM 221 TO 225, 3-LANE WIDENING (ID #61) | 0081 | Interstate | Reconstruction w/ Added Capacity | VDOT | Augusta County | HARRISONBURG | Staunton | SAW:Augusta County | Infrastructure Investment Division | John-Allen L Ennis | JohnAllen.Ennis@VDOT.Virginia.gov | (540) 332-9118 | Scott A Alexander | Scott.Alexander@VDOT.Virginia.gov | (540) 332-9030 |  |  |  | 0 |  | 0 | FY2025 | 140209650 | 140209650 | NO DATES SET YET-PE OPEN | G | Start Development milestone finished 159 days early | G | Project is on budget | [5 empty] | 2020-07-01 | 2020-01-27 | 2020-07-15 | 2020-02-07 | G | 2020-07-16 |  | 2021-08-24 |  | G | [5 empty] | 2022-08-23 |  | 2022-09-06 |  | G | 2023-12-05 |  | 2023-12-18 |  | G | 2024-05-15 |  | 2024-11-19 |  | G | 2024-01-05 |  | 2024-07-11 |  | G | 2023-05-22 |  | 2024-01-29 |  | G | [5 empty] | 2024-12-10 |  | 2024-12-10 |  | G | 2025-04-03 |  | 2025-04-03 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.10528
2558 | 116915 | TIMBER FENCE TRAIL - SEGMENT 2 | 0678 | Urban | Facilities for Pedestrians and Bicycles | Locally | Warrenton | WARRENTON | Culpeper | Northern Virginia:Warrenton | Local Assistance Division | Gregory J Cooley | Gregory.Cooley@vdot.virginia.gov | (434) 906-7979 | John P Price | John.Price@VDOT.Virginia.gov | (540) 347-6371 | Paul Bernard | pbernard@warrentonva.gov | (540) 347-1101 | 0 |  | 0 | FY2024 | 508890 | 508890 | NO DATES SET YET | G | Agreement with Locality milestone is 150 days ahead of the expected completion date | G | Project is on budget | 2021-03-16 |  | 2021-07-21 |  | G | 2021-07-22 |  | 2021-08-11 |  | G | 2022-02-24 |  | 2022-06-16 |  | G | [25 empty] | 2023-06-13 |  | 2023-11-09 |  | G | [5 empty] | 2024-01-16 |  | 2024-02-12 |  | G | 2024-05-01 |  | 2024-05-01 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.13183
2559 | 117082 | #SGR21LB (Fed ID 20608) Br Repl/E Chilhowie St over MF Holst | 0000 | Primary | Bridge Replacement w/o Added Capacity | VDOT | Marion | ABINGDON | Bristol | NonMPO:NonMPO | Infrastructure Investment/Asset Management Division | Gary Lester |  |  | Daniel B Cannon | Daniel.Cannon@VDOT.Virginia.gov | (276) 696-3376 | Cecil Hicks | rchicks@marionva.org | (276) 783-4113 | 0 |  | 1 | FY2025 | 4273941 | 4273941 | NO DATES SET YET | G | Start Development milestone is 247 days ahead of the expected completion date | G | Project is on budget | [5 empty] | 2021-10-05 |  | 2021-10-26 |  | G | 2021-10-27 |  | 2022-08-30 |  | G | [5 empty] | 2023-04-05 |  | 2023-05-02 |  | G | 2023-12-22 |  | 2024-01-31 |  | G | 2024-06-28 |  | 2024-10-29 |  | G | 2024-02-15 |  | 2024-07-15 |  | G | 2024-03-20 |  | 2024-08-15 |  | G | [5 empty] | 2024-11-12 |  | 2024-11-12 |  | G | 2025-02-06 |  | 2025-02-06 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.061809
2560 | 118100 | #81 CIP DETOUR IMPROVEMENTS - EXITS 220, 225, 227 AND 235 | 9999 | Primary | Other | VDOT | Augusta County | HARRISONBURG | Staunton | NonMPO:NonMPO | Infrastructure Investment Division | Keith M Rider | Keith.Rider@VDOT.Virginia.gov | (434) 856-8145 | Matthew Bond | Matthew.Bond@vdot.virginia.gov | (540) 332-9275 |  |  |  | 0 |  | 0 | FY2024 | 3925000 | 3925000 | NO DATES SET YET | R | Start Development milestone is 135 days past the expected completion date | G | Project is on budget | [5 empty] | 2020-09-21 |  | 2020-10-09 |  | R | 2020-10-12 |  | 2021-08-16 |  | G | [5 empty] | 2022-03-22 |  | 2022-04-18 |  | G | [5 empty] | 2022-12-09 |  | 2023-04-13 |  | G | [5 empty] | 2022-09-08 |  | 2023-02-13 |  | G | [5 empty] | 2023-05-09 |  | 2023-05-09 |  | G | 2023-07-28 |  | 2023-07-28 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.08569
2561 | 118304 | JERMANTOWN / RTE.29 SIGNAL UPGRADE - FY21 RVSH | 0029 | Urban | Traffic Management/Engineering | Locally | Fairfax | FAIRFAX | Northern Virginia | Northern Virginia:Fairfax | Local Assistance Division | Andrew G Beacher | Andrew.Beacher@vdot.virginia.gov | (703) 259-2239 | Amir Salahshoor | A.Salahshoor@VDOT.Virginia.gov | (703) 259-1957 | Wendy Sanford | wendy.sanford@fairfaxva.gov | (703) 385-7889 | 0 |  | 0 | FY2029 | 1417000 | 1417000 | NO DATES SET YET | G | Agreement with Locality milestone is 1433 days ahead of the expected completion date | G | Project is on budget | 2024-07-01 |  | 2025-01-24 |  | G | 2025-01-27 |  | 2025-02-14 |  | G | 2025-08-21 |  | 2025-12-17 |  | G | [10 empty] | 2027-04-12 |  | 2027-05-14 |  | G | [5 empty] | 2027-05-17 |  | 2027-10-13 |  | G | 2027-12-08 |  | 2028-05-09 |  | G | [5 empty] | 2028-01-25 |  | 2028-03-21 |  | G | 2028-06-08 |  | 2028-08-03 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.25315
2562 | 118597 | W Broad St Intersection Improvements at Dominion and Cox | 0250 | Primary | Safety | VDOT | Henrico County | ASHLAND | Richmond | Richmond:Henrico County | Infrastructure Investment Division | Raymond Chapman | Scott.Chapman@vdot.virginia.gov | (804) 609-5277 | Raymond Chapman | Scott.Chapman@vdot.virginia.gov | (804) 609-5277 |  |  |  | 0 |  | 0 | FY2026 | 13952000 | 13952000 | NO DATES SET YET | G | Start Development milestone is 590 days ahead of the expected completion date | G | Project is on budget | [5 empty] | 2022-09-14 |  | 2022-10-04 |  | G | 2022-10-05 |  | 2023-08-09 |  | G | [5 empty] | 2024-03-14 |  | 2024-04-10 |  | G | 2024-12-02 |  | 2025-01-07 |  | G | 2025-06-09 |  | 2025-10-07 |  | G | 2025-01-24 |  | 2025-06-23 |  | G | 2025-02-21 |  | 2025-07-21 |  | G | [5 empty] | 2025-10-14 |  | 2025-10-14 |  | G | 2026-01-08 |  | 2026-01-08 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.083043
2563 | 91248 | CONSTRUCTION OF SIDEWALKS AND CROSSWALKS | 0719 | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Round Hill | LEESBURG | Northern Virginia | Northern Virginia:Loudoun County | Local Assistance Division | Amir Salahshoor | A.Salahshoor@VDOT.Virginia.gov | (703) 259-1957 | Veljibhai M Desai | Veljibhai.Desai@vdot.virginia.gov | (703) 259-2927 | Edward del Rio | edward.delrio@loudoun.gov | (571) 258-3990 | 0 |  | 0 | FY2020 | 612500 | 2187955 | CONSTRUCTION STARTED | R | Start Delivery milestone finished 340 days late | R | Project estimate is less than $5M and is 20% or more over budget | [5 empty] | 2009-01-01 | 2009-06-23 | 2009-01-01 | 2009-06-23 | R | 2013-08-02 | 2013-08-02 | 2013-12-02 | 2015-01-02 | R | [10 empty] | 2015-07-31 | 2015-07-31 | 2015-09-18 | 2015-09-04 | G | [20 empty] | 2019-02-01 | 2019-09-05 | 2019-04-01 | 2019-09-05 | R | 2019-04-01 | 2019-11-05 | 2019-07-01 | 2020-06-05 | R | Design plans are being revised | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.49223
2564 | 104184 | #SGR18VB - RT 715 OVER NSRR (STR 2843) - BR REPLACEMENT | 0715 | Secondary | Bridge Replacement w/o Added Capacity | VDOT | Bedford County | BEDFORD | Salem | NonMPO:NonMPO | Infrastructure Investment/Asset Management Division | Anthony T Marshall | Todd.Marshall@VDOT.Virginia.gov | (540) 387-5460 | Matthew S Prosser | Matt.Prosser@vdot.virginia.gov | (540) 387-5330 |  |  |  | 0 |  | 1 | FY2023 | 3923766 | 3923766 | ACTIVITY DATES SET | R | Start Purchasing Right-of-Way milestone finished 237 days late | G | Project is on budget | [5 empty] | 2013-06-21 | 2013-06-21 | 2013-06-21 | 2013-06-21 | G | 2017-08-14 | 2017-08-14 | 2018-06-06 | 2018-06-04 | G | [5 empty] | 2018-10-25 | 2018-10-25 | 2018-11-26 | 2018-11-26 | G | 2019-12-05 | 2020-05-15 | 2019-12-18 | 2020-08-11 | R | 2020-09-22 | 2019-10-03 | 2021-04-01 |  | G | 2020-01-03 | 2020-10-06 | 2021-04-01 |  | Y | 2019-05-03 | 2018-07-24 | 2021-04-01 | 2018-07-24 | G | [5 empty] | 2021-03-10 |  | 2021-04-02 |  | Y | 2021-07-08 |  | 2022-10-05 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.088545
2565 | 104902 | #SGR21VB - BR Repl-Glade Road over Reed Creek (Fed 19734) | 0664 | Secondary | Bridge Replacement w/o Added Capacity | VDOT | Wythe County | WYTHEVILLE | Bristol | NonMPO:NonMPO | Infrastructure Investment Division | Jeffrey B Powell | Jeffrey.Powell@VDOT.Virginia.gov | (276) 696-3389 | Ronald C Flanary | Ronald.Flanary@VDOT.Virginia.gov | (276) 696-3252 |  |  |  | 0 |  | 0 | FY2021 | 1709715 | 2449699 | CONSTRUCTION STARTED | G | Start Delivery milestone finished on-time | R | Project estimate is less than $5M and is 20% or more over budget | [5 empty] | 2016-07-22 | 2016-07-08 | 2016-08-05 | 2016-08-10 | R | 2016-08-11 | 2016-08-09 | 2017-10-07 | 2017-10-07 | G | [5 empty] | 2017-12-28 | 2017-12-28 | 2018-01-04 | 2018-01-04 | G | 2018-05-01 | 2018-05-01 | 2018-05-11 | 2018-05-11 | G | [5 empty] | 2018-06-20 | 2018-06-20 | 2019-05-15 | 2019-05-15 | G | [10 empty] | 2020-10-06 | 2020-10-06 | 2020-10-06 | 2020-10-06 | G | 2020-11-16 | 2020-12-04 | 2020-12-04 | 2020-12-04 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.073367
2566 | 107194 | Berea Church Road - Reconstruction | 0654 | Secondary | Reconstruction w/o Added Capacity | Locally | Stafford County | FREDERICKSBURG | Fredericksburg | Fredericksburg:Stafford County | Local Assistance Division | Curtis B Holloway | Curtis.Holloway@vdot.virginia.gov | (540) 374-3367 | Curtis B Holloway | Curtis.Holloway@vdot.virginia.gov | (540) 374-3367 | Alex Owsiak | AOwsiak@staffordcountyva.gov | (540) 658-4593 | 0 |  | 0 | FY2022 | 5806355 | 6057208 | ACTIVITY DATES SET | Y | Solicit Bids milestone is 47 days ahead of the expected completion date and there is a risk of missing this milestone date | Y | Project estimate is between $5M and $10M and is up to $1M over budget | 2016-07-20 | 2016-07-20 | 2016-07-20 | 2016-07-20 | G | 2016-08-09 | 2016-08-09 | 2016-08-22 | 2016-08-22 | G | 2017-06-14 | 2017-06-14 | 2018-08-24 | 2018-08-13 | G | [10 empty] | 2019-03-21 | 2019-03-21 | 2019-04-03 | 2019-04-03 | G | [20 empty] | 2020-12-14 |  | 2021-04-09 |  | Y | 2021-04-12 |  | 2021-08-03 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.15017
2567 | 108867 | FY17 RS - Sidewalk, C&G and Storm Drain Improvements | 0000 | Urban | Facilities for Pedestrians and Bicycles | Locally | Christiansburg | CHRISTIANSBURG | Salem | New River Valley:Christiansburg | Local Assistance Division | Adam J Czesnowski | Adam.Czesnowski@vdot.virginia.gov | (540) 541-1216 | Adam J Czesnowski | Adam.Czesnowski@vdot.virginia.gov | (540) 541-1216 | Wayne Nelson | wnelson@christiansburg.org | (540) 382-6120 | 0 |  | 0 | FY2019 | 255300 | 255300 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 15 days early | G | Project is on budget | 2016-07-01 | 2016-07-01 | 2016-09-26 | 2016-08-29 | G | 2016-09-27 | 2016-10-05 | 2016-09-29 | 2016-10-12 | R | 2016-09-30 | 2016-08-29 | 2017-04-12 | 2017-05-05 | R | [10 empty] | 2018-03-21 | 2018-04-10 | 2018-04-10 | 2018-04-10 | G | [5 empty] | 2018-04-12 | 2018-04-10 | 2018-05-17 | 2018-04-10 | G | [10 empty] | 2018-06-05 | 2018-06-29 | 2018-07-02 | 2018-07-01 | G | 2018-07-03 | 2018-12-18 | 2019-01-02 | 2018-12-18 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.095723
2568 | 109294 | 1ST, 2ND & 3RD STREET BIKE LANES |  | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Richmond | ASHLAND | Richmond | Richmond:Richmond | Local Assistance Division | Brian J Lokker | Brian.Lokker@VDOT.Virginia.gov | (804) 524-6010 | Brian J Lokker | Brian.Lokker@VDOT.Virginia.gov | (804) 524-6010 | Jian Xu | jian.xu@richmondgov.com | (804) 646-5402 | 0 |  | 0 | FY2020 | 307000 | 354323 | AWARDED | G | Start Delivery milestone finished 35 days early | Y | Project estimate is less than $5M and is up to 20% over budget | 2017-12-12 | 2017-12-12 | 2018-04-26 | 2018-04-26 | G | 2018-05-03 | 2018-05-03 | 2018-05-08 | 2018-05-08 | G | 2018-05-09 | 2018-05-09 | 2018-11-13 | 2018-11-09 | G | [35 empty] | 2019-09-17 | 2019-11-12 | 2019-10-14 | 2019-12-13 | R | 2019-10-15 | 2020-02-13 | 2020-04-10 | 2020-03-06 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.35196
2569 | 109599 | #SGR17VB - RT 701 SUPERSTRUCTURE REPLACEMENT STR. 6059 | 0701 | Secondary | Bridge Replacement w/o Added Capacity | VDOT | Louisa County | CHARLOTTESVILLE | Culpeper | NonMPO:NonMPO | Infrastructure Investment/Asset Management Division | Braden C Chapman | Braden.Chapman@VDOT.Virginia.gov | (540) 829-7421 | Brian A Arnold | Brian.Arnold@VDOT.Virginia.gov | (540) 829-7557 |  |  |  | 0 |  | 1 | FY2025 | 2215000 | 2215000 | NO DATES SET YET-PE OPEN | G | Start Development milestone finished 1448 days early | G | Project is on budget | [5 empty] | 2021-05-25 | 2017-06-13 | 2021-06-07 | 2017-06-20 | G | 2021-06-08 |  | 2022-04-20 |  | G | [5 empty] | 2023-03-09 |  | 2023-03-22 |  | G | 2024-05-03 |  | 2024-05-16 |  | G | 2024-10-04 |  | 2025-04-03 |  | G | 2024-05-31 |  | 2024-11-28 |  | G | 2023-12-01 |  | 2024-11-14 |  | G | [5 empty] | 2025-04-08 |  | 2025-04-08 |  | G | 2025-05-28 |  | 2025-06-17 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.079734
2570 | 118288 | #SGR21VB(FED ID 12085) BRDG REPLACE RTE 17 NB DRAGON RUN | 0017 | Primary | Bridge Replacement w/o Added Capacity | VDOT | Middlesex County | SALUDA | Fredericksburg | NonMPO:NonMPO | Infrastructure Investment/Asset Management Division | Annette F Adams | Annette.Adams@VDOT.Virginia.gov | (540) 372-3583 | Annette F Adams | Annette.Adams@VDOT.Virginia.gov | (540) 372-3583 |  |  |  | 0 |  | 0 | FY2028 | 12559699 | 12559699 | NO DATES SET YET | G | Start Development milestone is 953 days ahead of the expected completion date | G | Project is on budget | [5 empty] | 2023-09-12 |  | 2023-10-02 |  | G | 2023-10-03 |  | 2024-12-17 |  | G | [5 empty] | 2026-01-15 |  | 2026-03-02 |  | G | 2027-03-23 |  | 2027-04-26 |  | G | 2027-11-15 |  | 2028-03-21 |  | G | 2027-05-18 |  | 2027-12-08 |  | G | 2027-05-10 |  | 2028-01-13 |  | G | [5 empty] | 2028-04-11 |  | 2028-04-11 |  | G | 2028-06-29 |  | 2028-06-29 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.068372
2571 | 118541 | #SGR21LB - Broad St - Bridge Replacement - FED ID 21575 |  | Urban | Bridge Replacement w/o Added Capacity | Locally | Richmond | ASHLAND | Richmond | Richmond:Richmond | Infrastructure Investment/Asset Management Division | Olena Fecek | Olena.Fecek@vdot.virginia.gov | (804) 524-6368 | Olena Fecek | Olena.Fecek@vdot.virginia.gov | (804) 524-6368 | TBD |  | TBD | 0 |  | 1 | FY2025 | 3965009 | 3965009 | NO DATES SET YET | G | Agreement with Locality milestone is 388 days ahead of the expected completion date | G | Project is on budget | 2021-11-01 |  | 2022-03-16 |  | G | 2022-03-17 |  | 2022-04-06 |  | G | 2022-05-05 |  | 2022-08-26 |  | G | [25 empty] | 2023-08-23 |  | 2024-01-29 |  | G | [5 empty] | 2024-03-27 |  | 2024-04-23 |  | G | 2024-07-12 |  | 2024-07-12 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.080002
2572 | 5542 | #SMART18 #SGR18VB - RT 622 - RECONSTRUCTION | 0622 | Secondary | Reconstruction w/o Added Capacity | VDOT | Campbell County | APPOMATTOX | Lynchburg | Lynchburg:Campbell County | Infrastructure Investment Division | Don Austin |  |  | Lindsey S Hodges | Lindsey.Hodges@vdot.virginia.gov | (434) 856-8143 |  |  |  | 1 | 2018 | 1 | FY2020 | 11029052 | 11029052 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 92 days early | G | Project is on budget | [5 empty] | 2005-07-18 | 2005-07-18 | 2005-08-31 | 2005-08-27 | G | 2005-10-03 | 2005-10-03 | 2006-03-31 | 2006-03-08 | G | [5 empty] | 2012-02-10 | 2012-02-10 | 2012-04-05 | 2012-04-05 | G | 2017-06-30 | 2017-06-30 | 2017-07-13 | 2017-07-13 | G | 2018-12-06 | 2018-12-06 | 2019-05-31 | 2019-03-15 | G | 2017-07-24 | 2017-07-24 | 2018-11-05 | 2018-11-05 | G | 2018-02-16 | 2018-02-16 | 2019-02-05 | 2019-01-22 | G | [5 empty] | 2019-06-07 | 2019-07-09 | 2019-07-16 | 2019-07-09 | G | 2019-10-24 | 2019-08-21 | 2019-12-19 | 2019-09-18 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.12337
2573 | 101020 | #HB2.FY17 RTE 10 (BERMUDA TRIANGLE RD TO MEADOWVILLE RD) | 0010 | Primary | Reconstruction w/ Added Capacity | Locally | Chesterfield County | CHESTERFIELD | Richmond | Richmond:Chesterfield County | Infrastructure Investment Division | Brian J Lokker | Brian.Lokker@VDOT.Virginia.gov | (804) 524-6010 | Brian J Lokker | Brian.Lokker@VDOT.Virginia.gov | (804) 524-6010 | Stan Newcomb | newcombs@chesterfield.gov | (804) 748-1037 | 1 | 2017 | 0 | FY2019 | 50500000 | 59231167 | CONSTRUCTION STARTED | R | Start Delivery milestone finished 56 days late | R | Project estimate is greater than $10M and is over budget by (a) 10% or more or (b) $5M or more | 2011-12-21 | 2011-12-21 | 2012-03-01 | 2012-02-08 | G | 2011-07-01 | 2012-02-29 | 2011-07-01 | 2012-02-29 | R | 2011-07-31 | 2012-04-09 | 2012-12-31 | 2012-04-20 | G | [5 empty] | 2014-05-12 | 2014-05-12 | 2014-08-26 | 2014-06-26 | G | 2014-07-25 | 2014-07-25 | 2014-11-06 | 2014-11-06 | G | [5 empty] | 2015-06-29 | 2015-06-29 | 2017-05-15 | 2017-05-15 | G | 2018-11-13 | 2018-03-20 | 2018-12-03 | 2018-11-30 | G | [5 empty] | 2018-12-31 | 2019-03-22 | 2018-12-31 | 2019-04-01 | R | 2019-04-01 | 2019-06-14 | 2019-05-31 | 2019-07-26 | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.1891
2574 | 104255 | ROCKY KNOB HERITAGE CENTER - Vistor Center Amenities | 0000 | Enhancement | Historic Preservation | Locally | Patrick County | MARTINSVILLE | Salem | NonMPO:NonMPO | Local Assistance Division | Erica L Jeter | Erica.Jeter@VDOT.Virginia.gov | (804) 609-5215 | Cheryl B Becker | Cheryl.Becker@vdot.virginia.gov | (540) 492-2531 | Kevin Byrd |  |  | 0 |  | 0 | FY2019 | 217125 | 84646 | ACTIVITY DATES SET | R | Solicit Bids milestone is 936 days past the expected completion date | Y | Estimate not current | [10 empty] | 2016-03-16 | 2016-03-16 | 2016-08-16 | 2016-08-16 | G | [35 empty] | 2018-07-02 |  | 2018-07-31 |  | R | 2018-08-01 |  | 2018-11-07 |  | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.27105
2575 | 105145 | Bridge Repl-Gen Spr Rd over Wolf Creek (Fed ID 19089) | 0670 | Secondary | Bridge Replacement w/o Added Capacity | VDOT | Washington County | ABINGDON | Bristol | NonMPO:NonMPO | Infrastructure Investment Division | Gary Lester |  |  | Anthony L Briggs | Anthony.Briggs@VDOT.Virginia.gov | (276) 696-3250 |  |  |  | 0 |  | 0 | FY2019 | 2380000 | 2380000 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 85 days early | G | Project is on budget | [5 empty] | 2014-07-01 | 2014-06-23 | 2014-07-01 | 2014-07-16 | R | 2014-09-08 | 2014-01-21 | 2015-05-01 | 2015-05-01 | G | [5 empty] | 2016-02-08 | 2016-02-08 | 2016-03-03 | 2016-03-03 | G | 2016-10-24 | 2016-10-24 | 2016-10-28 | 2016-10-28 | G | 2017-07-25 | 2017-07-25 | 2017-12-06 | 2017-12-06 | G | 2016-12-08 | 2016-12-08 | 2017-06-20 | 2017-06-20 | G | 2017-05-18 | 2017-05-18 | 2018-01-08 | 2018-01-08 | G | [5 empty] | 2018-07-05 | 2018-08-14 | 2018-08-14 | 2018-08-14 | G | 2018-11-15 | 2018-10-22 | 2019-01-15 | 2018-10-22 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.064626
2576 | 107519 | Dick and Willie Passage, Phase 6A |  | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Henry County | MARTINSVILLE | Salem | NonMPO:NonMPO | Local Assistance Division | Jessie Nester | Jessie.Nester@vdot.virginia.gov | (540) 613-4115 | Jessie Nester | Jessie.Nester@vdot.virginia.gov | (540) 613-4115 | Tim Pace | tpace@co.henry.va.us | (276) 634-2559 | 0 |  | 0 | FY2021 | 1618218 | 1618218 | ACTIVITY DATES SET | R | Solicit Bids milestone is 254 days past the expected completion date | G | Project is on budget | 2015-08-17 | 2015-08-17 | 2015-11-04 | 2015-11-04 | G | 2016-09-22 | 2016-09-22 | 2016-09-22 | 2016-09-22 | G | 2017-06-17 | 2017-06-17 | 2018-06-07 | 2019-06-10 | R | [10 empty] | 2019-12-04 | 2019-12-04 | 2020-01-22 | 2020-01-21 | G | [20 empty] | 2020-04-17 |  | 2020-06-12 |  | R | 2020-06-15 |  | 2020-10-21 |  | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.33519
2577 | 108896 | #HB2.FY17 Colonial Avenue Improvements | 8001 | Urban | Facilities for Pedestrians and Bicycles | Locally | Roanoke | SALEM | Salem | Roanoke:Roanoke City | Infrastructure Investment Division | Cheryl B Becker | Cheryl.Becker@vdot.virginia.gov | (540) 492-2531 | Cheryl B Becker | Cheryl.Becker@vdot.virginia.gov | (540) 492-2531 | Luke Pugh | luke.pugh@roanokeva.gov | (540) 853-5471 | 1 | 2017 | 0 | FY2018 | 7000000 | 7000000 | CONSTRUCTION STARTED | R | Start Delivery milestone finished 50 days late | G | Project is on budget | 2016-07-01 | 2016-07-01 | 2016-09-07 | 2016-09-07 | G | 2016-07-21 | 2016-07-21 | 2016-09-20 | 2016-09-20 | G | 2016-08-01 | 2016-08-01 | 2016-12-16 | 2016-12-16 | G | [35 empty] | 2017-09-25 | 2017-10-20 | 2017-10-23 | 2017-11-12 | R | 2017-10-24 | 2017-11-12 | 2017-12-06 | 2018-01-25 | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.35111
2578 | 109573 | ROUTE 522 ROAD DIET AND BIKE PEDESTRIAN IMPROVEMENTS | 0000 | Primary | Safety | Locally | Culpeper | WARRENTON | Culpeper | NonMPO:NonMPO | Infrastructure Investment Division | Ken Connors |  |  | John P Price | John.Price@VDOT.Virginia.gov | (540) 347-6371 | Jim Hoy | jhoy@Culpeperva.gov | (540) 829-8262 | 0 |  | 0 | FY2020 | 1600000 | 2570815 | AWARDED | R | Start Delivery milestone finished 305 days late | R | Project estimate is less than $5M and is 20% or more over budget | 2016-07-11 | 2016-07-11 | 2016-09-16 | 2016-09-16 | G | 2016-09-19 | 2016-09-19 | 2016-09-19 | 2016-09-19 | G | 2016-09-27 | 2016-09-27 | 2018-11-01 | 2019-04-15 | R | [10 empty] | 2019-07-11 | 2019-07-18 | 2019-07-31 | 2020-01-29 | R | [5 empty] | 2019-08-02 | 2020-01-30 | 2019-11-26 | 2020-06-11 | R | [10 empty] | 2019-12-16 | 2020-06-12 | 2020-01-30 | 2020-10-30 | R | 2020-01-31 | 2020-12-18 | 2020-04-10 | 2021-02-09 | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.10752
2579 | 109704 | #HB2.FY17 RTE 60 - LEFT & RIGHT TURN LANES AT RTE 56 | 6060 | Primary | Safety | VDOT | Buckingham County | DILLWYN | Lynchburg | NonMPO:NonMPO | Infrastructure Investment Division | Daniel J Brown | Daniel.Brown@VDOT.Virginia.gov | (434) 856-8265 | Gregory K Parsons | Gregory.Parsons@vdot.virginia.gov | (434) 856-8297 |  |  |  | 1 | 2017 | 0 | FY2021 | 2967687 | 2963042 | AWARDED | G | Start Delivery milestone finished 14 days early | G | Project is on budget | [5 empty] | 2016-08-08 | 2016-08-08 | 2016-08-10 | 2016-08-10 | G | 2016-08-15 | 2016-08-15 | 2017-01-10 | 2017-07-24 | R | [5 empty] | 2018-06-15 | 2018-06-15 | 2018-06-28 | 2018-06-15 | G | 2019-08-13 | 2019-06-27 | 2019-08-26 | 2019-07-02 | G | 2020-03-25 | 2020-04-22 | 2020-09-11 | 2020-09-10 | G | 2019-09-12 | 2019-08-14 | 2020-03-24 | 2020-03-05 | G | [10 empty] | 2020-10-13 | 2020-10-06 | 2020-10-13 | 2020-10-06 | G | 2020-12-08 | 2020-11-18 | 2020-12-29 | 2020-12-15 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.09596
2580 | 110878 | West Jackson Street Sidewalk Improvements | 0023 | Primary | Safety | Locally | Gate City | WISE | Bristol | Kingsport:Scott County | Infrastructure Investment Division | Chase R Buchanan | Chase.Buchanan@VDOT.Virginia.gov | (276) 696-3251 | Kenneth R Plummer | KR.Plummer@VDOT.Virginia.gov | (276) 696-3261 | Greg Jones | townmanager@mygatecity.com | (276) 386-3831 | 0 |  | 0 | FY2020 | 84817 | 203773 | ADVERTISED | R | Start Delivery milestone is 542 days past the expected completion date | R | Project estimate is less than $5M and is 20% or more over budget | 2017-09-15 | 2017-09-15 | 2017-12-13 | 2017-12-13 | G | 2017-12-14 | 2017-12-14 | 2017-12-18 | 2017-12-18 | G | 2017-12-19 | 2017-12-19 | 2018-06-26 | 2018-06-19 | G | [35 empty] | 2019-06-21 | 2020-10-11 | 2019-07-19 | 2020-11-12 | R | 2019-07-22 |  | 2019-08-29 |  | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.080984
2581 | 111393 | Rugby Avenue Shared Use Path |  | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Charlottesville | CHARLOTTESVILLE | Culpeper | Charlottesville:Charlottesville | Local Assistance Division | Kimberly Cameron | Kim.Cameron@vdot.virginia.gov | (540) 332-7886 | Michael D Barnes | MichaelD.Barnes@vdot.virginia.gov | (434) 422-9861 | Chris Gensic | gensic@charlottesville.gov | (434) 989-0061 | 0 |  | 0 | FY2020 | 419500 | 517501 | ACTIVITY DATES SET | R | Solicit Bids milestone is 627 days past the expected completion date | Y | Project estimate is less than $5M and is up to 20% over budget | 2017-10-02 | 2017-10-02 | 2017-12-29 | 2017-12-29 | G | 2018-01-02 | 2018-01-04 | 2018-01-04 | 2018-01-04 | G | 2018-01-05 | 2018-01-10 | 2018-07-12 | 2018-06-26 | G | [35 empty] | 2019-05-08 |  | 2019-06-05 |  | R | 2019-06-06 |  | 2019-07-17 |  | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.37491
2582 | 111733 | #SMART18 - ROUTE 20/649 INTERSECTION IMPROVEMENT | 0020 | Primary | Safety | VDOT | Albemarle County | CHARLOTTESVILLE | Culpeper | Charlottesville:Albemarle County | Infrastructure Investment Division | Gregory J Cooley | Gregory.Cooley@vdot.virginia.gov | (434) 906-7979 | William E Stowe | William.Stowe@vdot.virginia.gov | (540) 827-7287 |  |  |  | 1 | 2018 | 0 | FY2019 | 4000000 | 4207346 | CONSTRUCTION STARTED | R | Start Delivery milestone finished 34 days late | Y | Project estimate is less than $5M and is up to 20% over budget | [5 empty] | 2017-08-01 | 2017-10-12 | 2017-08-14 | 2017-10-26 | R | 2017-08-15 | 2017-10-27 | 2018-07-13 | 2017-10-27 | G | [10 empty] | 2018-11-01 | 2018-11-01 | 2018-11-14 | 2018-11-14 | G | [20 empty] | 2018-10-30 | 2018-10-30 | 2018-11-27 | 2018-11-27 | G | 2019-05-28 | 2019-06-26 | 2019-06-19 | 2019-07-23 | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | DESIGN BUILD/PPTA | 1 | 1 | 0.36422
2583 | 112182 | RESURFACE NON-HARDSURFACED ROAD-ROUTE 727 | 0727 | Secondary | Resurfacing | VDOT | Floyd County | CHRISTIANSBURG | Salem | NonMPO:NonMPO | Infrastructure Investment Division | David D Clarke | David.Clarke@VDOT.Virginia.gov | (540) 381-7190 | Marvin D Mann | M.Mann@VDOT.Virginia.gov | (540) 378-5055 | CHRISTOPHER PRICE |  |  | 0 |  | 0 | FY2020 | 925000 | 925000 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 125 days early | G | Project is on budget | [5 empty] | 2018-01-03 | 2017-09-12 | 2018-01-18 | 2017-10-10 | G | 2018-01-19 | 2017-10-18 | 2018-12-13 | 2018-06-18 | G | [5 empty] | 2018-06-18 | 2018-06-18 | 2018-06-18 | 2018-06-18 | G | 2018-07-10 | 2018-06-27 | 2018-07-10 | 2018-07-09 | G | 2018-05-14 | 2018-05-14 | 2018-05-14 | 2018-05-14 | G | 2018-07-11 | 2018-07-09 | 2018-10-03 | 2018-12-21 | R | 2018-06-19 | 2018-06-18 | 2018-10-03 | 2018-06-18 | G | [5 empty] | 2019-04-09 | 2019-03-26 | 2019-04-09 | 2019-03-26 | G | 2019-05-23 | 2019-05-28 | 2019-09-30 | 2019-05-28 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | SAAP CONTRACT | 1 | 0 | 0.07243
2584 | 112887 | DISTRICTWIDE CENTERLINE RUMBLE STRIP INSTALLATION | 9999 | Primary | Safety | VDOT | Lynchburg District-wide |  | Lynchburg | Lynchburg:Lynchburg District-wide | Infrastructure Investment Division | Lindsey S Hodges | Lindsey.Hodges@vdot.virginia.gov | (434) 856-8143 | Justin K Hsieh | Justin.Hsieh@vdot.virginia.gov | (804) 489-0208 |  |  |  | 0 |  | 0 | FY2020 | 941479 | 940842 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 173 days early | G | Project is on budget | [10 empty] | 2018-04-02 | 2018-04-02 | 2018-04-06 | 2018-04-20 | R | [35 empty] | 2018-12-11 | 2018-12-04 | 2018-12-11 | 2018-12-04 | G | 2019-02-19 | 2019-02-22 | 2019-08-14 | 2019-02-22 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.11567
2585 | 113124 | NORTHFAX WEST - ROADWAY NETWORK | 9999 | Urban | New Construction Roadway | Locally | Fairfax | FAIRFAX | Northern Virginia | Northern Virginia:Fairfax | Local Assistance Division | Andrew G Beacher | Andrew.Beacher@vdot.virginia.gov | (703) 259-2239 | Christer P Carshult | Christer.Carshult@vdot.virginia.gov | (703) 259-1765 | Wendy Block Sanford |  |  | 0 |  | 0 | FY2027 | 9600000 | 9600000 | NO DATES SET YET-PE OPEN | G | Start Development milestone finished on-time | G | Project is on budget | 2018-07-01 | 2018-07-01 | 2018-08-13 | 2018-08-13 | G | 2019-02-05 | 2019-02-05 | 2019-03-05 | 2019-03-05 | G | 2020-01-23 | 2020-01-23 | 2021-08-31 |  | G | [10 empty] | 2022-09-01 |  | 2022-10-31 |  | G | [5 empty] | 2022-11-01 |  | 2025-10-28 |  | G | 2025-07-15 |  | 2026-04-28 |  | G | [5 empty] | 2026-01-02 |  | 2026-06-30 |  | G | 2026-07-01 |  | 2026-11-30 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.26715
2586 | 113260 | Bethlehem Rd. Improvements | 9999 | Secondary | Reconstruction w/o Added Capacity | Locally | Henrico County | ASHLAND | Richmond | Richmond:Henrico County | Local Assistance Division | Douglas L Orcutt | Doug.Orcutt@vdot.virginia.gov | (804) 609-5428 | Douglas L Orcutt | Doug.Orcutt@vdot.virginia.gov | (804) 609-5428 | Conner Barnes | bar136@henrico.us | (804) 501-4224 | 0 |  | 0 | FY2024 | 5424000 | 5424000 | ACTIVITY DATES SET | R | Determine Requirements milestone finished 668 days late | G | Project is on budget | 2018-07-02 | 2018-07-02 | 2018-10-31 | 2018-09-27 | G | 2018-11-01 | 2018-10-15 | 2018-11-15 | 2018-10-16 | G | 2018-11-16 | 2018-10-17 | 2019-03-19 | 2021-01-15 | R | 2021-05-11 |  | 2021-07-12 |  | G | [5 empty] | 2021-07-27 |  | 2021-08-10 |  | G | 2023-04-11 |  | 2023-06-09 |  | G | 2021-09-07 |  | 2023-04-10 |  | G | 2022-09-29 |  | 2023-05-09 |  | G | [5 empty] | 2023-08-18 |  | 2023-09-15 |  | G | 2023-09-18 |  | 2024-05-10 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.35317
2587 | 113856 | Primary Extension Paving - Victoria Blvd (westbound) | 0143 | Urban | Resurfacing | Locally | Hampton | WILLIAMSBURG | Hampton Roads | Hampton Roads:Hampton | Local Assistance Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Derrick Williams | Derrick.Williams@vdot.virginia.gov | (757) 956-3097 | Sandon Rogers, L. S. P. E. | Sandon.rogers@hampton.gov | (757) 727-6786 | 0 |  | 1 | FY2019 | 325000 | 325000 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished on-time | G | Project is on budget | 2018-10-03 | 2018-10-03 | 2019-01-02 | 2019-01-17 | R | 2019-01-03 | 2019-01-15 | 2019-01-07 | 2019-01-17 | R | 2019-01-08 | 2018-07-11 | 2019-07-15 | 2019-01-17 | G | [25 empty] | 2018-05-14 | 2019-01-16 | 2019-01-17 | 2019-01-16 | G | [5 empty] | 2018-12-19 | 2018-12-19 | 2019-01-17 | 2019-01-17 | G | 2019-01-17 | 2019-01-17 | 2019-01-17 | 2019-01-17 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.089898
2588 | 115307 | Primary Extension - Blacksburg - Prices Fork Rd | 0412 | Urban | Reconstruction w/o Added Capacity | Locally | Blacksburg | CHRISTIANSBURG | Salem | New River Valley:Blacksburg | Local Assistance Division | Adam J Czesnowski | Adam.Czesnowski@vdot.virginia.gov | (540) 541-1216 | Adam J Czesnowski | Adam.Czesnowski@vdot.virginia.gov | (540) 541-1216 | John Boyer | jboyer@blacksburg.gov | (540) 443-1204 | 0 |  | 0 | FY2020 | 289725 | 289725 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 193 days early | G | Project is on budget | 2020-01-02 | 2019-07-01 | 2020-03-30 | 2019-07-25 | G | 2020-03-31 | 2019-09-03 | 2020-04-02 | 2019-09-05 | G | 2020-04-03 | 2019-09-18 | 2020-10-06 | 2019-09-19 | G | [35 empty] | 2019-12-31 | 2019-11-22 | 2019-12-31 | 2019-11-22 | G | 2020-01-27 | 2019-11-25 | 2020-06-30 | 2019-12-20 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.15912
2589 | 115952 | Town of Cape Charles- Multi-Use Trails, Phase III | 0000 | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Cape Charles | ACCOMAC | Hampton Roads | NonMPO:NonMPO | Local Assistance Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Keisha Wilkins | Keisha.Wilkins@vdot.virginia.gov | (757) 956-3110 | Bob Panek | bob.panek@capecharles.org | (757) 331-3259 | 0 |  | 0 | FY2020 | 879354 | 841907 | ADVERTISED | R | Start Delivery milestone is 241 days past the expected completion date | Y | Estimate not current | 2019-07-02 | 2019-07-02 | 2019-09-25 | 2019-09-19 | G | [5 empty] | 2019-07-02 | 2019-07-02 | 2019-07-16 | 2019-07-12 | G | [35 empty] | 2019-10-07 | 2019-09-23 | 2019-11-19 | 2019-10-23 | G | 2020-02-13 |  | 2020-06-25 |  | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.39635
2590 | 111297 | #SGR18VB - BRIDGE REHAB RT 657 OVER I-95 | 0657 | Secondary | Bridge Rehab w/o Added Capacity | VDOT | Hanover County | ASHLAND | Richmond | Richmond:Hanover County | Infrastructure Investment/Asset Management Division | Clayton M Thomas | Clay.Thomas@VDOT.Virginia.gov | (804) 609-5429 | Clayton M Thomas | Clay.Thomas@VDOT.Virginia.gov | (804) 609-5429 |  |  |  | 0 |  | 1 | FY2022 | 5000000 | 6000000 | ACTIVITY DATES SET | R | Engage Public milestone is 359 days past the expected completion date | R | Project estimate is between $5M and $10M and is a $1M or more over budget | [5 empty] | 2017-08-14 | 2017-08-14 | 2017-08-21 | 2017-08-21 | G | 2017-08-22 | 2017-08-22 | 2019-02-22 | 2019-06-12 | R | [5 empty] | 2020-02-14 | 2020-02-06 | 2020-02-28 |  | R | 2020-12-08 |  | 2020-12-21 |  | R | 2021-05-18 |  | 2021-11-22 |  | G | 2021-01-07 | 2021-01-07 | 2021-07-14 | 2021-02-05 | G | 2020-12-01 | 2020-07-01 | 2021-08-04 | 2020-07-01 | G | [5 empty] | 2021-12-14 |  | 2021-12-14 |  | G | 2022-02-08 |  | 2022-06-14 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.14614
2591 | 111456 | RTE. 2092 - SECONDARY ACCESS NORTH OF ROUTE 606 | 2092 | Secondary | Reconstruction w/ Added Capacity | VDOT | Spotsylvania County | FREDERICKSBURG | Fredericksburg | Fredericksburg:Spotsylvania County | Infrastructure Investment Division | Khalil Minhas | Khalil.Minhas@vdot.virginia.gov | (540) 374-3369 | Khalil Minhas | Khalil.Minhas@vdot.virginia.gov | (540) 374-3369 | Paul Agnello | pagnello@spotsylvania.va.us | (540) 507-7398 | 0 |  | 0 | FY2021 | 7820000 | 7735896 | ACTIVITY DATES SET | R | Complete Purchasing Right-of-Way milestone is 270 days past the expected completion date | G | Project is on budget | [5 empty] | 2017-09-01 | 2017-09-18 | 2017-09-15 | 2017-09-20 | R | 2017-09-18 | 2017-12-27 | 2018-08-15 | 2018-01-22 | G | [5 empty] | 2018-07-02 | 2018-06-14 | 2018-07-16 | 2018-07-13 | G | 2018-10-23 | 2018-10-23 | 2018-11-05 | 2018-11-05 | G | 2019-06-04 |  | 2020-09-04 |  | R | 2018-11-26 | 2018-11-28 | 2020-05-27 |  | R | 2018-03-14 | 2018-03-14 | 2019-09-06 | 2018-10-26 | G | [5 empty] | 2020-09-08 |  | 2020-09-08 |  | R | 2020-10-21 |  | 2020-12-22 |  | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.10188
2592 | 111787 | #SMART18 - Route 17 Widening between Rte 630 and Rte 173 | 0017 | Primary | Reconstruction w/ Added Capacity | VDOT | York County | WILLIAMSBURG | Hampton Roads | Hampton Roads:York County | Infrastructure Investment Division | Peter G Reilly | Peter.Reilly@vdot.virginia.gov | (757) 858-6748 | Andrew B Scott | Andrew.Scott@VDOT.Virginia.gov | (757) 956-3273 | Timothy Cross | tcross@yorkcounty.gov | (757) 890-3496 | 1 | 2018 | 0 | FY2026 | 17542603 | 24290479 | NO DATES SET YET-PE OPEN | G | Start Development milestone finished 704 days early | R | Project estimate is greater than $10M and is over budget by (a) 10% or more or (b) $5M or more | [5 empty] | 2020-08-03 | 2018-08-01 | 2020-08-14 | 2018-09-10 | G | 2020-08-17 |  | 2021-04-02 |  | G | [5 empty] | 2022-01-20 |  | 2022-02-02 |  | G | 2023-01-19 |  | 2023-02-01 |  | G | 2023-05-09 |  | 2025-07-08 |  | G | 2023-02-17 |  | 2024-04-02 |  | G | 2022-02-04 | 2018-11-28 | 2022-10-05 |  | G | [5 empty] | 2025-08-12 |  | 2025-08-12 |  | G | 2025-10-27 |  | 2025-12-24 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.18822
2593 | 112480 | LEESBURG PIKE & GEORGE MARSHALL DR SIGNAL IMPROVEMENTS | 0007 | Primary | Safety | VDOT | Fairfax County | FAIRFAX | Northern Virginia | Northern Virginia:Fairfax County | Infrastructure Investment Division | Ivan M Horodyskyj | Ivan.Horodyskyj@VDOT.Virginia.gov | (703) 259-2330 | Jessica Paris | Jessica.Paris@vdot.virginia.gov | (703) 259-2409 |  |  |  | 0 |  | 0 | FY2020 | 527089 | 527089 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 147 days early | G | Project is on budget | [5 empty] | 2018-10-01 | 2018-07-16 | 2018-10-12 | 2018-07-16 | G | 2018-10-16 | 2018-09-28 | 2019-09-12 | 2019-03-29 | G | [5 empty] | 2018-09-28 | 2018-09-28 | 2018-10-26 | 2018-10-26 | G | 2019-04-24 | 2019-04-01 | 2019-05-06 | 2019-04-01 | G | 2019-03-12 | 2019-04-01 | 2019-04-22 | 2019-04-01 | G | 2019-05-07 | 2019-04-01 | 2019-05-07 | 2019-04-01 | G | [10 empty] | 2019-07-09 | 2019-04-09 | 2019-08-13 | 2019-04-26 | G | 2019-09-19 | 2019-05-01 | 2019-09-25 | 2019-05-01 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | WORK/TASK ORDER | 1 | 0 | 0.051478
2594 | 112967 | #SGR19LP - Resurface New Hope Rd(RT 254) - Primary Extension | 0254 | Urban | Resurfacing | Locally | Staunton | HARRISONBURG | Staunton | SAW:Staunton | Local Assistance Division | Donald F Komara | Donald.Komara@VDOT.Virginia.gov | (540) 434-2587 | Michael S Fulcher | Michael.Fulcher@VDOT.Virginia.gov | (540) 332-2243 | Steve Yancey | yanceysc@ci.staunton.va.us | (540) 332-3892 | 0 |  | 1 | FY2020 | 60000 | 60000 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 412 days early | G | Project is on budget | 2018-12-31 | 2018-10-05 | 2019-03-28 | 2018-11-05 | G | 2019-03-29 | 2018-11-06 | 2019-04-02 | 2019-03-01 | G | 2019-04-03 | 2019-03-04 | 2019-10-04 | 2019-03-11 | G | [25 empty] | 2019-03-12 | 2019-03-10 | 2019-11-08 | 2019-03-12 | G | [5 empty] | 2020-01-21 | 2019-03-07 | 2020-02-18 | 2019-03-20 | G | 2020-05-06 | 2019-03-20 | 2020-05-06 | 2019-03-21 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.06301
2595 | 113219 | ECHOLS STREET SE RECONSTRUCTION | 0002 | Urban | Reconstruction w/o Added Capacity | Locally | Vienna | FAIRFAX | Northern Virginia | Northern Virginia:Vienna | Local Assistance Division | Andrew G Beacher | Andrew.Beacher@vdot.virginia.gov | (703) 259-2239 | Rita Hockman | Rita.Hockman@vdot.virginia.gov | (804) 824-7421 | Michael Gallagher | Michael.Gallagher@viennava.gov | (703) 255-6381 | 0 |  | 0 | FY2020 |  |  | CONSTRUCTION COMPLETED | G | Solicit Bids milestone finished 1 days early | R | Critical information missing | 2019-09-03 | 2019-02-19 | 2020-01-30 | 2019-09-19 | G | 2020-05-01 | 2019-09-20 | 2020-05-29 | 2019-11-07 | G | 2019-09-03 | 2019-11-12 | 2020-02-28 | 2019-11-12 | G | [35 empty] | 2019-11-13 | 2019-11-13 | 2019-11-14 | 2019-11-13 | G | 2020-02-10 | 2019-10-21 | 2020-02-12 | 2019-10-21 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.18488
2596 | 113289 | IRISH STREET - RECONSTRUCTION | 9999 | Urban | Reconstruction w/o Added Capacity | Locally | South Boston | HALIFAX | Lynchburg | NonMPO:NonMPO | Local Assistance Division | Sharon S White | Sharon.White@VDOT.Virginia.gov | (434) 856-8220 | Sharon S White | Sharon.White@VDOT.Virginia.gov | (434) 856-8220 | C. W. Crowder, Jr. | ccrowder@southboston.va.us | (434) 575-4261 | 0 |  | 0 | FY2021 | 713162 | 713162 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 143 days early | G | Project is on budget | 2020-01-31 | 2019-07-01 | 2020-04-24 | 2019-07-23 | G | 2020-04-27 | 2019-11-18 | 2020-04-29 | 2019-11-18 | G | 2020-04-30 | 2019-11-22 | 2020-11-03 | 2019-12-09 | G | [10 empty] | 2020-02-05 | 2020-02-05 | 2020-02-05 | 2020-02-05 | G | [5 empty] | 2020-02-07 | 2020-02-07 | 2020-02-07 | 2020-02-07 | G | [10 empty] | 2020-02-12 | 2020-02-12 | 2020-02-26 | 2020-02-26 | G | 2020-03-03 | 2020-03-03 | 2020-07-31 | 2020-03-10 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.072827
2597 | 115120 | #SMART20 ROUTE 301 AND ROUTE 3 MEDIAN U-TURN INTERSECTION | 0301 | Primary | Traffic Management/Engineering | VDOT | King George County | FREDERICKSBURG | Fredericksburg | NonMPO:NonMPO | Infrastructure Investment Division | Catherine C Coffey | Catherine.Coffey@vdot.virginia.gov | (540) 899-4280 | Khalil Minhas | Khalil.Minhas@vdot.virginia.gov | (540) 374-3369 |  |  |  | 1 | 2020 | 0 | FY2026 | 3300000 | 3300000 | NO DATES SET YET | G | Start Development milestone is 585 days ahead of the expected completion date | G | Project is on budget | [5 empty] | 2022-09-01 |  | 2022-09-29 |  | G | 2022-09-30 |  | 2023-07-21 |  | G | [5 empty] | 2024-01-10 |  | 2024-01-25 |  | G | 2025-01-06 |  | 2025-02-04 |  | G | 2025-08-25 |  | 2026-03-06 |  | G | 2025-02-21 |  | 2025-08-25 |  | G | 2024-06-20 |  | 2024-12-27 |  | G | [5 empty] | 2026-03-10 |  | 2026-03-10 |  | G | 2026-05-29 |  | 2026-05-29 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.096669
2598 | 115503 | #SMART20 Lafayette Street Signal & Pedestrian Improvements | 0005 | Urban | Safety | Locally | Williamsburg | WILLIAMSBURG | Hampton Roads | Hampton Roads:Williamsburg | Infrastructure Investment Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Chessica Villaflores | Chessica.Villaflores@vdot.virginia.gov | (757) 956-3094 | Aaron Small | asmall@williamsburgva.gov | (757) 220-6140 | 1 | 2020 | 0 | FY2026 | 91000 | 91000 | NO DATES SET YET | G | Agreement with Locality milestone is 1264 days ahead of the expected completion date | Y | Estimate not current | 2024-05-15 |  | 2024-08-08 |  | G | 2024-08-09 |  | 2024-08-13 |  | G | 2024-08-14 |  | 2025-02-25 |  | G | [25 empty] | 2025-04-02 |  | 2025-12-04 |  | G | [5 empty] | 2026-01-05 |  | 2026-02-03 |  | G | 2026-04-23 |  | 2026-04-23 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.23495
2599 | 116867 | MILLWOOD AVENUE TRAFFIC IMPROVEMENTS |  | Urban | Reconstruction w/ Added Capacity | Locally | Winchester | EDINBURG | Staunton | Winchester:Winchester | Local Assistance Division | Kimberly Cameron | Kim.Cameron@vdot.virginia.gov | (540) 332-7886 | Kimberly Cameron | Kim.Cameron@vdot.virginia.gov | (540) 332-7886 | Perry Eisenach | perry.eisenach@winchesterva.gov | (540) 667-1815 | 0 |  | 0 | FY2025 | 5000000 | 5000000 | NO DATES SET YET | G | Agreement with Locality milestone is 107 days ahead of the expected completion date | G | Project is on budget | 2021-02-01 |  | 2021-06-08 |  | G | 2021-06-09 |  | 2021-06-29 |  | G | 2021-07-29 |  | 2021-11-22 |  | G | [10 empty] | 2023-03-20 |  | 2023-04-21 |  | G | [5 empty] | 2023-04-24 |  | 2023-09-20 |  | G | 2024-03-27 |  | 2024-08-22 |  | G | [5 empty] | 2024-08-01 |  | 2024-08-28 |  | G | 2024-11-19 |  | 2024-11-19 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.18457
2600 | 117046 | Shrader Road Sidewalk | 9999 | Secondary | Facilities for Pedestrians and Bicycles | Locally | Henrico County | ASHLAND | Richmond | Richmond:Henrico County | Local Assistance Division | Douglas L Orcutt | Doug.Orcutt@vdot.virginia.gov | (804) 609-5428 | Douglas L Orcutt | Doug.Orcutt@vdot.virginia.gov | (804) 609-5428 | TBD |  | TBD | 0 |  | 0 | FY2029 | 1818100 | 1818100 | NO DATES SET YET | G | Agreement with Locality milestone is 1543 days ahead of the expected completion date | G | Project is on budget | 2025-01-06 |  | 2025-05-14 |  | G | 2025-05-15 |  | 2025-06-05 |  | G | 2025-12-15 |  | 2026-04-10 |  | G | [10 empty] | 2027-07-30 |  | 2027-09-02 |  | G | [5 empty] | 2027-09-03 |  | 2028-02-09 |  | G | 2028-01-05 |  | 2028-06-05 |  | G | [5 empty] | 2028-05-12 |  | 2028-06-09 |  | G | 2028-08-29 |  | 2028-08-29 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.35459
2601 | 117995 | Glade Creek Greenway Phase 2B |  | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Vinton | SALEM | Salem | Roanoke:Vinton | Local Assistance Division | Jessie Nester | Jessie.Nester@vdot.virginia.gov | (540) 613-4115 | Jessie Nester | Jessie.Nester@vdot.virginia.gov | (540) 613-4115 | Anita McMillan | amcmillan@vintonva.gov | (540) 983-0605 | 0 |  | 0 | FY2025 | 476000 | 476000 | NO DATES SET YET | G | Agreement with Locality milestone finished 63 days early | G | Project is on budget | 2020-12-01 | 2021-01-20 | 2021-04-12 | 2021-02-08 | G | 2021-04-13 |  | 2021-05-03 |  | G | 2021-11-08 |  | 2022-03-09 |  | G | [10 empty] | 2023-06-27 |  | 2023-08-01 |  | G | [5 empty] | 2023-08-02 |  | 2024-01-04 |  | G | 2023-11-30 |  | 2024-05-01 |  | G | [5 empty] | 2024-04-10 |  | 2024-05-07 |  | G | 2024-07-26 |  | 2024-07-26 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.398
2602 | 118180 | #SGR21VP - Roanoke FKEY 1364 Hollins Rd NE | 0000 | Urban | Resurfacing | VDOT | Roanoke | SALEM | Salem | Roanoke:Roanoke City | Infrastructure Investment/Asset Management Division | Ibrahim M Abuawad | Ibrahim.Abuawad@vdot.virginia.gov | (217) 418-8827 | Ibrahim M Abuawad | Ibrahim.Abuawad@vdot.virginia.gov | (217) 418-8827 | Mark Jamison | mark.jamison@roanokeva.gov | (540) 853-5471 | 0 |  | 1 | FY2021 | 400000 | 400000 | NO DATES SET YET | R | Determine Requirements milestone is 9 days past the expected completion date | G | Project is on budget | [10 empty] | 2021-02-01 |  | 2021-02-12 |  | R | [35 empty] | 2021-03-09 |  | 2021-03-09 |  | Y | 2021-05-27 |  | 2021-05-27 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.14925
2603 | 12546 | #HB2.FY17 RTE 58 - WIDEN TO 6-LANE DIVIDED FACILITY | 0058 | Urban | Reconstruction w/ Added Capacity | VDOT | Virginia Beach | NORFOLK | Hampton Roads | Hampton Roads:Virginia Beach | Infrastructure Investment Division | Samba Secka | Samba.Secka@vdot.virginia.gov | (757) 956-3058 | John K Arms | John.Arms@vdot.virginia.gov | (757) 995-5156 |  |  |  | 1 | 2017 | 0 | FY2020 | 57566051 | 77160000 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 156 days early | R | Project estimate is greater than $10M and is over budget by (a) 10% or more or (b) $5M or more | [5 empty] | 1992-08-24 | 1993-04-09 | 1992-08-31 | 1993-04-12 | R | 2016-04-11 | 2016-04-11 | 2016-12-12 | 2016-12-12 | G | [10 empty] | 2002-02-20 | 2002-02-20 | 2002-02-21 | 2002-02-21 | G | 2006-02-22 | 2006-02-22 | 2025-09-08 |  | G | 2002-05-30 | 2002-05-30 | 2014-10-23 | 2019-06-04 | R | 2017-06-05 | 2017-06-05 | 2019-05-28 | 2018-11-20 | G | [5 empty] | 2019-06-11 | 2019-01-22 | 2019-06-11 | 2019-01-22 | G | 2019-08-23 | 2019-05-15 | 2019-10-18 | 2019-05-15 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.14764
2604 | 93074 | #SGR17VB - RT 81 - APPROACHES & BR OVER RT 8 - 22513 & 22515 | 0081 | Interstate | Bridge Replacement w/o Added Capacity | VDOT | Christiansburg | CHRISTIANSBURG | Salem | New River Valley:Christiansburg | Infrastructure Investment/Asset Management Division | Dean W Hackett | Dean.Hackett@VDOT.Virginia.gov | (540) 387-5311 | Marvin D Mann | M.Mann@VDOT.Virginia.gov | (540) 378-5055 |  |  |  | 0 |  | 1 | FY2019 | 34014401 | 34014401 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 82 days early | G | Project is on budget | [5 empty] | 2010-05-14 | 2010-04-19 | 2010-05-14 | 2010-04-19 | G | 2011-04-01 | 2011-03-30 | 2017-10-26 | 2017-10-26 | G | [5 empty] | 2017-10-27 | 2017-10-27 | 2017-11-13 | 2017-11-13 | G | 2017-09-01 | 2017-09-01 | 2017-10-06 | 2017-10-06 | G | [20 empty] | 2017-10-04 | 2017-10-23 | 2017-10-23 | 2017-10-23 | G | 2018-04-11 | 2018-05-16 | 2018-08-06 | 2018-05-16 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | DESIGN BUILD/PPTA | 1 | 0 | 0.075416
2605 | 103005 | Centerville Turnpike Widening Phase 2 | 0000 | Urban | Reconstruction w/ Added Capacity | Locally | Virginia Beach | NORFOLK | Hampton Roads | Hampton Roads:Virginia Beach | Infrastructure Investment Division | Susan Wilson | Susan.Wilson@vdot.virginia.gov | (757) 956-3099 | Marci Thompson | Marci.Thompson@vdot.virginia.gov | (757) 956-3093 | Katie Shannon | kshannon@vbgov.com | (757) 385-1514 | 0 |  | 0 | FY2021 | 38194743 | 42907026 | ACTIVITY DATES SET | R | Complete Purchasing Right-of-Way milestone baseline missing | R | Project estimate is greater than $10M and is over budget by (a) 10% or more or (b) $5M or more | [5 empty] | 2013-07-01 | 2013-12-20 | 2013-09-15 | 2013-12-26 | R | 2013-12-26 | 2014-02-20 | 2014-07-01 | 2015-07-28 | R | [10 empty] | 2015-07-08 | 2015-07-08 | 2015-07-29 | 2015-07-29 | G | [9 empty] | R | [10 empty] | 2019-06-04 |  | 2019-07-01 |  | R | 2020-09-30 |  | 2020-11-16 |  | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.24094
2606 | 106968 | S. WALTER REED DRIVE BICYCLE & PED IMPROVEMENTS | 9999 | Secondary | Facilities for Pedestrians and Bicycles | Locally | Arlington County | FAIRFAX | Northern Virginia | Northern Virginia:Arlington County | Local Assistance Division | Amir Salahshoor | A.Salahshoor@VDOT.Virginia.gov | (703) 259-1957 | Rita Hockman | Rita.Hockman@vdot.virginia.gov | (804) 824-7421 | M. Valerie Mosley | mvmosley@arlingtonva.us | (703) 228-4938 | 0 |  | 0 | FY2019 | 2405000 | 2654019 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 35 days early | Y | Project estimate is less than $5M and is up to 20% over budget | [5 empty] | 2015-07-01 | 2015-12-16 | 2015-07-15 | 2015-12-16 | R | 2015-07-16 | 2015-07-16 | 2015-08-12 | 2015-11-30 | R | [35 empty] | 2018-05-03 | 2018-02-08 | 2018-05-03 | 2018-02-08 | G | 2018-06-18 | 2018-04-09 | 2018-07-09 | 2018-06-04 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.24561
2607 | 108854 | Prices Fork Road Pedestrian Safety Improvements | 0412 | Urban | Facilities for Pedestrians and Bicycles | Locally | Blacksburg | CHRISTIANSBURG | Salem | New River Valley:Blacksburg | Local Assistance Division | James M Guy | james.guy@vdot.virginia.gov | (540) 387-5247 | Adam J Czesnowski | Adam.Czesnowski@vdot.virginia.gov | (540) 541-1216 | Randy Formica | rformica@blacksburg.gov | (540) 443-1300 | 0 |  | 0 | FY2020 | 415000 | 415000 | CONSTRUCTION STARTED | G | Start Delivery milestone finished on-time | G | Project is on budget | 2016-07-01 | 2016-07-01 | 2016-08-24 | 2016-08-24 | G | 2016-09-29 | 2016-09-29 | 2016-10-07 | 2016-10-07 | G | 2016-11-07 | 2016-11-07 | 2018-02-15 | 2018-02-01 | G | [35 empty] | 2019-10-04 | 2020-03-17 | 2019-11-01 | 2020-04-08 | R | 2019-11-04 | 2020-04-29 | 2020-05-11 | 2020-05-11 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.16135
2608 | 109230 | RTE 1 AND RT 670 INTERSECTION IMPROVEMENTS | 0001 | Primary | Safety | VDOT | Dinwiddie County | PETERSBURG | Richmond | Tri-Cities:Dinwiddie County | Infrastructure Investment Division | Raymond Chapman | Scott.Chapman@vdot.virginia.gov | (804) 609-5277 | Raymond Chapman | Scott.Chapman@vdot.virginia.gov | (804) 609-5277 |  |  |  | 0 |  | 0 | FY2026 | 1692900 | 1692900 | NO DATES SET YET | G | Start Development milestone is 204 days ahead of the expected completion date | G | Project is on budget | [5 empty] | 2021-08-30 |  | 2021-09-13 |  | G | 2021-09-14 |  | 2022-08-11 |  | G | [5 empty] | 2023-06-19 |  | 2023-06-30 |  | G | 2024-10-04 |  | 2024-10-17 |  | G | 2025-03-20 |  | 2025-09-22 |  | G | 2024-11-05 |  | 2025-05-15 |  | G | 2024-03-27 |  | 2025-03-27 |  | G | [5 empty] | 2025-10-14 |  | 2025-10-14 |  | G | 2025-12-09 |  | 2025-12-30 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.060017
2609 | 110088 | #SGR17VB - BRIDGE REPLACEMENT -- RT 620 PISCATAWAY ID 06153 | 0620 | Secondary | Bridge Replacement w/o Added Capacity | VDOT | Essex County | SALUDA | Fredericksburg | NonMPO:NonMPO | Infrastructure Investment/Asset Management Division | Wesley Foor | Wesley.Foor@vdot.virginia.gov | (540) 604-1370 | Wesley Foor | Wesley.Foor@vdot.virginia.gov | (540) 604-1370 |  |  |  | 0 |  | 1 | FY2021 | 1600000 | 1600000 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 267 days early | G | Project is on budget | [5 empty] | 2016-10-03 | 2016-10-03 | 2016-10-17 | 2016-10-26 | R | 2016-10-18 | 2016-10-27 | 2017-09-14 | 2017-12-18 | R | [5 empty] | 2018-07-05 | 2018-05-09 | 2018-07-18 | 2018-06-14 | G | 2019-01-03 | 2018-06-19 | 2019-01-16 | 2018-08-14 | G | 2019-08-09 | 2018-03-21 | 2020-02-20 | 2018-03-21 | G | 2019-02-05 | 2018-09-20 | 2019-08-08 | 2019-02-04 | G | 2018-12-07 | 2018-08-01 | 2019-08-12 | 2019-02-08 | G | [5 empty] | 2020-03-10 | 2019-08-13 | 2020-03-10 | 2019-08-13 | G | 2020-06-11 | 2019-11-13 | 2020-08-06 | 2019-11-13 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.059608
2610 | 117132 | Jefferson Avenue Sidewalk-Green Grove to Industrial Park | 0143 | Urban | Facilities for Pedestrians and Bicycles | Locally | Newport News | WILLIAMSBURG | Hampton Roads | Hampton Roads:Newport News | Infrastructure Investment Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Chessica Villaflores | Chessica.Villaflores@vdot.virginia.gov | (757) 956-3094 | Bridjette Parker | parkerbj1@nnva.gov | (757) 926-8314 | 0 |  | 0 | FY2024 | 2000000 | 2000000 | NO DATES SET YET | Y | Agreement with Locality milestone is 11 days ahead of the expected completion date and there is a risk of missing this milestone date | G | Project is on budget | 2020-10-20 |  | 2021-03-04 |  | Y | 2021-03-05 |  | 2021-03-25 |  | G | 2021-09-29 |  | 2022-01-28 |  | G | [10 empty] | 2023-05-18 |  | 2023-06-22 |  | G | [5 empty] | 2023-06-23 |  | 2023-11-22 |  | G | 2023-10-19 |  | 2024-03-25 |  | G | [5 empty] | 2024-03-04 |  | 2024-03-29 |  | G | 2024-06-18 |  | 2024-06-18 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.26166
2611 | 118070 | Sharp Street Improvements |  | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Lawrenceville | SOUTH HILL | Richmond | NonMPO:NonMPO | Local Assistance Division | Jorg Huckabee-Mayfield | Jorg.Huckabee-Mayfield@VDOT.Virginia.gov | (804) 609-5292 | Jorg Huckabee-Mayfield | Jorg.Huckabee-Mayfield@VDOT.Virginia.gov | (804) 609-5292 | Ashleigh Zincone | azincone@southsidepdc.org | (434) 447-7101 | 0 |  | 0 | FY2025 | 642651 | 642651 | NO DATES SET YET | G | Agreement with Locality milestone is 199 days ahead of the expected completion date | G | Project is on budget | 2021-05-03 |  | 2021-09-08 |  | G | 2021-09-09 |  | 2021-09-29 |  | G | 2022-04-13 |  | 2022-08-04 |  | G | [10 empty] | 2023-11-28 |  | 2024-01-03 |  | G | [5 empty] | 2024-01-04 |  | 2024-06-04 |  | G | 2024-05-01 |  | 2024-09-27 |  | G | [5 empty] | 2024-09-06 |  | 2024-10-03 |  | G | 2024-12-27 |  | 2024-12-27 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.34915
2612 | 118246 | Mountain View Rd Reconstruction | 0000 | Urban | Reconstruction w/o Added Capacity | VDOT | Vinton | SALEM | Salem | Roanoke:Vinton | Local Assistance Division | Alex H Price | Alex.Price@VDOT.Virginia.gov | (540) 378-5053 | Alex H Price | Alex.Price@VDOT.Virginia.gov | (540) 378-5053 | Joey Hiner | JHiner@Vintonva.gov | 54098306 | 0 |  | 0 | FY2028 | 1000000 | 1000000 | NO DATES SET YET | G | Start Development milestone is 1307 days ahead of the expected completion date | G | Project is on budget | [5 empty] | 2024-08-30 |  | 2024-09-20 |  | G | 2024-09-23 |  | 2025-07-28 |  | G | [5 empty] | 2026-03-03 |  | 2026-03-30 |  | G | [5 empty] | 2026-11-18 |  | 2027-03-25 |  | G | [5 empty] | 2026-08-12 |  | 2027-01-14 |  | G | [5 empty] | 2027-04-13 |  | 2027-04-13 |  | G | 2027-07-01 |  | 2027-07-01 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.16584
2613 | 15959 | #SMART18 - I US360 HULL STREET SAFETY / OPS IMPROVE PHASE I | 0360 | Urban | Reconstruction w/ Added Capacity | Locally | Richmond | CHESTERFIELD | Richmond | Richmond:Richmond | Infrastructure Investment Division | Cynthia Crouch | Cynthia.Crouch@vdot.virginia.gov | (804) 609-5313 | Cynthia Crouch | Cynthia.Crouch@vdot.virginia.gov | (804) 609-5313 | Adel Edward | Adel.Edward@Richmond.gov | (804) 646-6584 | 1 | 2018 | 0 | FY2022 | 21099700 | 21078946 | ACTIVITY DATES SET | Y | Solicit Bids milestone is 37 days ahead of the expected completion date and there is a risk of missing this milestone date | G | Project is on budget | 2004-07-06 | 2004-07-06 | 2004-07-06 | 2004-07-06 | G | 1996-10-01 | 1996-06-11 | 1996-10-31 | 1996-06-12 | G | 1996-11-01 | 1996-06-12 | 1997-04-30 | 1997-04-09 | G | [10 empty] | 2018-10-01 | 2018-09-18 | 2018-10-01 | 2018-09-21 | G | 2021-01-04 |  | 2022-03-31 |  | G | 2018-10-08 | 2018-09-24 | 2021-03-30 |  | Y | [10 empty] | 2021-03-30 |  | 2021-03-30 |  | Y | 2021-06-30 |  | 2021-07-30 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.2254
2614 | 97171 | #HB2.FY17 Roanoke Co, RRG, Green Hill Pk to Riverside Pk |  | Enhancement | Landscaping/Beautification | Locally | Roanoke County | SALEM | Salem | Roanoke:Roanoke County | Infrastructure Investment Division | Cheryl B Becker | Cheryl.Becker@vdot.virginia.gov | (540) 492-2531 | Cheryl B Becker | Cheryl.Becker@vdot.virginia.gov | (540) 492-2531 | Lindsay Webb | LWEBB@roanokecountyva.gov | (540) 777-6328 | 1 | 2017 | 0 | FY2019 | 8032031 | 9562500 | ACTIVITY DATES SET | R | Solicit Bids milestone is 905 days past the expected completion date | R | Project estimate is between $5M and $10M and is a $1M or more over budget | [5 empty] | 2012-05-01 | 2012-05-01 | 2012-05-01 | 2012-05-01 | G | 2013-02-28 | 2014-03-18 | 2013-06-28 | 2016-02-23 | R | 2017-12-29 | 2017-12-29 | 2018-02-26 | 2018-02-26 | G | [5 empty] | 2017-02-28 | 2017-02-28 | 2017-08-01 | 2017-02-28 | G | [5 empty] | 2017-08-03 | 2018-04-16 | 2018-05-31 | 2018-04-16 | G | [10 empty] | 2018-07-02 |  | 2018-08-31 |  | R | 2018-09-05 |  | 2018-10-16 |  | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.37585
2615 | 104452 | Route 619 Dickenson Co. Va. Str.# 6128 Fed. Str. # 5846 | 0619 | Secondary | Bridge Rehab w/o Added Capacity | VDOT | Dickenson County | WISE | Bristol | NonMPO:NonMPO | Asset Management Division | Gary Lester |  |  | Daniel B Cannon | Daniel.Cannon@VDOT.Virginia.gov | (276) 696-3376 |  |  |  | 0 |  | 0 | FY2024 | 4280000 | 4280000 | ACTIVITY DATES SET | G | Determine Requirements milestone finished on-time | G | Project is on budget | [5 empty] | 2014-10-01 | 2014-10-01 | 2014-10-01 | 2014-10-01 | G | 2014-10-31 | 2014-01-14 | 2019-06-24 | 2019-06-24 | G | [35 empty] | 2024-02-28 |  | 2024-02-28 |  | G | 2024-05-13 |  | 2024-06-19 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.17745
2616 | 107461 | #HB2.FY17 RTE 64 EB - PAVEMENT MARKING | 0064 | Interstate | Reconstruction w/o Added Capacity | VDOT | Henrico County | ASHLAND | Richmond | Richmond:Henrico County | Infrastructure Investment Division | Jason C Williams | Jason.Williams@VDOT.Virginia.gov | (804) 609-5337 | Scott J Fisher | Scott.Fisher@VDOT.Virginia.gov | (804) 674-2452 |  |  |  | 1 | 2017 | 0 | FY2018 | 1500000 | 1482738 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 34 days early | G | Project is on budget | [5 empty] | 2015-08-12 | 2015-08-12 | 2015-08-12 | 2015-08-12 | G | 2016-08-02 | 2016-08-02 | 2016-12-05 | 2016-12-05 | G | [35 empty] | 2017-08-01 | 2017-03-17 | 2017-08-01 | 2017-03-17 | G | 2017-08-29 | 2017-07-19 | 2017-08-29 | 2017-07-26 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.095153
2617 | 108863 | FY17 RS - Peppers Ferry Road & Quin W. Stuart Boulevard | 0114 | Urban | Traffic Management/Engineering | Locally | Christiansburg | CHRISTIANSBURG | Salem | New River Valley:Christiansburg | Local Assistance Division | Adam J Czesnowski | Adam.Czesnowski@vdot.virginia.gov | (540) 541-1216 | Adam J Czesnowski | Adam.Czesnowski@vdot.virginia.gov | (540) 541-1216 | Wayne Nelson |  |  | 0 |  | 0 | FY2019 | 811000 | 811000 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 231 days early | G | Project is on budget | 2016-07-01 | 2016-07-01 | 2016-09-26 | 2016-08-29 | G | 2016-09-27 | 2016-10-05 | 2016-09-29 | 2016-10-12 | R | 2016-09-30 | 2016-10-13 | 2017-04-12 | 2017-02-15 | G | [10 empty] | 2017-09-06 | 2017-02-16 | 2017-09-26 | 2017-02-16 | G | [5 empty] | 2017-09-28 | 2017-11-13 | 2018-06-18 | 2017-11-13 | G | [10 empty] | 2018-07-05 | 2017-11-03 | 2018-08-01 | 2017-11-06 | G | 2018-08-02 | 2017-11-07 | 2018-09-12 | 2018-01-24 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.10462
2618 | 109529 | #HB2.FY17 RTE 15 - LEFT & RIGHT TURN LANES AT RTE 636 | 6015 | Primary | Safety | VDOT | Buckingham County | DILLWYN | Lynchburg | NonMPO:NonMPO | Infrastructure Investment Division | Daniel J Brown | Daniel.Brown@VDOT.Virginia.gov | (434) 856-8265 | Gregory K Parsons | Gregory.Parsons@vdot.virginia.gov | (434) 856-8297 |  |  |  | 1 | 2017 | 0 | FY2021 | 2652279 | 2652279 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 14 days early | G | Project is on budget | [5 empty] | 2016-08-12 | 2016-08-12 | 2016-08-25 | 2016-08-25 | G | 2016-08-12 | 2016-08-12 | 2017-11-20 | 2017-11-20 | G | [5 empty] | 2018-10-02 | 2018-10-02 | 2018-10-16 | 2018-10-09 | G | 2019-08-27 | 2019-07-03 | 2019-09-11 | 2019-07-16 | G | 2020-04-09 | 2020-04-20 | 2020-10-12 | 2021-01-05 | R | 2019-09-27 | 2019-08-06 | 2020-04-08 | 2020-04-08 | G | 2019-02-22 | 2019-02-19 | 2020-02-07 | 2019-02-19 | G | [5 empty] | 2020-10-13 | 2020-10-06 | 2020-10-13 | 2020-10-06 | G | 2020-12-08 | 2020-12-15 | 2020-12-29 | 2020-12-15 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.095638
2619 | 110840 | RTE 156 - INTERSECTION IMPROVEMENTS AT BERRY ST | 0156 | Urban | Safety | Locally | Hopewell | PETERSBURG | Richmond | Tri-Cities:Hopewell | Infrastructure Investment Division | James Shepherd | James.Shepherd@vdot.virginia.gov | (804) 609-5305 | James Shepherd | James.Shepherd@vdot.virginia.gov | (804) 609-5305 | Johnny Butler | jbutler@hopewellva.gov | (804) 541-2319 | 0 |  | 0 | FY2024 | 341000 | 341000 | NO DATES SET YET | G | Agreement with Locality milestone finished 80 days early | G | Project is on budget | 2020-12-01 | 2020-12-01 | 2021-04-12 | 2021-01-22 | G | 2021-04-13 |  | 2021-05-03 |  | G | 2021-06-02 |  | 2021-09-23 |  | G | [10 empty] | 2023-01-20 |  | 2023-02-24 |  | G | [5 empty] | 2023-02-27 |  | 2023-07-25 |  | G | 2023-06-21 |  | 2023-11-20 |  | G | [5 empty] | 2023-10-27 |  | 2023-11-28 |  | G | 2024-02-21 |  | 2024-02-21 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.08142
2620 | 110967 | BLACKSTONE SIDEWALKS |  | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Blackstone | PETERSBURG | Richmond | NonMPO:NonMPO | Local Assistance Division | Brian J Lokker | Brian.Lokker@VDOT.Virginia.gov | (804) 524-6010 | Brian J Lokker | Brian.Lokker@VDOT.Virginia.gov | (804) 524-6010 | Philip Vannoorbeek | Philipv@townofblackstoneva.com | (434) 292-7251 | 0 |  | 0 | FY2020 | 328330 | 427162 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished on-time | R | Project estimate is less than $5M and is 20% or more over budget | 2017-10-02 | 2017-07-24 | 2017-12-29 | 2017-10-04 | G | 2018-01-02 | 2017-11-14 | 2018-01-04 | 2017-11-29 | G | 2018-01-05 | 2017-11-30 | 2018-07-12 | 2018-07-12 | G | [35 empty] | 2019-05-23 | 2019-06-20 | 2019-06-20 | 2019-06-20 | G | 2019-06-21 | 2019-06-21 | 2019-08-15 | 2019-08-15 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.28007
2621 | 111135 | Flashing Yellow Arrow - Various locations - Roanoke City | 9999 | Urban | Safety | Locally | Roanoke | SALEM | Salem | Roanoke:Roanoke City | Infrastructure Investment Division | Cheryl B Becker | Cheryl.Becker@vdot.virginia.gov | (540) 492-2531 | Cheryl B Becker | Cheryl.Becker@vdot.virginia.gov | (540) 492-2531 | Hong Liu | hong.liu@roanokeva.gov | (540) 853-2686 | 0 |  | 0 | FY2022 | 277460 | 164478 | AWARDED | G | Start Delivery milestone finished 232 days early | G | Project is on budget | 2019-07-01 | 2019-07-03 | 2019-10-15 | 2019-11-06 | R | 2019-10-16 | 2019-11-07 | 2019-10-18 | 2019-11-21 | R | 2019-10-22 | 2019-11-22 | 2020-04-30 | 2020-01-27 | G | [35 empty] | 2021-03-15 | 2020-10-06 | 2021-04-09 | 2020-12-02 | G | 2021-04-12 | 2020-12-02 | 2021-08-03 | 2020-12-14 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.28942
2622 | 111277 | #SGR18VB - BRIDGE SUPERSTRUCTURE REPLACE-RT 46 OVER HWY 58 | 0046 | Primary | Bridge Replacement w/o Added Capacity | VDOT | Brunswick County | SOUTH HILL | Richmond | NonMPO:NonMPO | Infrastructure Investment/Asset Management Division | Phillip Frazer | Phillip.Frazer@vdot.virginia.gov | (804) 481-0906 | Susan Warr | Susan.Warr@VDOT.Virginia.gov | (804) 720-5478 |  |  |  | 0 |  | 1 | FY2019 | 1850000 | 1850000 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 2 days early | G | Project is on budget | [5 empty] | 2017-08-14 | 2017-08-14 | 2017-08-25 | 2017-08-25 | G | 2017-10-12 | 2017-10-12 | 2018-05-04 | 2018-05-04 | G | [5 empty] | 2018-06-21 | 2018-06-21 | 2018-07-05 | 2018-07-02 | G | 2018-07-27 | 2018-07-20 | 2018-07-27 | 2018-07-20 | G | 2018-06-01 | 2018-06-01 | 2018-06-01 | 2018-06-01 | G | 2018-07-27 | 2018-07-20 | 2018-07-27 | 2018-07-20 | G | 2017-11-28 | 2018-07-24 | 2018-08-31 | 2018-07-24 | G | [5 empty] | 2019-02-12 | 2019-04-09 | 2019-02-12 | 2019-04-09 | R | 2019-04-05 | 2019-06-26 | 2019-06-28 | 2019-06-26 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.059934
2623 | 111306 | #SMART18 - RTE 131 - RECONSTRUCTION | 0131 | Primary | Reconstruction w/ Added Capacity | VDOT | Appomattox | APPOMATTOX | Lynchburg | NonMPO:NonMPO | Infrastructure Investment Division | Brian J Casto | Brian.Casto@VDOT.Virginia.gov | (434) 856-8276 | Anthony W Revelle | Anthony.Revelle@vdot.virginia.gov | (434) 856-8258 |  |  |  | 1 | 2018 | 0 | FY2023 | 11546256 | 11546256 | ACTIVITY DATES SET | G | Obtained Permits milestone finished 241 days early | G | Project is on budget | [5 empty] | 2018-07-16 | 2018-07-27 | 2018-07-27 | 2018-07-27 | G | 2018-07-30 | 2018-07-30 | 2019-05-17 | 2019-04-19 | G | [5 empty] | 2020-02-21 | 2019-11-07 | 2020-03-05 | 2019-11-07 | G | 2021-03-11 |  | 2021-03-24 |  | G | 2021-12-29 |  | 2022-09-15 |  | G | 2021-04-09 |  | 2021-12-28 |  | G | 2020-03-09 | 2020-03-09 | 2020-11-05 | 2020-03-09 | G | [5 empty] | 2022-10-11 |  | 2022-10-11 |  | G | 2022-12-29 |  | 2023-02-28 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.11414
2624 | 111418 | Museum of the Shenandoah Valley Trail Connection |  | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Winchester | EDINBURG | Staunton | Winchester:Winchester | Local Assistance Division | Kimberly Cameron | Kim.Cameron@vdot.virginia.gov | (540) 332-7886 | Kimberly Cameron | Kim.Cameron@vdot.virginia.gov | (540) 332-7886 | Perry Eisenach | perry.eisenach@winchesterva.gov | (540) 667-1815 | 0 |  | 0 | FY2020 | 2767774 | 312500 | CONSTRUCTION STARTED | R | Start Delivery milestone finished 161 days late | G | Project is on budget | 2018-03-30 | 2017-11-01 | 2018-06-22 | 2018-02-12 | G | 2018-06-25 | 2018-02-16 | 2018-06-27 | 2018-02-27 | G | 2018-06-28 | 2018-02-28 | 2019-01-07 | 2018-08-30 | G | [35 empty] | 2019-07-15 | 2019-08-30 | 2019-08-09 | 2019-09-19 | R | 2019-08-12 | 2019-09-20 | 2019-09-20 | 2020-02-28 | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.3746
2625 | 111713 | #SMART18 - BBC Ph 1 - Bailey Br Conn., Brad McNeer Conn. | 0000 | Secondary | New Construction Roadway | Locally | Chesterfield County | CHESTERFIELD | Richmond | Richmond:Chesterfield County | Infrastructure Investment Division | Michael S Gray | Mike.Gray@vdot.virginia.gov | (804) 609-5347 | Michael S Gray | Mike.Gray@vdot.virginia.gov | (804) 609-5347 | Bill Arel | ArelB@chesterfield.gov | 7481037 | 1 | 2018 | 0 | FY2023 | 22960000 | 22960000 | NO DATES SET YET-PE OPEN | R | Determine Requirements milestone is 216 days past the expected completion date | G | Project is on budget | 2019-07-01 | 2018-06-14 | 2019-09-24 | 2018-10-04 | G | 2019-09-25 | 2018-10-26 | 2019-09-30 | 2018-10-31 | G | 2019-09-30 | 2018-11-05 | 2020-07-20 |  | R | [10 empty] | 2021-08-02 |  | 2021-08-20 |  | G | [5 empty] | 2021-08-24 |  | 2022-06-07 |  | G | [10 empty] | 2022-06-23 |  | 2022-07-21 |  | G | 2022-07-22 |  | 2022-08-31 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.30104
2626 | 112277 | #SGR19LB??- RT 460/67 APPROACHES & BR REPL.OVER CLINCH RIVER | 0460 | Urban | Bridge Rehab w/ Added Capacity | VDOT | Richlands | LEBANON | Bristol | NonMPO:NonMPO | Infrastructure Investment/Asset Management Division | Gary Lester |  |  | Daniel B Cannon | Daniel.Cannon@VDOT.Virginia.gov | (276) 696-3376 |  |  |  | 0 |  | 1 | FY2021 | 6796684 | 7819592 | ACTIVITY DATES SET | R | Obtained Permits milestone is 328 days past the expected completion date | R | Project estimate is between $5M and $10M and is a $1M or more over budget | [5 empty] | 2021-07-29 | 2018-02-22 | 2021-08-11 | 2018-09-19 | G | 2021-08-12 | 2018-09-20 | 2022-04-08 | 2019-05-24 | G | [5 empty] | 2019-08-20 | 2019-08-20 | 2019-08-20 | 2019-08-20 | G | [15 empty] | 2019-03-19 |  | 2020-03-30 |  | R | [5 empty] | 2020-09-08 |  | 2020-09-08 |  | R | 2020-10-23 |  | 2020-12-22 |  | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.075544
2627 | 113259 | Oyster Point Access Improvements- Ramps | 0017 | Interstate | Reconstruction w/ Added Capacity | VDOT | Newport News | WILLIAMSBURG | Hampton Roads | Hampton Roads:Newport News | Local Assistance Division | Samba Secka | Samba.Secka@vdot.virginia.gov | (757) 956-3058 | Samba Secka | Samba.Secka@vdot.virginia.gov | (757) 956-3058 | Bryan Stilley, P.E. | bstilley@nnva.gov | (757) 926-8699 | 0 |  | 0 | FY2024 | 3310000 | 3310000 | NO DATES SET YET-PE OPEN | R | Determine Requirements milestone is 192 days past the expected completion date | G | Project is on budget | [5 empty] | 2019-09-03 | 2020-01-03 | 2019-09-16 | 2020-09-14 | R | 2019-09-17 | 2020-09-15 | 2020-08-13 |  | R | [5 empty] | 2021-06-21 |  | 2021-07-02 |  | G | 2022-10-07 |  | 2022-10-21 |  | G | 2023-03-23 |  | 2023-09-25 |  | G | 2022-11-08 |  | 2023-05-18 |  | G | 2022-03-30 |  | 2022-09-30 |  | G | [5 empty] | 2023-10-10 |  | 2023-10-10 |  | G | 2024-01-05 |  | 2024-01-05 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 1 | 0.22881
2628 | 113287 | TOWNWIDE - TRAFFIC SIGNAL UPGRADES | 9999 | Urban | Traffic Management/Engineering | Locally | Farmville | DILLWYN | Lynchburg | NonMPO:NonMPO | Local Assistance Division | Sharon S White | Sharon.White@VDOT.Virginia.gov | (434) 856-8220 | Sharon S White | Sharon.White@VDOT.Virginia.gov | (434) 856-8220 | Gerry Spates | gspates@farmvilleva.com | (434) 392-5886 | 0 |  | 0 | FY2020 | 510000 | 510000 | CONSTRUCTION COMPLETED | G | Solicit Bids milestone finished 44 days early | G | Project is on budget | 2019-01-31 | 2018-07-10 | 2019-04-25 | 2018-07-10 | G | [5 empty] | 2019-01-31 | 2019-01-31 | 2019-02-13 | 2019-02-13 | G | [25 empty] | 2019-02-14 | 2019-02-14 | 2019-05-09 | 2019-02-14 | G | [5 empty] | 2019-05-10 | 2019-04-24 | 2019-06-07 | 2019-04-24 | G | 2019-08-27 | 2019-04-02 | 2019-08-27 | 2019-04-02 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.11511
2629 | 113322 | Hardy Road/Dillon Woods Crosswalk | 0000 | Urban | Facilities for Pedestrians and Bicycles | Locally | Vinton | SALEM | Salem | Roanoke:Vinton | Local Assistance Division | Jessie Nester | Jessie.Nester@vdot.virginia.gov | (540) 613-4115 | Jessie Nester | Jessie.Nester@vdot.virginia.gov | (540) 613-4115 | Anita McMillan | amcmillan@vintonva.gov | (540) 983-0601 | 0 |  | 0 | FY2023 | 182693 | 182693 | NO DATES SET YET | R | Agreement with Locality milestone is 53 days past the expected completion date | G | Project is on budget | 2020-10-01 |  | 2020-12-30 |  | R | 2020-12-31 |  | 2021-01-05 |  | R | 2021-01-06 |  | 2021-08-02 |  | G | [25 empty] | 2021-11-30 |  | 2022-08-03 |  | G | [5 empty] | 2022-08-19 |  | 2022-09-16 |  | G | 2023-02-16 |  | 2023-02-16 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.19242
2630 | 111041 | #SGR18LB - Simons Drive over Cohoon Creek | 0608 | Urban | Bridge Replacement w/o Added Capacity | Locally | Suffolk | NORFOLK | Hampton Roads | Hampton Roads:Suffolk | Infrastructure Investment Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Johndel A Alcaide | John.Alcaide@vdot.virginia.gov | (757) 956-3098 | L. Hansen | lhansen@suffolkva.us | (757) 514-7687 | 0 |  | 1 | FY2019 | 736229 | 769920 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 46 days early | Y | Project estimate is less than $5M and is up to 20% over budget | 2017-06-01 | 2017-06-01 | 2017-08-24 | 2017-10-05 | R | 2017-08-25 | 2017-11-21 | 2017-08-29 | 2017-12-21 | R | 2017-08-30 | 2017-12-22 | 2018-03-13 | 2018-03-16 | R | [35 empty] | 2018-05-21 | 2018-03-30 | 2018-06-18 | 2018-04-01 | G | 2018-06-19 | 2018-05-30 | 2018-07-30 | 2018-06-14 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.1088
2631 | 111230 | #SMART18 - (St) I-81 EXIT 247 INTERCHANGE IMPROVEMENTS | 0081 | Interstate | Reconstruction w/ Added Capacity | VDOT | Harrisonburg | HARRISONBURG | Staunton | Harrisonburg:Harrisonburg | Infrastructure Investment Division | John-Allen L Ennis | JohnAllen.Ennis@VDOT.Virginia.gov | (540) 332-9118 | John-Allen L Ennis | JohnAllen.Ennis@VDOT.Virginia.gov | (540) 332-9118 |  |  |  | 1 | 2018 | 0 | FY2023 | 6708146 | 5765784 | ACTIVITY DATES SET | G | Engage Public milestone finished 32 days early | G | Project is on budget | [5 empty] | 2019-08-01 | 2019-07-12 | 2019-08-14 | 2019-07-12 | G | 2019-08-15 | 2019-07-15 | 2020-03-25 | 2019-10-18 | G | [5 empty] | 2019-12-24 | 2019-12-24 | 2020-04-07 | 2020-03-06 | G | [15 empty] | 2020-10-01 |  | 2022-04-21 |  | G | [5 empty] | 2022-11-08 |  | 2022-11-08 |  | G | 2022-11-09 |  | 2023-06-15 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.066037
2632 | 111302 | #SGR18VB - BRIDGE REHAB I-95 OVER RT 608 (REYMET RD) CN ONLY | 0095 | Interstate | Bridge Rehab w/o Added Capacity | VDOT | Chesterfield County | CHESTERFIELD | Richmond | Richmond:Chesterfield County | Infrastructure Investment/Asset Management Division | Xuesong Zhang | Jason.Zhang@vdot.virginia.gov | (804) 609-5248 | Xuesong Zhang | Jason.Zhang@vdot.virginia.gov | (804) 609-5248 |  |  |  | 0 |  | 1 | FY2022 | 11000000 | 9408731 | ADVERTISED | G | Solicit Bids milestone finished 119 days early | G | Project is on budget | [10 empty] | 2017-08-01 | 2017-08-01 | 2018-07-25 | 2018-07-24 | G | [35 empty] | 2021-04-13 | 2020-12-15 | 2021-04-13 | 2020-12-15 | G | 2021-10-12 |  | 2021-10-12 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.14784
2633 | 111359 | #SMART18 - I-81 SB Safety Improvements MM167.4 to MM169.5 | 0081 | Interstate | Reconstruction w/o Added Capacity | VDOT | Botetourt County | SALEM | Salem | NonMPO:NonMPO | Infrastructure Investment Division | Thomas W Digiulian | Thomas.DiGiulian@VDOT.Virginia.gov | (540) 387-5356 | Marvin D Mann | M.Mann@VDOT.Virginia.gov | (540) 378-5055 | Bryan Hill | bhill@rvarc.org | (540) 343-4417 | 1 | 2018 | 0 | FY2021 | 8123654 | 8123654 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 8 days early | G | Project is on budget | [5 empty] | 2018-07-02 | 2018-05-22 | 2018-07-16 | 2018-06-21 | G | 2018-07-17 | 2018-06-22 | 2018-09-11 | 2018-09-11 | G | [5 empty] | 2019-02-20 | 2019-02-20 | 2019-04-02 | 2019-03-19 | G | [15 empty] | 2019-07-08 | 2018-12-12 | 2020-02-13 | 2018-12-12 | G | [5 empty] | 2020-03-10 | 2020-05-19 | 2020-03-10 | 2020-05-19 | R | 2020-05-21 | 2020-07-21 | 2020-07-29 | 2020-07-21 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.13461
2634 | 111659 | #SMART18 -RTE. 17 / LORETTO PARK & RIDE IMPROVEMENTS | 0017 | Secondary | Safety | VDOT | Essex County | SALUDA | Fredericksburg | NonMPO:NonMPO | Infrastructure Investment Division | Jessica Graves | Jessica.Graves@vdot.virginia.gov | (540) 899-4267 | Jessica Graves | Jessica.Graves@vdot.virginia.gov | (540) 899-4267 |  |  |  | 1 | 2018 | 0 | FY2022 | 915000 | 736182 | ACTIVITY DATES SET | G | Obtained Permits milestone finished 152 days early | G | Project is on budget | [5 empty] | 2019-07-19 | 2019-07-19 | 2019-08-01 | 2019-07-31 | G | 2019-08-02 | 2019-08-01 | 2020-03-25 | 2020-03-23 | G | [5 empty] | 2020-06-03 | 2020-06-03 | 2020-07-15 | 2020-07-10 | G | [5 empty] | 2020-12-29 | 2020-08-20 | 2021-04-23 | 2020-08-20 | G | [5 empty] | 2020-10-13 | 2020-08-21 | 2021-01-20 | 2020-08-21 | G | [5 empty] | 2021-05-11 |  | 2021-05-11 |  | G | 2021-08-13 |  | 2021-10-08 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.071398
2635 | 111742 | #SMART18 - RTE 601 LOW-SPEED CURVE REALIGNMENT #2 | 0601 | Secondary | Safety | VDOT | Orange County | LOUISA | Culpeper | NonMPO:NonMPO | Infrastructure Investment Division | Gregory J Cooley | Gregory.Cooley@vdot.virginia.gov | (434) 906-7979 | Justin Warfield | Justin.Warfield@vdot.virginia.gov | (540) 829-7599 |  |  |  | 1 | 2018 | 0 | FY2023 | 1400000 | 1400000 | NO DATES SET YET-PE OPEN | R | Determine Requirements milestone is 550 days past the expected completion date | G | Project is on budget | [5 empty] | 2018-09-10 | 2018-09-18 | 2018-09-21 | 2018-09-18 | G | 2018-09-24 | 2018-11-28 | 2019-08-21 |  | R | [5 empty] | 2020-06-12 |  | 2020-06-25 |  | R | 2021-07-01 |  | 2021-07-15 |  | G | 2022-01-28 |  | 2022-07-05 |  | G | 2021-08-02 |  | 2022-01-27 |  | G | 2021-01-14 |  | 2021-07-21 |  | G | [5 empty] | 2022-07-12 |  | 2022-07-12 |  | G | 2022-08-25 |  | 2022-10-21 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.081692
2636 | 112318 | Elbow Road Phase 2D |  | Urban | New Construction Roadway | Locally | Virginia Beach | NORFOLK | Hampton Roads | Hampton Roads:Virginia Beach | Infrastructure Investment Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Marci Thompson | Marci.Thompson@vdot.virginia.gov | (757) 956-3093 | Katie Shannon, PE | kshannon@vbgov.com | (757) 385-1514 | 0 |  | 0 | FY2026 | 27273632 | 27273632 | NO DATES SET YET | G | Agreement with Locality milestone is 488 days ahead of the expected completion date | G | Project is on budget | 2022-04-01 |  | 2022-06-24 |  | G | 2022-06-27 |  | 2022-07-11 |  | G | 2022-07-12 |  | 2023-07-12 |  | G | [10 empty] | 2024-07-24 |  | 2024-08-13 |  | G | [5 empty] | 2024-08-15 |  | 2025-05-29 |  | G | [10 empty] | 2025-06-16 |  | 2025-07-14 |  | G | 2025-07-15 |  | 2025-10-14 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.2404
2637 | 113265 | Burtons Point Road Reconstruction | 9999 | Urban | Reconstruction w/o Added Capacity | Locally | Portsmouth | NORFOLK | Hampton Roads | Hampton Roads:Portsmouth | Local Assistance Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Marci Thompson | Marci.Thompson@vdot.virginia.gov | (757) 956-3093 | James Wright, P.E. | wrightj@portsmouthva.gov | (757) 393-8592 | 0 |  | 0 | FY2022 | 2500000 | 2500000 | ACTIVITY DATES SET | G | Engage Public milestone finished 38 days early | G | Project is on budget | 2018-10-01 | 2018-10-01 | 2018-12-28 | 2019-02-26 | R | 2018-12-31 | 2019-02-27 | 2019-01-03 | 2019-03-08 | R | 2019-01-04 | 2019-03-11 | 2019-07-11 | 2020-06-30 | R | 2020-09-11 | 2020-09-11 | 2020-10-23 | 2020-09-15 | G | [30 empty] | 2021-06-24 |  | 2021-08-05 |  | G | 2021-10-26 |  | 2022-04-21 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.11529
2638 | 113288 | AUDUBON DRIVE - PEDESTRIAN IMPROVEMENTS | 9999 | Urban | Facilities for Pedestrians and Bicycles | Locally | Danville | HALIFAX | Lynchburg | Danville:Danville | Local Assistance Division | Gregg Allen | Gregg.Allen@vdot.virginia.gov | (434) 426-5575 | John E Neblett | John.Neblett@VDOT.Virginia.gov | (434) 856-8202 | Brian Dunevant, P.E. | dunevbl@danvilleva.gov | (434) 799-5019 | 0 |  | 0 | FY2023 | 769051 | 769051 | NO DATES SET YET-PE OPEN | R | Determine Requirements milestone is 110 days past the expected completion date | G | Project is on budget | 2020-01-31 | 2019-08-01 | 2020-04-24 | 2019-08-23 | G | 2020-04-27 | 2019-08-26 | 2020-04-29 | 2019-08-28 | G | 2020-04-30 | 2019-08-29 | 2020-11-03 |  | R | [10 empty] | 2021-11-05 |  | 2021-11-30 |  | G | [5 empty] | 2021-12-02 |  | 2022-09-12 |  | G | 2020-12-14 | 2019-12-16 | 2021-08-17 | 2019-12-16 | G | [5 empty] | 2022-09-28 |  | 2022-10-26 |  | G | 2023-01-23 |  | 2023-01-23 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.073991
2639 | 113411 | WATERLOO HISTORIC BRIDGE - RTE 613 | 0613 | Secondary | Special Bridge | VDOT | Fauquier County | WARRENTON | Culpeper | NonMPO:NonMPO | Local Assistance Division | David S Pearce | David.Pearce@VDOT.Virginia.gov | (540) 829-7513 | Howard M Tomlinson | Howard.Tomlinson@VDOT.virginia.gov | (540) 829-7436 | Erin Kozanecki | erin.konanecki@fauquiercounty.gov | (540) 422-8363 | 0 |  | 0 | FY2020 | 3125000 | 5008427 | CONSTRUCTION STARTED | R | Start Delivery milestone finished 125 days late | R | Project estimate is less than $5M and is 20% or more over budget | 2018-07-16 | 2018-07-16 | 2018-10-23 | 2018-08-16 | G | 2018-10-24 | 2018-09-17 | 2018-11-06 | 2018-09-18 | G | 2018-11-07 | 2017-05-17 | 2019-10-04 | 2017-05-17 | G | [5 empty] | 2017-05-18 | 2017-05-18 | 2017-05-18 | 2017-05-18 | G | 2018-09-25 | 2018-10-16 | 2018-11-06 | 2018-10-16 | G | 2019-05-20 | 2019-02-08 | 2019-07-18 | 2019-04-10 | G | 2018-11-26 | 2018-10-19 | 2019-05-17 | 2019-02-08 | G | 2018-08-01 | 2018-10-22 | 2018-12-11 | 2018-10-22 | G | [5 empty] | 2019-02-12 | 2019-10-08 | 2019-02-12 | 2019-10-08 | R | 2019-08-13 | 2019-12-16 | 2019-08-13 | 2019-12-16 | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.11539
2640 | 113994 | SHOULDER RUMBLE STRIPS - DISTRICT WIDE | 9999 | Primary | Safety | VDOT | Stafford County | FREDERICKSBURG | Fredericksburg | NonMPO:NonMPO | Infrastructure Investment Division | Jessica Graves | Jessica.Graves@vdot.virginia.gov | (540) 899-4267 | Jessica Graves | Jessica.Graves@vdot.virginia.gov | (540) 899-4267 |  |  |  | 0 |  | 0 | FY2023 | 2015000 | 2015000 | NO DATES SET YET | G | Start Development milestone is 593 days ahead of the expected completion date | G | Project is on budget | [5 empty] | 2022-09-19 |  | 2022-10-07 |  | G | 2022-10-10 |  | 2023-01-25 |  | G | [5 empty] | 2023-02-07 |  | 2023-02-21 |  | G | [25 empty] | 2023-03-09 |  | 2023-03-15 |  | G | 2023-03-16 |  | 2023-03-22 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | WORK/TASK ORDER | 0 | 0 | 0.067564
2641 | 114620 | FRED EX - I95 EXPRESS LANES EXTENSION. EXIT 143 TO EXIT 133 | 0095 | Interstate | Reconstruction w/ Added Capacity | VDOT | Stafford County | FREDERICKSBURG | Fredericksburg | Fredericksburg:Stafford County | Infrastructure Investment Division | William Arel |  |  | William Arel | [5 empty] | 0 |  | 0 | FY2019 | 488200000 | 488200000 | CONSTRUCTION STARTED | G | Start Purchasing Right-of-Way milestone finished 110 days early | G | Project is on budget | [10 empty] | 2019-01-03 | 2017-06-01 | 2019-07-02 | 2019-04-18 | G | [10 empty] | 2019-10-16 | 2019-10-16 | 2020-03-02 | 2019-11-13 | G | 2020-03-03 | 2019-11-18 | 2022-03-03 |  | G | 2020-03-03 | 2019-11-18 | 2022-03-03 |  | G | 2019-04-19 | 2019-04-19 | 2020-06-30 | 2019-04-19 | G | [5 empty] | 2018-03-26 | 2018-03-26 | 2018-03-27 | 2018-03-27 | G | 2018-03-27 | 2018-03-27 | 2019-04-18 | 2019-04-18 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.085028
2642 | 115108 | South Alleghany Avenue - Primary Extension Paving |  | Urban | Resurfacing | Locally | Covington | LEXINGTON | Staunton | NonMPO:NonMPO | Local Assistance Division | Susan E Hammond | Susan.Hammond@VDOT.Virginia.gov | (540) 462-6990 | Jamison Brown | Jamison.Brown@vdot.virginia.gov | (540) 332-7389 | City of Covington | adressler@covington.va.us | (540) 965-6300 | 0 |  | 0 | FY2020 | 429000 | 429000 | AWARDED | G | Start Delivery milestone finished on-time | G | Project is on budget | 2019-08-01 | 2019-10-01 | 2019-10-25 | 2019-10-23 | G | [5 empty] | 2019-08-01 | 2019-10-01 | 2019-08-14 | 2019-10-14 | R | [35 empty] | 2019-11-08 | 2019-11-08 | 2019-12-10 | 2019-12-10 | G | 2020-03-04 | 2020-03-04 | 2020-03-04 | 2020-03-04 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.062471
2643 | 115355 | #SGR20LP - City of Virginia Beach 2020 Shore Dr | 0060 | Urban | Resurfacing | Locally | Virginia Beach | NORFOLK | Hampton Roads | Hampton Roads:Virginia Beach | Infrastructure Investment/Asset Management Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Marci Thompson | Marci.Thompson@vdot.virginia.gov | (757) 956-3093 | Jimmy Evans | jrevans@vbgov.com | (757) 385-1505 | 0 |  | 1 | FY2020 | 261581 | 261581 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 213 days early | G | Project is on budget | 2019-08-02 | 2019-07-03 | 2019-10-28 | 2019-08-07 | G | [5 empty] | 2019-10-29 | 2019-07-18 | 2019-12-12 | 2019-08-08 | G | [35 empty] | 2019-12-03 | 2019-08-23 | 2019-12-31 | 2019-09-20 | G | 2020-03-24 | 2019-09-20 | 2020-04-20 | 2019-09-20 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.065168
2644 | 115493 | RTE 311 - CONSTRUCT CONNECTOR ROAD | 0311 | Primary | New Construction Roadway | VDOT | Pittsylvania County | HALIFAX | Lynchburg | Danville:Pittsylvania County | Infrastructure Investment Division | Robert F Guercia | Robert.Guercia@VDOT.Virginia.gov | (434) 841-6864 | Raina A Rosado | Raina.Rosado@VDOT.Virginia.gov | (434) 856-8318 |  |  |  | 0 |  | 0 | FY2028 | 33456704 | 33456704 | NO DATES SET YET-PE OPEN | G | Start Development milestone finished 1413 days early | G | Project is on budget | [5 empty] | 2023-08-15 | 2019-10-02 | 2023-08-28 | 2019-10-15 | G | 2023-08-29 |  | 2024-10-07 |  | G | [5 empty] | 2025-10-06 |  | 2025-10-17 |  | G | 2027-01-13 |  | 2027-01-28 |  | G | 2027-06-23 |  | 2027-12-30 |  | G | 2027-02-16 |  | 2027-08-18 |  | G | 2026-07-06 |  | 2027-03-12 |  | G | [5 empty] | 2028-01-11 |  | 2028-01-11 |  | G | 2028-05-02 |  | 2028-05-02 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.14355
2645 | 115794 | #I81CIP CURVE IMPROVEMENTS - CHEVRONS (ID #28) | 0081 | Interstate | Safety | VDOT | Botetourt County | SALEM | Salem | NonMPO:NonMPO | Infrastructure Investment Division | Thomas W Digiulian | Thomas.DiGiulian@VDOT.Virginia.gov | (540) 387-5356 | Anne C Booker | Anne.Booker@VDOT.Virginia.gov | (540) 375-0143 |  |  |  | 0 |  | 0 | FY2020 | 489000 | 489000 | WAITING FINANCIAL CLOSURE | G | Obtained Permits milestone finished 155 days early | G | Project is on budget | [10 empty] | 2019-08-01 | 2019-08-01 | 2019-08-07 | 2019-08-01 | G | [25 empty] | 2019-08-01 | 2019-09-09 | 2020-02-11 | 2019-09-09 | G | [5 empty] | 2020-03-10 | 2019-08-23 | 2020-03-10 | 2019-08-23 | G | 2020-05-29 | 2019-08-26 | 2020-05-29 | 2019-08-26 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.13191
2646 | 117246 | I64 Corr Tech Adv-60, 143, 199 Signal Comm Cam - NN to Nw Kn | 0199 | Primary | Safety | VDOT | Williamsburg | WILLIAMSBURG | Hampton Roads | Hampton Roads:Williamsburg | Infrastructure Investment/Asset Management Division | Dwayne K Cook | Dwayne.Cook@VDOT.Virginia.gov | (757) 956-3014 | Jesse Alan Williams | Alan.Williams@vdot.virginia.gov | (757) 925-1574 |  |  |  | 0 |  | 0 | FY2021 | 750000 | 750000 | NO DATES SET YET-PE OPEN | Y | Determine Requirements milestone is 23 days ahead of the expected completion date and there is a risk of missing this milestone date | G | Project is on budget | [5 empty] | 2020-07-15 | 2020-05-14 | 2020-08-04 | 2020-05-21 | G | 2020-08-05 | 2020-05-22 | 2021-03-16 |  | Y | [5 empty] | 2021-03-17 |  | 2021-03-30 |  | G | [25 empty] | 2021-04-15 |  | 2021-04-21 |  | Y | 2021-04-22 |  | 2021-04-28 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | WORK/TASK ORDER | 0 | 0 | 0.12143
2647 | 118313 | UNIVERSITY BLVD EXTENSION (PROGRESS COURT TO DEVLIN ROAD) | 0840 | Secondary | New Construction Roadway | Locally | Prince William County | MANASSAS | Northern Virginia | Northern Virginia:Prince William County | Infrastructure Investment Division | Angel Tao | Angel.Tao@vdot.virginia.gov | (703) 259-2377 | Rhoderick M Undan | Rhoderick.Undan@vdot.virginia.gov | (703) 259-3347 | Paolo Belita |  | (703) 792-6273 | 0 |  | 0 | FY2029 | 28500000 | 28500000 | NO DATES SET YET | G | Agreement with Locality milestone is 1433 days ahead of the expected completion date | G | Project is on budget | 2024-07-01 |  | 2025-01-24 |  | G | 2025-01-27 |  | 2025-02-14 |  | G | 2025-02-18 |  | 2025-10-16 |  | G | [10 empty] | 2028-01-25 |  | 2028-02-29 |  | G | [5 empty] | 2028-03-01 |  | 2028-11-14 |  | G | 2025-11-10 |  | 2026-07-17 |  | G | [5 empty] | 2028-12-01 |  | 2029-01-31 |  | G | 2029-02-01 |  | 2029-03-29 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.39694
2648 | 688 | 13TH STREET IMPROVEMENTS |  | Urban | Reconstruction w/o Added Capacity | VDOT | Roanoke | SALEM | Salem | Roanoke:Roanoke City | Infrastructure Investment Division | Thomas W Digiulian | Thomas.DiGiulian@VDOT.Virginia.gov | (540) 387-5356 | Brian H Becker | Brian.Becker@VDOT.Virginia.gov | (540) 204-7959 | RK&K Engineers |  |  | 0 |  | 0 | FY2022 | 17235900 | 25034586 | ACTIVITY DATES SET | R | Relocate Utilities milestone is 118 days past the expected completion date | R | Project estimate is greater than $10M and is over budget by (a) 10% or more or (b) $5M or more | [5 empty] | 1988-01-13 | 1987-02-01 | 1988-01-17 | 1987-02-27 | G | 1990-12-03 | 1988-03-04 | 1999-09-30 | 1988-05-24 | G | [5 empty] | 2009-12-24 | 2009-12-24 | 2010-02-18 | 2010-02-18 | G | 1988-01-13 | 2010-09-01 | 1988-02-03 | 2010-09-14 | R | 2020-08-26 |  | 2020-10-26 |  | R | 2011-04-25 | 2011-04-25 | 2020-11-04 | 2013-11-22 | G | 2012-09-21 | 2012-09-21 | 2013-10-09 | 2013-10-09 | G | [5 empty] | 2020-11-10 |  | 2020-12-08 |  | R | 2021-02-18 |  | 2021-08-20 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 1 | 0.29657
2649 | 17537 | RTE 58 - CORRIDOR DEVELOPMENT PROG - 4 LANES (Vesta) | 0058 | Primary | Reconstruction w/ Added Capacity | VDOT | Patrick County | MARTINSVILLE | Salem | NonMPO:NonMPO | Infrastructure Investment Division | Robert P Williams | Robbie.Williams@VDOT.Virginia.gov | (276) 229-9954 | Brian H Becker | Brian.Becker@VDOT.Virginia.gov | (540) 204-7959 |  |  |  | 0 |  | 0 | FY2022 | 6715000 | 154000000 | ACTIVITY DATES SET | R | Obtained Permits milestone is 380 days past the expected completion date | R | Project estimate is between $5M and $10M and is a $1M or more over budget | [5 empty] | 1997-07-01 | 1997-07-07 | 1997-07-31 | 1997-07-08 | G | 1997-08-01 | 1997-01-28 | 1998-01-30 | 1997-04-26 | G | [5 empty] | 1998-12-03 | 1998-12-03 | 1998-12-17 | 1998-12-17 | G | 2000-01-17 | 2000-01-17 | 2000-01-19 | 2000-01-19 | G | 2001-04-17 | 2001-04-17 | 2020-12-14 |  | R | 2000-02-14 | 2000-02-14 | 2020-12-14 |  | R | 2018-02-09 |  | 2020-02-07 |  | R | [5 empty] | 2016-07-12 |  | 2021-12-06 |  | G | 2021-12-20 |  | 2022-01-19 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.14242
2650 | 114062 | BUS 501 - CONSTRUCT SIDEWALK (KEMPER STREET) | 0501 | Urban | Safety | Locally | Lynchburg | APPOMATTOX | Lynchburg | Lynchburg:Lynchburg | Infrastructure Investment Division | Gregg Allen | Gregg.Allen@vdot.virginia.gov | (434) 426-5575 | Gregg Allen | Gregg.Allen@vdot.virginia.gov | (434) 426-5575 | Lee Newland | lee.newland@lynchburgva.gov | (434) 455-3947 | 0 |  | 0 | FY2023 | 384272 | 384272 | NO DATES SET YET-PE OPEN | R | Determine Requirements milestone is 110 days past the expected completion date | G | Project is on budget | 2020-01-31 | 2019-07-18 | 2020-04-24 | 2019-08-12 | G | 2020-04-27 | 2020-04-27 | 2020-04-29 | 2020-04-29 | G | 2020-04-30 | 2020-04-30 | 2020-11-03 |  | R | [10 empty] | 2021-11-05 |  | 2021-11-30 |  | G | [5 empty] | 2021-12-02 |  | 2022-09-12 |  | G | 2020-12-14 |  | 2021-08-17 |  | G | [5 empty] | 2022-09-28 |  | 2022-10-26 |  | G | 2023-01-23 |  | 2023-01-23 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.19121
2651 | 114767 | PEDESTRIAN SIGNAL UPGRADES - CITY OF ROANOKE | 0011 | Primary | Safety | VDOT | Roanoke | SALEM | Salem | Roanoke:Roanoke City | Infrastructure Investment Division | Bernard S Grinnell | Sean.Grinnell@VDOT.Virginia.gov | (540) 375-0148 | Bernard S Grinnell | Sean.Grinnell@VDOT.Virginia.gov | (540) 375-0148 |  |  |  | 0 |  | 0 | FY2020 | 751000 | 751000 | CONSTRUCTION COMPLETED | R | Start Delivery milestone finished 6 days late | G | Project is on budget | [10 empty] | 2019-02-05 | 2019-02-05 | 2019-06-12 | 2019-07-22 | R | [35 empty] | 2019-09-12 | 2019-07-02 | 2019-09-18 | 2019-07-25 | G | 2019-09-19 | 2019-10-01 | 2019-09-25 | 2019-10-01 | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | WORK/TASK ORDER | 1 | 1 | 0.25749
2652 | 115130 | #SMART20 Rte. 340/522 Lighting Improvements | 0340 | Primary | Safety | VDOT | Warren County | EDINBURG | Staunton | NonMPO:NonMPO | Infrastructure Investment Division | Keith M Rider | Keith.Rider@VDOT.Virginia.gov | (434) 856-8145 | Kunal Kothawade | Kunal.Kothawade@vdot.virginia.gov | (540) 332-9259 |  |  |  | 1 | 2020 | 0 | FY2028 | 3149948 | 3149948 | NO DATES SET YET | G | Start Development milestone is 904 days ahead of the expected completion date | G | Project is on budget | [5 empty] | 2023-08-01 |  | 2023-08-14 |  | G | 2023-08-15 |  | 2024-07-12 |  | G | [5 empty] | 2025-05-19 |  | 2025-06-02 |  | G | 2026-09-04 |  | 2026-09-18 |  | G | 2027-02-19 |  | 2027-08-23 |  | G | 2026-10-06 |  | 2027-04-16 |  | G | 2026-02-26 |  | 2026-08-28 |  | G | [5 empty] | 2027-09-14 |  | 2027-09-14 |  | G | 2027-12-08 |  | 2027-12-08 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.063594
2653 | 115486 | #SMART20-Lee Hwy and Euclid Ave Roundabout (APP ID#3836) | 0011 | Urban | Safety | Locally | Bristol | ABINGDON | Bristol | Bristol:Bristol | Infrastructure Investment Division | Tabitha H Crowder | Tabitha.Crowder@vdot.virginia.gov | (276) 696-3482 | Kenneth R Plummer | KR.Plummer@VDOT.Virginia.gov | (276) 696-3261 | Jay Detrick | jdetrick@bristolva.org |  | 1 | 2020 | 0 | FY2027 | 2825000 | 2825000 | NO DATES SET YET | G | Agreement with Locality milestone is 1012 days ahead of the expected completion date | G | Project is on budget | 2023-09-01 |  | 2023-11-30 |  | G | 2023-12-01 |  | 2023-12-05 |  | G | 2023-12-06 |  | 2024-06-12 |  | G | [10 empty] | 2025-06-16 |  | 2025-07-07 |  | G | [5 empty] | 2025-07-09 |  | 2026-04-21 |  | G | 2024-07-19 |  | 2025-03-27 |  | G | [5 empty] | 2026-05-07 |  | 2026-06-04 |  | G | 2026-08-24 |  | 2026-08-24 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.10339
2654 | 115547 | #SMART20 - PICKETT TRAIL CONNECTOR | 0237 | Urban | Facilities for Pedestrians and Bicycles | Locally | Fairfax | FAIRFAX | Northern Virginia | Northern Virginia:Fairfax | Infrastructure Investment Division | Bud Siegel |  |  | Christer P Carshult | Christer.Carshult@vdot.virginia.gov | (703) 259-1765 | Wendy Block Sanford | wendy.sanford@fairfaxva.gov | (703) 385-7889 | 1 | 2020 | 0 | FY2028 | 5965444 | 5965444 | NO DATES SET YET-PE OPEN | G | Start Development milestone finished 1516 days early | G | Project is on budget | 2023-08-01 | 2018-07-05 | 2024-02-29 | 2019-10-15 | G | 2024-03-01 | 2020-01-23 | 2024-03-29 | 2020-02-03 | G | 2024-11-01 | 2020-06-01 | 2025-07-31 |  | G | [10 empty] | 2026-08-03 |  | 2026-08-31 |  | G | [5 empty] | 2026-09-02 |  | 2027-06-30 |  | G | 2024-11-08 |  | 2025-07-17 |  | G | [5 empty] | 2027-08-02 |  | 2027-11-30 |  | G | 2028-02-23 |  | 2028-06-30 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.20666
2655 | 117138 | St. Paul's Roadway Improvements (Phase I) | 8575 | Urban | Reconstruction w/ Added Capacity | Locally | Norfolk | NORFOLK | Hampton Roads | Hampton Roads:Norfolk | Local Assistance Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Derrick Williams | Derrick.Williams@vdot.virginia.gov | (757) 956-3097 | Robert Brown | robert.brown@norfolk.gov | (757) 664-7305 | 0 |  | 0 | FY2024 | 9538123 | 9538123 | NO DATES SET YET | G | Agreement with Locality milestone is 52 days ahead of the expected completion date | G | Project is on budget | 2020-12-03 |  | 2021-04-14 |  | G | 2021-04-15 |  | 2021-05-05 |  | G | 2021-06-04 |  | 2021-09-27 |  | G | [25 empty] | 2022-09-22 |  | 2023-02-28 |  | G | [5 empty] | 2023-04-26 |  | 2023-05-23 |  | G | 2023-08-11 |  | 2023-08-11 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.2379
2656 | 118171 | #SGR21LP - Pulaski FKEY 1142 Randolph Ave | 0000 | Urban | Resurfacing | Locally | Pulaski | CHRISTIANSBURG | Salem | NonMPO:NonMPO | Infrastructure Investment/Asset Management Division | Adam J Czesnowski | Adam.Czesnowski@vdot.virginia.gov | (540) 541-1216 | Adam J Czesnowski | Adam.Czesnowski@vdot.virginia.gov | (540) 541-1216 | Rick Tawney | rtawney@pulaskitown.org | (540) 994-8618 | 0 |  | 1 | FY2024 | 274341 | 274341 | NO DATES SET YET | G | Agreement with Locality milestone is 50 days ahead of the expected completion date | G | Project is on budget | 2020-12-01 |  | 2021-04-12 |  | G | 2021-04-13 |  | 2021-05-03 |  | G | 2021-11-08 |  | 2022-03-09 |  | G | [25 empty] | 2023-03-06 |  | 2023-08-01 |  | G | [5 empty] | 2023-09-28 |  | 2023-10-26 |  | G | 2024-01-23 |  | 2024-01-23 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.066536
2657 | 673 | RTE. 122 OVER GOOSE CREEK (STR. 02604) - BRIDGE REPLACEMENT | 0122 | Primary | Bridge Replacement w/o Added Capacity | VDOT | Bedford County | BEDFORD | Salem | NonMPO:NonMPO | Infrastructure Investment Division | Anthony T Marshall | Todd.Marshall@VDOT.Virginia.gov | (540) 387-5460 | Anthony L Handy | Tony.Handy@VDOT.Virginia.gov | (540) 352-9050 | Ian Johnston, P.E. - Clark Nexsen | IJohnston@ClarkNexsen.com | (757) 351-1205 | 0 |  | 0 | FY2019 | 13458812 | 12186948 | CONSTRUCTION STARTED | G | Start Delivery milestone finished on-time | G | Project is on budget | [5 empty] | 2010-05-28 | 2010-05-10 | 2010-05-28 | 2010-05-27 | G | 2012-06-15 | 2012-06-06 | 2016-05-13 | 2016-05-13 | G | [5 empty] | 2016-08-03 | 2016-08-03 | 2016-12-09 | 2016-12-09 | G | 2016-09-01 | 2016-09-01 | 2017-01-19 | 2017-01-19 | G | 2017-08-30 | 2017-08-30 | 2018-09-28 | 2018-09-20 | G | 2017-02-03 | 2017-02-03 | 2017-08-28 | 2017-08-28 | G | 2018-04-04 | 2018-04-04 | 2019-04-05 | 2018-08-29 | G | [5 empty] | 2018-09-10 | 2018-12-18 | 2018-10-09 | 2018-12-18 | R | 2018-11-28 | 2019-03-20 | 2019-03-20 | 2019-03-20 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.13592
2658 | 13551 | #SMART18 - RTE 360 WIDENING | 0360 | Primary | Safety | Locally | Hanover County | ASHLAND | Richmond | Richmond:Hanover County | Infrastructure Investment Division | Cynthia Crouch | Cynthia.Crouch@vdot.virginia.gov | (804) 609-5313 | Cynthia Crouch | Cynthia.Crouch@vdot.virginia.gov | (804) 609-5313 | Joe Vidunas | jevidunas@co.hanover.va.us | (804) 365-6176 | 1 | 2018 | 0 | FY2023 | 24184000 | 23952529 | ACTIVITY DATES SET | G | Complete Purchasing Right-of-Way milestone finished 21 days early | G | Project is on budget | [5 empty] | 1993-07-16 | 1993-07-01 | 1993-07-30 | 1994-01-11 | R | 1994-02-01 | 1994-03-07 | 1994-03-31 | 1999-10-29 | R | [5 empty] | 2017-12-07 | 2017-12-07 | 2018-01-19 | 2018-01-19 | G | 2007-07-18 | 2007-07-18 | 2007-07-18 | 2007-07-18 | G | [5 empty] | 2018-07-02 | 2018-03-27 | 2020-06-30 | 2020-06-09 | G | [10 empty] | 2022-07-15 |  | 2022-07-15 |  | G | 2022-08-31 |  | 2022-10-31 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.11831
2659 | 93093 | RTE 46 - BRIDGE REHAB OVER NOTTOWAY RIVER (FED ID 3583) | 0046 | Primary | Bridge Rehab w/o Added Capacity | VDOT | Brunswick County | SOUTH HILL | Richmond | NonMPO:NonMPO | Infrastructure Investment Division | Anthony S Haverly | Anthony.Haverly@vdot.virginia.gov | (804) 609-5225 | Anthony S Haverly | Anthony.Haverly@vdot.virginia.gov | (804) 609-5225 |  |  |  | 0 |  | 0 | FY2022 | 11900000 | 9913639 | ACTIVITY DATES SET | G | Relocate Utilities milestone finished 436 days early | G | Project is on budget | [5 empty] | 2011-07-01 | 2012-02-01 | 2011-07-01 | 2012-02-01 | R | 2012-05-17 | 2015-07-15 | 2018-06-29 | 2018-06-27 | G | [5 empty] | 2018-10-18 | 2018-10-18 | 2018-12-19 | 2018-12-17 | G | 2019-11-06 | 2019-09-26 | 2019-11-20 | 2019-11-06 | G | 2021-01-11 | 2020-03-18 | 2021-08-11 | 2020-06-01 | G | 2019-12-09 | 2019-11-21 | 2020-12-09 | 2019-11-21 | G | 2019-11-07 | 2019-11-07 | 2019-12-18 | 2019-11-07 | G | [5 empty] | 2021-09-14 |  | 2021-10-12 |  | G | 2021-12-01 |  | 2022-04-12 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.15505
2660 | 94725 | RTE. 603 OVER CRAIG BR. (STR. 12187) BRIDGE REPLACEMENT | 0603 | Secondary | Bridge Replacement w/o Added Capacity | VDOT | Montgomery County | CHRISTIANSBURG | Salem | NonMPO:NonMPO | Infrastructure Investment Division | Anthony T Marshall | Todd.Marshall@VDOT.Virginia.gov | (540) 387-5460 | Leslie T Repass | Todd.Repass@VDOT.Virginia.gov | (540) 381-7195 |  |  |  | 0 |  | 0 | FY2021 | 2354746 | 2354746 | CONSTRUCTION COMPLETED | G | Start Delivery milestone finished 32 days early | G | Project is on budget | [5 empty] | 2010-08-02 | 2010-05-27 | 2010-08-31 | 2010-05-27 | G | 2015-08-04 | 2015-07-01 | 2017-10-19 | 2017-10-19 | G | [5 empty] | 2017-08-24 | 2017-08-24 | 2017-10-19 | 2017-10-19 | G | 2018-09-10 | 2018-11-01 | 2018-09-28 | 2018-12-06 | R | 2018-10-22 | 2018-12-11 | 2020-03-09 | 2019-12-11 | G | 2018-10-22 | 2018-12-11 | 2020-03-09 | 2019-04-23 | G | 2018-07-23 | 2019-12-12 | 2020-03-09 | 2020-02-19 | G | [5 empty] | 2019-06-21 | 2019-06-21 | 2020-03-10 | 2020-03-10 | G | 2020-04-16 | 2020-05-29 | 2020-08-14 | 2020-07-13 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.061275
2661 | 100921 | #HB2.FY17 Longhill Rd Widening | 0612 | Secondary | Reconstruction w/ Added Capacity | VDOT | James City County | WILLIAMSBURG | Hampton Roads | Hampton Roads:James City County | Infrastructure Investment Division | Peter G Reilly | Peter.Reilly@vdot.virginia.gov | (757) 858-6748 | Caleb Parsons | Caleb.Parsons@vdot.virginia.gov | (757) 359-1203 | Paul Holt, James City County Planning Director | Paul.Holt@jamescitycountyva.gov | (757) 253-6685 | 1 | 2017 | 0 | FY2019 | 19800000 | 19795276 | CONSTRUCTION STARTED | R | Start Delivery milestone finished 238 days late | G | Project is on budget | [5 empty] | 2016-10-14 | 2016-08-16 | 2016-11-14 | 2016-08-24 | G | 2016-07-18 | 2016-07-11 | 2016-12-22 | 2016-12-22 | G | [5 empty] | 2016-12-14 | 2016-12-14 | 2017-01-23 | 2017-01-23 | G | 2017-10-12 | 2017-10-12 | 2017-10-19 | 2017-10-19 | G | 2018-09-20 | 2018-09-24 | 2019-09-20 | 2020-08-31 | R | 2017-12-20 | 2017-12-20 | 2018-09-19 | 2018-08-14 | G | 2016-09-13 | 2016-09-13 | 2016-09-14 | 2016-09-14 | G | [5 empty] | 2018-11-13 | 2019-04-09 | 2018-11-13 | 2019-04-09 | R | 2019-01-03 | 2019-09-18 | 2019-01-23 | 2019-09-18 | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 1 | 0.36655
2662 | 104774 | GRADE, DRAIN AND PAVE | 0649 | Secondary | Reconstruction w/o Added Capacity | VDOT | Dickenson County | WISE | Bristol | NonMPO:NonMPO | Infrastructure Investment Division | Tamara D Pritchard | Tamara.Pritchard@VDOT.Virginia.gov | (276) 696-3249 | Brandi Halloway | Brandi.Halloway@vdot.virginia.gov | (276) 696-3254 |  |  |  | 0 |  | 0 | FY2022 | 1098315 | 1244547 | ACTIVITY DATES SET | G | Start Purchasing Right-of-Way milestone finished 12 days early | Y | Project estimate is less than $5M and is up to 20% over budget | [5 empty] | 2018-07-02 | 2018-07-02 | 2018-07-16 | 2018-07-16 | G | 2018-07-17 | 2018-07-17 | 2019-05-06 | 2019-05-06 | G | [10 empty] | 2020-12-28 | 2020-11-02 | 2020-12-28 | 2020-12-16 | G | [20 empty] | 2021-11-09 |  | 2021-11-09 |  | G | 2021-12-29 |  | 2022-02-28 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.10657
2663 | 107535 | DOREY PARK - SHARED-USE PATH - TAP |  | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Henrico County | ASHLAND | Richmond | Richmond:Henrico County | Local Assistance Division | Jorg Huckabee-Mayfield | Jorg.Huckabee-Mayfield@VDOT.Virginia.gov | (804) 609-5292 | Jorg Huckabee-Mayfield | Jorg.Huckabee-Mayfield@VDOT.Virginia.gov | (804) 609-5292 | Conner Barnes, Henrico County | bar136@henrico.us | (804) 501-4244 | 0 |  | 0 | FY2019 | 284425 | 384268 | AWARDED | R | Start Delivery milestone finished 522 days late | R | Project estimate is less than $5M and is 20% or more over budget | 2015-10-01 | 2015-10-01 | 2015-12-30 | 2016-11-10 | R | 2015-12-31 | 2017-02-14 | 2016-01-14 | 2017-09-07 | R | 2016-01-19 | 2018-03-12 | 2016-09-08 | 2018-04-18 | R | [10 empty] | 2018-10-02 | 2018-10-02 | 2018-10-02 | 2018-10-02 | G | [20 empty] | 2019-01-29 | 2019-01-07 | 2019-02-21 | 2019-05-22 | R | 2019-02-22 | 2019-05-23 | 2019-02-22 | 2020-07-28 | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.43022
2664 | 108498 | ROUTE 50 SIDEWALK FROM WESTCOTT STREET TO ANNANDALE ROAD | 0050 | Primary | Safety | Locally | Fairfax County | FAIRFAX | Northern Virginia | Northern Virginia:Fairfax County | Infrastructure Investment Division | Amir Salahshoor | A.Salahshoor@VDOT.Virginia.gov | (703) 259-1957 | Rita Hockman | Rita.Hockman@vdot.virginia.gov | (804) 824-7421 | Vannak (Sam) Lim | Vannak.Lim@fairfaxcounty.gov | (703) 324-5458 | 0 |  | 0 | FY2021 | 1800001 | 1818622 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 731 days early | Y | Project estimate is less than $5M and is up to 20% over budget | 2015-03-06 | 2015-03-06 | 2015-05-29 | 2015-05-29 | G | 2015-06-01 | 2015-06-01 | 2015-06-03 | 2015-06-03 | G | 2015-06-04 | 2015-06-04 | 2015-12-10 | 2015-12-10 | G | [10 empty] | 2016-10-03 | 2016-10-03 | 2019-10-07 | 2016-10-03 | G | [5 empty] | 2019-10-07 | 2017-06-16 | 2019-10-07 | 2017-06-16 | G | [10 empty] | 2019-12-11 | 2018-06-02 | 2020-06-30 | 2018-07-02 | G | 2020-07-01 | 2018-07-03 | 2020-11-30 | 2018-11-30 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.077675
2665 | 108644 | RTE 651 (Belmont Rd, Whitepine-Courthouse) - RECONSTRUCTION | 0651 | Secondary | Reconstruction w/o Added Capacity | Locally | Chesterfield County | CHESTERFIELD | Richmond | Richmond:Chesterfield County | Local Assistance Division | Brian J Lokker | Brian.Lokker@VDOT.Virginia.gov | (804) 524-6010 | Brian J Lokker | Brian.Lokker@VDOT.Virginia.gov | (804) 524-6010 | Nate Mathis | mathisn@chesterfield.gov | (804) 748-1037 | 0 |  | 0 | FY2020 | 3618225 | 3638248 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 17 days early | Y | Project estimate is less than $5M and is up to 20% over budget | 2017-01-31 | 2016-10-07 | 2017-04-25 | 2016-10-07 | G | 2017-04-26 | 2016-10-12 | 2017-04-28 | 2016-10-12 | G | 2017-05-01 | 2017-05-01 | 2017-11-02 | 2017-09-15 | G | [10 empty] | 2018-08-29 | 2018-02-02 | 2018-09-19 | 2018-02-07 | G | [5 empty] | 2018-09-21 | 2018-02-08 | 2019-07-05 | 2018-09-25 | G | [10 empty] | 2019-07-23 | 2019-02-27 | 2019-08-19 | 2019-02-27 | G | 2019-08-20 | 2019-09-20 | 2019-12-02 | 2019-11-15 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.32123
2666 | 108800 | Citywide Systematic Replacement of Non-MUTCD Compliant Signs | 0000 | Urban | Safety | Locally | Portsmouth | NORFOLK | Hampton Roads | Hampton Roads:Portsmouth | Infrastructure Investment Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Marci Thompson | Marci.Thompson@vdot.virginia.gov | (757) 956-3093 | James Wright, P. E. | wrightj@portsmouthva.gov | (757) 393-8592 | 0 |  | 0 | FY2021 | 534517 | 626887 | ACTIVITY DATES SET | R | Solicit Bids milestone is 54 days past the expected completion date | Y | Project estimate is less than $5M and is up to 20% over budget | 2017-02-13 | 2017-02-13 | 2017-05-08 | 2017-05-08 | G | 2017-11-20 | 2017-11-20 | 2017-11-20 | 2017-11-20 | G | 2018-03-27 | 2018-03-27 | 2019-06-06 | 2019-06-06 | G | [25 empty] | 2020-07-13 | 2019-10-12 | 2020-10-27 | 2019-10-12 | G | [5 empty] | 2020-11-13 |  | 2020-12-29 |  | R | 2021-03-23 |  | 2021-06-15 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.19675
2667 | 109309 | #HB2.FY17 UNIVERSITY DRIVE EXTENSION | 9999 | Urban | New Construction Roadway | Locally | Fairfax | FAIRFAX | Northern Virginia | Northern Virginia:Fairfax | Infrastructure Investment Division | Amir Salahshoor | A.Salahshoor@VDOT.Virginia.gov | (703) 259-1957 | Robert J Strevell | Robert.Strevell@vdot.virginia.gov | (703) 259-1988 | Wendy Block Sanford | wendy.sanford@fairfaxva.gov | (703) 385-7889 | 1 | 2017 | 0 | FY2022 | 9994370 | 11577427 | ACTIVITY DATES SET | R | Complete Purchasing Right-of-Way milestone finished 213 days late | R | Project estimate is between $5M and $10M and is a $1M or more over budget | 2017-04-05 | 2017-04-05 | 2017-06-28 | 2017-08-08 | R | 2017-06-29 | 2017-08-09 | 2017-07-03 | 2017-08-10 | R | 2017-07-05 | 2017-08-11 | 2018-01-11 | 2018-08-24 | R | [10 empty] | 2019-05-02 | 2019-07-03 | 2019-06-28 | 2019-10-15 | R | [5 empty] | 2019-07-02 | 2019-10-16 | 2020-06-30 | 2021-01-29 | R | 2020-10-01 | 2020-10-09 | 2021-02-26 | 2020-10-09 | G | [5 empty] | 2021-03-01 |  | 2021-07-30 |  | G | 2021-08-02 |  | 2022-01-31 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.28909
2668 | 110008 | Pembroke Ave (3A) - Reconstruct C&G, sidewalk, crosswalks | 0351 | Urban | Reconstruction w/o Added Capacity | Locally | Hampton | WILLIAMSBURG | Hampton Roads | Hampton Roads:Hampton | Local Assistance Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Derrick Williams | Derrick.Williams@vdot.virginia.gov | (757) 956-3097 | Philippe Fenouil, P.E. | philippe.fenouli@hampton.gov | (757) 727-6197 | 0 |  | 0 | FY2020 | 1210355 | 1646200 | ACTIVITY DATES SET | R | Solicit Bids milestone is 355 days past the expected completion date | R | Project estimate is less than $5M and is 20% or more over budget | 2016-12-13 | 2016-12-13 | 2017-02-14 | 2017-02-14 | G | 2017-03-21 | 2017-03-21 | 2017-03-27 | 2017-03-27 | G | 2017-03-28 | 2017-03-28 | 2018-08-17 | 2018-06-06 | G | [10 empty] | 2018-12-27 | 2019-01-17 | 2019-01-17 | 2019-01-17 | G | [5 empty] | 2019-01-23 | 2019-01-17 | 2019-11-06 | 2019-01-17 | G | [10 empty] | 2020-01-21 |  | 2020-03-03 |  | R | 2020-03-04 |  | 2020-04-13 |  | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.15483
2669 | 111086 | City of Suffolk Citywide Signal System Upgrade | 0000 | Urban | Safety | Locally | Suffolk | NORFOLK | Hampton Roads | Hampton Roads:Suffolk | Infrastructure Investment Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Johndel A Alcaide | John.Alcaide@vdot.virginia.gov | (757) 956-3098 | Robert Lewis | relewis@suffolkva.us | (757) 514-7603 | 0 |  | 0 | FY2026 | 2650000 | 2650000 | NO DATES SET YET | G | Agreement with Locality milestone is 947 days ahead of the expected completion date | Y | Estimate not current | 2023-07-03 |  | 2023-09-26 |  | G | 2023-09-27 |  | 2023-10-10 |  | G | 2023-10-11 |  | 2024-09-26 |  | G | [25 empty] | 2024-05-29 |  | 2025-02-04 |  | G | [5 empty] | 2025-08-08 |  | 2025-09-05 |  | G | 2025-09-08 |  | 2026-03-05 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.17159
2670 | 100200 | #SMART18 - SKIFFES CREEK CONNECTOR | 0060 | Primary | New Construction Roadway | VDOT | James City County | WILLIAMSBURG | Hampton Roads | Hampton Roads:James City County | Infrastructure Investment Division | Bruce L Duvall | Bruce.Duvall@VDOT.Virginia.gov | (757) 956-3054 | Wali Zaman | Wali.Zaman@VDOT.Virginia.gov | (757) 956-3272 | Paul Holt | steven.hicks@james-city.va.us | (757) 253-6671 | 1 | 2018 | 0 | FY2020 | 50503700 | 50503700 | CONSTRUCTION STARTED | G | Start Delivery milestone finished on-time | G | Project is on budget | [5 empty] | 2012-02-03 | 2011-06-28 | 2011-08-01 | 2011-06-29 | G | 2018-12-24 | 2011-06-28 | 2019-11-01 | 2019-06-07 | G | [10 empty] | 2019-07-19 | 2019-07-19 | 2019-08-01 | 2019-08-01 | G | [20 empty] | 2019-07-19 | 2019-07-19 | 2019-08-01 | 2019-08-01 | G | 2019-08-02 | 2019-08-02 | 2019-08-02 | 2019-08-02 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | DESIGN BUILD/PPTA | 1 | 1 | 0.28356
2671 | 101305 | HIRST ROAD - SAFETY IMPROVEMENTS | 0000 | Urban | Reconstruction w/o Added Capacity | Locally | Purcellville | LEESBURG | Northern Virginia | Northern Virginia:Purcellville | Local Assistance Division | Jan S Vaughan | Jan.Vaughan@VDOT.Virginia.gov | (703) 259-2425 | Rita Hockman | Rita.Hockman@vdot.virginia.gov | (804) 824-7421 | Dale Lehnig | dlehnig@purcellvilleva.gov | (540) 751-2314 | 0 |  | 0 | FY2020 | 790000 | 1090446 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 213 days early | R | Project estimate is less than $5M and is 20% or more over budget | 2011-09-16 | 2011-09-16 | 2011-09-16 | 2011-09-16 | G | 2011-07-01 | 2011-07-01 | 2011-07-01 | 2011-07-01 | G | 2012-01-03 | 2012-01-02 | 2012-01-09 | 2012-01-09 | G | [10 empty] | 2018-05-30 | 2018-05-30 | 2018-06-29 | 2018-06-29 | G | [20 empty] | 2019-04-01 | 2019-04-01 | 2019-07-15 | 2019-05-03 | G | 2019-10-01 | 2019-06-04 | 2020-01-03 | 2019-06-04 | G | Final design is still underway | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.32077
2672 | 105753 | #HB2.FY17 WIDEN RTE. 11 (2 TO 4 LANES) | 0011 | Urban | Reconstruction w/ Added Capacity | Locally | Bristol | ABINGDON | Bristol | Bristol:Bristol | Local Assistance Division | Tabitha H Crowder | Tabitha.Crowder@vdot.virginia.gov | (276) 696-3482 | Tabitha H Crowder | Tabitha.Crowder@vdot.virginia.gov | (276) 696-3482 | Joseph.Daft | Joseph.Daft@bristolva.org | (276) 645-7247 | 1 | 2017 | 0 | FY2018 | 9987500 | 9987500 | CONSTRUCTION STARTED | G | Start Delivery milestone finished on-time | G | Project is on budget | 2016-04-11 | 2016-04-11 | 2016-09-24 | 2016-09-24 | G | 2016-07-06 | 2016-07-06 | 2016-08-01 | 2016-07-28 | G | 2016-07-06 | 2016-07-06 | 2016-12-01 | 2016-12-01 | G | [10 empty] | 2016-12-01 | 2016-12-01 | 2017-02-09 | 2017-02-09 | G | [5 empty] | 2017-02-10 | 2017-02-10 | 2017-07-27 | 2017-07-27 | G | [10 empty] | 2017-08-29 | 2017-08-29 | 2017-08-29 | 2017-08-29 | G | 2017-08-29 | 2017-08-29 | 2017-10-16 | 2017-10-16 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.13338
2673 | 108497 | ROUTE 50 SIDEWALK FROM WOODLAWN AVE TO CHURCH PARKING LOT | 0050 | Primary | Safety | Locally | Fairfax County | FAIRFAX | Northern Virginia | Northern Virginia:Fairfax County | Infrastructure Investment Division | Amir Salahshoor | A.Salahshoor@VDOT.Virginia.gov | (703) 259-1957 | Rita Hockman | Rita.Hockman@vdot.virginia.gov | (804) 824-7421 | Jeanmarie Roberson | Jeanmarie.Roberson@fairfaxcounty.gov | (703) 877-5740 | 0 |  | 0 | FY2020 | 400001 | 309975 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 662 days early | G | Project is on budget | 2014-09-25 | 2014-09-25 | 2014-12-23 | 2014-12-23 | G | 2014-12-24 | 2014-12-24 | 2014-12-29 | 2014-12-29 | G | 2014-12-30 | 2014-12-30 | 2015-07-07 | 2015-07-07 | G | [10 empty] | 2016-05-02 | 2016-05-02 | 2016-08-24 | 2016-08-24 | G | [5 empty] | 2016-10-31 | 2016-10-31 | 2019-11-14 | 2017-06-05 | G | [10 empty] | 2019-12-04 | 2017-11-17 | 2020-01-02 | 2017-11-17 | G | 2020-01-03 | 2017-11-20 | 2020-02-14 | 2018-04-23 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.075804
2674 | 108633 | Sidewalk improvements adjacent to Tobacco Heritage Trail |  | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Lawrenceville | SOUTH HILL | Richmond | NonMPO:NonMPO | Local Assistance Division | Jorg Huckabee-Mayfield | Jorg.Huckabee-Mayfield@VDOT.Virginia.gov | (804) 609-5292 | Jorg Huckabee-Mayfield | Jorg.Huckabee-Mayfield@VDOT.Virginia.gov | (804) 609-5292 | Ashleigh Zincone | azincone@southsidepdc.org | (434) 447-7101 | 0 |  | 0 | FY2021 | 345002 | 345000 | ADVERTISED | R | Start Delivery milestone is 146 days past the expected completion date | G | Project is on budget | 2018-01-30 | 2017-11-06 | 2018-04-24 | 2017-12-13 | G | 2018-04-25 | 2018-01-03 | 2018-04-27 | 2018-01-09 | G | 2018-04-30 | 2018-01-10 | 2018-11-01 | 2018-01-31 | G | [10 empty] | 2019-07-18 | 2019-07-18 | 2019-09-18 | 2019-07-18 | G | [5 empty] | 2019-09-20 | 2019-07-18 | 2020-07-02 | 2019-07-18 | G | 2019-07-12 | 2019-08-27 | 2020-06-15 | 2019-08-27 | G | [5 empty] | 2020-07-21 | 2020-06-18 | 2020-08-17 | 2020-06-18 | G | 2020-08-18 |  | 2020-09-28 |  | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.34773
2675 | 108747 | STRUCTURAL REHABILITATION OF ASPHALT CONCRETE - VAR. RTES. | 9999 | Secondary | Restoration and Rehabilitation | VDOT | Wise County | WISE | Bristol | NonMPO:NonMPO | Local Assistance Division | Allan D Sumpter | Allan.Sumpter@VDOT.virginia.gov | (276) 525-6461 | Brandon C Bennett | Brandon.Bennett@VDOT.Virginia.gov | (276) 321-6453 |  |  |  | 0 |  | 0 | FY2019 | 450852 | 450852 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished on-time | G | Project is on budget | [5 empty] | 2017-05-01 | 2017-05-01 | 2017-05-12 | 2017-05-12 | G | 2017-05-15 | 2017-05-15 | 2018-01-08 | 2018-01-08 | G | [5 empty] | 2018-01-18 | 2018-01-18 | 2018-01-18 | 2018-01-18 | G | [5 empty] | 2017-12-04 | 2017-12-04 | 2017-12-04 | 2017-12-04 | G | [5 empty] | 2018-02-02 | 2018-02-26 | 2018-03-02 | 2018-02-26 | G | [5 empty] | 2018-06-12 | 2018-06-12 | 2018-06-12 | 2018-06-12 | G | 2018-08-02 | 2018-08-22 | 2018-08-22 | 2018-08-22 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | SAAP CONTRACT | 1 | 0 | 0.18525
2677 | 109314 | #HB2.FY17 NIKE PARK RD EXTENSION FROM REYNOLDS DR TO RTE 17 | 0669 | Secondary | New Construction Roadway | VDOT | Isle of Wight County | FRANKLIN | Hampton Roads | Hampton Roads:Isle of Wight County | Infrastructure Investment Division | Charles T Catlett | Tommy.Catlett@vdot.virginia.gov | (757) 346-3078 | Wali Zaman | Wali.Zaman@VDOT.Virginia.gov | (757) 956-3272 | Charles Catlett |  |  | 1 | 2017 | 0 | FY2024 | 11658000 | 12823800 | ACTIVITY DATES SET | R | Engage Public milestone is 104 days past the expected completion date | Y | Project estimate is greater than $10M and is over budget by (a) up to 10% or (b) up to $5M | [5 empty] | 2016-09-07 | 2016-09-07 | 2016-10-26 | 2016-10-24 | G | 2016-10-25 | 2016-10-25 | 2017-06-06 | 2020-03-10 | R | [5 empty] | 2020-09-14 |  | 2020-11-09 |  | R | 2021-12-02 |  | 2022-02-01 |  | G | 2022-08-23 |  | 2023-08-09 |  | G | 2022-02-17 |  | 2022-08-08 |  | G | 2016-11-30 | 2016-11-30 | 2020-12-08 |  | R | [5 empty] | 2023-10-10 |  | 2023-10-10 |  | G | 2023-11-28 |  | 2023-12-18 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 1 | 0.27323
2678 | 110335 | #HB2.FY17 DOWNTOWN POA - N MAPLE & LITTLE FALLS ST SIDEWALK | 9999 | Urban | Facilities for Pedestrians and Bicycles | Locally | Falls Church | FAIRFAX | Northern Virginia | Northern Virginia:Falls Church | Infrastructure Investment Division | Amir Salahshoor | A.Salahshoor@VDOT.Virginia.gov | (703) 259-1957 | Christer P Carshult | Christer.Carshult@vdot.virginia.gov | (703) 259-1765 | Alireza Khavari | akhavari@fallschurchva.gov | (703) 248-5394 | 1 | 2017 | 0 | FY2020 | 800000 | 800000 | ACTIVITY DATES SET | R | Start Purchasing Right-of-Way milestone is 746 days past the expected completion date | G | Project is on budget | 2017-04-07 | 2016-12-13 | 2017-06-30 | 2017-02-15 | G | 2017-07-03 | 2017-07-04 | 2017-07-06 | 2017-07-07 | R | 2017-07-07 | 2017-07-10 | 2018-01-17 | 2018-01-17 | G | [10 empty] | 2019-01-15 |  | 2019-02-06 |  | R | [5 empty] | 2019-02-08 |  | 2019-11-15 |  | R | [10 empty] | 2019-12-05 |  | 2020-01-03 |  | R | 2020-01-06 |  | 2020-02-18 |  | R | Delay due to changes in scope of work, project management, plan designs, or resolution of public comments | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.29994
2679 | 111106 | RTE 250 SIDEWALK - DOMINION BLVD TO SPRINGFIELD RD | 0250 | Primary | Safety | VDOT | Henrico County | ASHLAND | Richmond | Richmond:Henrico County | Infrastructure Investment Division | Roy Soto | Roy.Soto@vdot.virginia.gov | (804) 609-5239 | Roy Soto | Roy.Soto@vdot.virginia.gov | (804) 609-5239 |  |  |  | 0 |  | 0 | FY2022 | 2248000 | 2248000 | ACTIVITY DATES SET | R | Start Purchasing Right-of-Way milestone finished 128 days late | G | Project is on budget | [5 empty] | 2017-10-02 | 2017-08-16 | 2017-10-13 | 2017-08-22 | G | 2017-10-17 | 2017-08-23 | 2018-09-13 | 2018-09-11 | G | [5 empty] | 2019-04-18 | 2019-02-21 | 2019-05-01 | 2019-04-18 | G | 2020-04-28 | 2020-09-18 | 2020-05-19 | 2020-09-24 | R | 2021-02-18 |  | 2021-09-07 |  | G | 2020-06-05 | 2021-01-05 | 2021-03-11 |  | Y | 2019-08-21 | 2019-08-21 | 2021-03-10 | 2019-08-21 | G | [5 empty] | 2021-11-09 |  | 2021-11-15 |  | G | 2022-01-10 |  | 2022-05-06 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.072563
2680 | 111287 | #SGR18VB - RT 30 OVER N ANNA REHAB, HANOVER STR9378(CN ONLY) | 0030 | Primary | Bridge Rehab w/o Added Capacity | VDOT | Hanover County | ASHLAND | Richmond | Richmond:Hanover County | Infrastructure Investment/Asset Management Division | Warren T Hall | Warren.Hall@vdot.virginia.gov | (804) 337-1446 | Lawrence Ramsey | Brian.Ramsey@VDOT.Virginia.gov | (804) 585-3579 |  |  |  | 0 |  | 1 | FY2021 | 3000000 | 3000000 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 177 days early | G | Project is on budget | [10 empty] | 2021-08-05 | 2018-09-27 | 2021-08-18 | 2019-07-11 | G | [35 empty] | 2020-07-14 | 2020-05-05 | 2020-07-14 | 2020-05-05 | G | 2020-10-02 | 2020-07-21 | 2021-01-14 | 2020-07-21 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 1 | 0 | 0.10067
2681 | 111483 | #SMART18 - BROAD STREET MULTIMODAL IMPROVEMENTS | 0007 | Primary | Reconstruction w/o Added Capacity | Locally | Falls Church | FAIRFAX | Northern Virginia | Northern Virginia:Falls Church | Infrastructure Investment Division | Amir Salahshoor | A.Salahshoor@VDOT.Virginia.gov | (703) 259-1957 | Rhoderick M Undan | Rhoderick.Undan@vdot.virginia.gov | (703) 259-3347 | Susan Long | slong@fallschurchva.gov | (571) 651-0133 | 1 | 2018 | 0 | FY2021 | 3000000 | 3220000 | NO DATES SET YET-PE OPEN | R | Determine Requirements milestone is 839 days past the expected completion date | Y | Project estimate is less than $5M and is up to 20% over budget | 2017-07-03 | 2017-05-11 | 2018-01-31 | 2017-08-04 | G | 2018-02-01 | 2017-09-22 | 2018-02-05 | 2018-01-11 | G | 2018-02-06 | 2020-02-28 | 2018-11-05 |  | R | [10 empty] | 2019-08-02 |  | 2019-09-03 |  | R | [5 empty] | 2019-09-05 |  | 2020-09-01 |  | R | [10 empty] | 2021-02-01 |  | 2021-02-01 |  | R | 2021-02-02 |  | 2021-05-03 |  | G | Delay due to changes in scope of work, project management, plan designs, or resolution of public comments | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.22625
2682 | 111635 | #SMART18 - RT 106 & RT 630 INTERSECTION SAFETY PROJECT | 0106 | Primary | Safety | VDOT | Prince George County | PETERSBURG | Richmond | Tri-Cities:Prince George County | Infrastructure Investment Division | Ronald Svejkovsky |  |  | William Wheeler | William.Wheeler@vdot.virginia.gov | (804) 609-5280 |  |  |  | 1 | 2018 | 0 | FY2023 | 5755853 | 5755853 | ACTIVITY DATES SET | Y | Complete Purchasing Right-of-Way milestone is 44 days ahead of the expected completion date and there is a risk of missing this milestone date | G | Project is on budget | [5 empty] | 2018-07-02 | 2018-06-21 | 2018-07-16 | 2018-06-25 | G | 2018-07-17 | 2018-07-16 | 2018-12-11 | 2018-12-07 | G | [5 empty] | 2019-01-04 | 2019-01-04 | 2019-03-05 | 2019-03-05 | G | 2020-04-02 | 2020-04-10 | 2020-05-28 | 2020-05-12 | G | 2021-05-10 |  | 2022-05-10 |  | G | 2020-06-29 | 2020-07-02 | 2021-04-06 |  | Y | [10 empty] | 2022-07-12 |  | 2022-07-12 |  | G | 2022-08-25 |  | 2022-12-29 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.06731
2684 | 113193 | Chesapeake Boulevard Reconstruction | 9999 | Urban | Reconstruction w/o Added Capacity | Locally | Norfolk | NORFOLK | Hampton Roads | Hampton Roads:Norfolk | Local Assistance Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | Derrick Williams | Derrick.Williams@vdot.virginia.gov | (757) 956-3097 | Deborah A. Mangiaracina, P. E. | Deborah.Mangiaracina@norfolk.gov | (757) 664-7459 | 0 |  | 0 | FY2022 | 2850000 | 2850000 | ACTIVITY DATES SET | R | Determine Requirements milestone finished 62 days late | G | Project is on budget | 2019-09-06 | 2019-09-06 | 2019-12-04 | 2020-02-03 | R | 2019-12-05 | 2020-02-04 | 2019-12-09 | 2020-02-18 | R | 2019-12-10 | 2020-02-19 | 2020-06-16 | 2020-08-17 | R | [25 empty] | 2020-05-18 | 2020-05-18 | 2021-01-25 | 2020-05-18 | G | [5 empty] | 2021-06-29 |  | 2021-08-10 |  | G | 2021-08-11 |  | 2022-02-07 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.13715
2685 | 113880 | #SGR19LB??- Taz Av Beaver Pond Ck Bluefield VA 8002 Fed 2242 | 0000 | Urban | Bridge Rehab w/o Added Capacity | VDOT | Bluefield | LEBANON | Bristol | NonMPO:NonMPO | Infrastructure Investment/Asset Management Division | Gary Lester |  |  | John E Sproles | John.Sproles@VDOT.Virginia.gov | (276) 696-3391 |  |  |  | 0 |  | 1 | FY2021 | 3628042 | 1236429 | ADVERTISED | G | Solicit Bids milestone finished on-time | G | Project is on budget | [5 empty] | 2020-01-13 | 2018-10-01 | 2020-01-28 | 2018-12-03 | G | 2020-01-29 | 2018-12-04 | 2020-04-22 | 2019-09-05 | G | [35 empty] | 2021-01-12 | 2021-01-12 | 2021-01-12 | 2021-01-12 | G | 2021-04-06 |  | 2021-04-06 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.14522
2686 | 115129 | #SMART20 I-81 Exit 291 Northbound Ramp Widening | 0081 | Interstate | Reconstruction w/ Added Capacity | VDOT | Shenandoah County | EDINBURG | Staunton | NonMPO:NonMPO | Infrastructure Investment Division | Randolph S Kiser | Randy.Kiser@VDOT.Virginia.gov | (540) 332-9092 | Ronald L Tabor | Ronald.Tabor@vdot.virginia.gov | (540) 332-7887 |  |  |  | 1 | 2020 | 0 | FY2028 | 781701 | 781701 | NO DATES SET YET | G | Start Development milestone is 904 days ahead of the expected completion date | G | Project is on budget | [5 empty] | 2023-08-01 |  | 2023-08-14 |  | G | 2023-08-15 |  | 2024-07-12 |  | G | [5 empty] | 2025-05-19 |  | 2025-06-02 |  | G | 2026-09-04 |  | 2026-09-18 |  | G | 2027-02-19 |  | 2027-08-23 |  | G | 2026-10-06 |  | 2027-04-16 |  | G | 2026-02-26 |  | 2026-08-28 |  | G | [5 empty] | 2027-09-14 |  | 2027-09-14 |  | G | 2027-12-08 |  | 2027-12-08 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.061967
2687 | 115953 | Town of Cape Charles- Multi-Use Trails, Phase IV | 0000 | Enhancement | Facilities for Pedestrians and Bicycles | VDOT | Cape Charles | ACCOMAC | Hampton Roads | NonMPO:NonMPO | Local Assistance Division | Sonya A Hallums-Ponton | Sonya.Hallums-Ponton@VDOT.Virginia.gov | (757) 956-3091 | John G Harman | JohnG.Harman@vdot.virginia.gov | (757) 956-3269 | Bob Panek | bob.panek@capecharles.org | (757) 331-3259 | 0 |  | 0 | FY2022 | 1281619 | 1281619 | NO DATES SET YET | R | Start Development milestone is 517 days past the expected completion date | G | Project is on budget | [5 empty] | 2019-09-03 |  | 2019-09-23 |  | R | 2019-09-24 |  | 2020-07-28 |  | R | [5 empty] | 2021-03-03 |  | 2021-03-30 |  | G | [5 empty] | 2021-11-18 |  | 2022-03-25 |  | G | [5 empty] | 2021-08-11 |  | 2022-01-13 |  | G | [5 empty] | 2022-04-12 |  | 2022-04-12 |  | G | 2022-06-30 |  | 2022-06-30 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.31504
2688 | 116630 | NOVA SYSTEMIC FLASHING YELLOW ARROWS PH3 | 9999 | Miscellaneous | Safety | VDOT | Northern Virginia District-wide |  | Northern Virginia | Northern Virginia:Northern Virginia District-wide | Infrastructure Investment/Asset Management Division | Waqar A Siddiqui | Sid.Siddiqui@VDOT.Virginia.gov | (703) 259-3225 | Tienjung Ho | Tien-Jung.Ho@VDOT.Virginia.gov | (703) 259-2752 |  |  |  | 0 |  | 0 | FY2021 | 4200000 | 4200000 | CONSTRUCTION STARTED | G | Start Delivery milestone finished 7 days early | G | Project is on budget | [5 empty] | 2020-10-30 | 2020-05-06 | 2020-11-05 | 2020-05-16 | G | 2020-11-06 | 2020-05-18 | 2020-12-22 | 2020-11-20 | G | [5 empty] | 2020-11-20 | 2020-11-20 | 2020-11-20 | 2020-11-20 | G | [25 empty] | 2021-01-26 | 2021-01-26 | 2021-01-29 | 2021-01-27 | G | 2021-02-01 | 2021-01-27 | 2021-02-04 | 2021-01-28 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | WORK/TASK ORDER | 1 | 0 | 0.067886
2689 | 117094 | #REVSH21 RTE 501 - PIPE JACKING AT WHITE OAK DRIVE | 0501 | Urban | Other | Locally | South Boston | HALIFAX | Lynchburg | NonMPO:NonMPO | Local Assistance Division | Gregg Allen | Gregg.Allen@vdot.virginia.gov | (434) 426-5575 | Gregg Allen | Gregg.Allen@vdot.virginia.gov | (434) 426-5575 | CW CROWDER | cwcrowder@southbostonva.us | (434) 575-4261 | 0 |  | 0 | FY2025 | 189968 | 189968 | NO DATES SET YET | G | Agreement with Locality milestone is 106 days ahead of the expected completion date | G | Project is on budget | 2021-01-29 |  | 2021-06-07 |  | G | 2021-06-08 |  | 2021-06-28 |  | G | 2022-01-07 |  | 2022-05-03 |  | G | [10 empty] | 2023-08-22 |  | 2023-09-26 |  | G | [5 empty] | 2023-09-27 |  | 2024-03-04 |  | G | 2024-01-30 |  | 2024-06-26 |  | G | [5 empty] | 2024-06-05 |  | 2024-07-02 |  | G | 2024-09-20 |  | 2024-09-20 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.094936
2690 | 111305 | #SMART18 - RTE 750 - TURN LANE, ACCESS MANAGEMENT AT RTE 844 | 0750 | Secondary | Safety | VDOT | Pittsylvania County | HALIFAX | Lynchburg | Danville:Pittsylvania County | Infrastructure Investment Division | Brian J Casto | Brian.Casto@VDOT.Virginia.gov | (434) 856-8276 | Laura J Walton | Laura.Walton@VDOT.Virginia.gov | (434) 856-8286 |  |  |  | 1 | 2018 | 0 | FY2023 | 1083903 | 1083903 | ACTIVITY DATES SET | G | Engage Public milestone finished 37 days early | G | Project is on budget | [5 empty] | 2019-07-15 | 2019-06-25 | 2019-07-26 | 2019-06-28 | G | 2019-07-29 | 2019-07-01 | 2020-01-23 | 2020-11-30 | R | [5 empty] | 2021-02-11 | 2021-01-19 | 2021-02-25 | 2021-01-19 | G | 2021-04-02 |  | 2021-04-15 |  | G | 2022-11-04 |  | 2023-05-04 |  | G | 2021-05-03 |  | 2022-11-03 |  | G | 2021-03-22 |  | 2021-09-22 |  | G | [5 empty] | 2023-05-09 |  | 2023-05-09 |  | G | 2023-05-11 |  | 2023-06-08 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.10687
2691 | 111535 | CITY OF FAIRFAX PRIMARY EXTENSION PAVING FY18 - RTE 236WB | 0236 | Urban | Resurfacing | Locally | Fairfax | FAIRFAX | Northern Virginia | Northern Virginia:Fairfax | Local Assistance Division | Amir Salahshoor | A.Salahshoor@VDOT.Virginia.gov | (703) 259-1957 | Rita Hockman | Rita.Hockman@vdot.virginia.gov | (804) 824-7421 | Peter Millard | peter.millard@fairfaxva.gov | (703) 246-6330 | 0 |  | 0 | FY2019 | 117342 | 117342 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 140 days early | G | Project is on budget | 2017-07-03 | 2017-07-03 | 2017-10-25 | 2017-07-28 | G | [5 empty] | 2017-07-03 | 2017-11-09 | 2017-07-17 | 2017-12-12 | R | [35 empty] | 2017-12-13 | 2017-12-13 | 2018-06-29 | 2018-03-21 | G | 2018-07-02 | 2018-03-23 | 2018-08-10 | 2018-03-23 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.17517
2692 | 111716 | #SMART18 - RICHMOND-HENRICO TURNPIKE -- SOUTH SGMT | 7609 | Secondary | Reconstruction w/ Added Capacity | Locally | Henrico County | ASHLAND | Richmond | Richmond:Henrico County | Infrastructure Investment Division | Cynthia Crouch | Cynthia.Crouch@vdot.virginia.gov | (804) 609-5313 | Cynthia Crouch | Cynthia.Crouch@vdot.virginia.gov | (804) 609-5313 | Michael Aust | AUS019@henrico.us | (804) 501-4019 | 1 | 2018 | 0 | FY2023 | 18642000 | 18642000 | ACTIVITY DATES SET | R | Engage Public milestone is 10 days past the expected completion date | G | Project is on budget | 2017-09-05 | 2017-07-10 | 2017-12-01 | 2017-11-21 | G | 2017-12-04 | 2017-11-15 | 2017-12-06 | 2017-11-27 | G | 2017-12-07 | 2018-11-30 | 2018-12-07 | 2018-12-06 | G | [5 empty] | 2020-03-12 | 2020-03-12 | 2021-02-11 |  | R | 2021-02-02 |  | 2021-02-23 |  | Y | 2022-05-03 |  | 2022-10-18 |  | G | 2021-02-25 |  | 2022-05-31 |  | G | 2022-03-08 |  | 2022-09-08 |  | G | [5 empty] | 2022-06-16 |  | 2022-11-08 |  | G | 2023-02-01 |  | 2023-03-14 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.3403
2693 | 112051 | I-195 - SAFETY IMPROVEMENTS | 0195 | Interstate | Safety | VDOT | Richmond | ASHLAND | Richmond | Richmond:Richmond | Infrastructure Investment Division | Clayton M Thomas | Clay.Thomas@VDOT.Virginia.gov | (804) 609-5429 | Clayton M Thomas | Clay.Thomas@VDOT.Virginia.gov | (804) 609-5429 |  |  |  | 0 |  | 0 | FY2020 | 1464250 | 1464250 | ADVERTISED | R | Start Delivery milestone is 237 days past the expected completion date | G | Project is on budget | [5 empty] | 2018-01-19 | 2018-01-19 | 2018-01-22 | 2018-01-22 | G | 2018-01-19 | 2018-01-19 | 2018-11-20 | 2018-11-20 | G | [5 empty] | 2019-02-26 | 2019-02-26 | 2019-03-25 | 2019-03-21 | G | [5 empty] | 2019-05-03 | 2019-04-15 | 2019-05-03 | 2019-04-15 | G | [5 empty] | 2019-06-28 | 2019-06-28 | 2019-09-30 | 2019-06-28 | G | [5 empty] | 2020-02-11 | 2021-02-09 | 2020-02-11 | 2021-02-09 | R | 2020-06-29 |  | 2020-06-29 |  | R |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.071473
2694 | 113483 | #SGR20LP - RT 60 (SEMMES AV) (S) - RESURFACING | 0060 | Primary | Resurfacing | Locally | Richmond | ASHLAND | Richmond | Richmond:Richmond | Local Assistance Division | Michael G Campbell | disabled-Michael.Campbell@vdot.virginia.gov | (804) 998-3960 | Brian J Lokker | Brian.Lokker@VDOT.Virginia.gov | (804) 524-6010 | Kenny Horak | Kenny.Horak@richmondgov.com | (804) 646-4781 | 0 |  | 1 | FY2020 | 206000 | 205979 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 111 days early | G | Project is on budget | 2019-02-01 | 2018-12-19 | 2019-04-26 | 2019-01-29 | G | [5 empty] | 2019-02-01 | 2019-01-30 | 2019-02-14 | 2019-02-12 | G | [25 empty] | 2019-02-13 | 2019-02-14 | 2019-05-10 | 2019-02-14 | G | [5 empty] | 2019-05-14 | 2019-04-17 | 2019-06-11 | 2019-04-17 | G | 2019-08-29 | 2019-05-10 | 2019-08-29 | 2019-05-10 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 0 | 0.10394
2696 | 115296 | #SGR20LP - PRIMARY EXTENSION PAVING FY20 - EAST BROAD STREET | 0007 | Urban | Resurfacing | Locally | Falls Church | FAIRFAX | Northern Virginia | Northern Virginia:Falls Church | Infrastructure Investment/Asset Management Division | Andrew G Beacher | Andrew.Beacher@vdot.virginia.gov | (703) 259-2239 | Rita Hockman | Rita.Hockman@vdot.virginia.gov | (804) 824-7421 | Tara Puzin | tpuzin@fallschurchva.gov | (703) 405-0175 | 0 |  | 1 | FY2020 | 52315 | 52315 | WAITING FINANCIAL CLOSURE | G | Start Delivery milestone finished 51 days early | G | Project is on budget | 2019-07-01 | 2019-07-01 | 2019-09-30 | 2019-08-22 | G | [5 empty] | 2019-10-01 | 2019-09-11 | 2019-10-31 | 2019-09-11 | G | [35 empty] | 2019-09-13 | 2019-09-18 | 2019-10-11 | 2019-09-18 | G | 2019-10-14 | 2019-10-21 | 2019-12-11 | 2019-10-21 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 1 | 1 | 0.26351
2697 | 116328 | #I81CIP SWRO MGMT FEE FOR NEW CMS & CAMERAS FY20-25 | 0081 | Interstate | Safety | VDOT | Roanoke County | SALEM | Salem | Roanoke:Roanoke County | Infrastructure Investment Division | Ricky A Via | Ricky.Via@vdot.virginia.gov | (804) 371-2396 | Timothy L Martin | TimL.Martin@VDOT.Virginia.gov | (540) 375-0113 |  |  |  | 0 |  | 0 | FY2020 | 158748 | 158748 | CONSTRUCTION STARTED | G | Start Delivery milestone finished on-time | G | Project is on budget | [10 empty] | 2019-11-01 | 2019-08-23 | 2020-03-17 | 2019-10-28 | G | [35 empty] | 2019-12-30 | 2019-12-30 | 2020-01-06 | 2020-01-06 | G | 2020-01-07 | 2020-01-07 | 2020-01-13 | 2020-01-13 | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | WORK/TASK ORDER | 1 | 0 | 0.12994
2698 | 117032 | #SGR21VP - PM-6S-21 Asphalt Saluda Res. Primary System | 9999 | Primary | Resurfacing | VDOT | Stafford County | FREDERICKSBURG | Fredericksburg | NonMPO:NonMPO | Infrastructure Investment/Asset Management Division | Jessica Graves | Jessica.Graves@vdot.virginia.gov | (540) 899-4267 | Jessica Graves | Jessica.Graves@vdot.virginia.gov | (540) 899-4267 |  |  |  | 0 |  | 1 | FY2021 | 3479937 | 3479937 | ADVERTISED | G | Solicit Bids milestone finished 84 days early | G | Project is on budget | [10 empty] | 2020-08-03 | 2020-07-10 | 2020-08-14 | 2020-08-31 | R | [35 empty] | 2020-07-14 | 2020-12-15 | 2021-03-09 | 2020-12-15 | G | 2021-05-27 |  | 2021-05-27 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.094884
2699 | 118161 | Downtown - 1st Street, SW Drainage Improvement - Roanoke | 0000 | Urban | Mitigation of Water Pollution Due to Highway Runof | Locally | Roanoke | SALEM | Salem | Roanoke:Roanoke City | Local Assistance Division | Cheryl B Becker | Cheryl.Becker@vdot.virginia.gov | (540) 492-2531 | Cheryl B Becker | Cheryl.Becker@vdot.virginia.gov | (540) 492-2531 | Joseph Arthur | Joseph.Arthur@roanokeva.gov | (540) 853-5901 | 0 |  | 0 | FY2028 | 100000 | 100000 | NO DATES SET YET | G | Agreement with Locality milestone is 1422 days ahead of the expected completion date | G | Project is on budget | 2024-08-30 |  | 2025-01-13 |  | G | 2025-01-14 |  | 2025-02-05 |  | G | 2025-08-12 |  | 2025-12-08 |  | G | [25 empty] | 2026-12-03 |  | 2027-05-05 |  | G | [5 empty] | 2027-07-02 |  | 2027-07-30 |  | G | 2027-10-20 |  | 2027-10-20 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.20217
2700 | 118170 | #SGR21LP - Christiansburg FKEY 2437 Roanoke St | 0000 | Urban | Resurfacing | Locally | Christiansburg | CHRISTIANSBURG | Salem | New River Valley:Christiansburg | Infrastructure Investment/Asset Management Division | Adam J Czesnowski | Adam.Czesnowski@vdot.virginia.gov | (540) 541-1216 | Adam J Czesnowski | Adam.Czesnowski@vdot.virginia.gov | (540) 541-1216 | Wayne Nelson | wnelson@christiansburg.org | (540) 382-6120 | 0 |  | 1 | FY2024 | 951911 | 951911 | NO DATES SET YET | G | Agreement with Locality milestone is 50 days ahead of the expected completion date | G | Project is on budget | 2020-12-01 |  | 2021-04-12 |  | G | 2021-04-13 |  | 2021-05-03 |  | G | 2021-11-08 |  | 2022-03-09 |  | G | [25 empty] | 2023-03-06 |  | 2023-08-01 |  | G | [5 empty] | 2023-09-28 |  | 2023-10-26 |  | G | 2024-01-23 |  | 2024-01-23 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 0 | 0.060189
2701 | 118261 | #SGR21LP - RTE 250 BYPASS EB SGR PAVING | 0250 | Primary | Resurfacing | VDOT | Charlottesville | CHARLOTTESVILLE | Culpeper | Charlottesville:Charlottesville | Infrastructure Investment Division | David S Pearce | David.Pearce@VDOT.Virginia.gov | (540) 829-7513 | Donald R Schoch | Donald.Schoch@vdot.virginia.gov | (540) 829-7500 |  |  |  | 0 |  | 1 | FY2021 | 374644 | 374644 | ADVERTISED | G | Solicit Bids milestone finished 56 days early | G | Project is on budget | [10 empty] | 2021-03-05 | 2021-01-22 | 2021-03-18 | 2021-01-22 | G | [35 empty] | 2021-03-09 | 2021-02-09 | 2021-04-06 | 2021-02-09 | G | 2021-06-24 |  | 2021-06-24 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | RAAP CONTRACT | 0 | 0 | 0.12689
2702 | 118238 | COLUMBIA PIKE COMPLETE STREETS - PHASE I |  | Enhancement | Facilities for Pedestrians and Bicycles | Locally | Fairfax County | FAIRFAX | Northern Virginia | Northern Virginia:Fairfax County | Local Assistance Division | Andrew G Beacher | Andrew.Beacher@vdot.virginia.gov | (703) 259-2239 | Susie X Lue | Susie.Lue@vdot.virginia.gov | (703) 259-2918 | Chris Wells | chris.wells@fairfaxcounty.gov | (703) 877-5772 | 0 |  | 0 | FY2025 | 975000 | 975000 | NO DATES SET YET | G | Agreement with Locality milestone is 107 days ahead of the expected completion date | G | Project is on budget | 2021-02-01 | 2020-12-17 | 2021-06-08 |  | G | 2021-06-09 |  | 2021-06-29 |  | G | 2021-07-29 |  | 2021-11-22 |  | G | [10 empty] | 2023-03-20 |  | 2023-04-21 |  | G | [5 empty] | 2023-04-24 |  | 2023-09-20 |  | G | 2023-12-14 |  | 2024-05-15 |  | G | [5 empty] | 2023-12-28 |  | 2024-06-17 |  | G | 2024-09-05 |  | 2025-02-13 |  | G |  | 2021-02-21 11:00 | 2021-02-21 06:04 | NON VDOT | 0 | 1 | 0.25605